W-5806D | HIGHWAY | NC 27, SR 1581 | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | RIGHT-OF-WAY | 100000
W-5806D | HIGHWAY | NC 27, SR 1581 | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 586000 | FY 2023: 580000
W-5806E | HIGHWAY | NC 41 (MARTIN LUTHER KING JR DRIVE) | NC 41 (MARTIN LUTHER KING JR DRIVE) AT NC 72 (WEST SECOND STREET) AND SR 1599 (MARTIN LUTHER KING JR DRIVE). CONSTRUCT SIGNALIZED PEDESTRIAN CROSSINGS. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 315000 | FY 2023: 312000
W-5807A | HIGHWAY | US 220 EASTBOUND | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | HSIP | RIGHT-OF-WAY | 150000 | FY 2023: 150000
W-5807A | HIGHWAY | US 220 EASTBOUND | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | HSIP | CONSTRUCTION | 280000 | FY 2023: 3000; FY 2024: 277000
W-5807B | HIGHWAY | SR 1301 (BOONE STATION DRIVE) | SR 1301 (ST. MARKS CHURCH ROAD) / JAVA LANE AND GLIDWELL DRIVE / TIKI LANE IN BURLINGTON. INSTALL PEDESTRIAN SIGNALS AND CURB RAMPS, AND REVISE PAVEMENT MARKINGS. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | HSIP | CONSTRUCTION | 75000 | FY 2023: 75000
W-5808B | HIGHWAY | US 421 | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A REDUCED CONFLICT INTERSECTION. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 100000
W-5808B | HIGHWAY | US 421 | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A REDUCED CONFLICT INTERSECTION. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 736000 | FY 2024: 334000; FY 2025: 402000
W-5808C | HIGHWAY | SR 2055 (NORTH POPLAR STREET) | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | 8 | Triangle Area RPO | UNDER CONSTRUCTION. | DIVISION 8 |  | HSIP | RIGHT-OF-WAY | 2000
W-5808C | HIGHWAY | SR 2055 (NORTH POPLAR STREET) | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | 8 | Triangle Area RPO | UNDER CONSTRUCTION. | DIVISION 8 |  | HSIP | CONSTRUCTION | 15000
W-5809A | HIGHWAY | NC 109 | DENTON NORTHERN MUNICIPAL BOUNDARY TO SR 2067 (LAMBETH ROAD), AND SR 1798 (OLD GREENSBORO ROAD) / SR 1756 (WEST LEXINGTON AVENUE EXTENSION) TO SR 1711 (GUMTREE ROAD). INSTALL RUMBLE STRIPS AND LONG-LIFE PAVEMENT MARKINGS. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | REGION D |  | HSIP | CONSTRUCTION | 1100000
W-5813A | HIGHWAY | US 25 | US 25 (MCDOWELL STREET) AT DOCTOR'S DRIVE/ASHEVILLE HIGH SCHOOL ENTRANCE. INSTALL PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 64000
W-5813B | HIGHWAY | VARIOUS | VARIOUS SR LOCATIONS. INSTALL LONG LIFE PAVEMENT MARKINGS. | 13 | Foothills RPO, Greater Hickory MPO, High Country RPO | UNDER CONSTRUCTION. | DIVISION 13 |  | HSIP | CONSTRUCTION | 1600000 | FY 2023: 1584000
W-5813C | HIGHWAY | SR 1332 | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 2000
W-5813C | HIGHWAY | SR 1332 | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | HSIP | CONSTRUCTION | 95000 | FY 2023: 95000
W-5813D | HIGHWAY | US 25 | ALL SOULS CRESCENT AND US 25 ALT (LODGE STREET) INTERSECTIONS. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | 13 | French Broad River MPO |  | REGION G |  | HSIP | CONSTRUCTION | 96000 | FY 2023: 1000; FY 2024: 95000
W-5813E | HIGHWAY | US 19-23-74 ALT | US 19-23-74 ALT (PATTON AVENUE) AT US 19-23 BUS (HAYWOOD ROAD)/SR 1319 (JOHNSTON ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 115000 | FY 2023: 115000
W-5813F | HIGHWAY | US 19-23-74 ALT | US 19-23-74 ALT (SMOKEY PARK HIGHWAY) AT OLD HAYWOOD ROAD. INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 70000 | FY 2023: 70000
W-5813G | HIGHWAY | US 70; US 74 ALT | (1) US 70 (TUNNEL ROAD) AT OLD CHUNNS COVE ROAD, (2) US 74 ALT (S. TUNNEL ROAD) AT MAIN MALL ENTRANCE (EAST LEG), (3) US 74 ALT (S. TUNNEL ROAD) AT LOWER MALL ENTRANCE. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 135000 | FY 2023: 134000
W-5813H | HIGHWAY | NC 197 | NC 197 FROM SR 1338 TO THE MITCHELL COUNTY LINE, NEAR GREEN MOUNTAIN. INSTALL SHOULDER GUARDRAIL. | 13 | High Country RPO | COMPLETE | REGION G |  | HSIP | CONSTRUCTION | 474000
W-5813I | HIGHWAY | SR 2806 | SR 2806 (GARREN CREEK ROAD) FROM SR 2815 TO SR 2786, NEAR FAIRVIEW. INSTALL SHOULDER GUARDRAIL. | 13 | Land-of-Sky RPO | COMPLETE | DIVISION 13 |  | HSIP | CONSTRUCTION | 460000
W-5813J | HIGHWAY | US 221 | (1) US 221 IN RUTHERFORD COUNTY FROM US 64 TO THE MCDOWELL COUNTY LINE. (2) US 221 IN MCDOWELL COUNTY ROM THE RUTHERFOD COUNTY LINE TO I-40. INSTALL SINUSIODAL CENTERLINE RUMBLESTRIPES WITH LONG-LIFE PAVEMENT MARKINGS. | 13 | Foothills RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 501000 | FY 2023: 496000
W-5814A | HIGHWAY | US 276 | CONSTRUCT LEFT TURN LANE 0.3 MILES SOUTH OF SR 1326 (BOB BOYD ROAD). | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 380000
W-5814B | HIGHWAY | US 74 WB | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | 14 | Foothills RPO | COMPLETE | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 199000
W-5814C | HIGHWAY | US 74 EB | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | 14 | Foothills RPO | COMPLETE | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 179000
W-9999DIV | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | CONSTRUCTION | 45163000 | FY 2023: 4903000
W-9999REG | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | CONSTRUCTION | 55935000 | FY 2023: 15750000
W-9999SW | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 74580000 | FY 2023: 21000000
X-0002 | HIGHWAY | I-295 (FAYETTEVILLE OUTER LOOP) | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO I-95. FREEWAY ON NEW LOCATION WITH STRUCTURE OVER THE CAPE FEAR RIVER. | 6 | Fayetteville Area MPO | [5 empty] | 320483000
Y-4805F | RAIL | FAYETTEVILLE STREET (SR 2513) | FAYETTEVILLE STREET AND THE CAROLINA COASTAL RAILWAY TRACKS CROSSING CLOSURE IN KNIGHTDALE. | 5 | Capital Area MPO |  | DIVISION 5 |  | RR | CONSTRUCTION | 1600000 | FY 2025: 1600000
Y-4807B | RAIL | LOWDERMILK STREET SYKES AVENUE | PINE STREET CROSSING CLOSURE AND LOWDERMILK STREET / SYKES AVENUE REALIGNMENT IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | RR | CONSTRUCTION | 5000000 | FY 2023: 50000; FY 2024: 4477000; FY 2025: 473000
Y-4807B | RAIL | LOWDERMILK STREET SYKES AVENUE | PINE STREET CROSSING CLOSURE AND LOWDERMILK STREET / SYKES AVENUE REALIGNMENT IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  |  |  | 2430000
Y-4810K | RAIL | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | STATEWIDE MOBILITY |  |  |  | 2800000
Y-4810K | RAIL | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 450000 | FY 2023: 111000; FY 2024: 233000; FY 2025: 106000
Y-4810K | RAIL | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 18720000 | FY 2023: 4632000; FY 2024: 9675000; FY 2025: 4413000
Y-5500 | RAIL | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 1944000
Y-5500 | RAIL | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  | RR | CONSTRUCTION | 7560000 | FY 2023: 2500000
Y-5500 | RAIL | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  | RR | RIGHT-OF-WAY | 1500000 | FY 2023: 500000
Z-5400 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 28841000
Z-5700 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 16738000
Z-5800 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | CONSTRUCTION | 3280000
Z-5800 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | RIGHT-OF-WAY | 500000
Z-9999 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS - UNPROGRAMMED BALANCE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | RIGHT-OF-WAY | 500000 | FY 2023: 500000
Z-9999 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS - UNPROGRAMMED BALANCE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | CONSTRUCTION | 3000000 | FY 2023: 3000000

## Fund Sources
Fund Source | Fund Type | Description | Subject to STI
3037 | Federal | Job Assistance and Reverse Commute | No
5303 | Federal | Metropolitan Planning (FMPL) | No
5305 | Federal | FTA Discretionary Grant Funds | No
5307 | Federal | Urbanized Area Formula Program (FUZ) | No
5309 | Federal | Capital Program - Bus Earmark (FBUS) | No
5310 | Federal | Elderly and Persons with Disability (FEPD) | No
5311 | Federal | Non Urbanised Area Formula Program (FNU) | No
5312 | Federal | FUZ 5312 | No
5316 | Federal | Job Assistance And Reverse Commute (JARC) | No
5317 | Federal | New Freedom Program | No
5337 | Federal | Urbanized Area Formula Program (FUZ) | No
5339 | Federal | Capital Program - Bus Earmark (FBUS) | No
5339(b) | Federal | Capital Program - Bus Earmark (FBUS) - Discretionary Grant | No
ADHS | Federal | Appalachian Development Highway System | No
ADHSL | Federal | Appalachian Development Highway System (Local Access Roads) | No
ADTAP | Federal | Appalachian Development portion of 5311 - Non Urbanised Area Formula Program (FNU) | No
ARP | Federal | American Rescue Plan | No
BA | State | Bonus Allocation | No
BFP | Federal | Federal Bridge Improvement Program - Formula | Yes
BFPOFF | Federal | Federal Bridge Improvement Program - Formula (Off System) | Yes
BG | Federal | Surface Transportation Block Grant Program (Uncategorized) | Yes
BG5200 | Federal | Surface Transportation Block Grant Program (5K - 200K) | Yes
BGANY | Federal | Surface Transportation Block Grant Program (Any Area) | Yes
BGBA | Federal | Surface Transportation Block Grant Program (Bonus Allocation) | No
BGDA | Federal | Surface Transportation Block Grant Program (Direct Attributable) | Yes
BGDACV | Federal | COVID Relief Funds | Yes
BGIM | Federal | Surface Transportation Block Grant Program (Interstate Maintenance) | Yes
BGLT5 | Federal | Surface Transportation Block Grant Program (Less than 5K) | Yes
BGOFF | Federal | Surface Transportation Block Grant Program (Off System) | Yes
BOND R | Other | Revenue Bond | No
BRGI | Federal | Bridge Inspection | Yes
CARES | Federal | CARES Act Funding | No
CMAQ | Federal | Congestion Mitigation | No
CRP550 | Federal | Carbon Reduction Program - (5K - 50K) | No
CRPANY | Federal | Carbon Reduction Program - Any Area | No
CRPDA | Federal | Carbon Reduction Program - Direct Attributable (All MPOs) | No
CRPLT5 | Federal | Carbon Reduction Program - (Less than 5K) | No
DOD | Federal | Department of Defense | No
DP | Federal | Discretionary or Demonstration | No
ER | Federal | Emergency Relief | No
ERFO | Federal | Emergency Relief for Federally Owned Roads | No
FED | Federal | Unidentified Federal Funding | No
FEDT | Federal | Undesignated Federal Transit Funding | No
FF | Federal | FEDERAL FERRY | Yes
FLAP | Federal | Federal Lands Access Program (Park Roads) | No
FLPF | Federal | Federal Lands Program (Forest Roads) | No
FLTP | Federal | Federal Lands Transportation Program | No
FMOD | Federal | Fixed Guideway Modifications | Yes
FSPR | Federal | State Planning and Research | No
FTTP | Federal | Federal Tribal Transportation Program | No
FUZ | Federal | Capital Program - Bus Earmark (5309) | No
HF | State | Highway Fund | No
HFB | State | Highway Fund Bridge Replacement Program | Yes
HIB | Federal | Highway Infrastructure Bridge Replacement | Yes
HP | Federal | High Priority | Yes
HRRR | Federal | High Risk Rural Roads | Yes
HSIP | Federal | HIGHWAY SAFETY IMPROVEMENT PROGRAM | Yes
L | Other | Local | No
NEVI | Federal | National Electric Vehicle Infrasructure Program Funds | Yes
NHFP | Federal | National Highway Freight Program | Yes
NHP | Federal | National Highway Performance Program | Yes
NHPB | Federal | National Highway Performance Program(Bridge) | Yes
NHPBA | Federal | National Highway Performance Program(Bonus Allocation) | No
NHPIM | Federal | National Highway Performance Program (Interstate Maintenance) | Yes
NRT | Federal | National Recreation Trails | Yes
O | Other | Local, Non Federal or State Funds | No
PROTCT | Federal | PROTECT Formula Program (Promoting Resilient Operations…) | Yes
RR | Federal | Rail-Highway Safety | Yes
RTAP | Federal | Rural Transit Assistance Program | No
S | State | State | No
S(M) | State | State Match for STP-DA or Garvee Projects | Yes
S(M)BA | State | State Match for Bonus Allocation Projects using Federal funds | No
SBG | Federal | Scenic Byway Grant | Yes
SF | State | Ferries | Yes
SMAP | State | Operating Assistance and State Maintenance | No
SRTS | Federal | Safe Roads to School | Yes
SSO | Federal | Safety System Oversight | No
STHSR | Federal | Stimulus High Speed Rail | No
T | State | Highway Trust Funds | Yes
T(DA) | State | Highway Trust Funds - Fund Swaps for DA Projects | Yes
TA | Federal | Transportation Alternatives Program (Uncategorized) | Yes
TA5200 | Federal | Transportation Alternatives Program (5K - 200K) | Yes
TAANY | Federal | Transportation Alternatives Program (Any Area) | Yes
TADA | Federal | Transportation Alternatives Program (Direct Attributable) | Yes
TALT5 | Federal | Transportation Alternatives Program (Less than 5K) | Yes
TAP | Federal | Transportation Alternatives Program (Uncategorized) | Yes
TAPDA | Federal | Transportation Alternatives Program (Direct Attributable) | Yes