## 2024-2033 STIP
2024-2033 STATE TRANSPORTATION IMPROVEMENT PROGRAM
NOTES: AMOUNTS SHOWN ARE PROJECT ESTIMATE AMOUNTS REMAINING. ANY AMOUNTS PROGRAMMED FOR ACTIVITIES OTHER THAN RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION ARE INCLUDED UNDER "OTHER ACTIVITIES".
BASIC PROJECT INFORMATION | [10 empty] | FISCAL YEAR PROJECT PHASE SCHEDULED TO START
COUNTY(S) | ROUTE/CITY | RESPONSIBLE AGENCY | DESCRIPTION | MODE | FUNDING PROGRAM | DIVISION(S) | MPOs/RPOs | PROJECT ID | STI CATEGORY FUNDED | FUNDING SOURCE (SEE FUNDING SOURCES TAB FOR MORE INFO) | RIGHT-OF-WAY PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR RIGHT-OF-WAY | UTILITIES PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR UTILITIES | CONSTRUCTION PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR CONSTRUCTION | PROJECTED SCHEDULE FOR OTHER ACTIVITIES | TOTAL REMAINING FUNDS FOR OTHER ACTIVITIES | TOTAL REMAINING FUNDS NEEDED | COMMENT
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN THE RUNWAY 24 APPROACH. | AVIATION | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | AV-5737 | DIVISION 7 | L, T | 2027 | 1200000 | [6 empty] | 1200000
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | CONSTRUCT 100 FT PAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. | AVIATION | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | AV-5851 | DIVISION 7 | T |  |  |  |  | 2027 | 2080000 |  |  | 2080000
ALAMANCE | US 70 (NORTH CHURCH STREET) | BURLINGTON | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | EB-5879 | DIVISION 7 | L, TA5200 | 2024 | 28000 |  |  | 2024 | 66000 | 2022 | 16000 | 110000
ALAMANCE | US 70 (NORTH CHURCH STREET) | BURLINGTON | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | EB-5885 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 120000 |  |  | 120000
ALAMANCE | LEE AVENUE | ELON | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | EB-5988 | DIVISION 7 | L, TA5200 | 2025 | 5000 |  |  | 2026 | 272000 | 2024 | 30000 | 307000
ALAMANCE | SR 1212 (POND ROAD) | NCDOT | REPLACE BRIDGE 000170 OVER PRONG OF ALAMANCE CREEK IN ALAMANCE. | HIGHWAY | BRIDGES | 7 | BURLINGTON-GRAHAM MPO | B-5347 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
ALAMANCE | NC 87 | NCDOT | NC 87 AT I-40 EASTBOUND ON-RAMP. INSTALL PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | SAFETY | 7 | BURLINGTON-GRAHAM MPO | HS-2007F | REGION D | HSIP |  |  |  |  | 2023 | 87000 |  |  | 87000
ALAMANCE | I-40 /I-85 | NCDOT | EAST OF GUILFORD COUNTY LINE TO EAST OF NC 49. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | BURLINGTON-GRAHAM MPO | I-5309 | STATEWIDE MOBILITY | [10 empty] | CONSTRUCTION COMPLETED - PROJECT COST INCLUDES I-5836 CONSTRUCTION
ALAMANCE | I-40 / I-85 | NCDOT | SR 1007 (MEBANE-OAKS ROAD) IN MEBANE. INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | I-5711 | STATEWIDE MOBILITY | NHP, S(M) |  |  |  |  | 2020 | 13133000 |  |  | 13133000 | UNDER CONSTRUCTION; GARVEE BONDS: $2M FOR CONSTRUCTION - PAYBCK 2021-2035
ALAMANCE | I-40 / I-85 | NCDOT | 0.2 MILE EAST OF NC 49 TO 0.2 MILE EAST OF NC 54 IN GRAHAM. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | BURLINGTON-GRAHAM MPO | I-5836 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION FUNDED UNDER I-5309
ALAMANCE | I-40 / I-85 | NCDOT | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | I-6009 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 |  |  | 1800000
ALAMANCE | I-40 / I-85 | NCDOT | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | I-6059 | DIVISION 7 | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7100000 |  |  | 7900000
ALAMANCE | NC 119 | NCDOT | NC 119 RELOCATION, I-85 TO SOUTH OF SR 1918 (MRS. WHITE ROAD) IN MEBANE. FOUR-TO-SIX-LANE FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-3109
ALAMANCE | NC 119 | NCDOT | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-3109A | REGION D | T |  |  |  |  | 2019 | 42967000 | 2021 | 360000 | 43327000 | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NC 119 | NCDOT | NC 119 RELOCATION, NORTH OF SR 1921 (MEBANE ROGERS ROAD) TO SOUTH OF SR 1918 (MRS. WHITE ROAD) | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-3109B | REGION D | T |  |  |  |  | 2021 | 5835000 |  |  | 5835000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.533 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NEW ROUTE | NCDOT | NEW ROUTE, US 70 TO NC 100 IN ELON. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | HIGHWAY | PRE-STI (HISTORIC) | 7 | BURLINGTON-GRAHAM MPO | U-3110 | [11 empty] | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
ALAMANCE | NEW ROUTE | NCDOT | US 70 TO NORTH OF SR 1309 (WESTBROOK AVENUE) | HIGHWAY | PRE-STI (HISTORIC) | 7 | BURLINGTON-GRAHAM MPO | U-3110A | [11 empty] | COMPLETE
ALAMANCE | NEW ROUTE | NCDOT | IMPROVEMENTS ON SR 1311 (COOK ROAD), SR 1309 (WESTBROOK AVENUE) TO NC 100, PART ON NEW LOCATION | HIGHWAY | PRE-STI (HISTORIC) | 7 | BURLINGTON-GRAHAM MPO | U-3110B | PRE-STI (TRANSITION) | BG5200 |  |  |  |  | 2011 | 3444000 |  |  | 3444000 | COMPLETE; GARVEE BOND FUNDING $10.5 MILLION; PAYBACK FY 2011 - FY 2022
ALAMANCE | US 70 (NORTH CHURCH STREET) | NCDOT | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-5843 | DIVISION 7 | T |  |  |  |  | 2019 | 2167000 | 2021 | 810000 | 2977000 | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NC 62 | NCDOT | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-5844 | DIVISION 7 | T | 2024 | 13300000 | 2024 | 3400000 | 2025 | 8700000 |  |  | 25400000
ALAMANCE | US 70 (SOUTH CHURCH STREET) | NCDOT | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6009 | REGION D | T | 2028 | 26600000 | 2028 | 5100000 | 2030 | 11700000 |  |  | 43400000
ALAMANCE | US 70 (SOUTH CHURCH STREET) | NCDOT | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6010 | REGION D | T | 2020 | 6000000 |  |  | 2022 | 16100000 |  |  | 22100000 | UNDER CONSTRUCTION
ALAMANCE | US 70 (SOUTH CHURCH STREET) | NCDOT | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6011 | REGION D | T | 2022 | 3000000 | 2022 | 630000 | 2025 | 2400000 |  |  | 6030000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | NC 119 | NCDOT | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6013 | DIVISION 7 | T | 2023 | 5500000 | 2023 | 900000 | 2024 | 7300000 |  |  | 13700000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | SR 1716 (GRAHAM- HOPEDALE ROAD) | NCDOT | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6014 | DIVISION 7 | T | 2023 | 1500000 | 2023 | 1200000 | 2025 | 10300000 |  |  | 13000000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | VARIOUS | NCDOT | UPGRADE BURLINGTON-GRAHAM SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6015 | DIVISION 7 | T |  |  |  |  | 2021 | 6125000 |  |  | 6125000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6017 | DIVISION 7 | T | 2022 | 2000000 | 2022 | 550000 | 2024 | 2100000 |  |  | 4650000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | NC 62 (ALAMANCE ROAD) | NCDOT | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6114 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 |  |  | 1800000
ALAMANCE | NC 54 | NCDOT | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) TO SOUTH OF SR 2107 (WHITTEMORE ROAD) IN GRAHAM. IMPROVE SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTION, UPGRADE RAMP INTERSECTIONS AT I-40 / I-85, IMPROVE SR 2106 (WOODY ROAD) INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6115 | REGION D
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6115A | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 |  |  | 5100000
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6115B | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8001000 |  |  | 9501000
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6115C | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 250000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 |  |  | 6150000
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6115D | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 490000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 120000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 |  |  | 2710000
ALAMANCE | NC 54 (WEST HARDEN STREET) | NCDOT | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6131 | REGION D | BG50200 | 2025 | 4100000 | 2025 | 1100000 | 2026 | 3500000 |  |  | 8700000
ALAMANCE | SR 1716 (NORTH MAIN STREET) | NCDOT | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6132 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 |  |  | 2200000
ALAMANCE | NC 87 (WEBB AVENUE) | NCDOT | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6182 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 180000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 |  |  | 2480000
ALAMANCE | NC 49 (ROXBORO ROAD) | NCDOT | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6183 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 |  |  | 4500000
ALAMANCE | NC 54 (CHAPEL HILL ROAD) | NCDOT | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6184 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8400000 |  |  | 14600000
ALAMANCE | SR 1455 (EAST HAGGARD AVENUE) | NCDOT | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | BURLINGTON-GRAHAM MPO | U-6214 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3401000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5600000 |  |  | 11401000
ALAMANCE | SR 1301 (BOONE STATION DRIVE) | NCDOT | SR 1301 (ST. MARKS CHURCH ROAD) / JAVA LANE AND GLIDWELL DRIVE / TIKI LANE IN BURLINGTON. INSTALL PEDESTRIAN SIGNALS AND CURB RAMPS, AND REVISE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 7 | BURLINGTON-GRAHAM MPO | W-5807B | DIVISION 7 | HSIP |  |  |  |  | 2023 | 75000 |  |  | 75000
ALAMANCE | LINK TRANSIT | LINK TRANSIT | IMPROVEMENTS, BUS SHELTERS, CONSTRUCTION, ENGINEERING AND DESIGN. | PUBLIC TRANSIT |  | 7 | BURLINGTON-GRAHAM MPO | TA-6322 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 1081000 | 1081000
ALAMANCE | LINK TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. | PUBLIC TRANSIT |  | 7 | BURLINGTON-GRAHAM MPO | TA-6733 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 8170000 | 8170000 | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | BURLINGTON | BURLINGTON | CAPITAL FOR PEDESTRIAN IMPROVEMENTS FOR FIXED ROUTR SERVICES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | BURLINGTON-GRAHAM MPO | TD-6322 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 60000 | 60000 | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | ROUTINE CAPITAL/PREVENTATIVE, MAINTENANCE/PASSENGER AMENITITES/MOBILITY MANAGEMENT | PUBLIC TRANSIT |  | 7 | BURLINGTON-GRAHAM MPO | TG-0012 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 750000 | 750000
ALAMANCE | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PASSENGER AMENITIES, PARTS, EQUIPMENT, PREVENTIVE MAINTENANCE, AND CAPITAL COST OF CONTRACTING. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7 | BURLINGTON-GRAHAM MPO | TG-6137B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 750000 | 750000
ALAMANCE | ALAMANACE COUNTY TRANSPORTATION | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7 | BURLINGTON-GRAHAM MPO | TG-6811B | PUBLIC TRANSIT | 5307, FED, L | [6 empty] | 2024 | 250000 | 250000
ALAMANCE | BURLINGTON | BURLINGTON | ADA SERVICES | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | BURLINGTON-GRAHAM MPO | TG-6812A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 211000 | 211000 | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | ALAMANACE COUNTY TRANSPORTATION | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | BURLINGTON-GRAHAM MPO | TK-6103 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1424000 | 1424000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | LINK TRANSIT | LINK TRANSIT | CAPITAL IMPROVEMENTS FOR TRANSIT VEHICLES. | PUBLIC TRANSIT |  | 7 | BURLINGTON-GRAHAM MPO | TL-0029 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 1550000 | 1550000
ALAMANCE | LINK TRANSIT | LINK TRANSIT | PREVENTATIVE MAINTENANCE. | PUBLIC TRANSIT |  | 7 | BURLINGTON-GRAHAM MPO | TM-0046 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 3072000 | 3072000
ALAMANCE | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | BURLINGTON-GRAHAM MPO | TO-5134 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 9842000 | 9842000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | ALAMANACE COUNTY TRANSPORTATION | ALAMANACE COUNTY TRANSPORTATION | OPERATING FOR ALAMANCE COUNTY TRANSPORTATION IN THE BURLINGTON URBAN AREA - THROUGH NCDOT | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | BURLINGTON-GRAHAM MPO | TO-5214 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 9070000 | 9070000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | LINK TRANSIT | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | BURLINGTON-GRAHAM MPO | TO-6170 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 9840000 | 9840000 | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO.
ALAMANCE | LINK TRANSIT | LINK TRANSIT | ADA SERVICE. | PUBLIC TRANSIT |  | 7 | BURLINGTON-GRAHAM MPO | TO-6812A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 1356000 | 1356000
ALAMANCE | BURLINGTON | BURLINGTON | PLANNING FOR FIXED ROUTE SERVICE EXPANSION | PUBLIC TRANSIT | PLANNING | 7 | BURLINGTON-GRAHAM MPO | TP-5161 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 5000 | 5000 | ADD PROJECT TP-5161 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | BURLINGTON | BURLINGTON | PLANNING FOR PLANNING FACILITY FEASIBILITY STUDY | PUBLIC TRANSIT | PLANNING | 7 | BURLINGTON-GRAHAM MPO | TP-5162 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 95000 | 95000 | ADD PROJECT TP-5162 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | LINK TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT SYSTEM MANAGEMENT. | PUBLIC TRANSIT |  | 7 | BURLINGTON-GRAHAM MPO | TU-0016 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 1345000 | 1345000
ALAMANCE | PIEDMONT CORRIDOR | PIEDMONT CORRIDOR | GRAHAM TO HAW RIVER. SIDING AND CURVE REALIGNMENT. | RAIL | PRE-STI (HISTORIC) | 7 | BURLINGTON-GRAHAM MPO | P-5205 | PRE-STI (TRANSITION) | [10 empty] | COMPLETED
ALAMANCE, CASWELL, GUILFOR D, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5707REG | REGION D | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | BO-2407 | DIVISION 7 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. | HIGHWAY | SAFETY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | HS-2007
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 7 | BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, PIEDMONT TRIAD RPO, TRIANGLE AREA RPO | HS-2007C | DIVISION 7 | HSIP |  |  |  |  | 2021 | 1717000 |  |  | 1717000 | UNDER CONSTRUCTION
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. | HIGHWAY | SAFETY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | HS-2407 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | R-5787 | DIVISION 7 | S, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | DIVISION 7 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5207 | [11 empty] | COMPLETED
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. | HIGHWAY | SAFETY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5707 | [11 empty] | IN PROGRESS
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5707DIV | DIVISION 7 | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5707SW | STATEWIDE MOBILITY | HSIP | 2020 | 120000 |  |  | 2020 | 740000 |  |  | 860000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. | HIGHWAY | SAFETY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5807
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 7. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | RC-2007 | DIVISION 7 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | RX-2007 | DIVISION 7
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | RX-2407 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALAMANCE, GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | BURLINGTON-GRAHAM MPO | TO-5136 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 3268000 | 3268000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE, GUILFORD, ORANGE | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE BURLINGON PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 7 | BURLINGTON-GRAHAM MPO | HL-0091 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 1708000 |  |  | 1708000
ALAMANCE, ORANGE | I-40 / I-85 | NCDOT | EAST OF NC 54 IN GRAHAM IN ALAMANCE COUNTY TO WEST OF SR 1114 (BUCKHORN ROAD) IN ORANGE COUINTY. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | BURLINGTON-GRAHAM MPO | I-5954 | STATEWIDE MOBILITY | [10 empty] | COMPLETED
ALEXANDER | SR 1348 | NCDOT | REPLACE BRIDGE 10291 OVER DUCK CREEK. | HIGHWAY | BRIDGES | 12 | GREATER HICKORY MPO | BR-0201 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1050000 |  |  | 1050000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.88
ALEXANDER | NC 16 | NCDOT | INTERSECTION OF NC 16 AND SR 1609 (COUNTY HOME ROAD). CONSTRUCT INTERSECTION IMPROVMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | R-5762 | DIVISION 12 | T | 2022 | 120000 |  |  | 2023 | 635000 |  |  | 755000 | UNDER CONSTRUCTION.
ALEXANDER | ALEXANDER COUNTY | NCDOT | CONSTRUCT ACCESS ROAD INTO ALEXANDER INDUSTRIAL PARK. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 12 | GREATER HICKORY MPO | R-5870 | EXEMPT | ADHSL, T |  |  |  |  | 2021 | 1675000 |  |  | 1675000 | COMPLETE - ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING.
ALEXANDER | US 64 | NCDOT | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-6041 | DIVISION 12 | T | 2024 | 200000 | 2024 | 400000 | 2025 | 1450000 |  |  | 2050000
ALEXANDER | NC 16 | NCDOT | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-6151 | NOT FUNDED | T | NOT FUNDED | 17300000 | NOT FUNDED | 3500000 | NOT FUNDED | 55000000 |  |  | 75800000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | REPLACEMENT BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TA-4927 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 360000 | 360000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TA-4928 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 362000 | 362000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | REPLACEMENT VAN | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TA-4929 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1893000 | 1893000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REPLACEMENT VAN | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TA-6501 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 184000 | 184000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TA-6507 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 920000 | 920000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TG-4774 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 200000 | 200000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TG-4774A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TG-4774B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 444000 | 444000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - SERVICE VEHICLE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TG-6142A | PUBLIC TRANSIT | 5311, L | [6 empty] | 2021 | 39000 | 39000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TG-6159 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 80000 | 80000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TK-5181 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1420000 | 1420000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE - NON-URBAN | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TM-6108 | PUBLIC TRANSIT | 5316, L | [6 empty] | 2020 | 736000 | 736000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE - SMALL-URBAN | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TN-6109 | PUBLIC TRANSIT | 5317, L | [6 empty] | 2020 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 11, 12, 13 | GREATER HICKORY MPO | TO-4733 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 4954000 | 4954000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 11, 12, 13 | GREATER HICKORY MPO | TO-6109 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 784000 | 784000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | PLANNING ASSISTANCE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TP-4733A | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 210000 | 210000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PLANNING ASSISTANCE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TP-4733B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 327000 | 327000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TP-5106 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 401000 | 401000 | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | PREVENTIVE MAINTENANCE - PARATRANSIT | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TQ-6503 | PUBLIC TRANSIT | 5310, L, S | [6 empty] | 2020 | 38000 | 38000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ELDERLY AND DISABLED PERSONS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11, 12, 13 | GREATER HICKORY MPO | TQ-6507 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 1294000 | 1294000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | SAFETY & SECURITY | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11, 12, 13 | GREATER HICKORY MPO | TS-5128 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 24000 | 24000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, CATAWBA | NC 127 | NCDOT | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | R-3603
ALEXANDER, CATAWBA | NC 127 | NCDOT | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | R-3603A | DIVISION 12 | T | 2024 | 26900000 | 2024 | 100000 | 2026 | 55101000 |  |  | 82101000 | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040).
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | BO-2412 | DIVISION 12 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | HS-2012
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | HS-2412 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | R-5792 | DIVISION 12 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5212 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS; SEGMENT J: ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. STATE MATCH TO BE FUNDED WITH SPOT SAFETY FUNDS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5712 | [11 empty] | IN PROGRESS
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5712DIV | DIVISION 12 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5712REG | REGION F | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5712SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5812 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 12. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | RC-2012 | DIVISION 12 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | RX-2012 | DIVISION 12 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | RX-2412 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CABARRUS | I-85 | NCDOT | SOUTH OF SR 2894 (CONCORD MILLS - BRUTON SMITH BOULEVARD) TO NC 73 IN CABARRUS COUNTY. WIDEN TO 8-LANES. | HIGHWAY | PRE-STI (HISTORIC) | 10 | CABARRUS-ROWAN MPO | I-3803B | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2010 | 22592000 |  |  | 22592000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
ALLEGHANY | SR 1422 | NCDOT | REPLACE BRIDGE 20035 OVER GLADE CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | BR-0206 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 750000 |  |  | 750000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.157
ALLEGHANY | SR 1433 | NCDOT | REPLACE BRIDGE 20133 OVER LITTLE RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | BR-0207 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 500000 |  |  | 500000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.159
ALLEGHANY | SR 1433 | NCDOT | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0067 | DIVISION 11 | DP, HFB | 2024 | 140000 |  |  | 2025 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
ALLEGHANY | ALLEGHANY COUNTY | ALLEGHANY COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11 | HIGH COUNTRY RPO | TK-6105 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 620000 | 620000 | FUNDS AUTHORIZED IN PROGRESS
ANSON | SR 1627 (PINKSTON ROAD) | NCDOT | REPLACE BRIDGE OVER WSSB RAILROAD. | HIGHWAY | BRIDGES | 10 | ROCKY RIVER RPO | B-4410 | [11 empty] | UNDER CONSTRUCTION. LOCAL FUNDING PROVIDED BY TOWN OF ANSONVILLE
ANSON | SR 1627 (PINKSTON ROAD) | NCDOT | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. | HIGHWAY | BRIDGES | 10 | ROCKY RIVER RPO | B-4410A | PRE-STI (TRANSITION) | L, T | 2022 | 25000 |  |  | 2023 | 360000 |  |  | 385000 | UNDER CONSTRUCTION.
ANSON | SR 1142 (CITY POND ROAD) | NCDOT | REPLACE BRIDGE 030075 OVER NORTH FORK JONES CREEK. | HIGHWAY | BRIDGES | 10 | ROCKY RIVER RPO | B-5809 | DIVISION 10 | BGOFF | 2020 | 105000 |  |  | 2022 | 1180000 |  |  | 1285000 | UNDER CONSTRUCTION.
ANSON | SR 1634 (GRASSY ISLAND ROAD) | NCDOT | REPLACE BRIDGE 030007 OVER BROWN CREEK. NC FLAP DOT 1634(1). | HIGHWAY | BRIDGES | 10 | ROCKY RIVER RPO | B-5817 | EXEMPT | [10 empty] | STATE MATCHING FUNDS FROM DIVISION 10 17BP FUNDS. COMPLETED.
ANSON | WADESBORO | WADESBORO | REPLACE BRIDGE 030316 ON BURNS STREET OVER LAMPLEY CREEK. | HIGHWAY | MUNICIPAL BRIDGE | 10 | ROCKY RIVER RPO | B-5988 | DIVISION 10 | BGOFF, L | 2021 | 169000 |  |  | 2022 | 1211000 |  |  | 1380000 | UNDER CONSTRUCTION. PLANNING/DESIGN BY TOWN OF WADESBORO.
ANSON | SR 1812 (DIGGS ROAD) | NCDOT | REPLACE BRIDGE 030039 OVER JONES CREEK. | HIGHWAY | BRIDGES | 10 | ROCKY RIVER RPO | B-6048 | DIVISION 10 | BGOFF | 2023 | 190000 |  |  | 2027 | 1900000 |  |  | 2090000 | RIGHT-OF-WAY IN PROGRESS.
ANSON | US 74 (ANDREW JACKSON HIGHWAY) | NCDOT | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | HIGHWAY | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | R-5798 | STATEWIDE MOBILITY | BGANY | 2025 | 14800000 | 2025 | 4900000 | 2029 | 21300000 |  |  | 41000000
ANSON | US 74 | NCDOT | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | R-5871 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10800000 |  |  | 25100000
ANSON | NEW ROUTE - WADESBORO BYPASS | NCDOT | US 74 WEST OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | R-5878
ANSON | NEW ROUTE - WADESBORO BYPASS | NCDOT | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | R-5878A | NOT FUNDED | NHP | NOT FUNDED | 4000000 | NOT FUNDED | 600000 | NOT FUNDED | 104300000 |  |  | 108900000
ANSON | NEW ROUTE - WADESBORO BYPASS | NCDOT | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | R-5878B | REGION E | T | 2028 | 32400000 | 2028 | 3200000 | 2030 | 134100000 |  |  | 169700000
ANSON | ANSON COUNTY | ANSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 10 | ROCKY RIVER RPO | TK-6106 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 820000 | 820000 | FUNDS AUTHORIZED IN PROGRESS
ANSON | CSX SF LINE | NCDOT | CONSTRUCT SIDING EXTENSION IN POLKTON | RAIL | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | P-5750 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
ANSON | CSX SF LINE | CSXT RR | CONSTRUCT SIDING EXTENSION IN POLKTON. | RAIL | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | P-5750A | REGION E | DP, T | 2024 | 600000 |  |  | 2024 | 13037000 |  |  | 13637000
ANSON | CSX SF LINE | NCDOT | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. | RAIL | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | P-5750B | REGION E | T |  |  |  |  | 2026 | 16380000 |  |  | 16380000
ANSON | SR 1714 (STANBACK FERRY ICE PLANT ROAD) | NCDOT | CSX CROSSING 631750C NEAR WADESBORO. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 10 | ROCKY RIVER RPO | RX-2010B | DIVISION 10 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | BO-2410 | DIVISION 10 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | HS-2010
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | HS-2410 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | R-5790 | DIVISION 10 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5210 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5710 | [11 empty] | STATE MATCH FOR SEGMENTS Y & Z ARE SPOT SAFETY FUNDS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5710DIV | DIVISION 10 | HSIP | 2020 | 410000 |  |  | 2020 | 2025000 |  |  | 2435000 | IN PROGRESS.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5710REG | REGION E | HSIP | 2020 | 540000 |  |  | 2020 | 720000 |  |  | 1260000 | IN PROGRESS.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5710SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5810 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 10. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | RC-2010 | DIVISION 10 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | RX-2010 | DIVISION 10
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | RX-2410 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, ROBESON, RICHMOND, SCOTLAND, UNION | US 74 | NCDOT | EASTERN END OF MONROE BYPASS TO I-95 IN LUMBERTON. INSTALL BROADBAND AND ITS COMPONENTS INCLUDING CONNECTIONS TO SIGNAL SYSTEMS, DMS, AND CCTV. | HIGHWAY | OTHER | 6, 8, 10 | LUMBER RIVER RPO, ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO | HO-0002B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 14216000 |  |  | 14216000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002C. UNDER CONSTRUCTION.
ASHE | ASHE COUNTY AIRPORT (GEV) | ASHE COUNTY AIRPORT (GEV) | CONSTRUCT APRON EXPANSONS. | AVIATION | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | AV-5848 | DIVISION 11 | T |  |  |  |  | 2021 | 2700000 |  |  | 2700000 | UNDER CONSTRUCTION.
ASHE | NORTHWEST DRIVE, AEV LANE | NCDOT | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AMERICAN EMERGENCY VEHICLES LANE FROM NORTHWEST DRIVE TO AMERICAN EMERGENCY VEHICLES FACILITY. WIDEN PAVEMENT AND INSTALL SIGNAL AT NC 88 AND NORTHWEST DRIVE. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 11 | HIGH COUNTRY RPO | HA-0006 | EXEMPT | ADHSL | 2024 | 60000 |  |  | 2025 | 643000 | 2023 | 47000 | 750000 | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000
ASHE | SR 1523 | NCDOT | REPLACE BRIDGE 040047 OVER HELTON CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0043 | DIVISION 11 | DP, HFB | 2025 | 126000 |  |  | 2026 | 720000 |  |  | 846000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1644 | NCDOT | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0044 | DIVISION 11 | DP, HFB | 2027 | 210000 |  |  | 2028 | 1200000 |  |  | 1410000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1609 | NCDOT | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0045 | DIVISION 11 | DP, HFB | 2027 | 140000 |  |  | 2028 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1105 | NCDOT | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0046 | DIVISION 11 | DP, HFB | 2024 | 182000 |  |  | 2025 | 1040000 |  |  | 1222000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1528 | NCDOT | REPLACE BRIDGE 040304 OVER HELTON CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0047 | DIVISION 11 | DP, HFB | 2025 | 112000 |  |  | 2026 | 640000 |  |  | 752000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1606 | NCDOT | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0048 | DIVISION 11 | DP, HFB | 2027 | 140000 |  |  | 2028 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1602 | NCDOT | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0049 | DIVISION 11 | DP, HFB | 2027 | 280000 |  |  | 2028 | 1600000 |  |  | 1880000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1563 | NCDOT | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0050 | DIVISION 11 | DP, HFB | 2027 | 280000 |  |  | 2028 | 1600000 |  |  | 1880000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1159 | NCDOT | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0051 | DIVISION 11 | DP, HFB | 2025 | 210000 |  |  | 2026 | 1200000 |  |  | 1410000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1104 | NCDOT | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0052 | DIVISION 11 | DP, HFB | 2024 | 182000 |  |  | 2025 | 1040000 |  |  | 1222000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1126 | NCDOT | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0053 | DIVISION 11 | DP, HFB | 2027 | 126000 |  |  | 2028 | 720000 |  |  | 846000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1222 | NCDOT | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0054 | DIVISION 11 | DP, HFB | 2025 | 280000 |  |  | 2026 | 1600000 |  |  | 1880000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1527 | NCDOT | REPLACE BRIDGE 040048 OVER HELTON CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0068 | DIVISION 11 | DP, HFB | 2024 | 140000 |  |  | 2025 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | NC 16 | NCDOT | US 221 TO THE VIRGINIA STATE LINE. INSTALL NEW AND UPGRADE EXISTING GUARDRAIL. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO | HS-2011E | REGION F | HSIP |  |  |  |  | 2023 | 1425000 |  |  | 1425000 | UNDER CONSTRUCTION.
ASHE | US 221 | NCDOT | SR 1003 (IDLEWILD ROAD) TO NORTH OF SOUTH FORK NEW RIVER | HIGHWAY | TRANSITION | 11 | HIGH COUNTRY RPO | R-2915B | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
ASHE | US 221 | NCDOT | NORTH OF SOUTH FORK NEW RIVER TO SOUTH OF NC 194 | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2915C | DIVISION 11 | BGLT5 |  |  |  |  | 2017 | 19700000 |  |  | 19700000 | COMPLETE
ASHE | US 221 | NCDOT | SOUTH OF NC 194 TO US 221 BYPASS | HIGHWAY | TRANSITION | 11 | HIGH COUNTRY RPO | R-2915D | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
ASHE | US 221 | NCDOT | US 221 BYPASS TO US 221 BUSINESS/NC 88 IN JEFFERSON | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2915E | DIVISION 11 | T |  |  |  |  | 2020 | 42059000 |  |  | 42059000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
ASHE | NC 88 | NCDOT | NC 88 TO NC 194. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5832 | DIVISION 11 | T | 2024 | 12800000 | 2024 | 4600000 | 2025 | 32700000 |  |  | 50100000
ASHE | US 221 BUSINESS | NCDOT | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT REDUCED CONFLICT INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5833 | NOT FUNDED | T | NOT FUNDED | 1100000 | NOT FUNDED | 50000 | NOT FUNDED | 2800000 |  |  | 3950000
ASHE | ASHE COUNTY TRANSPORTATION | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 11 | HIGH COUNTRY RPO | TA-6674 | DIVISION 11 | 5311, L, T
ASHE | ASHE COUNTY TRANSPORTATION | ASHE COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11 | HIGH COUNTRY RPO | TK-6108 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 784000 | 784000 | FUNDS AUTHORIZED IN PROGRESS
ASHE, WATAUGA | US 221 | NCDOT | US 421 IN WATAUGA COUNTY TO US 221 BUSINESS/NC 88 IN JEFFERSON. WIDEN TO FOUR LANES DIVIDED. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2915
ASHE, WATAUGA | US 221 | NCDOT | US 421 IN WATAUGA COUNTY TO SR 1003 (IDLEWILD ROAD) IN ASHE COUNTY | HIGHWAY | TRANSITION | 11 | HIGH COUNTRY RPO | R-2915A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
AVERY | SR 1306 (HICKS HOLLOW ROAD) | NCDOT | REPLACE BRIDGE 050125 OVER ELK RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | B-5835 | DIVISION 11 | BGOFF | 2025 | 150000 | 2025 | 300000 | 2026 | 2000000 |  |  | 2450000
AVERY | SR 1326 | NCDOT | REPLACE BRIDGE 050091 OVER ELK RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0055 | DIVISION 11 | DP, HFB | 2024 | 140000 |  |  | 2025 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
AVERY | SR 1511 (ROSEBORO ROAD) | NCDOT | INSTALL SHOULDER GUARDRAIL. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO | HS-2011C | DIVISION 11 | HSIP |  |  |  |  | 2021 | 7000 |  |  | 7000 | UNDER CONSTRUCTION.
AVERY | US 19E-NC 194 | NCDOT | SR 1106 TO US 221. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2520B | NOT FUNDED | T | NOT FUNDED | 4300000 |  |  | NOT FUNDED | 25600000 |  |  | 29900000
AVERY | NC 184 | NCDOT | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5902 | NOT FUNDED | T | NOT FUNDED | 18200000 | NOT FUNDED | 7900000 | NOT FUNDED | 64798000 |  |  | 90898000
AVERY | US 19E | NCDOT | NC 194 INTERSECTION. CONSTRUCT RIGHT TURN LANE FROM US 19E NORTHBOUND TO NC 194 EASTBOUND. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5911 | DIVISION 11 | BGLT5 | 2022 | 200000 |  |  | 2023 | 1100000 |  |  | 1300000 | UNDER CONSTRUCTION.
AVERY, MITCHELL | US 19E, NC 194 | NCDOT | MULTI-LANE SECTION EAST OF SPRUCE PINE TO US 221. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 11, 13 | HIGH COUNTRY RPO | R-2520
AVERY, MITCHELL | US 19E | NCDOT | MULTI-LANES EAST OF SPRUCE PINE TO SR 1106. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 11, 13 | HIGH COUNTRY RPO | R-2520A | DIVISION 11, 13 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 50801000 |  |  | 69501000
AVERY, WATAUGA | NC 105 | NCDOT | US 221 IN AVERY COUNTY TO SR 1136 (CLARKS CREEK ROAD) IN WATAUGA COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2566A | NOT FUNDED | T | NOT FUNDED | 1000000 |  |  | NOT FUNDED | 60350000 |  |  | 61350000
BEAUFORT | WARREN FIELD (OCW) | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | AVIATION | STI (PRIORITIZATION) | 2 | MID-EAST RPO | AV-5743 | DIVISION 2 | T | 2028 | 1635000 |  |  | 2029 | 3648000 |  |  | 5283000
BEAUFORT | SR 1112 (MOUTH OF THE CREEK ROAD) | NCDOT | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | HIGHWAY | BRIDGES | 2 | MID-EAST RPO | B-5614 | DIVISION 2 | BGOFF | 2022 | 319000 | 2022 | 108000 | 2023 | 9801000 |  |  | 10228000 | RIGHT-OF-WAY IN PROGRESS.
BEAUFORT | US 264 | NCDOT | CONSTRUCT REDUCED CONFLICT INTERSECTION AT US 264 AND SR 1410 (VOA ROAD). | HIGHWAY | SAFETY | 2 | MID-EAST RPO | HS-2002D | STATEWIDE MOBILITY | HSIP | 2022 | 15000 |  |  | 2022 | 889000 |  |  | 904000 | UNDER CONSTRUCTION.
BEAUFORT | US 17 | NCDOT | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). | HIGHWAY | STI (PRIORITIZATION) | 2 | MID-EAST RPO | R-2513E | NOT FUNDED | T | NOT FUNDED | 4600000 | NOT FUNDED | 600000 | NOT FUNDED | 18300000 |  |  | 23500000
BEAUFORT | NC 32 | NCDOT | BRICK KILN ROAD. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 2 | MID-EAST RPO | R-5897 | NOT FUNDED | T | NOT FUNDED | 454000 | NOT FUNDED | 200000 | NOT FUNDED | 1400000 |  |  | 2054000
BEAUFORT | SR 1306 (15TH STREET) | NCDOT | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | MID-EAST RPO | U-5860 | DIVISION 2 | T | 2026 | 8900000 | 2026 | 2800000 | 2028 | 11000000 |  |  | 22700000
BEAUFORT | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 2 | MID-EAST RPO | TK-6110 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 564000 | 564000 | FUNDS AUTHORIZED IN PROGRESS
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | NCDOT | REPLACEMENT VESSEL (SUPPORT FLEET) FOR TUGS AND BARGES | FERRY | STI (PRIORITIZATION) | 1, 2, 3 | JACKSONVILLE URBAN AREA MPO, ALBEMARLE RPO, CAPE FEAR RPO, WILMINGTON URBAN AREA MPO, EASTERN CAROLINA RPO, GRAND STRAND AREA TRANSPORTATION STUDY, GREENVILLE URBAN AREA MPO, MID-CAROLINA RPO, MID-EAST RPO, NEW BERN AREA MPO, PEANUT BELT RPO | F-5703 | DIVISION 1, 2, 3
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | NCDOT | Z-DRIVE TOWING AND PUSHING TUG | FERRY | STI (PRIORITIZATION) | 1, 2, 3 | ALBEMARLE RPO, CAPE FEAR RPO, DOWN EAST RPO, WILMINGTON URBAN AREA MPO, EASTERN CAROLINA RPO, GRAND STRAND AREA TRANSPORTATION STUDY, GREENVILLE URBAN AREA MPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, MID-EAST RPO, NEW BERN AREA MPO, PEANUT BELT RP | F-5703A | DIVISION 1, 2, 3 | T |  |  |  |  | 2019 | 3250000 |  |  | 3250000 | COMPLETED.
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | NCDOT | TWO SUPPORT/ANCHOR TUGS, ONE SUPPORT TUG, THREE BARGES | FERRY | STI (PRIORITIZATION) | 1, 2, 3 | ALBEMARLE RPO, CAPE FEAR RPO, DOWN EAST RPO, WILMINGTON URBAN AREA MPO, EASTERN CAROLINA RPO, GRAND STRAND AREA TRANSPORTATION STUDY, GREENVILLE URBAN AREA MPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, MID-EAST RPO, NEW BERN AREA MPO, PEANUT BELT RP | F-5703B | DIVISION 1, 2, 3 | T |  |  |  |  | 2019 | 2100000 |  |  | 2100000 | COMPLETED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | BO-2402 | DIVISION 2 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | HS-2002
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | HS-2402 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | R-5782 | DIVISION 2 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | DIVISION 2 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO | W-5202 | REGION B | [10 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5702 | [11 empty] | IN PROGRESS
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5702DIV | DIVISION 2 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5702REG | REGION B | HSIP | 2020 | 131000 |  |  | 2020 | 3125000 |  |  | 3256000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5702SW | STATEWIDE MOBILITY | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5802
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 2. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | RC-2002 | DIVISION 2
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | RX-2002 | DIVISION 2
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | RX-2402 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BEAUFORT, PASQUOTANK, PITT, WILSON, BERTIE, CHOWAN, EDGECOMBE, FRANKLIN, MARTIN, NASH, PERQUIMANS, WAKE | GREYHOUND LINES | GREYHOUND LINES | INTERCITY BUS FROM RALEIGH TO NORFOLK, VA VIA ELIZABETH CITY ALONG US 64, US 301, US 264, AND US 17 WITH STOPS AT RALEIGH, ROCKY MOUNT, WILSON, GREENVILLE, WASHINGTON, WILLIAMSTON, EDENTON, AND ELIZABETH CITY | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1, 2, 4, 5 |  | TI-6104 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 9248000 | 9248000 | FUNDS AUTHORIZED IN PROGRESS
BERTIE | NC 45 | NCDOT | HERTFORD COUNTY LINE TO WASHINGTON COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5809
BERTIE | NC 45 | NCDOT | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5809A | DIVISION 1 | T | 2023 | 5000 | 2023 | 4420000 | 2024 | 17399000 |  |  | 21824000 | RIGHT-OF-WAY IN PROGRESS.
BERTIE | NC 45 | NCDOT | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5809B | DIVISION 1 | T | 2025 | 3012000 | 2025 | 12944000 | 2027 | 33498000 |  |  | 49454000
BERTIE | NC 45 | NCDOT | SOUTHERN CITY LIMITS OF COLERAIN TO HERTFORD COUNTY LINE. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5809C | DIVISION 1 | [10 empty] | COMPLETED.
BERTIE, CURRITUCK | VARIOUS | NCDOT | UPGRADE WARNING SIGNS AT CURVES AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | PEANUT BELT RPO, ALBEMARLE RPO | HS-2001E | DIVISION 1 | HSIP |  |  |  |  | 2023 | 12000 |  |  | 12000 | UNDER CONSTRUCTION.
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5701DIV | DIVISION 1 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5701REG | REGION A | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5701SW | STATEWIDE MOBILITY | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
BERTIE, HALIFAX, HERTFORD, NORTHAMPTON | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1, 4 | PEANUT BELT RPO | TK-6119 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1972000 | 1972000 | FUNDS AUTHORIZED IN PROGRESS
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | BO-2401 | DIVISION 1 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | HS-2001
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | HS-2401 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | R-5781 | DIVISION 1 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | DIVISION 1 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5201 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5701 | [11 empty] | IN PROGRESS.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5801 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5801DIV | DIVISION 1
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5801REG | REGION A
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5801SW | STATEWIDE MOBILITY
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 1. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | RC-2001 | DIVISION 1 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | RX-2001 | DIVISION 1
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | RX-2401 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BLADEN | FIELD (EYF) CURTIS L BROWN JR | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. | AVIATION | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | AV-5826 | DIVISION 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7200000 |  |  | 7200000
BLADEN | NC 87 | NCDOT | REPLACE BRIDGE 080014 OVER HAMMOND CREEK. | HIGHWAY | BRIDGES | 6 | MID-CAROLINA RPO | B-5945 | STATEWIDE MOBILITY | BFP | 2027 | 700000 |  |  | 2028 | 7200000 |  |  | 7900000
BLADEN | SR 1534 (OVER LYON ROAD) | NCDOT | REPLACE BRIDGE 080197 OVER KELLY CANAL. | HIGHWAY | BRIDGES | 6 | MID-CAROLINA RPO | B-6004 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION.
BLADEN | SR 1536 (JAMES PORTER ROAD) | NCDOT | REPLACE BRIDGE 080198 OVER KELLY CANAL. | HIGHWAY | BRIDGES | 6 | MID-CAROLINA RPO | B-6008 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION.
BLADEN | NC 87 | NCDOT | NC 87 AT SR 1004 (TAR HEEL ROAD) AND SR 1316 (TAR HEEL FERRY ROAD). REVISE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO | HS-2006L | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 80000 |  |  | 80000 | UNDER CONSTRUCTION.
BLADEN | SR 1325 (GUM SPRINGS ROAD) | NCDOT | SR 1325 (GUM SPRINGS ROAD) NEAR SR 1327. CURVE IMPROVEMENTS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO | HS-2006M | DIVISION 6 | HSIP |  |  |  |  | 2024 | 174000 |  |  | 174000
BLADEN | NC 87 | NCDOT | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO, MID-CAROLINA RPO | R-2561B | NOT FUNDED | T | NOT FUNDED | 13437000 | NOT FUNDED | 1612000 | NOT FUNDED | 57000000 |  |  | 72049000
BLADEN | NC 87 | NCDOT | IMPROVE ROADWAY FOR SMITHFIELD FOODS PROCESSING CENTER. | HIGHWAY | ECONOMIC DEVELOPMENT | 6 | MID-CAROLINA RPO | R-5866 | REGION C | T |  |  |  |  | 2018 | 1042000 |  |  | 1042000 | COMPLETED. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SMITHFIELD FOODS PROCESSING.
BLADEN | BLADEN COUNTY | BLADEN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6 | MID-CAROLINA RPO | TK-6111 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 484000 | 484000 | FUNDS AUTHORIZED IN PROGRESS
BLADEN, COLUMBUS | NC 87 | NCDOT | ELIZABETHTOWN BYPASS IN BLADEN COUNTY TO US 74/US 76 IN COLUMBUS COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO, MID-CAROLINA RPO | R-2561
BLADEN, COLUMBUS | NC 87 | NCDOT | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | R-2561A | NOT FUNDED | T | NOT FUNDED | 13781000 | NOT FUNDED | 1654000 | NOT FUNDED | 96100000 |  |  | 111535000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | BO-2406 | DIVISION 6 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | HS-2006
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | HS-2406 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | R-5786 | DIVISION 6 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. S FUNDS REFLECT STATE HIGHWAY FUNDS.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5206 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5706 | [11 empty] | IN PROGRESS
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5706DIV | DIVISION 6 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5706REG | REGION C | HSIP | 2020 | 135000 |  |  | 2020 | 519000 |  |  | 654000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5706SW | STATEWIDE MOBILITY | HSIP | 2020 | 90000 |  |  | 2020 | 500000 |  |  | 590000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5806
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 6. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | RC-2006 | DIVISION 6 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | RX-2006 | DIVISION 6
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | RX-2406 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BRUNSWICK | CAPE FEAR REGIONAL (SUT) | CAPE FEAR REGIONAL (SUT) | APPROACH CLEARING AT RUNWAY 5 AND RUNWAY 23. | AVIATION | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | AV-5739 | DIVISION 3 | [10 empty] | COMPLETED.
BRUNSWICK | ODELL WILLIAMSON MUNICIPAL AIRPORT (60J) | ODELL WILLIAMSON MUNICIPAL AIRPORT (60J) | RUNWAY PROTECTION ZONE 2 - RUNWAY 24 LAND ACQUISITION AND OBSTRUCTION REMOVAL. | AVIATION | STI (PRIORITIZATION) | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | AV-5742 | DIVISION 3 | [10 empty] | RIGHT-OF-WAY IN PROGRESS.
BRUNSWICK | VARIOUS | NCDOT | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION TRANSPORTATION ALTERNATIVES PROGRAM. | BIKE/PED | LOCALLY SELECTED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | BL-0021 | DIVISION 3 | TADA |  |  |  |  | 2022 | 1215000 |  |  | 1215000
BRUNSWICK | SR 1116 (OCEAN BOULEVARD) | NCDOT | INSTALL BIKE LANES ALONG SR 1116 (OCEAN BOULEVARD) FROM JUST WEST OF SHELL DRIVE TO DUNESCAPE DRIVE IN HOLDEN BEACH. | BIKE/PED | LOCALLY SELECTED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | BL-0046 | DIVISION 3 | BGDA, L |  |  |  |  | 2022 | 1613000 |  |  | 1613000 | UNDER CONSTRUCTION.
BRUNSWICK | US 17 | LELAND | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | BL-0074 | DIVISION 3 | BGDA, L | 2024 | 24000 |  |  | 2025 | 548000 | 2023 | 262000 | 834000
BRUNSWICK | NC 211 (NORTH HOWE STREET) | SOUTHPORT | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | EB-5982 | DIVISION 3 | L, TA5200 | 2024 | 50000 |  |  | 2025 | 175000 | 2023 | 30000 | 255000
BRUNSWICK | RICE HOPE MULTI-USE PATH | BELVILLE | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | EB-6025 | DIVISION 3 | BGDA, L |  |  |  |  | 2023 | 167000 | 2020 | 30000 | 197000 | UNDER CONSTRUCTION.
BRUNSWICK | BELVILLE ELEMENTARY MULTI-USE PATH | BELVILLE | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | EB-6026 | DIVISION 3 | L, TADA |  |  |  |  | 2023 | 118000 | 2020 | 30000 | 148000 | UNDER CONSTRUCTION.
BRUNSWICK | SR 1144 (FIRST STREET) | OCEAN ISLE BEACH | CONSTRUCTION OF BIKE LANES ON BOTH SIDES OF FIRST STREET FROM EAST OF WEST FIRST STREET EXTENSION TO EAST OF GREENSBORO STREET IN OCEAN ISLE BEACH. | BIKE/PED | LOCALLY SELECTED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | EB-6034 | DIVISION 3 | BGDA, L |  |  |  |  | 2021 | 1036000 |  |  | 1036000 | UNDER CONSTRUCTION.
BRUNSWICK | SR 1342 (MAKATOKA ROAD NORTHWEST) | NCDOT | REPLACE BRIDGE 090100 OVER MUDDY BRANCH. | HIGHWAY | BRIDGES | 3 | CAPE FEAR RPO | B-4439 | DIVISION 3 | BGOFF | 2022 | 550000 |  |  | 2022 | 1250000 |  |  | 1800000 | UNDER CONSTRUCTION.
BRUNSWICK | SR 1515 (OLD MILL CREEK ROAD SE) | NCDOT | REPLACE BRIDGE 090040 OVER MILL CREEK. | HIGHWAY | BRIDGES | 3 | CAPE FEAR RPO | B-5629 | DIVISION 3 | BGOFF | 2022 | 115000 |  |  | 2023 | 2450000 |  |  | 2565000 | UNDER CONSTRUCTION.
BRUNSWICK | SR 1300 (ASH-LITTLE RIVER ROAD NORTHWEST) | NCDOT | REPLACE BRIDGE 090126 OVER CAWCAW SWAMP. | HIGHWAY | BRIDGES | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | B-5996 | DIVISION 3 | BGOFF | 2022 | 100000 |  |  | 2022 | 2000000 |  |  | 2100000 | UNDER CONSTRUCTION.
BRUNSWICK | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GRAND STRAND AREA TRANSPORTATION STUDY PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | HL-0103 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 289000 |  |  | 289000
BRUNSWICK | US 17 | NCDOT | US 17 AND SR 1130 (MOUNT PISGAH ROAD) / SR 1344 (SELLERS ROAD). INSTALL SIGNALIZED LEFTOVER. | HIGHWAY | SAFETY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | HS-2003D | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2025 | 269000 |  |  | 269000
BRUNSWICK | NC 130 | NCDOT | NC 130 AND SR 1120 (SABBATH HOME ROAD) / SR 1239 (OCEAN VIEW AVENUE) IN HOLDEN BEACH. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | HS-2003G | REGION B | HSIP |  |  |  |  | 2026 | 84000 |  |  | 84000
BRUNSWICK | US 74/76 | NCDOT | US 74/76 AT SR 1714 (ENTERPRISE DRIVE) AND US 74/76 AT SR 1494 (WOOD TREATMENT ROAD). INSTALL TRAFFIC SIGNALS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003O | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2026 | 533000 |  |  | 533000
BRUNSWICK | US 17 | NCDOT | US 17 AT SR 1136 (RED BUG ROAD) AND US 17 AT SR 1345 (ROYAL OAK ROAD). INSTALL A REDUCED CONFLICT INTERSECTION. | HIGHWAY | SAFETY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | HS-2003W | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION.
BRUNSWICK | I-140 | NCDOT | US 17 TO NORTH OF US 74. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | I-6036 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 8500000 |  |  | 8500000 | UNDER CONSTRUCTION.
BRUNSWICK | I-140/US 17 WILMINGTON BYPASS | NCDOT | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO SR 1430 (CEDAR HILL ROAD). | HIGHWAY | TRANSITION | 3 | WILMINGTON URBAN AREA MPO | R-2633BA | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2014 | 30750000 |  |  | 30750000 | COMPLETED. GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK 2014 - 2025.
BRUNSWICK | NC 211 | NCDOT | SR 1500 (MIDWAY ROAD) TO NC 87. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | R-5021 | DIVISION 3 | BG5200 |  |  |  |  | 2022 | 239876000 |  |  | 239876000 | UNDER CONSTRUCTION.
BRUNSWICK | US 17 | NCDOT | NC 904. UPGRADE TO REDUCED CONFLICT INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5851 | NOT FUNDED | T | NOT FUNDED | 850000 | NOT FUNDED | 115000 | NOT FUNDED | 4950000 |  |  | 5915000
BRUNSWICK | US 17 | NCDOT | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5857 | STATEWIDE MOBILITY | T | 2023 | 770000 | 2023 | 330000 | 2026 | 21600000 |  |  | 22700000 | RIGHT-OF-WAY IN PROGRESS.
BRUNSWICK | I-74 (CAROLINA BAYS PARKWAY EXTENSION) | NCDOT | FROM SC STATE LINE TO US 17 AT NC 130. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO, GRAND STRAND AREA TRANSPORTATION STUDY | R-5876 | NOT FUNDED | O | NOT FUNDED | 128600000 | NOT FUNDED | 5300000 | NOT FUNDED | 232800000 |  |  | 366700000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
BRUNSWICK | NC 211 | NCDOT | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | R-5947 | NOT FUNDED | T | NOT FUNDED | 7300000 | NOT FUNDED | 4300000 | NOT FUNDED | 45700000 |  |  | 57300000
BRUNSWICK | US 17 BUSINESS (MAIN STREET) | NCDOT | WALL STREET/SHALLOTTE AVENUE. REALIGN INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5788 | DIVISION 3 | T |  |  |  |  | 2021 | 1939000 |  |  | 1939000 | UNDER CONSTRUCTION.
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | NCDOT | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5862 | REGION B | T | 2028 | 5240000 | 2028 | 1840000 | 2030 | 22000000 |  |  | 29080000
BRUNSWICK | VARIOUS | NCDOT | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | HIGHWAY | LOCALLY SELECTED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5910 | DIVISION 3 | BGDA, L | [6 empty] | 2023 | 290000 | 290000 | IN PROGRESS
BRUNSWICK | NC 133 | NCDOT | US 17/US 74/US 76 TO SR 1554 (OLD RIVER ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5914 | DIVISION 3 | T |  |  |  |  | 2023 | 2428000 |  |  | 2428000 | UNDER CONSTRUCTION.
BRUNSWICK | US 17 | NCDOT | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO, GRAND STRAND AREA TRANSPORTATION STUDY | U-5932 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38989000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1920000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36102000 |  |  | 77011000
BRUNSWICK | VARIOUS | NCDOT | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | HIGHWAY | LOCALLY SELECTED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5990 | DIVISION 3 | BGDA |  |  |  |  | 2022 | 9483000 |  |  | 9483000
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | NCDOT | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-6104 | NOT FUNDED | NHP | NOT FUNDED | 4233000 | NOT FUNDED | 300000 | NOT FUNDED | 19200000 |  |  | 23733000
BRUNSWICK | BRUNSWICK TRANSIT SYSTEM, INC. | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 3 | CAPE FEAR RPO | TK-6112 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 712000 | 712000 | FUNDS AUTHORIZED IN PROGRESS
BRUNSWICK, NEW HANOVER | SOUTHPORT-FORT FISHER | NCDOT | SOUTHPORT-FORT FISHER FERRY. CONSTRUCT RIVER CLASS FERRY. | FERRY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5705 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 14000000 |  |  | 14000000
BRUNSWICK, NEW HANOVER | SOUTHPORT - FORT FISHER | NCDOT | CONSTRUCT MOORING FACILITIES. | FERRY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5707 | REGION B | T |  |  |  |  | 2025 | 5000000 |  |  | 5000000
BRUNSWICK, NEW HANOVER | I-140/US 17 (WILMINGTON BYPASS) | NCDOT | US 17 SOUTH OF NC 87 IN BRUNSWICK COUNTY TO I-40 IN NEW HANOVER COUNTY. FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633AA | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2010 | 6810000 |  |  | 6810000 | COMPLETED. GARVEE BOND FUNDING: $31.05M FOR CONSTRUCTION, PAYBACK 2010 - 2021.
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633AB | [11 empty] | COMPLETED.
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO WEST OF US 421 NORTH OF WILMINGTON. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633BC | [11 empty] | COMPLETED.
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | IMPLEMENTATION OF INTELLIGENT TRANSPORTATION SYSTEMS (ITS). | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633D | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
BRUNSWICK, NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE OPERATING ASSISTANCE PROJECT WILL ALLOW THE CONTINUATION OF COMPLEMENTARY PARATRANSIT SERVICE TO TWO COUNTIES AND FOUR MUNICIPLITIES WITHIN THE UZA. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | TG-5246 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 393000 | 393000
BRUNSWICK, ONSLOW, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY, WILMINGTON URBAN AREA MPO | W-5203SW | STATEWIDE MOBILITY
BUNCOMBE | ASHEVILLE REGIONAL AIRPORT | ASHEVILLE REGIONAL AIRPORT (AVL) | MODERNIZE AIRPORT TERMINAL BUILDING. | AVIATION | OTHER | 13 | FRENCH BROAD RIVER MPO | AO-0001 | EXEMPT | FED, L, S |  |  |  |  | 2022 | 153808000 |  |  | 153808000 | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "S" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT
BUNCOMBE | ASHEVILLE REGIONAL AIRPORT (AVL) | ASHEVILLE REGIONAL AIRPORT (AVL) | AIRFIELD IMPROVEMENTS PROGRAM - RUNWAY CONSTRUCTION | AVIATION | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | AV-5735 | REGION G | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | ASHEVILLE REGIONAL AIRPORT (AVL) | ASHEVILLE REGIONAL AIRPORT (AVL) | EXPAND TERMINAL APRON TO THE SOUTH. | AVIATION | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | AV-5882 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2019 | 6695000 |  |  | 6695000 | COMPLETE.
BUNCOMBE | NC 251/ SR 1781 (BROADWAY STREET) | NCDOT | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | BL-0005 | DIVISION 13 | BGDA, HF, HSIP, S(M) |  |  |  |  | 2022 | 1124000 | 2021 | 4000 | 1128000 | COMPLETE. "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. HF FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID.
BUNCOMBE | VARIOUS | NCDOT | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | BL-0006 | DIVISION 13 | BGDA, L |  |  |  |  | 2026 | 750000 | 2026 | 75000 | 825000
BUNCOMBE | SWANNANOA GREENWAY | ASHEVILLE | BLEACHERY ROAD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | BL-0077 | DIVISION 13 | BGDA, L |  |  |  |  | 2028 | 3125000 |  |  | 3125000
BUNCOMBE | TEXAS ROAD | MONTREAT | REPLACE EXISTING HIGHWAY BRIDGE WITH PEDESTRIAN BRIDGE. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | BL-0079 | DIVISION 13 | BGDA, L |  |  |  |  | 2024 | 191000 |  |  | 191000
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | BLACK MOUTAIN | CONSTRUCT MULTI-USE PATH FROM EXISTING FLAT CREEK GREENWAY TRAILHEAD NORTH OF US 70 TO THE OAKS TRAIL. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5547 | DIVISION 13 | [10 empty] | $3.234M IN BGANY USED AS PART OF MULTIPLE FUND SWAPS. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.991M. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.915M.
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | BLACK MOUTAIN | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5547A | DIVISION 13 | BGANY, L | 2023 | 40000 |  |  | 2024 | 1559000 | 2023 | 290000 | 1889000
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | BLACK MOUTAIN | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5547B | DIVISION 13 | BGANY, L | 2023 | 20000 |  |  | 2024 | 1551000 | 2022 | 184000 | 1755000
BUNCOMBE | NC 251 (RIVERSIDE DRIVE) MULTI-USE PATH | BUNCOMBE COUNTY | US 19/23/70 (EXIT 25) TO US 25. CONSTRUCT MULTI-USE PATH VIA BEAVERDAM CREEK. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5774 | DIVISION 13 | BGDA, L | [6 empty] | 2020 | 2000000 | 2000000 | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION
BUNCOMBE | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | ASHEVILLE | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5774A | DIVISION 13 | BGDA, CRPDA, L, TADA | 2023 | 4259000 |  |  | 2025 | 6010000 |  |  | 10269000
BUNCOMBE | BEAVERDAM CREEK GREENWAY | ASHEVILLE | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5774B | DIVISION 13 | BGANY, BGDA, L, TADA | 2025 | 608000 |  |  | 2026 | 3450000 |  |  | 4058000
BUNCOMBE | ASHEVILLE | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5790 | DIVISION 13 | BGDA, L, TAANY |  |  |  |  | 2023 | 1496000 |  |  | 1496000 | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919
BUNCOMBE | REEMS CREEK GREENWAY | BUNCOMBE COUNTY | CONSTRUCT MULTI-USE PATH ALONG REEMS CREEK CORRIDOR FROM WESTERN EDGE OF TOWN OF WEAVERVILLE TO KARPEN SOCCER FIELDS | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5821 | DIVISION 13 | [10 empty] | IN PROGRESS
BUNCOMBE | NORTH RAD GREENWAY | ASHEVILLE | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | BIKE/PED | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | EB-5822 | DIVISION 13 | BGDA, L, TAANY | 2023 | 129000 |  |  | 2025 | 4000000 | 2021 | 600000 | 4729000
BUNCOMBE | BENT CREEK GREENWAY | BUNCOMBE COUNTY | CONSTRUCT MULTI-USE PATH FROM HOMINY CREEK RIVER PARK TO WESTERN NC FARMERS MARKET. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5823 | DIVISION 13 | BGDA, L | [6 empty] | 2029 | 400000 | 400000
BUNCOMBE | HOMINY CREEK GREENWAY | NCDOT | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5824 | DIVISION 13 | BGANY, BGDA, L |  |  |  |  | 2023 | 3844000 | 2021 | 1310000 | 5154000 | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES.
BUNCOMBE | ASHEVILLE | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5831 | DIVISION 13 | BGANY, BGDA, L, TADA | 2024 | 300000 |  |  | 2025 | 11000000 | 2023 | 900000 | 12200000 | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP.
BUNCOMBE | ASHEVILLE | ASHEVILLE | JOHNSTON BOULEVARD, PATTON AVENUE TO IONA CIRCLE. CONSTRUCT SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5944 | DIVISION 13 | BGDA, L |  |  |  |  | 2023 | 2350000 |  |  | 2350000
BUNCOMBE | ASHEVILLE | ASHEVILLE | NEW HAW CREEK ROAD, BEVERLY ROAD TO BELL ROAD. CONSTRUCT SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5947 | DIVISION 13 | BGANY, L |  |  |  |  | 2023 | 2375000 |  |  | 2375000 | $1.9M IN BGANY USED AS PART OF FUND SWAP
BUNCOMBE | ASHEVILLE | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | EB-5948 | DIVISION 13 | BGDA, L, TADA |  |  |  |  | 2023 | 1140000 |  |  | 1140000 | UNDER CONSTRUCTION.
BUNCOMBE | DEAVERVIEW ROAD | ASHEVILLE | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | EB-5965 | DIVISION 13 | L, TAANY | 2026 | 250000 |  |  | 2027 | 2245000 | 2024 | 710000 | 3205000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | SR 1781 (BROADWAY STREET) TO US 25/70 | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | FRENCH BROAD RIVER MPO | A-0010AA | REGION G | T | 2028 | 42700000 | 2028 | 1000000 | 2031 | 279800000 |  |  | 323500000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | US 25/70 TO SR 2207 (N BUNCOMBE SCHOOL ROAD) | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | FRENCH BROAD RIVER MPO | A-0010AB | NOT FUNDED | T | NOT FUNDED | 5600000 |  |  | NOT FUNDED | 72000000 |  |  | 77600000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | SR 2207 (N BUNCOMBE SCHOOL ROAD) TO SOUTH OF SR 2148 (STOCKTON ROAD) | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | FRENCH BROAD RIVER MPO | A-0010AC | NOT FUNDED | T | NOT FUNDED | 700000 |  |  | NOT FUNDED | 27000000 |  |  | 27700000
BUNCOMBE | US 19/US 23/US 25/ US 70 | NCDOT | REPLACE BRIDGE 100370, AND BRIDGE 100373 OVER REEMS CREEK. | HIGHWAY | BRIDGES | 13 | FRENCH BROAD RIVER MPO | B-4442 | STATEWIDE MOBILITY | NHPB | 2022 | 400000 |  |  | 2022 | 29996000 |  |  | 30396000 | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION.
BUNCOMBE | US 19/US 23/US 25/ US 70 | NCDOT | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | HIGHWAY | BRIDGES | 13 | FRENCH BROAD RIVER MPO | B-4443 | STATEWIDE MOBILITY | BFP | 2025 | 720000 |  |  | 2029 | 15000000 |  |  | 15720000 | COORDINATE WITH A-0010A
BUNCOMBE | US 19/23/25/70 | NCDOT | REHABILITATE DECK ON BRIDGE 100353 OVER SR 1882. | HIGHWAY | BRIDGES | 13 | FRENCH BROAD RIVER MPO | B-4444 | STATEWIDE MOBILITY | BFP |  |  |  |  | 2026 | 1000000 |  |  | 1000000 | COORDINATE WITH A-0010A
BUNCOMBE | MONTREAT (TEXAS ROAD) | NCDOT | REPLACE BRIDGE 100528 OVER FLAT CREEK. | HIGHWAY | TRANSITION | 13 | FRENCH BROAD RIVER MPO | B-5196 | DIVISION 13 | [10 empty] | MUNICIPAL BRIDGE
BUNCOMBE | SR 2027 (MARTINS CREEK ROAD) | NCDOT | REPLACE BRIDGE 100142 OVER MARTIN CREEK. | HIGHWAY | BRIDGES | 13 | LAND-OF-SKY RPO | B-6016 | DIVISION 13 | BGOFF | 2022 | 50000 |  |  | 2022 | 700000 |  |  | 750000 | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014
BUNCOMBE | SR 1296 (BROOKS BRANCH ROAD) | NCDOT | REPLACE BRIDGE 100536 OVER NEWFOUND CREEK. | HIGHWAY | BRIDGES | 13 | FRENCH BROAD RIVER MPO | B-6018 | DIVISION 13 | BGOFF | 2021 | 55000 |  |  | 2021 | 872000 |  |  | 927000 | RIGHT-OF-WAY IN PROGRESS. RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION.
BUNCOMBE | I-26 | NCDOT | CONSTRUCT NEW INTERCHANGE NEAR AND ACCESS ROAD NEAR MILEMARKER 35, CONNECTING TO FREDERICK LAW OLMSTEAD WAY EAST. | HIGHWAY | ECONOMIC DEVELOPMENT | 13 | FRENCH BROAD RIVER MPO | HE-0001 | EXEMPT | ADHSL, S |  |  |  |  | 2024 | 32500000 |  |  | 32500000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. STATE FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY.
BUNCOMBE | US 19/23 BUSINESS (HAYWOOD ROAD) | NCDOT | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | HIGHWAY | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | HL-0003 | REGION G | BGANY, BGDA, S(M) |  |  |  |  | 2024 | 7543000 | 2022 | 300000 | 7843000 | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
BUNCOMBE | I-240 | NCDOT | US 70 (CHARLOTTE STREET) INTERSECTIONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS AND A RIGHT TURN LANE ON THE I-240 EASTBOUND OFF-RAMP. | HIGHWAY | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | HL-0012 | EXEMPT | BGDA, S(M) |  |  |  |  | 2023 | 1680000 |  |  | 1680000 | UNDER CONSTRUCTION. "S(M)" FUNDS REPRESENT SPOT MOBILITY AND HIGH IMPACT/LOW COST FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. PE AND ROW FUNDED UNDER SM-5713E (HIGHWAY FUNDS).
BUNCOMBE | 9TH STREET | NCDOT | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | HIGHWAY | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | HL-0013 | DIVISION 13 | BGANY, BGDA, L | 2023 | 120000 |  |  | 2024 | 680000 | 2022 | 315000 | 1115000 | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP
BUNCOMBE | SR 3214 (BILTMORE AVENUE) | ASHEVILLE | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | HL-0014 | DIVISION 13 | BGANY, BGDA, L | 2023 | 25000 |  |  | 2023 | 340000 | 2022 | 75000 | 440000 | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP
BUNCOMBE | SR 1003 (REEMS CREEK ROAD) | NCDOT | SR 2106 TO SR 2114 NEAR WEAVERVILLE. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | HS-2013K | DIVISION 13 | HSIP |  |  |  |  | 2024 | 440000 |  |  | 440000
BUNCOMBE | I-26/I-240 | NCDOT | I-26 CONNECTOR, I-40 TO US 19/US 23. CONSTRUCT MULTI-LANE FREEWAY, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-2513
BUNCOMBE | I-40 | NCDOT | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-2513AA | STATEWIDE MOBILITY | HP, NHFP, NHPIM | 2023 | 1900000 | 2023 | 100000 | 2024 | 29700000 |  |  | 31700000 | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS.
BUNCOMBE | I-26, I-40 | NCDOT | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-2513AB | REGION G | HP, NHP | 2023 | 3400000 |  |  | 2024 | 20200000 |  |  | 23600000 | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS.
BUNCOMBE | I-26/I-240 | NCDOT | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-2513AC | REGION G | T | 2023 | 43015000 | 2023 | 3750000 | 2024 | 179970000 |  |  | 226735000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE); $22.5M FOR CONSTRUCTION, PAYBACK 2026-2040 (FY 2026 / YR 8 SALE).
BUNCOMBE | I-40, I-26 | NCDOT | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-2513B | STATEWIDE MOBILITY | NHP, S(M) | 2024 | 174525000 | 2024 | 23200000 | 2024 | 686575000 |  |  | 884300000 | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D.
BUNCOMBE | I-26/I-240 | NCDOT | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-2513C | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4075000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 185001000 |  |  | 206476000
BUNCOMBE | SR 1477 (RIVERSIDE DRIVE) | NCDOT | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET) | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-2513D | DIVISION 13 | BGANY | 2024 | 15300000 | 2024 | 3100000 | 2024 | 13100000 |  |  | 31500000 | TO BE LET WITH I-2513B.
BUNCOMBE | SR 2500 (BLUE RIDGE ROAD) | NCDOT | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-4409 | DIVISION 13 | NHP | 2023 | 6300000 | 2023 | 900000 | 2025 | 24700000 |  |  | 31900000
BUNCOMBE | I-40 | NCDOT | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-4759 | STATEWIDE MOBILITY | BGANY, BGDA | 2019 | 15582000 | 2019 | 700000 | 2026 | 35200000 |  |  | 51482000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033
BUNCOMBE | I-40 | NCDOT | MILE MARKER 45 TO MILE MARKER 50. PAVEMENT REHABILITATION. | HIGHWAY | PRE-STI (HISTORIC) | 13 | FRENCH BROAD RIVER MPO | I-5108 | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 512000 |  |  | 512000 | COMPLETE - GARVEE BOND FUNDING $4.67 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020
BUNCOMBE | I-40 | NCDOT | HAYWOOD COUNTY LINE TO MILE MARKER 43 IN BUNCOMBE COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | PRE-STI (HISTORIC) | 13 | FRENCH BROAD RIVER MPO | I-5109 | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 669000 |  |  | 669000 | COMPLETE - GARVEE BOND FUNDING $6.1 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020
BUNCOMBE | I-26 | NCDOT | NC 191 (BREVARD ROAD). UPGRADE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-5504 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION AS DESIGN-BUILD PROJECT
BUNCOMBE | I-40 | NCDOT | US 25A (SWEETEN CREEK ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-5886 | DIVISION 13 | [10 empty] | COMPLETE
BUNCOMBE | I-40 | NCDOT | MILE MARKER 37 TO MILE MARKER 44. REHABILIATE PAVEMENT AND BRIDGES. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-5888
BUNCOMBE | I-40 | NCDOT | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE PAVEMENT AND BRIDGES. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-5888A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
BUNCOMBE | I-40 | NCDOT | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE BRIDGES. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-5888B | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 4110000 |  |  | 4110000
BUNCOMBE | I-40 | NCDOT | MILE MARKER 45.25 TO MILE MARKER 50. REHABILTATE PAVEMENT AND PRESERVE BRIDGES. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-5889
BUNCOMBE | I-40 | NCDOT | MILE MARKER 46 TO MILE MARKER 50. PRESERVE BRIDGES. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-5889A | STATEWIDE MOBILITY | [10 empty] | COMPLETED
BUNCOMBE | I-40 | NCDOT | MILE MARKER 45.25 TO MILE MARKER 50. REHABILITATE PAVEMENT AND PRESERVE BRIDGES 100352, 100356, 100344, 100347, 100339, AND 100334. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-5889B | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2023 | 20409000 |  |  | 20409000 | UNDER CONSTRUCTION.
BUNCOMBE | I-40 | NCDOT | MILEMARKER 55 TO MILEMARKER 67.5. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-5890 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 23160000 |  |  | 23160000 | COMPLETE - GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033.
BUNCOMBE | I-240 | NCDOT | MILEMARKER 4 TO MILEMARKER 9. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-5901 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 20906000 |  |  | 20906000
BUNCOMBE | I-40 | NCDOT | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-6018 | NOT FUNDED | NHP | NOT FUNDED | 4000000 | NOT FUNDED | 700000 | NOT FUNDED | 117200000 |  |  | 121900000
BUNCOMBE | I-40 | NCDOT | SR 2838 (PORTERS COVE ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-6021 | NOT FUNDED | NHP |  |  | NOT FUNDED | 200000 | NOT FUNDED | 1700000 |  |  | 1900000
BUNCOMBE | I-40 | NCDOT | SR 1200 (WIGGINS ROAD) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | I-6054C | NOT FUNDED | NHP | NOT FUNDED | 13900000 | NOT FUNDED | 4700000 | NOT FUNDED | 200199000 |  |  | 218799000
BUNCOMBE | I-40 | NCDOT | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | I-6063 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 30222000 |  |  | 30222000 | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | NCDOT | US 25 (HENDERSONVILLE ROAD) TO ROBERTS ROAD IN ASHEVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-2801
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | NCDOT | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-2801AA | REGION G | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 92500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39400000 |  |  | 142100000
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | NCDOT | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-2801AB | REGION G | BGANY | 2028 | 56599000 | 2028 | 7100000 | 2031 | 53499000 |  |  | 117198000
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | NCDOT | SR 3081 (ROCK HILL ROAD) TO SR 3079 (ROBERTS ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 13 | FRENCH BROAD RIVER MPO | U-2801B | [11 empty] | COMPLETE
BUNCOMBE | NC 63 (LEICESTER HIGHWAY) | NCDOT | SR 1615 (GILBERT ROAD) TO WEST OF SR 1004 (NEWFOUND ROAD) IN ASHEVILLE. WIDEN TO MULTI-LANES, SOME RELOCATION. | HIGHWAY | PRE-STI (HISTORIC) | 13 | FRENCH BROAD RIVER MPO | U-3301 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION - DESIGN BUILD PROJECT
BUNCOMBE | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NCDOT | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-3403B | NOT FUNDED | T | NOT FUNDED | 23800000 | NOT FUNDED | 3900000 | NOT FUNDED | 48873000 |  |  | 76573000
BUNCOMBE | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NCDOT | NORTH OF BLUE RIDGE PARKWAY TO NC 112 (SARDIS ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 13 | FRENCH BROAD RIVER MPO | U-3403C | [11 empty] | COMPLETE
BUNCOMBE | CITYWIDE | NCDOT | ASHEVILLE SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-4715 | [11 empty] | A PORTION OF THE SIGNALS ARE NOT ELIGIBLE FOR FEDERAL FUNDING DUE THE ROAD'S FUNCTIONAL CLASSIFICATION. THE RESULTING FUNDING SPLIT IS 74% FEDERAL AND 26% STATE
BUNCOMBE | US 25 (HENDERSONVILLE ROAD) | NCDOT | SIGNAL IMPROVEMENTS | HIGHWAY | PRE-STI (HISTORIC) | 13 | FRENCH BROAD RIVER MPO | U-4715AA | [11 empty] | COMPLETE
BUNCOMBE | PATTON AVENUE AND COLLEGE STREET. | NCDOT | SIGNAL IMPROVEMENTS | HIGHWAY | PRE-STI (HISTORIC) | 13 | FRENCH BROAD RIVER MPO | U-4715AB | [11 empty] | COMPLETE
BUNCOMBE | CITYWIDE | NCDOT | SIGNAL IMPROVEMENTS | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-4715B | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | SR 3556 (AMBOYROAD/ MEADOW ROAD) | NCDOT | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-4739 | DIVISION 13 | BGANY | 2025 | 18500000 | 2025 | 7400000 | 2028 | 38900000 |  |  | 64800000
BUNCOMBE | ASHEVILLE EAST OF THE RIVERWAY MULTI-MODAL NETWORK | NCDOT | CONSTRUCT INTERCONNECTED NETWORK OF PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. PROJECT INCLUDES: CLINGMAN FOREST AND TOWN BRANCH GREENWAYS, FRENCH BROAD RIVER WEST GREENWAY, WILMA DIKEMAN RIVERWAY AND FIVE POINTS ROUNDABOUT, LIVINGSTON S | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5019 | [11 empty] | SEGMENT A - $3.42M IN BGANY USED AS PART OF FUND SWAP, $8K USED FOR PRELIMINARY ENGINEERING
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | CONSTRUCT TOWN BRANCH GREENWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5019A | DIVISION 13 | BGANY, L |  |  |  |  | 2023 | 4267000 |  |  | 4267000
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | FRENCH BROAD RIVER WEST GREENWAY, FRENCH BROAD RIVER PARK TO HAYWOOD ROAD. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5019B | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | WILMA DYKEMAN RIVERWAY - RADTIP AND FIVE POINTS ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5019C | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | LIVINGSTON STREET COMPLETE STREETS IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5019D | DIVISION 13 | L |  |  |  |  | 2023 | 1500000 |  |  | 1500000
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5019E | DIVISION 13 | BGANY, L |  |  |  |  | 2024 | 5250000 |  |  | 5250000
BUNCOMBE | NEW LEICESTER HIGHWAY | ASHEVILLE | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. | HIGHWAY | TRANSITION | 13 | FRENCH BROAD RIVER MPO | U-5190 | PRE-STI (TRANSITION) | BGANY, BGDA, L | 2020 | 241000 |  |  | 2022 | 3322000 |  |  | 3563000 | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | NCDOT | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5832 | DIVISION 13 | T | 2028 | 24400000 | 2028 | 1700000 | 2030 | 21901000 |  |  | 48001000
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | NCDOT | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5834 | DIVISION 13 | T | 2019 | 12333000 |  |  | 2024 | 14925000 |  |  | 27258000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE).
BUNCOMBE | SR 2002 (RICEVILLE ROAD) | NCDOT | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5837 | DIVISION 13 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9100000 |  |  | 25700000
BUNCOMBE | ASHEVILLE | NCDOT | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY) . CONSTRUCTION INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5971
BUNCOMBE | ASHEVILLE | NCDOT | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT INITIAL INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5971A | REGION G | [10 empty] | SUPPLEMENT WITH SPOT MOBILITY FUNDS. UNDER CONSTRUCTION
BUNCOMBE | ASHEVILLE | NCDOT | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT DRAINAGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5971AA | REGION G | T | 2021 | 100000 |  |  | 2022 | 550000 |  |  | 650000 | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION.
BUNCOMBE | ASHEVILLE | NCDOT | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5971B | NOT FUNDED | T | NOT FUNDED | 35590000 | NOT FUNDED | 300000 | NOT FUNDED | 6500000 |  |  | 42390000
BUNCOMBE | ASHEVILLE | NCDOT | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5972 | NOT FUNDED | T | NOT FUNDED | 66000000 | NOT FUNDED | 6700000 | NOT FUNDED | 31899000 |  |  | 104599000
BUNCOMBE | WEAVERVILLE | NCDOT | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-5973 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 200000 |  |  | 200000
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | NCDOT | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-6046 | DIVISION 13 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24700000 |  |  | 43100000 | COORDINATE WITH U-5832.
BUNCOMBE | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NCDOT | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-6047 | DIVISION 13 | BGANY | 2028 | 60799000 | 2028 | 6800000 | 2031 | 68999000 |  |  | 136598000
BUNCOMBE | SR 1332 (NORTH LOUISIANA AVENUE) | NCDOT | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-6162 | DIVISION 13 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 |  |  | 20000000
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | NCDOT | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | U-6163 | DIVISION 13 | S, T | 2024 | 100000 | 2024 | 300000 | 2024 | 2400000 |  |  | 2800000 | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS
BUNCOMBE | WALK OFF WAY | NCDOT | CONSTRUCT WALK OFF WAY EXTENSION FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | HIGHWAY | ECONOMIC DEVELOPMENT | 13 | FRENCH BROAD RIVER MPO | U-6230 | DIVISION 13 | T |  |  |  |  | 2021 | 1300000 |  |  | 1300000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR HAAKON INDUSTRIES. AWARD AMOUNT = $1,300,000 - COMPLETE.
BUNCOMBE | NEW ROUTE- ENKA HERITAGE ROAD | NCDOT | CONSTRUCT ACCESS ROAD FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | FRENCH BROAD RIVER MPO | U-6251 | EXEMPT | ADHSL | [6 empty] | 2022 | 140000 | 140000 | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. STATE FUNDS ARE SPOT MOBILITY FUNDS.
BUNCOMBE | NEW ROUTE - ENKA HERITAGE ROAD | NCDOT | US 19/23 (SMOKEY PARK HIGHWAY) TO WALKOFF WAY. CONSTRUCT ACCESS ROAD ON NEW LOCATION. | HIGHWAY | ECONOMIC DEVELOPMENT | 13 | FRENCH BROAD RIVER MPO | U-6251A | EXEMPT | ADHSL, L |  |  |  |  | 2022 | 2850000 |  |  | 2850000 | UNDER CONSTRUCTION.
BUNCOMBE | US 19/23 (SMOKEY PARK HIGHWAY) | NCDOT | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | HIGHWAY | ECONOMIC DEVELOPMENT | 13 | FRENCH BROAD RIVER MPO | U-6251B | EXEMPT | ADHSL, L, S | 2022 | 900000 |  |  | 2023 | 395000 |  |  | 1295000 | UNDER CONSTRUCTION.
BUNCOMBE | VARIOUS | NCDOT | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | W-5213DIV | DIVISION 13 | HSIP | 2020 | 50000 |  |  | 2020 | 700000 |  |  | 750000 | IN PROGRESS.
BUNCOMBE | SR 2002 (RICEVILLE ROAD) | NCDOT | US 70 TO SR 2419 (BULL CREEK ROAD) NEAR HAW CREEK. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | W-5213G | DIVISION 13 | HSIP |  |  |  |  | 2023 | 1225000 |  |  | 1225000 | UNDER CONSTRUCTION.
BUNCOMBE | US 25 | NCDOT | US 25 (MCDOWELL STREET) AT DOCTOR'S DRIVE/ASHEVILLE HIGH SCHOOL ENTRANCE. INSTALL PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | W-5813A | REGION G | HSIP |  |  |  |  | 2022 | 64000 |  |  | 64000 | UNDER CONSTRUCTION.
BUNCOMBE | SR 1332 | NCDOT | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | W-5813C | DIVISION 13 | HSIP | 2022 | 2000 |  |  | 2023 | 95000 |  |  | 97000 | UNDER CONSTRUCTION.
BUNCOMBE | US 25 | NCDOT | ALL SOULS CRESCENT AND US 25 ALT (LODGE STREET) INTERSECTIONS. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | W-5813D | REGION G | HSIP |  |  |  |  | 2023 | 96000 |  |  | 96000
BUNCOMBE | US 19-23-74 ALT | NCDOT | US 19-23-74 ALT (PATTON AVENUE) AT US 19-23 BUS (HAYWOOD ROAD)/SR 1319 (JOHNSTON ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS AND CURB RAMPS. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | W-5813E | REGION G | HSIP |  |  |  |  | 2023 | 115000 |  |  | 115000 | UNDER CONSTRUCTION.
BUNCOMBE | US 19-23-74 ALT | NCDOT | US 19-23-74 ALT (SMOKEY PARK HIGHWAY) AT OLD HAYWOOD ROAD. INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | W-5813F | REGION G | HSIP |  |  |  |  | 2023 | 70000 |  |  | 70000 | UNDER CONSTRUCTION.
BUNCOMBE | US 70; US 74 ALT | NCDOT | (1) US 70 (TUNNEL ROAD) AT OLD CHUNNS COVE ROAD, (2) US 74 ALT (S. TUNNEL ROAD) AT MAIN MALL ENTRANCE (EAST LEG), (3) US 74 ALT (S. TUNNEL ROAD) AT LOWER MALL ENTRANCE. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | HIGHWAY | SAFETY | 13 | FRENCH BROAD RIVER MPO | W-5813G | REGION G | HSIP |  |  |  |  | 2022 | 135000 |  |  | 135000 | UNDER CONSTRUCTION.
BUNCOMBE | SR 2806 | NCDOT | SR 2806 (GARREN CREEK ROAD) FROM SR 2815 TO SR 2786, NEAR FAIRVIEW. INSTALL SHOULDER GUARDRAIL. | HIGHWAY | SAFETY | 13 | LAND-OF-SKY RPO | W-5813I | DIVISION 13 | HSIP |  |  |  |  | 2022 | 460000 |  |  | 460000 | COMPLETE
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | ART BUSES AND OTHER ROUTINE CAPITAL ITEMS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 13 | FRENCH BROAD RIVER MPO | TA-6626 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 1439000 | 1439000
BUNCOMBE | BUNCOMBE MOUNTAIN MOBILITY - | BUNCOMBE MOUNTAIN MOBILITY - | REPLACEMENT VANS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 13 | FRENCH BROAD RIVER MPO | TA-6701 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 544000 | 544000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT LO-NO TRANSIT VEHICLE PURCHASE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 13 | FRENCH BROAD RIVER MPO | TA-6703 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 3365000 | 3365000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | BUSES AND BUS FACILITIES - BUS STOP IMPROVEMENT PROGRAM | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | TG-0011 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 1250000 | 1250000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | TRANSIT PREVENTATIVE MAINTENANCE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | TG-6183B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1000000 | 1000000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY BUNCOMBE - BUNCOMBE COUNTY TRANSIT ROUTINE CAPITAL COST OF CONTRACTING. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | TG-6786 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 1927000 | 1927000
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 13 | LAND-OF-SKY RPO | TK-6148 | PUBLIC TRANSIT | 5309, 5311, L, S | [6 empty] | 2020 | 1816000 | 1816000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | JARC OPERATIONS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | TM-5138 | PUBLIC TRANSIT | 3037, L | [6 empty] | 2021 | 734000 | 734000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | TRANSIT OPERATIONS | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 13 | FRENCH BROAD RIVER MPO | TO-4075 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 1965000 | 1965000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | BUNCOMBE COUNTY TRANSIT OPERATING ASSISTANCE. | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 13 | FRENCH BROAD RIVER MPO | TO-6154 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2251000 | 2251000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | PLANNING ASSISTANCE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 13 | FRENCH BROAD RIVER MPO | TP-5113 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 180000 | 180000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | PLANNING FOR MOUNTAIN MOBILITY | PUBLIC TRANSIT | PLANNING | 13 | FRENCH BROAD RIVER MPO | TP-5153 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 604000 | 604000
BUNCOMBE | ASHEVILLE REDEFINES TRANSIT | ASHEVILLE REDEFINES TRANSIT | 5310 TRADITIONAL PROJECTS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 13 | FRENCH BROAD RIVER MPO | TQ-6186 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 693000 | 693000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | 5310 OTHER PROJECTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 13 | FRENCH BROAD RIVER MPO | TQ-6187 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 688000 | 688000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT. 5310 ADMINISTRATIVE OVERSIGHT. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 13 | FRENCH BROAD RIVER MPO | TQ-7010 | PUBLIC TRANSIT | 5310 | [6 empty] | 2021 | 67000 | 67000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 13 | FRENCH BROAD RIVER MPO | TS-5102 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 36000 | 36000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | BO-2413 | DIVISION 13 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | HS-2013
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | HS-2413 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | R-5793 | DIVISION 13 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5213 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5713 | [11 empty] | COMPLETE
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5713DIV | DIVISION 13 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5713REG | REGION G | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5713SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5813
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 13. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | RC-2013 | DIVISION 13 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | RX-2013 | DIVISION 13 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | RX-2413 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, HAYWOOD | I-40 | NCDOT | US 74 (SMOKY MOUNTAIN EXPRESSWAY) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 13, 14 | FRENCH BROAD RIVER MPO | I-6054
BUNCOMBE, HAYWOOD | CITY OF ASHEVILLE | CITY OF ASHEVILLE | CITY OF ASHEVILLE ADMINISTRATIVE OVERSIGHT OF JARC PROJECTS IN THE ASHEVILLE UAZ | PUBLIC TRANSIT | LOCALLY SELECTED | 13, 14 | FRENCH BROAD RIVER MPO | TM-5163 | PUBLIC TRANSIT | L | [6 empty] | 2020 | 85000 | 85000
BUNCOMBE, HENDERSON | I-26 | NCDOT | NC 280 (EXIT 40) TO I-40 AT ASHEVILLE. ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 13, 14 | FRENCH BROAD RIVER MPO | I-4700 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 62468000 |  |  | 62468000 | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033
BUNCOMBE, HENDERSON | NC 191 (BREVARD ROAD) | NCDOT | NC 280 TO NC 112 (SARDIS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 13, 14 | FRENCH BROAD RIVER MPO | U-3403
BUNCOMBE, HENDERSON | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NCDOT | NC 280 (BOYLSTON HIGHWAY) TO SR 3498 (LEDBETTER ROAD). | HIGHWAY | STI (PRIORITIZATION) | 13, 14 | FRENCH BROAD RIVER MPO | U-3403A | NOT FUNDED | T | NOT FUNDED | 9000000 |  |  | NOT FUNDED | 17700000 |  |  | 26700000
BUNCOMBE, HENDERSON, HAYWOOD | VARIOUS | NCDOT | STBG-DA IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 13, 14 | FRENCH BROAD RIVER MPO | U-5100 | DIVISION 13, 14 | BGDA, L |  |  |  |  | 2020 | 40194000 |  |  | 40194000
BUNCOMBE, HENDERSON, HAYWOOD, MADISON | VARIOUS | NCDOT | FRENCH BROAD RIVER MPO TRANSPORTATION ALTERNATIVES (TA) PROGRAM. | BIKE/PED | LOCALLY SELECTED | 13, 14 | FRENCH BROAD RIVER MPO | U-5535 | DIVISION 13, 14 | L, TADA |  |  |  |  | 2020 | 5487000 |  |  | 5487000
BUNCOMBE, HENDERSON, HAYWOOD, MADISON | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 13, 14 | FRENCH BROAD RIVER MPO | HL-0090 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 0
BUNCOMBE, HENDERSON, HAYWOOD, MADISON | VARIOUS | NCDOT | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | HIGHWAY | LOCALLY SELECTED | 13, 14 | FRENCH BROAD RIVER MPO | U-5616 | DIVISION 13, 14 | BGDA, L | [6 empty] | 2020 | 4067000 | 4067000
BUNCOMBE, MADISON | I-26 (US 19/US 23) | NCDOT | SR 1781 (BROADWAY STREET) IN ASHEVILLE TO TENNESSEE STATE LINE AT SAMS GAP. MULTI-LANE FREEWAY, PART ON NEW LOCATION. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | A-0010 | [11 empty] | COORDINATE WITH B-4442, B-4443, B-4444.
BUNCOMBE, MADISON | I-26 (US 19/US 23) | NCDOT | SOUTH OF SR 2148 IN BUNCOMBE COUNTY TO NORTH OF NC 213 | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO | A-0010BA | [11 empty] | COMPLETE
BUNCOMBE, MADISON | US 25/70 | NCDOT | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | U-6173 | NOT FUNDED | BGANY | NOT FUNDED | 300000 | NOT FUNDED | 600000 | NOT FUNDED | 33249000 |  |  | 34149000
BURKE | MAIN AVENUE EAST | NCDOT | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 13 | GREATER HICKORY MPO | BL-0001 | DIVISION 13 | BGANY, BGDA, L | 2023 | 100000 |  |  | 2023 | 340000 | 2022 | 80000 | 520000 | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
BURKE | MORGANTON | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. | BIKE/PED | LOCALLY SELECTED | 13 | GREATER HICKORY MPO | EB-5807 | DIVISION 13 | BGANY, BGDA, L |  |  |  |  | 2021 | 1619000 |  |  | 1619000 | RIGHT-OF-WAY IN PROGRESS
BURKE | FONTA FLORA TRAIL | BURKE COUNTY | FONTA FLORA STATE TRAIL, INTERSECTION OF LAUREL RIDGE COURT AND NORTH POWERHOUSE ROAD TO THE PROPOSED HARRIS WHISNANT TRAILHEAD AT THE INTERSECTION OF HARRY WHISNANT ROAD AND COBB ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN FACILITY. | BIKE/PED | LOCALLY SELECTED | 13 | GREATER HICKORY MPO | EB-5827 | DIVISION 13 | BGANY, L | 2023 | 626000 | [6 empty] | 626000 | $410K IN STBG-DA FUNDS SWITCHED WITH $410K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
BURKE | HICKORY | HICKORY | RIVERWALK. CONSTRUCT MULTI-USE PATH FROM OLD LENOIR ROAD AT CITY OWNED PROPERTY TO END OF PROPOSED ROSALES BRIDGE. | BIKE/PED | LOCALLY SELECTED | 13 | GREATER HICKORY MPO | EB-5939 | DIVISION 13 | BGDA, L |  |  |  |  | 2023 | 6500000 |  |  | 6500000 | UNDER CONSTRUCTION.
BURKE | COLLEGE STREET MULTIMODAL CONNECTOR | MORGANTON | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | EB-5978 | DIVISION 13 | L, TAANY | 2022 | 100000 |  |  | 2024 | 2900000 |  |  | 3000000
BURKE | US 64/70 | NCDOT | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 13 | GREATER HICKORY MPO | B-5869 | REGION G | BFP, BGDA | 2021 | 3200000 | 2021 | 270000 | 2023 | 19200000 |  |  | 22670000 | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION.
BURKE | SR 1430 (HARLAND ROAD) | NCDOT | REPLACE BRIDGE 110145 OVER BRISTOL CREEK. | HIGHWAY | BRIDGES | 13 | GREATER HICKORY MPO | B-6011 | DIVISION 13 | BGOFF | 2022 | 65000 |  |  | 2022 | 725000 |  |  | 790000 | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION.
BURKE | SR 1913 (SUGAR LOAF ROAD) | NCDOT | REPLACE BRIDGE 110237 OVER ROCK CREEK. | HIGHWAY | BRIDGES | 13 | GREATER HICKORY MPO | B-6015 | DIVISION 13 | BGOFF | 2021 | 100000 |  |  | 2021 | 819000 |  |  | 919000 | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION.
BURKE | I-40 | NCDOT | REPLACE BRIDGES 110114 AND 110120 OVER SILVER CREEK. | HIGHWAY | BRIDGES | 13 | GREATER HICKORY MPO | BR-0130 | STATEWIDE MOBILITY | BFP |  |  |  |  | 2030 | 11800000 |  |  | 11800000
BURKE | NEW ROUTE | NCDOT | CONSTRUCT ACCESS ROAD INTO BURKE COUNTY INDUSTRIAL PARK. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | GREATER HICKORY MPO | HA-0001 | EXEMPT | ADHSL |  |  |  |  | 2023 | 1613000 | 2021 | 287000 | 1900000 | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000
BURKE | US 321 | NCDOT | BRIDGES #366 AND #367 AT THE CATAWBA COUNTY LINE. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 13 | GREATER HICKORY MPO | HS-2013A | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 92000 |  |  | 92000 | COMPLETE
BURKE | NC 181 | NCDOT | US 64 TO SR 1405 (BROWN MOUNTAIN BEACH ROAD). UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 13 | GREATER HICKORY MPO | HS-2013C | REGION G | HSIP |  |  |  |  | 2021 | 195000 |  |  | 195000 | COMPLETE
BURKE | US 64/NC 18 | NCDOT | NC 181 TO CALDWELL COUNTY LINE. UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 13 | GREATER HICKORY MPO | HS-2013E | REGION G | HSIP |  |  |  |  | 2021 | 385000 |  |  | 385000 | COMPLETE
BURKE | I-40 | NCDOT | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | I-5008 | REGION G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29600000 |  |  | 35400000 | PROJECT TO BE LET WITH I-5875.
BURKE | I-40 | NCDOT | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | I-5009 | REGION G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26200000 |  |  | 48700000
BURKE | I-40 | NCDOT | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | I-5874 | REGION G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17500000 |  |  | 19400000
BURKE | I-40 | NCDOT | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | I-5875 | REGION G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20700000 |  |  | 22800000 | PROJECT TO BE LET WITH I-5008
BURKE | I-40 | NCDOT | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | I-5971 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21500000 |  |  | 23000000
BURKE | I-40 | NCDOT | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | I-5975 | NOT FUNDED | NHP | NOT FUNDED | 2660000 | NOT FUNDED | 100000 | NOT FUNDED | 5200000 |  |  | 7960000
BURKE | I-40 | NCDOT | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | I-5990 | DIVISION 13 | NHP | 2023 | 2500000 | 2023 | 1100000 | 2024 | 9600000 |  |  | 13200000 | RIGHT-OF-WAY IN PROGRESS.
BURKE | I-40 | NCDOT | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | I-6058 | NOT FUNDED | NHP | NOT FUNDED | 300000 | NOT FUNDED | 1100000 | NOT FUNDED | 4300000 |  |  | 5700000
BURKE | SR 1001 (MALCOLM BOULEVARD) | NCDOT | US 70 TO CATAWBA RIVER. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | R-3430A | NOT FUNDED | T | NOT FUNDED | 10000000 | NOT FUNDED | 1600000 | NOT FUNDED | 20000000 |  |  | 31600000
BURKE | SR 1001 (CONNELLY SPRINGS ROAD) | NCDOT | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | HIGHWAY | BRIDGES | 13 | GREATER HICKORY MPO | R-3430B | HIGHWAY FUND | HFB | 2022 | 880000 | 2022 | 370000 | 2025 | 20900000 |  |  | 22150000 | RIGHT-OF-WAY IN PROGRESS.
BURKE | SR 1687 (GOAT FARM ROAD) | NCDOT | IMPROVE EXISTING SR 1687 (GOAT FARM ROAD) ACCESS ROAD INTO THE PROPOSED INDUSTRIAL PARK. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | GREATER HICKORY MPO | R-5967 | EXEMPT | ADHSL, L |  |  |  |  | 2023 | 2152000 |  |  | 2152000 | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY. UNDER CONSTRUCTION.
BURKE | NC 181 | NCDOT | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | U-5836 | REGION G | T | 2027 | 3000000 |  |  | 2029 | 7800000 |  |  | 10800000
BURKE | NC 181 | NCDOT | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | U-5978 | NOT FUNDED | T | NOT FUNDED | 8500000 | NOT FUNDED | 1700000 | NOT FUNDED | 14000000 |  |  | 24200000
BURKE | MORGANTON | NCDOT | SOUTH STERLING STREET TO WEST PARKER ROAD. CONSTRUCT CONNECTOR ROAD. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | GREATER HICKORY MPO | U-6057 | EXEMPT | [10 empty] | UNDER CONSTRUCTION. ARC PROJECT NO. 18703. AWARD AMOUNT = $1,374,714.
BURKE | US 64 (BURKEMONT AVENUE) | NCDOT | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | U-6123 | NOT FUNDED | NHP | NOT FUNDED | 200000 | NOT FUNDED | 300000 | NOT FUNDED | 2000000 |  |  | 2500000
BURKE | NC 126 | NCDOT | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | GREATER HICKORY MPO | U-6164 | NOT FUNDED | BGLT5 | NOT FUNDED | 4000000 | NOT FUNDED | 6500000 | NOT FUNDED | 36300000 |  |  | 46800000
BURKE, CALDWELL | US 321 | NCDOT | INTERIM STRUCTURE IMPROVEMENTS ON US 321 SOUTHBOUND BRIDGE OVER LAKE HICKORY. | HIGHWAY | BRIDGES | 11, 13 | GREATER HICKORY MPO | U-4700AA | STATEWIDE MOBILITY | NHP |  |  |  |  | 2022 | 2400000 |  |  | 2400000 | UNDER CONSTRUCTION.
BURKE, MITCHELL, RUTHERFORD | US 321, US 70, US 19E, US 221A | NCDOT | UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 13 | GREATER HICKORY MPO, FOOTHILLS RPO, HIGH COUNTRY RPO | HS-2013F | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 348000 |  |  | 348000 | COMPLETE
DAVIDSON, ROWAN | I-85 | NCDOT | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO NORTH OF NC 150 IN DAVIDSON COUNTY, INCLUDING YADKIN RIVER BRIDGE | HIGHWAY | PRE-STI (HISTORIC) | 9 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO | I-2304AC | EXEMPT | NHP | 2009 | 1066000 |  |  | 2010 | 8220000 |  |  | 9286000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC
CABARRUS | VARIOUS | KANNAPOLIS | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73. CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD). CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP | HIGHWAY | ECONOMIC DEVELOPMENT | 10 | CABARRUS-ROWAN MPO | U-6098 | DIVISION 10 | T |  |  |  |  | 2019 | 850000 |  |  | 850000 | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION.
ROWAN | I-85 | NCDOT | US 29 / US 601 IN CHINA GROVE TO US 601 (JAKE ALEXANDER BOULEVARD) IN SALISBURY AND FROM SOUTH OF US 52 IN SALISBURY TO NORTH OF SR 2120 (LONG FERRY ROAD) IN SPENCER. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | CABARRUS-ROWAN MPO | I-5858 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 12012000 |  |  | 12012000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033
ROWAN | NEW ROUTE | NCDOT | SR 2576 (BENDIX DRIVE) TO SR 1006 (FAITH ROAD) IN SALISBURY. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | U-5820A | DIVISION 9 | T |  |  |  |  | 2019 | 2609000 |  |  | 2609000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.023 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONCORD REGIONAL AIRPORT (JQF) | REHABILITATE APRON AND TAXIWAY PAVEMENT. | AVIATION | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | AV-5890 | REGION E | T |  |  |  |  | 2020 | 300000 |  |  | 300000 | COMPLETE.
CABARRUS | CONCORD | CONCORD | DOWNTOWN PEDESTRIAN SIGNAL UPGRADES. | BIKE/PED | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | EB-5902 | DIVISION 10 | L, TADA |  |  |  |  | 2020 | 312000 |  |  | 312000 | COMPLETE.
CABARRUS | CONCORD | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. | BIKE/PED | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | EB-5903 | DIVISION 10 | CMAQ, L, TADA |  |  |  |  | 2020 | 866000 |  |  | 866000 | COMPLETE.
CABARRUS, ROWAN | VARIOUS | CONCORD | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | HIGHWAY | OTHER | 9, 10 | CABARRUS-ROWAN MPO | C-5603 | EXEMPT | CMAQ, L | 2020 | 309000 |  |  | 2020 | 1848000 | 2020 | 927000 | 3084000 | IN PROGRESS
CABARRUS, ROWAN | VARIOUS | NCDOT | STBG-DA IN THE CABARRUS-ROWAN METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. | HIGHWAY | LOCALLY SELECTED | 9, 10 | CABARRUS-ROWAN MPO | U-5614 | DIVISION 9, 10 | BGDA, L |  |  |  |  | 2020 | 57539000 |  |  | 57539000 | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP
ROWAN | NEW ROUTE | NCDOT | SR 1006 (FAITH ROAD) TO US 52 (EAST INNES STREET) IN SALISBURY. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | U-5820B | DIVISION 9 | T |  |  |  |  | 2020 | 1100000 |  |  | 1100000
CABARRUS | US 29/US 601 | NCDOT | REPLACE BRIDGE 120066 AND BRIDGE 120069 OVER SOUTHERN RAILROAD. | HIGHWAY | TRANSITION | 10 | CABARRUS-ROWAN MPO | B-5136 | REGION E | T |  |  |  |  | 2021 | 2790000 |  |  | 2790000 | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
CABARRUS | SR 2894 (CONCORD MILLS BOULEVARD) | NCDOT | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | U-5806 | DIVISION 10 | T |  |  |  |  | 2021 | 10380000 | 2021 | 1755000 | 12135000 | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 9 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO | HS-2009A | DIVISION 9 | HSIP |  |  |  |  | 2021 | 1900000 |  |  | 1900000
ROWAN | SR 2120 (LONG FERRY ROAD) | NCDOT | SR 2182 (I-85 SERVICE ROAD) NEAR SPENCER. CONSTRUCT RIGHT-TURN LANE ON SR 2120, AND CONSTRUCT CUL-DE-SAC, REMOVE RESIDUAL PAVEMENT AND STRENGTHEN REMAINING PAVEMENT ON SR 2182. | HIGHWAY | ECONOMIC DEVELOPMENT | 9 | CABARRUS-ROWAN MPO | U-6237 | DIVISION 9 | T |  |  | 2021 | 50000 | 2021 | 365000 |  |  | 415000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM
CABARRUS | SR 1132 (MIAMI CHURCH ROAD) | NCDOT | REPLACE BRIDGE 120137 OVER DUTCH BUFFALO CREEK. | HIGHWAY | BRIDGES | 10 | CABARRUS-ROWAN MPO | B-5375 | DIVISION 10 | BGOFF |  |  |  |  | 2022 | 1573000 |  |  | 1573000 | UNDER CONSTRUCTION.
CABARRUS, ROWAN | CONCORD KANNAPOLIS AREA TRANSIT | CONCORD KANNAPOLIS AREA TRANSIT | EXPANSION BUS | PUBLIC TRANSIT | LOCALLY SELECTED | 9, 10 | CABARRUS-ROWAN MPO | TL-0005 | DIVISION 9, 10 | BGDA, L |  |  |  |  | 2022 | 725000 |  |  | 725000
ROWAN | SR 1724 (HURLEY SCHOOL ROAD) | NCDOT | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 9 | CABARRUS-ROWAN MPO | B-5772 | DIVISION 9 | BGOFF | 2021 | 77000 | 2021 | 31000 | 2022 | 1950000 |  |  | 2058000 | UNDER CONSTRUCTION
ROWAN | VARIOUS | SALISBURY | CITY OF SALISBURY SIGNAL SYSTEM UPGRADE. | HIGHWAY | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | HL-0005 | DIVISION 9 | BGDA, L |  |  |  |  | 2022 | 429000 |  |  | 429000
ROWAN | SR 2528 (JULIAN ROAD) | NCDOT | US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2667 (SUMMIT PARK DRIVE) IN SALISBURY. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | U-5738 | DIVISION 9 | T |  |  |  |  | 2022 | 14995000 |  |  | 14995000 | UNDER CONSTRUCTION
ALEXANDER, CATAWBA, IREDELL | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ON APPROXIMATELY 65 SECONDARY ROADS. | HIGHWAY | SAFETY | 12 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | HS-2012D | DIVISION 12 | HSIP |  |  |  |  | 2023 | 3615000 |  |  | 3615000 | UNDER CONSTRUCTION.
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. | AVIATION | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | AV-5892 | REGION E | O, T |  |  |  |  | 2023 | 2170000 |  |  | 2170000 | OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT
CABARRUS | US 29 US 601 | NCDOT | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | HIGHWAY | BRIDGES | 10 | CABARRUS-ROWAN MPO | B-5808 | REGION E | BFP, NHPB | 2021 | 255000 | 2021 | 1156000 | 2023 | 10100000 |  |  | 11511000 | UNDER CONSTRUCTION.
CABARRUS | NC 49 | NCDOT | PRINCE CIRCLE TO WEST OF GENERAL SERVICES DRIVE SW. CONVERT EXISTING FULL ACCESS CROSSOVER TO RCI WITH LEFTOVERS AND SIGNALIZED U-TURN LEFTOVERS. | HIGHWAY | ECONOMIC DEVELOPMENT | 10 | CABARRUS-ROWAN MPO | HE-0015 | REGION E | T |  |  |  |  | 2023 | 2000000 |  |  | 2000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841.
CABARRUS | I-85 | NCDOT | ITS FOR I-3802 A | HIGHWAY | PRE-STI (HISTORIC) | 10 | CABARRUS-ROWAN MPO | I-3802AA | PRE-STI (TRANSITION) | CMAQ |  |  |  |  | 2023 | 1630000 |  |  | 1630000 | UNDER CONSTRUCTION.
CABARRUS | CONCORD | CONCORD | PURCHASE NEW 35 FOOT HYBRID ELECTRIC HEAVY DUTY LOW FLOOR BUS | PUBLIC TRANSIT | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | TL-0021 | DIVISION 10 | BGDACV, L |  |  |  |  | 2023 | 725000 |  |  | 725000
CABARRUS | NORFOLK SOUTHERN MAINLINE | NCDOT | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. | RAIL | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | Y-4810K | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 19170000 |  |  | 19170000 | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN
CABARRUS, ROWAN | VARIOUS | NCDOT | CABARRUS ROWAN MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | BIKE/PED | LOCALLY SELECTED | 9, 10 | CABARRUS-ROWAN MPO | U-5545 | DIVISION 9, 10 | L, TADA |  |  |  |  | 2023 | 6223000 |  |  | 6223000
CABARRUS, ROWAN | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CABARRUS-ROWAN PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 9, 10 | CABARRUS-ROWAN MPO | HL-0093 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 3057000 |  |  | 3057000
ROWAN | GRANTS CREEK GREENWAY | SALISBURY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO WILTSHIRE VILLAGE. CONSTRUCT MULTIUSE PATH. | BIKE/PED | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | EB-5619B | DIVISION 9 | BGDA, L | 2020 | 825000 |  |  | 2023 | 1439000 |  |  | 2264000 | RIGHT OF WAY IN PROGRESS
ROWAN | OLD CONCORD ROAD | SALISBURY | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. | HIGHWAY | OTHER | 9 | CABARRUS-ROWAN MPO | C-5603D | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 369000 |  |  | 369000
ROWAN | BRENNER AVENUE | SALISBURY | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. | HIGHWAY | OTHER | 9 | CABARRUS-ROWAN MPO | C-5603H | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 643000 |  |  | 643000
ROWAN | NC 152 | NCDOT | NC 152, INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. INTERMEDIATE INTERSECTION IMPROVEMENTS. WIDEN PAVEMENT AND CONSTRUCT TURN LANES FOR PHASE I OF ROADWAY IMPROVEMENTS. | HIGHWAY | ECONOMIC DEVELOPMENT | 9 | CABARRUS-ROWAN MPO | HE-0009A | DIVISION 9 | T |  |  |  |  | 2023 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION. CONSTRUCTION BY STATE FORCES. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS.
ROWAN | SR 1007 (JAKE ALEXANDER BOULEVARD) | NCDOT | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | HIGHWAY | SAFETY | 9 | CABARRUS-ROWAN MPO | HS-2009D | DIVISION 9 | HSIP | 2022 | 50000 | 2022 | 20000 | 2023 | 350000 |  |  | 420000 | UNDER CONSTRUCTION
ROWAN | SR 1002 (OLD CONCORD ROAD) | NCDOT | SR 1002 (OLD CONCORD ROAD) FROM JAKE ALEXANDER BOULEVARD IN SALISBURY TO THE CABARRUS COUNTY LINE. INSTALL PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 9 | CABARRUS-ROWAN MPO | HS-2009E | DIVISION 9 | HSIP |  |  |  |  | 2023 | 396000 |  |  | 396000
ROWAN | NORFOLK SOUTHERN | SALISBURY | SALISBURY NORFOLK SOUTHERN CROSSOVER RELOCATION. | RAIL | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | P-5726B | REGION D | T |  |  |  |  | 2023 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION
CABARRUS | NORTH WASHINGTON STREET | MOUNT PLEASANT | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | BIKE/PED | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | BL-0043 | EXEMPT | CMAQ, L |  |  |  |  | 2024 | 524000 | 2022 | 115000 | 639000
CABARRUS | VARIOUS CONCORD | CONCORD | ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. GLENN STREET NORTHWEST FROM ELM AVENUE NORTHWEST TO ACADEMY AVENUE NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. INSTALL SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | BL-0087 | DIVISION 10 | L, TADA |  |  |  |  | 2024 | 1625000 |  |  | 1625000
CABARRUS | KANNAPOLIS | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | EB-5844 | DIVISION 10 | CMAQ, L, TAANY | 2023 | 400000 |  |  | 2024 | 1334000 |  |  | 1734000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | US 601 | CONCORD | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION | HIGHWAY | OTHER | 10 | CABARRUS-ROWAN MPO | C-5603I | EXEMPT | CMAQ, L | 2023 | 250000 |  |  | 2024 | 1145000 |  |  | 1395000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | NC 24/27 | NCDOT | SR 1120 (BETHEL SCHOOL ROAD) INTERSECTION. INSTALL A REDUCED CONFLICT INTERSECTION (RCI) WITH UNSIGNALIZED BULBOUTS. | HIGHWAY | SAFETY | 10 | CABARRUS-ROWAN MPO | HS-2010D | REGION E | HSIP | 2023 | 301000 |  |  | 2024 | 392000 |  |  | 693000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) | NCDOT | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | U-5761 | REGION E | T |  |  |  |  | 2024 | 8100000 |  |  | 8100000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | SR 1002 (OLD SALISBURY CONCORD ROAD) | NCDOT | SR 2400 (IRISH POTATO ROAD) NEAR KANNAPOLIS. CONSTRUCT SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 10 | CABARRUS-ROWAN MPO | W-5710AO | DIVISION 10 | HSIP |  |  |  |  | 2024 | 1000000 |  |  | 1000000
CABARRUS | KANNAPOLIS | NCDOT | CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL, SIGNALING EQUIPMENT | RAIL | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | P-5725 | REGION E | T |  |  |  |  | 2024 | 10099000 |  |  | 10099000 | RIGHT-OF-WAY IN PROGRESS
ROWAN | GRANTS CREEK GREENWAY | SALISBURY | WILTSHIRE VILLAGE TO KELSEY SCOTT PARK. CONSTRUCT MULTIUSE PATH. | BIKE/PED | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | EB-5619C | DIVISION 9 | BGDA, L |  |  |  |  | 2024 | 2352000 | 2023 | 368000 | 2720000
ROWAN | THIRD STREET GREENWAY | SPENCER | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | EB-5861 | DIVISION 9 | L, TAANY |  |  |  |  | 2024 | 4287000 | 2023 | 185000 | 4472000
ROWAN | NC 152 | NCDOT | WIDEN PAVEMENT AND CONSTRUCT ROUNDABOUT AT THE INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. | HIGHWAY | ECONOMIC DEVELOPMENT | 9 | CABARRUS-ROWAN MPO | HE-0009 | DIVISION 9 | T |  |  |  |  | 2024 | 3900000 | 2022 | 600000 | 4500000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS.
ROWAN | BRENNER AVENUE | SALISBURY | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | HIGHWAY | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | HL-0049 | DIVISION 9 | BGDACV, L | 2023 | 14000 |  |  | 2024 | 830000 | 2022 | 181000 | 1025000
ROWAN | US 29 MAIN STREET | SALISBURY | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | HL-0064 | DIVISION 9 | BGDA, L |  |  | 2024 | 3261000 | 2024 | 6021000 |  |  | 9282000
ROWAN | EAST FISHER STREET | SALISBURY | REPLACE BRIDGE 138 OVER NORFOLK SOUTHERN RAILROAD BETWEEN SOUTH LONG STREET AND SOUTH LEE STREET IN SALISBURY. | HIGHWAY | MUNICIPAL BRIDGE | 9 | CABARRUS-ROWAN MPO | HM-0001 | DIVISION 9 | BFPOFF |  |  |  |  | 2024 | 2000000 |  |  | 2000000
ROWAN | NC 153 (RICE STREET) | NCDOT | NC 153 (RICE STREET) AT SR 1197 (CANNON FARM ROAD / MT MORIAH CHURCH ROAD) IN CHINA GROVE | HIGHWAY | SAFETY | 9 | CABARRUS-ROWAN MPO | W-5709E | REGION D | HSIP |  |  |  |  | 2024 | 700000 |  |  | 700000
ROWAN | NORFOLK SOUTHERN | NCDOT | SALISBURY TRAIN STATION SECOND PLATFORM AND PEDESTRIAN UNDERPASS. | RAIL | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | P-5726A | REGION D | T |  |  |  |  | 2024 | 2500000 |  |  | 2500000 | UNDER CONSTRUCTION
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) | AVIATION | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | AV-5731 | REGION E | O, T |  |  |  |  | 2025 | 7917000 |  |  | 7917000
CABARRUS | CLARKE CREEK GREENWAY | CONCORD | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | BIKE/PED | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | BL-0060 | EXEMPT | CMAQ, L |  |  |  |  | 2025 | 1938000 |  |  | 1938000
CABARRUS | SR 1138 (HICKORY RIDGE ROAD) | HARRISBURG | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | BL-0086 | DIVISION 10 | L, TADA | 2024 | 172000 | 2024 | 56000 | 2025 | 1563000 | 2024 | 287000 | 2078000
CABARRUS | SR 1394 (POPLAR TENT ROAD) | CONCORD | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | HIGHWAY | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | HL-0001 | DIVISION 10 | BGANY, BGDA, L | 2023 | 5520000 |  |  | 2025 | 7850000 | 2022 | 1710000 | 15080000 | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022.
CABARRUS | NC 49 | HARRISBURG | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | HL-0062 | EXEMPT | BGDA, L | 2024 | 955000 | 2024 | 382000 | 2025 | 6445000 | 2023 | 1396000 | 9178000 | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS.
CABARRUS | SR 1173 (CALDWELL ROAD) | HARRISBURG | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | HIGHWAY | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | HL-0063 | DIVISION 10 | BGDA, L | 2024 | 1108000 | 2024 | 10000 | 2025 | 4156000 | 2023 | 833000 | 6107000
CABARRUS | NC 24/27 | NCDOT | NC 24/27 AND SR 1100 (PINE BLUFF ROAD/ REED MINE ROAD) NEAR LOCUST. INSTALL A REDUCED CONFLICT INTERSECTION. | HIGHWAY | SAFETY | 10 | CABARRUS-ROWAN MPO | HS-2010F | REGION E | HSIP | 2023 | 5000 |  |  | 2025 | 747000 |  |  | 752000
CABARRUS | NC 49 | NCDOT | SR 1155 (ZION CHURCH ROAD) INTERSECTION NEAR CONCORD. INSTALL REDUCED CONFLICT INTERSECTION WITH SIGNALIZED BULBOUTS. | HIGHWAY | SAFETY | 10 | CABARRUS-ROWAN MPO | HS-2010H | STATEWIDE MOBILITY | HSIP | 2024 | 105000 | 2024 | 70000 | 2025 | 1949000 |  |  | 2124000
CABARRUS | US 29 | NCDOT | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | U-5956 | REGION E | T | 2022 | 3400000 | 2022 | 2100000 | 2025 | 11800000 |  |  | 17300000 | RIGHT-OF-WAY IN PROGRESS.
ROWAN | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) | SALISBURY | WEST OF KELSEY SCOTT PARK GREENWAY TO END OF SALISBURY MALL GREENWAY/CAROLINA THREAD TRAIL. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | BL-0034 | EXEMPT | CMAQ, L | 2024 | 90000 |  |  | 2025 | 604000 | 2022 | 151000 | 845000
ROWAN | GRANITE QUARRY VARIOUS | GRANITE QUARRY | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | BL-0088 | REGION D | L, TADA | 2024 | 90000 | 2024 | 10000 | 2025 | 380000 | 2024 | 70000 | 550000
ROWAN | RAILROAD NORFOLK SOUTHERN | NCDOT | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | RAIL | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | P-5726 | REGION D | L, T |  |  |  |  | 2025 | 9600000 |  |  | 9600000
CABARRUS | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | NCDOT | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | BIKE/PED | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | EB-5732 | DIVISION 10 | L, TAANY | 2025 | 100000 |  |  | 2026 | 6000000 |  |  | 6100000
ROWAN | NORFOLK SOUTHERN | NCDOT | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | RAIL | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | P-5733 | DIVISION 9 | L, T | 2025 | 600000 |  |  | 2026 | 2600000 |  |  | 3200000
CABARRUS | SR 1394 (POPLAR TENT ROAD) | NCDOT | EAST OF I-85 TO GEORGE LILES PARKWAY. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | U-3415A | DIVISION 10 | T | 2025 | 12900000 | 2025 | 900000 | 2028 | 27713000 |  |  | 41513000
ROWAN, CABARRUS | US 52 | NCDOT | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. UPGRADE ROADWAY AND ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 9, 10 | CABARRUS-ROWAN MPO | R-5860A | DIVISION 9, 10 | T | 2027 | 7048000 | 2027 | 846000 | 2029 | 39320000 |  |  | 47214000
CABARRUS | GEORGE LILES PARKWAY | NCDOT | NC 49 TO SR 1304 (ROBERTA ROAD) | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | R-2246A | DIVISION 10 | T | 2028 | 4100000 | 2028 | 2900000 | 2030 | 24100000 |  |  | 31100000
ROWAN | NEW ROUTE | NCDOT | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTI-LANE RIGHT OF WAY. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | U-5901 | DIVISION 9 | T | 2027 | 8900000 | 2027 | 6900000 | 2030 | 39502000 |  |  | 55302000
ROWAN | SR 2739 (NORTH MAIN STREET) | KANNAPOLIS | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | EB-5921 | DIVISION 9 | L, TAANY | 2028 | 630000 |  |  | 2031 | 2100000 | 2027 | 450000 | 3180000 | COORDINATE WITH U-6062
ROWAN, CABARRUS | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | NCDOT | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | HIGHWAY | STI (PRIORITIZATION) | 9, 10 | CABARRUS-ROWAN MPO | U-6062 | DIVISION 9, 10 | T | 2028 | 28900000 | 2028 | 3900000 | 2031 | 28399000 |  |  | 61199000 | COORDINATE WITH EB-5921
CABARRUS | US 29 | NCDOT | REPLACE BRIDGE 120014 AND 120019 OVER ROCKY RIVER AND ACCESS ROAD. | HIGHWAY | BRIDGES | 10 | CABARRUS-ROWAN MPO | B-5123 | REGION E | [10 empty] | COMPLETE
CABARRUS | KANNAPOLIS | KANNAPOLIS | IRISH BUFFALO CREEK GREENWAY IN KANNAPOLIS. CONSTRUCT GREENWAY. | HIGHWAY | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | C-5161 | EXEMPT | [10 empty] | UNDER CONSTRUCTION
CABARRUS | SR 1643 (BETHPAGE ROAD) | KANNAPOLIS | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS | HIGHWAY | OTHER | 10 | CABARRUS-ROWAN MPO | C-5603F | EXEMPT | CMAQ, L
CALDWELL | HUDSON US 321A (MAIN STREET)/ | NCDOT | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | BIKE/PED | LOCALLY SELECTED | 11 | GREATER HICKORY MPO | BL-0002 | DIVISION 11 | BGANY, BGDA, L | 2024 | 24000 |  |  | 2024 | 440000 | 2022 | 80000 | 544000 | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CALDWELL | LENIOR GREENWAY | LENOIR | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 11 | GREATER HICKORY MPO | BL-0065 | DIVISION 11 | BGDA, L | 2024 | 281000 |  |  | 2025 | 1581000 | 2023 | 306000 | 2168000
CALDWELL | LENOIR | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 11 | GREATER HICKORY MPO | EB-5806 | DIVISION 11 | BGANY, BGDACV, L, TADA | 2021 | 120000 |  |  | 2023 | 1000000 |  |  | 1120000 | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION.
CALDWELL | US 321 | NCDOT | REPLACE BRIDGE 130367 OVER CATAWBA RIVER. | HIGHWAY | BRIDGES | 11 | GREATER HICKORY MPO | B-4450 | [11 empty] | TO BE CONSTRUCTED WITH U-4700
CALDWELL | SR 1514 | NCDOT | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | HIGHWAY | BRIDGES | 11 | GREATER HICKORY MPO | HB-0056 | DIVISION 11 | DP, HFB | 2026 | 140000 |  |  | 2027 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | SR 1356 | NCDOT | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | HIGHWAY | BRIDGES | 11 | GREATER HICKORY MPO | HB-0057 | DIVISION 11 | DP, HFB | 2023 | 140000 |  |  | 2024 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | SR 1356 | NCDOT | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | HIGHWAY | BRIDGES | 11 | GREATER HICKORY MPO | HB-0058 | DIVISION 11 | DP, HFB | 2023 | 140000 |  |  | 2024 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | SR 1356 | NCDOT | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | HIGHWAY | BRIDGES | 11 | GREATER HICKORY MPO | HB-0059 | DIVISION 11 | DP, HFB | 2023 | 140000 |  |  | 2024 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | SR 1356 | NCDOT | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | HIGHWAY | BRIDGES | 11 | GREATER HICKORY MPO | HB-0060 | DIVISION 11 | DP, HFB | 2023 | 182000 |  |  | 2024 | 1040000 |  |  | 1222000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | SR 1574 | NCDOT | REPLACE BRIDGE 130349 OVER JONES CREEK. | HIGHWAY | BRIDGES | 11 | GREATER HICKORY MPO | HB-0061 | DIVISION 11 | DP, HFB | 2026 | 112000 |  |  | 2027 | 640000 |  |  | 752000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | NCDOT | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | HIGHWAY | FEDERAL LANDS ACCESS PROGRAM | 11 | GREATER HICKORY MPO | HF-0001 | EXEMPT | FLAP, S(M) |  |  |  |  | 2022 | 235000 | 2022 | 5000 | 240000 | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION.
CALDWELL | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | NCDOT | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | HIGHWAY | FEDERAL LANDS ACCESS PROGRAM | 11 | GREATER HICKORY MPO | HF-0003 | EXEMPT | FLAP, S(M) |  |  |  |  | 2024 | 1575000 | 2022 | 175000 | 1750000 | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. STATE MATCH ARE HIGHWAY FUNDS.
CALDWELL | SR 1001 (CONNELLY SPRINGS ROAD) | NCDOT | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | R-3430C | DIVISION 11 | BGANY | 2028 | 27500000 | 2028 | 4000000 | 2031 | 47000000 |  |  | 78500000
CALDWELL | US 64/NC 90/NC 18 (WILKESBORO BLVD) | NCDOT | INTERSECTION OF US 64/NC 90/NC 18 (WILKESBORO BOULEVARD) AND US 64/NC 90 (TAYLORSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | R-5745 | DIVISION 11 | T |  |  |  |  | 2019 | 1695000 |  |  | 1695000 | COMPLETE; BUILD NC BOND FUNDING: $1.313M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE)
CALDWELL | GRANITE FALLS | NCDOT | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 11 | GREATER HICKORY MPO | R-5775 | EXEMPT | BGANY, BGDA, S(M) |  |  |  |  | 2022 | 1935000 |  |  | 1935000 | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE MATCH IS SPOT SAFETY (SS-4911 AL); $487KM IN BGANY USED AS PART OF FUND SWAP.
CALDWELL | US 321 | NCDOT | US 321A TO SR 1108 (MISSION ROAD) | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-4700B | NOT FUNDED | NHP | NOT FUNDED | 35000000 | NOT FUNDED | 4000000 | NOT FUNDED | 57500000 |  |  | 96500000
CALDWELL | US 321 | NCDOT | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-4700C | NOT FUNDED | NHP | NOT FUNDED | 5000000 | NOT FUNDED | 2000000 | NOT FUNDED | 12000000 |  |  | 19000000
CALDWELL | US 321 | NCDOT | SR 1160 (MOUNT HERMAN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-4700CA | REGION F | NHP | 2020 | 420000 |  |  | 2023 | 4101000 |  |  | 4521000 | DESIGN BY DIVISION. UNDER CONSTRUCTION.
CALDWELL | US 321 | NCDOT | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-4700CB | STATEWIDE MOBILITY | NHP | 2020 | 400000 | 2020 | 100000 | 2024 | 9200000 |  |  | 9700000 | RIGHT-OF-WAY IN PROGRESS.
CALDWELL | US 321 | NCDOT | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-4700CC | STATEWIDE MOBILITY | NHP | 2020 | 450000 | 2020 | 100000 | 2024 | 5900000 |  |  | 6450000 | RIGHT-OF-WAY IN PROGRESS.
CALDWELL | US 64/ NC 18 | NCDOT | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-6033 | DIVISION 11 | T | 2019 | 400000 | 2019 | 450000 | 2023 | 2246000 |  |  | 3096000 | UNDER CONSTRUCTION.
CALDWELL | US 321 ALT | NCDOT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-6034 | DIVISION 11 | BGANY | 2024 | 9000000 | 2024 | 3000000 | 2026 | 14400000 |  |  | 26400000
CALDWELL | SR 1002 (DUDLEY SHOALS ROAD) | NCDOT | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-6035 | DIVISION 11 | T | 2019 | 200000 | 2019 | 230000 | 2024 | 1700000 |  |  | 2130000 | RIGHT-OF-WAY IN PROGRESS
CALDWELL | SR 1109 (PINEWOOD ROAD) | NCDOT | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-6036 | DIVISION 11 | T | 2019 | 1500000 | 2019 | 400000 | 2024 | 12599000 |  |  | 14499000 | RIGHT-OF-WAY IN PROGRESS
CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) | NCDOT | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-6157 | DIVISION 11 | BGANY | 2023 | 9200000 | 2023 | 10200000 | 2025 | 23901000 |  |  | 43301000 | RIGHT-OF-WAY IN PROGRESS.
CALDWELL | US 321 | NCDOT | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | HIGHWAY | STI (PRIORITIZATION) | 11 | GREATER HICKORY MPO | U-6161 | DIVISION 11 | NHP | 2025 | 800000 | 2025 | 200000 | 2027 | 4000000 |  |  | 5000000 | COORDINATE WITH U-4700A
CALDWELL | SR 1159 (PLEASANT HILL ROAD) | NCDOT | CWCY CROSSING 729801L IN HUDSON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 11 | GREATER HICKORY MPO | RX-2011A | DIVISION 11 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
CALDWELL, BURKE | SR 1001 (MALCOLM BLVD/ CONNELLY SPRINGS ROAD) | NCDOT | US 70 TO SR 1933 (SOUTH-WEST BOULEVARD) IN LENOIR. MODERNIZE ROADWAY TO INCLUDE BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 11, 13 | GREATER HICKORY MPO | R-3430
CALDWELL, CATAWBA, BURKE | US 321 | NCDOT | NORTH OF US 70 IN HICKORY TO SR 1933 (SOUTHWEST BOULEVARD). WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 11, 12, 13 | GREATER HICKORY MPO | U-4700 | [11 empty] | INCLUDES B-4450.
CALDWELL, CATAWBA, LINCOLN, MECKLENBURG, WATAUGA | COACH AMERICA | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 10, 11, 12 |  | TI-6101 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 2384000 | 2384000 | FUNDS AUTHORIZED IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | BO-2411 | DIVISION 11 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | HS-2011
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | INSTALL LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | HS-2011A | DIVISION 11 | HSIP |  |  |  |  | 2021 | 1816000 |  |  | 1816000 | UNDER CONSTRUCTION.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | INSTALL LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | HS-2011D | DIVISION 11 | HSIP |  |  |  |  | 2021 | 855000 |  |  | 855000 | UNDER CONSTRUCTION.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | HS-2411 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | R-5791 | DIVISION 11 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | DIVISION 11 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5211 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5711
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5711DIV | DIVISION 11 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5711REG | REGION F | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5711SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5811 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 11. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | RC-2011 | DIVISION 11 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | RX-2011 | DIVISION 11
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | RX-2411 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CAMDEN | US 17 (FUTURE I-87) | NCDOT | PASQUOTANK COUNTY LINE TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 1 | ALBEMARLE RPO | I-6026 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 8400000 |  |  | 8400000
CAMDEN | SR 1224 (OLD SWAMP ROAD) | NCDOT | 0.15 SOUTH OF SR 1225 (LILLY ROAD) TO 0.25 MILES NORTH OF SR 1225 (LILLY ROAD). | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5717A | DIVISION 1 | [10 empty] | UNDER CONSTRUCTION.
CAMDEN | SR 1224 (OLD SWAMP ROAD) | NCDOT | REPLACE BRIDGE 140013 OVER JOYCE CREEK. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5717B | DIVISION 1 | T |  |  |  |  | 2024 | 1400000 |  |  | 1400000
CAMDEN | NC 343 | NCDOT | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5807 | DIVISION 1 | BGLT5 | 2024 | 508000 | 2024 | 9232000 | 2027 | 19700000 |  |  | 29440000
CAMDEN, CHOWAN, CURRITUCK, PASQUOTANK, PERQUIMANS | ALBEMARLE REGIONAL HEALTH SERVICE | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1 | ALBEMARLE RPO | TK-6104 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1656000 | 1656000 | FUNDS AUTHORIZED IN PROGRESS
CAMDEN, CURRITUCK | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NCDOT | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN EXISTING LANES, WIDEN EXISTING SHOULDERS, AND INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5717 | DIVISION 1 | T |  |  |  |  | 2024 | 23700000 |  |  | 23700000 | RIGHT-OF-WAY IN PROGRESS.
CARTERET | MICHAEL J. SMITH FIELD (MRH) | MICHAEL J. SMITH FIELD (MRH) | FULL PARALLEL TAXIWAY 8-26. | AVIATION | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | AV-5746 | DIVISION 2 | [10 empty] | COMPLETE
CARTERET | US 70 | NCDOT | REPLACE BRIDGE 150033 OVER NORTH RIVER AND REPAIRS TO EXISTING STRUCTURE TO SERVE AS DETOUR. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-4722 | REGION B
CARTERET | US 70 | NCDOT | REQUIRED REPAIRS NECESSARY FOR EXISTING STRUCTURE TO SERVE AS THE DETOUR ROUTE FOR B-4722B. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-4722A | [11 empty] | COMPLETED.
CARTERET | US 70 | NCDOT | REPLACEMENT OF BRIDGE NO. 33 OVER NORTH RIVER. | HIGHWAY | TRANSITION | 2 | DOWN EAST RPO | B-4722B | REGION B | [10 empty] | COMPLETED.
CARTERET | SR 1335 (ISLAND ROAD) | NCDOT | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-4863 | DIVISION 2 | DP, T |  |  |  |  | 2021 | 73735000 |  |  | 73735000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS.
CARTERET | SR 1182 (ATLANTIC BEACH CAUSEWAY) | NCDOT | REHABILITATE BRIDGE 150068 OVER BOGUE SOUND. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-5938 | DIVISION 2 | T |  |  |  |  | 2019 | 7195000 |  |  | 7195000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE)
CARTERET | NC 58 | NCDOT | REHABILITATE BRIDGE 150006 OVER BOGUE SOUND. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-5939 | REGION B | [10 empty] | UNDER CONSTRUCTION
CARTERET | NC 24 | NCDOT | NC 24 BETWEEN SR 1259 (TAYLOR NOTION ROAD) AND US 70. INSTALL PAVEMENT MARKINGS AND RUMBLE STRIPES ON TWO-WAY LEFT TURN LANE. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | HS-2002B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 640000 |  |  | 640000 | COMPLETED.
CARTERET | NC 58 (SALTER PATH ROAD) | NCDOT | NC 58 (SALTER PATH ROAD) AT THE OCEAN CLUB ENTRANCE JUST WEST OF TRADEWINDS DRIVE. INSTALL CROSSWALK WITH RAPID FLASHING BEACONS. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | HS-2002G | REGION B | HSIP |  |  |  |  | 2022 | 25000 |  |  | 25000 | COMPLETED.
CARTERET | NC 58 (WEST FORT MACON ROAD) | NCDOT | NC 58 (WEST FORT MACON ROAD) AT ATLANTIC STATION SHOPPING CENTER / ATLANTIC BEACH TOWN PARK. INSTALL PEDESTRIAN HEADS FOR EXISTING SIGNAL AND WHEEL CHAIR RAMP REVISIONS. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | HS-2002H | REGION B | HSIP |  |  |  |  | 2022 | 12000 |  |  | 12000 | UNDER CONSTRUCTION.
CARTERET | NC 58 | NCDOT | NC 58 JUST WEST OF CEDAR LANE. INSTALL CROSSWALKS, CONCRETE MONOLITHIC PEDESTRIAN REFUGE ISLAND, SIDEWALKS, AND RECTANGULAR RAPID-FLASHING BEACONS. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | HS-2002I | REGION B | HSIP | 2024 | 5000 |  |  | 2025 | 77000 |  |  | 82000
CARTERET | SR 1310 (LENNOXVILLE ROAD) | NCDOT | SR 1310 (LENNOXVILLE ROAD) AT CARTERET AVENUE IN BEAUFORT. INSTALL CROSSWALK SIGNALIZATION. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | HS-2002U | DIVISION 2 | HSIP |  |  |  |  | 2023 | 25000 |  |  | 25000 | UNDER CONSTRUCTION.
CARTERET | US 70/NC 12 | NCDOT | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-4746 | NOT FUNDED | T | NOT FUNDED | 30900000 | NOT FUNDED | 9100000 | NOT FUNDED | 71199000 |  |  | 111199000
CARTERET | SR 1176 (BRIDGES STREET EXTENSION) | NCDOT | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5727 | DIVISION 2 | T | 2027 | 12701000 | 2027 | 1300000 | 2029 | 62700000 |  |  | 76701000
CARTERET | NC 58 (WEST FORT MACON) | NCDOT | ATLANTIC BEACH CAUSEWAY. ADD RIGHT TURN LANE. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5816 | REGION B | T | 2020 | 600000 |  |  | 2023 | 1650000 |  |  | 2250000 | UNDER CONSTRUCTION.
CARTERET | NC 24 | NCDOT | NC 58. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5858 | STATEWIDE MOBILITY | T | 2023 | 750000 |  |  | 2026 | 6000000 |  |  | 6750000 | RIGHT OF WAY IN PROGRESS.
CARTERET | NC 58 (EMERALD DRIVE) | NCDOT | LOON STREET. INSTALL ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5884 | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 300000 | NOT FUNDED | 1400000 |  |  | 2000000
CARTERET | NC 58 (EMERALD DRIVE) | NCDOT | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5886 | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 1600000 | NOT FUNDED | 1700000 |  |  | 3600000
CARTERET | SR 1175 (BRIDGES STREET) | NCDOT | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5941 | DIVISION 2 | T | 2027 | 7400000 | 2027 | 1100000 | 2029 | 2000000 |  |  | 10500000
CARTERET | NC 58 (EMERALD DRIVE) | NCDOT | MANGROVE DRIVE. UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5944 | DIVISION 2 | T | 2027 | 337000 | 2027 | 100000 | 2029 | 3100000 |  |  | 3537000
CARTERET | US 70 (LIVE OAK STREET) | NCDOT | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5945 | DIVISION 2 | NHP | 2027 | 31800000 | 2027 | 600000 | 2029 | 23601000 |  |  | 56001000
CARTERET | US 70 (LIVE OAK STREET) | NCDOT | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5946 | DIVISION 2 | NHP | 2027 | 4900000 | 2027 | 700000 | 2029 | 2200000 |  |  | 7800000
CARTERET | US 70 (CEDAR STREET) | NCDOT | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-5962 | NOT FUNDED | T | NOT FUNDED | 3300000 | NOT FUNDED | 370000 | NOT FUNDED | 1700000 |  |  | 5370000
CARTERET | US 70 (ARENDELL STREET) | NCDOT | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | U-5876 | STATEWIDE MOBILITY | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 85201000 |  |  | 103001000
CARTERET | US 70 (LIVE OAK STREET) | NCDOT | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | U-6058 | REGION B | L, T | 2023 | 859000 | 2023 | 193000 | 2025 | 3550000 |  |  | 4602000 | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT.
CARTERET | SR 1493 | NCDOT | SR 1493 (LIVE OAK STREET) AT CAMPEN ROAD. REVISE TRAFFIC SIGNAL, INSTALL PEDESTRIAN CROSSING WITH SIGNAL HEADS, AND UPGRADE SIDEWALK. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | W-5802A | DIVISION 2 | HSIP |  |  |  |  | 2021 | 38000 |  |  | 38000 | COMPLETED.
CARTERET | NC 58 | NCDOT | NC 58 (E. FORT MACON ROAD) AT BROOKS STREET. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | W-5802B | REGION B | HSIP |  |  |  |  | 2021 | 30000 |  |  | 30000 | COMPLETED.
CARTERET | NC 58 | NCDOT | NC 58 (E. FORT MACON ROAD) AT E. BOGUE SOUND DRIVE. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | W-5802C | REGION B | HSIP |  |  |  |  | 2021 | 30000 |  |  | 30000 | COMPLETED.
CARTERET | CARTERET COUNTY | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | TA-6717 | DIVISION 2 | 5311, L, T |  |  |  |  | 2020 | 70000 |  |  | 70000
CARTERET | CARTERET COUNTY | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | TA-6718 | DIVISION 2 | 5311, L, T |  |  |  |  | 2020 | 70000 |  |  | 70000
CARTERET | CARTERET COUNTY | CARTERET COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 2 | DOWN EAST RPO | TK-6115 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 300000 | 300000 | FUNDS AUTHORIZED IN PROGRESS
CARTERET | NS/NCRR EC LINE | NCDOT | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | RAIL | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | P-5742 | NOT FUNDED | O, T | NOT FUNDED | 2000000 |  |  | NOT FUNDED | 13000000 |  |  | 15000000 | OTHER FUNDS PROVIDED BY NS.
CARTERET, HYDE | NC 12 | NCDOT | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY | FERRY | STI (PRIORITIZATION) | 1, 2 | ALBEMARLE RPO, DOWN EAST RPO | F-5704 | DIVISION 1, 2 | T |  |  |  |  | 2025 | 25600000 |  |  | 25600000
CASWELL | SR 1710 (GRIERS CHURCH ROAD) | NCDOT | REPLACE BRIDGE 160007 OVER HYCO CREEK. | HIGHWAY | BRIDGES | 7 | PIEDMONT TRIAD RPO | B-5725 | DIVISION 7 | BGOFF | 2030 | 30000 |  |  | 2031 | 1700000 |  |  | 1730000
CASWELL | NC 86 | NCDOT | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | R-5822 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 183000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14200000 |  |  | 14683000 | SCOPE INCLUDES SPOT ID H170625
CASWELL | US 158 / NC 86 | NCDOT | SR 1572 (COUNTY HOME ROAD) TO SR 1734 (RP FUQUAY ROAD). CONSTRUCT PASSING LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | R-5926 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 269000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3649000 |  |  | 4001000
CASWELL | CASWELL COUNTY | CASWELL COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | PIEDMONT TRIAD RPO | TK-6116 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 448000 | 448000 | FUNDS AUTHORIZED IN PROGRESS
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. | AVIATION | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | AV-5741 | DIVISION 12 | O, T |  |  |  |  | 2025 | 3844000 |  |  | 3844000
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | HICKORY REGIONAL AIRPORT (HKY) | LAND ACQUISITION AND OBSTRUCTION REMOVAL. | AVIATION | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | AV-5752 | DIVISION 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | [6 empty] | 600000
CATAWBA | SPRINGS ROAD NE | HICKORY | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | BL-0066 | DIVISION 12 | BGDA, L, TADA | 2024 | 313000 |  |  | 2025 | 2250000 | 2023 | 437000 | 3000000
CATAWBA | AVIATION WALK CONNECTOR | HICKORY | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | BL-0067 | DIVISION 12 | BGDA, L | 2024 | 313000 |  |  | 2025 | 1500000 | 2023 | 187000 | 2000000
CATAWBA | ISLAND FORD ROAD | MAIDEN | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | BL-0068 | DIVISION 12 | BGDA, L | 2025 | 500000 |  |  | 2027 | 850000 | 2023 | 405000 | 1755000
CATAWBA | MAIN AVENUE NW/NE | HICKORY | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | BIKE/PED | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | EB-5750 | DIVISION 12 | BGANY, L, TAANY |  |  |  |  | 2020 | 14100000 |  |  | 14100000
CATAWBA | CLAREMONT | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | EB-5828 | DIVISION 12 | BGANY, BGDA, L | 2023 | 31000 |  |  | 2024 | 541000 |  |  | 572000 | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | OLD LENOIR ROAD MULTI-USE PATH | HICKORY | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | EB-5911 | DIVISION 12 | L, TAANY | 2021 | 1205000 |  |  | 2023 | 8123000 |  |  | 9328000 | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP.
CATAWBA | CLAREMONT | CLAREMONT | CONSTRUCT SIDEWALK ALONG CENTENNIAL BOULEVARD FROM NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II). | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | EB-5935 | DIVISION 12 | BGANY, L |  |  |  |  | 2024 | 600000 |  |  | 600000 | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | HICKORY | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | EB-5937 | DIVISION 12 | BGANY, L, TADA | 2021 | 225000 |  |  | 2023 | 1775000 |  |  | 2000000 | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION.
CATAWBA | HICKORY | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | EB-5938 | DIVISION 12 | BGANY, L, TADA | 2021 | 105000 |  |  | 2023 | 3095000 |  |  | 3200000 | UNDER CONSTRUCTION.
CATAWBA | 9TH STREET NW CONNECTOR | HICKORY | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | EB-5977 | DIVISION 12 | BGDA, BGDACV, L | 2021 | 108000 |  |  | 2023 | 1460000 |  |  | 1568000 | UNDER CONSTRUCTION.
CATAWBA | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | HICKORY | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | BIKE/PED | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | EB-6038 | EXEMPT | DP, L | 2020 | 662000 |  |  | 2021 | 19216000 | 2020 | 2052000 | 21930000 | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT.
CATAWBA | CLAREMOUNT | CLAREMOUNT | PRESERVATION OF BUNKER HILL COVERED BRIDGE. | HIGHWAY | TRANSITION | 12 | GREATER HICKORY MPO | B-5542 | DIVISION 12 | O |  |  |  |  | 2022 | 296000 |  |  | 296000 | UNDER CONSTRUCTION. OTHER FUNDS NATIONAL HISTORIC BRIDGE PROGRAM FUNDS.
CATAWBA | SR 1709 (ROCK BARN ROAD) | NCDOT | REPLACE BRIDGE 170173 OVER I-40. | HIGHWAY | BRIDGES | 12 | GREATER HICKORY MPO | B-5847 | DIVISION 12 | BFP | 2023 | 1400000 |  |  | 2030 | 10300000 |  |  | 11700000
CATAWBA | I-40 | NCDOT | REPLACE BRIDGE 170177 AND 170178 OVER LYLE CREEK. | HIGHWAY | BRIDGES | 12 | GREATER HICKORY MPO | B-6041 | STATEWIDE MOBILITY | BFP | 2025 | 860000 |  |  | 2030 | 13500000 |  |  | 14360000
CATAWBA | CLAREMONT | CLAREMONT | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN CLAREMONT. | HIGHWAY | TRANSITION | 12 | GREATER HICKORY MPO | C-5195 | EXEMPT | [10 empty] | UNDER CONSTRUCTION
CATAWBA | HICKORY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | HIGHWAY | TRANSITION | 12 | GREATER HICKORY MPO | C-5196 | DIVISION 12 | BGANY, CMAQ, L | 2023 | 2856000 |  |  | 2025 | 4988000 | 2023 | 500000 | 8344000 | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP.
CATAWBA | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | HIGHWAY | OTHER | 12 | GREATER HICKORY MPO | C-5608 | EXEMPT | CMAQ, L | 2020 | 51000 |  |  | 2020 | 303000 | 2020 | 153000 | 507000 | IN PROGRESS
CATAWBA | CONOVER | CONOVER | CONSTRUCT 1ST STREET/US 70 BIKE AND PEDESTRIAN IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | C-5624 | DIVISION 12 | BGANY, L |  |  |  |  | 2024 | 2654000 |  |  | 2654000 | $2.123M IN BGANY USED AS PART OF FUND SWAP.
CATAWBA | US 70 | HICKORY | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | HL-0002 | EXEMPT | BGANY, BGDA, L | 2022 | 100000 |  |  | 2023 | 400000 |  |  | 500000 | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | 17TH STREET NW | HICKORY | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | HIGHWAY | LOCALLY SELECTED | 12 | GREATER HICKORY MPO | HL-0004 | DIVISION 12 | BGANY, BGDA, L | 2023 | 720000 |  |  | 2024 | 4800000 | 2021 | 480000 | 6000000 | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | SR 1849 (MOUNT PLEASANT ROAD) | NCDOT | INSTALL GUARDRAIL ON BRIDGE 163 ON SR 1849 OVER MOUNTAIN CREEK PORTION OF LAKE NORMAN | HIGHWAY | SAFETY | 12 | GREATER HICKORY MPO | HS-2012A | DIVISION 12 | HSIP |  |  |  |  | 2021 | 85000 |  |  | 85000 | COMPLETE
CATAWBA | SR 1844 (SLANTING BRIDGE ROAD) | NCDOT | UPGRADE GUARDRAIL AND END UNITS AT BRIDGE 23 | HIGHWAY | SAFETY | 12 | GREATER HICKORY MPO | HS-2012B | DIVISION 12 | HSIP |  |  |  |  | 2021 | 372000 |  |  | 372000 | COMPLETE
CATAWBA | I-40 | NCDOT | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | I-5716 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2026 | 8500000 |  |  | 8500000 | RIGHT-OF-WAY IN PROGRESS
CATAWBA | I-40 | NCDOT | US 321 TO NC 16. WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | I-5991
CATAWBA | I-40 | NCDOT | US 321 TO SR 1476 (FAIRGROVE CHURCH ROAD). WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | I-5991A | STATEWIDE MOBILITY | NHP |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 69300000 |  |  | 69900000
CATAWBA | I-40 | NCDOT | SR 1476 (FAIRGROVE CHURCH ROAD) TO NC 16. WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | I-5991B | NOT FUNDED | NHP | NOT FUNDED | 4600000 |  |  | NOT FUNDED | 85000000 |  |  | 89600000
CATAWBA | NC 16 | NCDOT | SR 1895 TO SR 1800 SOUTHEAST OF NEWTON. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | R-3100
CATAWBA | NC 16 | NCDOT | SR 1895 (TOWER ROAD) TO SR 1814 (CALDWELL ROAD) | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | R-3100A | DIVISION 12 | T |  |  |  |  | 2021 | 42510000 |  |  | 42510000 | COMPLETE; BUILD NC BOND FUNDING: $33.028 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
CATAWBA | NC 16 | NCDOT | SR 1814 (CALDWELL ROAD) TO SR 1801 (CLAREMONT ROAD) | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | R-3100B | DIVISION 12 | [10 empty] | COMPLETE.
CATAWBA | NC 16 | NCDOT | SR 1801 (CLAREMONT ROAD) TO SR 1800 (CALEB SETZER ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 12 | GREATER HICKORY MPO | R-3100C | [11 empty] | COMPLETE.
CATAWBA | SR 1005 (STARTOWN ROAD) | NCDOT | US 70 TO NC 10. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | R-5113 | DIVISION 12 | T | 2028 | 38600000 | 2028 | 9700000 | 2031 | 42600000 |  |  | 90900000
CATAWBA | HICKORY | NCDOT | EAST SIDE THOROUGHFARE (MCDONALD PARKWAY), US 70-321 TO NC 127. MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-2307 | [11 empty] | STBG-DA FUNDS (W/ STATE MATCH) AS A RESULT OF FUNDING SWAP WITH EB-5911.
CATAWBA | HICKORY | NCDOT | US 70-321 TO NORTH OF I-40. | HIGHWAY | PRE-STI (HISTORIC) | 12 | GREATER HICKORY MPO | U-2307AA | [11 empty] | COMPLETE
CATAWBA | HICKORY | NCDOT | NORTH OF I-40 TO SR 1453 (SPRINGS ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 12 | GREATER HICKORY MPO | U-2307AB | [11 empty] | COMPLETE
CATAWBA | HICKORY | NCDOT | NORTH OF I-40 TO NORTH OF SR 1692 (TATE BOULEVARD) | HIGHWAY | PRE-STI (HISTORIC) | 12 | GREATER HICKORY MPO | U-2307AD | [11 empty] | COMPLETE
CATAWBA | HICKORY | NCDOT | NORTH OF SR 1692 (TATE BOULEVARD) TO SR 1453 (SPRINGS ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 12 | GREATER HICKORY MPO | U-2307AE | [11 empty] | COMPLETE
CATAWBA | MCDONALD PARKWAY | NCDOT | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-2307B | DIVISION 12 | BGANY, BGDA, S(M), T | 2025 | 22600000 | 2025 | 9800000 | 2028 | 42000000 |  |  | 74400000
CATAWBA | HICKORY | NCDOT | HICKORY EAST SIDE THOROUGHFARE TO 15TH AVE SE | HIGHWAY | PRE-STI (HISTORIC) | 12 | GREATER HICKORY MPO | U-2307C | [11 empty] | COMPLETE
CATAWBA | NC 127 | NCDOT | WIDEN NC 127 TO MULTI-LANES, SR 1132 TO SR 1008. UPGRADE AND EXTEND SR 1213 (CURRENTLY NC 127), PROPOSED US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-2530
CATAWBA | NC 127 | NCDOT | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-2530A | DIVISION 12 | T | 2025 | 23900000 | 2025 | 3800000 | 2027 | 25500000 |  |  | 53200000
CATAWBA | NC 127 | NCDOT | NORTH OF US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182 | HIGHWAY | PRE-STI (HISTORIC) | 12 | GREATER HICKORY MPO | U-2530B | [11 empty] | COMPLETE
CATAWBA | NC 127 | NCDOT | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-5777 | REGION F | T | 2019 | 2150000 |  |  | 2025 | 3951000 |  |  | 6101000 | RIGHT-OF-WAY IN PROGRESS
CATAWBA | SR 1124 (33RD STREET SW) | NCDOT | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-6042 | DIVISION 12 | T | 2027 | 1400000 | 2027 | 200000 | 2029 | 3300000 |  |  | 4900000
CATAWBA | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | NCDOT | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-6135 | NOT FUNDED | T | NOT FUNDED | 19700000 | NOT FUNDED | 6100000 | NOT FUNDED | 23299000 |  |  | 49099000
CATAWBA | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | NCDOT | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO | U-6176 | DIVISION 12 | BGANY, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20499000 |  |  | 49599000
CATAWBA | TRIVIUM PARKWAY, NEW ROUTE | HICKORY | EXTEND TRIVIUM PARKWAY AND CONSTRUCT NEW ROADWAY IN TRIVIUM CORPORATE CENTER. | HIGHWAY | ECONOMIC DEVELOPMENT | 12 | GREATER HICKORY MPO | U-6238 | DIVISION 12 | T |  |  |  |  | 2023 | 1316000 |  |  | 1316000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CATALER NORTH AMERICA.
CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PUBLIC TRANSIT | CAPITAL (NON-STI) | 12 | GREATER HICKORY MPO | TA-6707 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2520000 | 2520000
CATAWBA | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 12 | GREATER HICKORY MPO | TA-6708 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 2477000 | 2477000 | FUNDING ADDED TO FY 21 AT THE REQUEST OF THE MPO (FUNDING UNCHANGED IN FY 20 ALREADY FLEXED FROM CMAQ TO FUZ)
CATAWBA | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES LIGHT TRANSIT VEHICLE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 12 | GREATER HICKORY MPO | TA-6709 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2535000 | 2535000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GREATER HICKORY MPO | TG-6798 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 970000 | 970000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTIVE MAINTANENCE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 12 | GREATER HICKORY MPO | TG-6799 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3894000 | 3894000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, COMPUTER HARDWARE AND SOFTWARE, AVL SOFTWARE, ETC. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 12 | GREATER HICKORY MPO | TG-6800 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1559000 | 1559000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GREATER HICKORY MPO | TG-6801 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2117000 | 2117000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE-ADA PARATRANSIT | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GREATER HICKORY MPO | TG-6802 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 300000 | 300000
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PROGRAM ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GREATER HICKORY MPO | TL-1000 | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 232000 | 232000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 12 | GREATER HICKORY MPO | TO-6162 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 19730000 | 19730000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | CAPITAL PURCHASE OF SERVICE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 12 | GREATER HICKORY MPO | TQ-9039 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 1161000 | 1161000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | PUBLIC TRANSIT | CAPITAL (NON-STI) | 12 | GREATER HICKORY MPO | TQ-9040 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 312000 | 312000 | MODIFYING FUNDING IN FY 20, FY 21, FY 22, FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | SAFETY AND SECURITY | PUBLIC TRANSIT | CAPITAL (NON-STI) | 12 | GREATER HICKORY MPO | TS-7002 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 342000 | 342000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA, ALEXANDER, BURKE, CALDWELL | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREATER HICKORY PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 11, 12, 13 | GREATER HICKORY MPO | HL-0100 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 3018000 |  |  | 3018000
CATAWBA, ALEXANDER, BURKE, CALDWELL | VARIOUS | NCDOT | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. | HIGHWAY | LOCALLY SELECTED | 11, 12, 13 | GREATER HICKORY MPO | U-5924 | DIVISION 11, 12, 13 | BGDA, L | [6 empty] | 2020 | 1750000 | 1750000
CATAWBA, BURKE, CALDWELL | HICKORY | HICKORY | UPGRADE CURRENT PEDESTRIAN SIGNALS AND INSTALL NEW PEDESTRIAN SIGNALS. | BIKE/PED | LOCALLY SELECTED | 11, 12, 13 | GREATER HICKORY MPO | EB-5808 | DIVISION 11, 12, 13 | BGANY, L |  |  |  |  | 2023 | 402000 |  |  | 402000 | $322K IN STBG-DA FUNDS SWITCHED WITH $322K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA, BURKE, CALDWELL, ALEXANDER | VARIOUS | NCDOT | GREATER HICKORY MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | BIKE/PED | LOCALLY SELECTED | 11, 12, 13 | GREATER HICKORY MPO | U-5546 | DIVISION 11, 12, 13 | L, TADA |  |  |  |  | 2023 | 5834000 |  |  | 5834000
CATAWBA, BURKE, CALDWELL, ALEXANDER | VARIOUS | NCDOT | STBG-DA IN THE GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. | HIGHWAY | LOCALLY SELECTED | 11, 12, 13 | GREATER HICKORY MPO | U-5615 | DIVISION 11, 12, 13 | BGDA, L |  |  |  |  | 2020 | 51171000 |  |  | 51171000
CATAWBA, CALDWELL, BURKE | US 321 | NCDOT | NORTH OF US 70 IN HICKORY TO US 321A | HIGHWAY | STI (PRIORITIZATION) | 11, 12, 13 | GREATER HICKORY MPO | U-4700A | STATEWIDE MOBILITY | L, NHP, S(M) | 2021 | 88015000 |  |  | 2026 | 220299000 |  |  | 308314000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035
CATAWBA, IREDELL, LINCOLN | NC 150 | NCDOT | RELOCATED NC 16 (STIP PROJECT R-2206) TO US 21. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO, GASTON-CLEVELAND-LINCOLN MPO | R-2307 | [11 empty] | SEGMENT B INCORPORATES WORK PREVIOUSLY UNDER I-5717.
CATAWBA, LINCOLN | NC 150 | NCDOT | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | HIGHWAY | STI (PRIORITIZATION) | 12 | GREATER HICKORY MPO, GASTON-CLEVELAND-LINCOLN MPO | R-2307A | REGION F | BGANY, T | 2027 | 92259000 | 2027 | 17800000 | 2030 | 115901000 |  |  | 225960000 | BUILD NC BOND FUNDING: $15.961 M FOR RIGHT-OF-WAY, PAYBACK FY 2027-2040 (FY 2026 / YR 8 SALE), BUILD NC BOND FUNDING: $18.736M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE)
CHATHAM | SILER CITY MUNICIPAL AIRPORT (SCR) | SILER CITY MUNICIPAL AIRPORT (SCR) | ACQUIRE NAVIGATION EASEMENTS IN RUNWAY 4 AND RUNWAY 22 APPROACHES, AND REMOVE OBSTRUCTIONS IN EASEMENTS. | AVIATION | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | AV-5736 | DIVISION 8 | T | 2024 | 365000 | [6 empty] | 365000
CHATHAM | SILER CITY MUNICIPAL AIRPORT (SCR) | SILER CITY MUNICIPAL AIRPORT (SCR) | EXTEND RUNWAY 22 AND PARALLEL TAXIWAY BY 500 FT, INCLUDING RELOCATION OF AIRPORT ROAD | AVIATION | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | AV-5816 | DIVISION 8 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 80000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5700000 |  |  | 7780000
CHATHAM | CHATHAM BUSINESS DR | PITTSBORO | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | BIKE/PED | LOCALLY SELECTED | 8 | TRIANGLE AREA RPO | BL-0035 | EXEMPT | CMAQ, L | 2022 | 10000 |  |  | 2023 | 160000 | 2022 | 40000 | 210000
CHATHAM | VARIOUS | NCDOT | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | BIKE/PED | LOCALLY SELECTED | 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0070 | DIVISION 8 | BGDA, BGDACV, L, S |  |  |  |  | 2023 | 175000 | 2023 | 5000 | 180000 | "S" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS.
CHATHAM | SR 2103 (EAST RALEIGH STREET) | SILER CITY | SOUTH 7TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5734 | DIVISION 8 | L, TA5200 |  |  |  |  | 2023 | 744000 |  |  | 744000
CHATHAM | SR 1107 (WEST 3RD STREET) | SILER CITY | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-6006 | DIVISION 8 | L, TA5200 | 2024 | 45000 |  |  | 2026 | 850000 | 2022 | 113000 | 1008000
CHATHAM | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SILER CITY | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-6007 | NOT FUNDED | L, TA5200 | NOT FUNDED | 70000 |  |  | NOT FUNDED | 920000 | NOT FUNDED | 127000 | 1117000
CHATHAM | SR 1916 (CORINTH ROAD) | NCDOT | REPLACE BRIDGE 180010 OVER SHADDOX CREEK. | HIGHWAY | BRIDGES | 8 | TRIANGLE AREA RPO | B-4461 | HIGHWAY FUND | [10 empty] | COMPLETE
CHATHAM | PITTSBORO ELEMENTARY SCHOOL ROAD | PITTSBORO | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | HIGHWAY | LOCALLY SELECTED | 8 | TRIANGLE AREA RPO | BL-0062 | EXEMPT | CMAQ, L | 2024 | 5000 |  |  | 2024 | 141000 | 2023 | 59000 | 205000
CHATHAM | VARIOUS | NCDOT | CONSTRUC ROADWAY IMPROVEMENTS NEAR THE TRIANGLE INNOVATION POINT MEGASITE. | HIGHWAY | ECONOMIC DEVELOPMENT | 8 | TRIANGLE AREA RPO | HE-0006 | HIGHWAY FUND | [10 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
CHATHAM | VARIOUS | NCDOT | CONSTRUCTION OF SITE DESIGN 1A. RESURFACING AND STRENGTHENING OF SURROUNDING ROADWAYS NEAR TRIANGLE INNOVATION POINT MEGASITE. | HIGHWAY | ECONOMIC DEVELOPMENT | 8 | TRIANGLE AREA RPO | HE-0006A | HIGHWAY FUND | S |  |  |  |  | 2023 | 7000000 |  |  | 7000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
CHATHAM | VARIOUS | NCDOT | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. | HIGHWAY | ECONOMIC DEVELOPMENT | 8 | TRIANGLE AREA RPO | HE-0006B | HIGHWAY FUND | S | 2023 | 10000000 | 2023 | 5000000 | 2024 | 175000000 | 2023 | 3000000 | 193000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
CHATHAM | VARIOUS | NCDOT | CONSTRUCTION OF SITE DESIGN 2A AND 2B. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. | HIGHWAY | ECONOMIC DEVELOPMENT | 8 | TRIANGLE AREA RPO | HE-0006C | HIGHWAY FUND | S |  |  |  |  | 2025 | 50000000 |  |  | 50000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
CHATHAM | VARIOUS | NCDOT | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. | HIGHWAY | ECONOMIC DEVELOPMENT | 8 | TRIANGLE AREA RPO | HE-0011 | DIVISION 8 | T | 2023 | 250000 | 2023 | 250000 | 2024 | 8500000 | 2023 | 1000000 | 10000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED.
CHATHAM | US 15 / US 501 | NCDOT | SOUTH OF US 64 BUSINESS TO POWELL PLACE LANE IN PITTSBORO. WIDEN TO MULTI-LANES, MILL AND RESURFACE, AND CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5724
CHATHAM | US 15 / US 501 | NCDOT | US 15 / US 501, SOUTH OF US 64 BUSINESS TO NORTH OF US 64 BUSINESS. CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5724A | DIVISION 8 | T |  |  |  |  | 2021 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION
CHATHAM | US 15 / US 501 | NCDOT | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5724B | DIVISION 8 | T | 2023 | 3900000 | 2023 | 1300000 | 2026 | 10199000 |  |  | 15399000 | RIGHT-OF-WAY IN PROGRESS
CHATHAM | NC 751 | NCDOT | SR 1731 (O'KELLY CHAPEL ROAD). UPGRADE AND REALIGN INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5825 | DIVISION 8 | T |  |  |  |  | 2023 | 1251000 |  |  | 1251000 | ROW in progress.
CHATHAM | NEW ROUTE CHATHAM PARK WAY | NCDOT | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5930 | DIVISION 8 | O, T | 2023 | 3693000 | 2023 | 360000 |  |  |  |  | 4053000 | "O" FUNDING REFLECTS LOCAL PARTICIPATION.
CHATHAM | NEW ROUTE - CHATHAM PARK WAY | NCDOT | NORTHERN TERMINUS OF EXISTING CHATHAM PARK WAY JUST NORTH OF US 64 TO NORTH OF PROPOSED GRANT DRIVE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5930A | DIVISION 8 | O, T |  |  |  |  | 2024 | 14800000 |  |  | 14800000
CHATHAM | NEW ROUTE - CHATHAM PARK WAY | NCDOT | NORTH OF PROPOSED GRANT DRIVE TO US 15/ US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5930B | DIVISION 8 | T |  |  |  |  | 2024 | 17800000 |  |  | 17800000
CHATHAM | NC 87 | NCDOT | NC 902 IN PITTSBORO TO US 64 BYPASS. WIDEN TO 12-FT LANES AND 4-FT PAVED SHOULDERS. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5961 | NOT FUNDED | T | NOT FUNDED | 2500000 | NOT FUNDED | 2200000 | NOT FUNDED | 13200000 |  |  | 17900000
CHATHAM | NEW ROUTE | NCDOT | US 15 / US 501 / NC 87 TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5963
CHATHAM | NEW ROUTE | NCDOT | US 15 / US 501 SOUTH OF PITTSBORO TO SR 1012 (MONCURE-PITTSBORO ROAD). CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5963A | DIVISION 8 | T | 2024 | 2686000 | 2024 | 26000 | 2027 | 12629000 |  |  | 15341000 | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 23 AND CONSTRUCTION FY 23 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT.
CHATHAM | NEW ROUTE | NCDOT | SR 1012 (MONCURE-PITTSBORO ROAD) TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5963B | DIVISION 8 | T | 2024 | 3573000 | 2024 | 36000 | 2027 | 32679000 |  |  | 36288000 | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 24 AND CONSTRUCTION FY 24 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT.
CHATHAM | NEW ROUTE | NCDOT | US 64 BUSINESS TO JUST NORTH OF US 64. WIDEN EXISTING 2-LANE ROADWAY TO 4-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5963C | DIVISION 8 | T |  |  | 2024 | 30000 | 2027 | 9771000 |  |  | 9801000
CHATHAM | CHATHAM PARK WAY | NCDOT | CONSTRUCTION OF NEW WESTBOUND ON-RAMP FROM CHATHAM PARK WAY TO US 64 AND REALIGNMENT OF SUTTLES ROAD TO NEW INTERSECTION WITH CHATHAM PARK WAY. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5963D | DIVISION 8 | T | 2025 | 500000 |  |  | 2027 | 2000000 |  |  | 2500000 | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 23 AND CONSTRUCTION FY 23 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT.
CHATHAM | US 64 (EAST 11TH STREET) | NCDOT | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5737 | REGION E | T | 2024 | 4931000 | 2023 | 2671000 | 2028 | 20501000 |  |  | 28103000
CHATHAM | US 421 | NCDOT | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A REDUCED CONFLICT INTERSECTION. | HIGHWAY | SAFETY | 8 | TRIANGLE AREA RPO | W-5808B | STATEWIDE MOBILITY | HSIP | 2022 | 100000 |  |  | 2024 | 736000 |  |  | 836000 | RIGHT-OF-WAY IN PROGRESS
CHATHAM | VARIOUS | CHATHAM TRANSIT NETWORK | CHATHAM TRANSIT NETWORK. PURCHASE 3 NEW RAMP-EQIPPED MINIVANS. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6719 | DIVISION 8 | L, T | [6 empty] | 2021 | 141000 | 141000
CHATHAM | CHATHAM TRANSIT NETWORK | CHATHAM TRANSIT NETWORK | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 8 | TRIANGLE AREA RPO | TK-6117 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 944000 | 944000 | FUNDS AUTHORIZED IN PROGRESS
CHATHAM | SR 1916 (CORINTH ROAD) | NCDOT | CSX CROSSING 630723C NEAR HAYWOOD. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 8 | TRIANGLE AREA RPO | RX-2008A | DIVISION 8 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
CHATHAM, HOKE, LEE, RANDOLPH, SCOTLAND | VARIOUS | NCDOT | VARIOUS SECONDARY ROUTES IN CHATHAM, LEE, HOKE, RANDOLPH AND SCOTLAND COUNTIES. INSTALL LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, FAYETTEVILLE AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2008C | REGION E | HSIP |  |  |  |  | 2022 | 1580000 |  |  | 1580000
CHATHAM, LEE | SR 1007 (PLANK ROAD) | NCDOT | REPLACE BRIDGE 180169 OVER DEEP RIVER. | HIGHWAY | BRIDGES | 8 | TRIANGLE AREA RPO | HB-0034 | DIVISION 8 | BGOFF | 2025 | 325000 | 2025 | 325000 | 2026 | 6500000 |  |  | 7150000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | BO-2408 | DIVISION 8 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2008
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2408 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | R-5788 | DIVISION 8 | S, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | DIVISION 8 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5208 | [11 empty] | UNDER CONSTRUCTION
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5708 | [11 empty] | IN PROGRESS
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5708DIV | DIVISION 8 | HSIP | 2020 | 90000 |  |  | 2020 | 540000 |  |  | 630000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5708REG | REGION E | HSIP | 2020 | 90000 |  |  | 2020 | 540000 |  |  | 630000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5708SW | STATEWIDE MOBILITY | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5808
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 8. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RC-2008 | DIVISION 8 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RX-2008 | DIVISION 8
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RX-2408 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHATHAM, ORANGE | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | HIGHWAY | OTHER | 7, 8 | TRIANGLE AREA RPO | C-5618 | EXEMPT | CMAQ, L | 2020 | 45000 |  |  | 2020 | 255000 | 2020 | 135000 | 435000
CHATHAM, ORANGE | US 15 / US 501 | NCDOT | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | HIGHWAY | STI (PRIORITIZATION) | 7, 8 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-6192 | DIVISION 7, 8 | T | 2028 | 9299000 | 2028 | 30000000 | 2031 | 78400000 |  |  | 117699000
CHATHAM, WAKE | US 64 | NCDOT | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 5, 8 | TRIANGLE AREA RPO, CAPITAL AREA MPO | R-5887 | REGION C, E | NHP | 2027 | 3299000 | 2027 | 1500000 | 2029 | 31000000 |  |  | 35799000
CHEROKEE | SR 1326 | NCDOT | REPLACE BRIDGE 159 OVER HANGING DOG CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-4069 | DIVISION 14 | BGOFF | 2024 | 295000 |  |  | 2027 | 1800000 |  |  | 2095000
CHEROKEE | SR 1548 (OLD HIGHWAY 64) | NCDOT | REPLACE BRIDGE 223 OVER HIWASSEE RIVER. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-5925 | DIVISION 14 | BFP | 2023 | 260000 |  |  | 2024 | 2600000 |  |  | 2860000
CHEROKEE | US 19/US 74/ US 64/US 129 | NCDOT | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5735 | DIVISION 14 | T | 2020 | 4815000 |  |  | 2020 | 15390000 | 2020 | 2700000 | 22905000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE)
CHEROKEE | US 19/US 74/US 64/US 129 | NCDOT | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5735A | DIVISION 14 | [10 empty] | CLEARING ONLY.
CHEROKEE | US 19/129 | NCDOT | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5861 | DIVISION 14 | BGLT5, T | 2022 | 11400000 | 2022 | 1100000 | 2024 | 54900000 |  |  | 67400000 | RIGHT-OF-WAY IN PROGRESS.
CHEROKEE | US 19/US 74/ US 129 | NCDOT | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5908 | DIVISION 14 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 870000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16001000 |  |  | 18871000
CHEROKEE | CHEROKEE COUNTY | CHEROKEE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | SOUTHWESTERN RPO | TK-6118 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 712000 | 712000 | FUNDS AUTHORIZED IN PROGRESS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | BO-2414 | DIVISION 14 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | HS-2014
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | HS-2414 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | R-5794 | DIVISION 14 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | DIVISION 14 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO | W-5214 | [11 empty] | IN PROGRESS - DIVISION PURCHASE ORDER CONTRACT (DPOC)
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5714 | [11 empty] | IN PROGRESS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5714DIV | DIVISION 14 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5714REG | REGION G | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5714SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5814
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 14. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | RC-2014 | DIVISION 14 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | RX-2014 | DIVISION 14 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | RX-2414 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, GRAHAM, JACKSON, SWAIN | EASTERN BAND OF CHEROKE INDIANS | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | SOUTHWESTERN RPO | TK-6127 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 464000 | 464000 | FUNDS AUTHORIZED IN PROGRESS
CHEROKEE, MACON | US 74 | NCDOT | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5920 | NOT FUNDED | BGLT5 | NOT FUNDED | 20000000 | NOT FUNDED | 1000000 | NOT FUNDED | 71998000 |  |  | 92998000
CHOWAN | NC 32 | NCDOT | REPLACE BRIDGE 200024 OVER WARWICK CREEK, BRIDGE 200020 OVER DILLARD CREEK, AND BRIDGE 200021 OVER SAND RUN. | HIGHWAY | BRIDGES | 1 | ALBEMARLE RPO | B-5507 | HIGHWAY FUND | [10 empty] | COMPLETED.
CHOWAN | US 17 (FUTURE I-87) | NCDOT | BERTIE COUNTY LINE TO PERQUIMANS COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 1 | ALBEMARLE RPO | I-6027 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2029 | 8250000 |  |  | 8250000
CLAY | US 64/NC 69 | NCDOT | NC 69, GEORGIA STATE LINE TO US 64. WIDEN TO FOUR LANES DIVIDED. US 64, NC 69 TO EAST OF NC 175. WIDEN TO MULTI-LANES. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0011 | [11 empty] | APD FUNDS ARE 100% FEDERAL
CLAY | NC 69 | NCDOT | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). UPGRADE EXISTING TWO-LANES | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0011A | [11 empty] | COMPLETE
CLAY | US 64 | NCDOT | NC 69 IN HAYESVILLE TO EAST OF THE HIWASSEE RIVER | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0011BA | [11 empty] | COMPLETE
CLAY | US 64 | NCDOT | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175 | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0011BB | [11 empty] | COMPLETE
CLAY | NC 69 | NCDOT | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). WIDEN TO FOUR-LANES | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0011C | EXEMPT | ADHS |  |  |  |  | 2020 | 52600000 |  |  | 52600000 | UNDER CONSTRUCTION
CLAY | US 64 | NCDOT | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0011D | NOT FUNDED | ADHS | NOT FUNDED | 20845000 | NOT FUNDED | 378000 | NOT FUNDED | 52800000 |  |  | 74023000
CLAY | SR 1140 (MYERS CHAPEL ROAD) | NCDOT | REPLACE BRIDGE #63 OVER BLAIR CREEK AND BRIDGE #88 OVER HYATT MILL CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | HF-0005 | EXEMPT | FLAP, S(M) |  |  |  |  | 2024 | 1200000 | 2021 | 300000 | 1500000 | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. STATE FUNDS ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS.
CLAY | SR 1100 (OLD HIGHWAY 64 WEST) | NCDOT | SR 1135 (SETTAWIG ROAD) NEAR BRASSTOWN. WIDEN AND INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO | HS-2014F | DIVISION 14 | HSIP | 2023 | 16000 |  |  | 2023 | 320000 |  |  | 336000 | UNDER CONSTRUCTION.
CLAY | NC 175 | NCDOT | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5742 | DIVISION 14 | T | 2020 | 540000 |  |  | 2020 | 28077000 | 2020 | 2505000 | 31122000 | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
CLAY | NC 175 | NCDOT | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5742A | DIVISION 14 | [10 empty] | CLEARING ONLY.
CLAY | US 64 BUSINESS | NCDOT | US 64 TO SR 1307 (MAIN STREET). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5863 | DIVISION 14 | T | 2022 | 4200000 |  |  | 2023 | 6100000 |  |  | 10300000 | RIGHT-OF-WAY IN PROGRESS.
CLAY | US 64 | NCDOT | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5922 | NOT FUNDED | BGLT5 | NOT FUNDED | 3700000 | NOT FUNDED | 2700000 | NOT FUNDED | 39700000 |  |  | 46100000
CLAY | CLAY COUNTY | CLAY COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | SOUTHWESTERN RPO | TK-6120 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 704000 | 704000 | FUNDS AUTHORIZED IN PROGRESS
CLAY, CHEROKEE | US 64 | NCDOT | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5847 | NOT FUNDED | T | NOT FUNDED | 32000000 | NOT FUNDED | 6000000 | NOT FUNDED | 95901000 |  |  | 133901000 | WORK FOR B-5911 INCLUDED.
CLEVELAND | SHELBY RAIL TRAIL | SHELBY | SOUTH DEKALB STREET TO WEST GROVER STREET IN SHELBY. CONSTRUCT MULTIUSE PATH. | BIKE/PED | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-6037A | DIVISION 12 | L, TAANY |  |  |  |  | 2024 | 5200000 |  |  | 5200000
CLEVELAND | US 74 | NCDOT | REPLACE BRIDGES 220048 AND 220049 OVER SANDY RUN. | HIGHWAY | BRIDGES | 12 | GASTON-CLEVELAND-LINCOLN MPO | BR-0012 | HIGHWAY FUND | HFB | 2022 | 42000 |  |  | 2024 | 10300000 |  |  | 10342000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045
CLEVELAND | US 74 (SHELBY BYPASS) | NCDOT | FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | WEST OF SR 1162 (PEACHTREE ROAD) TO EAST OF SR 1315 (PLATO LEE ROAD). RIGHT-OF-WAY ONLY. | HIGHWAY | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707A | [11 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | WEST OF SR 1162 (PEACHTREE ROAD) TO EAST OF SR 1318 (KIMBRELL ROAD). GRADING, STRUCTURES, PAVING | HIGHWAY | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707AA | [11 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF SR 1318 (KIMBRELL ROAD) TO EAST OF SR 1315 (PLATO LEE ROAD). GRADING AND STRUCTURES | HIGHWAY | TRANSITION | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707AB | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF SR 1315 (PLATO LEE ROAD) TO EAST OF NC 226. GRADING AND STRUCTURES | HIGHWAY | TRANSITION | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707B | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707C | REGION F | T |  |  |  |  | 2020 | 40335000 | 2021 | 75000 | 40410000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707D | REGION F | T | 2019 | 18808000 |  |  | 2024 | 114205000 |  |  | 133013000 | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | US 74 WEST OF SR 2238 (LONG BRANCH ROAD) TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707E | REGION F | T | 2019 | 14290000 |  |  | 2024 | 50399000 |  |  | 64689000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF SR 1318 (KIMBRELL ROAD) TO EAST OF NC 226. PAVING | HIGHWAY | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707F | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CLEVELAND | US 74 | NCDOT | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-4045 | REGION F | DP, T | 2023 | 3000000 | 2023 | 1900000 | 2023 | 25001000 |  |  | 29901000 | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION.
CLEVELAND | US 74 | NCDOT | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5713 | REGION F | T |  |  |  |  | 2024 | 1950000 |  |  | 1950000
CLEVELAND | NEW ROUTE | NCDOT | CONSTRUCT IMPROVEMENTS TO SR 1313 (WASHBURN SWITCH ROAD) AND A NEW 3-LANE ROAD OFF SR 1313 (WASHBURN SWITCH ROAD) FOR ACCESS TO NEW INDUSTRIAL SITES. | HIGHWAY | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5849 | DIVISION 12 | [10 empty] | UNDER CONSTRUCTION
CLEVELAND | US 74 (DIXON BOULEVARD) | NCDOT | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2567 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25200000 |  |  | 48100000 | TO BE LET WITH U-5929
CLEVELAND | US 74 BUSINESS (MARION STREET) | NCDOT | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5775 | REGION F | L, T |  |  |  |  | 2022 | 3999000 |  |  | 3999000 | UNDER CONSTRUCTION. $300,000 FROM CITY OF SHELBY
CLEVELAND | US 74 (DIXON BOULEVARD) | NCDOT | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5929 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6500000 |  |  | 15700000 | TO BE LET WITH U-2567
CLEVELAND | NC 150 | NCDOT | MILEPOST 19.3 TO GASTON COUNTY LINE AND FROM THE CLEVELAND COUNTY LINE TO MILEPOST 1.2. CONSTRUCT SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO | W-5712U | REGION F | HSIP |  |  |  |  | 2025 | 625000 |  |  | 625000
CLEVELAND | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GASTON-CLEVELAND-LINCOLN MPO | TK-6166 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1196000 | 1196000 | FUNDS AUTHORIZED IN PROGRESS
CLEVELAND, GASTON | I-85 | NCDOT | SOUTH CAROLINA STATE LINE TO US 74 | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985A | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 150300000 |  |  | 157000000
CLEVELAND, POLK, GASTON, HENDERSON, RUTHERFORD, MECKLENBURG, BUNCOMBE | US 74 | NCDOT | I-40 IN ASHEVILLE TO I-77 AT I-485 (SOUTH) IN CHARLOTTE. INSTALL BROADBAND. | HIGHWAY | OTHER | 10, 12, 13, 14 | GASTON-CLEVELAND-LINCOLN MPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, CHARLOTTE REGIONAL TPO | HO-0002A | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 18435000 |  |  | 18435000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002B, AND HO-0002C.
COLUMBUS | COLUMBUS COUNTY AIRPORT (CPC) | COLUMBUS COUNTY AIRPORT (CPC) | APRON EXPANSION. | AVIATION | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | AV-5748 | DIVISION 6 | T |  |  |  |  | 2024 | 1808000 |  |  | 1808000
COLUMBUS | SR 1159 (OLD TRAM ROAD) | NCDOT | REPLACE BRIDGE 230313 OVER BOOGY BRANCH. | HIGHWAY | BRIDGES | 6 | CAPE FEAR RPO | B-6006 | DIVISION 6 | [10 empty] | COMPLETED.
COLUMBUS | ROAD) SR 1800 (BLACKSMITH | NCDOT | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | HIGHWAY | BRIDGES | 6 | CAPE FEAR RPO | HB-0009 | DIVISION 6 | BGOFF | 2029 | 140000 | 2029 | 110000 | 2030 | 1400000 |  |  | 1650000
COLUMBUS | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM EAST OF NC 214 TO WEST OF SR 1824 (WATER TANK ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | CAPE FEAR RPO | HI-0015 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2024 | 10300000 |  |  | 10300000
COLUMBUS | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM WEST OF US 701 BUSINESS TO WEST OF NC 214. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | CAPE FEAR RPO | HI-0018 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 24200000 |  |  | 24200000
COLUMBUS | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM WEST OF SR 1585 (UNION VALLEY ROAD) TO WEST OF US 701 BUSINESS. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | CAPE FEAR RPO | HI-0019 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2029 | 5400000 |  |  | 5400000
COLUMBUS | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM THE ROBESON COUNTY LINE TO WEST OF SR 1585 (UNION VALLEY ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | CAPE FEAR RPO | HI-0020 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2029 | 15002000 |  |  | 15002000
COLUMBUS | NC 211 | NCDOT | NC 211 FROM THE BRUNSWICK COUNTY LINE TO NC 214. INSTALL RUMBLE STRIPES. | HIGHWAY | SAFETY | 6 | CAPE FEAR RPO | HS-2006F | REGION C | HSIP |  |  |  |  | 2023 | 574000 |  |  | 574000 | UNDER CONSTRUCTION.
COLUMBUS | NC 87 | NCDOT | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-2561C | DIVISION 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26512000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4488000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 85800000 |  |  | 116800000
COLUMBUS | NC 87 | NCDOT | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-2561CA | REGION C | BGLT5, T | 2020 | 3304000 | 2020 | 3000000 | 2023 | 29700000 |  |  | 36004000 | UNDER CONSTRUCTION.
COLUMBUS | NC 87 | NCDOT | CONSTRUCT DETOUR ROUTE. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-2561CB | REGION C | T |  |  |  |  | 2023 | 900000 |  |  | 900000 | UNDER CONSTRUCTION.
COLUMBUS | US 701 BYPASS (MADISON STREET- POWELL BOULEVARD) | NCDOT | SOUTH OF SR 1166 (PLEASANT PLAINS ROAD) TO NORTH OF US 74/US 76 BYPASS IN WHITEVILLE. WIDEN TO MULTI-LANE FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-5020 | [11 empty] | RIGHT-OF-WAY IN PROGRESS.
COLUMBUS | US 701 BYPASS | NCDOT | SR 1166 (PLEASANT PLAINS CHURCH ROAD) TO SR 1437 (VIRGIL AVENUE). | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-5020A | REGION C | NHP |  |  |  |  | 2029 | 47299000 |  |  | 47299000
COLUMBUS | US 701 BYPASS | NCDOT | SR 1437 (VIRGIL AVENUE) TO US 74/US 76. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-5020B | DIVISION 6 | T |  |  |  |  | 2022 | 32485000 |  |  | 32485000 | UNDER CONSTRUCTION.
COLUMBUS | US 74 | NCDOT | SR 1506 (BOARDMAN ROAD). UPGRADE AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-5797 | REGION C | T |  |  |  |  | 2021 | 18620000 |  |  | 18620000 | UNDER CONSTRUCTION.
COLUMBUS | US 74/US 76 | NCDOT | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-5819 | REGION C | T | 2021 | 346000 | 2021 | 129000 | 2022 | 11665000 |  |  | 12140000 | COMBINE WITH R-5820. UNDER CONSTRUCTION.
COLUMBUS | US 74 / 76 | NCDOT | ADVANCED CONSTRUCTION OF TEMPORARY REDUCED CONFLICT INTERSECTIONS AT SR 1735 (CHAUNCEY TOWN ROAD) AND SR 1740 (OLD LAKE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-5819A | REGION C | T |  |  |  |  | 2021 | 2300000 |  |  | 2300000 | UNDER CONSTRUCTION.
COLUMBUS | US 74/US 76 | NCDOT | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO | R-5820 | REGION C | T | 2021 | 931000 | 2021 | 1297000 | 2022 | 50713000 |  |  | 52941000 | COMBINE WITH R-5819. UNDER CONSTRUCTION.
COLUMBUS | NC 11 | NCDOT | NC 11 AT SR 1740 (OLD LAKE ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | SAFETY | 6 | CAPE FEAR RPO | W-5806A | REGION C | HSIP | 2024 | 85000 |  |  | 2025 | 1342000 |  |  | 1427000
COLUMBUS | COLUMBUS COUNTY | COLUMBUS COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6 | CAPE FEAR RPO | TK-6121 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 688000 | 688000 | FUNDS AUTHORIZED IN PROGRESS
COLUMBUS, ROBESON | US 74 | NCDOT | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPE FEAR RPO, LUMBER RIVER RPO | I-6011 | NOT FUNDED | T | NOT FUNDED | 179000 | NOT FUNDED | 1469000 | NOT FUNDED | 169100000 |  |  | 170748000
COLUMBUS, ROBESON, ANSON, SCOTLAND, RICHMOND, BRUNSWICK, UNION | US 74 | NCDOT | EASTERN END OF MONROE BYPASS TO I-140 IN WILMINGTON. VULNERABILITY ASSESSMENTS, INSTALLATION OF FLOOD GAUGES, AND FLOOD MONITORING. | HIGHWAY | OTHER | 3, 6, 8, 10 | LUMBER RIVER RPO, CAPE FEAR RPO, ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, WILMINGTON URBAN AREA MPO | HO-0002D | STATEWIDE MOBILITY | DP, T | [6 empty] | 2022 | 2200000 | 2200000
COLUMBUS, ROBESON, BRUNSWICK | US 74 | NCDOT | I-95 IN LUMBERTON TO I-140 IN WILMINGTON. INSTALL BROADBAND. | HIGHWAY | OTHER | 3, 6 | CAPE FEAR RPO, LUMBER RIVER RPO, WILMINGTON URBAN AREA MPO | HO-0002C | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 10456000 |  |  | 10456000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002B. UNDER CONSTRUCTION.
COLUMBUS, ROBESON, CLEVELAND, ANSON, GASTON, POLK, SCOTLAND, HENDERSON, RICHMOND, RUTHERFORD, MECKLENBURG, BRUNSWICK, BUNCOMBE, UNION | US 74 | NCDOT | I-40 IN ASHEVILLE TO I-140 IN WILMINGTON. IMPLEMENT BROADBAND, ITS, AND RESILIENCY IMPROVEMENTS. | HIGHWAY | OTHER | 3, 6, 8, 10, 12, 13, 14 | LUMBER RIVER RPO, CAPE FEAR RPO, GASTON-CLEVELAND-LINCOLN MPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, WILMINGTON URBAN AREA MPO | HO-0002 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS.
CRAVEN | COASTAL CAROLINA REGIONAL AIRPORT (EWN) | COASTAL CAROLINA REGIONAL AIRPORT (EWN) | RUNWAY EXTENSION. | AVIATION | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | AV-5891 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 300000 |  |  | 300000
CRAVEN | ROAD) SR 1470 (MAPLE CYPRESS | NCDOT | REPLACE BRIDGE 240138 AND 240139 OVER NEUSE RIVER. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-4484 | DIVISION 2 | T |  |  |  |  | 2021 | 18700000 |  |  | 18700000 | UNDER CONSTRUCTION.
CRAVEN | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE NEW BERN PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 2 | NEW BERN AREA MPO | HL-0104 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 792000 |  |  | 792000
CRAVEN | SR 1001 / SR 1256 (MAIN STREET) | NCDOT | SR 1001 / SR 1256 (MAIN STREET) AT SR 1005 (SUNSET BOULEVARD). INSTALL ALL WAY STOP, REVISE OVERHEAD FLASHER, AND INSTALL CHANNELIZATION. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | HS-2002F | DIVISION 2 | HSIP | 2022 | 15000 |  |  | 2023 | 58000 |  |  | 73000 | RIGHT-OF-WAY IN PROGRESS.
CRAVEN | US 17 BUSINESS (MARTIN LUTHER KING JR. BOULEVARD) | NCDOT | US 17 BUSINESS (MARTIN LUTHER KING JR. BOULEVARD) AT TRENT CREEK ROAD. INSTALL FLASHER. | HIGHWAY | SAFETY | 2 | NEW BERN AREA MPO | HS-2002O | REGION B | HSIP |  |  |  |  | 2023 | 25000 |  |  | 25000 | UNDER CONSTRUCTION.
CRAVEN | NC 55 (NEUSE BOULEVARD) | NCDOT | AT SR 1215 (SIMMONS STREET) IN NEW BERN. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | HIGHWAY | SAFETY | 2 | NEW BERN AREA MPO | HS-2002V | REGION B | HSIP |  |  |  |  | 2024 | 18000 |  |  | 18000
CRAVEN | NC 55 (NEUSE BOULEVARD) | NCDOT | AT SR 1309 / SR 1402 (GLENBURNIE ROAD) IN NEW BERN. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | HIGHWAY | SAFETY | 2 | NEW BERN AREA MPO | HS-2002W | REGION B | HSIP |  |  |  |  | 2024 | 18000 |  |  | 18000
CRAVEN | US 70 (HAVELOCK BYPASS) | NCDOT | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-1015 | [11 empty] | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8M FOR RIGHT-OF-WAY, $2.2M FOR UTILITIES, AND $100M FOR CONSTRUCTION, PAYBACK FY 2019 - 2033.
CRAVEN | US 70 (HAVELOCK BYPASS) | NCDOT | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | R-1015DIV | DIVISION 2 | NHP, S(M) | 2019 | 2603000 | 2019 | 1517000 | 2019 | 114172000 |  |  | 118292000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
CRAVEN | US 70 (HAVELOCK BYPASS) | NCDOT | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | R-1015REG | REGION B | NHP, S(M) | 2019 | 2603000 | 2019 | 1517000 | 2019 | 105707000 |  |  | 109827000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
CRAVEN | US 17 NEW BERN BYPASS | NCDOT | US 17 SOUTH OF NEW BERN TO US 70. | HIGHWAY | PRE-STI (HISTORIC) | 2 | NEW BERN AREA MPO | R-2301A | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 3713000 |  |  | 3713000 | COMPLETED.
CRAVEN | US 17 NEW BERN BYPASS | NCDOT | US 70 TO US 17 NORTH OF NEW BERN. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-2301B | NOT FUNDED | T | NOT FUNDED | 15800000 |  |  | NOT FUNDED | 146000000 |  |  | 161800000
CRAVEN | US 17 | NCDOT | NC 43 TO SR 1438 (SPRUILL TOWN ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-2513
CRAVEN | US 17 | NCDOT | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-2513A | DIVISION 2 | T | 2026 | 3000000 | 2026 | 2400000 | 2028 | 15200000 |  |  | 20600000
CRAVEN | US 17 | NCDOT | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-2513B | NOT FUNDED | T | NOT FUNDED | 5800000 | NOT FUNDED | 800000 | NOT FUNDED | 16300000 |  |  | 22900000
CRAVEN | US 17 | NCDOT | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-2513C | NOT FUNDED | T | NOT FUNDED | 2300000 | NOT FUNDED | 600000 | NOT FUNDED | 11300000 |  |  | 14200000
CRAVEN | US 17 | NCDOT | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-2513D | NOT FUNDED | T | NOT FUNDED | 4600000 | NOT FUNDED | 600000 | NOT FUNDED | 21000000 |  |  | 26200000
CRAVEN | US 17 | NCDOT | MILLS STREET IN BRIDGETON TO NC 43. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-3403 | REGION B
CRAVEN | US 17 | NCDOT | MILLS STREET IN BRIDGETON TO NORTH "C" STREET. | HIGHWAY | PRE-STI (HISTORIC) | 2 | DOWN EAST RPO | R-3403AA | [11 empty] | COMPLETED.
CRAVEN | US 17 | NCDOT | NORTH "C" STREET TO NORTH OF SR 1433 (ANTIOCH ROAD). | HIGHWAY | PRE-STI (HISTORIC) | 2 | DOWN EAST RPO | R-3403AB | [11 empty] | COMPLETED.
CRAVEN | US 17 | NCDOT | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-3403B | REGION B | T | 2027 | 6000000 | 2027 | 4500000 | 2029 | 71799000 |  |  | 82299000
CRAVEN | NC 43 CONNECTOR | NCDOT | NC 43/NC 55 TO US 17 IN NEW BERN. CONSTRUCT ROUTE ON NEW LOCATION WITH INTERCHANGE AT US 70. | HIGHWAY | PRE-STI (HISTORIC) | 2 | NEW BERN AREA MPO | R-4463
CRAVEN | NC 43 CONNECTOR | NCDOT | US 17 BUSINESS TO SOUTH OF US 17/US 70. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | R-4463A | REGION B | T | 2020 | 3440000 | 2023 | 1000000 | 2025 | 24500000 | 2020 | 1725000 | 30665000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
CRAVEN | NC 43 CONNECTOR | NCDOT | SOUTH OF US17/US 70 TO US 70. | HIGHWAY | TRANSITION | 2 | NEW BERN AREA MPO | R-4463AA | [11 empty] | COMPLETED.
CRAVEN | NC 43 CONNECTOR | NCDOT | US 70 TO NC 43/NC 55. | HIGHWAY | ECONOMIC DEVELOPMENT | 2 | NEW BERN AREA MPO | R-4463B | [11 empty] | COMPLETED. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOSCH CORPORATION.
CRAVEN | US 70 | NCDOT | SLOCUMB ROAD AT CHERRY POINT MILITARY BASE. CONSTRUCT INTERCHANGE. | HIGHWAY | TRANSITION | 2 | DOWN EAST RPO | R-5516 | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CRAVEN | US 70 | NCDOT | SR 1124 (GRANTHAM ROAD) TO THE PROPOSED US 70 HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | R-5777
CRAVEN | US 70 | NCDOT | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | R-5777A | STATEWIDE MOBILITY | T | 2020 | 47438000 | 2020 | 300000 | 2020 | 50778000 |  |  | 98516000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713.
CRAVEN | US 70 | NCDOT | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | R-5777B | REGION B | T | 2020 | 47447000 | 2020 | 300000 | 2020 | 50778000 | 2020 | 105000 | 98630000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
CRAVEN | US 70 | NCDOT | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | R-5777C | STATEWIDE MOBILITY | T | 2023 | 29129000 | 2023 | 13344000 | 2023 | 278703000 |  |  | 321176000 | RIGHT-OF-WAY IN PROGRESS.
CRAVEN | SR 1763 (MILLER BOULEVARD) | NCDOT | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | U-3431 | DIVISION 2 | T | 2026 | 18759000 | 2026 | 4864000 | 2028 | 36399000 |  |  | 60022000
CRAVEN | US 70 | NCDOT | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | U-5713 | STATEWIDE MOBILITY | T | 2020 | 75600000 | 2020 | 1000000 | 2020 | 152337000 |  |  | 228937000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B.
CRAVEN | NC 55 (NEUSE BOULEVARD) | NCDOT | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | U-5993 | REGION B | T | 2026 | 400000 |  |  | 2028 | 4200000 |  |  | 4600000
CRAVEN | US 70 | NCDOT | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | U-6102 | NOT FUNDED | T | NOT FUNDED | 2700000 | NOT FUNDED | 500000 | NOT FUNDED | 21200000 |  |  | 24400000
CRAVEN | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | NCDOT | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO | U-6198 | NOT FUNDED | T | NOT FUNDED | 18000000 | NOT FUNDED | 3100000 | NOT FUNDED | 24700000 |  |  | 45800000
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | TA-5165 RURAL VEHICLE REPLACEMENT. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 2 | NEW BERN AREA MPO | TA-5165 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 310000 | 310000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | MOBILITY MANAGEMENT | PUBLIC TRANSIT | CAPITAL (NON-STI) | 2 | NEW BERN AREA MPO | TC-5100 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 90000 | 90000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CARTS | CARTS | TG-5026 LEASE OF TABLETS | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 2 | NEW BERN AREA MPO | TG-5026 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 0
CRAVEN | CARTS | CARTS | TG-5122 SHORT RANGE PLANNING | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 2 | NEW BERN AREA MPO | TG-5122 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 0
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 2 | NEW BERN AREA MPO | TG-5256 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 170000 | 170000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | ADA/PARATRANSIT | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 2 | NEW BERN AREA MPO | TG-5257 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 274000 | 274000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 2 | DOWN EAST RPO | TK-6122 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1356000 | 1356000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 2 | NEW BERN AREA MPO | TO-5024 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2100000 | 2100000
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 2 | NEW BERN AREA MPO | TO-5204 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 2 | DOWN EAST RPO | TO-6102 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 344000 | 344000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | SHORT RANGE PLANNING | PUBLIC TRANSIT | PLANNING | 2 | NEW BERN AREA MPO | TP-5122 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 30000 | 30000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | LEASE OF TABLETS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 2 | NEW BERN AREA MPO | TT-5206 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 36000 | 36000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN, JOHNSTON, WAYNE, LENOIR, CARTERET, WAKE | US 70 | NCDOT | INSTALL BROADBAND FIBER ALONG US 70 FROM I-40 TO PORT OF MOREHEAD CITY. | HIGHWAY | STI (PRIORITIZATION) | 2, 4, 5 | DOWN EAST RPO, EASTERN CAROLINA RPO, NEW BERN AREA MPO, UPPER COASTAL PLAIN RPO, GOLDSBORO URBAN AREA MPO, CAPITAL AREA MPO | R-5777D | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2021 | 26000000 |  |  | 26000000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5986C, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
CRAVEN, JONES | US 17 (NEW BERN BYPASS) | NCDOT | US 17 SOUTH OF NEW BERN TO US 17 NORTH OF NEW BERN. FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 2 | NEW BERN AREA MPO, DOWN EAST RPO | R-2301 | [11 empty] | SECTION A GARVEE BOND FUNDING: $33.9 MILLION FOR CON, PAYBACK FY 2009-2020.
CUMBERLAND | FAYETTEVILLE REGIONAL AIRPORT (FAY) | FAYETTEVILLE REGIONAL AIRPORT (FAY) | REPLACE PERIMETER FENCING AND ROAD. | AVIATION | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | AV-5734 | REGION C | O, T |  |  |  |  | 2024 | 3440000 |  |  | 3440000
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | CAPE FEAR RIVER GREENWAY, CLARK PARK SOUTH TO THE CAPE FEAR BOTANICAL GARDENS. CONSTRUCT SECOND PHASE OF AN OFF-ROAD MULTI-USE TRAIL. | BIKE/PED | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | EB-4539 | PRE-STI (TRANSITION)
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | I-95 BUSINESS/US 301 TO THE SOUTH SIDE OF CSX RAIL LINE. | BIKE/PED | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | EB-4539A | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION.
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | EXISTING TRAIL AT CLARK PARK TO NORTH SIDE OF CSX RAIL LINE. | BIKE/PED | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | EB-4539BB | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION.
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | NORTH OF CSX RAIL LINE TO SOUTH OF CSX RAIL LINE. | BIKE/PED | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | EB-4539BC | PRE-STI (TRANSITION) | L, TAANY |  |  |  |  | 2020 | 951000 |  |  | 951000 | UNDER CONSTRUCTION.
CUMBERLAND | LITTLE CROSS CREEK GREENWAY EXTENSION | FAYETTEVILLE | FILTER PLANT DRIVE TO ROWAN STREET BRIDGE IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | EB-5540 | DIVISION 6 | L, TAANY |  |  |  |  | 2023 | 750000 |  |  | 750000
CUMBERLAND | BIG CROSS CREEK GREENWAY | FAYETTEVILLE | LITTLE CROSS CREEK TO SMITH LAKE IN FORT BRAGG. CONSTRUCT MULTI-USE TRAIL. | BIKE/PED | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | EB-5541 | NOT FUNDED | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY USING STBGDA FUNDS
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | EB-5907 | DIVISION 6 | L, TAANY | 2024 | 10000 |  |  | 2026 | 842000 | 2023 | 84000 | 936000
CUMBERLAND | US 401 BYPASS (SKIBO ROAD) | FAYETTEVILLE | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | BIKE/PED | LOCALLY SELECTED | 6 | FAYETTEVILLE AREA MPO | EB-6030 | DIVISION 6 | L, TADA | 2023 | 75000 |  |  | 2024 | 450000 | 2022 | 75000 | 600000
CUMBERLAND | US 401 (RAMSEY STREET) | FAYETTEVILLE | CONSTRUCT SIDEWALK FROM SUMMERCHASE DRIVE TO SR 1611 (ANDREWS ROAD). | BIKE/PED | LOCALLY SELECTED | 6 | FAYETTEVILLE AREA MPO | EB-6031 | DIVISION 6 | L, TADA |  |  |  |  | 2021 | 85000 |  |  | 85000 | UNDER CONSTRUCTION.
CUMBERLAND | NC 59 (HOPE MILLS ROAD) | FAYETTEVILLE | CONSTRUCT SIDEWALK FROM FAYETTEVILLE CITY LIMITS TO SUMAC CIRCLE. | BIKE/PED | LOCALLY SELECTED | 6 | FAYETTEVILLE AREA MPO | EB-6032 | DIVISION 6 | L, TADA |  |  |  |  | 2022 | 375000 |  |  | 375000 | UNDER CONSTRUCTION.
CUMBERLAND | SPRING LAKE | SPRING LAKE | CONSTRUCT GREENWAY TRAIL NEAR THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | BIKE/PED | LOCALLY SELECTED | 6 | FAYETTEVILLE AREA MPO | EB-6041 | DIVISION 6 | L, TADA |  |  |  |  | 2020 | 545000 |  |  | 545000 | UNDER CONSTRUCTION.
CUMBERLAND | NC 24/NC 210 | NCDOT | REPLACE BRIDGE 250116 OVER CSX RAILROAD, NORFOLK SOUTHERN RAILROAD, AND HILLSBORO STREET. | HIGHWAY | BRIDGES | 6 | FAYETTEVILLE AREA MPO | B-4490 | STATEWIDE MOBILITY | [10 empty] | COMPLETED.
CUMBERLAND | NC 59 | NCDOT | REPLACE BRIDGE 250022 OVER I-95 BUSINESS/US 301. | HIGHWAY | BRIDGES | 6 | FAYETTEVILLE AREA MPO | B-4491 | REGION C | NHPB |  |  |  |  | 2018 | 3533000 |  |  | 3533000 | COMPLETED.
CUMBERLAND | NC 24 | NCDOT | REPLACE BRIDGE 250144 OVER SOUTH RIVER. | HIGHWAY | BRIDGES | 6 | MID-CAROLINA RPO | B-5708 | STATEWIDE MOBILITY | T | 2026 | 464000 | 2026 | 56000 | 2027 | 5000000 |  |  | 5520000
CUMBERLAND | SR 2030 (HOLLOW BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 250044 OVER SANDY CREEK AND BRIDGE 250043 OVER SANDY CREEK OVERFLOW. | HIGHWAY | BRIDGES | 6 | MID-CAROLINA RPO | B-6009 | DIVISION 6 | [10 empty] | COMPLETED.
CUMBERLAND | SR 1716 (JACKIE LEE ROAD) | NCDOT | REPLACE BRIDGE 250091 OVER WADE CANAL. | HIGHWAY | BRIDGES | 6 | FAYETTEVILLE AREA MPO | HB-0010 | DIVISION 6 | BGOFF | 2029 | 120000 |  |  | 2030 | 850000 |  |  | 970000
CUMBERLAND | FAYETTEVILLE | NCDOT | CONSTRUCT NEW ACCESS ROAD WITH IMPROVEMENTS AT INTERSECTION WITH SR 1838 (DUNN ROAD) IN FAYETTEVILLE. | HIGHWAY | ECONOMIC DEVELOPMENT | 6 | FAYETTEVILLE AREA MPO | HE-0012 | DIVISION 6 | T | 2023 | 20000 | 2023 | 50000 | 2023 | 1100000 |  |  | 1170000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC.
CUMBERLAND | I-95 | NCDOT | I-95 FROM THE ROBESON COUNTY LINE TO NC 53/210. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | FAYETTEVILLE AREA MPO | HI-0021 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2029 | 8000000 |  |  | 8000000
CUMBERLAND | I-95 | NCDOT | I-95 FROM NC 53 TO I-95 BUSINESS / US 301. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | FAYETTEVILLE AREA MPO | HI-0022 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2029 | 5800000 |  |  | 5800000
CUMBERLAND | NC 59 (NORTH MAIN STREET) | HOPE MILLS | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW SIDEWALK ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | HIGHWAY | LOCALLY SELECTED | 6 | FAYETTEVILLE AREA MPO | HL-0036 | DIVISION 6 | L, TADA |  |  |  |  | 2023 | 449000 | 2021 | 50000 | 499000
CUMBERLAND | SR 1415 (YADKIN ROAD) | NCDOT | SR 1415 (YADKIN ROAD) AT US 401 (SKIBO ROAD), AT SR 1437 (SANTE FE DRIVE), AND AT SOUTHWICK DRIVE. ADD SIGNALIZED PEDESTRIAN CROSSINGS TO ALL THREE INTERSECTIONS AND UPGRADE SIGNAL AT SOUTHWICK DRIVE. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006A | DIVISION 6 | HSIP |  |  |  |  | 2023 | 455000 |  |  | 455000 | UNDER CONSTRUCTION.
CUMBERLAND | SR 1006 (PERSON STREET) | NCDOT | SR 1006 (PERSON STREET) FROM US 301 / I-95 BUSINESS (EASTERN BOULEVARD) TO JUST EAST OF WATER STREET. CONVERT SECTION FROM FOUR LANES TO THREE LANES WITH INTERSECTION IMPROVEMENTS AT BROAD STREET AND EASTERN BOULEVARD IN FAYETTEVILLE. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006B | DIVISION 6 | HSIP |  |  |  |  | 2022 | 651000 |  |  | 651000 | UNDER CONSTRUCTION.
CUMBERLAND | NC 53 (CEDAR CREEK ROAD) | NCDOT | NC 53 (CEDAR CREEK ROAD) FROM JUST NORTH OF PLYMOUTH STREET TO JUST SOUTH OF TROY DRIVE. INSTALL MEDIAN WITH SOUTHBOUND U-TURN AND BULB-OUT, SIDEWALK, AND RECTANGULAR RAPID FLASHING BEACON PEDESTRIAN CROSSING WITH REFUGE IN FAYETTEVILLE. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006C | REGION C | HSIP | 2023 | 15000 |  |  | 2024 | 1142000 |  |  | 1157000 | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND | SR 1835 (ROCK HILL ROAD) | NCDOT | SR 1835 (ROCK HILL ROAD) AT SR 1838 (DUNN ROAD) IN EASTOVER. REALIGN SR 1838 (DUNN ROAD) TO FORM A T-INTERSECTION WITH SR 1835 (ROCK HILL ROAD) AND REMOVE SLIP LANES. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006G | DIVISION 6 | HSIP |  |  |  |  | 2023 | 336000 |  |  | 336000 | UNDER CONSTRUCTION.
CUMBERLAND | SR 1596 (GLENSFORD DRIVE) | NCDOT | FROM US 401 (RAEFORD ROAD) AND SR 1400 (CLIFFDALE ROAD) IN FAYETTEVILLE. PAVEMENT MARKING AND SIGNING IMPROVEMENTS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006N | DIVISION 6 | HSIP |  |  |  |  | 2024 | 81000 |  |  | 81000
CUMBERLAND | SR 1596 (GLENSFORD DRIVE) | NCDOT | SR 1596 (GLENSFORD DRIVE) AT BEREAN BAPTIST ACADEMY AND AT CHAMBERSURG ROAD IN FAYETTEVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS WITH REFUGE ISLANDS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006O | DIVISION 6 | HSIP |  |  |  |  | 2024 | 250000 |  |  | 250000
CUMBERLAND | SR 3950 (RAMSEY STREET) | NCDOT | SR 3950 (RAMSEY STREET) AT RAILROAD BRIDGE 250216 IN FAYETTEVILLE. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006P | DIVISION 6 | HSIP |  |  |  |  | 2024 | 191000 |  |  | 191000
CUMBERLAND | SR 1600 (MCARTHUR ROAD) | NCDOT | SR 1600 (MCARTHUR ROAD) AT SR 1615 (ROSEHILL ROAD/STACY WEAVER ROAD) IN FAYETTEVILLE. CONSTRUCT SIGNALIZED PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006V | DIVISION 6 | HSIP |  |  |  |  | 2024 | 190000 |  |  | 190000
CUMBERLAND | US 401 (SKIBO ROAD) | NCDOT | AT SR 1007 (ALL AMERICAN FREEWAY) NORTHBOUND AND SOUTHBOUND RAMPS IN FAYETTEVILLE. INSTALL SIGNALIZED PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006X | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2024 | 880000 |  |  | 880000
CUMBERLAND | NC 24 | NCDOT | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO SR 1853 (JOHN NUNNERY ROAD). | HIGHWAY | PRE-STI (HISTORIC) | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO | R-2303A | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
CUMBERLAND | I-295 | NCDOT | SOUTH OF SR 1118 (PARKTON ROAD) TO SOUTH OF SR 1003 (CAMDEN ROAD). | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO, LUMBER RIVER RPO | U-2519AB | REGION C | [10 empty] | DESIGN BUILD PROJECT. WORK BEING ACCOMPLISHED UNDER U-2519AA.
CUMBERLAND | I-295 | NCDOT | SOUTH OF SR 1003 (CAMDEN ROAD) TO SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-2519BA | REGION C | NHP |  |  |  |  | 2022 | 161113000 |  |  | 161113000 | UNDER CONSTRUCTION.
CUMBERLAND | I-295 | NCDOT | SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD) TO SOUTH OF US 401. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-2519BB | REGION C | NHP |  |  |  |  | 2022 | 55880000 |  |  | 55880000 | UNDER CONSTRUCTION.
CUMBERLAND | I-295 | NCDOT | SOUTH OF US 401 TO SOUTH OF SR 1400 (CLIFFDALE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-2519CA | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION. DESIGN BUILD PROJECT.
CUMBERLAND | I-295 | NCDOT | SOUTH OF SR 1400 (CLIFFDALE ROAD) TO EAST OF SR 1415 (YADKIN ROAD). | HIGHWAY | TRANSITION | 6 | FAYETTEVILLE AREA MPO | U-2519CB | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
CUMBERLAND | I-295 | NCDOT | EAST OF SR 1415 (YADKIN ROAD) TO WEST OF NC24/NC 87 (BRAGG BOULEVARD). | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | U-2519DA | [11 empty] | COMPLETED.
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NCDOT | NC 59 (HOPE MILLS ROAD) TO SR 1007 (OWEN DRIVE) IN FAYETTEVILLE. WIDEN ROADWAY TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | U-2810
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NCDOT | NC 59 (HOPE MILLS ROAD) TO NC 162 (HOPE MILLS BYPASS). | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | U-2810A | [11 empty] | COMPLETED.
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NCDOT | NC 162 (HOPE MILLS BYPASS TO EAST OF CSX RAILROAD. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | U-2810B | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NCDOT | EAST OF CSX RAILROAD TO SR 1007 (OWEN DRIVE). | HIGHWAY | TRANSITION | 6 | FAYETTEVILLE AREA MPO | U-2810C | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NCDOT | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-3422 | DIVISION 6 | BGANY, T | 2021 | 9975000 | 2021 | 2825000 | 2024 | 36980000 |  |  | 49780000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE).
CUMBERLAND | US 401 (RAMSEY STREET) | NCDOT | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO NORTH OF SLOCUMB ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4403
CUMBERLAND | US 401 BUSINESS | NCDOT | NC 24/210 (GROVE STREET) TO US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY). | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4403A | NOT FUNDED | T | NOT FUNDED | 3121000 |  |  | NOT FUNDED | 7400000 |  |  | 10521000
CUMBERLAND | US 401 BUSINESS | NCDOT | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4403B | REGION C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10123000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12020000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33002000 |  |  | 55145000
CUMBERLAND | US 401 | NCDOT | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4403C | DIVISION 6 | T | 2026 | 27001000 | 2026 | 26328000 | 2029 | 34699000 |  |  | 88028000 | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | NCDOT | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4404 | DIVISION 6 | T | 2028 | 4391000 | 2028 | 1020000 | 2030 | 10400000 |  |  | 15811000
CUMBERLAND | US 401 (RAEFORD ROAD) | NCDOT | SR 3569 (OLD RAEFORD ROAD) TO EAST OF SR 3828 (ROBESON STREET) IN FAYETTEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4405 | DIVISION 6 | [10 empty] | RIGHT OF WAY IN PROGRESS.
CUMBERLAND | US 401 (RAEFORD ROAD) | NCDOT | OLD RAEFORD ROAD TO EAST OF BUNCE ROAD. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4405A | DIVISION 6 | BGANY |  |  |  |  | 2022 | 35403000 |  |  | 35403000 | UNDER CONSTRUCTION.
CUMBERLAND | US 401 (RAEFORD ROAD) | NCDOT | EAST OF BUNCE ROAD TO EAST OF GLENSFORD DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4405B | DIVISION 6 | BGANY |  |  |  |  | 2024 | 23099000 |  |  | 23099000
CUMBERLAND | US 401 (RAEFORD ROAD) | NCDOT | EAST OF SR 1596 (GLENSFORD DRIVE) TO EAST OF ROBESON STREET. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4405C | DIVISION 6 | BGANY |  |  |  |  | 2025 | 41401000 |  |  | 41401000
CUMBERLAND | SR 1007 (ALL AMERICAN FREEWAY) | NCDOT | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4414 | REGION C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1548000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 919000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 67101000 |  |  | 69568000
CUMBERLAND | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | NCDOT | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4709 | DIVISION 6 | T | 2022 | 9556000 | 2022 | 1575000 | 2024 | 13700000 |  |  | 24831000 | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND | NC 210 (MURCHISON ROAD) | NCDOT | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-4900 | EXEMPT | BGDA, S(M) | 2023 | 10600000 | 2023 | 15000000 | 2025 | 23300000 |  |  | 48900000 | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT.
CUMBERLAND | NC 210 (MURCHISON ROAD) | NCDOT | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5015 | NOT FUNDED | T | NOT FUNDED | 14900000 | NOT FUNDED | 2200000 | NOT FUNDED | 8300000 |  |  | 25400000
CUMBERLAND | SR 1437 (SHAW ROAD) SR 1614 (SHAW MILL ROAD) SR 16 | NCDOT | NC 24/87 (BRAGG BLVD) TO US 401 (RAMSEY STREET). WIDEN ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5101 | DIVISION 6
CUMBERLAND | SR 1437 (SHAW RD) | NCDOT | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5101A | DIVISION 6 | T | 2026 | 22090000 | 2026 | 9167000 | 2028 | 36601000 |  |  | 67858000 | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT OF WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
CUMBERLAND | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NCDOT | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5101B | NOT FUNDED | T | NOT FUNDED | 38500000 | NOT FUNDED | 21445000 | NOT FUNDED | 36300000 |  |  | 96245000
CUMBERLAND | FAYETTEVILLE | NCDOT | FAYETTEVILLE COMPUTERIZED TRAFFIC SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5742 | REGION C | T |  |  |  |  | 2019 | 735000 |  |  | 735000 | COMPLETED. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
CUMBERLAND | SR 1102 (GILLIS HILL ROAD) | NCDOT | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO FOUR LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5798A | DIVISION 6 | T | 2020 | 9322000 | 2020 | 475000 | 2022 | 26036000 |  |  | 35833000 | UNDER CONSTRUCTION.
CUMBERLAND | NC 24 / NC 87 | NCDOT | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5802 | DIVISION 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25101000 |  |  | 63101000
CUMBERLAND | NC 24 (NORTH BRAGG BOULEVARD) | NCDOT | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5930 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 67500000 |  |  | 97400000
CUMBERLAND | NC 59 (SOUTH MAIN STREET) | NCDOT | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6001 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1028000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10699000 |  |  | 12427000
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | NCDOT | STRICKLAND BRIDGE ROAD TO GOLFVIEW ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6072
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | NCDOT | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6072A | NOT FUNDED | T | NOT FUNDED | 13600000 | NOT FUNDED | 4960000 | NOT FUNDED | 24500000 |  |  | 43060000
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | NCDOT | CAMDEN ROAD TO GOLFVIEW ROAD. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6072B | NOT FUNDED | T | NOT FUNDED | 10400000 | NOT FUNDED | 1100000 | NOT FUNDED | 4300000 |  |  | 15800000
CUMBERLAND | FISHER ROAD | NCDOT | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6073 | DIVISION 6 | BGANY | 2026 | 17600000 | 2026 | 2138000 | 2028 | 22300000 |  |  | 42038000
CUMBERLAND | US 401 BUSINESS (SKIBO ROAD) | NCDOT | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6133 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6900000 |  |  | 15900000
CUMBERLAND | US 401 (ROBESON STREET) | NCDOT | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6152 | NOT FUNDED | NHP | NOT FUNDED | 17500000 | NOT FUNDED | 19700000 | NOT FUNDED | 19900000 |  |  | 57100000
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | NCDOT | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6209 | DIVISION 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 32300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36400000 |  |  | 86000000
CUMBERLAND | SR 1104 (STRICKLAND BRIDGE ROAD) | NCDOT | US 401 TO FISHER ROAD. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6210 | NOT FUNDED | T | NOT FUNDED | 15000000 | NOT FUNDED | 7900000 | NOT FUNDED | 22800000 |  |  | 45700000
CUMBERLAND | SR 1219 (IRELAND DRIVE) | NCDOT | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-6213 | NOT FUNDED | T | NOT FUNDED | 16600000 | NOT FUNDED | 19750000 | NOT FUNDED | 22500000 |  |  | 58850000
CUMBERLAND | NC 24 (BRAGG BOULEVARD) | NCDOT | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | U-6229 | DIVISION 6 | HSIP, T |  |  | 2022 | 200000 | 2023 | 5400000 |  |  | 5600000 | UNDER CONSTRUCTION.
CUMBERLAND | VARIOUS | NCDOT | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | W-5206DIV | DIVISION 6
CUMBERLAND | VARIOUS | NCDOT | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | W-5206SW | STATEWIDE MOBILITY
CUMBERLAND | I-95 BUSINESS/US 301 | NCDOT | NC 87 SOUTH TO NC 59. SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | W-5519 | REGION C | [10 empty] | COMPLETED.
CUMBERLAND | SR 1404 (HAY STREET / MORGANTON ROAD) | NCDOT | AT THE SR 3578 (FORT BRAGG ROAD), OAKRIDGE AVENUE, AND HIGHLAND AVENUE INTERSECTION IN FAYETTEVILLE. UPGRADE TRAFFIC SIGNALS AND IMPROVE PEDESTRIAN CROSSINGS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | W-5706U | DIVISION 6 | HSIP |  |  |  |  | 2025 | 100000 |  |  | 100000
CUMBERLAND | SR 1615 (ROSEHILL ROAD) | NCDOT | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | W-5806C | DIVISION 6 | HSIP | 2021 | 75000 |  |  | 2023 | 1850000 |  |  | 1925000 | UNDER CONSTRUCTION.
CUMBERLAND | I-295 (FAYETTEVILLE OUTER LOOP) | NCDOT | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO I-95. FREEWAY ON NEW LOCATION WITH STRUCTURE OVER THE CAPE FEAR RIVER. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). - GRADING AND STRUCTURES | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002B | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). PAVING | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002BB | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | NC 210 (MURCHISON ROAD) TO 1.1 MILES EAST OF NC 210. GRADING AND STRUCTURES | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002BC | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | 1.1 MILES EAST OF NC 210 (MURCHISON ROAD) TO EAST OF SR 1600 (MCARTHUR ROAD). GRADING AND STRUCTURES | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002CA | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | EAST OF SR 1600 (MCARTHUR ROAD) TO US 401. - GRADING AND STRUCTURES | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002CB | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | EAST OF SR 1007 (ALL AMERICAN FREEWAY) TO EAST OF US 401 (RAMSEY STREET). PAVING | HIGHWAY | TRANSITION | 6 | FAYETTEVILLE AREA MPO | X-0002CC | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | WEST OF US 401 TO EAST OF SR 1714 (RIVER ROAD). | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002DA | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | EAST OF SR 1714 (RIVER ROAD) TO WEST OF US 301. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002DB | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | CONNECTOR FROM US 301 TO US 13. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002DC | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | WEST OF US 301 TO EAST OF I-95. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002DD | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | SR 1714 (RIVER ROAD) TO WEST OF US 301. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002DF | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | EAST OF NORFOLK SOUTHERN RAILWAY TO SR 1714 (RIVER ROAD). | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002E | [11 empty] | COMPLETED.
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NCDOT | ITS FOR FAYETTEVILLE OUTER LOOP. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO | X-0002F | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 6 | FAYETTEVILLE AREA MPO | TA-4743A | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 225000 | 225000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN | PUBLIC TRANSIT | CAPITAL (NON-STI) | 6 | FAYETTEVILLE AREA MPO | TA-4743B | PUBLIC TRANSIT | 5307, 5339, L, S | [6 empty] | 2021 | 1850000 | 1850000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 6 | FAYETTEVILLE AREA MPO | TA-4948A | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 2750000 | 2750000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (NON-TRADITIONAL) | PUBLIC TRANSIT | CAPITAL (NON-STI) | 6 | FAYETTEVILLE AREA MPO | TA-5139 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 500000 | 500000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | TA-6685 | DIVISION 6 | FEDT, L, T |  |  |  |  | 2026 | 490000 |  |  | 490000
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | SYSTEM TRANSIT FAYETTEVILLE AREA | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6 | FAYETTEVILLE AREA MPO | TG-5224A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 6000000 | 6000000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 6 | FAYETTEVILLE AREA MPO | TG-5224C | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 840000 | 840000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - SUPPORT VEHICLE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 6 | FAYETTEVILLE AREA MPO | TG-5224D | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 100000 | 100000
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - ADA SERVICES | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 6 | FAYETTEVILLE AREA MPO | TG-5224E | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 363000 | 363000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | CUMBERLAND COUNTY | CUMBERLAND COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6 | MID-CAROLINA RPO | TK-6123 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 320000 | 320000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 6 | FAYETTEVILLE AREA MPO | TO-5132 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 2136000 | 2136000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE (LESS THAN 75 BUSES) MAP 21 | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 6 | FAYETTEVILLE AREA MPO | TO-5144 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1600000 | 1600000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | CAPITAL (NON-STI) | 6 | FAYETTEVILLE AREA MPO | TP-5103 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 264000 | 264000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6 | FAYETTEVILLE AREA MPO | TP-5103B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1800000 | 1800000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (TRADITIONAL) | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6 | FAYETTEVILLE AREA MPO | TQ-6514 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 624000 | 624000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 6 | FAYETTEVILLE AREA MPO | TS-5109 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 6 | FAYETTEVILLE AREA MPO | TT-5204 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2022 | 50000 | 50000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SR 1714 (CHURCH STREET) | NCDOT | CSX CROSSING 629869Y IN WADE. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | MID-CAROLINA RPO | RX-2006A | DIVISION 6 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
CUMBERLAND, HARNETT | I-95 | NCDOT | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO | I-5986A | STATEWIDE MOBILITY | T | 2019 | 30400000 | 2023 | 2000000 | 2019 | 375400000 |  |  | 407800000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | NCDOT | FAYETTEVILLE URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. | BIKE/PED | LOCALLY SELECTED | 6, 8 | FAYETTEVILLE AREA MPO | U-5528 | DIVISION 6, 8 | TADA |  |  |  |  | 2020 | 19017000 |  |  | 19017000 | IN PROGRESS.
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | NCDOT | FAYETTEVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | HIGHWAY | LOCALLY SELECTED | 6, 8 | FAYETTEVILLE AREA MPO | HL-0026 | DIVISION 6, 8 | BGDA |  |  |  |  | 2022 | 88993000 |  |  | 88993000
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FAYETTEVILLE PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 6, 8 | FAYETTEVILLE AREA MPO | HL-0095 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 4413000 |  |  | 4413000
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | NCDOT | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. | HIGHWAY | LOCALLY SELECTED | 6, 8 | FAYETTEVILLE AREA MPO | U-5207 | DIVISION 6, 8 | BGDA, L | [6 empty] | 2020 | 2950000 | 2950000 | IN PROGRESS.
CUMBERLAND, HARNETT, JOHNSTON | I-95 | NCDOT | I-95 BUSINESS/US 301 (EXIT 56) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 4, 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, UPPER COASTAL PLAIN RPO | I-5986
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | NCDOT | US 401 (RAEFORD ROAD) TO SR 1418 (LINDSAY ROAD). WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 6, 8 | FAYETTEVILLE AREA MPO | U-5798 | DIVISION 6, 8 | [10 empty] | COORDINATE WITH U-5753, U-5857, AND U-5858.
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | NCDOT | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 6, 8 | FAYETTEVILLE AREA MPO | U-5798B | DIVISION 6, 8 | T | 2023 | 3700000 | 2023 | 710000 | 2025 | 15500000 |  |  | 19910000 | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND, MOORE, ANSON, HOKE, RICHMOND, UNION | COACH AMERICA | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6, 8, 10 |  | TI-6102 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 2584000 | 2584000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND, ROBESON | I-295 (FAYETTEVILLE OUTER LOOP) | NCDOT | I-95 SOUTH OF FAYETTEVILLE TO WEST OF NC 24/87 (BRAGG BOULEVARD). FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO, LUMBER RIVER RPO | U-2519
CUMBERLAND, ROBESON | I-295 | NCDOT | ITS FOR FAYETTEVILLE OUTER LOOP. | HIGHWAY | PRE-STI (HISTORIC) | 6 | FAYETTEVILLE AREA MPO, LUMBER RIVER RPO | U-2519F | STATEWIDE MOBILITY | NHP |  |  |  |  | 2025 | 6000000 |  |  | 6000000
CURRITUCK | US 158 | NCDOT | REHABILITATE BRIDGE 260016 OVER CURRITUCK SOUND. | HIGHWAY | BRIDGES | 1 | ALBEMARLE RPO | B-5937 | STATEWIDE MOBILITY | [10 empty] | COMPLETED.
CURRITUCK | NC 615 (MARSH CAUSEWAY) | NCDOT | HQ/ VC ENTRACE ROAD TO WEST OF KNOTTS ISLAND ROAD. IMPROVE CORRIDOR AT VARIOUS LOCATIONS. | HIGHWAY | FEDERAL LANDS ACCESS PROGRAM | 1 | ALBEMARLE RPO | HF-0008 | EXEMPT | FLAP |  |  |  |  | 2025 | 700000 |  |  | 700000 | FLAP PROJECT NC 71. AWARDED $700K.
CURRITUCK | US 158 | NCDOT | CONSTRUCT ROUNDABOUT AT US 158 AND SR 1147 (INDIANTOWN ROAD). | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO | HS-2001A | REGION A | HSIP |  |  |  |  | 2023 | 45000 |  |  | 45000 | UNDER CONSTRUCTION.
CURRITUCK | US 158 | NCDOT | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO | HS-2001F | REGION A | HSIP, T | 2023 | 2300000 | 2023 | 800000 | 2024 | 2400000 |  |  | 5500000 | RIGHT-OF-WAY IN PROGRESS.
CURRITUCK | NEW ROUTE | NCDOT | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2576 | DIVISION 1 | BGLT5, BOND R, S(M) | 2024 | 16496000 | 2024 | 17412000 | 2024 | 434004000 |  |  | 467912000 | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2024-2038.
CURRITUCK, CAMDEN | US 158 (SHORTCUT ROAD) | NCDOT | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2574 | REGION A | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24151000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5176000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 76201000 |  |  | 105528000
DARE | US 158 | KITTY HAWK | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | EB-5848 | DIVISION 1 | L, TALT5 |  |  |  |  | 2025 | 1280000 |  |  | 1280000
DARE | NC 12 | NCDOT | HATTERAS PARKING LOT IMPROVEMENTS AND CONNECTIVITY MEASURES, HATTERAS LOADING FACILITY | FERRY | OTHER | 1 | ALBEMARLE RPO | F-5702A | DIVISION 1 | [10 empty] | COMPLETED. WORK ACCOMPLISHED UNDER F-5702B.
DARE | NC 12 | NCDOT | REPLACE BRIDGE 270011 (HERBERT C. BONNER BRIDGE) OVER OREGON INLET AND NC 12 IMPROVEMENTS. | HIGHWAY | PRE-STI (HISTORIC) | 1 | ALBEMARLE RPO | B-2500 | PRE-STI (TRANSITION)
DARE | NC 12 | NCDOT | PHASE II, SHORT-TERM IMPROVEMENTS AT PEA ISLAND. | HIGHWAY | PRE-STI (HISTORIC) | 1 | ALBEMARLE RPO | B-2500AB | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
DARE | NC 12 | NCDOT | PHASE II, LONG-TERM IMPROVEMENTS AT RODANTHE. | HIGHWAY | TRANSITION | 1 | ALBEMARLE RPO | B-2500B | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
DARE | NC 12 | NCDOT | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS | HIGHWAY | BRIDGES | 1 | ALBEMARLE RPO | B-5610 | REGION A | NHPB | 2021 | 320000 | 2021 | 440000 | 2023 | 1403000 |  |  | 2163000 | RIGHT-OF-WAY IN PROGRESS.
DARE | US 64 | NCDOT | PRESERVATION OF BRIDGE 270009 ON US 64 IN MANNS HARBOR. | HIGHWAY | BRIDGES | 1 | ALBEMARLE RPO | HB-0017 | REGION A | BFP |  |  |  |  | 2022 | 38823000 |  |  | 38823000 | UNDER CONSTRUCTION.
DARE | US 64 | NCDOT | EAST OF SR 1153 (OLD FERRY LANDING ROAD) TO US 264. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2544 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
DARE | US 64 | NCDOT | EAST OF SR 1153 (OLD FERRY LANDING ROAD) TO WEST OF SR 1102 (EAST LAKE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2544A | NOT FUNDED | T | NOT FUNDED | 1175000 | NOT FUNDED | 315000 | NOT FUNDED | 14700000 |  |  | 16190000
DARE | US 64 | NCDOT | WEST OF SR 1102 (EAST LAKE ROAD) TO EAST OF DARE COUNTY LANDFILL. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2544B | NOT FUNDED | T | NOT FUNDED | 1350000 | NOT FUNDED | 1401000 | NOT FUNDED | 23300000 |  |  | 26051000
DARE | US 64 | NCDOT | EAST OF DARE COUNTY LANDFILL TO US 264. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2544C | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 1860000 | NOT FUNDED | 46200000 |  |  | 48360000
DARE | US 158 | NCDOT | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-3419 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20237000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9608000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 137000000 |  |  | 166845000
DARE | US 158 | NCDOT | NC 12. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-4457 | NOT FUNDED | NHP | NOT FUNDED | 1100000 | NOT FUNDED | 400000 | NOT FUNDED | 5800000 |  |  | 7300000
DARE | SR 1217 (COLLINGTON ROAD) | NCDOT | DEAD END TO US 158 (CROATON HIGHWAY) IN KILL DEVIL HILLS. OPERATIONAL-SAFETY IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5014 | DIVISION 1 | BG5200 |  |  |  |  | 2022 | 22368000 |  |  | 22368000 | UNDER CONSTRUCTION.
DARE | SR 1208 (WEST KITTY HAWK ROAD) | NCDOT | SR 1210 (BOB PERRY ROAD) TO IVY LANE. UPGRADE FACILITY AND REPLACE BRIDGE 270040. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5738 | DIVISION 1 | T |  |  |  |  | 2019 | 4646000 |  |  | 4646000 | COMPLETED. BUILD NC BOND FUNDING: $3,561,232 FOR CONSTRUCTION PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
DARE | VARIOUS | NCDOT | DEPLOYMENT OF AUTOMATED SHUTTLE AT WRIGHT BROTHERS NATIONAL MEMORIAL. | HIGHWAY | OTHER | 1 | ALBEMARLE RPO | R-5753A | EXEMPT | FLTP | [6 empty] | 2021 | 95000 | 95000
DARE | DARE COUNTY | DARE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1 | ALBEMARLE RPO | TK-6124 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 512000 | 512000 | FUNDS AUTHORIZED IN PROGRESS
DARE, HALIFAX | NC 12 | NCDOT | HATTERAS AND OCRACOKE DOCK IMPROVEMENTS | FERRY | OTHER | 1, 4 | ALBEMARLE RPO | F-5702E | DIVISION 1, 4 | [10 empty] | COMPLETED. WORK ACCOMPLISHED UNDER F-5702B.
DARE, HYDE | NC 12 | NCDOT | CONSTRUCT RIVER CLASS FERRY. | FERRY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | F-5700 | DIVISION 1 | [10 empty] | COMPLETE
DARE, HYDE | NC 12 | NCDOT | HATTERAS FERRY DOCK IN DARE COUNTY TO OCRACOKE FERRY DOCKS IN HYDE COUNTY. CONSTRUCT TWO PASSENGER FERRIES TO BE USED ALONG NEW ROUTE. IMPLEMENT TRANSIT SYSTEM TO AID PASSENGERS ON OCRACOKE ISLAND. | FERRY | OTHER | 1 | ALBEMARLE RPO | F-5702 | DIVISION 1 | [10 empty] | OTHER FUNDS ARE FROM STATE APPROPRIATION 7355.
DARE, HYDE | NC 12 | NCDOT | CONSTRUCT TWO PASSENGER FERRIES | FERRY | OTHER | 1 | ALBEMARLE RPO | F-5702C | DIVISION 1 | [10 empty] | UNDER CONSTRUCTION.
DARE, HYDE | HATTERAS - SOUTH DOCK | NCDOT | CONSTRUCT PASSENGER FERRY. | FERRY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | F-5706 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 6500000 |  |  | 6500000
DARE, HYDE | NC 12 | NCDOT | HATTERAS AND OCRACOKE ISLAND FERRY RAMP AND DOCK IMPROVEMENTS. | FERRY | FEDERAL LANDS ACCESS PROGRAM | 1 | ALBEMARLE RPO | FF-0001 | EXEMPT | FLAP |  |  |  |  | 2026 | 2430000 | 2023 | 1070000 | 3500000 | FLAP PROJECT NC 62. AWARDED $3.5M.
DARE, TYRRELL | US 64 | NCDOT | WEST OF ALLIGATOR RIVER TO EAST OF SR 1153 (OLD FERRY LANDING ROAD). | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2545B | NOT FUNDED | T | NOT FUNDED | 3175000 | NOT FUNDED | 1156000 | NOT FUNDED | 503100000 |  |  | 507431000
DAVIDSON | DAVIDSON COUNTY AIRPORT (EXX) | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE AND STRENGTHEN RUNWAY TO ACCOMMODATE LARGER PRIVATE AIRCRAFT. | AVIATION | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | AV-5831 | DIVISION 9 | T |  |  |  |  | 2022 | 14551000 |  |  | 14551000 | UNDER CONSTRUCTION. TO BE LET WITH AV-5900.
DAVIDSON | DAVIDSON COUNTY AIRPORT (EXX) | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE TAXIWAY AND APRON. | AVIATION | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | AV-5900 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION, LET WITH AV-5831. FUNDING SHOWN UNDER PROJECT AV-5831
DAVIDSON | NC 8 | NCDOT | REPLACE BRIDGE 280027 OVER US 29 / US 64 / US 70 / I-85 BUSINESS IN LEXINGTON. | HIGHWAY | TRANSITION | 9 | HIGH POINT URBAN AREA MPO | B-3159 | REGION D | [10 empty] | COMPLETE
DAVIDSON | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | NCDOT | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | HIGHWAY | BRIDGES | 9 | HIGH POINT URBAN AREA MPO | B-5779 | REGION D | BFP | 2028 | 130000 | 2028 | 290000 | 2029 | 7700000 |  |  | 8120000
DAVIDSON | NC 47 | NCDOT | REPLACE BRIDGE 280017 OVER SWEARING CREEK. | HIGHWAY | BRIDGES | 9 | HIGH POINT URBAN AREA MPO | B-5780 | HIGHWAY FUND | [10 empty] | COMPLETE
DAVIDSON | US 29 / US 70 / BUSINESS 85 | NCDOT | REPLACE BRIDGE 280164 AND BRIDGE 280168 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 9 | HIGH POINT URBAN AREA MPO | B-5783 | REGION D | BFP |  |  |  |  | 2023 | 5778000 |  |  | 5778000 | UNDER CONSTRUCTION
DAVIDSON | VARIOUS | LEXINGTON | TRANSIT OPERATIONS SUPPORT FOR CITY OF LEXINGTON CIRCULATOR ROUTE AND THOMASVILLE / LEXINGTON CONNECTOR ROUTE. | HIGHWAY | PRE-STI (HISTORIC) | 9 | HIGH POINT URBAN AREA MPO | C-5559 | EXEMPT | [10 empty] | IMPLEMENTATION BY DAVIDSON COUNTY - IN PROGRESS
DAVIDSON | US 64 | NCDOT | EXTEND LEFT TURN LANE AND CONSTRUCT RIGHT TURN LANE AT PROPOSED NEW ACCESS ROAD ACROSS FROM SR 2112 (DECKER ROAD) AND WIDEN RAIL CROSSING 836515Y. | HIGHWAY | ECONOMIC DEVELOPMENT | 9 | HIGH POINT URBAN AREA MPO | HE-0008 | DIVISION 9 | T |  |  |  |  | 2023 | 1500000 | 2022 | 300000 | 1800000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR.
DAVIDSON | SR 1104 OLD LINWOOD ROAD | NCDOT | CONSTRUCT NEW ACCESS ROAD NORTH OF SR 1254 (BROWN STREET) AND IMPROVEMENTS TO SR 1104 (OLD LINWOOD ROAD). | HIGHWAY | ECONOMIC DEVELOPMENT | 9 | HIGH POINT URBAN AREA MPO | HE-0014 | DIVISION 9 | T |  |  | 2024 | 10000 | 2024 | 8590000 | 2023 | 400000 | 9000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY.
DAVIDSON | NC 109 | NCDOT | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | HIGHWAY | LOCALLY SELECTED | 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | HL-0061 | DIVISION 9 | BGANY, BGDA, L | 2024 | 2300000 |  |  | 2025 | 387000 | 2023 | 599000 | 3286000 | ROW FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
DAVIDSON | US 64 | NCDOT | US 64 FROM SR 2782 (BOWERS ROAD TO EAST OF SR 2012 / SR 2227 (HEATH CHURCH ROAD / NEW BOWERS ROAD). CONSTRUCT 4 REDUCED CONFLICT INTERSECTIONS AND LEFT-OVER WITH U-TURN BULB EAST OF SR 2012 / SR 2227. | HIGHWAY | SAFETY | 9 | HIGH POINT URBAN AREA MPO | HS-2009B | REGION D | HSIP |  |  | 2023 | 20000 | 2023 | 1500000 |  |  | 1520000 | IN PROGRESS
DAVIDSON | US 29 / US 70 | NCDOT | US 29 / US 70, VICINITY OF FLEET DARR ROAD WEST OF SR 2123 (LEXINGTON AVENUE) CONNECTOR. INSTALL DIRECTIONAL LEFTOVERS. | HIGHWAY | SAFETY | 9 | HIGH POINT URBAN AREA MPO | HS-2009C | REGION D | HSIP |  |  |  |  | 2026 | 500000 |  |  | 500000
DAVIDSON | I-85 | NCDOT | NORTH OF NC 150 TO US 29-70-52/BUSINESS 85 IN DAVIDSON COUNTY | HIGHWAY | PRE-STI (HISTORIC) | 9 | HIGH POINT URBAN AREA MPO | I-2304AD | PRE-STI (TRANSITION) | NHP | 2009 | 984000 | [6 empty] | 984000 | COMPLETE; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021
DAVIDSON | I-85 | NCDOT | NORTH CAROLINA RAILROAD MP 327.4 - CURVE REALIGNMENT | HIGHWAY | PRE-STI (HISTORIC) | 9 | HIGH POINT URBAN AREA MPO | I-2304AE | [11 empty] | COMPLETE
DAVIDSON | I-85 | NCDOT | SR 2205 (OLD US 64) TO 0.4 MILES NORTH OF US 64. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | HIGH POINT URBAN AREA MPO | I-5740 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
DAVIDSON | I-85 | NCDOT | REHABILITATE BRIDGE 280181 AND BRIDGE 280182. | HIGHWAY | BRIDGES | 9 | HIGH POINT URBAN AREA MPO | I-5740A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
DAVIDSON | I-85 | NCDOT | I-285 / US 29 / US 52 / US 70 TO NORTH OF US 64. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | HIGH POINT URBAN AREA MPO | I-5950 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 28542000 |  |  | 28542000
DAVIDSON | US 64 | NCDOT | US 64, I-85 BUSINESS IN LEXINGTON TO EAST OF I-85. | HIGHWAY | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | R-2220A | [11 empty] | COMPLETE
DAVIDSON | US 64 | NCDOT | I-85 EAST OF LEXINGTON TO NC 109 | HIGHWAY | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | R-2220B | NOT FUNDED | T | NOT FUNDED | 30992000 | NOT FUNDED | 5635000 | NOT FUNDED | 40572000 |  |  | 77199000
DAVIDSON | NC 109 | NCDOT | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | R-4734 | DIVISION 9 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1337000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 132097000 |  |  | 133934000
DAVIDSON | US 29 / US 70 / BUSINESS 85 | NCDOT | SR 1798 (OLD GREENSBORO ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | R-5737 | DIVISION 9 | T |  |  |  |  | 2022 | 29777000 |  |  | 29777000 | UNDER CONSTRUCTION; INCLUDES PARTICIPATION BY DAVIDSON COUNTY COMMUNITY COLLEGE
DAVIDSON | NC 8 (WINSTON ROAD) | NCDOT | 9TH STREET TO SR 1408 (BIESECKER ROAD) IN LEXINGTON. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | U-5757 | REGION D | T | 2019 | 17575000 |  |  | 2024 | 8800000 |  |  | 26375000 | RIGHT-OF-WAY IN PROGRESS
DAVIDSON | SR 1508 (HICKORY TREE ROAD) | NCDOT | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-5786 | DIVISION 9 | BGANY | 2026 | 5000000 | 2026 | 5100000 | 2028 | 22000000 |  |  | 32100000
DAVIDSON | NC 109 | NCDOT | DENTON NORTHERN MUNICIPAL BOUNDARY TO SR 2067 (LAMBETH ROAD), AND SR 1798 (OLD GREENSBORO ROAD) / SR 1756 (WEST LEXINGTON AVENUE EXTENSION) TO SR 1711 (GUMTREE ROAD). INSTALL RUMBLE STRIPS AND LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 9 | HIGH POINT URBAN AREA MPO | W-5809A | REGION D | HSIP |  |  |  |  | 2022 | 1100000 |  |  | 1100000 | UNDER CONSTRUCTION
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | TG-6808B | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2020 | 408360000 |  |  | 408360000
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | ROUTINE CAPITAL - PASSENGER SHELTERS, PASSENGER AMENITIESA, SHOP EQUIPMENT, SPARE PARTS, CAPITAL COST OF CONTRACTING, ETC. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | TG-6809 | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2020 | 204180000 |  |  | 204180000
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9 | PIEDMONT TRIAD RPO | TK-6125 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 836000 | 836000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON | DAVIDSON COUNTY TRANSPORTATION SYSTEM | DAVIDSON COUNTY TRANSPORTATION SYSTEM | INSTALLING COVERED BUS SHELTERS WITH ADA ACCESS TO MAJOR STOPS SUCH AS WALMART AND BIG LOTS. INSTALL SIMME SEATS AT THE REMAINDER OF BUS STOPS. SIMME SEATS PROVIDE TWO SEATS ATTACHED TO THE BUS STOP SIGN POLE. | PUBLIC TRANSIT | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | TL-0014 | DIVISION 9 | BGDA, L | [6 empty] | 2021 | 140000 | 140000
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | OPERATING FUNIDING FOR DAVIDSON COUNTY TRANSPORATION FOR SERVICE IN THE HIGH POINT URBAN AREA - THROUGH NCDOT | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 9 | HIGH POINT URBAN AREA MPO | TO-5215 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 360000 | 360000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | TO-6165 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 326688000 | 326688000
DAVIDSON | NORFOLK SOUTHERN | LEXINGTON | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD. | RAIL | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | P-5722 | REGION D | O, T |  |  |  |  | 2025 | 2038000 |  |  | 2038000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DAVIDSON | NORFOLK SOUTHERN | NCDOT | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | RAIL | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | P-5731 | DIVISION 9 | DP, L, T | 2024 | 6900000 |  |  | 2025 | 25000000 |  |  | 31900000 | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT
DAVIDSON | NCRR | LEXINGTON | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTI-MODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. | RAIL | OTHER | 9 | HIGH POINT URBAN AREA MPO | P-5732 | EXEMPT | DP, L, O |  |  |  |  | 2024 | 15700000 |  |  | 15700000 | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT
DAVIDSON | NCRR / NORFOLK SOUTHERN MAIN LINE | NCDOT | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. | RAIL | STI (PRIORITIZATION) | 9 | HIGH POINT URBAN AREA MPO | P-5751 | DIVISION 9 | O, T | 2028 | 5000000 |  |  | 2031 | 22001000 |  |  | 27001000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DAVIDSON | LS (FIRST STREET) | NCDOT | WSS CROSSING 849955C IN DENTON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 9 | HIGH POINT URBAN AREA MPO | RX-2009A | DIVISION 9 | RR |  |  |  |  | 2024 | 303000 |  |  | 303000
DAVIDSON, ALAMANCE, CABARRUS, DURHAM, GUILFORD, MECKLENBURG, ORANGE, ROWAN, WAKE | PIEDMONT CORRIDOR | NCDOT | NEW TRAINS AND MAINTENANCE FACILITY. | RAIL | STI (PRIORITIZATION) | 5, 7, 9, 10 | CAPITAL AREA MPO, HIGH POINT URBAN AREA MPO, BURLINGTON-GRAHAM MPO, CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO | P-5719C | REGION C, D, E | DP, T |  |  |  |  | 2023 | 212528000 |  |  | 212528000 | UNDER CONSTRUCTION.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | BO-2409 | DIVISION 9 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. | HIGHWAY | SAFETY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | HS-2009
CABARRUS | I-85 | NCDOT | ITS FOR I-3803B | HIGHWAY | TRANSITION | 10 | CABARRUS-ROWAN MPO | I-3803BA | PRE-STI (TRANSITION)
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. | HIGHWAY | SAFETY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | HS-2409 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | R-5789 | DIVISION 9 | S, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | DIVISION 9 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5209 | [11 empty] | COMPELTE
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. | HIGHWAY | SAFETY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5709 | [11 empty] | IN PROGRESS; $1.3M NHP FUNDING APPLIED TO W-5709E
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5709DIV | DIVISION 9 | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5709REG | REGION D | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5709SW | STATEWIDE MOBILITY | HSIP | 2020 | 120000 |  |  | 2020 | 740000 |  |  | 860000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. | HIGHWAY | SAFETY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5809
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 9. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | RC-2009 | DIVISION 9 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | RX-2009 | DIVISION 9
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | RX-2409 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DAVIDSON, FORSYTH | NC 109 | NCDOT | NC 109. FORSYTH COUNTY FROM MILE POST 0.256 TO DAVIDSON COUNTY MILE POST 38.367. INSTALL CENTERLINE AND EDGELINE SINUSOIDAL RUMBLESTRIPES. | HIGHWAY | SAFETY | 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | HS-2009F | REGION D | HSIP |  |  |  |  | 2023 | 600000 |  |  | 600000
DAVIDSON, GUILFORD, FORSYTH | VARIOUS | HIGH POINT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | HIGHWAY | OTHER | 7, 9 | HIGH POINT URBAN AREA MPO | C-5609 | EXEMPT | CMAQ, L | 2020 | 243000 |  |  | 2020 | 1455000 | 2020 | 729000 | 2427000 | IN PROGRESS
DAVIDSON, GUILFORD, RANDOLPH | HIGH POINT TRANSIT SYSTEM / HI-TRAN | HIGH POINT TRANSIT SYSTEM / HI-TRAN | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7, 8, 9 | HIGH POINT URBAN AREA MPO | TS-5113 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 64000 | 64000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON, GUILFORD, RANDOLPH, FORSYTH | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE HIGH POINT PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 7, 8, 9 | HIGH POINT URBAN AREA MPO | HL-0101 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 2366000 |  |  | 2366000
DAVIDSON, RANDOLPH | US 64 | NCDOT | US 64, EAST OF I-85 BUSINESS IN LEXINGTON TO ASHEBORO BYPASS. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8, 9 | HIGH POINT URBAN AREA MPO, PIEDMONT TRIAD RPO | R-2220
DAVIDSON, ROWAN | I-85 | NCDOT | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO US 29 / US 52 / US 70 / BUSINESS 85 IN DAVIDSON COUNTY. ADDITIONAL LANES AND YADKIN RIVER BRIDGE RECONSTRUCTION. (PROJECT INCLUDES B-3833). | HIGHWAY | PRE-STI (HISTORIC) | 9 | HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | I-2304 | PRE-STI (TRANSITION) | [10 empty] | INCLUDES B-3833; TIGER AWARD / INTERSTATE MAINTENANCE DISCRETIONARY FUNDING $11.7 MILLION; GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
CABARRUS | GEORGE LILES PARKWAY | NCDOT | NC 49 TO SOUTH OF I-85. WIDEN TO FOUR LANES DIVIDED, SOME NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | R-2246
CABARRUS | GEORGE LILES PARKWAY | NCDOT | SR 1304 (ROBERTA ROAD) TO SR 1431 (WEDDINGTON ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 10 | CABARRUS-ROWAN MPO | R-2246B | [11 empty] | COMPLETE
DAVIE | BLUE HERON TRAIL | BERMUDA RUN | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5958 | DIVISION 9 | BGANY, BGDA, L |  |  |  |  | 2022 | 3693000 |  |  | 3693000 | UNDER CONSTRUCTION
DAVIE | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | HIGHWAY | OTHER | 9 | NORTHWEST PIEDMONT RPO | C-5614 | EXEMPT | CMAQ, L | 2020 | 12000 |  |  | 2020 | 57000 | 2020 | 36000 | 105000
DAVIE | I-40 | NCDOT | 0.5 MILES WEST OF US 601 TO 1.2 MILES EAST OF SR 1410 (FARMINGTON ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | NORTHWEST PIEDMONT RPO | I-5765 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
DAVIE | I-40 | NCDOT | IREDELL COUNTY LINE TO 0.5 MILE WEST OF US 601. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | NORTHWEST PIEDMONT RPO | I-5823 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
DAVIE | I-40 | NCDOT | SR 1436 (PINEBROOK SCHOOL ROAD) TO WEST OF NC 801. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO | I-6003 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2021 | 7677000 |  |  | 7677000 | UNDER CONSTRUCTION
DAVIE | US 601 | NCDOT | SOUTH SALISBURY STREET IN MOCKSVILLE. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 9 | NORTHWEST PIEDMONT RPO | R-5728 | REGION D | [10 empty] | UNDER CONSTRUCTION
DAVIE | US 601 | NCDOT | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 9 | NORTHWEST PIEDMONT RPO | R-5736 | DIVISION 9 | BGANY | 2026 | 5000000 | 2026 | 800000 | 2028 | 17001000 |  |  | 22801000
DAVIE | SR 1410 (FARMINGTON ROAD) | NCDOT | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 9 | NORTHWEST PIEDMONT RPO | R-5854 | DIVISION 9 | T | 2023 | 100000 | 2023 | 300000 | 2025 | 1900000 |  |  | 2300000 | RIGHT-OF-WAY IN PROGRESS
DAVIE | WILKESBORO STREET | NCDOT | YADKINVILLE ROAD IN MOCKSVILLE. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 9 | NORTHWEST PIEDMONT RPO | U-6002 | DIVISION 9 | T |  |  |  |  | 2022 | 1800000 |  |  | 1800000 | RIGHT-OF-WAY IN PROGRESS
DAVIE | NEW ROUTE | NCDOT | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-6187 | DIVISION 9 | BGANY, T | 2024 | 3400000 | 2024 | 300000 | 2025 | 30035000 |  |  | 33735000 | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
DAVIE, FORSYTH | I-40 | NCDOT | WEST OF NC 801 IN DAVIE COUNTY TO SR 1101 (HARPER ROAD) IN FORSYTH COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | I-0911A | REGION D | T |  |  |  |  | 2021 | 35894000 |  |  | 35894000 | COMPLETE; DESIGN-BUILD PROJECT; BUILD NC BONDS: $27.889 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
DAVIE, FORSYTH | I-40 | NCDOT | 0.3 MILE WEST OF NC 801 IN DAVIE COUNTY TO SR 1101 (HARPER ROAD) IN FORSYTH COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | I-5794 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
DAVIE, STOKES, SURRY, YADKIN | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9, 11 | NORTHWEST PIEDMONT RPO | TK-6174 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1704000 | 1704000 | FUNDS AUTHORIZED IN PROGRESS
DUPLIN | NC 11/NC 111 | NCDOT | BRIDGE 300082 OVER BURNT COAT CREEK. | HIGHWAY | BRIDGES | 3 | EASTERN CAROLINA RPO | B-5534 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2675000 |  |  | 2675000 | UNDER CONSTRUCTION.
DUPLIN | SR 1828 (CYPRESS CREEK ROAD) | NCDOT | REPLACE BRIDGE 300187 OVER BLACK SWAMP. | HIGHWAY | BRIDGES | 3 | EASTERN CAROLINA RPO | B-5632 | DIVISION 3 | BGOFF | 2023 | 190000 |  |  | 2023 | 1900000 |  |  | 2090000 | UNDER CONSTRUCTION.
DUPLIN | NC 11 | NCDOT | BRIDGE 300036 OVER MAXWELL CREEK. | HIGHWAY | BRIDGES | 3 | EASTERN CAROLINA RPO | B-5639 | HIGHWAY FUND | HFB | 2020 | 56000 |  |  | 2021 | 3422000 |  |  | 3478000 | UNDER CONSTRUCTION.
DUPLIN | SR 1946 (NORTHEAST ROAD) | NCDOT | REPLACE BRIDGE 300201 OVER ISLAND CREEK. | HIGHWAY | BRIDGES | 3 | EASTERN CAROLINA RPO | B-5641 | DIVISION 3 | BGOFF |  |  |  |  | 2022 | 1669000 |  |  | 1669000 | UNDER CONSTRUCTION.
DUPLIN | SR 1135 (PROVIDENCE CHURCH ROAD) | NCDOT | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | HIGHWAY | BRIDGES | 3 | EASTERN CAROLINA RPO | B-5647 | DIVISION 3 | BGOFF | 2023 | 60000 | 2023 | 25000 | 2024 | 1500000 |  |  | 1585000 | RIGHT-OF-WAY IN PROGRESS.
DUPLIN | US 117 NBL | NCDOT | REPLACE BRIDGE 300016 OVER CSX RAILROAD. BRIDGE PRESERVATION OF BRIDGE 300017 OVER CSX. | HIGHWAY | BRIDGES | 3 | EASTERN CAROLINA RPO | B-5981 | STATEWIDE MOBILITY | BGLT5 | 2022 | 443000 |  |  | 2023 | 7100000 |  |  | 7543000 | UNDER CONSTRUCTION.
DUPLIN | SR 1162 (BAY ROAD) | NCDOT | REPLACE BRIDGE 300045 OVER ISLAND CREEK. | HIGHWAY | BRIDGES | 3 | EASTERN CAROLINA RPO | BR-0243 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 1700000 |  |  | 1700000 | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.83 PROJECT.
DUPLIN | I-40 | NCDOT | I-40 FROM THE SAMPSON COUNTY LINE (MILE MARKER 360) TO THE PENDER COUNTY LINE (MILE MARKER 388). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 3 | EASTERN CAROLINA RPO | HI-0012 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2028 | 31100000 |  |  | 31100000
DUPLIN | SR 1535 (LIDDELL ROAD) | NCDOT | SR 1535 (LIDDELL ROAD) AND SR 1534 (DRUMMERSVILLE ROAD). INSTALL ALL WAY STOP. | HIGHWAY | SAFETY | 3 | EASTERN CAROLINA RPO | HS-2003C | DIVISION 3 | HSIP |  |  |  |  | 2024 | 31000 |  |  | 31000
DUPLIN | US 117 (SYCAMORE STREET) | NCDOT | US 117 (SYCAMORE STREET) AND SR 1102 (CHARITY ROAD) IN ROSE HILL. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 3 | EASTERN CAROLINA RPO | HS-2003E | REGION B | HSIP |  |  |  |  | 2025 | 97000 |  |  | 97000
DUPLIN | NC 403 | NCDOT | NC 403 AT SR 1306 (BEAUTANCUS ROAD). INSTALL ALL WAY STOP, STOP AHEAD WARNING SIGNS, BRIGHTSIDES, STOP BARS, CONCRETE ISLAND, AND REFRESH PAVEMENT MARKINGS. REMOVE ACTUATED CURVE WARNING FLASHER. | HIGHWAY | SAFETY | 3 | EASTERN CAROLINA RPO | HS-2003I | REGION B | HSIP |  |  |  |  | 2024 | 154000 |  |  | 154000
DUPLIN | US 117 (NORWOOD STREET) | NCDOT | US 117 (NORWOOD STREET) AND SR 1173 (SOUTHERLAND STREET) IN WALLACE. REVISE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 3 | EASTERN CAROLINA RPO | HS-2003M | REGION B | HSIP |  |  |  |  | 2025 | 44000 |  |  | 44000
DUPLIN | NC 24 BUSINESS (ROUTELEDGE ROAD) | NCDOT | NC 24 BUSINESS (ROUTELEDGE ROAD) AND NC 24 / NC 903 (SOUTH KENANSVILLE BYPASS). REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 3 | EASTERN CAROLINA RPO | HS-2003N | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2025 | 252000 |  |  | 252000
DUPLIN | DUPLIN COUNTY | DUPLIN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 3 | EASTERN CAROLINA RPO | TK-6177 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 836000 | 836000 | FUNDS AUTHORIZED IN PROGRESS
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | BO-2403 | DIVISION 3 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | HS-2003
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, DOWN EAST RPO, JACKSONVILLE URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | HS-2403 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | R-5783 | DIVISION 3 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO | W-5203 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5703 | [11 empty] | IN PROGRESS
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5703DIV | DIVISION 3 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5703REG | REGION B | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5703SW | STATEWIDE MOBILITY | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5803
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 3. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | RC-2003 | DIVISION 3 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | RX-2003 | DIVISION 3 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, DOWN EAST RPO, JACKSONVILLE URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | RX-2403 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DUPLIN, PENDER | I-40 | NCDOT | DUPLIN COUNTY LINE (MILE MARKER 360) TO WEST OF US 117 (MILE MARKER 390). PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 3 | EASTERN CAROLINA RPO, CAPE FEAR RPO | I-5940 | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2019 | 29326000 |  |  | 29326000 | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION.
DUPLIN, SAMPSON | VARIOUS | NCDOT | INSTALL PAVEMENT MARKINGS ALONG VARIOUS ROUTES. | HIGHWAY | SAFETY | 3 | EASTERN CAROLINA RPO, MID-CAROLINA RPO | HS-2003B | DIVISION 3 | HSIP |  |  |  |  | 2021 | 3432000 |  |  | 3432000 | UNDER CONSTRUCTION.
DUPLIN, SAMPSON | US 117 (FUTURE 1-795) | NCDOT | I-40 TO SR 1006 (WEST TRADE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 3 | EASTERN CAROLINA RPO, MID-CAROLINA RPO | U-3125A | NOT FUNDED | NHP | NOT FUNDED | 7183000 | NOT FUNDED | 2238000 | NOT FUNDED | 103500000 |  |  | 112921000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
DURHAM | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | DURHAM | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | BIKE/PED | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0028 | DIVISION 5 | CMAQ, L, STBG |  |  |  |  | 2023 | 911000 | 2022 | 154000 | 1065000
DURHAM | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | DURHAM | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | BIKE/PED | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0030 | DIVISION 5 | BGDA, BGDACV, L |  |  |  |  | 2022 | 162000 | 2022 | 36000 | 198000
DURHAM | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | DURHAM | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STPEHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | BIKE/PED | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0031 | DIVISION 5 | L, STBG |  |  |  |  | 2023 | 340000 | 2022 | 60000 | 400000
DURHAM | NC 751 / SR 1183 / SR 2220 / NON-SYSTEM (UNIVERSIT | DURHAM | SR 1116 (GARRETT ROAD) TO SR 1158 (CORNWALLIS ROAD) IN DURHAM. ADD BICYCLE LANES AND PEDESTRIAN IMPROVEMENTS. | BIKE/PED | TRANSITION | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5514 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF DURHAM
DURHAM | LASALLE STREET | DURHAM | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5703 | DIVISION 5 | L, TAANY | 2022 | 150000 |  |  | 2023 | 1300000 |  |  | 1450000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | RAYNOR STREET | DURHAM | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5704 | DIVISION 5 | L, TAANY | 2022 | 169000 |  |  | 2023 | 580000 |  |  | 749000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | NC 54 | DURHAM | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5708 | DIVISION 5 | L, SRTS, TAANY | 2021 | 177000 |  |  | 2023 | 430000 |  |  | 607000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | US 501 BYPASS (NORTH DUKE STREET) | DURHAM | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5715 | DIVISION 5 | L, TAANY | 2021 | 296000 |  |  | 2023 | 2680000 |  |  | 2976000 | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM
DURHAM | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | DURHAM | NC 55 TO TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5720 | DIVISION 5 | HP, L, TAANY | 2024 | 14000 |  |  | 2024 | 6020000 |  |  | 6034000 | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT.
DURHAM | NC 157 / SR 1322 (GUESS ROAD) | DURHAM | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5834 | DIVISION 5 | BGDACV, L, TAANY | 2025 | 204000 |  |  | 2026 | 1293000 | 2023 | 108000 | 1605000
DURHAM | NC 55 (ALSTON AVENUE) | DURHAM | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5835 | DIVISION 5 | L, TAANY | 2027 | 50000 |  |  | 2028 | 1196000 | 2023 | 105000 | 1351000
DURHAM | THIRD FORK CREEK TRAIL | DURHAM | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5837 | DIVISION 5 | L, TAANY | 2023 | 17000 |  |  | 2024 | 5600000 |  |  | 5617000
DURHAM | DURHAM BELTLINE TRAIL | DURHAM | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | BIKE/PED | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5904 | DIVISION 5 | BGDA, DP, L, TAANY, TADA |  |  |  |  | 2023 | 17409000 |  |  | 17409000 | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT
DURHAM | SR 1158 (CORNWALLIS ROAD) | DURHAM | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | BIKE/PED | TRANSITION | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4724 | PRE-STI (TRANSITION) | BGANY, BGDA, L | 2023 | 2233000 |  |  | 2024 | 4978000 |  |  | 7211000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | SR 1321 (HILLANDALE ROAD) | DURHAM | I-85 TO NC 147 (DURHAM FREEWAY) IN DURHAM. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4726HN | EXEMPT | BGDA, L |  |  |  |  | 2023 | 2939000 |  |  | 2939000
DURHAM | CARPENTER - FLETCHER ROAD | DURHAM | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4726HO | EXEMPT | BGANY, L, TADA | 2023 | 27000 |  |  | 2024 | 7881000 |  |  | 7908000
DURHAM | US 15 / US 501 NORTHBOUND | NCDOT | REPLACE BRIDGE 310080 OVER SR 1308 (CORNWALLIS ROAD) IN DURHAM. | HIGHWAY | BRIDGES | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | B-5674 | REGION C | BFP | 2027 | 700000 |  |  | 2027 | 5450000 |  |  | 6150000
DURHAM | (HORTON ROAD) SR 1443 | NCDOT | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | HIGHWAY | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0063 | EXEMPT | CMAQ, L | 2023 | 571000 |  |  | 2024 | 275000 | 2023 | 359000 | 1205000
DURHAM | SR 1317 (MORREENE ROAD) | DURHAM | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | HIGHWAY | TRANSITION | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-4928 | DIVISION 5 | BGANY, BGDA, CMAQ, L | 2022 | 3060000 |  |  | 2023 | 7371000 |  |  | 10431000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS
DURHAM | VARIOUS | DURHAM | CONSTRUCT SIDEWALKS IN DURHAM. | HIGHWAY | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5183 | EXEMPT
DURHAM | SR 1945 (S. ALSTON AVE.) | DURHAM | SR 1171 (RIDDLE RD.) TO CAPPS ST. | HIGHWAY | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5183B | EXEMPT | BGDA, CMAQ, L |  |  |  |  | 2023 | 1346000 |  |  | 1346000 | UNDER CONSTRUCTION
DURHAM | VARIOUS | DURHAM | INSTALL SIGNS & KIOSKS | HIGHWAY | OTHER | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5605H | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 605000 |  |  | 605000
DURHAM | SR 2220 | NCDOT | SR 1113 (POPE ROAD) TO SR 1116 (GARRETT ROAD) | HIGHWAY | TRANSITION | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-4707B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
DURHAM | VARIOUS | NCDOT | CONSTRUCT ACCESS ROAD AND INTERSECTION IMPROVEMENTS AT SR 1004 (OLD OXFORD ROAD), SR 1794 (TEKNIKA PARKWAY), AND SR 2635 (INTERNATIONAL DRIVE). | HIGHWAY | ECONOMIC DEVELOPMENT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HE-0007 | DIVISION 5 | [10 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK.
DURHAM | SR 1004 (OLD OXFORD ROAD) | NCDOT | FIRST AVE (MERCK DRIVEWAY). CONSTRUCT RIGHT TURN LANE. | HIGHWAY | ECONOMIC DEVELOPMENT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HE-0007A | DIVISION 5 | T |  |  |  |  | 2023 | 165000 | 2023 | 25000 | 190000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK.
DURHAM | SR 1794 (TEKNIKA PARKWAY) | NCDOT | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | HIGHWAY | ECONOMIC DEVELOPMENT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HE-0007B | DIVISION 5 | T | 2023 | 95000 |  |  | 2023 | 815000 | 2023 | 90000 | 1000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS
DURHAM | SR 2635 (INTERNATIONAL DRIVE) | NCDOT | SR 1004 (OLD OXFORD RD) TO NEW LOCATION. CONSTRUCT NEW LANES. | HIGHWAY | ECONOMIC DEVELOPMENT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HE-0007C | DIVISION 5 | T | [6 empty] | 2023 | 600000 | 600000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
DURHAM | I-885 | NCDOT | I-40 TO 0.4 MILES NORTH OF TW ALEXANDER DRIVE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HI-0023 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2024 | 3300000 |  |  | 3300000
DURHAM | NC 54 | NCDOT | NC 55 IN DURHAM. INSTALL CONCRETE PEDESTRIAN REFUGE ISLANDS IN ALL QUADRANTS. | HIGHWAY | SAFETY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005C | REGION C | HSIP |  |  |  |  | 2023 | 75000 |  |  | 75000
DURHAM | SR 1303 (PICKETT ROAD) | NCDOT | SR 1116 (GARRETT ROAD)/(LUNA LANE) INTERSECTION IN DURHAM. INSTALL TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005D | DIVISION 5 | HSIP | 2023 | 2000 |  |  | 2023 | 100000 |  |  | 102000
DURHAM | US 15 / US 501 BUSINESS | NCDOT | NC 751 (ACADEMY ROAD) INTERCHANGE IN DURHAM. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005E | REGION C | HSIP |  |  |  |  | 2023 | 175000 |  |  | 175000
DURHAM | SR 1973 (PAGE ROAD) | NCDOT | CHURCHILL HALL/ARBY'S/MCDONALD DRIVEWAY. INSTALL DIRECTIONAL CROSSOVER. | HIGHWAY | SAFETY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005H | DIVISION 5 | HSIP |  |  |  |  | 2023 | 20000 |  |  | 20000
DURHAM | SR 1327 (GREGSON STREET) | NCDOT | SR 1327 (GREGSON STREET) AT KNOX STREET. INSTALL TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005L | DIVISION 5 | HSIP |  |  |  |  | 2023 | 110000 |  |  | 110000
DURHAM | NC 55 (ALSTON AVENUE) | NCDOT | NC 98 AT SR 1670 (GEER STREET). REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNAL HEADS. | HIGHWAY | SAFETY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005M | REGION C | HSIP |  |  |  |  | 2023 | 62000 |  |  | 62000
DURHAM | NC 98 | NCDOT | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | HIGHWAY | SAFETY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005N | REGION C | HSIP, L, T | 2024 | 500000 |  |  | 2025 | 1785000 |  |  | 2285000
DURHAM | I-40 | NCDOT | ORANGE COUNTY LINE TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM | HIGHWAY | PRE-STI (HISTORIC) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306B | [11 empty] | COMPLETE
DURHAM | I-40 | NCDOT | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5707 | STATEWIDE MOBILITY | NHP | 2025 | 900000 | 2025 | 205000 | 2027 | 8200000 |  |  | 9305000
DURHAM | I-85 | NCDOT |  | HIGHWAY | PRE-STI (HISTORIC) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5729 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
DURHAM | I-85 | NCDOT | ORANGE COUNTY LINE TO US 15 / US 501 IN DURHAM. PAVEMENT REHABILITATION | HIGHWAY | INTERSTATE MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5941 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2024 | 16800000 |  |  | 16800000
DURHAM | I-40 | NCDOT | US 15 / US 501 TO EAST OF NC 147. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5993 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 37326000 |  |  | 37326000 | TO BE LET WITH I-5994
DURHAM | I-85 / US 15 | NCDOT | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-6010 | NOT FUNDED | NHP | NOT FUNDED | 10417000 | NOT FUNDED | 1774000 | NOT FUNDED | 55301000 |  |  | 67492000
DURHAM | NEW ROUTE | NCDOT | EAST END CONNECTOR, NC 147 (DURHAM FREEWAY) TO NORTH OF NC 98 IN DURHAM. FOUR-LANE DIVIDED FREEWAY WITH AUXILIARY LANES, PART ON NEW LOCATION. | HIGHWAY | TRANSITION | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-0071 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
DURHAM | NC 55 (ALSTON AVENUE) | NCDOT | NC 147 (DURHAM FREEWAY) TO US 70 BUSINESS / NC 98 (HOLLOWAY STREET) IN DURHAM. WIDEN TO FOUR-LANE DIVIDED FACILITY FROM NC 147 TO MAIN STREET AND REPLACE NORFOLK SOUTHERN RAILROAD BRIDGES. MODERNIZE FROM MAIN STREET TO US 70 BUSINESS / NC 98 (HOLLOWAY ST | HIGHWAY | TRANSITION | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-3308 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
DURHAM | US 501 (ROXBORO ROAD) | NCDOT | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5516 | REGION C | L, NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11292000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2076000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12402000 |  |  | 25770000 | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM
DURHAM | US 15 / US 501 | NCDOT | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5717 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2027 | 32001000 |  |  | 32001000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067
DURHAM | US 70 (MIAMI BOULEVARD) | NCDOT | LYNN ROAD TO EAST OF SR 2095 (PAGE ROAD EXTENSION). UPGRADE TO CONTROLLED-ACCESS FACILITY AND CONVERT SR 1811 AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720
DURHAM | US 70 (MIAMI BOULEVARD) | NCDOT | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720A | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 46401000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1306000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36502000 |  |  | 84209000
DURHAM | US 70 (MIAMI BOULEVARD) | NCDOT | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720B | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 140500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1218000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 81700000 |  |  | 223418000 | INCLUDES INTERCHANGE AT SR 1811
DURHAM | US 70 | NCDOT | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720C | [11 empty] | PROJECT DELETED - WORK TO BE ACCOMPLISHED UNDER U-5720B
DURHAM | NC 751 (HOPE VALLEY ROAD) | NCDOT | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5745 | REGION C | T | 2019 | 435000 |  |  | 2019 | 1313000 | 2019 | 624000 | 2372000 | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
DURHAM | NC 54 | NCDOT | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774C | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 934000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 267000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11599000 |  |  | 12800000
DURHAM | NC 54 | NCDOT | FALCONBBRIDGE ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774D | [11 empty] | SCOPE INCLUDED IN U-5774F
DURHAM | NC 54 | NCDOT | SR 1110 (FARRINGTON ROAD). CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774E | [11 empty] | SCOPE INCLUDED IN U-5774F
DURHAM | I-40 | NCDOT | NC 54 INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS, INCLUDING UPGRADE OF NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774F | STATEWIDE MOBILITY | NHP | 2028 | 91470000 | 2028 | 15700000 | 2031 | 88399000 |  |  | 195569000
DURHAM | NC 54 | NCDOT | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774G | NOT FUNDED | T | NOT FUNDED | 1800000 | NOT FUNDED | 800000 | NOT FUNDED | 16900000 |  |  | 19500000
DURHAM | NC 54 | NCDOT | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774H | NOT FUNDED | T | NOT FUNDED | 5900000 | NOT FUNDED | 726000 | NOT FUNDED | 18000000 |  |  | 24626000
DURHAM | NC 54 | NCDOT | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774I | NOT FUNDED | T | NOT FUNDED | 2500000 | NOT FUNDED | 617000 | NOT FUNDED | 12300000 |  |  | 15417000
DURHAM | NC 54 | NCDOT | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774J | NOT FUNDED | T | NOT FUNDED | 3200000 | NOT FUNDED | 420000 | NOT FUNDED | 17100000 |  |  | 20720000
DURHAM | WOODCROFT PARKWAY EXTENSION | DURHAM | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5823 | DIVISION 5 | BGANY, L | 2024 | 900000 | 2024 | 400000 | 2025 | 3750000 |  |  | 5050000 | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM
DURHAM | I-885 | NCDOT | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5934 | STATEWIDE MOBILITY | NHP | 2028 | 100000 | 2028 | 300000 | 2029 | 142301000 |  |  | 142701000
DURHAM | NC 147 (DURHAM FREEWAY) | NCDOT | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5937 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7750000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 64300000 |  |  | 81350000
DURHAM | VARIOUS | NCDOT | CITY OF DURHAM. UPGRADE ITS / SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5968 | REGION C | T |  |  |  |  | 2021 | 13000000 |  |  | 13000000 | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
DURHAM | SR 1118 (FAYETTEVILLE ROAD) | NCDOT | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6021 | DIVISION 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15200000 |  |  | 26000000
DURHAM | US 15 / US 501 | NCDOT | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6067 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 42800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 62898000 |  |  | 109398000 | COORDINATE WITH U-5717
DURHAM | NC 55 | NCDOT | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6118 | DIVISION 5 | T | 2028 | 300000 | 2028 | 200000 | 2029 | 4799000 |  |  | 5299000
DURHAM | NC 98 (HOLLOWAY STREET) | NCDOT | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6120 | DIVISION 5 | T | 2028 | 7000000 | 2028 | 1200000 | 2030 | 9999000 |  |  | 18199000
DURHAM | DURHAM AREA TRANSIT AUTHORITY | DURHAM AREA TRANSIT AUTHORITY | REPLACEMENT BUS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4923 | DIVISION 5 | 5307, 5339, L | [6 empty] | 2021 | 6184000 | 6184000 | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY
DURHAM | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | PARATRANSIT VEHICLES, BUS REFURBISHMENT, AND BUS SHELTERS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-5019A | DIVISION 5 | [10 empty] | IN PROGRESS BY CHAPEL HILL TRANSIT
DURHAM | GO TRIANGLE TRANSIT | GO TRIANGLE TRANSIT | ROUGEMONT PARK-AND-RIDE. PROFESSIONAL SERVICES AND PROPERTY ACQUISITION. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5273 | EXEMPT | BGDA, L |  |  |  |  | 2023 | 177000 |  |  | 177000 | IN PROGRESS BY TRIANGLE TRANSIT
DURHAM | GO TRIANGLE | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5286 | REGION C | 5307, L, T |  |  |  |  | 2021 | 1590000 |  |  | 1590000
DURHAM | GO TRIANGLE | GO TRIANGLE | NC 98 (HOLLOWAY STREET) TRANSIT CORRIDOR. CONSTRUCT ACCESS AND BUS STOP IMPROVEMENTS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5294 | REGION C | [10 empty] | UNDER CONSTRUCTION BY GO TRIANGLE
DURHAM | AUTHORITY DURHAM AREA TRANSIT | AUTHORITY DURHAM AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4738 | PUBLIC TRANSIT | 5307, 5339, CMAQ, L | [6 empty] | 2020 | 2376000 | 2376000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | AUTHORITY DURHAM AREA TRANSIT | AUTHORITY DURHAM AREA TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4738A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 15000000 | 15000000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GO TRIANGLE | GO TRIANGLE | SAFETY AND SECURITY - CAMERAS. | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-5235 | DIVISION 5 | BGDA, L | [9 empty] | IN PROGRESS
DURHAM | GO TRIANGLE | GO TRIANGLE | ESTABLISH NEIGHBORHOOD TRANSIT CENTERS IN DURHAM. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-5255 | REGION C | [10 empty] | IN PROGRESS
DURHAM | VARIOUS | GO DURHAM TRANSIT | NEIGHBORHOOD TRANSIT CENTER IN SOUTH DURHAM IN CONNECTION WITH SOUTHPOINT PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-5255B | REGION C
DURHAM | VARIOUS | GO DURHAM TRANSIT | NEIGHBORHOOD TRANSIT CENTER IN SOUTHWEST DURHAM IN CONNECTION WITH PATTERSON PLACE T PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-5255E | REGION C
DURHAM | DURHAM COUNTY ACCESS | DURHAM COUNTY ACCESS | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TK-6126 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 252000 | 252000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GODURHAM | GO DURHAM TRANSIT | ACQUISITION OF SIX (6) ELECTRIC TRANSIT BUSES. | PUBLIC TRANSIT |  | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TM-0043 | PUBLIC TRANSIT | CMAQ, L | [6 empty] | 2023 | 1729000 | 1729000
DURHAM | DURHAM AREA TRANSIT AUTHORITY | DURHAM AREA TRANSIT AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TO-5130 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 11224000 | 11224000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | DURHAM AREA TRANSIT AUTHORITY | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TP-5108 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 560000 | 560000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | DURHAM AREA TRANSIT AUTHORITY | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5307 | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TP-5109 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1920000 | 1920000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | DURHAM AREA TRANSIT AUTHORITY | DURHAM AREA TRANSIT AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TS-5108 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 172000 | 172000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GODURHAM | GODURHAM | GODURHAM IS PLANNING IMPROVEMENTS TO DURHAM STATION TO EXPAND EQUITABLE ACCESS TO TRANSIT, IMPROVE STATION AMENITIES, AND INCREASE CONNECTIONS TO EMPLOYMENT, HEALTHCARE AND EDUCATION OPPORTUNITIES AND CONSTRUCT 8 BUS BAYS, REDESIGNED BUS LANES, AND PLACE NEW PAVEMENT. | PUBLIC TRANSIT | PLANNING | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TU-0013 | PUBLIC TRANSIT | 5339(b), L | [6 empty] | 2023 | 13500000 | 13500000
DURHAM | NORFOLK SOUTHERN H LINE | NCDOT | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | RAIL | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5706 | STATEWIDE MOBILITY | T | 2023 | 11243000 | 2023 | 2604000 | 2028 | 33801000 |  |  | 47648000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS.
DURHAM | NORFOLK SOUTHERN H LINE | NCDOT | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | RAIL | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5717 | REGION C | T | 2022 | 8900000 | 2022 | 1878000 | 2024 | 30700000 |  |  | 41478000 | RIGHT-OF-WAY IN PROGRESS.
DURHAM | SR 1978 (HOPSON ROAD) | NCDOT | NORFOLK SOUTHERN RAILROAD-NORTH CAROLINA RAILROAD. CONSTRUCT RAILROAD GRADE SEPARATION AND SHIFT RAIL LINE | RAIL | OTHER | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4716A | [11 empty] | PROJECT COMPLETE
DURHAM | SR 1980 (CHURCH STREET) | NCDOT | NORFOLK SOUTHERN RAILROAD / NC RAILROAD TO SR 1978 (HOPSON ROAD) REALIGN AND CLOSE CROSSING 734 748M OF THE NORFOLK SOUTHERN-NORTH CAROLINA RAILROAD | RAIL | PRE-STI (HISTORIC) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4716B | PRE-STI (TRANSITION) | [10 empty] | PROJECT COMPLETE
DURHAM | SR 1978 (HOPSON ROAD) | NCDOT | SR 1978 (HOPSON ROAD), EAST OF SR 1999 (DAVIS DRIVE) TO NC 54, WIDEN TO MULTILANES | RAIL | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4716D | NOT FUNDED | O | NOT FUNDED | 1126000 |  |  | NOT FUNDED | 3160000 |  |  | 4286000
DURHAM, ORANGE | SR 2220 (OLD CHAPEL HILL ROAD) SR 1838 (OLD DURHAM | DURHAM | US 15 / US 501 IN ORANGE COUNTY TO SR 1116 (GARRETT ROAD) IN DURHAM COUNTY. BICYCLE, PEDESTRIAN, AND TRANSIT IMPROVEMENTS; AND CONSTRUCTION OF ROUNDABOUT. | HIGHWAY | PRE-STI (HISTORIC) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-4707 | PRE-STI (TRANSITION)
DURHAM, ORANGE | NC 54 | NCDOT | US 15 / US 501 IN CHAPEL HILL TO NC 55 IN DURHAM. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774 | [11 empty] | PARTS A THROUGH F ON EXPANDED NHS
DURHAM, ORANGE | TRIANGLE TRANSIT AUTHORITY | TRIANGLE TRANSIT AUTHORITY | REPLACEMENT BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4818B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 962000 | 962000
DURHAM, ORANGE | TRIANGLE TRANSIT AUTHORITY | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-5123B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 3242000 | 3242000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | DURHAM AREA TRANSIT AUTHORITY | DURHAM AREA TRANSIT AUTHORITY | OPERATING ASSISTANCE - NEW FREEDOM - URBAN | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TN-5102 | PUBLIC TRANSIT | 5317, L | [6 empty] | 2020 | 504000 | 504000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | TRIANGLE TRANSIT AUTHORITY | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | PUBLIC TRANSIT | PLANNING | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TP-4732A | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 2952000 | 2952000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | TRIANGLE TRANSIT AUTHORITY | TRIANGLE TRANSIT AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TS-5119 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 76000 | 76000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. | BIKE/PED | LOCALLY SELECTED | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4726 | DIVISION 5, 7, 8 | BGANY, BGDA, L | 2021 | 1909000 |  |  | 2021 | 11766000 |  |  | 13675000 | IN PROGRESS
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | HIGHWAY | OTHER | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5605 | EXEMPT | CMAQ, L | 2020 | 447000 |  |  | 2020 | 6095000 | 2020 | 2051000 | 8593000 | IN PROGRESS
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE DURHAM PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | HL-0094 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 4945000 |  |  | 4945000
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. | HIGHWAY | LOCALLY SELECTED | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4727 | DIVISION 5, 7, 8 | BGDA, L | [6 empty] | 2023 | 27818000 | 27818000 | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | LOCALLY SELECTED | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5023 | DIVISION 5, 7, 8 | BGDA |  |  |  |  | 2023 | 48984000 |  |  | 48984000 | INCLUDES $137K TO BE ALLOCATED TO TG-5235; $1548K ALLOCATED TO U-4726.
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | LOCALLY SELECTED | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6219 | DIVISION 5, 7, 8 | TADA |  |  |  |  | 2023 | 9449000 |  |  | 9449000
DURHAM, WAKE | I-40 SR 1728 (WADE AVENUE) | NCDOT | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | HIGHWAY | STI (PRIORITIZATION) | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO | I-6006 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 114999000 |  |  | 115999000
DURHAM, WAKE | VARIOUS PIEDMONT CORRIDOR | NCDOT | VARIOUS ROUTES AND NORFOLK SOUTHERN RAILROAD-NORTH CAROLINA RAILROAD IN DURHAM AND MORRISVILLE, SOUTH OF I-40 TO NORTH OF MCCRIMMON PARKWAY. CONSTRUCT A GRADE SEPARATION AT SR 1978 (HOPSON ROAD), EXTEND CHURCH STREET TO HOPSON ROAD, CLOSE CHURCH STREET C | RAIL | OTHER | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO | U-4716
DURHAM, WAKE | NORFOLK-SOUTHERN RAILROAD / NC RAILROAD | NCDOT | CLEGG TO NELSON. CONSTRUCT PASSING SIDING | RAIL | OTHER | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-4716C | [11 empty] | PROJECT COMPLETE
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | BO-2405 | DIVISION 5 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2405 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | R-5785 | DIVISION 5 | S, TA |  |  |  |  | 2023 | 1000000 |  |  | 1000000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5205 | [11 empty] | UNDER CONSTRUCTION
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5705 | [11 empty] | IN PROGRESS;
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5705DIV | DIVISION 5 | HSIP | 2020 | 104000 |  |  | 2020 | 540000 |  |  | 644000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5705REG | REGION C | HSIP | 2020 | 104000 |  |  | 2020 | 540000 |  |  | 644000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5705SW | STATEWIDE MOBILITY | HSIP | 2020 | 137000 |  |  | 2020 | 720000 |  |  | 857000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5 | HIGHWAY | SAFETY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5805 | [11 empty] | W-5805B PROJECT DELETED AT REQUEST OF DIVISION; WORK TO BE ACCOMPLISHED UNDER U-6023.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 5. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RC-2005 | DIVISION 5 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RX-2005 | DIVISION 5 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RX-2405 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
EDGECOMBE | TARBORO EDGECOMBE AIRPORT (ETC) | TARBORO EDGECOMBE AIRPORT (ETC) | RUNWAY EXTENSION. | AVIATION | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | AV-5897 | DIVISION 4 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4500000 |  |  | 4500000
EDGECOMBE | NC 43 BUSINESS | ROCKY MOUNT | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | BIKE/PED | LOCALLY SELECTED | 4 | ROCKY MOUNT URBAN AREA MPO | BL-0032 | DIVISION 4 | CMAQ, L | 2023 | 10000 |  |  | 2023 | 340000 | 2022 | 100000 | 450000 | UNDER CONSTRUCTION.
EDGECOMBE | NC 97 (ATLANTIC AVENUE) | ROCKY MOUNT | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5729 | DIVISION 4 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | 8600000
EDGECOMBE | EAST RALEIGH BOULEVARD | ROCKY MOUNT | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5984 | DIVISION 4 | L, TA5200 |  |  |  |  | 2028 | 2700000 | 2026 | 300000 | 3000000
EDGECOMBE | US 258 | NCDOT | REPLACE BRIDGE 320022 OVER TOWN CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-4931 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2129000 |  |  | 2129000 | UNDER CONSTRUCTION.
EDGECOMBE | NC 33 | NCDOT | REPLACE BRIDGE 320080 OVER TAR RIVER. REPLACE BRIDGE 320049 OVER TAR RIVER OVERFLOW. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-4933 | REGION A | BFP | 2025 | 860000 |  |  | 2027 | 11700000 |  |  | 12560000
EDGECOMBE | NC 111 / NC 122 | NCDOT | REPLACE BRIDGE 320011 OVER TOWN CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-5655 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1950000 |  |  | 1950000 | UNDER CONSTRUCTION.
EDGECOMBE | NC 97 | NCDOT | REPLACE BRIDGE 320087 OVER SWIFT CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-5671 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2279000 |  |  | 2279000 | UNDER CONSTRUCTION.
EDGECOMBE | NC 97 | NCDOT | REPLACE BRIDGE 320051 OVER TAR RIVER. | HIGHWAY | BRIDGES | 4 | ROCKY MOUNT URBAN AREA MPO | B-5952 | REGION A | BFP | 2028 | 100000 | 2028 | 703000 | 2030 | 6900000 |  |  | 7703000
EDGECOMBE | SR 1126 (FAITH BAPTIST CHURCH ROAD) | NCDOT | REPLACE BRIDGE 320064 OVER TOWN CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-6002 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | UNDER CONSTRUCTION.
EDGECOMBE | US 64 WEST ALTERNATE | TARRBORO | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10' MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | HIGHWAY | LOCALLY SELECTED | 4 | UPPER COASTAL PLAIN RPO | BL-0064 | EXEMPT | CMAQ, L | 2023 | 51000 |  |  | 2024 | 717000 | 2023 | 134000 | 902000
EDGECOMBE | SR 1404 (SEVEN BRIDGES ROAD) | NCDOT | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | BR-0111 | DIVISION 4 | DP | 2020 | 420000 | 2020 | 56000 | 2021 | 5450000 |  |  | 5926000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
EDGECOMBE | SR 1616 (SHARP POINT ROAD) | NCDOT | REPLACE BRIDGE 320035 OVER OTTER CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | BR-0112 | DIVISION 4 | DP |  |  |  |  | 2021 | 1112000 |  |  | 1112000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
EDGECOMBE | SR 1243 (LEGGETT ROAD) | NCDOT | REPLACE BRIDGE 320054 OVER TAR RIVER. | HIGHWAY | BRIDGES | 4 | ROCKY MOUNT URBAN AREA MPO | BR-0241 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 4.R.101 PROJECT.
EDGECOMBE | US 64 (FUTURE I-87) | NCDOT | SR 1225 (KINGSBORO ROAD) TO NC 33. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-6041 | STATEWIDE MOBILITY | HP, NHPIM |  |  |  |  | 2023 | 29900000 |  |  | 29900000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196.
EDGECOMBE | US 64 (FUTURE I-87) | NCDOT | REHABILITATE BRIDGES 320104, 320155, 320148, 320153, 320154, 320156, 320157, 320320, 320325, AND 320326. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-6041A | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION.
EDGECOMBE | US 64 (FUTURE I-87) | NCDOT | NC 33 TO MARTIN COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-6042 | STATEWIDE MOBILITY | HP, NHPIM |  |  |  |  | 2023 | 19700000 |  |  | 19700000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196.
EDGECOMBE | US 64 (FUTURE I-87) | NCDOT | REHABILITATE BRIDGE 320327 AND 320328. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-6042A | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 300000 |  |  | 300000 | UNDER CONSTRUCTION.
EDGECOMBE | NEW ROUTE | NCDOT | SR 1252 (DUNBAR ROAD) TO SR 1225 (KINGSBORO ROAD). CONSTRUCT TWO LANE ROAD ON NEW LOCATION AND IMPROVEMENTS TO SR 1225 TO SERVE KINGSBORO MEGASITE. | HIGHWAY | ECONOMIC DEVELOPMENT | 4 | UPPER COASTAL PLAIN RPO | R-5868 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION. THIS IN AN ECONOMIC DEVELOPMENT PROJECT FOR TRIANGLE TYRE.
EDGECOMBE | US 258 | NCDOT | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | R-5949 | DIVISION 4 | T | 2027 | 1901000 | 2027 | 900000 | 2029 | 25400000 |  |  | 28201000
EDGECOMBE | NC 111 (WILSON STREET) | NCDOT | US 64 ALTERNATE (WESTERN BOULEVARD) TO NC 122 (MCNAIR ROAD). WIDEN TO THREE LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | U-4424 | DIVISION 4 | T |  |  |  |  | 2023 | 20000000 |  |  | 20000000 | UNDER CONSTRUCTION.
EDGECOMBE | SR 1250 (SPRINGFIELD ROAD) | NCDOT | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | U-4762 | DIVISION 4 | T |  |  |  |  | 2019 | 6255000 | 2021 | 1995000 | 8250000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
EDGECOMBE | CSX A LINE | CSXT RR | CCX INTERMODAL TERMINAL AND TRACK IMPROVEMENTS. | RAIL | OTHER | 4 | ROCKY MOUNT URBAN AREA MPO | P-5711A | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 43100000 |  |  | 43100000 | UNDER CONSTRUCTION.
EDGECOMBE, HALIFAX | US 258 | NCDOT | US 258 BETWEEN THE PITT COUNTY LINE AND US 64 IN EDGECOMBE COUNTY AND BETWEEN PRINCEVILLE AND SR 1102 (MULLIN ROAD) IN HALIFAX COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS, SNOWPLOWABLE PAVEMENT MARKERS, AND RUMBLE STRIPES. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, PEANUT BELT RPO | HS-2004R | REGION A | HSIP |  |  |  |  | 2023 | 780000 |  |  | 780000 | UNDER CONSTRUCTION.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | OTHER | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | BO-2404 | DIVISION 4 | S, TA |  |  |  |  | 2024 | 5000000 |  |  | 5000000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | HS-2004
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | HS-2404 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | OTHER | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | R-5784 | DIVISION 4 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. S FUNDS REFLECT STATE HIGHWAY FUNDS.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5204 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5704 | [11 empty] | IN PROGRESS
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5704DIV | DIVISION 4 | HSIP | 2020 | 144000 |  |  | 2022 | 360000 |  |  | 504000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5704REG | REGION A | HSIP | 2022 | 30000 |  |  | 2020 | 455000 |  |  | 485000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5704SW | STATEWIDE MOBILITY | HSIP | 2022 | 40000 |  |  | 2022 | 480000 |  |  | 520000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5804
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 4. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | RC-2004 | DIVISION 4
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | RX-2004 | DIVISION 4
EDGECOMBE, JOHNSTON, WAYNE, WILSON, HALIFAX, NASH | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | RX-2404 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
EDGECOMBE, NASH | ROCKY MOUNT | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5763 | DIVISION 4 | L, TA5200 | 2024 | 300000 |  |  | 2025 | 1500000 | 2022 | 200000 | 2000000
EDGECOMBE, NASH | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | HIGHWAY | OTHER | 4 | ROCKY MOUNT URBAN AREA MPO | C-5616 | EXEMPT | CMAQ, L | 2020 | 116000 |  |  | 2020 | 910000 | 2020 | 348000 | 1374000
EDGECOMBE, NASH | US 64 (FUTURE I-87) | NCDOT | SR 1603 (OLD CARRIAGE ROAD) TO SR 1225 (KINGSBORO ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | ROCKY MOUNT URBAN AREA MPO, UPPER COASTAL PLAIN RPO | I-6046 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 24006000 |  |  | 24006000 | UNDER CONSTRUCTION.
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | ROCKY MOUNT URBAN AREA MPO | TG-4785A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | ROCKY MOUNT URBAN AREA MPO | TG-4785B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2400000 | 2400000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | ROCKY MOUNT URBAN AREA MPO | TK-5180 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 780000 | 780000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | PURCHASE AND INSTALL 20 BUS SHELTERS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 4 | ROCKY MOUNT URBAN AREA MPO | TL-0015 | PUBLIC TRANSIT | CARES | [6 empty] | 2022 | 150000 | 150000
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | UPDATE THE TAR RIVER TANSIT AUTOMATED VEHICLE LOCATOR SYSTEM | PUBLIC TRANSIT | CAPITAL (NON-STI) | 4 | ROCKY MOUNT URBAN AREA MPO | TL-0016 | PUBLIC TRANSIT | CARES | [6 empty] | 2022 | 300000 | 300000
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 4 | ROCKY MOUNT URBAN AREA MPO | TO-5127 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 4000000 | 4000000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | VARIOUS | CSXT RR | CAROLINIAN CORRIDOR - CSXT MP A 115.9 (ARMSTRONG CROSSING). | RAIL | TRANSITION | 4 | ROCKY MOUNT URBAN AREA MPO | P-5005B | PRE-STI (TRANSITION)
EDGECOMBE, NASH | CSX A LINE | CSXT RR | CONSTRUCT FREIGHT RAIL AND INTERMODAL TERMINAL INFRASTRUCTURE (CCX) ALONG NATIONAL GATEWAY CORRIDOR. | RAIL | OTHER | 4 | ROCKY MOUNT URBAN AREA MPO, UPPER COASTAL PLAIN RPO | P-5711 | STATEWIDE MOBILITY
EDGECOMBE, NASH | CSX A LINE | NCDOT | HIGHWAY IMPROVEMENTS | RAIL | OTHER | 4 | ROCKY MOUNT URBAN AREA MPO | P-5711C | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION.
FORSYTH | SMITH REYNOLDS AIRPORT (INT) | SMITH REYNOLDS AIRPORT (INT) | ACQUIRE LAND AND CLEAR TERRAIN OBSTRUCTIONS EAST OF RUNWAY 15-33 TO DRAIN AND GRADE MATERIAL IN PLACE. | AVIATION | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | AV-5738 | DIVISION 9 | T |  |  |  |  | 2031 | 2450000 |  |  | 2450000 | RIGHT-OF-WAY IN PROGRESS BY AIRPORT
FORSYTH | AIRPORT (INT) SMITH REYNOLDS | SMITH REYNOLDS AIRPORT (INT) | CONSTRUCT NEW TAXILANE. | AVIATION | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | AV-5832 | DIVISION 9 | T |  |  |  |  | 2025 | 15700000 |  |  | 15700000
FORSYTH | SR 4278 (SOUTH CHERRY STREET) | KERNERSVILLE | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0014 | DIVISION 9 | BGANY, BGDA, L | 2023 | 145000 |  |  | 2024 | 2257000 | 2022 | 361000 | 2763000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | BROAD STREET | KERNERSVILLE | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0015 | DIVISION 9 | BGDA, L | 2025 | 99000 |  |  | 2026 | 964000 | 2025 | 47000 | 1110000
FORSYTH | HARMON LANE | KERNERSVILLE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0016 | DIVISION 9 | BGDA, L | 2024 | 79000 |  |  | 2025 | 365000 | 2024 | 10000 | 454000
FORSYTH | SOUTHERN STREET GREENWAY | KERNERSVILLE | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0017 | DIVISION 9 | BGDA, L | 2024 | 50000 |  |  | 2025 | 851000 | 2023 | 146000 | 1047000
FORSYTH | BREWER ROAD | WINSTON-SALEM | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0018 | DIVISION 9 | BGANY, BGDA, L | 2023 | 513000 |  |  | 2024 | 2326000 | 2023 | 205000 | 3044000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | LONG BRANCH TRAIL PHASE II | WINSTON-SALEM | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0019 | DIVISION 9 | BGDA, DP, L | 2025 | 100000 |  |  | 2025 | 7500000 | 2024 | 1000000 | 8600000 | DP REPRESENT RAISE GRANT FUNDS
FORSYTH | DEPOT STREET | WALKERTOWN | US 311 (MAIN STREET) TO SR 1992 (SULLIVANTOWN ROAD) IN WALKERTOWN. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0020 | DIVISION 9 | BGDA, L |  |  |  |  | 2023 | 479000 |  |  | 479000
FORSYTH | SALEM CREEK GREENWAY BRIDGE | WINSTON-SALEM | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0072 | DIVISION 9 | BGDA, L | 2024 | 115000 |  |  | 2025 | 575000 | 2023 | 322000 | 1012000
FORSYTH | BRUSHY FORK GREENWAY | WINSTON-SALEM | WATERWORKS ROAD TO REYNOLDS PARK ROAD IN WINSTON-SALEM. PAVED MULTI-USE TRAIL. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-4020 | PRE-STI (TRANSITION)
FORSYTH | BRUSHY FORK GREENWAY | WINSTON-SALEM | WATERWORKS ROAD TO OLD GREENSBORO ROAD | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-4020A | [11 empty] | COMPLETE
FORSYTH | BRUSHY FORK GREENWAY | WINSTON-SALEM | OLD GREENSBORO ROAD TO LOWERY STREET | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-4020B | [11 empty] | COMPLETE
FORSYTH | BRUSHY FORK GREENWAY | WINSTON-SALEM | LOWERY STREET TO REYNOLDS PARK ROAD | BIKE/PED | TRANSITION | 9 | WINSTON-SALEM URBAN AREA MPO | EB-4020C | PRE-STI (TRANSITION) | BGANY, L |  |  |  |  | 2023 | 2158000 |  |  | 2158000 | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | NC 67 (SILAS CREEK PARKWAY) | WINSTON-SALEM | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | BIKE/PED | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5722 | DIVISION 9 | BGANY, BGDA, L, TAANY | 2022 | 910000 |  |  | 2023 | 4038000 |  |  | 4948000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | BARBARA JANE AVENUE | WINSTON-SALEM | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5810 | DIVISION 9 | BGDA, L, TAANY |  |  |  |  | 2024 | 226000 |  |  | 226000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SALEM CREEK GREENWAY | WINSTON-SALEM | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5812 | DIVISION 9 | L, TAANY |  |  |  |  | 2026 | 1500000 | 2020 | 150000 | 1650000
FORSYTH | US 158 / US 421 / NC 150 (SALEM PARKWAY) | WINSTON-SALEM | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5840 | DIVISION 9 | BGDA, L, TAANY, TADA |  |  |  |  | 2023 | 3730000 |  |  | 3730000 | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT
FORSYTH | SR 1122 (JONESTOWN ROAD) | WINSTON-SALEM | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | BIKE/PED | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5920 | DIVISION 9 | L, TAANY | 2024 | 80000 | 2024 | 85000 | 2025 | 585000 | 2021 | 50000 | 800000
FORSYTH | FAIRLAWN DRIVE | WINSTON-SALEM | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5952 | DIVISION 9 | BGANY, BGDA, L | 2022 | 248000 |  |  | 2023 | 741000 |  |  | 989000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 4000 (UNIVERSITY PARKWAY) | WINSTON-SALEM | SR-1686 (SHATTALON DRIVE) TO ROBIN WOOD LANE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5953 | DIVISION 9 | BGDA, L |  |  |  |  | 2024 | 635000 |  |  | 635000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM
FORSYTH | GRIFFITH ROAD | WINSTON-SALEM | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5954 | DIVISION 9 | BGANY, L | 2023 | 42000 |  |  | 2023 | 1620000 |  |  | 1662000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 1348 (ROBINHOOD ROAD) | WINSTON-SALEM | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5955 | DIVISION 9 | BGANY, L | 2022 | 66000 |  |  | 2024 | 470000 |  |  | 536000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 1992 (SULLIVANTOWN ROAD) | WALKERTOWN | US 311 AT HARLEY DRIVE TO WALKERTOWN HIGH/MIDDLE SCHOOL IN WALKERTOWN. INSTALL BICYCLE AND PEDESTRIAN FACILITIES AND CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5956 | DIVISION 9 | BGDA, L |  |  |  |  | 2023 | 560000 |  |  | 560000
FORSYTH | SR 2648 (OLD WINSTON ROAD) | KERNERSVILLE | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5957 | DIVISION 9 | BGANY, BGDA, L | 2021 | 36000 |  |  | 2023 | 232000 |  |  | 268000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 3000 (IDOLS ROAD) | CLEMMONS | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5959 | DIVISION 9 | BGANY, BGDA, L |  |  |  |  | 2025 | 897000 | 2021 | 110000 | 1007000 | IN PROGRESS
FORSYTH | SR 1101 (HARPER ROAD) | CLEMMONS | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5960 | DIVISION 9 | BGANY, BGDA, L, TADA |  |  |  |  | 2023 | 1126000 | 2021 | 125000 | 1251000 | IN PROGRESS
FORSYTH | US 158 / US 421 (SALEM PARKWAY) | WINSTON-SALEM | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | EB-6008 | DIVISION 9 | CMAQ, L, TAANY | 2024 | 408000 |  |  | 2025 | 3444000 | 2020 | 339000 | 4191000
FORSYTH | SR 1101 (HARPER ROAD) | CLEMMONS | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-6040 | DIVISION 9 | BGDA, L |  |  |  |  | 2023 | 598000 | 2022 | 66000 | 664000
FORSYTH | PIEDMONT REGIONAL GREENWAY | WINSTON-SALEM | WINSTON-SALEM - PIEDMONT REGIONAL GREENWAY | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-4741OK | DIVISION 9 | L, TADA | 2023 | 900000 | [6 empty] | 900000
FORSYTH | WEST FIRST STREET | WINSTON-SALEM | REPLACE BRIDGE 330296 OVER NORFOLK SOUTHERN RAILWAY IN WINSTON-SALEM. | HIGHWAY | MUNICIPAL BRIDGE | 9 | WINSTON-SALEM URBAN AREA MPO | B-5007 | DIVISION 9 | BFPOFF | 2027 | 70000 |  |  | 2028 | 700000 |  |  | 770000
FORSYTH | SALISBURY RIDGE ROAD | NCDOT | REPLACE BRIDGE 330243 OVER NC 150 IN WINSTON-SALEM. | HIGHWAY | BRIDGES | 9 | WINSTON-SALEM URBAN AREA MPO | B-5770 | DIVISION 9 | BGOFF |  |  |  |  | 2022 | 5501000 |  |  | 5501000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | NC 67 (WESTBOUND) (SILAS CREEK PARKWAY) | NCDOT | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | HIGHWAY | BRIDGES | 9 | WINSTON-SALEM URBAN AREA MPO | B-5950 | REGION D | BFP | 2026 | 750000 | 2026 | 1000 | 2027 | 7501000 |  |  | 8252000
FORSYTH | LEWISVILLE | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | C-5705 | EXEMPT | CMAQ, L | 2024 | 100000 |  |  | 2025 | 392000 | 2023 | 40000 | 532000
FORSYTH | THIRD STREET | NCDOT | REPLACE BRIDGE 330185 OVER US 52 / NC 8 IN WINSTON-SALEM. | HIGHWAY | BRIDGES | 9 | WINSTON-SALEM URBAN AREA MPO | HB-0031 | DIVISION 9 | BGOFF | 2025 | 275000 | 2025 | 275000 | 2026 | 5500000 |  |  | 6050000
FORSYTH | POLO ROAD | NCDOT | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | HIGHWAY | BRIDGES | 9 | WINSTON-SALEM URBAN AREA MPO | HB-0033 | DIVISION 9 | BFP | 2027 | 300000 | 2027 | 300000 | 2028 | 6000000 |  |  | 6600000
FORSYTH | SIXTEENTH STREET | NCDOT | REPLACE BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | HIGHWAY | BRIDGES | 9 | WINSTON-SALEM URBAN AREA MPO | HB-0036 | DIVISION 9 | BGOFF | 2026 | 210000 | 2026 | 210000 | 2027 | 4200000 |  |  | 4620000
FORSYTH | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | KERNERSVILLE | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | HL-0015 | EXEMPT | BGANY, BGDA, L | 2024 | 282000 |  |  | 2025 | 3181000 | 2022 | 821000 | 4284000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | US 311 (MAIN STREET) | WALKERTOWN | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | HL-0016 | EXEMPT | BGDA, L | 2024 | 90000 |  |  | 2024 | 515000 |  |  | 605000
FORSYTH | NC 8 (GERMANTON ROAD) | NCDOT | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | HL-0059 | EXEMPT | BGDA, CMAQ, S | 2023 | 330000 | 2023 | 250000 | 2023 | 1244000 | 2023 | 75000 | 1899000 | "S" FUNDS REFLECT SPOT MOBILITY FUNDS
FORSYTH | NC (REYNOLDS ROAD) | NCDOT | NC 67 (REYNOLDA ROAD) AT BETHABARA PARK BOULEVARD. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND OTHER PEDESTRIAN ACCOMODATIONS. | HIGHWAY | SAFETY | 9 | WINSTON-SALEM URBAN AREA MPO | HS-2009G | REGION D | HSIP | 2023 | 25000 | 2023 | 60000 | 2024 | 331000 |  |  | 416000
FORSYTH | I-40 | NCDOT | 1.3 MILES EAST OF NC 150 (PETERS CREEK PARKWAY) TO NC 109 (THOMASVILLE ROAD) IN WINSTON-SALEM. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | I-5766 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - COORDINATE WITH I-5857
FORSYTH | I-74 / US 311 | NCDOT | I-40 TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO | I-5767 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED IN I-5736
FORSYTH | I-40 | NCDOT | 0.3 MILE EAST OF SR 3153 (HANES MALL BOULEVARD) TO 0.9 MILE EAST OF NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM AND SR 2747 (CLEMMONSVILLE ROAD) IN WINSTON-SALEM TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION AND REHABILITATION OF BRIDGES 330161, 330162, 330444, 330448, 330449,330508, AND 330509. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | I-5795 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2020 | 23814000 |  |  | 23814000 | UNDER CONSTRUCTION
FORSYTH | I-40 / US 311 | NCDOT | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | I-5880 | REGION D | NHP, T | 2023 | 2600000 | 2023 | 800000 | 2025 | 24000000 |  |  | 27400000
FORSYTH | I-40 | NCDOT | SR 1101 (HARPER ROAD) IN CLEMMONS TO EAST OF US 421 / BUSINESS 40 IN WINSTON-SALEM. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | I-5952 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION. DELETE I-5952A. WORK ACCOMPLISHED UNDER I-5795.
FORSYTH | I-40 | NCDOT | I-74 / US 311 TO SR 2643 (UNION CROSS ROAD). | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981A | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 61293000 |  |  | 67693000
FORSYTH | I-40 | NCDOT | SR 2643 (UNION CROSS ROAD) TO NC 66. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981B | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38194000 |  |  | 40394000
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, I-40 TO US 52. FOUR LANE EXPRESSWAY ON NEW LOCATION., INCLUDING ITS DEPLOYMENT. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247A | NOT FUNDED | NHP, T | NOT FUNDED | 13200000 | NOT FUNDED | 18900000 | NOT FUNDED | 39101000 |  |  | 71201000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247B | NOT FUNDED | NHP, T | NOT FUNDED | 31900000 | NOT FUNDED | 3000000 | NOT FUNDED | 149499000 |  |  | 184399000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CA | REGION D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 261000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 140899000 |  |  | 141660000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CB | REGION D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 92000000 |  |  | 117000000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, MUDDY CREEK. REPLACE BRIDGE NO. 221 AND BRIDGE NO. 222 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CC | [11 empty] | COMPLETE - WORK ACCOMPLISHED UNDER B-4507
FORSYTH | SR 1891 / NON-SYSTEM (PEACE HAVEN ROAD) | NCDOT | SR 1891 / NON-SYSTEM (PEACE HAVEN ROAD) - US 421 INTERCHANGE AND APPROACHES | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CD | STATEWIDE MOBILITY | [10 empty] | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247EC
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247D | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2299000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 65000000 |  |  | 68499000
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EA | REGION D | NHP, T | 2028 | 14700000 | 2028 | 1100000 | 2030 | 160198000 |  |  | 175998000
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE AT US 52 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EB | STATEWIDE MOBILITY | NHP |  |  |  |  | 2018 | 83655000 |  |  | 83655000 | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032
FORSYTH | US 52 / FUTURE I-74 | NCDOT | NC 65 INTERCHANGE. RECONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EC | STATEWIDE MOBILITY | [10 empty] | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247CD
FORSYTH | US 158 | NCDOT | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | R-2577A | REGION D | T | 2021 | 36300000 | 2021 | 469000 | 2024 | 73905000 |  |  | 110674000 | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE)
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO US 52. MULTI-LANE FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579 | [11 empty] | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO I-40 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579AA | REGION D | NHP |  |  |  |  | 2023 | 144951000 |  |  | 144951000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579AB | REGION D | NHP, S(M) |  |  |  |  | 2022 | 310367000 |  |  | 310367000 | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158 | HIGHWAY | TRANSITION | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579B | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2015 | 68971000 |  |  | 68971000 | UNDER CONSTRUCTION; GARVEE BONDS: $96 MILLION FOR CONSTRUCTION - PAYBACK 2015-2026
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158. STREAM RELOCATION. | HIGHWAY | TRANSITION | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579BA | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2021 | 9300000 |  |  | 9300000 | UNDER CONSTRUCTION
FORSYTH | FUTURE I-74 | NCDOT | CONSTRUCT NOISE WALL | HIGHWAY | TRANSITION | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579BB | PRE-STI (TRANSITION) | T |  |  | 2022 | 234000 | 2023 | 2855000 |  |  | 3089000 | UNDER CONSTRUCTION
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579C | REGION D | NHP, T | 2016 | 6138000 |  |  | 2018 | 27222000 |  |  | 33360000 | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 311 TO SR 2211 (BAUX MOUNTAIN ROAD) | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579D | STATEWIDE MOBILITY | NHP |  |  |  |  | 2018 | 42380000 |  |  | 42380000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $38 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, SR 2211 (BAUX MOUNTAIN ROAD) TO NC 8 | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579E | STATEWIDE MOBILITY | NHP |  |  |  |  | 2018 | 33462000 |  |  | 33462000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $30 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, NC 8 TO WEST OF NC 66 (UNIVERSITY PARKWAY) | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579F | STATEWIDE MOBILITY | NHP |  |  |  |  | 2018 | 26767000 |  |  | 26767000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $24 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | SR 2667 (HASTINGS HILL ROAD) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, BRIDGE NO. 366 OVER US 421 / NC 150 / BUSINESS 40 | HIGHWAY | PRE-STI (HISTORIC) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579G | [11 empty] | PROJECT COMPLETE
FORSYTH | SR 3000 (IDOLS ROAD) | NCDOT | SR 2999 (HAMPTON ROAD) TO US 158 IN CLEMMONS. CONSTRUCT TWO-LANE SHOULDER SECTION ON NEW LOCATION AND REPLACE BRIDGE 330109 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2707 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
FORSYTH | SR 1672 (HANES MILL ROAD) | NCDOT | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2729 | DIVISION 9 | T | 2019 | 686000 |  |  | 2023 | 17599000 | 2020 | 1092000 | 19377000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
FORSYTH | US 158 / US 421 / NC 150 / BUSINESS 40 | NCDOT | I-40 TO WEST OF US 158 IN WINSTON-SALEM. PAVEMENT REHABILITATION, REPLACE BRIDGES 330178, 330269, 330278, 330286, 330288 330291, 330293, 330305, 330312 330313, 330336 AND VARIOUS SAFETY IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2827
FORSYTH | US 421 / BUSINESS 40 | NCDOT | WEST OF OLD VINEYARD ROAD TO EAST OF US 158 (STRATFORD ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2827A | [11 empty] | COMPLETE
FORSYTH | US 158 / US 421 / NC 150 / BUSINESS 40 | NCDOT | WEST OF FOURTH STREET TO EAST OF CHURCH STREET | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2827B | REGION D | [10 empty] | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT
FORSYTH | US 158 / US 421 / NC 150 / BUSINESS 40 | NCDOT | WEST OF US 311 (MARTIN LUTHER KING, JR. DRIVE) TO WEST OF US 158 | HIGHWAY | PRE-STI (HISTORIC) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2827C | [11 empty] | COMPLETE
FORSYTH | NEW ROUTE | NCDOT | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE) TO SR 4325 (MARTIN LUTHER KING, JR. DRIVE) IN WINSTON-SALEM. MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | PRE-STI (HISTORIC) | 9 | WINSTON-SALEM URBAN AREA MPO | U-2925 | PRE-STI (TRANSITION) | [10 empty] | DESIGN-BUILD PROJECT COMPLETE
FORSYTH | NEW ROUTE | WINSTON-SALEM | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-2925C | DIVISION 9 | BGANY, BGDA, L |  |  |  |  | 2024 | 1358000 | 2021 | 453000 | 1811000 | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | NEW ROUTE | NCDOT | MACY GROVE ROAD EXTENSION, SR 1005 (EAST MOUNTAIN STREET) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. FOUR-LANE DIVIDED FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-4734 | DIVISION 9 | T |  |  |  |  | 2019 | 11172000 |  |  | 11172000 | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
FORSYTH | NEW ROUTE | NCDOT | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-5536 | DIVISION 9 | T | 2022 | 14792000 | 2022 | 1300000 | 2024 | 18792000 |  |  | 34884000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | WINSTON-SALEM | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-5539A | DIVISION 9 | BGANY, L | 2023 | 600000 |  |  | 2024 | 2188000 |  |  | 2788000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | SR 1173 (WILLIAMS ROAD) | LEWISVILLE | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-5617 | DIVISION 9 | BGANY, L |  |  |  |  | 2023 | 2109000 |  |  | 2109000 | UNDER CONSTRUCTION.
FORSYTH | KERNERSVILLE SOUTHERN LOOP (PHASE I) | NCDOT | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-5760 | DIVISION 9 | T | 2022 | 11500000 | 2022 | 4000000 | 2025 | 44462000 |  |  | 59962000 | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
FORSYTH | NC 66 (OLD HOLLOW ROAD) | NCDOT | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-5824 | DIVISION 9 | T | 2021 | 18798000 |  |  | 2024 | 19900000 |  |  | 38698000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | NEW ROUTE | NCDOT | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-5899 | DIVISION 9 | T | 2022 | 4300000 | 2022 | 1300000 | 2024 | 9001000 |  |  | 14601000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | NEW ROUTE | NCDOT | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-6003 | DIVISION 9 | T |  |  |  |  | 2024 | 12400000 |  |  | 12400000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | NCDOT | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-6004 | DIVISION 9 | BGANY, T | 2024 | 15400000 | 2024 | 2600000 | 2026 | 23735000 |  |  | 41735000 | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | NCDOT | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-6005 | DIVISION 9 | T | 2023 | 3800000 | 2023 | 900000 | 2025 | 5300000 |  |  | 10000000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | US 421 (SALEM PARKWAY) | NCDOT | SR 2662 (LINVILLE ROAD) IN WINSTON-SALEM. UPGRADE INTERCHANGE AND REPLACE BRIDGE 330211 ON SR 2377 (OLD GREENSBORO ROAD NE) OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 9 | WINSTON-SALEM URBAN AREA MPO | U-6059
FORSYTH | SR 2377 (OLD GREENSBORO ROAD NE) | NCDOT | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 9 | WINSTON-SALEM URBAN AREA MPO | U-6059A | DIVISION 9 | BGOFF | 2025 | 4229000 | 2025 | 1100000 | 2027 | 6800000 |  |  | 12129000
FORSYTH | US 421 (SALEM PARKWAY) | NCDOT | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-6059B | NOT FUNDED | T | NOT FUNDED | 11100000 | NOT FUNDED | 1332000 | NOT FUNDED | 28860000 |  |  | 41292000 | COORDINATE WITH U-6068
FORSYTH | SR 1308 (LEWISVILLE-VIENNA ROAD) | LEWISVILLE | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-6154 | DIVISION 9 | BGANY, BGDA, L | 2023 | 474000 |  |  | 2023 | 1867000 | 2023 | 341000 | 2682000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 1969 (PINEY GROVE ROAD) | NCDOT | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-6188 | DIVISION 9 | T | 2027 | 1100000 | 2027 | 400000 | 2029 | 4100000 |  |  | 5600000
FORSYTH | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | NCDOT | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-6189 | DIVISION 9 | T | 2027 | 10700000 | 2027 | 800000 | 2029 | 12400000 |  |  | 23900000
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | NCDOT | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | U-6190 | DIVISION 9 | T | 2027 | 1700000 | 2027 | 400000 | 2029 | 3100000 |  |  | 5200000
FORSYTH | NEW ROUTE | NCDOT | SR 4001 (REYNOLDS BOULEVARD) TO SR 2264 (AKRON DRIVE) AT INTERSECTION OF SR 1763 (INDIANA AVENUE) IN WINSTON-SALEM. CONSTRUCT ACCESS ROAD. | HIGHWAY | ECONOMIC DEVELOPMENT | 9 | WINSTON-SALEM URBAN AREA MPO | U-6231 | DIVISION 9 | L, T |  |  |  |  | 2021 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL.
FORSYTH | SR 4315 (SOUTH MAIN STREET); SR 2648 (OLD WINSTON | NCDOT | SR 4315 (SOUTH MAIN STREET), BUSINESS 40 / US 421 / NC 150 TO NORTH OF SR 4278 (SOUTH CHERRY STREET), AND SR 2648 (OLD WINSTON ROAD), WEST OF SOUTH CHERRY STREET TO SOUTH MAIN STREET IN KERNERSVILLE. SAFETY IMPROVEMENTS, INCLUDING RAISED MEDIAN, TURN LANE | HIGHWAY | SAFETY | 9 | WINSTON-SALEM URBAN AREA MPO | W-5510 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | WINSTON-SALEM EXPRESS. PURCHASE ONE EXPANSION 40-FT BUS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | WINSTON-SALEM URBAN AREA MPO | TA-6682 | REGION D
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5339 BUS AND BUS FACILITIES GRANT | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | WINSTON-SALEM URBAN AREA MPO | TD-5303 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 5840000 | 5840000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | TG-5126 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 18210000 | 18210000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | TG-5241 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 23610000 | 23610000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT |  | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | TG-6731 | PUBLIC TRANSIT | CMAQ, L | [6 empty] | 2020 | 1013000 | 1013000
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL, PASSENGER SHELTERS, PASSENGER AMENITIES, SHOP EQUIPMENT, SPARE PARTS | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | TG-6783 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 1111000 | 1111000
FORSYTH | WINSTON SALEM TRANSIT AUTHORITY | WINSTON SALEM TRANSIT AUTHORITY | THE INNOVATIVE COORDINATED ACCESS AND MOBILITY (ICAM) GRANT WILL BE USED TO IMPROVE PARATRANSIT TRACKING AND ACCESSIBILITY THROUGH GPS AND NOTIFICATION SERVICES, AS WELL AS PROVIDE MOBILE TICKETING OPTIONS FOR WINSTON SALEM TRANSIT AUTHORITY`S (WSTA) FIXED ROUTE BUS SERVICES. | PUBLIC TRANSIT |  | 9 | WINSTON-SALEM URBAN AREA MPO | TL-0025 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 400000 | 400000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | TM-5309 | PUBLIC TRANSIT | 5316, L | [6 empty] | 2020 | 660000 | 660000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 9 | WINSTON-SALEM URBAN AREA MPO | TO-5126 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 5802000 | 5802000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 9 | WINSTON-SALEM URBAN AREA MPO | TO-6150 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 5610000 | 5610000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | WINSTON-SALEM URBAN AREA MPO | TP-5105 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 618000 | 618000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPET GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE TRANSPORTATION NEEDS OF LOW INCOME, DISABLED AND ELDERLY POPULATIONS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | TQ-6702 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 2635000 | 2635000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPETE GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE NEEDS OF LOW INCOME, DISABLED, AND ELDERLY POPULATIONS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | TQ-6782 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 3607000 | 3607000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | WINSTON-SALEM URBAN AREA MPO | TS-5120 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 266000 | 266000
FORSYTH | SR 2385 (WALKERTOWN-GUTHRIE ROAD) | NCDOT | NORFOLK SOUTHERN CROSSING 722063Y IN WALKERTOWN. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 9 | WINSTON-SALEM URBAN AREA MPO | RX-2009B | DIVISION 9 | RR |  |  |  |  | 2025 | 411000 |  |  | 411000
FORSYTH | SR 2381 (WILLSTON ROAD) | NCDOT | NORFOLK SOUTHERN CROSSING 470210K IN WALKERTOWN. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 9 | WINSTON-SALEM URBAN AREA MPO | RX-2009C | DIVISION 9 | RR |  |  |  |  | 2026 | 601000 |  |  | 601000
FORSYTH | SR 1686 (SHATTALON DRIVE) | NCDOT | NORFOLK SOUTHERN CROSSING 722024H IN WINSTON-SALEM. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 9 | WINSTON-SALEM URBAN AREA MPO | RX-2009D | DIVISION 9 | RR |  |  |  |  | 2027 | 492000 |  |  | 492000
FORSYTH, DAVIDSON | I-285 / US 52 / NC 8 | NCDOT | I-40 IN FORSYTH COUNTY TO SR 3010 (OLD US 52) IN DAVIDSON COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 9 | WINSTON-SALEM URBAN AREA MPO | HI-0005 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2025 | 27000000 |  |  | 27000000
FORSYTH, DAVIDSON, DAVIE | VARIOUS | WINSTON-SALEM | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | HIGHWAY | OTHER | 9 | WINSTON-SALEM URBAN AREA MPO | C-5620 | EXEMPT | CMAQ, L | 2020 | 366000 |  |  | 2020 | 5331000 | 2020 | 1098000 | 6795000 | IN PROGRESS
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | BIKE/PED | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-4741 | DIVISION 9 | BGANY, BGDA, L, TADA | 2022 | 788000 |  |  | 2020 | 2953000 |  |  | 3741000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WINSTON-SALEM PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | HL-0108 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 5559000 |  |  | 5559000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-4742 | DIVISION 9 | BGDA, L |  |  |  |  | 2020 | 875000 |  |  | 875000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-4951 | DIVISION 9 | BGDA, L | [6 empty] | 2020 | 4430000 | 4430000 | FORMERLY U-9999D - IN PROGRESS
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-5022 | DIVISION 9 | BGDA |  |  |  |  | 2023 | 93095000 |  |  | 93095000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | LOCALLY SELECTED | 9 | WINSTON-SALEM URBAN AREA MPO | U-6221 | DIVISION 9 | TADA |  |  |  |  | 2022 | 12941000 |  |  | 12941000
FORSYTH, DAVIE | I-40 | NCDOT | WEST OF NC 801 IN BERMUDA RUN TO WEST OF SR 1122 (JONESTOWN ROAD) IN WINSTON-SALEM. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 9 | WINSTON-SALEM URBAN AREA MPO | I-0911 | [11 empty] | PARTS B AND C COMPLETE
FORSYTH, GUILFORD | I-40 | NCDOT | I-74 US 311 IN WINSTON-SALEM TO US 421 / BUSINESS 40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | HIGHWAY | STI (PRIORITIZATION) | 7, 9 | WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO | I-5981
FORSYTH, GUILFORD | US 158 | NCDOT | MULTLANES NORTH OF US 421 / I-40 BUSINESS IN WINSTON-SALEM TO US 220 IN STOKESDALE. WIDEN TO A FOUR LANE DIVIDED FACILITY | HIGHWAY | STI (PRIORITIZATION) | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | R-2577
FORSYTH, GUILFORD | US 158 | NCDOT | SR 1965 (BELEWS CREEK ROAD) IN FORSYTH COUNTY TO SR 2034 (ANTHONY ROAD) IN GUILFORD COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | R-2577B | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 60300000 |  |  | 108800000
FORSYTH, GUILFORD | US 421 (SALEM PARKWAY) | NCDOT | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | HIGHWAY | STI (PRIORITIZATION) | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6068 | NOT FUNDED | T | NOT FUNDED | 57300000 | NOT FUNDED | 2114000 | NOT FUNDED | 71300000 |  |  | 130714000 | COORDINATE WITH U-6059B
FORSYTH, GUILFORD, RANDOLPH | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE VEHICLES FOR VANPOOL FLEET EXPANSION. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 7, 8, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | TA-6722 | DIVISION 7, 8, 9 | L, T |  |  |  |  | 2021 | 100000 |  |  | 100000
FORSYTH, GUILFORD, WATAUGA, WILKES, YADKIN | COACH AMERICA | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7, 9, 11 |  | TI-6103 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 3520000 | 3520000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH, SURRY | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 | PUBLIC TRANSIT | STI (PRIORITIZATION) | 9, 11 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO | TA-6681 | REGION D, F | FEDT, L, T | [6 empty] | 2020 | 466000 | 466000
FRANKLIN | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. | AVIATION | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | AV-5819 | DIVISION 5 | T | 2026 | 3100000 |  |  | 2028 | 22700000 |  |  | 25800000
FRANKLIN | SR 1600 (EAST RIVER ROAD) | NCDOT | REPLACE BRIDGE 340076 OVER SYCAMORE CREEK. | HIGHWAY | BRIDGES | 5 | KERR-TAR RPO | B-5210 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION - BRIDGE PURCHASE ORDER CONTRACT (BPOC)
FRANKLIN | SR 1609 (BAPTIST CHURCH ROAD) | NCDOT | REPLACE BRIDGE 340078 OVER TAR RIVER | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-6003 | DIVISION 5 | BGOFF | 2030 | 440000 |  |  | 2031 | 4400000 |  |  | 4840000
FRANKLIN | FRANKLIN COUNTY RAILS TO TRAILS | FRANKLINTON | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0053 | EXEMPT | CMAQ, L | 2023 | 120000 |  |  | 2023 | 3000000 | 2023 | 600000 | 3720000
FRANKLIN | US-401 | NCDOT | REPLACE BRIDGE 340056 OVER SANDY CREEK. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | HB-0024 | DIVISION 5 | BGOFF | 2027 | 100000 | 2027 | 100000 | 2028 | 2846000 |  |  | 3046000
FRANKLIN | (BUNN ROAD) SR 1230 | LOUISBURG | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | KERR-TAR RPO | HL-0044 | EXEMPT | CMAQ, L | 2023 | 36000 |  |  | 2023 | 468000 | 2022 | 102000 | 606000
FRANKLIN | US 401 | NCDOT | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO, KERR-TAR RPO | R-2814D | DIVISION 5 | BGLT5 | 2028 | 3049000 | 2028 | 3200000 | 2031 | 48701000 |  |  | 54950000
FRANKLIN | US 401 | NCDOT | SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG TO NC 39 IN LOUISBURG | HIGHWAY | PRE-STI (HISTORIC) | 5 | KERR-TAR RPO | R-2814E | [11 empty] | COMPLETE
FRANKLIN | US 401 / NC 39 | NCDOT | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | R-3608 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15299000 |  |  | 21099000 | COORDINATE WITH U-6024
FRANKLIN | NC 56 | NCDOT | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | R-5893 | NOT FUNDED | T | NOT FUNDED | 5900000 | NOT FUNDED | 9000000 | NOT FUNDED | 21899000 |  |  | 36799000
FRANKLIN | US 401 / NC 39 (BICKETT BOULEVARD) | NCDOT | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | U-6024 | DIVISION 5 | T | 2028 | 3200000 | 2028 | 1800000 | 2031 | 15998000 |  |  | 20998000 | COORDINATE WITH R-3608
FRANKLIN | CSX S-LINE | NCDOT | HOLDING AVENUE GRADE SEPERATION, ELM AVENUE IMPROVEMNTS AND BRICK STREET PEDESTRIAN CROSSING. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753BD | STATEWIDE MOBILITY
FRANKLIN | CSX S-LINE | NCDOT | MAIN STREET AND NC 96 BYPASS GRADE SEPERATION AND YOUNGSVILLE ROADWAY IMPROVEMENTS. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753BE | STATEWIDE MOBILITY
FRANKLIN, GRANVILLE, VANCE, WARREN | KERR AREA TRANSPORTATION | KERR AREA TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | KERR-TAR RPO | TK-6139 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 2048000 | 2048000 | FUNDS AUTHORIZED IN PROGRESS
FRANKLIN, GRANVILLE, VANCE, WARREN | KERR AREA TRANSPORTATION | KERR AREA TRANSPORTATION | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 5 | KERR-TAR RPO | TO-6103 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
FRANKLIN, VANCE, WAKE, WARREN | CSX S-LINE | NCDOT | CSX S-LINE FROM RALEIGH TO VIRGINIA STATE LINE AND CSX SA-LINE FROM RALEIGH TO WELDON. AQUIRE RIGHT OF WAY, UPGRADE EXISTING TRACK AND CONSTRUCT NEW TRACK. | RAIL | OTHER | 5 | CAPITAL AREA MPO, KERR-TAR RPO | P-5753 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
FRANKLIN, WAKE | US 401 | NCDOT | NORTH OF SR 2044 (LIGON MILL ROAD) TO NC 39 IN LOUISBURG. WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY, SOME NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO, KERR-TAR RPO | R-2814 | [11 empty] | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
FRANKLIN, WAKE | US 401 | NCDOT | NC 96 TO SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-2814C | DIVISION 5 | BGLT5 |  |  |  |  | 2018 | 36803000 |  |  | 36803000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING $33 MILLION FOR CONSTRUCTION - PAYBACK FY 2018 - FY 2032
GASTON | (TRYON COURTHOUSE ROAD) NC 274 | GASTON COUNTY | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | BIKE/PED | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | BL-0033 | EXEMPT | CMAQ, L | 2024 | 50000 |  |  | 2025 | 1449000 | 2023 | 188000 | 1687000
GASTON | BESSEMER CITY | BESSEMER CITY | PHASE I: 12TH STREET, CHADWICK COURT TO KAISER ROAD. PHASE II: YELLOW JACKET LANE/BESS TOWN ROAD, 12TH STREET TO 14TH STREET (NC 274). CONSTRUCT SIDEWALKS. | BIKE/PED | TRANSITION | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5531 | PRE-STI (TRANSITION) | BGANY |  |  |  |  | 2022 | 300000 |  |  | 300000
GASTON | GASTONIA | GASTONIA | POSTON PARK TO SOUTH FORK RIVER GREENWAY. CONSTRUCT TRAIL. | BIKE/PED | TRANSITION | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5533 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GASTON | US 29/74 (EAST FRANKLIN BOULEVARD) | GASTONIA | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5701 | DIVISION 12 | L, TA5200 | 2023 | 220000 | 2023 | 75000 | 2024 | 1533000 |  |  | 1828000
GASTON | NC 279 (SOUTH NEW HOPE ROAD) | GASTONIA | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5743 | DIVISION 12 | L, TA5200 |  |  |  |  | 2025 | 1285000 | 2023 | 321000 | 1606000
GASTON | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | NCDOT | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5745 | DIVISION 12 | L, TA5200 | 2024 | 135000 |  |  | 2025 | 1230000 | 2023 | 308000 | 1673000
GASTON | BEATY ROAD | GASTONIA | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5748 | DIVISION 12 | L, TA5200 |  |  |  |  | 2027 | 405000 | 2022 | 101000 | 506000
GASTON | SOUTH MARIETTA STREET/ HILLTOP DRIVE | GASTONIA | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5768 | DIVISION 12 | L, TA5200 | 2024 | 60000 |  |  | 2024 | 1260000 | 2023 | 350000 | 1670000
GASTON | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5912 | DIVISION 12 | L, TAANY | 2025 | 727000 |  |  | 2027 | 1745000 | 2023 | 436000 | 2908000
GASTON | CRAMERTON | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5913 | DIVISION 12 | L, TAANY |  |  |  |  | 2025 | 354000 | 2023 | 164000 | 518000
GASTON | NC 279 (NEW HOPE ROAD) | GASTONIA | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5975 | DIVISION 12 | L, TA5200 |  |  |  |  | 2025 | 2065000 | 2023 | 516000 | 2581000
GASTON | SR 2200 (COX ROAD) | GASTONIA | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | BIKE/PED | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5976 | DIVISION 12 | L, TA5200 |  |  |  |  | 2025 | 1400000 | 2023 | 350000 | 1750000
GASTON | SR 1421 (MARYS GROVE ROAD) | NCDOT | REPLACE BRIDGE 350097 OVER UN-NAMED TRIBUTARY OF MUDDY FORK CREEK. | HIGHWAY | BRIDGES | 12 | GASTON-CLEVELAND-LINCOLN MPO | B-5961 | DIVISION 12 | BGOFF | 2021 | 67000 |  |  | 2022 | 705000 |  |  | 772000 | UNDER CONSTRUCTION.
GASTON | US 29 / US 74 | NCDOT | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | HIGHWAY | BRIDGES | 12 | GASTON-CLEVELAND-LINCOLN MPO | B-6051 | REGION F | BFP, HIB | 2023 | 4000000 |  |  | 2024 | 40899000 |  |  | 44899000 | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143.
GASTON | NC 279 (NEW HOPE ROAD) | NCDOT | NC 279 (NEW HOPE ROAD), BURTONWOOD DRIVE TO SR 2466 (GARRISON BOULEVARD) IN GASTONIA. ADD TURN LANE. | HIGHWAY | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-4934 | EXEMPT | [10 empty] | UNDER CONSTRUCTION
GASTON | BELMONT | BELMONT | RAIL TRAIL, WOODLAWN AVENUE TO BELMONT ABBEY COLLEGE AND DOWNTOWN. CONVERT ABANDONED NCDOT RAILROAD LINE TO A PEDESTRIAN TRAIL. | HIGHWAY | TRANSITION | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5505 | EXEMPT | [10 empty] | IN PROGRESS
GASTON | NC 161 | BESSEMER CITY | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606B | EXEMPT | CMAQ, L | 2023 | 5000 |  |  | 2024 | 529000 | 2018 | 126000 | 660000 | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847.
GASTON | US 321 BUSINESS, NC 275/279 | DALLAS | CONSTRUCT SIDEWALKS ALONG PORTIONS OF US 321 BUSINESS AND NC 275/279 NEAR GASTON COLLEGE, INCLUDING A CROSSWALK ACROSS NC 275/279. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606D | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 393000 |  |  | 393000 | UNDER CONSTRUCTION.
GASTON | NEW ROUTE | GASTON COUNTY | TECHNOLOGY PARK TO GASTON COLLEGE. CONSTRUCT GREENWAY. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606E | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 588000 |  |  | 588000 | UNDER CONSTRUCTION.
GASTON | NEW ROUTE | GASTON COUNTY | CONSTRUCT POSTON PARK SIDEWALK CONNECTOR. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606J | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 186000 |  |  | 186000
GASTON | NEW ROUTE | GASTON COUNTY | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606K | EXEMPT | CMAQ, L | 2023 | 15000 |  |  | 2024 | 1581000 | 2023 | 129000 | 1725000
GASTON | NEAL HAWKINS ROAD | GASTON COUNTY | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606M | EXEMPT | CMAQ, L | 2024 | 19000 |  |  | 2025 | 1364000 | 2023 | 477000 | 1860000
GASTON | GASTON COUNTY | GASTON COUNTY | HIGHLAND BRANCH GREENWAY, PHASE I. CONSTRUCT GREENWAY | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5622 | EXEMPT | L |  |  |  |  | 2022 | 53000 |  |  | 53000 | UNDER CONSTRUCTION
GASTON | GASTONIA | NCDOT | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | HIGHWAY | OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5703 | REGION F | CMAQ, L, S(M) | 2022 | 750000 |  |  | 2022 | 11363000 |  |  | 12113000 | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1).
GASTON | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CRAMERTON | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5704 | EXEMPT | CMAQ, L | 2024 | 51000 |  |  | 2024 | 653000 | 2022 | 98000 | 802000
GASTON | I-85 | NCDOT | CONSTRUCT NEW I-85 NBL WEIGH STATION FROM SR 1302 (CROWDERS MOUNTAIN ROAD) TO SR 1307 (EDGEWOOD ROAD). | HIGHWAY | TRANSITION | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-4928 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GASTON | I-85 | NCDOT | I-85/US 321. GEOMETRIC SAFETY IMPROVEMENTS TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5000 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GASTON | I-85 | NCDOT | US 321 TO NC 273. WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5719 | STATEWIDE MOBILITY | DP, NHP, S(M), T | 2024 | 127621000 | 2024 | 71001000 | 2024 | 489575000 |  |  | 688197000 | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT.
GASTON | I-85 | NCDOT | CLEVELAND COUNTY LINE TO MILE MARKER 14. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5921 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 16830000 |  |  | 16830000
GASTON | I-85 | NCDOT | US 74 TO US 321 | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985B | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 219400000 |  |  | 233100000
GASTON | NC 150 | NCDOT | NC 279 AT CHERRYVILLE TO THE LINCOLN COUNTY LINE. | HIGHWAY | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617A | [11 empty] | COMPLETE
GASTON | NC 279 | NCDOT | NC 7 TO WEST OF NC 275 IN DALLAS. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523 | REGION F
GASTON | NC 279 | NCDOT | NC 7 (OZARK AVENUE) TO NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD). | HIGHWAY | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523A | [11 empty] | COMPLETE
GASTON | NC 279 | NCDOT | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523B | REGION F | BG50200 | 2026 | 12500000 | 2026 | 2300000 | 2028 | 20200000 |  |  | 35000000 | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778).
GASTON | NC 273 (SOUTH MAINSTREET) | NCDOT | TUCKASEEGEE ROAD (AT BEATTY DRIVE) TO HIGHLAND STREET (AT A & E DRIVE) IN MOUNT HOLLY. WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-3633 | REGION F | T |  |  |  |  | 2021 | 6315000 |  |  | 6315000 | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746
GASTON | NC 7 | NCDOT | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5800 | REGION F | BGANY | 2024 | 2400000 | 2024 | 3600000 | 2024 | 4400000 |  |  | 10400000 | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719.
GASTON | NC 27 (WEST CHARLOTTE AVENUE) | NCDOT | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5819 | DIVISION 12 | T | 2028 | 700000 | 2028 | 600000 | 2030 | 2800000 |  |  | 4100000
GASTON | NC 279 (NEW HOPE ROAD) | NCDOT | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5821 | DIVISION 12 | T | 2023 | 55250000 | 2023 | 6010000 | 2026 | 51700000 |  |  | 112960000 | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS.
GASTON | US 74 (WILKINSON BOULEVARD) | NCDOT | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5959 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5999000 |  |  | 16699000
GASTON | NC 274 (UNION ROAD) | NCDOT | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5961 | REGION F | BG50200, O | 2024 | 13400000 | 2024 | 3700000 | 2027 | 11400000 |  |  | 28500000 | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA
GASTON | US 29 (FRANKLIN BOULEVARD) | NCDOT | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5965 | REGION F | T | 2023 | 6900000 | 2023 | 300000 | 2025 | 3600000 |  |  | 10800000 | RIGHT-OF-WAY IN PROGRESS.
GASTON | US 321 (SOUTH YORK ROAD) | NCDOT | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5970 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1900000 |  |  | 4500000
GASTON | US 74 (WILKINSON BOULEVARD) | NCDOT | NC 7 (CATAWBA STREET) TO SR 2209 (WESLEYAN DRIVE). IMPLEMENT ADAPTIVE SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6038 | DIVISION 12 | T |  |  |  |  | 2019 | 600000 |  |  | 600000 | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE)
GASTON | US 29/US 74 (FRANKLIN BOULEVARD) | NCDOT | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6043 | DIVISION 12 | T | 2023 | 1300000 | 2023 | 900000 | 2025 | 2700000 |  |  | 4900000 | RIGHT-OF-WAY IN PROGRESS.
GASTON | SR 2200 (COX ROAD) | NCDOT | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6044 | DIVISION 12 | BG50200 | 2025 | 21100000 | 2025 | 1200000 | 2028 | 5400000 |  |  | 27700000
GASTON | NC 275 | NCDOT | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6078 | DIVISION 12 | T | 2025 | 3000000 | 2025 | 400000 | 2027 | 5500000 |  |  | 8900000
GASTON | NC 279 (NORTH NEW HOPE ROAD) | NCDOT | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6138 | REGION F | BG50200 | 2025 | 5600000 | 2025 | 300000 | 2026 | 800000 |  |  | 6700000
GASTON | US 29/74 (FRANKLIN BOULEVARD) | NCDOT | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6141 | NOT FUNDED | NHP | NOT FUNDED | 12200000 | NOT FUNDED | 900000 | NOT FUNDED | 8800000 |  |  | 21900000
GASTON | NC 7 (EAST CATAWBA STREET) | NCDOT | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6143 | REGION F | L, NHP | 2023 | 1600000 | 2023 | 1100000 | 2024 | 4400000 |  |  | 7100000 | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS.
GASTON | US 29/74 (WILKINSON BOULEVARD) | NCDOT | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6146 | REGION F | HFB, T | 2022 | 8380000 | 2021 | 5500000 | 2024 | 34600000 |  |  | 48480000 | RIGHT-OF-WAY IN PROGRESS. BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
GASTON | NC 273 | NCDOT | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6150 | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 1500000 | NOT FUNDED | 1700000 |  |  | 3500000
GASTON | NC 279 (DALLAS CHERRYVILLE HIGHWAY) | NCDOT | SOUTH OF (ST MARK'S CHURCH ROAD) TO NORTH OF NC 275 - CONSTRUCT SAFETY IMPROVEMENTS, INCLUDING PASSING ZONES | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO | W-5212N | REGION F | T |  |  |  |  | 2021 | 12750000 |  |  | 12750000 | COMPELTE; BUILD NC BOND FUNDING: $9.912 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
GASTON | NC 274 | NCDOT | SR 1443 (DAMERON ROAD) TO SR 1405 (RAMSEUR ROAD) REALIGNMENT AND WIDENING. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO | W-5601R | REGION F | HSIP |  |  |  |  | 2025 | 2500000 |  |  | 2500000
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6183A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 767000 | 767000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | PREVENTATIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6184B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 1160000 | 1160000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTON TRANSIT | GASTON TRANSIT | TRANSIT ENHANCEMENTS - PEDESTRIAN WALKWAYS | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6792 | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2022 | 2236000 |  |  | 2236000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | TRANSIT APP | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6804 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 63000 | 63000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTON COUNTY ACCESS | GASTON COUNTY ACCESS | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | GASTON-CLEVELAND-LINCOLN MPO | TK-6128 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 936000 | 936000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | GASTONIA TRANSIT PAYMENT KIOSK. | PUBLIC TRANSIT |  | 12 | GASTON-CLEVELAND-LINCOLN MPO | TM-0045 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 219000 | 219000
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO | TO-5142 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 1068000 | 1068000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | OPERATING EXPENSES | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO | TO-6061 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 2480000 | 2480000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | P & N CORRIDOR REACTIVATION | NCDOT | CROSSING SIGNAL CONSTRUCTION. | RAIL | OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO | P-5200A | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVATION | NCDOT | CROSSING SIGN/PAVEMENT MARKING INSTALLATION. | RAIL | OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO | P-5200B | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVATION | NCDOT | RAIL TRACK CONSTRUCTION ENGINEERING OVERSIGHT. | RAIL | OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO | P-5200C | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVIATION | NCDOT | BELMONT SPUR. | RAIL | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | P-5200D | PRE-STI (TRANSITION) | BGANY | 2023 | 50000 |  |  | 2023 | 850000 |  |  | 900000
GASTON, CLEVELAND | I-85 | NCDOT | IMPLEMENT FLOOD RISK, VULNERABILITY ASSESSMENT, AND FLOOD WARNING SYSTEM ALONG THE I-85 CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5719A | STATEWIDE MOBILITY | DP, T | [6 empty] | 2024 | 200000 | 200000 | DP REPRESENTS 2022 INFRA GRANT.
GASTON, CLEVELAND | I-85 | NCDOT | INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5719B | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2025 | 700000 |  |  | 700000 | DP REPRESENTS 2022 INFRA GRANT.
GASTON, CLEVELAND | I-85 | NCDOT | SOUTH CAROLINA STATE LINE TO NC 273. INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT, INCIDENT MANAGEMENT, STATEWIDE RESILIENCE, BROADBAND (SOUTH CAROLINA STATE LINE TO US 74), CONNECTED VEHICLE TECHNOLOGY, AND TRAVELER INFORMATION. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5719C | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2025 | 21170000 |  |  | 21170000 | DP REPRESENTS 2022 INFRA GRANT.
GASTON, CLEVELAND | I-85 | NCDOT | SOUTH CAROLINA STATE LINE TO US 321. ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985
GASTON, CLEVELAND, LINCOLN | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GASTON-CLEVELAND-LINCOLN MPO. | HIGHWAY | OTHER | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606 | EXEMPT | [10 empty] | STATE FUNDS ON SEGMENT I ARE CONTIGENCY FUNDS
GASTON, CLEVELAND, LINCOLN | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GASTON CLEVELAND LINCOLN PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | HL-0096 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 2410000 |  |  | 2410000
GASTON, IREDELL, CATAWBA | VARIOUS | NCDOT | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE REGIONAL CATEGORY. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | W-5212REG | REGION F
GASTON, LINCOLN | LINCOLN COUNTY | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 12 | GASTON-CLEVELAND-LINCOLN MPO | TA-5185 | DIVISION 12 | 5310, L, T
GASTON, MECKLENBURG | PIEDMONT AND NORTHERN RAILROAD | NCDOT | RAIL CORRIDOR BETWEEN GASTONIA AND MOUNT HOLLY INCLUDING THE BELMONT SPUR. REACTIVATION OF RAIL CORRIDOR | RAIL | OTHER | 10, 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO | P-5200
GATES | US 158 | NCDOT | SR 1002 (ACORN HILL ROAD) TO PASQUOTANK COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5808 | DIVISION 1 | NHP | 2022 | 93000 |  |  | 2023 | 19700000 |  |  | 19793000 | UNDER CONSTRUCTION.
GATES | GATES COUNTY | GATES COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1 | ALBEMARLE RPO | TK-6129 | PUBLIC TRANSIT | 5311 | [6 empty] | 2020 | 544000 | 544000 | FUNDS AUTHORIZED IN PROGRESS
GATES, CHOWAN | NC 32 | NCDOT | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5938 | DIVISION 1 | T | 2028 | 29184000 | 2028 | 26976000 | 2031 | 75901000 |  |  | 132061000
GRAHAM | US 129, NC 143 | NCDOT | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009CA | EXEMPT | ADHS | 2021 | 1900000 | 2021 | 2030000 | 2022 | 54624000 |  |  | 58554000 | UNDER CONSTRUCTION.
GRAHAM | NC 143 | NCDOT | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009CB | EXEMPT | ADHS | 2021 | 3300000 | 2021 | 1300000 | 2022 | 133871000 |  |  | 138471000 | UNDER CONSTRUCTION.
GRAHAM | NC 143, NC 28 | NCDOT | NC 143 FROM NORTH OF APPALACHIAN TRAIL TO NC 28; NC 28 FROM NC 143 TO WEST OF SR 1228 (STECOAH ROAD). UPGRADE ROADWAY. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009CC | EXEMPT | ADHS | 2021 | 2300000 | 2021 | 550000 | 2023 | 77500000 |  |  | 80350000 | UNDER CONSTRUCTION.
GRAHAM | NC 28 | NCDOT | WEST OF SR 1228 (STECOAH ROAD) TO EAST OF SR 1235 (GUNTERS GAP ROAD). UPGRADE ROADWAY. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009CD | NOT FUNDED | ADHS |  |  |  |  | NOT FUNDED | 35100000 |  |  | 35100000
GRAHAM | NC 28 | NCDOT | WEST OF SR 1231 (TOBACCO BRANCH ROAD) TO CALFPEN GAP | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009DC | [11 empty] | COMPLETE
GRAHAM | NC 28 | NCDOT | NC 28 AT STECOAH TO WEST OF SR 1231 (TOBACCO BRANCH ROAD) | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009DD | [11 empty] | COMPLETE
GRAHAM | NC 143 | NCDOT | LONG HUNGRY ROAD INTERSECTION. IMPROVE ALIGNMENT AND SUPERELEVATION. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO | HS-2014G | REGION G | HSIP | 2024 | 2000 |  |  | 2024 | 515000 |  |  | 517000
GRAHAM | NC 143 | NCDOT | NC 143, WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-2822
GRAHAM | NC 143 | NCDOT | NC 143 BUSINESS, SOUTH OF SR 1115 TO NORTH OF SR 1125 | HIGHWAY | PRE-STI (HISTORIC) | 14 | SOUTHWESTERN RPO | R-2822A | [11 empty] | COMPLETE
GRAHAM | NC 143 | NCDOT | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-2822B | REGION G | T | 2023 | 1101000 | 2023 | 700000 | 2025 | 29201000 |  |  | 31002000 | RIGHT-OF-WAY IN PROGRESS.
GRAHAM | NC 28 | NCDOT | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5839BA | DIVISION 14 | T | 2027 | 100000 | 2027 | 200000 | 2029 | 13001000 |  |  | 13301000
GRAHAM | NC 28 | NCDOT | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5839BB | NOT FUNDED | T | NOT FUNDED | 46332000 | NOT FUNDED | 80000 | NOT FUNDED | 37000000 |  |  | 83412000
GRAHAM | NC 28 | NCDOT | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5839C | NOT FUNDED | T | NOT FUNDED | 90000 | NOT FUNDED | 20000 | NOT FUNDED | 58300000 |  |  | 58410000
GRAHAM | NC 28 | NCDOT | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5839D | NOT FUNDED | T | NOT FUNDED | 730000 | NOT FUNDED | 80000 | NOT FUNDED | 57500000 |  |  | 58310000
GRAHAM | NC 28 | NCDOT | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5839E | NOT FUNDED | T | NOT FUNDED | 60000 | NOT FUNDED | 100000 | NOT FUNDED | 22000000 |  |  | 22160000
GRAHAM | NEW ROUTE | NCDOT | US 129 (RODNEY ORR BYPASS) TO ROBINSVILLE HIGH SCHOOL AND MIDDLE SCHOOL. CONSTRUCT NEW ROUTE INCLUDING BRIDGE OVER CHEOAH RIVER. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | U-5866 | DIVISION 14 | [10 empty] | UNDER CONSTRUCTION
GRAHAM, CHEROKEE | FUTURE US 74 | NCDOT | US 19 BUSINESS IN ANDREWS TO US 129 | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009A | NOT FUNDED | NHP | NOT FUNDED | 14300000 | NOT FUNDED | 925000 | NOT FUNDED | 366000000 |  |  | 381225000
GRAHAM, SWAIN | SR 1286/ SR 1383 (TSALI ROAD) | NCDOT | NC 28 TO END OF MAINTENANCE. RESURFACE AND REPAIR CORRIDOR. | HIGHWAY | FEDERAL LANDS ACCESS PROGRAM | 14 | SOUTHWESTERN RPO | HF-0007 | EXEMPT | FLAP |  |  |  |  | 2025 | 1050000 | 2023 | 150000 | 1200000 | FLAP PROJECT NC 65. AWARDED $1.2M.
GRAHAM, SWAIN | NC 28 (FONTANA ROAD) | NCDOT | US 129 TO NC 143. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5839
GRAHAM, SWAIN, CHEROKEE | US 19, US 74, US 129, NC 28, NC 143 | NCDOT | CORRIDOR "K", ANDREWS TO NC 28 EAST OF ALMOND. UPGRADE ROADWAY TO INCLUDE EXISTING FACILITIES AND NEW LOCATION. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009
GRANVILLE | NC 56 | CREEDMOOR | GREENWAY IN CREEDMOOR. CONSTRUCT BIKE-PEDESTRIAN TRAIL SYSTEM. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | C-5166 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY TOWN OF CREEDMOOR; LET WITH EB-5513
GRANVILLE | NC 56 | CREEDMOOR | GREENWAY IN CREEDMOOR - EASTERN SECTION | BIKE/PED | TRANSITION | 5 | CAPITAL AREA MPO | C-5166A | EXEMPT | [10 empty] | UNDER CONSTRUCTION
GRANVILLE | NC 56 | CREEDMOOR | GREENWAY IN CREEDMOOR - WESTERN SECTION | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | C-5166B | EXEMPT | [10 empty] | UNDER CONSTRUCTION
GRANVILLE | US 15 | CREEDMOOR | SR 1110 IWEST HILLSBORO STREET) TO NC 56 IN CREEDMOOR. CONSTRUCT SIDEWALK / PATH. | BIKE/PED | TRANSITION | 5 | CAPITAL AREA MPO | EB-5513 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF CREEDMOOR; LET WITH C-5166A AND C-5166B
GRANVILLE | SR 1139 (ENON ROAD) | NCDOT | REPLACE BRIDGE 380096 OVER TAR RIVER. | HIGHWAY | BRIDGES | 5 | KERR-TAR RPO | B-5320 | DIVISION 5 | [10 empty] | PROJECT COMPLETE
GRANVILLE | SR 1442 (DAVE WINSTON ROAD) | NCDOT | REPLACE BRIDGE 380143 OVER JOHNSON CREEK. | HIGHWAY | BRIDGES | 5 | KERR-TAR RPO | B-5323 | DIVISION 5 | BFPOFF |  |  |  |  | 2023 | 3700000 |  |  | 3700000 | UNDER CONSTRUCTION
GRANVILLE | US 15 | CREEDMOOR | INTERSECTION OF US 15 AND SR 1129 (HESTER ROAD) IN CREEDMOOR. IMPROVE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0120 | DIVISION 5 | BGDA, L | 2024 | 180000 |  |  | 2024 | 1716000 | 2024 | 322000 | 2218000
GRANVILLE | SR 1602 (MAIN STREET) | NCDOT | SR 1207 (SPRING STREET) INTERSECTION IN OXFORD. CONSTRUCT MINI-ROUNDABOUT. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO | HS-2005A | DIVISION 5 | HSIP |  |  |  |  | 2021 | 100000 |  |  | 100000 | UNDER CONSTRUCTION
GRANVILLE | NC 56 | NCDOT | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-5707 | REGION C | T |  |  |  |  | 2019 | 4988000 | 2021 | 989000 | 5977000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GRANVILLE | NC 56 (EAST C STREET) | NCDOT | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | U-6020 | DIVISION 5 | L, T |  |  |  |  | 2025 | 6000000 |  |  | 6000000 | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER
GRANVILLE, DURHAM | I-85 / US 15 | NCDOT | NORTH OF SR 1637 (REDWOOD ROAD) IN DURHAM COUNTY TO SOUTH OF US 15 / SR 1100 (GATE ONE ROAD) IN GRANVILLE COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO, KERR-TAR RPO | HI-0001 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 5665000 |  |  | 5665000 | UNDER CONSTRUCTION
GRANVILLE, FRANKLIN, PERSON | VARIOUS | HENDERSON COUNTY | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | HIGHWAY | OTHER | 5 | KERR-TAR RPO | C-5610 | EXEMPT | CMAQ, L | 2020 | 105000 |  |  | 2020 | 618000 | 2020 | 315000 | 1038000 | IN PROGRESS
GREENE | US 264 (FUTURE I-587) | NCDOT | PITT COUNTY LINE TO WILSON COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 2 | EASTERN CAROLINA RPO | I-6032 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 4830000 |  |  | 4830000 | COMPLETED. TO BE LET WITH I-6035. GARVEE BOND FUNDING: $4,020,000 FOR CON, PAYBACK FY 2019-2033.
GREENE | US 13 BYPASS | NCDOT | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-5812 | DIVISION 2 | L, T |  |  |  |  | 2020 | 9165000 | 2020 | 1290000 | 10455000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
GREENE | NC 58 (KINGOLD BOULEVARD) | NCDOT | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-5898 | NOT FUNDED | T | NOT FUNDED | 200000 | NOT FUNDED | 200000 | NOT FUNDED | 7500000 |  |  | 7900000
GREENE | US 13/US 258 | NCDOT | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-5942 | NOT FUNDED | T | NOT FUNDED | 11800000 | NOT FUNDED | 2300000 | NOT FUNDED | 62202000 |  |  | 76302000
GREENE | US 13 | NCDOT | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-5943 | DIVISION 2 | BGLT5 | 2025 | 2000000 | 2025 | 300000 | 2028 | 1200000 |  |  | 3500000
GREENE | GREENE COUNTY | GREENE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 2 | EASTERN CAROLINA RPO | TK-6131 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 460000 | 460000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L EXTENSION PROGRAM | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5701 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 21000000 |  |  | 21000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY G. | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5707 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 16900000 |  |  | 16900000 | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY OVER FUTURE I-73 EAST OF SR 2085 (BRYAN BOULEVARD). | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5708 | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 1500000 |  |  | 1500000 | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5711 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2026 | 9000000 |  |  | 9000000 | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5715 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 11000000 |  |  | 11000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | HIGH SPEED TAXIWAY TO RUNWAY 5R-23L. | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5718 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 4000000 |  |  | 4000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY J EXTENSION, TAXIWAY D TO TAXIWAY J2. | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5800 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 7000000 |  |  | 7000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT NORTHWEST APRON TO INCREASE CAPACITY FOR FUTURE EXPANSION. | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5802 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 11000000 |  |  | 11000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. | AVIATION | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | AV-5803 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 28000000 |  |  | 28000000
GUILFORD | LATHAM PARK GREENWAY LAKE DANIEL GREENWAY; | GREENSBORO | LAKE DANIEL GREENWAY, FRIENDLY AVENUE TO JOSEPHINE BOYD STREET, AND LATHAM PARK GREENWAY AT TENNIS COURTS NEAR WENDOVER AVENUE IN GREENSBORO. REPAIR SURFACES. | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | BL-0041 | DIVISION 7 | BGDACV |  |  |  |  | 2023 | 500000 |  |  | 500000
GUILFORD | VANCE ARLINGTON GREENWAY | GREENSBORO | NORTH OF FLORIDA STREET TO BRAGG STREET IN GREENSBORO. CONSTRUCT GREENWAY AND SIDEPATH. | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | BL-0042 | DIVISION 7 | BGDACV |  |  |  |  | 2023 | 1200000 |  |  | 1200000
GUILFORD | HIGH POINT | HIGH POINT | SUNSET DRIVE FROM HARVELL PARK AND GOLDSTON PARK. CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 7 | HIGH POINT URBAN AREA MPO | BL-0071 | EXEMPT | DP | 2023 | 2000000 |  |  |  |  | 2023 | 5000000 | 7000000 | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "S" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING.
GUILFORD | SOUTHWEST HERITAGE GREENWAY | HIGH POINT | CONSTRUCT GREENWAY ON NEW LOCATION CONNECTING HARVELL PARK AND GOLDSTON PARK. | BIKE/PED | LOCALLY SELECTED | 7 | HIGH POINT URBAN AREA MPO | BL-0071A | EXEMPT | DP, L, S |  |  |  |  | 2024 | 7826000 |  |  | 7826000
GUILFORD | ELM STREET | HIGH POINT | CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS FROM SUNSET DRIVE TO COMMERCE AVENUE. | BIKE/PED | LOCALLY SELECTED | 7 | HIGH POINT URBAN AREA MPO | BL-0071B | EXEMPT | DP, L, O |  |  |  |  | 2024 | 13864000 |  |  | 13864000
GUILFORD | NEW PEDESTRIAN BRIDGE AND APPROACHES | HIGH POINT | EXISTING SIDEWALK TO PIEDMONT ENVIRONMENTAL CENTER ENTRANCE IN HIGH POINT AND JAMESTOWN. CONSTRUCT PEDESTRIAN BRIDGE OVER EAST FORK OF DEEP RIVER. | BIKE/PED | TRANSITION | 7 | HIGH POINT URBAN AREA MPO | EB-5517 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN
GUILFORD | LATHAM PARK GREENWAY | GREENSBORO | BATTLEGROUND AVENUE TO MENDENHALL STREET IN GREENSBORO. REMOVE THROUGH LANE ON HILL STREET AND CONSTRUCT MULTI-USE PATH. | BIKE/PED | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | EB-5518 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | SR 4121 (EAST MAIN STREET) | JAMESTOWN | EXISTING SIDEWALK NEAR JAMESTOWN MUNICIPAL BUILDING TO YORKLEIGH LANE NEAR GUILFORD TECHNICAL COMMUNITY COLLEGE JAMESTOWN CAMPUS/RAGSDALE HIGH SCHOOL COMPLEX IN JAMESTOWN. CONSTRUCT SIDEWALK. | BIKE/PED | TRANSITION | 7 | HIGH POINT URBAN AREA MPO | EB-5519 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN
GUILFORD | HOLDEN ROAD; EAST LINDSAY STREET | GREENSBORO | HOLDEN ROAD, SOUTH OF MEADOWVIEW ROAD TO SPRING GARDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK ON WEST SIDE. EAST LINDSAY STREET, MURROW BOULEVARD TO BESSEMER AVENUE IN GREENSBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5716 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 1278 (SOUTH COLLEGE DRIVE) | HIGH POINT | SR 1300 (EAST GREEN DRIVE) TO SR 1113 (EAST KIVETT DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-5873 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 360000 |  |  | 360000
GUILFORD | NC 68 (EASTCHESTER DRIVE) | HIGH POINT | JOHNSON STREET TO SR 1278 (NORTH COLLEGE DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-5874 | DIVISION 7 | L, TA50200 |  |  |  |  | 2023 | 630000 |  |  | 630000
GUILFORD | HOLDEN ROAD | GREENSBORO | SR 4121 (WEST GATE CITY BOULEVARD) TO NORTH OF SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5876 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | FARMINGTON DRIVE | GREENSBORO | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWLAKS. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5877 | DIVISION 7 | L, TAANY | 2022 | 25000 |  |  | 2023 | 300000 |  |  | 325000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | WEST MEADOWVIEW ROAD | GREENSBORO | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5878 | DIVISION 7 | L, TAANY | 2022 | 175000 |  |  | 2023 | 259000 |  |  | 434000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | US 220 (WENDOVER AVENUE) | GREENSBORO | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5883 | DIVISION 7 | L, TAANY | 2023 | 296000 |  |  | 2024 | 2811000 |  |  | 3107000
GUILFORD | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | JAMESTOWN | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-5889 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 500000 |  |  | 500000
GUILFORD | SUMMERFIELD SOUTH GREENWAY | SUMMERFIELD | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5900 | DIVISION 7 | L, TAANY | 2023 | 390000 |  |  | 2024 | 3900000 |  |  | 4290000
GUILFORD | NC 68 (EASTCHESTER DRIVE) | HIGH POINT | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-5922 | DIVISION 7 | L, TA5200 |  |  |  |  | 2025 | 135000 |  |  | 135000
GUILFORD | CONE BOULEVARD | GREENSBORO | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5985 | DIVISION 7 | L, TAANY | 2023 | 78000 |  |  | 2023 | 471000 | 2022 | 150000 | 699000
GUILFORD | BENJAMIN PARKWAY; WESTOVER TERRACE | GREENSBORO | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5986 | DIVISION 7 | L, TAANY | 2023 | 70000 |  |  | 2024 | 1200000 | 2023 | 50000 | 1320000
GUILFORD | OLD BATTLEGROUND ROAD | GREENSBORO | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5987 | DIVISION 7 | L, TAANY | 2024 | 11000 |  |  | 2025 | 990000 | 2022 | 99000 | 1100000
GUILFORD | CEDROW DRIVE | HIGH POINT | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-5989 | DIVISION 7 | L, TA5200 | 2025 | 50000 |  |  | 2026 | 1200000 | 2024 | 120000 | 1370000
GUILFORD | HIGH POINT RAILROAD ESPLANADE | HIGH POINT | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-5990 | DIVISION 7 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | 8800000
GUILFORD | SPRING GARDEN STREET | GREENSBORO | MERRITT DRIVE TO EXISTING SIDEWALK WEST OF HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5992 | DIVISION 7 | L, TAANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 315000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35000 | 350000
GUILFORD | LAWNDALE DRIVE | GREENSBORO | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5995 | DIVISION 7 | L, TAANY | 2023 | 48000 |  |  | 2025 | 381000 |  |  | 429000
GUILFORD | SR 1001 (NORTH CHURCH STREET) | GREENSBORO | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5996 | DIVISION 7 | L, TAANY | 2024 | 100000 |  |  | 2025 | 830000 |  |  | 930000
GUILFORD | GREEN VALLEY ROAD | GREENSBORO | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-5997 | DIVISION 7 | L, TAANY | 2024 | 45000 |  |  | 2025 | 288000 | 2023 | 70000 | 403000
GUILFORD | JOHNSON STREET | HIGH POINT | PARRIS AVENUE TO SR 1896 (EAST HARTLEY DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-5999 | DIVISION 7 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 145000 |  |  | 145000
GUILFORD | SR 1536 (PENNY ROAD) | HIGH POINT | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-6000 | DIVISION 7 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 150000 | 1650000
GUILFORD | SR 2526 (SUMMIT AVENUE) | GREENSBORO | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | BIKE/PED | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | EB-6009 | DIVISION 7 | L, TAANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3719000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 656000 | 4375000
GUILFORD | US 70 (WEST WENDOVER AVENUE) | HIGH POINT | NC 68 (EASTCHESTER DRIVE) TO GIBSON PARK ENTRANCE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | EB-6010 | DIVISION 7 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 220000 |  |  | 220000 | COORDINATE WITH U-6121
GUILFORD | A&Y GREENWAY | GREENSBORO | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | EB-6037C | DIVISION 7 | BGANY, L, TAANY |  |  |  |  | 2023 | 8936000 |  |  | 8936000
GUILFORD | VARIOUS | GREENSBORO | PEDESTRIAN AND BICYCLE PROJECTS IN THE GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO). | BIKE/PED | OTHER | 7 | GREENSBORO URBAN AREA MPO | EL-5101 | DIVISION 7 | [10 empty] | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS - IN PROGRESS
GUILFORD | MURROW BLVD | GREENSBORO | MURROW BOULEVARD BRIDGE OVER CHURCH STREET. REPAIR BRIDGE DECK AND COMPLETE GREENWAY ACROSS STRUCTURE. | BIKE/PED | OTHER | 7 | GREENSBORO URBAN AREA MPO | EL-5101DR | DIVISION 7 | BGDA, L |  |  |  |  | 2023 | 1800000 |  |  | 1800000 | UNDER CONSTRUCTION
GUILFORD | VARIOUS | GREENSBORO | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-5532 | DIVISION 7 | BGANY, BGDA, L, TAANY, TADA | 2021 | 748000 |  |  | 2021 | 16154000 | 2023 | 100000 | 17002000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | VARIOUS | GREENSBORO | BIG TREE WAY-WENDOVER AVENUE TO ELKHOUND TRAIL; SHELBY DRIVE-BIG TREE WAY TO EDITH LANE; HEWITT STREET-NORWOLK STREET TO MERRITT DRIVE; BRIDFORD PARKWAY AND HORNADAY ROAD-WENDOVER AVENUE TO EXISTING WEST OF NICHOLAS ROAD. | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-5532E | DIVISION 7 | L, TADA |  |  |  |  | 2023 | 2436000 |  |  | 2436000
GUILFORD | VARIOUS | GREENSBORO | HOLDEN ROAD SIDEWALK (1) HOLDEN ROAD FROM WALKER AVENUE TO SPRING GARDEN STREET - BOTH SIDES, 2) HOLDEN ROAD FROM DARDEN ROAD TO VANDALIA ROAD - WEST SIDE, 3) HOLDEN ROAD FROM MADISON AVENUE TO WALKER AVENUE - BOTH SIDES, 4) RANKIN ROAD / MARTIN AVENUE SOUTH SIDE OF RANKIN ROAD FROM SUMMIT AVENUE TO MARTIN AVENUE. | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-5532F | DIVISION 7 | L, TADA |  |  |  |  | 2023 | 1898000 |  |  | 1898000
GUILFORD | VARIOUS | GREENSBORO | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-5532G | DIVISION 7 | L, TADA | 2022 | 70000 | 2022 | 5000 | 2023 | 1150000 |  |  | 1225000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | VARIOUS | GREENSBORO | NORTH SIDE OF SEMINOLE DRIVE FROM JOSEHPINE BOYD STREET; NORTH SIDE OF WHIPPOORWILL DRIVE FROM PENNYDALE DRIVE TO JANE STREET; AND NORTH SIDE OF WEST BESSEMER AVENUE FROM GRECADE STREET TO HILL STREET | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-5532H | DIVISION 7 | L, TADA |  |  |  |  | 2023 | 670000 |  |  | 670000
GUILFORD | VARIOUS | GREENSBORO | HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD. | BIKE/PED | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-5532I | DIVISION 7 | L, TADA | 2023 | 400000 |  |  | 2023 | 1168000 | 2023 | 81000 | 1649000
GUILFORD | SR 2128 (BUNCH ROAD) | NCDOT | REPLACE BRIDGE 400106 OVER REEDY FORK CREEK IN OAK RIDGE. | HIGHWAY | BRIDGES | 7 | GREENSBORO URBAN AREA MPO | B-4958 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 3058 (JUDGE ADAMS ROAD) | NCDOT | REPLACE BRIDGE 400214 OVER LITTLE ALAMANCE CREEK. | HIGHWAY | TRANSITION | 7 | BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO | B-4960 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 / BUSINESS 85 (WESTBOUND) | NCDOT | REPLACE BRIDGE 400291 AND BRIDGE 400349 OVER US 29 / US 70 / US 220 IN GREENSBORO. | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | B-5119 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 2821 (HARVEST ROAD) | NCDOT | REPLACE BRIDGE 400161 OVER SOUTH BUFFALO CREEK. | HIGHWAY | BRIDGES | 7 | GREENSBORO URBAN AREA MPO | B-5344 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | NCDOT | REPLACE BRIDGE 400299 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | HIGHWAY | BRIDGES | 7 | GREENSBORO URBAN AREA MPO | B-5356 | STATEWIDE MOBILITY | BFP |  |  |  |  | 2028 | 11700000 |  |  | 11700000 | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965
GUILFORD | BALLINGER ROAD | GREENSBORO | REPLACE BRIDGE 400098 OVER A TRIBUTARY OF HORSEPEN CREEK IN GREENSBORO. | HIGHWAY | MUNICIPAL BRIDGE | 7 | GREENSBORO URBAN AREA MPO | B-5553 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO; MUNICIPAL BRIDGE PROJECT
GUILFORD | WILLOW ROAD | NCDOT | REPLACE BRIDGE 400352 OVER I-40 / BUSINESS 85 IN GREENSBORO. | HIGHWAY | BRIDGES | 7 | GREENSBORO URBAN AREA MPO | B-5713 | DIVISION 7 | BFP | 2029 | 1000000 |  |  | 2030 | 8000000 |  |  | 9000000 | "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING
GUILFORD | SR 4240 (GATE CITY BOULEVARD) | NCDOT | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | HIGHWAY | BRIDGES | 7 | GREENSBORO URBAN AREA MPO | B-5717 | DIVISION 7 | BFP, S | 2021 | 710000 | 2021 | 165000 | 2022 | 8957000 |  |  | 9832000 | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING
GUILFORD | PATTON AVENUE | NCDOT | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | HIGHWAY | BRIDGES | 7 | GREENSBORO URBAN AREA MPO | B-5718 | DIVISION 7 | BFP | 2027 | 218000 | 2027 | 74000 | 2028 | 3350000 |  |  | 3642000 | COORDINATEWITH I-5965
GUILFORD | SR 1158 (JACKSON LAKE ROAD) | NCDOT | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | HIGHWAY | BRIDGES | 7 | HIGH POINT URBAN AREA MPO | B-5723 | DIVISION 7 | BGOFF | 2030 | 30000 | 2030 | 570000 | 2031 | 2100000 |  |  | 2700000
GUILFORD | VARIOUS | GREENSBORO | SIDEWALK PROJECTS AT SELECTED LOCATIONS IN GREENSBORO. | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | C-5555 | EXEMPT | [10 empty] | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | VARIOUS | GREENSBORO | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | HIGHWAY | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | C-5555E | EXEMPT | BGDA, CMAQ, L |  |  |  |  | 2022 | 1153000 |  |  | 1153000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | VARIOUS | HIGH POINT | CITY OF HIGH POINT SIGNAL SYSTEM EXPANSION AND UPGRADE. | HIGHWAY | OTHER | 7 | HIGH POINT URBAN AREA MPO | C-5558 | EXEMPT | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-85 | NCDOT | GUILDFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS | HIGHWAY | OTHER | 7 | GREENSBORO URBAN AREA MPO | C-5600E | EXEMPT | CMAQ, L, S(M) |  |  |  |  | 2023 | 1891000 |  |  | 1891000
GUILFORD | VARIOUS | GREENSBORO | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | HIGHWAY | OTHER | 7 | GREENSBORO URBAN AREA MPO | C-5607 | EXEMPT | CMAQ, L | 2020 | 360000 |  |  | 2020 | 2154000 | 2020 | 1080000 | 3594000
GUILFORD | VARIOUS | JAMESTOWN | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. | HIGHWAY | OTHER | 7 | HIGH POINT URBAN AREA MPO | C-5609F | EXEMPT | CMAQ, L | 2023 | 40000 |  |  | 2023 | 550000 |  |  | 590000
GUILFORD | VARIOUS | HIGH POINT | SIDEWALK IMPROVEMENTS. | HIGHWAY | OTHER | 7 | HIGH POINT URBAN AREA MPO | C-5609L | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 1860000 |  |  | 1860000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | OAKDALE ROAD | JAMESTOWN | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | HIGHWAY | LOCALLY SELECTED | 7 | HIGH POINT URBAN AREA MPO | C-5700 | EXEMPT | CMAQ, L |  |  |  |  | 2024 | 170000 |  |  | 170000
GUILFORD | VARIOUS | NCDOT | CONSTUCT ROAD IMPROVEMENTS AND WETLANDS MITIGATION AT THE PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. | HIGHWAY | ECONOMIC DEVELOPMENT | 7 | GREENSBORO URBAN AREA MPO | HE-0005 | EXEMPT | S | 2022 | 1000000 | 2022 | 500000 | 2023 | 30000000 |  |  | 31500000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION
GUILFORD | BOULEVARD) SR 4240 (EAST GATE CITY | GREENSBORO | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | HIGHWAY | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | HL-0046 | DIVISION 7 | BGDA, L | 2023 | 150000 |  |  | 2023 | 3560000 |  |  | 3710000
GUILFORD | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | GREENSBORO | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | HIGHWAY | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | HL-0047 | DIVISION 7 | BGDA, L | 2023 | 70000 |  |  | 2024 | 550000 |  |  | 620000
GUILFORD | VARIOUS | GREENSBORO | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | HIGHWAY | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | HL-0048 | DIVISION 7 | BGDA, BGDACV, L | 2023 | 10000 |  |  | 2024 | 1000000 | 2022 | 255000 | 1265000
GUILFORD | HIGH POINT | HIGH POINT | HIGH POINT SIGNAL SYSTEM RETIMING STUDY | HIGHWAY | LOCALLY SELECTED | 7 | HIGH POINT URBAN AREA MPO | HL-0060 | EXEMPT | CMAQ, L | [6 empty] | 2023 | 1523000 | 1523000
GUILFORD | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENSBORO PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | HL-0098 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 4434000 |  |  | 4434000
GUILFORD | I-85 BUSINESS/US29/70 | NCDOT | I-85 BUSINESS/US 29/70 SOUTHBOUND AND NORTHBOUND FROM RANDOLPH COUNTY LINE TO NORTH OF SR 1145 (RIVERDALE DRIVE) IN HIGH POINT. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 7 | GREENSBORO URBAN AREA MPO | HS-2007A | REGION D | HSIP |  |  |  |  | 2021 | 540000 |  |  | 540000 | UNDER CONSTRUCTION
GUILFORD | I-85 BUSINESS/US29/70 | NCDOT | I-85 BUSINESS/US 29/70 NORTHBOUND FROM NORTH OF SR 1145 (RIVERDALE DRIVE) TO I-85 IN HIGH POINT. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 7 | GREENSBORO URBAN AREA MPO | HS-2007B | REGION D | HSIP |  |  |  |  | 2021 | 270000 |  |  | 270000 | UNDER CONSTRUCTION
GUILFORD | I-74 AND US 29/70 | NCDOT | I-74 AND US 29/70 (I-85 BUSINESS INTERCHANGE). UPGRADE SIGNALS, PAVEMENT MARKINGS, AND SIGNING. | HIGHWAY | SAFETY | 7 | HIGH POINT URBAN AREA MPO | HS-2007D | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 400000 |  |  | 400000 | UNDER CONSTRUCTION
GUILFORD | NC 62 | NCDOT | NC 62 FROM WEST OF SR 1138 (TOM BALL ROAD) TO WEST OF THE ALAMANCE COUNTY LINE. INSTALL PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 7 | GREENSBORO URBAN AREA MPO | HS-2007E | DIVISION 7 | HSIP |  |  |  |  | 2023 | 802000 |  |  | 802000 | UNDER CONSTRUCTION
GUILFORD | FUTURE I-73 | NCDOT | NC 68 TO GREENSBORO WESTERN LOOP. SIX-LANE FREEWAY ON NEW LOCATION. | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | I-5110 | PRE-STI (TRANSITION) | [10 empty] | COMBINED WITH R-2413A AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | I-40 / US 421 | NCDOT | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | I-5712 | STATEWIDE MOBILITY | NHP | 2026 | 12700000 | 2026 | 800000 | 2028 | 18600000 |  |  | 32100000
GUILFORD | I-40 | NCDOT | 1.3 MILES EAST OF SR 1850 (SANDY RIDGE ROAD) TO 1.1 MILES EAST OF SR 1556 (GALLIMORE DAIRY ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5734 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - PRIOR YEAR COST IS FOR BRIDGE PRESERVATION; PAVEMENT REHABILITATION COST INCLUDED IN I-5762
GUILFORD | I-74 / US 311 | NCDOT | FORSYTH COUNTY LINE TO SR 1300 (GREEN ROAD) IN HIGH POINT. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | HIGH POINT URBAN AREA MPO | I-5736 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - AMOUNT INCLUDES I-5767 CONSTRUCTION
GUILFORD | I-40 | NCDOT | FORSYTH COUNTY LINE TO 1.3 MILES EAST OF SR 1850 (SANDY RIDGE ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | I-5762 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - INCLUDES CONSTRUCTION COST FOR I-5734
GUILFORD | I-85 | NCDOT | SR 1113 (KIVETT DRIVE) TO 0.4 MILE NORTH OF I-85 BUSINESS IN HIGH POINT. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | HIGH POINT URBAN AREA MPO | I-5789 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDES I-5738 AND I-5821
GUILFORD | I-85 | NCDOT | 0.2 MILE NORTH OF SR 3039 (NELSON FARM ROAD) TO 1.3 MILES NORTH OF SR 3029 (YOUNGS MILL ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5790 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - AMOUNT INCLUDES I-5855 CONSTRUCTION
GUILFORD | I-40 | NCDOT | WEST OF I-73 / US 421 TO HOLDEN ROAD IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5811 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 / BUSINESS 85 I-40 / I-85 I-85 | NCDOT | I-40 / BUSINESS 85, EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) TO I-85; I-85 NORTH OF SR 3000 (MCCONNELL ROAD) TO I-40; I-40 / I-85, WEST OF SR 3048 (MOUNT HOPE CHURCH ROAD) TO EAST OF SR 3056 (ROCK CREEK DAIRY ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5812 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-85 | NCDOT | RANDOLPH COUNTY LINE TO SR 1113 (KIVETT DRIVE). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | HIGH POINT URBAN AREA MPO | I-5821 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789
GUILFORD | I-73 | NCDOT | I-85 TO SR 2085 (BRYAN BOULEVARD) IN GREENSBORO. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5852
GUILFORD | I-73 / US 421 | NCDOT | I-85 TO I-40 | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5852A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / I-840 | NCDOT | I-40 TO SR 2085 (BRYAN BOULEVARD) | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5852B | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-85 / US 29 / US 70 | NCDOT | 1 MILE SOUTH OF SR 1129 (GROOMETOWN ROAD) TO 0.3 MILE NORTH OF SR 1129 (GROOMETOWN ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5853 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-85 | NCDOT | NORTH OF I-73 / US 421 INTERCHANGE TO SR 3300 (SOUTH ELM-EUGENE STREET). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5854 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-85 | NCDOT | SR 3300 (SOUTH ELM-EUGENE STREET) TO 0.2 MILE NORTH OF SR 3039 (NELSON FARM ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5855 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED IN I-5790
GUILFORD | I-785 / I-840 | NCDOT | I-85 TO US 70. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5953 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 | NCDOT | SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5955 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 8900000 |  |  | 8900000 | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356
GUILFORD | I-40 | NCDOT | I-40, SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. REHABILITATE BRIDGES 400678, 400367, 400364, 400357, 400349, 400348, 400340, 400339, 400336, 400329, 400327, 400299, 400291, AND 400285. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | I-5955A | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2024 | 10100000 |  |  | 10100000
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | NCDOT | ELM-EUGENE STREET IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | I-5964 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2023 | 575000 |  |  | 575000 | UNDER CONSTRUCTION
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | NCDOT | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | I-5965 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3732000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 109200000 |  |  | 123932000 | COORDINATE WITH B-5356 AND B-5718
GUILFORD | I-40 | NCDOT | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | I-5980 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3824000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33700000 |  |  | 40924000
GUILFORD | I-40 / I-85 | NCDOT | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | I-6004 | DIVISION 7 | NHP | 2026 | 1400000 | 2026 | 429000 | 2027 | 10900000 |  |  | 12729000
GUILFORD | US 220 | NCDOT | SR 2182 (HORSEPEN CREEK ROAD) TO US 220-NC 68 CONNECTOR (R-2413) IN GREENSBORO AND SUMMERFIELD. WIDEN TO MULTI-LANES. | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | R-2309
GUILFORD | US 220 | NCDOT | COTSWALD TERRACE NORTH OF GREENSBORO TO SR 2182 (HORSEPEN CREEK ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | R-2309AA | [11 empty] | COMPLETE
GUILFORD | US 220 | NCDOT | SR 2182 (HORSEPEN CREEK ROAD) TO NORTH OF SR 2313 (WINFREE ROAD) IN GREENSBORO | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | R-2309AB | [11 empty] | UNDER CONSTRUCTION
GUILFORD | FUTURE I-73 | NCDOT | FOUR LANES AT SR 2011 (EDGEFIELD ROAD) TO SR 2127 (BROOK BANK ROAD) | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | R-2413A | [11 empty] | COMBINED WITH I-5110 AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | FUTURE I-73 | NCDOT | SR 2127 (BROOK BANK ROAD) TO HAW RIVER | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | R-2413B | [11 empty] | COMBINED WITH I-5110 AND R-2413A FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | US 158 | NCDOT | NORTH OF SR 2034 (ANTHONY ROAD) TO US 220. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | R-2577C | NOT FUNDED | T | NOT FUNDED | 74608000 | NOT FUNDED | 625000 | NOT FUNDED | 48400000 |  |  | 123633000
GUILFORD | US 421 | NCDOT | SR 3389 (WOODY MILL ROAD) AND SR 3418 (NEELLEY ROAD) SOUTH OF GREENSBORO. CONVERT AT-GRADE INTERSECTIONS TO INTERCHANGES. | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | R-2612 | EXEMPT
GUILFORD | US 421 | NCDOT | SR 3389 (WOODY MILL ROAD) INTERSECTION SOUTH OF GREENSBORO | HIGHWAY | SAFETY | 7 | GREENSBORO URBAN AREA MPO | R-2612A | [11 empty] | COMPLETE
GUILFORD | US 421 | NCDOT | SR 3418 (NEELLEY ROAD) INTERSECTION SOUTH OF GREENSBORO | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | R-2612B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 29; SR 4771 (REEDY FORK PARKWAY) | NCDOT | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | R-4707 | REGION D | T | 2019 | 5824000 |  |  | 2021 | 62660000 | 2019 | 4019000 | 72503000 | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $25 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE)
GUILFORD | NC 68; NC 150 | NCDOT | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | R-5725 | REGION D | T | 2022 | 1287000 | 2022 | 500000 | 2023 | 7300000 |  |  | 9087000 | COORDINATE WITH U-6127. RIGHT OF WAY IN PROGRESS
GUILFORD | US 29 (FUTURE I-785) | NCDOT | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | R-5889A | REGION D | T | 2028 | 17066000 | 2028 | 1876000 | 2031 | 69700000 |  |  | 88642000
GUILFORD | SR 1486 (GREENSBORO ROAD) / SR 4121 (HIGH POINT RO | NCDOT | PROPOSED US 311 BYPASS IN HIGH POINT TO SR 1424 (HILLTOP ROAD) IN GREENSBORO. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-2412
GUILFORD | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | NCDOT | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | U-2412A | DIVISION 7 | T |  |  |  |  | 2018 | 80599000 |  |  | 80599000 | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | NCDOT | SR 4228 (VICKREY CHAPEL ROAD) TO SR 1424 (HILLTOP ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | U-2412B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / I-840 / FUTURE I-840 / US 421 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF I-85 TO LAWNDALE DRIVE IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2524 | [11 empty] | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
GUILFORD | SR 1546 (GUILFORD COLLEGE ROAD) | NCDOT | SOUTH OF SR 1541 (WENDOVER AVENUE) TO NORTH OF SR 1560 (SAPP ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2524AA | [11 empty] | COMPLETE
GUILFORD | I-73 / US 421 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF I-85 NEAR SR 1129 (GROOMETOWN ROAD) TO NORTH OF SR 4121 (HIGH POINT ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2524AB | [11 empty] | COMPLETE
GUILFORD | I-73 / US 421 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF SR 4121 (HIGH POINT ROAD) TO SOUTH OF I-40 | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2524AC | [11 empty] | COMPLETE
GUILFORD | I-73 / US 421 | NCDOT | GREENSBORO WESTERN LOOP, INTERCHANGE AT PROPOSED HIGH POINT ROAD RELOCATION | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2524AE | [11 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / I-840 | NCDOT | GREENSBORO WESTERN LOOP, SOUTH OF I-40 TO NORTH OF SR 2147 (WEST FRIENDLY AVENUE) | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2524BA | [11 empty] | COMPLETE
GUILFORD | I-73 / I-840 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF SR 2147 (WEST FRIENDLY AVENUE) TO NORTH OF SR 2176 (BRYAN BOULEVARD) | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2524BB | [11 empty] | COMPLETE
GUILFORD | I-73 / I-840 | NCDOT | SR 2085 (BRYAN BOULEVARD) INTERCHANGE MODIFICATIONS, INCLUDING AUXILIARY LANES, ITS, AND INMAN ROAD BRIDGE REPLACEMENT. | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | U-2524BC | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
GUILFORD | FUTURE I-840 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF SR 2176 (BRYAN BOULEVARD) TO US 220 (BATTLEGROUND AVENUE) | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2524C | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2013 | 54285000 |  |  | 54285000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING $105.9 MILLION; PAYBACK FY 2013-2024
GUILFORD | FUTURE I-840 | NCDOT | GREENSBORO WESTERN LOOP, US 220 (BATTLEGROUND AVENUE) TO SR 2303 (LAWNDALE DRIVE) | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2524D | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / I-840 | NCDOT | GREENSBORO WESTERN LOOP, ITS INSTALLATION | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2524E | [11 empty] | COMPLETE
GUILFORD | FUTURE I-840 | NCDOT | GREENSBORO WESTERN LOOP, INTERCHANGE AT PROPOSED LEWISTON-FLEMING ROAD EXTENSION | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2524F | NOT FUNDED | NHP |  |  |  |  | NOT FUNDED | 15000000 |  |  | 15000000
GUILFORD | I-785 / I-840; FUTURE I-785; FUTURE I-840 | NCDOT | GREENSBORO EASTERN LOOP, LAWNDALE DRIVE TO NORTH OF I-40 / I-85 IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2525
GUILFORD | I-785 / I-840 | NCDOT | GREENSBORO EASTERN LOOP, SOUTH OF SR 3041 (CLAPP FARMS ROAD) TO US 70 RELOCATION | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-2525A | [11 empty] | COMPLETE
GUILFORD | FUTURE I-785 / FUTURE I-840 | NCDOT | GREENSBORO EASTERN LOOP, US 70 RELOCATION TO US 29 NORTH OF GREENSBORO | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | U-2525B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | FUTURE I-840 | NCDOT | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2525C | STATEWIDE MOBILITY | T |  |  |  |  | 2018 | 94831000 | 2021 | 8340000 | 103171000 | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | FUTURE I-840 | NCDOT | INTERCHANGE AT PROPOSED CONE BOULEVARD EXTENSION | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2525D | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 15000000 |  |  | 15000000
GUILFORD | US 70 | NCDOT | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2581
GUILFORD | US 70 | NCDOT | SR 2851 (PENRY ROAD) TO SR 2828 (WILLOWLAKE ROAD) | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2581A | [11 empty] | PROJECT COMPLETE
GUILFORD | US 70 | NCDOT | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2581BA | DIVISION 7 | T | 2020 | 2618000 |  |  | 2020 | 15535000 | 2020 | 1609000 | 19762000 | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | US 70 | NCDOT | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2581BB | NOT FUNDED | T | NOT FUNDED | 2113000 | NOT FUNDED | 626000 | NOT FUNDED | 8200000 |  |  | 10939000
GUILFORD | US 70 | NCDOT | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-2581BC | NOT FUNDED | T | NOT FUNDED | 3040000 | NOT FUNDED | 901000 | NOT FUNDED | 11800000 |  |  | 15741000
GUILFORD | SR 1820 (SKEET CLUB ROAD) | NCDOT | US 311 TO NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. WIDEN TO FOUR- AND FIVE-LANE DIVIDED FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | U-3615
GUILFORD | SR 1820 (SKEET CLUB ROAD) | NCDOT | US 311 TO EAST OF SR 1818 (JOHNSON STREET). WIDEN TO FIVE-LANE FACILITY FROM US 311 TO NORTH OF US 311 AND TO FOUR-LANE MEDIAN DIVIDED FACILITY FROM NORTH OF US 311 TO EAST OF SR1818 (JOHNSON STREET). | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | U-3615A | NOT FUNDED | T | NOT FUNDED | 5700000 |  |  | NOT FUNDED | 15500000 |  |  | 21200000
GUILFORD | SR 1820 (SKEET CLUB ROAD) | NCDOT | EAST OF SR 1818 (JOHNSON STREET) TO WEST OF NC 68 (EASTCHESTER DRIVE). WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY. | HIGHWAY | TRANSITION | 7 | HIGH POINT URBAN AREA MPO | U-3615B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | NCDOT | NC 68 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-4015
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | NCDOT | NC 68 TO AIRPARK ROAD IN GREENSBORO. WIDEN TO MULTILANES | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-4015A | DIVISION 7 | T |  |  |  |  | 2024 | 11500000 |  |  | 11500000 | RIGHT OF WAY IN PROGRESS
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | NCDOT | AIRPARK ROAD TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-4015B | [11 empty] | COMPLETE
GUILFORD | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | NCDOT | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | U-4758 | DIVISION 7 | BG5200, HP, S(M) | 2022 | 13221000 | 2022 | 7200000 | 2024 | 45699000 |  |  | 66120000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | VARIOUS | NCDOT | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-5021 | DIVISION 7 | BGDA |  |  |  |  | 2023 | 71646000 |  |  | 71646000
GUILFORD | I-74 / US 311 | NCDOT | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. RECONSTRUCT INTERCHANGE AND APPROACHES. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | U-5169 | REGION D | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION AND SIDEWALK IMPROVEMENTS AT CONE BOULEVARD-BENJAMIN PARKWAY, WESTRIDGE ROAD, NEW GARDEN ROAD, AND BRASSFIELD ROAD INTERSECTIONS IN GREENSBORO. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5306
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION WITH BENJAMIN PARKWAY / CONE BOULEVARD AND APPROACHES | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | U-5306A | PRE-STI (TRANSITION) | [10 empty] | PROJECT COMPLETE
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION WITH WESTRIDGE ROAD AND APPROACHES | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5306B | REGION D | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION WITH NEW GARDEN ROAD AND APPROACHES | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | U-5306C | PRE-STI (TRANSITION) | [10 empty] | PROJECT COMPLETE
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION WITH BRASSFIELD ROAD AND APPROACHES | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO | U-5306D | [11 empty] | PROJECT COMPLETE
GUILFORD | SR 1008 (MARKET STREET) | NCDOT | SR 1546 (COLLEGE ROAD) IN GREENSBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5326 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | US 29 / US 70 / US 220 (O'HENRY BOULEVARD) | NCDOT | I-40 / BUSINESS 85 TO SOUTH OF FLORIDA STREET IN GREENSBORO. ADD LANE ON I-40 / BUSINESS 85 EASTBOUND RAMP ONTO NORTHBOUND US 29 / US 70 / US 220 AND EXTEND US 29 / US 70 / US 220 SOUTHBOUND RAMP ONTO SR 3762 (MARTIN LUTHER KING, JR. DRIVE) | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5754 | REGION D | T |  |  |  |  | 2022 | 6750000 |  |  | 6750000 | UNDER CONSTRUCTION
GUILFORD | VARIOUS | GREENSBORO | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5812 | DIVISION 7 | BGANY, L | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 180000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 750000 |  |  | 930000 | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | FRIENDLY AVENUE | NCDOT | WEST OF GREEN VALLEY ROAD TO LINDELL ROAD IN GREENSBORO. WIDENING AND INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5841 | DIVISION 7 | T |  |  |  |  | 2023 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION
GUILFORD | PISGAH CHURCH ROAD | GREENSBORO | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5842 | DIVISION 7 | BGANY, L | 2023 | 180000 |  |  | 2024 | 750000 |  |  | 930000 | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | SR 1007 (RANDLEMAN ROAD) | NCDOT | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5850 | DIVISION 7 | T | 2022 | 800000 | 2022 | 500000 | 2025 | 3000000 |  |  | 4300000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | SR 1001 (CHURCH STREET) | NCDOT | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5851 | DIVISION 7 | T | 2028 | 9400000 | 2028 | 997000 | 2030 | 11999000 |  |  | 22396000
GUILFORD | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | NCDOT | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5852 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 855000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11599000 |  |  | 13054000
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-5892 | REGION D | NHP | 2023 | 7531000 | 2023 | 1472000 | 2026 | 12400000 |  |  | 21403000
GUILFORD | US 29 / US 70 / BUSINESS 85 | NCDOT | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | U-5896 | DIVISION 7 | T | 2019 | 8834000 |  |  | 2022 | 15400000 | 2019 | 1820000 | 26054000 | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
GUILFORD | NC 68 | NCDOT | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | U-5974 | REGION D | T | 2027 | 10200000 | 2027 | 6600000 | 2029 | 27300000 |  |  | 44100000 | COORDINATE WITH U-6122
GUILFORD | SR 2085 (BRYAN BOULEVARD) | NCDOT | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6008 | DIVISION 7 | T | 2027 | 1600000 | 2027 | 300000 | 2029 | 4600000 |  |  | 6500000
GUILFORD | SR 2124 (LEWISTON ROAD) | NCDOT | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6016 | DIVISION 7 | T | 2022 | 836000 | 2022 | 215000 | 2024 | 1300000 |  |  | 2351000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | NC 62 | NCDOT | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | U-6018 | DIVISION 7 | T | 2021 | 2600000 | 2021 | 1311000 | 2024 | 14200000 |  |  | 18111000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | SR 2334 (AIR HARBOR ROAD) | NCDOT | SR 2347 (LAKE BRANDT ROAD). CONSTRUCT TURN LANES AND SIDEWALKS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6019 | DIVISION 7 | T |  |  |  |  | 2022 | 1300000 |  |  | 1300000 | UNDER CONSTRUCTION
GUILFORD | SR 1850 (SANDY RIDGE ROAD) | NCDOT | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6045 | DIVISION 7 | T | 2027 | 6800000 | 2027 | 1200000 | 2030 | 23100000 |  |  | 31100000
GUILFORD | VARIOUS | NCDOT | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. | HIGHWAY | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-6085 | DIVISION 7 | BGDA, L | [6 empty] | 2022 | 5300000 | 5300000 | IN PROGRESS
GUILFORD | US 29; US 70; US 220 | NCDOT | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6100 | NOT FUNDED | T | NOT FUNDED | 4400000 | NOT FUNDED | 2200000 | NOT FUNDED | 24000000 |  |  | 30600000
GUILFORD | US 70 / US 220 (WENDOVER AVENUE) | GREENSBORO | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6108 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 44600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12500000 |  |  | 58700000
GUILFORD | US 70 (WENDOVER AVENUE) | NCDOT | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | HIGHWAY | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6121 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39499000 |  |  | 53499000 | COORDINATE WITH EB-6010
GUILFORD | NC 68 | NCDOT | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | U-6122 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14200000 |  |  | 22700000 | COORDINATE WITH U-5974
GUILFORD | NC 68 | NCDOT | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6127 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9800000 |  |  | 12300000 | COORDINATE WITH R-5725
GUILFORD | WEST FRIENDLY AVENUE | GREENSBORO | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6129 | DIVISION 7 | BGANY, L | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 150000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 52000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 550000 |  |  | 752000 | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | SR 2835 (MCKNIGHT MILL ROAD) | NCDOT | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6181 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 216000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 |  |  | 1916000
GUILFORD | MCCONNELL ROAD | GREENSBORO | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6185 | DIVISION 7 | BGANY, L | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 |  |  | 2100000 | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | SR 1001 (NORTH CHURCH STREET) | NCDOT | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6186 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2850000 |  |  | 4950000
GUILFORD | SR 2133 (PLEASANT RIDGE ROAD) | NCDOT | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6211 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 |  |  | 3500000
GUILFORD | NC 62 | NCDOT | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | U-6212 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 |  |  | 1800000
GUILFORD | VARIOUS | NCDOT | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | LOCALLY SELECTED | 7 | GREENSBORO URBAN AREA MPO | U-6220 | DIVISION 7 | TADA |  |  |  |  | 2022 | 11164000 |  |  | 11164000
GUILFORD | NC 68 | NCDOT | SOUTH OF SR 2111 (EAST HARRELL ROAD) TO SR 4831 (BARTONSHIRE DRIVE) IN OAK RIDGE AND SUMMERFIELD. CONSTRUCT TURN LANES, CLOSE ACCESS TO SR 2029 (WEST HARRELL ROAD), AND RELOCATE SR 2111 INTERSECTION AND PORTION OF SR 2111. | HIGHWAY | TRANSITION | 7 | GREENSBORO URBAN AREA MPO | W-5114 | [11 empty] | UNDER CONSTRUCTION
GUILFORD | NC 62; SR 1129 (GROOMETOWN ROAD) | NCDOT | SR 1129 AT SR 4019 (GROOMETOWN ROAD); NC 62 AT SR 1129 (GROOMETOWN ROAD). REALIGN BOTH INTERSECTIONS AND REMOVE ACCESS BETWEEN SR 4019 AND NC 62. | HIGHWAY | TRANSITION | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | W-5305 | REGION D | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 220 EASTBOUND | NCDOT | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | HIGHWAY | SAFETY | 7 | GREENSBORO URBAN AREA MPO | W-5807A | REGION D | HSIP | 2023 | 150000 |  |  | 2023 | 280000 |  |  | 430000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | GTA | GTA | REPLACEMENT PARATRANSIT BUSES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TA-4767 | PUBLIC TRANSIT | 5309, L | [6 empty] | 2022 | 4844000 | 4844000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GTA | GTA | CLEAN DIESEL REPLACEMENT BUSES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TA-4771 | PUBLIC TRANSIT | 5307, CMAQ, L | [6 empty] | 2022 | 4457000 | 4457000
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE ONE EXPANSION 40-FT BUS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TA-6679 | REGION D | [10 empty] | IN ACQUISITION
GUILFORD | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | REPLACEMENT VEHICLES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TA-6690 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2022 | 315000 | 315000
GUILFORD | GTA | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TA-6714 | PUBLIC TRANSIT | 5339, CMAQ, L | [6 empty] | 2023 | 4685000 | 4685000 | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT
GUILFORD | SYSTEM / HI-TRAN HIGH POINT TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | HIGH POINT URBAN AREA MPO | TA-6729 | PUBLIC TRANSIT | 5307, CMAQ, L | [6 empty] | 2022 | 500000 | 500000
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | VEHICLE REPLACEMENT AND EXPANSION | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TA-6732 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2020 | 8480000 |  |  | 8480000 | PROJECT ADDED AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TD-5279 | PUBLIC TRANSIT | 5339, L, S | [6 empty] | 2020 | 2284000 | 2284000 | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | SYSTEM / HI-TRAN HIGH POINT TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | BUILDING / FACILITY RENOVATION AND UPGRADE FOR PARATRANSIT ADMINISTRATION. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | HIGH POINT URBAN AREA MPO | TD-5283 | REGION D | [10 empty] | N PROGRESS
GUILFORD | GREENSBORO TRANSIT AGENCY | GREENSBORO TRANSIT AGENCY | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TG-4759 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 27153000 | 27153000
GUILFORD | AUTHORITY GREENSBORO TRANSIT | AUTHORITY GREENSBORO TRANSIT | OPERATING-ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TG-4957 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 5761000 | 5761000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | AUTHORITY GREENSBORO TRANSIT | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TG-5105 | PUBLIC TRANSIT | 5307, 5339, L | [6 empty] | 2022 | 1967000 | 1967000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PREVENTIVE MAINTENANCE, SECURITY AND PESSENGER AMENITIES. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TG-6173B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 1138000 | 1138000
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TG-6185 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 535000 | 535000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GUILFORD COUNTY TRANSPORTATION | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TK-6132 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 908000 | 908000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GTA | GTA | EXPANDED SUNDAY SERVICE, NEW SERVICE OPERATIONAL FUNDING | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TL-0012 | PUBLIC TRANSIT | CMAQ, L | [6 empty] | 2021 | 2705000 | 2705000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | GREENSBORO URBAN AREA MPO | TO-4971 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2022 | 54460000 | 54460000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | GREENSBORO URBAN AREA MPO | TO-5209 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2022 | 12202000 | 12202000 | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY
GUILFORD | GUILFORD COUNTY TRANSPORTATION | GUILFORD COUNTY TRANSPORTATION | OPERATING FUNDING FOR GUILFORD COUNTY THROUGH HIGH-POINT MPO | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | HIGH POINT URBAN AREA MPO | TO-5216 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1330000 | 1330000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GUILFORD COUNTY TRANSPORTATION | GUILFORD COUNTY TRANSPORTATION | OPERATING- RURAL TRANSIT | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | GREENSBORO URBAN AREA MPO | TO-5221 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 490000 | 490000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 OPERATING | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | GREENSBORO URBAN AREA MPO | TO-6139 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2022 | 384000 | 384000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO
GUILFORD | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | OPERATING | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | BURLINGTON-GRAHAM MPO | TO-6151 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2016000 | 2016000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303 | PUBLIC TRANSIT | PLANNING | 7 | GREENSBORO URBAN AREA MPO | TP-5101 | PUBLIC TRANSIT | 5303, L, SMAP | [6 empty] | 2021 | 1458000 | 1458000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | HIGH POINT TRANSIT SYSTEM / HI-TRAN | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | HIGH POINT URBAN AREA MPO | TP-5104 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 176000 | 176000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 CAPITAL PROJECT | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TQ-6783 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2022 | 1677000 | 1677000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 PROGRAM ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TQ-7000 | PUBLIC TRANSIT | 5310 | [6 empty] | 2022 | 166000 | 166000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | SAFETY & SECURITY | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | GREENSBORO URBAN AREA MPO | TS-4758 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 567000 | 567000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GTA | GTA | TRANSIT SAFETY INNOVATIONS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | GREENSBORO URBAN AREA MPO | TT-5207 |  | 5312, L | [6 empty] | 2020 | 86000 | 86000 | FUNDING ADDED TO FY20, FY21, FY22 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GTA | GTA | THE CITY OF GREENSBORO WILL RECEIVE FUNDING TO PREPARE A TECHNICAL PLAN TO ESTABLISH WHAT WILL BE REQUIRED TO PROVIDE FREE BROADBAND INTERNET ACCESS IN LOW - INCOME AREAS USING TRANSIT, TRANSPORTATION AND OTHER PUBLIC INFRASTRUCTURE. | PUBLIC TRANSIT | PLANNING | 7 | GREENSBORO URBAN AREA MPO | TU-0002 | PUBLIC TRANSIT | 5305, L | [6 empty] | 2021 | 260000 | 260000
GUILFORD | NORFOLK SOUTHERN MAINLINE | NSR RR | NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. | RAIL | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | P-5700 | DIVISION 7 | O, T |  |  |  |  | 2024 | 1700000 |  |  | 1700000 | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION
GUILFORD | NORFOLK SOUTHERN H LINE | NCDOT | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | RAIL | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | P-5709 | REGION D | O, T | 2022 | 3484000 | 2022 | 1566000 | 2024 | 20100000 |  |  | 25150000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | NCDOT | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | RAIL | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | P-5713 | STATEWIDE MOBILITY | O, T | 2025 | 3431000 | 2025 | 952000 | 2026 | 8901000 |  |  | 13284000 | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION
GUILFORD | NCRR NORFOLK SOUTHERN | NCDOT | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. | RAIL | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | P-5714 | REGION D | O, T |  |  |  |  | 2025 | 3100000 |  |  | 3100000 | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN | JAMESTOWN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | RAIL | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | P-5721 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 4070000 |  |  | 4070000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN MAIN LINE | NCDOT | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | RAIL | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | P-5735 | STATEWIDE MOBILITY | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12700000 |  |  | 16200000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD
GUILFORD | NCRR NORFOLK SOUTHERN H LINE | NCDOT | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | RAIL | STI (PRIORITIZATION) | 7 | GREENSBORO URBAN AREA MPO | P-5747 | REGION D | O, T | 2025 | 2300000 |  |  | 2026 | 14899000 |  |  | 17199000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NCRR / NORFOLK SOUTHERN MAIN LINE | NCDOT | HOSKINS STREET IN HIGH POINT. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722351T. | RAIL | STI (PRIORITIZATION) | 7 | HIGH POINT URBAN AREA MPO | P-5752 | DIVISION 7 | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19000000 |  |  | 21900000
GUILFORD | SR 2748 (SPRINGWOOD AVENUE) | GIBSONVILLE | NORFOLK SOUTHERN RAILROAD CROSSING 722990L IN GIBSONVILLE. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 7 | BURLINGTON-GRAHAM MPO | RX-2007A | DIVISION 7 | RR |  |  |  |  | 2023 | 500000 |  |  | 500000 | UNDER CONSTRUCTION
GUILFORD | SR 2531 (HILLCROFT ROAD) | GREENSBORO | NORFOLK SOUTHERN RAILROAD CROSSING 722545Y NEAR GREENSBORO. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 7 | GREENSBORO URBAN AREA MPO | RX-2007C | DIVISION 7 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
GUILFORD | LOWDERMILK STREET SYKES AVENUE | NCDOT | PINE STREET CROSSING CLOSURE AND LOWDERMILK STREET / SYKES AVENUE REALIGNMENT IN GREENSBORO. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 7 | GREENSBORO URBAN AREA MPO | Y-4807B | DIVISION 7 | RR |  |  |  |  | 2023 | 5000000 |  |  | 5000000
GUILFORD, ALAMANCE | I-40 / I-85 | NCDOT | EAST OF SR 3056 (ROCK CREEK DAIRY ROAD) IN GUILFORD COUNTY TO WEST OF SR 1226 (UNIVERSITY DRIVE) IN ALAMANCE COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO | I-5956 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD, ALAMANCE, FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7, 9 | WINSTON-SALEM URBAN AREA MPO | TS-5115 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 8000 | 8000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD, DAVIDSON, RANDOLPH | SYSTEM / HI-TRAN HIGH POINT TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC ($40K CAPITAL COST OF CONTRACTING) | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7, 8, 9 | HIGH POINT URBAN AREA MPO | TG-4814 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 916000 | 916000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | GEORGE LILES PARKWAY | NCDOT | SR 1431 (WEDDINGTON ROAD) TO SOUTH OF I-85 | HIGHWAY | PRE-STI (HISTORIC) | 10 | CABARRUS-ROWAN MPO | R-2246C | [11 empty] | COMPLETE
CABARRUS | SR 1394 (POPLAR TENT ROAD) | NCDOT | SR 1445 (DERITA ROAD) TO US 29/601 BYPASS. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | U-3415
CABARRUS | NC 3 | NCDOT | PROPOSED WEST SIDE BYPASS (U-2009) TO SR 1691 (LOOP ROAD) IN KANNAPOLIS. WIDEN TO A FOUR-LANE DIVIDED FACILITY. | HIGHWAY | TRANSITION | 10 | CABARRUS-ROWAN MPO | U-3440 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
CABARRUS | SR 1445 (DERITA ROAD) | NCDOT | SR 2894 (CONCORD MILLS BOULEVARD) TO SR 1394 (POPLAR TENT ROAD) IN CONCORD. WIDEN TO 4-LANES DIVIDED. | HIGHWAY | TRANSITION | 10 | CABARRUS-ROWAN MPO | U-4910 | [11 empty] | SEGMENTS A AND B LET TOGETHER
CABARRUS | SR 1445 (DERITA ROAD) | NCDOT | SR 2894 (CONCORD MILLS BOULEVARD) TO AVIATION BOULEVARD. WIDEN TO 4-LANES DIVIDED. | HIGHWAY | LOCALLY SELECTED | 10 | CABARRUS-ROWAN MPO | U-4910A | DIVISION 10 | [10 empty] | UNDER CONSTRUCTION
CABARRUS | SR 1445 (DERITA ROAD) | NCDOT | AVIATION BOULEVARD TO SR 1394 (POPLAR TENT ROAD). WIDEN TO 4-LANES DIVIDED. | HIGHWAY | PRE-STI (HISTORIC) | 10 | CABARRUS-ROWAN MPO | U-4910B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
CABARRUS | VARIOUS | NCDOT | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN REGIONAL CATEGORY. | HIGHWAY | SAFETY | 10 | CABARRUS-ROWAN MPO | W-5210REG | REGION E
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - CAPITAL | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CABARRUS-ROWAN MPO | TA-5128A | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 2500000 | 2500000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - OPERATING | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CABARRUS-ROWAN MPO | TA-5128B | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 1350000 | 1350000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD, FORSYTH | I-40 | NCDOT | NC 66 TO US 421 / BUSINESS 40. | HIGHWAY | STI (PRIORITIZATION) | 7, 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | I-5981C | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38798000 |  |  | 39198000
GUILFORD, FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7, 9 | HIGH POINT URBAN AREA MPO | TO-5134C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 6000000 | 6000000
GUILFORD, FORSYTH, CASWELL, DAVIDSON, MONTGOMERY, RANDOLPH, ROCKINGHAM | VARIOUS | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PART) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PART). IMPLEMENT A REGIONAL AIR QUALITY AWARENESS PROGRAM. | HIGHWAY | OTHER | 7, 8, 9 | GREENSBORO URBAN AREA MPO, NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO | C-4936 | EXEMPT | [10 empty] | IN PROGRESS BY PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION
GUILFORD, ORANGE | VARIOUS | BURLINGTON | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | HIGHWAY | OTHER | 7 | BURLINGTON-GRAHAM MPO | C-5602 | EXEMPT | CMAQ, L | 2020 | 18000 |  |  | 2020 | 99000 | 2020 | 54000 | 171000
GUILFORD, ROCKINGHAM | FUTURE I-73 | NCDOT | NC 68 AT SR 2011 (EDGEFIELD ROAD) IN GUILFORD COUNTY TO US 220-NC 68 INTERSECTION IN ROCKINGHAM COUNTY. FOUR-LANE FREEWAY, ON NEW LOCATION, NC 68 TO US 220 AND FOUR LANES ALONG US 220 TO NC 68 IN ROCKINGHAM COUNTY. | HIGHWAY | PRE-STI (HISTORIC) | 7 | GREENSBORO URBAN AREA MPO, PIEDMONT TRIAD RPO | R-2413 | PRE-STI (TRANSITION)
GUILFORD, WAKE, MECKLENBURG | PIEDMONT CORRIDOR | NCDOT | ACQUIRE AND REBUILD 2 ADDITIONAL LOCOMOTIVES. | RAIL | STI (PRIORITIZATION) | 5, 7, 10 | GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-5719A | EXEMPT | [10 empty] | COMPLETE
GUILFORD, WAKE, MECKLENBURG | PIEDMONT CORRIDOR | NCDOT | ACQUIRE AND REFURBISH 2 COACH AND 1 LOUNGE/BAGGAGE RAIL CARS. | RAIL | STI (PRIORITIZATION) | 5, 7, 10 | GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-5719B | EXEMPT | [10 empty] | IN PROGRESS
HALIFAX | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | CONSTRUCT TAXI LANE AND PREPARATION FOR ADDITIONAL T-HANGARS. | AVIATION | STI (PRIORITIZATION) | 4 | PEANUT BELT RPO | AV-5822 | DIVISION 4 | T |  |  |  |  | 2024 | 1100000 |  |  | 1100000
HALIFAX | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. | AVIATION | STI (PRIORITIZATION) | 4 | PEANUT BELT RPO | AV-5833 | DIVISION 4 | T |  |  |  |  | 2026 | 2300000 |  |  | 2300000
HALIFAX | EAST 10TH STREET | ROANOKE RAPIDS | MARSHALL STREET TO PARKE AVENUE IN ROANOKE RAPIDS. CONSTRUCT SIDEWALK ON BOTH SIDES OF ROAD. | BIKE/PED | STI (PRIORITIZATION) | 4 | PEANUT BELT RPO | EB-5843 | DIVISION 4 | L, TA5200 |  |  |  |  | 2025 | 200000 |  |  | 200000
HALIFAX | SR 1100 (BELLS BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 410065 AND 410066 OVER DEEP CREEK. | HIGHWAY | BRIDGES | 4 | PEANUT BELT RPO | B-5660 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION.
HALIFAX | NC 561 | NCDOT | REPLACE BRIDGE 410093 OVER CONOCONNARA SWAMP. | HIGHWAY | BRIDGES | 4 | PEANUT BELT RPO | B-5662 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2581000 |  |  | 2581000 | UNDER CONSTRUCTION.
HALIFAX | SR 1309 (SPRUILLS BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 410138 OVER LITTLE FISHING CREEK. | HIGHWAY | BRIDGES | 4 | PEANUT BELT RPO | B-5665 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. DIVISION PURCHASE ORDER CONTRACT.
HALIFAX | SR 1601 (SLEDGE ROAD) | NCDOT | REPLACE BRIDGE 410115 OVER ROCKY SWAMP. | HIGHWAY | BRIDGES | 4 | PEANUT BELT RPO | BR-0113 | DIVISION 4 | DP, HFB | 2020 | 130000 |  |  | 2021 | 796000 |  |  | 926000 | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
HALIFAX | SR 1710 (GRACE DRIVE/ WATKINS DRIVE) AND SR 1737 | NCDOT | FROM US-158 TO NORTH OF SR 1734 (KENNAMETAL DRIVE). WIDEN TO FOUR LANES. REALIGN SR 1737 (POWER PLACE) AND US-158 INTERSECTION. | HIGHWAY | ECONOMIC DEVELOPMENT | 4 | PEANUT BELT RPO | HE-0003 | DIVISION 4 | T |  |  |  |  | 2022 | 2000000 |  |  | 2000000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR ROSEBURG FOREST PRODUCTS.
HALIFAX | NC 48 | NCDOT | INSTALL ALL WAY STOP AND REVISE EXISTING OVERHEAD AND SHOULDER-MOUNTED FLASHERS AT NC 48 AND NC 903. | HIGHWAY | SAFETY | 4 | PEANUT BELT RPO | HS-2004G | REGION A | HSIP |  |  |  |  | 2022 | 50000 |  |  | 50000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004H.
HALIFAX | US 158 | NCDOT | US 158 FROM EASTERN LITTLETON TOWN LIMITS AND 0.15 MILES WEST OF SR 1432 (EVERETTS SCHOOL ROAD). INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 4 | PEANUT BELT RPO | HS-2004T | REGION A | HSIP |  |  |  |  | 2023 | 230000 |  |  | 230000 | UNDER CONSTRUCTION.
HALIFAX | I-95 | NCDOT | NC 481 (MILE MARKER 154) TO MILE MARKER 167. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | PEANUT BELT RPO | I-5932
HALIFAX | I-95 | NCDOT | NC 561 (MILE MARKER 160) TO MILE MARKER 167. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | PEANUT BELT RPO | I-5932A | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2021 | 7376000 |  |  | 7376000 | UNDER CONSTRUCTION.
HALIFAX | I-95 | NCDOT | NC 481 (MILE MARKER 154) TO NC 561 (MILE MARKER 160). | HIGHWAY | INTERSTATE MAINTENANCE | 4 | PEANUT BELT RPO | I-5932B | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2021 | 7823000 |  |  | 7823000 | UNDER CONSTRUCTION.
HALIFAX | NEW ROUTE | NCDOT | NC 125 TO SOUTH OF US 158. CONSTRUCT THREE LANE FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 4 | PEANUT BELT RPO | R-3822 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH U-5725. CONSTRUCTION FUNDS SHOWN UNDER U-5725.
HALIFAX | NC 125 | NCDOT | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | PEANUT BELT RPO | U-5725 | DIVISION 4 | T |  |  |  |  | 2019 | 27240000 | 2021 | 2130000 | 29370000 | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3).
HALIFAX | VARIOUS | CSXT RR | CAROLINIAN CORRIDOR - CSXT MP A 101.0 (ENFIELD CROSSING). | RAIL | TRANSITION | 4 | PEANUT BELT RPO | P-5005A | PRE-STI (TRANSITION)
HALIFAX | VARIOUS | CSXT RR | CAROLINIAN CORRIDOR - CSXT MP A 86.4 (SOUTH WELDON CROSSING). | RAIL | TRANSITION | 4 | PEANUT BELT RPO | P-5005C | PRE-STI (TRANSITION)
HALIFAX, JOHNSTON | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 4 | PEANUT BELT RPO, UPPER COASTAL PLAIN RPO | HS-2004J | DIVISION 4 | HSIP |  |  |  |  | 2022 | 5246000 |  |  | 5246000 | UNDER CONSTRUCTION.
HALIFAX, NORTHAMPTON | CSX A LINE | NCDOT | CONSTRUCT NEW MAIN TRACK BETWEEN MILE POST A-80.7 AND MILE POST A-82.4 INCLUDING REHABILITATION OF CSX SA-LINE BRIDGE OVER ROANOKE RIVER. NEW CONNECTION BETWEEN A-LINE AND SA-LINE AT MILE POST A-80.7. RECONSTRUCT MAIN TRACK BETWEEN MILE POST A-82.4 AND MILE POST A-84.7. CREATE SECOND MAIN. | RAIL | STI (PRIORITIZATION) | 1, 4 | PEANUT BELT RPO | P-5741 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 62000000 |  |  | 67000000
HALIFAX, WAKE, NASH, EDGECOMBE | CSXT RR | CSXT RR | CONGESTION MITIGATION CROSSOVERS. | RAIL | OTHER | 4, 5 | PEANUT BELT RPO, CAPITAL AREA MPO, ROCKY MOUNT URBAN AREA MPO | P-5005 | [11 empty] | IN PROGRESS.
HARNETT | EAST MCLVER STREET, SOUTH WILMA STREET | ANGIER | EAST MCLVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | BIKE/PED | LOCALLY SELECTED | 6 | CAPITAL AREA MPO | BL-0090 | DIVISION 6 | BGDA, L | 2024 | 50000 |  |  | 2024 | 898000 | 2024 | 150000 | 1098000
HARNETT | NC 210 | ANGIER | CONSTRUCT A MULTI-USE PATH FROM HARNETT CENTRAL ROAD TO NORTH HARNETT PRIMARY SCHOOL ROAD. | BIKE/PED | LOCALLY SELECTED | 6 | CAPITAL AREA MPO | BL-0094 | DIVISION 6 | BGDA, L | 2024 | 10000 |  |  | 2024 | 550000 | 2024 | 40000 | 600000
HARNETT | CAMPBELL UNIVERSITY SIDEWALK | BUIES CREEK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | EB-6014 | DIVISION 6 | L, TALT5 | 2021 | 35000 |  |  | 2021 | 565000 |  |  | 600000 | UNDER CONSTRUCTION.
HARNETT | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | ANGIER | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | BIKE/PED | LOCALLY SELECTED | 6 | CAPITAL AREA MPO | EB-6020 | DIVISION 6 | BGDA, L | 2024 | 150000 |  |  | 2024 | 1457000 | 2021 | 175000 | 1782000
HARNETT | SR 1210 (HOOVER ROAD) | NCDOT | REPLACE BRIDGE 420234 OVER BARBEQUE SWAMP. | HIGHWAY | BRIDGES | 6 | MID-CAROLINA RPO | B-6005 | DIVISION 6 | [10 empty] | COMPLETED.
HARNETT | CHURCH ROAD) SR 1214 (MOUNT PISGAH | NCDOT | REPLACE BRIDGE 420034 OVER UPPER LITTLE RIVER. | HIGHWAY | BRIDGES | 6 | MID-CAROLINA RPO | HB-0008 | DIVISION 6 | BGOFF | 2027 | 330000 |  |  | 2028 | 1900000 |  |  | 2230000
HARNETT | NC 27 | NCDOT | NC 24/27 FROM THE MOORE COUNTY LINE AND THE NC 24/27 SPLIT, NC 27 FROM NC 24 TO LILLINGTON, NC 27 FROM US 421 TO COATS, AND NC 27 FROM COATS TO THE JOHNSTON COUNTY LINE. INSTALL RUMBLE STRIPES, RUMBLE STRIPS, AND LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO | HS-2006H | REGION C | HSIP |  |  |  |  | 2023 | 1065000 |  |  | 1065000 | UNDER CONSTRUCTION.
HARNETT | SR 1441 (CHALYBEATE SPRINGS ROAD) | NCDOT | FROM NC 55 TO US 401. CURVE AND PAVEMENT MARKING IMPROVEMENTS. | HIGHWAY | SAFETY | 6 | CAPITAL AREA MPO | HS-2006K | DIVISION 6 | HSIP |  |  |  |  | 2025 | 822000 |  |  | 822000
HARNETT | SR 1532 (LANGDON ROAD) | NCDOT | SR 1532 (LANGDON ROAD) AT BRIDGE 420015. UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO | HS-2006Q | DIVISION 6 | HSIP | 2023 | 60000 |  |  | 2023 | 190000 |  |  | 250000 | UNDER CONSTRUCTION.
HARNETT | SR 1115 (BUFFALO LAKE ROAD) | NCDOT | FROM NC 27 TO NC 87. INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO | HS-2006Y | DIVISION 6 | HSIP |  |  |  |  | 2023 | 235000 |  |  | 235000 | UNDER CONSTRUCTION.
HARNETT | I-95 | NCDOT | CUMBERLAND COUNTY LINE TO THE JOHNSTON COUNTY LINE. PAVEMENT REPAIR. | HIGHWAY | PRE-STI (HISTORIC) | 6 | MID-CAROLINA RPO | I-4906 | PRE-STI (TRANSITION) | [10 empty] | COMPLETED. GARVEE BOND FUNDING $3.15 MILLION; PAYBACK FY 2008 - FY 2019.
HARNETT | I-95 | NCDOT | SR 1811 (BUD HAWKINS ROAD) (EXIT 70) AND SR 1001 (LONG BRANCH ROAD) (EXIT 71). IMPROVE INTERCHANGES. | HIGHWAY | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | I-5877 | STATEWIDE MOBILITY | T | 2023 | 3304000 |  |  | 2020 | 69733000 |  |  | 73037000 | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION.
HARNETT | I-95 | NCDOT | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). IMPROVE INTERCHANGES. | HIGHWAY | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | I-5878 | STATEWIDE MOBILITY | T |  |  |  |  | 2022 | 78860000 |  |  | 78860000 | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION.
HARNETT | I-95 | NCDOT | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). CLEARING FOR UTILITIES. | HIGHWAY | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | I-5878A | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 139000 |  |  | 139000 | COMPLETED.
HARNETT | I-95 | NCDOT | SR 1808 (JONESBORO ROAD) (EXIT 75) AND SR 1709 (HODGES CHAPEL ROAD) (EXIT 77). IMPROVE INTERCHANGES. | HIGHWAY | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | I-5883 | STATEWIDE MOBILITY | T |  |  |  |  | 2022 | 100613000 |  |  | 100613000 | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION.
HARNETT | NC 55 | NCDOT | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 6 | CAPITAL AREA MPO | R-5705A | DIVISION 6 | T | 2021 | 28835000 | 2021 | 3100000 | 2024 | 59200000 |  |  | 91135000 | UNDER CONSTRUCTION.
HARNETT | US 401 (NORTH MAIN STREET) | NCDOT | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | HIGHWAY | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | R-5890 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4500000 |  |  | 4800000
HARNETT | NC 55 | NCDOT | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 6 | MID-CAROLINA RPO | R-5953 | NOT FUNDED | T | NOT FUNDED | 14600000 | NOT FUNDED | 4600000 | NOT FUNDED | 66299000 |  |  | 85499000
HARNETT | SR 1121 (RAY ROAD) | NCDOT | NC 210 TO SR 1120 (OVERHILLS ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | TRANSITION | 6 | FAYETTEVILLE AREA MPO | U-3465 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION.
HARNETT | NC 87/24 | NCDOT | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 6 | FAYETTEVILLE AREA MPO | U-5933 | STATEWIDE MOBILITY | BGDA, BGDACV, S(M), T | 2023 | 17000 | 2023 | 23000 | 2023 | 3540000 |  |  | 3580000 | UNDER CONSTRUCTION.
HARNETT | NC 27 | NCDOT | CONSTRUCT ROUNDABOUTS AT NC 27/SR 1006 (OLD STAGE ROAD) AND SR 2084 (LESLIE CAMPBELL AVENUE) AND AT NC 27/SR 1006 (OLD STAGE ROAD) AND SR 1516. CLOSE NC 27/SR 1516 INTERSECTION. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO | W-5706L | REGION C | HSIP |  |  | 2024 | 275000 | 2024 | 2500000 |  |  | 2775000 | RIGHT-OF-WAY IN PROGRESS.
HARNETT | SR 1117, SR 3242, SR 1615 | NCDOT | SR 1117 (NURSERY ROAD) FROM NC 27 TO SR 3242 (OVERHILLS ROAD). SR 3242 (OVERHILLS ROAD) FROM NC 24/87 TO SR 1117 (NURSERY ROAD). SR 1121 (RAY ROAD) FROM SR 1117 (NURSERY ROAD) TO SR 3242 (OVERHILLS ROAD). WIDEN CURVES AND INSTALL RUMBLE STRIPS. | HIGHWAY | SAFETY | 6 | FAYETTEVILLE AREA MPO, MID-CAROLINA RPO | W-5806B | DIVISION 6 | HSIP |  |  |  |  | 2022 | 400000 |  |  | 400000 | UNDER CONSTRUCTION.
HARNETT | NC 27, SR 1581 | NCDOT | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO | W-5806D | REGION C | HSIP | 2021 | 100000 |  |  | 2022 | 586000 |  |  | 686000 | UNDER CONSTRUCTION.
HARNETT | HARNETT COUNTY | HARNETT COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6 | MID-CAROLINA RPO | TK-6133 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 880000 | 880000 | FUNDS AUTHORIZED IN PROGRESS
HARNETT | HARNETT STREET | NCDOT | CSX CROSSING 629751J IN DUNN. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | MID-CAROLINA RPO | RX-2006C | DIVISION 6 | RR |  |  |  |  | 2025 | 446000 |  |  | 446000
HARNETT | EDGERTON STREET | NCDOT | CSX CROSSING 629752R IN DUNN. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | MID-CAROLINA RPO | RX-2006D | DIVISION 6 | RR |  |  |  |  | 2025 | 446000 |  |  | 446000
HARNETT | US 401 (MAIN STREET) | NCDOT | RFR CROSSING 465860F IN LILLINGTON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | MID-CAROLINA RPO | RX-2006F | DIVISION 6 | RR |  |  |  |  | 2026 | 345000 |  |  | 345000
HARNETT, BLADEN, CUMBERLAND, COLUMBUS | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO | HS-2006E | DIVISION 6 | HSIP |  |  |  |  | 2022 | 4715000 |  |  | 4715000 | UNDER CONSTRUCTION.
HARNETT, CUMBERLAND | US 401 | NCDOT | BETWEEN FAYETTEVILLE AND HARNETT COUNTY (MILEPOST 20 - 27.7), BETWEEN CUMBERLAND COUNTY AND LILLINGTON (MILEPOST 0 - 9.5), AND BETWEEN LILLINGTON AND WAKE COUNTY (MILEPOST 12.5 - 22.1). INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS. | HIGHWAY | SAFETY | 6 | MID-CAROLINA RPO, CAPITAL AREA MPO, FAYETTEVILLE AREA MPO | HS-2006W | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 975000 |  |  | 975000 | UNDER CONSTRUCTION.
HARNETT, JOHNSTON | I-95 | NCDOT | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 4, 6 | MID-CAROLINA RPO, UPPER COASTAL PLAIN RPO | I-5986B | STATEWIDE MOBILITY | T | 2020 | 42100000 | 2020 | 700000 | 2022 | 92456000 |  |  | 135256000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883.
HARNETT, JOHNSTON | I-95 | NCDOT | SR 1001 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). CLEARING FOR UTILITIES. | HIGHWAY | STI (PRIORITIZATION) | 4, 6 | MID-CAROLINA RPO, UPPER COASTAL PLAIN RPO | I-5986BA | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 144000 |  |  | 144000 | UNDER CONSTRUCTION.
HARNETT, WAKE | NC 55 | NCDOT | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 42 IN FUQUAY-VARINA. WIDEN TO MULTI-LANES. PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5, 6 | CAPITAL AREA MPO | R-5705
HAYWOOD | HAZELWOOD AVENUE (PLOTT CREEK ROAD) | NCDOT | HAZELWOOD AVENUE (PLOTT CREEK ROAD), RICHLAND CREEK BRIDGE TO WILL HYATT ROAD. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 14 | FRENCH BROAD RIVER MPO | EB-5859 | DIVISION 14 | [10 empty] | UNDER CONSTRUCTION
HAYWOOD | US 19 (SOCO ROAD) | NCDOT | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 14 | FRENCH BROAD RIVER MPO | EB-5926 | DIVISION 14 | BGANY, L |  |  |  |  | 2022 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION. $1.44M IN BGANY USED AS PART OF FUND SWAP; $80K ADDED AS ADMINISTRATIVE MODIFICATION.
HAYWOOD | TOWN OF CANTON | CANTON | CHAMPION DRIVE, NORTH CANTON ROAD TO THICKETY ROAD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 14 | FRENCH BROAD RIVER MPO | EB-5945 | DIVISION 14 | BGDA, L | 2023 | 384000 | [6 empty] | 384000 | RIGHT-OF-WAY IN PROGRESS.
HAYWOOD | US 23/US 74 | NCDOT | REPLACE BRIDGE 430155, AND BRIDGE 430158 OVER RICHLAND CREEK. | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | B-3186 | STATEWIDE MOBILITY | NHPB | 2021 | 800000 |  |  | 2024 | 6100000 |  |  | 6900000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH B-5898.
HAYWOOD | WAYNESVILLE (DEPOT STREET) | WAYNESVILLE | REPLACE BRIDGE 430262 OVER RICHLAND CREEK. | HIGHWAY | MUNICIPAL BRIDGE | 14 | FRENCH BROAD RIVER MPO | B-5013 | DIVISION 14 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY THE TOWN OF WAYNESVILLE - MUNICIPAL BRIDGE
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430236 OVER SR 1513. | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | B-5541 | HIGHWAY FUND | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY
HAYWOOD | US 23/ US 74 | NCDOT | REPLACE BRIDGE 430168 OVER US 19 AND US 23. | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | B-5898 | STATEWIDE MOBILITY | NHPB | 2021 | 150000 |  |  | 2024 | 3100000 |  |  | 3250000 | UNDER CONSTRUCTION. TO BE LET WITH B-3186.
HAYWOOD | SR 1216 (STEEL BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 430246 OVER WEST FORK PIGEON CREEK. | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | B-5920 | DIVISION 14 | BGOFF | 2023 | 30000 |  |  | 2024 | 640000 |  |  | 670000
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGES (430057, 430159, 430171, 430124, AND 430142) ON I-40 IN HAYWOOD COUNTY. | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | B-6054 | STATEWIDE MOBILITY
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430057 OVER US FOREST SERVICE ROAD/COLD SPRINGS CREEK AT HARMON'S DEN. | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | B-6054A | STATEWIDE MOBILITY | T |  |  |  |  | 2022 | 21788000 | 2020 | 500000 | 22288000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | B-6054B | STATEWIDE MOBILITY | T |  |  | 2022 | 5000 | 2023 | 25000000 | 2020 | 500000 | 25505000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | B-6054C | STATEWIDE MOBILITY | T | 2022 | 47000 | 2022 | 5000 | 2022 | 79725000 | 2020 | 2500000 | 82277000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | B-6054D | STATEWIDE MOBILITY | T | 2024 | 5000 | 2024 | 5000 | 2024 | 62100000 | 2021 | 500000 | 62610000
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | B-6054E | STATEWIDE MOBILITY | T | 2023 | 50000 | 2023 | 5000 | 2023 | 31100000 | 2021 | 2000000 | 33155000 | RIGHT-OF-WAY IN PROGRESS.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | HB-0002 | STATEWIDE MOBILITY | BFP | 2023 | 2000000 |  |  | 2024 | 17500000 |  |  | 19500000 | RIGHT-OF-WAY IN PROGRESS.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430239 OVER SR 1550 (INCINERATOR ROAD). | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | HB-0003 | STATEWIDE MOBILITY | BFP | 2023 | 1000000 |  |  | 2024 | 17100000 |  |  | 18100000
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430243 OVER NC 215 (CHAMPION DRIVE). | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | HB-0004 | STATEWIDE MOBILITY | BFP | 2023 | 1000000 |  |  | 2023 | 7300000 |  |  | 8300000
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGES 430205 AND 430208 OVER SR 1364 (COLEMAN MOUNTAIN ROAD). | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | HB-0005 | STATEWIDE MOBILITY | BFP | 2024 | 2000000 |  |  | 2030 | 9400000 |  |  | 11400000
HAYWOOD | US 74 | NCDOT | REPLACE BRIDGE 430126 OVER I-40. | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | HB-0006 | STATEWIDE MOBILITY | BFP | 2024 | 1000000 |  |  | 2030 | 9000000 |  |  | 10000000
HAYWOOD | US 19/23/74 | NCDOT | REPLACE BRIDGE 430133 OVER JONES COVE ROAD (SR 1527). | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | HB-0015 | HIGHWAY FUND | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY
HAYWOOD | SR 1876 (SONOMA ROAD) | NCDOT | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. | HIGHWAY | BRIDGES | 14 | FRENCH BROAD RIVER MPO | HB-0023 | DIVISION 14 | BGOFF | 2023 | 80000 | 2023 | 80000 | 2024 | 1600000 |  |  | 1760000 | RIGHT-OF-WAY IN PROGRESS.
HAYWOOD | SR 1355 (PANTHER CREEK ROAD) | NCDOT | REPLACE BRIDGE 430206 OVER FINES CREEK. | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | HB-0027 | DIVISION 14 | BGOFF | 2024 | 50000 | 2024 | 50000 | 2027 | 1000000 |  |  | 1100000
HAYWOOD | GREAT SMOKY MOUNTAINS NATIONAL PARK | NCDOT | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. | HIGHWAY | OTHER | 14 | LAND-OF-SKY RPO | HO-0003 | EXEMPT | CMAQ, L | [6 empty] | 2022 | 250000 | 250000
HAYWOOD | US 19 | NCDOT | HOLSTON VILLAGE ROAD AND SR 1197 (GOLF COURSE ROAD). UPGRADE INTERSECTIONS. | HIGHWAY | SAFETY | 14 | FRENCH BROAD RIVER MPO | HS-2014K | REGION G | HSIP |  |  |  |  | 2023 | 110000 |  |  | 110000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | MILE MARKER 27 TO MILE MARKER 34. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 14 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | I-5834 | [11 empty] | 6-13-2022: $2.566M IN NHPIM FUNDS SWITCHED WITH $2.566M IN BGDA AS PART OF FUND SWAP.
HAYWOOD | I-40 | NCDOT | MILE MARKER 27 TO MILE MARKER 30. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 14 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | I-5834A | STATEWIDE MOBILITY | BGDA, NHPIM |  |  |  |  | 2021 | 7299000 |  |  | 7299000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | MILE MARKER 30 TO MILE MARKER 34. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 14 | FRENCH BROAD RIVER MPO | I-5834B | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 13475000 |  |  | 13475000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | MILE MARKER 15 TO MILE MARKER 20.5. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 14 | LAND-OF-SKY RPO | I-5924 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 10900000 |  |  | 10900000
HAYWOOD | I-40 | NCDOT | MILE MARKER 34 TO BUNCOMBE COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 14 | FRENCH BROAD RIVER MPO | I-5928 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2028 | 8751000 |  |  | 8751000
HAYWOOD | I-40 | NCDOT | US 74 (SMOKY MOUNTAIN EXPRESSWAY) TO NC 215 (CHAMPION DRIVE). ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | I-6054A | NOT FUNDED | NHP | NOT FUNDED | 2700000 | NOT FUNDED | 500000 | NOT FUNDED | 57300000 |  |  | 60500000
HAYWOOD | US 276 (JONATHAN CREEK) | NCDOT | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO | R-5921 | DIVISION 14 | BGLT5 | 2023 | 6500000 | 2023 | 110000 | 2024 | 30000000 |  |  | 36610000 | RIGHT-OF-WAY IN PROGRESS.
HAYWOOD | US 23 BUSINESS (SOUTH MAIN STREET) | NCDOT | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-4712 | DIVISION 14 | T | 2027 | 25200000 | 2027 | 3800000 | 2030 | 20000000 |  |  | 49000000
HAYWOOD | US 276 (RUSS AVENUE) | NCDOT | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-5839 | DIVISION 14 | T | 2019 | 6830000 | 2020 | 750000 | 2024 | 24600000 | 2020 | 3330000 | 35510000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888.
HAYWOOD | US 23 BUSINESS | NCDOT | INTERSECTION OF US 23 BUSINESS (NORTH MAIN STREET) AND WALNUT STREET. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-5888 | DIVISION 14 | T |  |  |  |  | 2022 | 7022000 |  |  | 7022000 | UNDER CONSTRUCTION. TO BE LET WITH U-5839.
HAYWOOD | CANTON | NCDOT | NC 110 (PISGAH DRIVE) AT LOCUST STREET. IMPROVE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 14 | FRENCH BROAD RIVER MPO | U-6055 | EXEMPT | [10 empty] | UNDER CONSTRUCTION. STBGDA FUNDS ARE EXEMPT BECAUSE THEY ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE IS PAYING MATCH BECAUSE PROJECT CAME IN RANK ORDER OFF P3.0 PRIORITIZATION LIST
HAYWOOD | US 276 | NCDOT | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-6158 | DIVISION 14 | T | 2028 | 500000 | 2028 | 200000 | 2030 | 3101000 |  |  | 3801000
HAYWOOD | US 276 (RUSS AVENUE) | NCDOT | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-6159 | DIVISION 14 | BGANY | 2028 | 14500000 | 2028 | 2300000 | 2030 | 13401000 |  |  | 30201000
HAYWOOD | US 276 | NCDOT | CONSTRUCT LEFT TURN LANE 0.3 MILES SOUTH OF SR 1326 (BOB BOYD ROAD). | HIGHWAY | SAFETY | 14 | LAND-OF-SKY RPO | W-5814A | REGION G | HSIP |  |  |  |  | 2022 | 380000 |  |  | 380000 | UNDER CONSTRUCTION.
HAYWOOD | CITY OF ASHEVILLE | CITY OF ASHEVILLE | MOUNTAIN PROJECTS ( HAYWOOD COUNTY) DEVIATED FIXED ROUTE CAPITAL AND CARES FUNDS. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 14 | FRENCH BROAD RIVER MPO | TG-6788 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 448000 | 448000
HAYWOOD | MOUNTAIN PROJECTS, INC. | MOUNTAIN PROJECTS, INC. | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | LAND-OF-SKY RPO | TK-6149 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 932000 | 932000 | FUNDS AUTHORIZED IN PROGRESS
HAYWOOD, BUNCOMBE | I-40 | NCDOT | NC 215 (CHAMPION DRIVE) TO SR 1200 (WIGGINS ROAD). ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 13, 14 | FRENCH BROAD RIVER MPO | I-6054B | NOT FUNDED | NHP | NOT FUNDED | 5300000 | NOT FUNDED | 700000 | NOT FUNDED | 163500000 |  |  | 169500000
HAYWOOD, BUNCOMBE | US 19, US 23 | NCDOT | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13, 14 | FRENCH BROAD RIVER MPO | U-6048 | DIVISION 13, 14 | T | 2028 | 300000 | 2028 | 700000 | 2030 | 28201000 |  |  | 29201000
HAYWOOD, HENDERSON, JACKSON, POLK, TRANSYLVANIA | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS PRIMARY AND SECONDARY ROUTES. | HIGHWAY | SAFETY | 14 | FOOTHILLS RPO, FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO, SOUTHWESTERN RPO | HS-2014R | REGION G | HSIP |  |  |  |  | 2023 | 1225000 |  |  | 1225000 | UNDER CONSTRUCTION.
HAYWOOD, HENDERSON, MACON, POLK, SWAIN | VARIOUS | NCDOT | INSTALL SNOWPLOWABLE MARKERS AND PAVEMENT MARKINGS FOR WRONG WAY RAMP ARROWS ON VARIOUS FREEWAY RAMPS. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO | HS-2014C | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 50000 |  |  | 50000 | UNDER CONSTRUCTION.
HAYWOOD, JACKSON | US 74 | NCDOT | IMPROVE PAVEMENT FROM SR 1392 TO EAST OF SR 1388 AND FROM JACKSON COUNTY LINE TO BRIDGES 107 AND 110. | HIGHWAY | SAFETY | 14 | FRENCH BROAD RIVER MPO, SOUTHWESTERN RPO | HS-2014E | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 975000 |  |  | 975000 | UNDER CONSTRUCTION.
HAYWOOD, JACKSON | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | NCDOT | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO, SOUTHWESTERN RPO | U-6172 | DIVISION 14
HAYWOOD, JACKSON | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | NCDOT | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO, SOUTHWESTERN RPO | U-6172B | DIVISION 14 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 80000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 250000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2800000 |  |  | 3130000
HAYWOOD, POLK | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS SECONDARY ROUTES. | HIGHWAY | SAFETY | 14 | FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | HS-2014J | DIVISION 14 | HSIP |  |  |  |  | 2023 | 2570000 |  |  | 2570000 | UNDER CONSTRUCTION.
HAYWOOD, ROBESON | I-40 AND I-95 | NCDOT | I-40 FROM TENNESSEE STATE LINE TO MM 20 AND I-95 FROM EXIT 13 TO SOUTH OF PROPOSED I-295. IMPLEMENT SYSTEM TO PROVIDE REAL TIME ALERTS IN VEHICLES WHEN DRIVERS ENCOUNTER A ROAD ANOMALY REQUIRING THEM TO TAKE DRIVING ACTION. | HIGHWAY | OTHER | 6, 14 | LAND-OF-SKY RPO, LUMBER RIVER RPO | HO-0011 | STATEWIDE MOBILITY | DP, O | [6 empty] | 2024 | 1972000 | 1972000 | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH.
HAYWOOD, SWAIN | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | HIGHWAY | OTHER | 14 | LAND-OF-SKY RPO, SOUTHWESTERN RPO | C-5612 | EXEMPT | CMAQ, L | 2020 | 4000 |  |  | 2020 | 19000 | 2020 | 12000 | 35000
HENDERSON | ECUSTA RAIL-TRAIL | NCDOT | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 14 | FRENCH BROAD RIVER MPO | BL-0007 | DIVISION 14 | BGANY, BGDA, L, TADA |  |  |  |  | 2023 | 8685000 | 2022 | 1046000 | 9731000 | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021
HENDERSON | CLEAR CREEK GREENWAY/ HENDERSONVILLE | HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | BIKE/PED | LOCALLY SELECTED | 14 | FRENCH BROAD RIVER MPO | BL-0008 | DIVISION 14 | BGANY, BGDA, L |  |  |  |  | 2024 | 2952000 | 2022 | 1403000 | 4355000 | $78K IN BGANY USED AS PART OF FUND SWAP
HENDERSON | ECUSTA TRAIL | HENDERSON COUNTY | US 64 TO TRANSYLVANIA COUNTY LINE. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | BL-0078 | DIVISION 14 | BGDA, L |  |  |  |  | 2027 | 13083000 |  |  | 13083000
HENDERSON | BLYTHE STREET | NCDOT | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | EB-5860 | DIVISION 14 | L, TAANY | 2025 | 45000 | 2025 | 35000 | 2026 | 1300000 | 2024 | 120000 | 1500000
HENDERSON | TOWN OF MILLS RIVER | MILLS RIVER | NC 280, FRENCH BROAD RIVER TO HAYWOOD ROAD (NC 191). CONSTRUCT MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 14 | FRENCH BROAD RIVER MPO | EB-5946 | DIVISION 14 | L, TADA | [6 empty] | 2026 | 375000 | 375000
HENDERSON | GROVE STREET | NCDOT | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | EB-5963 | DIVISION 14 | L, TAANY | 2025 | 800000 | 2025 | 95000 | 2026 | 900000 | 2024 | 157000 | 1952000
HENDERSON | TRACY GROVE ROAD | NCDOT | REPLACE BRIDGE 440350 OVER DEVILS FORK CREEK. | HIGHWAY | MUNICIPAL BRIDGE | 14 | FRENCH BROAD RIVER MPO | B-5929 | DIVISION 14 | BGOFF, L |  |  |  |  | 2023 | 1150000 |  |  | 1150000 | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE
HENDERSON | SR 1970 (COMMERCIAL BLVD) | NCDOT | CONSTRUCT ROADWAY EXTENSION TO INDUSTRIAL PARK. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | FRENCH BROAD RIVER MPO | HA-0003 | EXEMPT | ADHSL | 2021 | 70000 |  |  | 2021 | 1830000 |  |  | 1900000 | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000
HENDERSON | US 25 BUSINESS (ASHEVILLE HIGHWAY) | NCDOT | HENDERSONVILLE CITY LIMIT TO SR 1534. INSTALL RUMBLE STRIPS WITH LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 14 | FRENCH BROAD RIVER MPO | HS-2014I | REGION G | HSIP |  |  |  |  | 2023 | 140000 |  |  | 140000
HENDERSON | US 64 | NCDOT | SR 1574 (FRUITLAND ROAD), SR 1006 (HOWARD GAP ROAD), SR 1519 (THOMPSON STREET)/ SR 1751 (FREEMAN STREET), SR 1749 (ORR'S CAMP ROAD)/ SR 1634 (CAROLINA AVENUE). UPGRADE INTERSECTIONS. | HIGHWAY | SAFETY | 14 | FRENCH BROAD RIVER MPO | HS-2014L | REGION G | HSIP |  |  |  |  | 2023 | 570000 |  |  | 570000 | UNDER CONSTRUCTION.
HENDERSON | US 64 (7TH AVENUE) | NCDOT | NORTH GROVE STREET/ 7TH AVENUE. UPGRADE INTERSECTION. | HIGHWAY | SAFETY | 14 | FRENCH BROAD RIVER MPO | HS-2014N | REGION G | HSIP |  |  |  |  | 2023 | 240000 |  |  | 240000
HENDERSON | US 64 | NCDOT | SR 1586 (SOUTH MILLS GAP ROAD)/ TUTTLE ROAD. INSTALL TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 14 | FRENCH BROAD RIVER MPO | HS-2014O | REGION G | HSIP |  |  |  |  | 2023 | 55000 |  |  | 55000
HENDERSON | US 64, US 25 BUSINESS | NCDOT | UPGRADE SIGNAL SYSTEM AT 33 INTERSECTIONS ALONG US 64 AND US 25 BUSINESS. | HIGHWAY | SAFETY | 14 | FRENCH BROAD RIVER MPO | HS-2014Q | REGION G | HSIP |  |  |  |  | 2023 | 225000 |  |  | 225000 | UNDER CONSTRUCTION.
HENDERSON | I-26 | NCDOT | US 25 TO US 64 | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | I-4400A | NOT FUNDED | NHP | NOT FUNDED | 1600000 | NOT FUNDED | 500000 | NOT FUNDED | 114800000 |  |  | 116900000
HENDERSON | I-26 | NCDOT | US 64 INTERCHANGE IMPROVEMENTS | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | I-4400BA | DIVISION 14 | T |  |  | 2027 | 400000 | 2029 | 29100000 |  |  | 29500000
HENDERSON | I-26 | NCDOT | US 64 TO US 25 BUSINESS | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | I-4400BB | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 52752000 |  |  | 52752000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $43,911,307 FOR CONSTRUCTION, PAYBACK FY 2019-2033
HENDERSON | I-26 | NCDOT | MILE MARKER 50 TO POLK COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 14 | FRENCH BROAD RIVER MPO | I-5925 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 15199000 |  |  | 15199000
HENDERSON | NC 191 | NCDOT | US 25 IN HENDERSONVILLE TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | R-2588
HENDERSON | NC 191 | NCDOT | US 25 TO SR 1381 (MOUNTAIN ROAD). | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | R-2588A | NOT FUNDED | BGANY | NOT FUNDED | 15200000 | NOT FUNDED | 1800000 | NOT FUNDED | 18800000 |  |  | 35800000
HENDERSON | NC 191 | NCDOT | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | R-2588B | DIVISION 14 | NHP, T | 2021 | 9500000 | 2022 | 15500000 | 2025 | 117686000 |  |  | 142686000 | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). BUILD NC BONDS: $17.7M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (YR 10 / 2028 SALE).
HENDERSON | SR 1127 (KANUGA ROAD) | NCDOT | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | R-5748 | DIVISION 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22099000 |  |  | 52199000
HENDERSON | SR 1690 (BROADPOINTE DRIVE) | NCDOT | IMPROVE EXISTING SR 1690 (BROADPOINTE DRIVE) TO 24 FEET PAVED ROADWAY AND REPLACE BRIDGE 440107. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | FRENCH BROAD RIVER MPO | R-5771 | EXEMPT | [10 empty] | ARC PROJECT NO. 18340 - UNDER CONSTRUCTION
HENDERSON | NC 225 SR 1164 (ERKWOOD DRIVE) | NCDOT | NC 225/SR 1164 (ERKWOOD DRIVE)/SR 1779(SHEPHERD STREET) IN HENDERSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | TRANSITION | 14 | FRENCH BROAD RIVER MPO | U-5105 | PRE-STI (TRANSITION) | [10 empty] | DIVISION PROJECT - UNDER CONSTRUCTION
HENDERSON | US 64 | NCDOT | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-5783 | REGION G | T | 2022 | 17400000 | 2022 | 3900000 | 2024 | 20198000 |  |  | 41498000 | RIGHT-OF-WAY IN PROGRESS.
HENDERSON | SR 1547 (OLD AIRPORT ROAD) | NCDOT | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-5840 | DIVISION 14 | T | 2020 | 855000 |  |  | 2020 | 12150000 | 2020 | 1575000 | 14580000 | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE).
HENDERSON | SR 1170 (WHITE STREET) | NCDOT | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-5886 | DIVISION 14 | T | 2023 | 18700000 | 2023 | 2600000 | 2026 | 15200000 |  |  | 36500000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049.
HENDERSON | SR 1783 (HIGHLAND LAKE ROAD) | NCDOT | NC 225 TO US 176. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-5887 | DIVISION 14 | T | 2020 | 2295000 |  |  | 2021 | 7676000 |  |  | 9971000 | UNDER CONSTRUCTION.
HENDERSON | NC 225 (SOUTH MAIN STREET) | NCDOT | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-6049 | REGION G | T | 2023 | 3400000 | 2023 | 400000 | 2026 | 4000000 |  |  | 7800000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886
HENDERSON | NC 280 (BOYLSTON HIGHWAY) | NCDOT | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 14 | FRENCH BROAD RIVER MPO | U-6124 | NOT FUNDED | NHP | NOT FUNDED | 3300000 | NOT FUNDED | 1800000 | NOT FUNDED | 23000000 |  |  | 28100000
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | REPLACEMENT TRANSIT VEHICLE ACQUISITION | PUBLIC TRANSIT | CAPITAL (NON-STI) | 14 | FRENCH BROAD RIVER MPO | TA-5229 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 60000 | 60000
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | FRENCH BROAD RIVER MPO | TG-4951 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 1921000 | 1921000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | CITY OF ASHEVILLE | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 14 | FRENCH BROAD RIVER MPO | TG-6143 | PUBLIC TRANSIT | 5307, 5311, L | [6 empty] | 2021 | 202000 | 202000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | TRANSIT ROUTINE CAPITAL COST OF CONTRACTING | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 14 | FRENCH BROAD RIVER MPO | TG-6181 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2856000 | 2856000
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | FRENCH BROAD RIVER MPO | TK-5176 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 540000 | 540000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 14 | FRENCH BROAD RIVER MPO | TO-6106 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 224000 | 224000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 14 | FRENCH BROAD RIVER MPO | TS-5101 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 11000 | 11000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | PROGRAM SUPPORT. | PUBLIC TRANSIT | PLANNING | 14 | FRENCH BROAD RIVER MPO | TU-0010 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 600000 | 600000
HENDERSON, BUNCOMBE | I-26 | NCDOT | US 25 TO NC 280. WIDEN TO ADD ADDITIONAL LANES. | HIGHWAY | STI (PRIORITIZATION) | 13, 14 | FRENCH BROAD RIVER MPO | I-4400
HENDERSON, BUNCOMBE | I-26 | NCDOT | US 25 BUSINESS TO NC 280 | HIGHWAY | STI (PRIORITIZATION) | 13, 14 | FRENCH BROAD RIVER MPO | I-4400C | REGION G | NHP |  |  |  |  | 2019 | 61776000 |  |  | 61776000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035
HENDERSON, TRANSYLVANIA | ECUSTA TRAIL | NCDOT | BREVARD BIKE PATH IN BREVARD TO KANUGA ROAD IN HENDERSONVILLE. CONSTRUCT MULTIUSE PATH. | BIKE/PED | LOCALLY SELECTED | 14 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | EB-6037B | DIVISION 14 | L, TAANY | 2021 | 8000000 | [6 empty] | 8000000 | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE.
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | TRI-COUNTY AIRPORT (ASJ) | RUNWAY EXTENSION. | AVIATION | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | AV-5778 | DIVISION 1 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 |  |  | 1700000
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | TRI-COUNTY AIRPORT (ASJ) | CONSTRUCT ACCESS ROAD TO T-HANGARS. | AVIATION | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | AV-5878 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 2200000 |  |  | 2200000
HERTFORD | US 13/NC 11 | NCDOT | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5311
HERTFORD | US 13/NC 11 | NCDOT | WEST OF MODLIN ROAD TO EAST OF NC 11/SR 1213 (OLD NC 11 ROAD). CONSTRUCT GRADE SEPARATION AT SR 1130 (MODLIN ROAD) AND INTERCHANGE AT OLD NC 11/SR 1213 (OLD NC 11 ROAD). | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5311A | STATEWIDE MOBILITY | [10 empty] | COMPLETED.
HERTFORD | US 13/NC 11 | NCDOT | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5311B | REGION A | T | 2028 | 6300000 | 2028 | 1200000 | 2031 | 101401000 |  |  | 108901000
HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | NCDOT | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5796 | REGION A | T | 2024 | 2576000 | 2024 | 1570000 | 2025 | 13735000 |  |  | 17881000 | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
HERTFORD | NC 461 | NCDOT | NC 45 TO END OF STATE MAINTENANCE. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5811 | DIVISION 1 | T |  |  |  |  | 2023 | 5252000 |  |  | 5252000 | UNDER CONSTRUCTION.
HERTFORD | SR 1409 (HALL SIDING ROAD) | NCDOT | NCVA CROSSING 642347G IN AHOSKIE. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 1 | PEANUT BELT RPO | RX-2001A | DIVISION 1 | HSIP |  |  |  |  | 2023 | 355000 |  |  | 355000 | UNDER CONSTRUCTION.
HOKE | SR 1203 (TURNPIKE ROAD) | NCDOT | REPLACE BRIDGE 460008 OVER LUMBER RIVER. | HIGHWAY | BRIDGES | 8 | LUMBER RIVER RPO | B-4967 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION
HOKE | SR 1406 (ROCKFISH ROAD) | NCDOT | REPLACE BRIDGE 460057 OVER PUPPY CREEK. | HIGHWAY | BRIDGES | 8 | FAYETTEVILLE AREA MPO | B-5755 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION
HOKE | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | NCDOT | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | FAYETTEVILLE AREA MPO | U-5753 | DIVISION 8 | BGANY, T | 2022 | 42100000 | 2022 | 5000000 | 2026 | 48270000 |  |  | 95370000 | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS
HOKE | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | NCDOT | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | FAYETTEVILLE AREA MPO | U-5857 | DIVISION 8 | T | 2027 | 18000000 | 2027 | 5700000 | 2029 | 46001000 |  |  | 69701000 | COORDINATE WITH U-5753 AND U-5798.
HOKE | HOKE COUNTY | HOKE COUNTY | OPERATING ASSISTANCE FY20-21 | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 8 | FAYETTEVILLE AREA MPO | TO-6157 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 932000 | 932000
HOKE | SR 1003 (ARABIA ROAD) | NCDOT | AR CROSSING 847348H IN DUNDARRACH. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 8 | LUMBER RIVER RPO | RX-2008D | DIVISION 8 | RR |  |  |  |  | 2024 | 345000 |  |  | 345000
HOKE, MOORE | NC 211 | NCDOT | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO A FOUR LANE DIVIDED FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO | R-5709 | REGION E | T | 2021 | 59423000 | 2021 | 4976000 | 2024 | 166299000 |  |  | 230698000 | RIGHT-OF-WAY IN PROGRESS
HOKE, MOORE | NC 211 | NCDOT | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. CLEARING, GRUBBING, AND EROSION CONTROL. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO | R-5709A | REGION E | T |  |  |  |  | 2022 | 17625000 |  |  | 17625000 | UNDER CONSTRUCTION
HOKE, SCOTLAND | US 401 | NCDOT | US 401 BUSINESS NORTH OF LAURINBURG TO US 401 BUSINESS EAST OF RAEFORD. CONSTRUCT PASSING LANES, TURN LANES, AND PAVED SHOULDERS. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | R-3333 | NOT FUNDED | NHP | NOT FUNDED | 273000 | NOT FUNDED | 15507000 | NOT FUNDED | 38800000 |  |  | 54580000
HYDE | HYDE COUNTY AIRPORT (7W6) | HYDE COUNTY AIRPORT (7W6) | EXTEND RUNWAY TO 5000 FEET. | AVIATION | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | AV-5812 | DIVISION 1 | T |  |  |  |  | 2023 | 1800000 |  |  | 1800000 | UNDER CONSTRUCTION.
HYDE | NC 45 | NCDOT | SWAN QUARTER VISITORS CENTER. REPLACEMENT. | FERRY | TRANSITION | 1 | ALBEMARLE RPO | F-5003 | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
HYDE | NC 12 | NCDOT | OCRACOKE PEDESTRIAN WAITING AND ACCESS ACCOMMODATIONS | FERRY | OTHER | 1 | ALBEMARLE RPO | F-5702B | DIVISION 1 | [10 empty] | COMPLETED.
HYDE | HYDE COUNTY NON-PROFIT | HYDE COUNTY NON-PROFIT | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1 | ALBEMARLE RPO | TK-6135 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 400000 | 400000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | STATESVILLE REGIONAL AIRPORT (SVH) | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. | AVIATION | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | AV-5896 | DIVISION 12 | T | 2026 | 5610000 |  |  | 2027 | 3725000 |  |  | 9335000
IREDELL | NC 152 (NORTH MAIN STREET) | MOORESVILLE | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | BL-0009 | DIVISION 12 | BGDA, L | 2025 | 617000 |  |  | 2027 | 732000 | 2024 | 138000 | 1487000
IREDELL | MOORE AVENUE | MOORESVILLE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | BL-0013 | DIVISION 12 | BGDA, L |  |  |  |  | 2025 | 2000000 |  |  | 2000000
IREDELL | MOORESVILLE | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. | BIKE/PED | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | BL-0055 | DIVISION 12 | BGDA, L |  |  |  |  | 2026 | 2081000 | 2025 | 363000 | 2444000
IREDELL | SR 2162 (WHITE OAK ROAD) MAPLE AVENUE McNEELY AVEN | MOORESVILLE | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | BIKE/PED | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | BL-0056 | DIVISION 12 | BGDA, L | 2025 | 104000 |  |  | 2026 | 1972000 | 2024 | 563000 | 2639000
IREDELL | NC 115 | MOORESVILLE | FAIRVIEW ROAD TO WATERLYNN ROAD. INSTALL SHARED USE PATH. | BIKE/PED | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | BL-0082 | REGION F | L, TADA | 2027 | 700000 |  |  | 2029 | 3829000 | 2025 | 344000 | 4873000
IREDELL | MOORESVILLE | MOORESVILLE | BELLINGHAM PARK GREENWAY EXTENSION TO JOHNSON DAIRY ROAD. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | EB-5787 | DIVISION 12 | BGDA, L |  |  |  |  | 2023 | 4444000 |  |  | 4444000 | UNDER CONSTRUCTION.
IREDELL | STATESVILLE | STATESVILLE | SHELTON AVENUE MULTI-USE PATH, GARNER BAGNAL BOULEVARD TO AMITY HILL ROAD. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | EB-5788 | DIVISION 12 | BGDA, L | 2023 | 251000 | [6 empty] | 251000 | RIGHT-OF-WAY IN PROGRESS
IREDELL | STATESVILLE | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). | BIKE/PED | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | EB-5818 | DIVISION 12 | BGDA, L |  |  |  |  | 2023 | 1670000 |  |  | 1670000 | UNDER CONSTRUCTION.
IREDELL | TROUTMAN | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | BIKE/PED | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | EB-5930 | DIVISION 12 | L, TADA | 2022 | 199000 |  |  | 2023 | 1623000 | 2021 | 312000 | 2134000
IREDELL | TROUTMAN | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | BIKE/PED | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | EB-5932 | DIVISION 12 | L, TADA | 2022 | 217000 |  |  | 2023 | 1250000 | 2021 | 122000 | 1589000
IREDELL | SR 2402 (HOOVER ROAD) | NCDOT | REPLACE BRIDGE 480020 OVER I-L CREEK. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | B-5843 | DIVISION 12 | BGOFF | 2023 | 67000 |  |  | 2030 | 675000 |  |  | 742000
IREDELL | SR 1892 (JENNINGS ROAD) | NCDOT | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | B-5846 | DIVISION 12 | BGOFF | 2022 | 85000 | 2022 | 325000 | 2023 | 3300000 |  |  | 3710000 | RIGHT-OF-WAY IN PROGRESS.
IREDELL | SR 1639 (MEACHAM RD) | NCDOT | REPLACE BRIDGE 480118 OVER I-40. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | BR-0025 | DIVISION 12 | BFP |  |  |  |  | 2029 | 5500000 |  |  | 5500000
IREDELL | SR 1577 | NCDOT | REPLACE BRIDGE 480131 OVER UT TO SNOW CREEK. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | BR-0107 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 800000 |  |  | 800000 | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT.
IREDELL | SR 1601 (BRANTON ROAD) | NCDOT | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | BR-0114 | DIVISION 12 | DP, HFB | 2020 | 150000 |  |  | 2021 | 1150000 |  |  | 1300000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
IREDELL | SR 1595 (COOLBROOK ROAD) | NCDOT | REPLACE BRIDGE 480166 ON SR 1595 OVER ROCKY CREEK. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | BR-0115 | DIVISION 12 | DP, HFB | 2020 | 170000 |  |  | 2021 | 1600000 |  |  | 1770000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
IREDELL | SR 1892 | NCDOT | REPLACE BRIDGE 480212 OVER PATTERSON CREEK. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | BR-0202 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1250000 |  |  | 1250000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.49
IREDELL | SR 1896 | NCDOT | REPLACE BRIDGE 480214 OVER PATTERSON CREEK | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | BR-0203 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.50
IREDELL | SR 1892 | NCDOT | REPLACE BRIDGE 480219 OVER OLIN CREEK. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | BR-0204 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 900000 |  |  | 900000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.51
IREDELL | MOORESVILLE | MOORESVILLE | NC 115 AND NC 150 IN MOORESVILLE. CONSTRUCT SOUTHBOUND NC 115 RIGHT TURN LANE AT NC 150 AND WESTBOUND NC 150 SHARED THROUGH-RIGHT LANE AT NC 115. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | C-5200 | EXEMPT | BGDA, L |  |  |  |  | 2020 | 1514000 |  |  | 1514000 | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES.
IREDELL | MOORESVILLE | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | C-5529 | EXEMPT | BGDA, L |  |  |  |  | 2023 | 1128000 | 2023 | 259000 | 1387000 | UNDER CONSTRUCTION
IREDELL | MOORESVILLE | MOORESVILLE | KISTLER FARM-BRIARCLIFF-BELLINGHAM-WHITE OAK SIDEWALK NETWORK IN MOORESVILLE. CONSTRUCT SIDEWALKS IN VARIOUS LOCATIONS. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | C-5531 | EXEMPT | BGDA, L |  |  |  |  | 2020 | 801000 |  |  | 801000 | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES.
IREDELL | MOORESVILLE | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | C-5701 | EXEMPT | BA, BGDA, CMAQ, L | 2020 | 324000 |  |  | 2020 | 3236000 |  |  | 3560000 | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
IREDELL | I-40 | NCDOT | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | HB-0018 | STATEWIDE MOBILITY | BFP | 2022 | 700000 | 2022 | 700000 | 2026 | 40600000 |  |  | 42000000
IREDELL | SR 1004 (HUDSON CHAPEL ROAD) | NCDOT | REPLACE BRIDGE 480081 CATAWBA RIVER. | HIGHWAY | BRIDGES | 12 | CHARLOTTE REGIONAL TPO | HB-0032 | DIVISION 12 | BGOFF | 2025 | 775000 | 2025 | 775000 | 2027 | 15500000 |  |  | 17050000
IREDELL | VARIOUS | NCDOT | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING AND PAVEMENT RESTRIPING. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | HL-0037 | DIVISION 12 | BGDACV |  |  |  |  | 2023 | 975000 |  |  | 975000
IREDELL | LANGTREE ROAD | MOORESVILLE | PIN OAK LANE TO MOUNT MOURNE LOOP. WIDEN ROADWAY. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | HL-0114 | DIVISION 12 | BGDA, L | [6 empty] | 2024 | 1091000 | 1091000
IREDELL | SR 1125 (SHEARERS ROAD) | NCDOT | SR 1147 (ROCKY RIVER ROAD) INTERSECTION. INSTALL TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 12 | CHARLOTTE REGIONAL TPO | HS-2012C | DIVISION 12 | HSIP |  |  |  |  | 2022 | 190000 | 2022 | 20000 | 210000 | UNDER CONSTRUCTION.
IREDELL | I-40/I-77 | NCDOT | STATESVILLE, MODIFICATION OF I-40/I-77 INTERCHANGE AREA. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | I-3819 | [11 empty] | GARVEE BOND FUNDING - SEGMENT A: $10M FOR CONSTRUCTION, PAYBACK FY 2012-2023
IREDELL | I-40/I-77 | NCDOT | INITIAL I-40/I-77 INTERCHANGE IMPROVEMENTS | HIGHWAY | PRE-STI (HISTORIC) | 12 | CHARLOTTE REGIONAL TPO | I-3819A | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2012 | 4388000 |  |  | 4388000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
IREDELL | I-40/I-77 | NCDOT | FINAL I-40/I-77 INTERCHANGE IMPROVEMENTS | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | I-3819B | STATEWIDE MOBILITY | T |  |  |  |  | 2019 | 358665000 |  |  | 358665000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
IREDELL | I-77 | NCDOT | MILE MARKER 57.83 TO MILE POST 61.74. PAVEMENT REHABILITATION. | HIGHWAY | PRE-STI (HISTORIC) | 12 | CHARLOTTE REGIONAL TPO | I-5106 | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 439000 |  |  | 439000 | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020
IREDELL | I-77 | NCDOT | EXIT 45 TO EXIT 54, EXCLUDING PROJECT AREA FOR I-3819 A. PAVEMENT REHABILITATION. | HIGHWAY | TRANSITION | 12 | CHARLOTTE REGIONAL TPO | I-5606 | [11 empty] | COMPLETE
IREDELL | I-40 | NCDOT | SR 2158 (OLD MOCKSVILLE ROAD) TO DAVIE COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 12 | CHARLOTTE REGIONAL TPO | I-5805 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 70500000 |  |  | 70500000
IREDELL | I-77 | NCDOT | MILEMARKER 36.5 TO MILEMARKER 50.0. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 12 | CHARLOTTE REGIONAL TPO | I-5918 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 24400000 |  |  | 24400000
IREDELL | I-77 | NCDOT | MILEMARKER 53.7 TO MILEMARKER 56.8. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 12 | CHARLOTTE REGIONAL TPO | I-5919 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 10500000 |  |  | 10500000
IREDELL | I-77 | NCDOT | MILE MARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 12 | CHARLOTTE REGIONAL TPO | I-5920 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2028 | 19279000 |  |  | 19279000
IREDELL | I-77 | NCDOT | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | I-5962 | STATEWIDE MOBILITY | NHP, O | 2027 | 3000000 | 2027 | 500000 | 2029 | 36101000 |  |  | 39601000 | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE
IREDELL | NC 150 | NCDOT | GOOD LUCK LANE TO MORRISON PLANTATION PARKWAY. EXTEND EASTBOUND RIGHT AND THROUGH LANE. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | R-2307BA | REGION F | T |  |  |  |  | 2023 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION.
IREDELL | US 21 - NC 115 | NCDOT | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | R-2522 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16800000 |  |  | 34800000
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | NCDOT | SR 1177 (CHUCKWOOD ROAD) TO US 21. WIDEN TO MULTI-LANES WITH INTERCHANGE AT I-77. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | R-3833 | [11 empty] | $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE.
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | NCDOT | SR 1177 (CHUCKWOOD ROAD) TO SR 1109 (CENTRE CHURCH ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 12 | CHARLOTTE REGIONAL TPO | R-3833A | [11 empty] | COMPLETE
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | NCDOT | SR 1109 (CENTRE CHURCH ROAD) TO I-77 | HIGHWAY | PRE-STI (HISTORIC) | 12 | CHARLOTTE REGIONAL TPO | R-3833B | [11 empty] | COMPLETE
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | NCDOT | I-77 TO US 21 | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | R-3833C | DIVISION 12 | L, T | 2019 | 5050000 |  |  | 2024 | 32470000 |  |  | 37520000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE).
IREDELL | SR 1206 (ALCOVE ROAD) | NCDOT | RELOCATION OF ROADWAY IN MOORESVILLE. | HIGHWAY | PRE-STI (HISTORIC) | 12 | CHARLOTTE REGIONAL TPO | R-4757 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY - PLANNING BY TOWN OF MOORESVILLE
IREDELL | SR 1109 (WILLIAMSON ROAD) | NCDOT | I-77 TO NC 150. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | R-5100 | [11 empty] | COORDINATE WITH U-5817.
IREDELL | SR 1109 (WILLIAMSON ROAD) | NCDOT | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | R-5100A | DIVISION 12 | T | 2020 | 8850000 | 2022 | 5300000 | 2025 | 39299000 | 2020 | 600000 | 54049000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE).
IREDELL | SR 1109 (WILLIAMSON ROAD) | NCDOT | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | R-5100B | DIVISION 12 | T | 2019 | 9515000 | 2022 | 1300000 | 2025 | 5900000 |  |  | 16715000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE).
IREDELL | US 21 | NCDOT | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | R-5711 | REGION F | T |  |  |  |  | 2025 | 2950000 |  |  | 2950000 | RIGHT-OF-WAY IN PROGRESS
IREDELL | NC 115 | NCDOT | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-5779 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22099000 |  |  | 37599000
IREDELL | NC 150 | NCDOT | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-5780 | REGION F | T | 2019 | 550000 |  |  | 2024 | 1450000 |  |  | 2000000 | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U.
IREDELL | US 21 | NCDOT | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-5799 | REGION F | T | 2020 | 22360000 | 2020 | 1600000 | 2024 | 20200000 | 2020 | 2265000 | 46425000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE)
IREDELL | SR 1305 (OATES ROAD - MIDNIGHT LANE) | NCDOT | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-5816 | DIVISION 12 | T | 2026 | 12600000 | 2026 | 3200000 | 2029 | 29601000 |  |  | 45401000
IREDELL | SR 1246 (FAIRVIEW ROAD) | NCDOT | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-5817 | DIVISION 12 | BA, BGANY, BGDA | 2019 | 5800000 | 2019 | 1900000 | 2025 | 17700000 |  |  | 25400000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100.
IREDELL | NC 150 (OAK RIDGE FARM HIGHWAY) | NCDOT | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-5960 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27000000 |  |  | 49500000
IREDELL | US 64 (DAVIE AVENUE) | NCDOT | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-5964 | REGION F | BGANY | 2024 | 11000000 | 2024 | 700000 | 2026 | 3298000 |  |  | 14998000
IREDELL | US 21 (CHARLOTTE HIGHWAY) | NCDOT | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-6037 | DIVISION 12 | T | 2027 | 15500000 | 2027 | 4600000 | 2030 | 23800000 |  |  | 43900000
IREDELL | SR 2321 (EAST BROAD STREET) | NCDOT | VINE STREET TO SR 2422 (SIGNAL HILL DRIVE). UPGRADE ROADWAY AND IMPLEMENT ACCESS MANAGEMENT SOLUTIONS. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-6039 | DIVISION 12 | T |  |  |  |  | 2019 | 5350000 |  |  | 5350000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B
IREDELL | STATESVILLE | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | U-6054 | DIVISION 12 | BGANY, BGDA, L | 2023 | 1540000 |  |  | 2024 | 2218000 | 2020 | 326000 | 4084000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS.
IREDELL | NC 3 | NCDOT | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-6145 | NOT FUNDED | T | NOT FUNDED | 5200000 | NOT FUNDED | 3300000 | NOT FUNDED | 28801000 |  |  | 37301000
IREDELL | STATESVILLE | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | U-6153 | DIVISION 12 | BA, O, T |  |  |  |  | 2024 | 4648000 | 2020 | 452000 | 5100000 | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT.
IREDELL | SR 1005 (OLD MOUNTAIN ROAD) | NCDOT | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO | U-6175 | NOT FUNDED | BGLT5 | NOT FUNDED | 21800000 | NOT FUNDED | 3540000 | NOT FUNDED | 28602000 |  |  | 53942000
IREDELL | MOORESVILLE | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | U-6239 | EXEMPT | DP, L | 2022 | 6149000 |  |  | 2023 | 15056000 | 2021 | 525000 | 21730000 | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE
IREDELL | NC 115 | MOORESVILLE | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | U-6249 | EXEMPT | BGDA, L | 2023 | 500000 |  |  | 2025 | 4006000 | 2021 | 560000 | 5066000 | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT
IREDELL | SR 1302 (PERTH ROAD) | NCDOT | SR 1302 (PERTH ROAD) AT SR 1378 (JUDAS ROAD) AND SR1302 (CORNELIUS ROAD) INTERSECTIONS. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | TRANSITION | 12 | CHARLOTTE REGIONAL TPO | W-5212J | DIVISION 12 | BGDA, S(M) | [6 empty] | 2020 | 356000 | 356000 | $178K IN BGANY USED AS PART OF FUND SWAP.
IREDELL | SR 1302 (PERTH ROAD) | NCDOT | INSTALL SIGNAL AT SR 1302 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | HIGHWAY | SAFETY | 12 | CHARLOTTE REGIONAL TPO | W-5212JA | DIVISION 12 | BGANY, BGDA, S(M) | 2020 | 25000 |  |  | 2022 | 125000 |  |  | 150000 | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION.
IREDELL | SR 1303 (PERTH ROAD) | NCDOT | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | HIGHWAY | SAFETY | 12 | CHARLOTTE REGIONAL TPO | W-5212JB | DIVISION 12 | BGANY, S(M) | 2022 | 125000 |  |  | 2023 | 450000 |  |  | 575000 | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP.
IREDELL | NC 150 | NCDOT | NC 150 AT NC 152 (WESTERN INTERSECTION) | HIGHWAY | SAFETY | 12 | CHARLOTTE REGIONAL TPO | W-5601U | REGION F | HSIP | 2022 | 472000 |  |  | 2024 | 1150000 |  |  | 1622000 | RIGHT-OF-WAY IN PROGRESS.
IREDELL | IREDELL COUNTY | IREDELL COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | CHARLOTTE REGIONAL TPO | TK-6179 | PUBLIC TRANSIT | 5311 | [6 empty] | 2020 | 1040000 | 1040000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | IREDELL COUNTY | IREDELL COUNTY | OPERATING ASSISTANCE FOR THE IREDELL COUNTY AREA TRANSPORTATION SYSTEM (ICATS) | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 12 | CHARLOTTE REGIONAL TPO | TO-5149 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 687000 | 687000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | IREDELL COUNTY | IREDELL COUNTY | OPERATION FOR FY20-21 | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 12 | CHARLOTTE REGIONAL TPO | TO-6158 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2372000 | 2372000 | ADDING FUNDS FOR FFY2020
IREDELL | SR 2395 (MAZEPPA ROAD) | NCDOT | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | RAIL | LOCALLY SELECTED | 12 | CHARLOTTE REGIONAL TPO | RL-0001 | EXEMPT | BGDA, DP, L | 2023 | 320000 |  |  | 2025 | 12633000 | 2021 | 1298000 | 14251000 | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
IREDELL, CATAWBA | I-40 | NCDOT | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | I-5915
IREDELL, CATAWBA | I-40 | NCDOT | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | I-5915A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
IREDELL, CATAWBA | I-40 | NCDOT | BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | I-5915B | STATEWIDE MOBILITY | BGDA, NHPIM, S(M) |  |  |  |  | 2023 | 11840000 |  |  | 11840000 | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION.
IREDELL, CATAWBA | NC 150 | NCDOT | EAST OF SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | R-2307B | REGION F | NHP, S(M) |  |  |  |  | 2025 | 164500000 |  |  | 164500000 | RIGHT-OF-WAY IN PROGRESS. $5M IN STBG-DA FUNDS SWITCHED WITH $5M NHP AS PART OF FUND SWAP.
IREDELL, CATAWBA | VARIOUS | NCDOT | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. | HIGHWAY | SAFETY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | W-5212DIV | DIVISION 12 | HSIP | 2020 | 50000 |  |  | 2020 | 2500000 |  |  | 2550000 | IN PROGRESS.
IREDELL, MECKLENBURG | I-77 | NCDOT | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150. WIDEN AND RECONSTRUCT ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 10, 12 | CHARLOTTE REGIONAL TPO | I-4750 | [11 empty] | FUNDING FOR I-4750 AA INCLUDED IN I-5405
IREDELL, MECKLENBURG | I-77 | NCDOT | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150 (EXIT 36). CONSTRUCT HIGH OCCUPANCY/TOLL (HOT) LANES. | HIGHWAY | TRANSITION | 10, 12 | CHARLOTTE REGIONAL TPO | I-4750AA | [11 empty] | COMPLETE - UNDER CONSTRUCTION WITH PROJECT I-5405
IREDELL, MECKLENBURG | I-77 | NCDOT | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150 (EXIT 36). CONSTRUCT ONE ADDITIONAL LANE IN EACH DIRECTION. | HIGHWAY | STI (PRIORITIZATION) | 10, 12 | CHARLOTTE REGIONAL TPO | I-4750AB | NOT FUNDED | NHP | NOT FUNDED | 10500000 | NOT FUNDED | 675000 | NOT FUNDED | 133000000 |  |  | 144175000
IREDELL, MECKLENBURG | ICATS INTERCOUNTY EXPRESS BUS | ICATS INTERCOUNTY EXPRESS BUS | PURCHASE 3 OVER-THE-ROAD COACH BUSES AND 5 SETS OF BUS STOP SHELTERS TO EXPAND INTERCOUNTY SERVICE BETWEEN STATESVILLE, TROUTMAN, MOORESVILLE, AND CATS ROUTES BETWEEN HUNTERSVILLE AND CHARLOTTE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 10, 12 | CHARLOTTE REGIONAL TPO | TA-6713 | REGION E, F | T |  |  |  |  | 2021 | 1000000 |  |  | 1000000
JACKSON | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | NCDOT | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. | BIKE/PED | FEDERAL LANDS ACCESS PROGRAM | 14 | SOUTHWESTERN RPO | BF-0001 | EXEMPT | FLAP, S(M) |  |  |  |  | 2022 | 190000 | 2022 | 10000 | 200000 | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION.
JACKSON | SR 1432 (SKYLAND DRIVE) | NCDOT | SR 1429 (CHIPPER CURVE ROAD) TO US 23 BUSINESS. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | EB-5923 | DIVISION 14 | L, TALT5 |  |  |  |  | 2023 | 960000 |  |  | 960000 | UNDER CONSTRUCTION.
JACKSON | SR 1120 (CEDAR CREEK ROAD) | NCDOT | REPLACE BRIDGE 490008 CEDAR CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-5921 | DIVISION 14 | BGOFF | 2023 | 20000 |  |  | 2024 | 400000 |  |  | 420000
JACKSON | SR 1300 (PUMPKINTOWN ROAD) | NCDOT | REPLACE BRIDGE 490069 OVER SAVANNAH CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6031 | DIVISION 14 | BGOFF | 2024 | 80000 |  |  | 2025 | 800000 |  |  | 880000
JACKSON | SR 1397 (THOMAS VALLEY ROAD) | NCDOT | REPLACE BRIDGE 490144 OVER NATIONS CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6032 | DIVISION 14 | BGOFF | 2021 | 50000 |  |  | 2022 | 983000 |  |  | 1033000 | UNDER CONSTRUCTION. 80 2019 BGOFF R 0
JACKSON | SR 1445 (LEE BUMGARNER ROAD) | NCDOT | REPLACE BRIDGE 490129 OVER SCOTT CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6033 | DIVISION 14 | BGOFF |  |  |  |  | 2029 | 1200000 |  |  | 1200000 | RIGHT-OF-WAY IN PROGRESS
JACKSON | SR 1300 (PUMPKINTOWN ROAD) | NCDOT | REPLACE BRIDGE 490065 OVER SAVANNAH CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6034 | DIVISION 14 | BGOFF | 2024 | 80000 |  |  | 2027 | 800000 |  |  | 880000
JACKSON | SR 1738 (HOOPER CEMETERY ROAD) | NCDOT | REPLACE BRIDGE 490203 OVER CANEY FORK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6035 | DIVISION 14 | BGOFF | 2021 | 70000 |  |  | 2022 | 1415000 |  |  | 1485000 | UNDER CONSTRUCTION.
JACKSON | SR 1737 (CANEY FORK ROAD) | NCDOT | REPLACE BRIDGE 490081 OVER JOHNS CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6036 | DIVISION 14 | BGOFF | 2023 | 70000 |  |  | 2027 | 700000 |  |  | 770000
JACKSON | SR 1157 (CULLOWHEE MOUNTAIN ROAD) | NCDOT | INSTALL GUARDRAIL FROM MILEPOST 2.6 TO 6.6, NEAR CULLOWHEE. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO | HS-2014B | DIVISION 14 | HSIP |  |  |  |  | 2022 | 110000 |  |  | 110000 | UNDER CONSTRUCTION.
JACKSON | SR 1325 (CENTENNIAL DRIVE) | NCDOT | INSTALL RECTANGULAR RAPID FLASHING BEACONS (RRFB) AT THREE MIDBLOCK CROSSINGS NEAR SR 1169 (CENTRAL DRIVE). | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO | HS-2014D | DIVISION 14 | HSIP |  |  |  |  | 2022 | 59000 |  |  | 59000 | UNDER CONSTRUCTION.
JACKSON | VARIOUS | NCDOT | US 23 BUSINESS (HAYWOOD ROAD) AT CHURCH STREET AND SR 1557 (FRONT STREET) AT SR 1558 (DEPOT STREET). INSTALL RECTANGULAR RAPID FLASHING BEACON (RRFB) AND UPGRADE CURB RAMPS. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO | HS-2014H | REGION G | HSIP |  |  |  |  | 2023 | 96000 |  |  | 96000
JACKSON | US 64 | NCDOT | CASHIERS TO JACKSON-TRANSYLVANIA COUNTY LINE | HIGHWAY | PRE-STI (HISTORIC) | 14 | SOUTHWESTERN RPO | R-2409A | [11 empty] | COMPLETE
JACKSON | US 64 | NCDOT | 1.1 MILES EAST OF CASHIERS TO 1.6 MILES EAST OF CASHIERS | HIGHWAY | PRE-STI (HISTORIC) | 14 | SOUTHWESTERN RPO | R-2409B | [11 empty] | COMPLETE
JACKSON | NC 107 | NCDOT | SR 1002 TO NC 281. UPGRADE EXISTING ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-4753 | DIVISION 14 | [10 empty] | UNDER CONSTRUCTION
JACKSON | NC 107 (US 23 BUSINESS) | NCDOT | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5600 | REGION G | NHP, T | 2022 | 58440000 | 2022 | 7200000 | 2025 | 56199000 |  |  | 121839000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT OF WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE).
JACKSON | NC 107 | NCDOT | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO APPROXIMATELY 1 MILE NORTH OF SR 1157 (PINE CREEK ROAD). WIDEN PAVEMENT TO 24 FEET WITH 5 FEET PAVED SHOULDERS. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5841
JACKSON | NC 107 | NCDOT | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5841A | NOT FUNDED | T | NOT FUNDED | 2599000 | NOT FUNDED | 200000 | NOT FUNDED | 17899000 |  |  | 20698000
JACKSON | NC 107 | NCDOT | 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM TO APPROXIMATELY 1 MILE NORTH OF SR 1157 (PINE CREEK ROAD). | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5841B | NOT FUNDED | T | NOT FUNDED | 6400000 | NOT FUNDED | 300000 | NOT FUNDED | 102800000 |  |  | 109500000
JACKSON | US 64 | NCDOT | NC 107 INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5881 | REGION G | T | 2028 | 14900000 | 2028 | 800000 | 2030 | 6700000 |  |  | 22400000
JACKSON | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | NCDOT | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5907 | DIVISION 14 | BGLT5 | 2028 | 3500000 | 2028 | 200000 | 2030 | 19900000 |  |  | 23600000
JACKSON | US 64 | NCDOT | SR 1119 (SAPPHIRE POSTOFFICE ROAD) AT CHRYSLER CURVE NEAR SAPPHIRE. CONSTRUCT SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO | W-5714E | REGION G | HSIP |  |  |  |  | 2024 | 975000 |  |  | 975000
JACKSON | JACKSON COUNTY | JACKSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | SOUTHWESTERN RPO | TK-6137 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 752000 | 752000 | FUNDS AUTHORIZED IN PROGRESS
JACKSON, HAYWOOD | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | NCDOT | BLUE RIDGE PARKWAY INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO | U-6172A | DIVISION 14 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 110000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 110000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 |  |  | 1920000
JACKSON, SWAIN | VARIOUS | NCDOT | INDIAN RESERVATION ROAD (IRR) PROGRAM. ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED BY EASTERN BAND OF CHEROKEE INDIANS. | HIGHWAY | OTHER | 14 | SOUTHWESTERN RPO | R-5500 | EXEMPT | [10 empty] | PROGRAM IN PROGRESS
JOHNSTON | JOHNSTON COUNTY AIRPORT (JNX) | JOHNSTON COUNTY AIRPORT (JNX) | LAND ACQUISITION & CLEARING PROJECT. | AVIATION | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | AV-5745 | DIVISION 4 | T |  |  |  |  | 2023 | 335000 |  |  | 335000
JOHNSTON | EAST CLAYTON CONNECTOR GREENWAY | CLAYTON | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | EB-6016 | DIVISION 4 | L, TAANY | 2027 | 10000 |  |  | 2028 | 1242000 | 2026 | 258000 | 1510000
JOHNSTON | MOUNTAINS TO SEA TRAIL | CLAYTON | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | EB-6017 | DIVISION 4 | L, TAANY |  |  |  |  | 2028 | 414000 | 2026 | 83000 | 497000
JOHNSTON | SR 2143 (BEULAHTOWN ROAD) | NCDOT | REPLACE BRIDGE 500216 OVER LITTLE BUFFALO CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-4562 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION. DESIGN BUILD PROJECT.
JOHNSTON | I-95 | NCDOT | REPLACE BRIDGE 500118 AND 500119 OVER CSX RAILROAD. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-4937 | STATEWIDE MOBILITY | T |  |  |  |  | 2029 | 9600000 |  |  | 9600000
JOHNSTON | SR 1555 (BARBOUR MILL ROAD) | NCDOT | REPLACE BRIDGE 500145 OVER SWIFT CREEK. | HIGHWAY | BRIDGES | 4 | CAPITAL AREA MPO | B-5664 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION.
JOHNSTON | SR 1399 (ZACK'S MILL ROAD) | NCDOT | REPLACE BRIDGE 500277 OVER POLECAT BRANCH. | HIGHWAY | BRIDGES | 4 | CAPITAL AREA MPO | B-5997 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION.
JOHNSTON | SR 1153 (MILL CREEK ROAD) | NCDOT | REPLACE BRIDGE 500068 OVER JUNIPER SWAMP. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-6001 | DIVISION 4 | BGOFF |  |  |  |  | 2021 | 1015000 |  |  | 1015000 | UNDER CONSTRUCTION.
JOHNSTON | I-95 | NCDOT | REPLACE BRIDGE 500082 AND 500085 OVER BLACK CREEK AND BRIDGE 500100 AND 500101 OVER NEUSE RIVER. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-6044 | STATEWIDE MOBILITY | BFP | 2027 | 90000 |  |  | 2029 | 28800000 |  |  | 28890000
JOHNSTON | SR 2137 (PITTMAN ROAD) SR 2130 (E MAIN STREET) SR | NCDOT | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-6050 | DIVISION 4 | BFP | 2025 | 1500000 |  |  | 2027 | 15000000 |  |  | 16500000
JOHNSTON | SR 1004 (EAST MAIN STREET) | CLAYTON | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 4 | CAPITAL AREA MPO | BL-0050 | EXEMPT | CMAQ, L | 2023 | 200000 |  |  | 2024 | 450000 |  |  | 650000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | US 301 | NCDOT | REPLACE BRIDGE 500056 OVER BLACK CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | HB-0042 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY.
JOHNSTON | I-95 | NCDOT | I-95 FROM MILE MARKER 97 TO MILE MARKER 101. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | HI-0008 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 7229000 |  |  | 7229000 | UNDER CONSTRUCTION.
JOHNSTON | NC 242 | NCDOT | CURVE IMPROVEMENTS BETWEEN 0.08 MILES AND 0.31 MILES NORTH OF SR 1116 (GODWIN LAKE ROAD). | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | HS-2004L | REGION A | HSIP | 2023 | 272000 |  |  | 2023 | 555000 |  |  | 827000 | UNDER CONSTRUCTION.
JOHNSTON | US 301 (BRIGHTLEAF BOULEVARD) | NCDOT | US 301 (BRIGHTLEAF BOULEVARD) AT NORTH STREET IN SMITHFIELD. INSTALL / UPGRADE HIGH VISIBILITY CROSSWALKS, AUDIBLE COUNTDOWN PEDESTRIAN SIGNAL HEADS, PEDESTRIAN IMPROVEMENTS, TRAFFIC SIGNAL, AND TRAFFIC SIGNAL SYSTEM. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | HS-2004P | REGION A | HSIP |  |  |  |  | 2023 | 70000 |  |  | 70000 | UNDER CONSTRUCTION.
JOHNSTON | SR 1902 (GLEN LAUREL ROAD) | NCDOT | SR 1902 (GLEN LAUREL ROAD) AT SR 1903 (VINSON ROAD). TRAFFIC SIGNAL INSTALLATION. | HIGHWAY | SAFETY | 4 | CAPITAL AREA MPO | HS-2004S | DIVISION 4 | HSIP |  |  |  |  | 2023 | 96000 |  |  | 96000 | UNDER CONSTRUCTION.
JOHNSTON | US 70 | NCDOT | US 70 AT US 70A/SR 2532 (WEST EDWARDS STREET) AND US 70 AT SR 2314 (PONDFIELD ROAD). INSTALL REDUCED CONFLICT INTERSECTION WITH WESTBOUND U-TURN AT SR 2314 (PONDFIELD ROAD). | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | HS-2004W | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2024 | 800000 |  |  | 800000
JOHNSTON | I-95 | NCDOT | US 70 (EXIT 97) TO US 301 (EXIT 107). PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-3318
JOHNSTON | I-95 | NCDOT | US 70 (EXIT 97) TO NORTH OF SR 1001 (MILE MARKER 100). | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-3318A | [11 empty] | COMPLETED.
JOHNSTON | I-95 | NCDOT | REPLACE BRIDGE NO. 114 AND BRIDGE NO. 116 AND APPROACHES OVER LITTLE RIVER. | HIGHWAY | TRANSITION | 4 | UPPER COASTAL PLAIN RPO | I-3318BB | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION.
JOHNSTON | I-40 | NCDOT | ACCESS IMPROVEMENTS IN THE VICINITY OF EXISTING I-40/NC 42 INTERCHANGE (EXIT 312). | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | I-4739 | STATEWIDE MOBILITY | NHP | 2019 | 19305000 |  |  | 2018 | 40137000 |  |  | 59442000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033.
JOHNSTON | I-40 | NCDOT | WAKE COUNTY LINE TO NC 42. | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | I-5111REG | REGION A | NHP | 2019 | 3479000 |  |  | 2018 | 23795000 |  |  | 27274000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
JOHNSTON | I-40 | NCDOT | SR 1010 (CLEVELAND ROAD) (MILE MARKER 312.2) TO WEST OF SR 1211 (MORGAN ROAD) (MILE MARKER 328.5). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-5781 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION. NATIONAL HIGHWAY FREIGHT PROGRAM PROJECT.
JOHNSTON | I-95 | NCDOT | SOUTH OF SR 1001 (LIZZIE MILL ROAD) TO THE JOHNSTON/WILSON COUNTY LINE NORTH OF NC 222. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-5786 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION.
JOHNSTON | I-95 | NCDOT | REPLACE BRIDGE 500117 ON SR 2399 (TRUCK STOP ROAD) OVER I-95 AND ADJUST SERVICE ROADS AND APPROACHES. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-5786A | STATEWIDE MOBILITY
JOHNSTON | I-95 | NCDOT | US 70 BUSINESS. UPGRADE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | I-5972 | REGION A | NHFP, NHP |  |  |  |  | 2024 | 34500000 |  |  | 34500000 | RIGHT-OF-WAY IN PROGRESS
JOHNSTON | I-95 | NCDOT | US 701/NC 96. CONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | I-5974 | REGION A | NHP | 2026 | 13695000 | 2026 | 2026000 | 2028 | 48399000 |  |  | 64120000
JOHNSTON | US 70 (FUTURE I-42) | NCDOT | SR 1003 (BUFFALO ROAD) TO WAYNE COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-6044 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 6090000 |  |  | 6090000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132 FOR CONSTRUCTION, PAYBACK FY 2019-2033.
JOHNSTON | I-95 | NCDOT | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | I-6061 | DIVISION 4 | T | 2027 | 1300000 | 2027 | 1900000 | 2029 | 17199000 |  |  | 20399000
JOHNSTON | I-95 | NCDOT | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | I-6062 | DIVISION 4 | T | 2027 | 3600000 | 2027 | 1300000 | 2029 | 19000000 |  |  | 23900000
JOHNSTON | NC 42 | NCDOT | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | R-3410 | REGION A | BGANY | 2027 | 14697000 | 2027 | 19600000 | 2029 | 74200000 |  |  | 108497000
JOHNSTON | NC 42 | NCDOT | US 70 TO SR 1003 (BUFFALO ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | R-3825
JOHNSTON | NC 42 | NCDOT | US 70 AT CLAYTON TO EAST OF SR 1902 (GLEN LAUREL ROAD). | HIGHWAY | PRE-STI (HISTORIC) | 4 | CAPITAL AREA MPO | R-3825A | [11 empty] | COMPLETED.
JOHNSTON | NC 42 | NCDOT | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | R-3825B | DIVISION 4 | T |  |  |  |  | 2019 | 68448000 |  |  | 68448000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
JOHNSTON | SR 1003 (BUFFALO ROAD) | NCDOT | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | R-5718 | DIVISION 4 | BG5200, T | 2022 | 6937000 | 2022 | 1190000 | 2025 | 14300000 |  |  | 22427000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | NC 242 | NCDOT | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | R-5761 | DIVISION 4 | T | 2027 | 2200000 | 2027 | 500000 | 2029 | 13300000 |  |  | 16000000
JOHNSTON | US 70 | NCDOT | US 301 TO I-95. ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | R-5795 | REGION A | T | 2027 | 4630000 | 2027 | 4400000 | 2029 | 11700000 |  |  | 20730000
JOHNSTON | US 70 | NCDOT | WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET) TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | R-5829B | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13077000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4774000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 71902000 |  |  | 89753000
JOHNSTON | SR 1501 (SWIFT CREEK ROAD) | NCDOT | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | R-5950 | DIVISION 4 | T | 2027 | 2000000 | 2027 | 1222000 | 2029 | 3600000 |  |  | 6822000
JOHNSTON | US 301/NC 39/NC 96 | NCDOT | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | U-5726 | DIVISION 4 | BG5T50 | 2025 | 11200000 | 2025 | 1400000 | 2027 | 14600000 |  |  | 27200000
JOHNSTON | CLAYTON | NCDOT | CLAYTON SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | U-5943 | REGION A | BGANY | 2023 | 10000 | 2023 | 260000 | 2025 | 4500000 |  |  | 4770000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | NC 42 | NCDOT | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | U-5998 | DIVISION 4 | T | 2025 | 3400000 | 2025 | 3000000 | 2027 | 14800000 |  |  | 21200000
JOHNSTON | NC 210 | NCDOT | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | U-6203 | DIVISION 4 | T | 2026 | 28963000 | 2026 | 4360000 | 2028 | 45201000 |  |  | 78524000
JOHNSTON | NEW ROUTE | NCDOT | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | U-6208 | DIVISION 4 | T | 2027 | 3000000 | 2027 | 10000000 | 2029 | 14499000 |  |  | 27499000
JOHNSTON | SR 1010 (CLEVELAND ROAD) | NCDOT | NC 42 TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | U-6216 | DIVISION 4 | T | 2027 | 34300000 | 2027 | 6654000 | 2029 | 43700000 |  |  | 84654000
JOHNSTON | SR 1560 (RANCH ROAD EXTENSION) | NCDOT | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | HIGHWAY | LOCALLY SELECTED | 4 | CAPITAL AREA MPO | U-6223 | DIVISION 4 | BGDA, HF, L, S | 2021 | 2169000 |  |  | 2022 | 11250000 |  |  | 13419000 | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS.
JOHNSTON | SR 1524 (OLD DRUG STORE ROAD) | NCDOT | IMPROVE SUPERELEVATION IN CURVE ON SR 1524 (OLD DRUG STORE ROAD) SOUTH OF SR 1525 (CORNWALLIS ROAD). INSTALL SIGNAL AT INTERSECTION OF SR 1524 (OLD DRUG STORE ROAD) AND SR 1525 (CORNWALLIS ROAD). | HIGHWAY | SAFETY | 4 | CAPITAL AREA MPO | W-5204E | DIVISION 4 | HSIP | 2023 | 200000 |  |  | 2024 | 650000 |  |  | 850000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | US 70 | NCDOT | US 70 BUSINESS TO NEUSE RIVER BRIDGE. CONVERT TO FREEWAY WITH INTERCHANGES AT SR 1501 (SWIFT CREEK ROAD) AND SR 1919 (WILSON'S MILLS ROAD). | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | W-5600 | REGION A | NHP |  |  |  |  | 2021 | 67693000 |  |  | 67693000 | UNDER CONSTRUCTION.
JOHNSTON | SR 1700 (COVERED BRIDGE ROAD) | NCDOT | SAFETY IMPROVEMENTS FROM 0.1 MILES EAST OF SR 1003 (BUFFALO ROAD) TO 0.1 MILES WEST OF SR 2685 (HELENA LANE). | HIGHWAY | SAFETY | 4 | CAPITAL AREA MPO | W-5704E | DIVISION 4 | HSIP, T |  |  |  |  | 2024 | 10600000 |  |  | 10600000
JOHNSTON | JOHNSTON COUNTY | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO, CAPITAL AREA MPO | TA-6720 | DIVISION 4 | 5311, L, T |  |  |  |  | 2026 | 330000 |  |  | 330000
JOHNSTON | JOHNSTON COUNTY COUNCIL ON AGING, INC. | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | TK-6138 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1176000 | 1176000 | FUNDS AUTHORIZED IN PROGRESS
JOHNSTON | NS/NCRR H LINE | CLAYTON | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | RAIL | STI (PRIORITIZATION) | 4 | CAPITAL AREA MPO | P-5743 | NOT FUNDED | O, T | NOT FUNDED | 3000000 |  |  | NOT FUNDED | 11100000 |  |  | 14100000 | OTHER FUNDS PROVIDED BY NS.
JOHNSTON | SR 2383 (PRESTON STREET) | NCDOT | CLOSURE OF SR 2383 (PRESTON STREET) AT CSX (CROSSING 629 950L) IN SELMA. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 4 | UPPER COASTAL PLAIN RPO | RC-2004B | DIVISION 4 | RR | 2024 | 50000 | 2024 | 20000 | 2025 | 500000 |  |  | 570000
JOHNSTON | SR 1357 (GILBERT ROAD) | NCDOT | CSX CROSSING 629731X NEAR BENSON. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004C | DIVISION 4 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
JOHNSTON | PARRISH DRIVE | NCDOT | CSX CROSSING 629739C IN BENSON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004D | DIVISION 4 | RR |  |  |  |  | 2024 | 388000 |  |  | 388000
JOHNSTON | SR 2130 (MAIN STREET) | NCDOT | CSX CROSSING 629943B IN MICRO. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004G | DIVISION 4 | RR |  |  |  |  | 2025 | 417000 |  |  | 417000
JOHNSTON | SR 1709 (STALLINGS STREET) | NCDOT | NORFOLK SOUTHERN CROSSING 735396M IN CLAYTON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | CAPITAL AREA MPO | RX-2004H | DIVISION 4 | RR |  |  |  |  | 2025 | 475000 |  |  | 475000
JOHNSTON | SR 2339 (BAGLEY ROAD) | NCDOT | CSX CROSSING 629939L IN KENLY. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004J | DIVISION 4 | RR |  |  |  |  | 2026 | 434000 |  |  | 434000
JOHNSTON | LEE STREET | NCDOT | CSX CROSSING 629964U IN SMITHFIELD. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004K | DIVISION 4 | RR |  |  |  |  | 2027 | 388000 |  |  | 388000
JOHNSTON | SR 2500 (WALLPAT ROAD) | NCDOT | CSX CROSSING 629966H IN SMITHFIELD. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004L | DIVISION 4 | RR |  |  |  |  | 2027 | 388000 |  |  | 388000
JOHNSTON, EDGECOMBE, NASH | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | HIGHWAY | OTHER | 4 | UPPER COASTAL PLAIN RPO | C-5619 | EXEMPT | CMAQ, L | 2020 | 420000 |  |  | 2020 | 2495000 | 2020 | 1260000 | 4175000
JOHNSTON, WAKE | US 70 BUSINESS | NCDOT | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 4, 5 | CAPITAL AREA MPO | U-6113 | NOT FUNDED | T | NOT FUNDED | 7600000 | NOT FUNDED | 1500000 | NOT FUNDED | 83200000 |  |  | 92300000
JOHNSTON, WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 4, 5 | CAPITAL AREA MPO | TO-6166D | REGION A, C | L, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21993000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6114000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 115650000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | 145257000
JOHNSTON, WILSON | VARIOUS | NCDOT | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | W-5204DIV | DIVISION 4
JOHNSTON, WILSON | VARIOUS | NCDOT | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | W-5204REG | REGION A
JONES | SR 1142 (WEYERHAEUSER ROAD) | NCDOT | REPLACE BRIDGE 510032 OVER TUCKAHOE SWAMP. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-5994 | DIVISION 2 | [10 empty] | UNDER CONSTRUCTION.
JONES | US 17 | NCDOT | NORTH OF MAYSVILLE TO SOUTH OF NC 58. | HIGHWAY | TRANSITION | 2 | DOWN EAST RPO | R-2514C | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
JONES | US 17 | NCDOT | SOUTH OF NC 58 TO THE NEW BERN BYPASS. | HIGHWAY | TRANSITION | 2 | DOWN EAST RPO | R-2514D | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
JONES | US 70 (FUTURE I-42) | NCDOT | EAST OF SR 1002 (WYSE FORK ROAD) TO EXISTING FREEWAY NEAR DOVER. | HIGHWAY | STI (PRIORITIZATION) | 2 | DOWN EAST RPO | R-2553E | NOT FUNDED | T | NOT FUNDED | 6805000 | NOT FUNDED | 1756000 | NOT FUNDED | 53000000 |  |  | 61561000
JONES, ONSLOW | US 17 | NCDOT | MULTI-LANES NORTH OF JACKSONVILLE TO NEW BERN BYPASS. WIDEN TO MULTI-LANES WITH BYPASSES OF BELGRADE, MAYSVILLE AND POLLOCKSVILLE ON NEW LOCATION. | HIGHWAY | PRE-STI (HISTORIC) | 2, 3 | DOWN EAST RPO, JACKSONVILLE URBAN AREA MPO | R-2514
LEE | RALEIGH EXECUTIVE SANFORD - LEE COUNTY AIRPORT (TT | RALEIGH EXECUTIVE SANFORD - LEE COUNTY AIRPORT (TT | CONSTRUCT CORPORATE AREA APRON PHASE I. | AVIATION | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | AV-5762 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION; INCLUDES $1.5 M IN ECONOMIC DEVELOPMENT FUNDING
LEE | RALEIGH EXECUTIVE JETPORT (TTA) | RALEIGH EXECUTIVE JETPORT (TTA) | RUNWAY 21 AND RUNWAY 3 BYPASS TAXIWAY. CONSTRUCT AIRPLANE RUN-UP LANE AT EACH END OF TAXIWAY. | AVIATION | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | AV-5899 | DIVISION 8 | T |  |  |  |  | 2024 | 1700000 |  |  | 1700000
LEE | NC 42 (WICKER STREET) | SANFORD | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5742 | DIVISION 8 | L, TA5200 |  |  |  |  | 2024 | 1011000 | 2022 | 77000 | 1088000 | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS
LEE | US 1 BUSINESS (CARTHAGE STREET) | SANFORD | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5863 | DIVISION 8 | L, TA5200 | 2023 | 150000 |  |  | 2024 | 1469000 | 2021 | 295000 | 1914000
LEE | SR 1107 (FIELDS DRIVE) | SANFORD | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5867 | DIVISION 8 | L, TA5200 | 2023 | 102000 | 2023 | 90000 | 2024 | 1015000 | 2022 | 149000 | 1356000
LEE | WOODLAND STREET | SANFORD | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5868 | DIVISION 8 | L, TA5200 | 2024 | 111000 | 2024 | 100000 | 2025 | 1105000 | 2023 | 116000 | 1432000
LEE | SR 1579 (SOUTH MAIN STREET) | BROADWAY | SR 1531 (MANSFIELD DRIVE) TO END OF EXISTING SIDEWALK IN BROADWAY. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5870 | DIVISION 8 | L, TALT5 |  |  |  |  | 2023 | 86000 |  |  | 86000
LEE | SR 1002 (CHARLOTTE AVENUE) | SANFORD | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-6002 | DIVISION 8 | L, TA5200 |  |  |  |  | 2025 | 1400000 | 2023 | 191000 | 1591000
LEE | MCIVER STREET | SANFORD | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-6003 | NOT FUNDED | L, TA5200 |  |  |  |  | NOT FUNDED | 864000 | NOT FUNDED | 128000 | 992000
LEE | SR 1400 (CUMNOCK ROAD) | NCDOT | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 8 | TRIANGLE AREA RPO | B-5976 | DIVISION 8 | BGOFF | 2030 | 600000 |  |  | 2031 | 6200000 |  |  | 6800000
LEE | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NCDOT | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-3830 | DIVISION 8 | T | 2019 | 10228000 |  |  | 2023 | 76047000 |  |  | 86275000 | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE)
LEE | NC 42 | NCDOT | RAILROAD MITIGATION | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-3830A | DIVISION 8 | T |  |  |  |  | 2021 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION
LEE | SR 1521 (KELLY DRIVE) | NCDOT | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5959 | DIVISION 8 | T | 2023 | 1900000 | 2023 | 700000 | 2025 | 7300000 |  |  | 9900000
LEE | NEW ROUTE | NCDOT | SR 1133 (LEE AVENUE) TO EXISTING COMMERCE DRIVE IN SANFORD. CONSTRUCT 2-LANE EXTENSION OF COMMERCE DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5960 | DIVISION 8 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 138000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 104000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6500000 |  |  | 6742000
LEE | SR 1237 (CARTHAGE STREET) | NCDOT | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5709 | DIVISION 8 | T | 2022 | 3427000 | 2022 | 1700000 | 2025 | 13198000 |  |  | 18325000 | RIGHT-OF-WAY IN PROGRESS
LEE | US 421 BUSINESS / NC 87 | NCDOT | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5722 | REGION E | T | 2028 | 24700000 | 2028 | 7564000 | 2031 | 15099000 |  |  | 47363000
LEE | US 1 / US 15 / US 501 | NCDOT | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION AND RELOCATE NC 78 (TRAMWAY ROAD). | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5727 | REGION E | NHP, T | 2023 | 12300000 | 2023 | 1500000 | 2026 | 14401000 |  |  | 28201000 | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS
LEE | US 1 / US 15 / US 501 | NCDOT | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5975 | REGION E | BGANY, T | 2023 | 4100000 | 2023 | 3300000 | 2026 | 29899000 |  |  | 37299000 | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS
LEE | LEE COUNTY | LEE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 8 | TRIANGLE AREA RPO | TK-6140 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 632000 | 632000 | FUNDS AUTHORIZED IN PROGRESS
LEE | US 1 BUSINESS (CARTHAGE STREET / CHARLOTTE AVENUE) | NCDOT | ATW CROSSING 721059F IN SANFORD. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 8 | TRIANGLE AREA RPO | RX-2008E | DIVISION 8 | RR |  |  |  |  | 2025 | 450000 |  |  | 450000
LENOIR | NC 903 | NCDOT | REPLACE BRIDGE 530045 OVER NEUSE RIVER. | HIGHWAY | BRIDGES | 2 | EASTERN CAROLINA RPO | B-4566 | REGION B | BFP |  |  |  |  | 2028 | 6500000 |  |  | 6500000
LENOIR | SR 1389 (HARDY BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 530052 OVER NEUSE RIVER AND 530152 OVER NEUSE RIVER OVERFLOW. | HIGHWAY | BRIDGES | 2 | EASTERN CAROLINA RPO | B-5619 | DIVISION 2 | BGOFF | 2020 | 500000 |  |  | 2021 | 9170000 |  |  | 9670000 | UNDER CONSTRUCTION.
LENOIR | US 70 | NCDOT | INSTALL RESTRICTED CROSSING INTERSECTIONS AT US 70 AND SR 1324 (KENNEDY HOME ROAD) / SR 1519 (EASON ROAD) AND AT ADJACENT CROSSOVER TO THE WEST. | HIGHWAY | SAFETY | 2 | EASTERN CAROLINA RPO | HS-2002C | STATEWIDE MOBILITY | HSIP |  |  | 2022 | 20000 | 2022 | 250000 |  |  | 270000 | UNDER CONSTRUCTION.
LENOIR | NC 11 | NCDOT | NC 11 AT SR 1716 (HARVEY ROUSE ROAD), NC 11 AT NC 118/SR 1091 (GRIFTON-HUGO ROAD), AND NC 11 AT SR 1714 (CREEK ROAD). CONVERT MEDIAN OPENINGS TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | SAFETY | 2 | EASTERN CAROLINA RPO | HS-2002K | REGION B | HSIP |  |  | 2023 | 80000 | 2023 | 846000 |  |  | 926000 | UNDER CONSTRUCTION.
LENOIR | US 258 | NCDOT | US 258 AT SR 1342 (WILL BAKER ROAD / CENTRAL AVENUE). INSTALL FLASHER AND UPGRADE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 2 | EASTERN CAROLINA RPO | HS-2002N | REGION B | HSIP |  |  |  |  | 2023 | 62000 |  |  | 62000 | UNDER CONSTRUCTION.
LENOIR | US 258 | NCDOT | US 258 AT SR 1120 (NOBLES MILL ROAD) AND US 258 AT SR 1908 (BILL STROUD ROAD). CONSTRUCT TURN LANES. | HIGHWAY | SAFETY | 2 | EASTERN CAROLINA RPO | HS-2002P | REGION B | HSIP |  |  | 2024 | 150000 | 2024 | 661000 |  |  | 811000 | UTILITY RELOCATION IN PROGRESS.
LENOIR | US 70 (FUTURE I-42) | NCDOT | EXISTING FREEWAY NEAR LAGRANGE TO EXISTING FREEWAY NEAR DOVER. UPGRADE ROADWAY TO FREEWAY, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-2553
LENOIR | US 70 (FUTURE I-42) | NCDOT | EXISTING FREEWAY NEAR LAGRANGE TO SR 1522 (ALBERT SUGGS ROAD). | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-2553A | NOT FUNDED | T | NOT FUNDED | 45842000 | NOT FUNDED | 1447000 | NOT FUNDED | 44000000 |  |  | 91289000
LENOIR | US 70 (FUTURE I-42) | NCDOT | SR 1522 (ALBERT SUGGS ROAD) TO NC 148 (HARVEY PARKWAY). | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-2553B | NOT FUNDED | T | NOT FUNDED | 8300000 | NOT FUNDED | 6000000 | NOT FUNDED | 55801000 |  |  | 70101000
LENOIR | US 70 (FUTURE I-42) | NCDOT | NC 148 (HARVEY PARKWAY) TO US 70 EAST OF NC 58. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-2553C | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 82600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 320701000 |  |  | 407201000
LENOIR | NC 148 (CF HARVEY PARKWAY) | NCDOT | NC 58 TO NC 11. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-5703 | REGION B | T |  |  |  |  | 2018 | 74609000 |  |  | 74609000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
LENOIR | US 70 | NCDOT | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONVERT AT GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-5813 | NOT FUNDED | T | NOT FUNDED | 10100000 | NOT FUNDED | 2797000 | NOT FUNDED | 69900000 |  |  | 82797000
LENOIR | SR 1569 (CAREY ROAD EXTENSION) | NCDOT | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | U-3618 | DIVISION 2 | BGANY | 2025 | 4699000 | 2025 | 1000000 | 2028 | 28301000 |  |  | 34000000
LENOIR | LENOIR COUNTY | LENOIR COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 2 | EASTERN CAROLINA RPO | TK-6178 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1048000 | 1048000 | FUNDS AUTHORIZED IN PROGRESS
LENOIR | LINCOLN STREET | NCDOT | NORFOLK SOUTHERN CROSSING 722766G IN KINSTON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 2 | EASTERN CAROLINA RPO | RX-2002D | DIVISION 2 | RR |  |  |  |  | 2025 | 411000 |  |  | 411000
LENOIR, GREENE | US 258 | NCDOT | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO | R-5814 | DIVISION 2 | T | 2027 | 11900000 | 2027 | 3400000 | 2029 | 31302000 |  |  | 46602000
LENOIR, JONES | US 70 (FUTURE I-42) | NCDOT | EAST OF NC 58 TO EAST OF SR 1002 (WYSE FORK ROAD). | HIGHWAY | STI (PRIORITIZATION) | 2 | EASTERN CAROLINA RPO, DOWN EAST RPO | R-2553D | NOT FUNDED | T | NOT FUNDED | 14731000 | NOT FUNDED | 1964000 | NOT FUNDED | 60000000 |  |  | 76695000
LENOIR, ONSLOW, JONES | US 258 | NCDOT | US 258 BETWEEN NC 24 IN RICHLANDS AND US 70 IN KINSTON. INSTALL RUMBLES STRIPES. | HIGHWAY | SAFETY | 2, 3 | EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, DOWN EAST RPO | HS-2002Q | REGION B | HSIP |  |  |  |  | 2025 | 585000 |  |  | 585000
LINCOLN | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | OBSTRUCTION REMOVAL IN RUNWAY 5 APPROACH. | AVIATION | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | AV-5753 | DIVISION 12 | T | 2025 | 295000 | [6 empty] | 295000
LINCOLN | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LAND ACQUISITION FOR RUNWAY 5 APPROACH. | AVIATION | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | AV-5755 | DIVISION 12 | T | 2024 | 176000 | [6 empty] | 176000
LINCOLN | NC 27 | LINCOLNTON | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | HIGHWAY | LOCALLY SELECTED | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606I | EXEMPT | CMAQ, L, S |  |  |  |  | 2023 | 406000 |  |  | 406000 | UNDER CONSTRUCTION.
LINCOLN | SR 1360 (BETH HAVEN CHURCH ROAD) | NCDOT | SR 1373 (WINGATE HILL ROAD/ FORNEY HILL ROAD). INSTALL ALL WAY STOP, UPGRADE SIGNS AND PAVEMENT MARKINGS, AND IMPROVE SHOULDERS. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO | HS-2012F | DIVISION 12 | HSIP |  |  |  |  | 2023 | 25000 |  |  | 25000 | UNDER CONSTRUCTION.
LINCOLN | NC 150 | NCDOT | GASTON COUNTY LINE TO WEST OF INDIAN CREEK. | HIGHWAY | PRE-STI (HISTORIC) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617BA | [11 empty] | COMPLETE
LINCOLN | NC 150 | NCDOT | WEST OF INDIAN CREEK TO US 321 AT LINCOLNTON. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617BB | NOT FUNDED | T | NOT FUNDED | 5300000 | NOT FUNDED | 2500000 | NOT FUNDED | 40900000 |  |  | 48700000
LINCOLN | NC 150 | NCDOT | US 321 AT LINCOLNTON TO US 321 BYPASS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617C | NOT FUNDED | T | NOT FUNDED | 600000 | NOT FUNDED | 3900000 | NOT FUNDED | 71600000 |  |  | 76100000
LINCOLN | NC 16 BUSINESS | NCDOT | INTERSECTION OF NC 16 BUSINESS AND SR 1439 (UNITY CHURCH ROAD)/SR 1387 (TRIANGLE CIRCLE). ADD TURN LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5712 | REGION F | T |  |  |  |  | 2023 | 2300000 |  |  | 2300000 | RIGHT-OF-WAY IN PROGRESS
LINCOLN | NC 16 BUSINESS | NCDOT | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5962 | REGION F | O, T | 2024 | 3300000 | 2024 | 300000 | 2026 | 4200000 |  |  | 7800000 | OTHER FUNDING PROVIDED BY LINCOLN COUNTY
LINCOLN | NC 16 BYPASS | NCDOT | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6134 | REGION F | T | 2024 | 500000 | 2024 | 100000 | 2026 | 25400000 |  |  | 26000000
LINCOLN | NC 73 | NCDOT | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6139 | NOT FUNDED | NHP | NOT FUNDED | 5900000 | NOT FUNDED | 1500000 | NOT FUNDED | 42000000 |  |  | 49400000
LINCOLN | NC 27 (EAST MAIN STREET) | NCDOT | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6140 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34999000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33500000 |  |  | 77799000
LINCOLN | NC 73 EXTENSION | NCDOT | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6142 | NOT FUNDED | T | NOT FUNDED | 32300000 | NOT FUNDED | 4800000 | NOT FUNDED | 69302000 |  |  | 106402000
LINCOLN | NC 16 | NCDOT | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6144 | NOT FUNDED | T | NOT FUNDED | 5500000 | NOT FUNDED | 4900000 | NOT FUNDED | 21599000 |  |  | 31999000
LINCOLN | SR 1003 (BUFFALO SHOALS ROAD) | NCDOT | SR 1343 (IVEY CHURCH ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO | W-5712R | DIVISION 12 | HSIP |  |  |  |  | 2025 | 625000 |  |  | 625000
LINCOLN | LINCOLN COUNTY | LINCOLN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 12 | EASTERN CAROLINA RPO | TK-6141 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 876000 | 876000 | FUNDS AUTHORIZED IN PROGRESS
LINCOLN, CLEVELAND, GASTON | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ON APPROXIMATELY 59 SECONDARY ROADS. | HIGHWAY | SAFETY | 12 | GASTON-CLEVELAND-LINCOLN MPO | HS-2012E | DIVISION 12 | HSIP |  |  |  |  | 2023 | 2675000 |  |  | 2675000 | UNDER CONSTRUCTION.
LINCOLN, GASTON | NC 150 | NCDOT | NC 279 AT CHERRYVILLE TO RELOCATED US 321. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617 | REGION F
LINCOLN, MECKLENBURG | NC 73 | NCDOT | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. | HIGHWAY | STI (PRIORITIZATION) | 10, 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO | R-5721A | REGION E, F | T | 2026 | 46399000 | 2026 | 10400000 | 2029 | 102002000 |  |  | 158801000
MACON | MACON COUNTY AIRPORT | MACON COUNTY AIRPORT | EXTEND RUNWAY. | AVIATION | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | AV-5850 | DIVISION 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 166000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4834000 |  |  | 5000000
MACON | SR 1729 (DEPOT STREET) | NCDOT | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | BIKE/PED | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | EB-5756 | DIVISION 14 | L, TA5200 |  |  |  |  | 2023 | 294000 | 2022 | 18000 | 312000 | UNDER CONSTRUCTION.
MACON | EAST MAIN ST/US 441 BUS | NCDOT | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | BIKE/PED | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | EB-5964 | DIVISION 14 | L, TA5200 | 2023 | 20000 |  |  | 2024 | 650000 | 2022 | 20000 | 690000
MACON | SR 1114 (SHOPE ROAD) | NCDOT | REPLACE BRIDGE 550244 OVER NORTH FORK COWEETA CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6025 | DIVISION 14 | BGOFF | 2023 | 15000 |  |  | 2023 | 550000 |  |  | 565000 | UNDER CONSTRUCTION.
MACON | SR 1500 (WATAUGA ROAD) | NCDOT | REPLACE BRIDGE 550214 OVER WATAUGA CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6026 | DIVISION 14 | BGOFF | 2024 | 50000 |  |  | 2028 | 500000 |  |  | 550000
MACON | SR 1528 (LITTLE ELLIJAY ROAD) | NCDOT | REPLACE BRIDGE 550150 OVER ELLIJAY CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6028 | DIVISION 14 | BGOFF |  |  |  |  | 2022 | 1800000 |  |  | 1800000 | UNDER CONSTRUCTION.
MACON | SR 1001 (ELLIJAY ROAD) | NCDOT | REPLACE BRIDGE 550009 OVER NORTH PRONG ELLIJAY CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6029 | DIVISION 14 | BGOFF | 2023 | 70000 |  |  | 2023 | 700000 |  |  | 770000 | UNDER CONSTRUCTION.
MACON | SR 1351 (MATLOCK CREEK ROAD) | NCDOT | REPLACE BRIDGE 550220 OVER MATLOCK CREEK. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | B-6030 | DIVISION 14 | BGOFF |  |  |  |  | 2029 | 625000 |  |  | 625000 | RIGHT-OF-WAY IN PROGRESS
MACON | US 441 | NCDOT | SR 1515 (HYATT ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND RIGHT-IN/RIGHT-OUT AT INGLES DEVELOPMENT SITE. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | HA-0004 | EXEMPT | ADHSL |  |  |  |  | 2022 | 1500000 |  |  | 1500000 | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,500,000. UNDER CONSTRUCTION.
MACON | SR 1679 (PEEKS CREEK ROAD) | NCDOT | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | HB-0030 | DIVISION 14 | BGOFF | 2025 | 100000 | 2025 | 100000 | 2026 | 2000000 |  |  | 2200000
MACON | SR 1679 (GOLD MINE ROAD) | NCDOT | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | HIGHWAY | BRIDGES | 14 | SOUTHWESTERN RPO | HB-0037 | DIVISION 14 | BGOFF | 2026 | 50000 | 2026 | 50000 | 2027 | 1000000 |  |  | 1100000
MACON | US 64 | NCDOT | DRY FALLS RECREATION AREA. IMPROVE PARKING AREA, CONSTRUCT PEDESTRIAN BRIDGE, AND CONSTRUCT OBSERVATION PLATFORM. | HIGHWAY | FEDERAL LANDS ACCESS PROGRAM | 14 | SOUTHWESTERN RPO | HF-0006 | EXEMPT | FLAP |  |  |  |  | 2026 | 500000 | 2024 | 500000 | 1000000 | FLAP PROJECT NC 64. AWARDED $1.0M.
MACON | US 64/NC 28 | NCDOT | INSTALL CENTERLINE RUMBLESTRIPS, LONG LIFE PAVEMENT MARKINGS, AND INTERMITTMENT PAVED SHOULDERS FROM SR 1560 TO SR 1533, NEAR FRANKLIN. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO | HS-2014A | REGION G | HSIP |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | UNDER CONSTRUCTION.
MACON | US 23/US 441 | NCDOT | US 64 TO SR 1649 (PRENTISS BRIDGE ROAD). IMPLEMENT ACCESS MANAGEMENT STRATEGIES. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5734 | [11 empty] | SEGMENT A INCLUDES THE REPLACEMENT OF BRIDGE 314 FORMERLY SCHEDULED TO BE REPLACED UNDER 17BP.14.R.154
MACON | US 23/US 441 | NCDOT | US 64 TO SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE). | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5734A | DIVISION 14 | T |  |  |  |  | 2021 | 12600000 | 2021 | 2310000 | 14910000 | COMPLETE; BUILD NC BOND FUNDING: $1.788 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $9.797 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
MACON | US 23/US 441 | NCDOT | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5734B | NOT FUNDED | T | NOT FUNDED | 13800000 | NOT FUNDED | 3200000 | NOT FUNDED | 26600000 |  |  | 43600000
MACON | US 23/US 441 | NCDOT | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5734C | NOT FUNDED | T | NOT FUNDED | 5000000 | NOT FUNDED | 600000 | NOT FUNDED | 53600000 |  |  | 59200000
MACON | US 441 BUSINESS | NCDOT | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | U-5604 | REGION G | T |  |  |  |  | 2020 | 7080000 | 2021 | 1830000 | 8910000 | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE).
MACON | MACON COUNTY | MACON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | SOUTHWESTERN RPO | TK-6142 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 764000 | 764000 | FUNDS AUTHORIZED IN PROGRESS
MACON, CHEROKEE, JACKSON | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS PRIMARY AND SECONDARY ROUTES. | HIGHWAY | SAFETY | 14 | SOUTHWESTERN RPO | HS-2014P | REGION G | HSIP |  |  |  |  | 2024 | 2955000 |  |  | 2955000 | UNDER CONSTRUCTION.
MADISON | MARSHALL | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | BIKE/PED | STI (PRIORITIZATION) | 13 | LAND-OF-SKY RPO | EB-5918 | DIVISION 13 | L, TALT5 |  |  |  |  | 2024 | 150000 | 2023 | 45000 | 195000
MADISON | I-26 (US 19/US 23) | NCDOT | NORTH OF NC 213 TO NORTH OF US 19 | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | LAND-OF-SKY RPO | A-0010BB | [11 empty] | COMPLETE
MADISON | I-26 (US 19/US 23) | NCDOT | NORTH OF US 19 TO SR 1318 (BIG LAUREL ROAD) AT LAUREL CREEK | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | LAND-OF-SKY RPO | A-0010C | [11 empty] | COMPLETE
MADISON | I-26 (US 19/US 23) | NCDOT | SR 1318 (BIG LAUREL ROAD) AT LAUREL CREEK TO THE TENNESSEE STATE LINE AT SAMS GAP | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | LAND-OF-SKY RPO | A-0010D | [11 empty] | COMPLETE
MADISON | SR 1503 (LAUREL VALLEY) | NCDOT | REPLACE BRIDGE 560246 OVER LAUREL CREEK. | HIGHWAY | BRIDGES | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | B-4182 | DIVISION 13 | [10 empty] | CONSTRUCTION FUNDED WITH STATE LEGISLATIVE BRIDGE PROGRAM FUNDS (17BP.13.R.105)
MADISON | SR 1395 | NCDOT | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | HIGHWAY | BRIDGES | 13 | LAND-OF-SKY RPO | B-5989 | DIVISION 13 | BGOFF | 2022 | 13000 | 2023 | 130000 | 2023 | 4600000 |  |  | 4743000 | UNDER CONSTRUCTION.
MADISON | SR 1183 (UPPER SHUT-IN ROAD) | NCDOT | REPLACE BRIDGE 560302 OVER SHUT IN CREEK. | HIGHWAY | BRIDGES | 13 | LAND-OF-SKY RPO | B-6010 | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
MADISON | SR 1341 (FOSTER CREEK ROAD) | NCDOT | REPLACE BRIDGE 560073 OVER FOSTER CREEK. | HIGHWAY | BRIDGES | 13 | FRENCH BROAD RIVER MPO | B-6012 | DIVISION 13 | T |  |  |  |  | 2019 | 4828000 |  |  | 4828000 | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
MADISON | SR 1151 (BALTIMORE BRANCH ROAD) | NCDOT | REPLACE BRIDGE 560222 OVER BACK BRANCH. | HIGHWAY | BRIDGES | 13 | LAND-OF-SKY RPO | B-6017 | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
MADISON | SR 1127 (ROBERTS BRANCH ROAD) | NCDOT | REPLACE BRIDGE 560311 OVER ROBERTS BRANCH. | HIGHWAY | BRIDGES | 13 | LAND-OF-SKY RPO | B-6019 | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
MADISON | SR 1318 (BIG LAUREL ROAD) | NCDOT | SR 1340 TO SR 1636 NEAR MARS HILL. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 13 | LAND-OF-SKY RPO | HS-2013I | DIVISION 13 | HSIP |  |  |  |  | 2024 | 525000 |  |  | 525000
MADISON | I-26 | NCDOT | TENNESSEE STATE LINE TO MILE MARKER 9. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | LAND-OF-SKY RPO | I-5831
MADISON | I-26 | NCDOT | TENNESSEE STATE LINE TO MILE MARKER 9. REPLACE CURB AND DRAINAGE BOXES, AND REHABILITATE BRIDGES. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | LAND-OF-SKY RPO | I-5831A | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2022 | 8728000 |  |  | 8728000 | UNDER CONSTRUCTION.
MADISON | I-26 | NCDOT | TENNESSEE STATE LINE TO MILE MARKER 9. REHABILITATE PAVEMENT. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | LAND-OF-SKY RPO | I-5831B | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2025 | 9000000 |  |  | 9000000
MADISON | SR 1631 (CROSSROADS PARKWAY) | NCDOT | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | HIGHWAY | STI (PRIORITIZATION) | 13 | FRENCH BROAD RIVER MPO | R-5779 | DIVISION 13 | ADHSL, O, T |  |  |  |  | 2021 | 4071000 |  |  | 4071000 | COMPLETE. UNDER CONSTRUCTION. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170)
MADISON | US 25 | NCDOT | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | LAND-OF-SKY RPO | R-5837 | NOT FUNDED | T | NOT FUNDED | 5100000 | NOT FUNDED | 9700000 | NOT FUNDED | 18500000 |  |  | 33300000
MADISON | US 25/70 | NCDOT | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | LAND-OF-SKY RPO | R-5924 | NOT FUNDED | BGLT5 | NOT FUNDED | 1800000 | NOT FUNDED | 3000000 | NOT FUNDED | 32101000 |  |  | 36901000
MADISON | MADISON COUNTY TRANSPORTATION | MADISON COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 13 | LAND-OF-SKY RPO | TK-6143 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 548000 | 548000 | FUNDS AUTHORIZED IN PROGRESS
MARTIN | MARTIN COUNTY AIRPORT (MCZ) | MARTIN COUNTY AIRPORT (MCZ) | CONSTRUCT TAXILANES AND APRON. | AVIATION | STI (PRIORITIZATION) | 1 | MID-EAST RPO | AV-5788 | DIVISION 1 | T |  |  |  |  | 2023 | 950000 |  |  | 950000 | UNDER CONSTRUCTION.
MARTIN | EAST MAIN STREET | WILLIAMSTON | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | BIKE/PED | STI (PRIORITIZATION) | 1 | MID-EAST RPO | EB-5979 | DIVISION 1 | L, TA5200 |  |  |  |  | 2027 | 90000 | 2025 | 10000 | 100000
MARTIN | SR 1142 (PRISON CAMP ROAD) | NCDOT | REPLACE BRIDGE 570053 OVER COLLIE SWAMP. | HIGHWAY | BRIDGES | 1 | MID-EAST RPO | B-5503 | DIVISION 1 | [10 empty] | COMPLETED.
MARTIN | US 13/US 64 (FUTURE I-87) | NCDOT | EDGECOMBE COUNTY LINE TO US 13/17 AND US 64 INTERCHANGE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 1 | MID-EAST RPO | I-6028 | STATEWIDE MOBILITY | [10 empty] | "A" BREAK DELETED, WORK WAS COMPLETED WITH CONTRACT RESURFACING.
MARTIN | US 64 (FUTURE I-87) | NCDOT | US 64 ALTERNATE TO NC 125. | HIGHWAY | INTERSTATE MAINTENANCE | 1 | MID-EAST RPO | I-6028B | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2020 | 5873000 |  |  | 5873000 | COMPLETED.
MARTIN | US 64 (FUTURE I-87) | NCDOT | NC 125 TO US 13/17 AND US 64 INTERCHANGE. | HIGHWAY | INTERSTATE MAINTENANCE | 1 | MID-EAST RPO | I-6028C | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 6000000 |  |  | 6000000 | UNDER CONSTRUCTION.
MARTIN | NC 125 | NCDOT | SR 1182 (EAST COLLEGE ROAD) TO NC 125 NORTHWEST OF WILLIAMSTON. TWO LANES, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 1 | MID-EAST RPO | R-3826 | REGION A | [10 empty] | COMPLETED.
MARTIN | SR 1142 (PRISON CAMP ROAD) | NCDOT | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 1 | MID-EAST RPO | R-4705 | DIVISION 1 | BGLT5 |  |  | 2023 | 2100000 | 2022 | 48147000 |  |  | 50247000 | UNDER CONSTRUCTION.
MARTIN | US 17 | NCDOT | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 1 | MID-EAST RPO | R-5810 | DIVISION 1 | BGLT5, T | 2025 | 30000 | 2025 | 720000 | 2027 | 8100000 |  |  | 8850000
MARTIN | US 13/US 17 | NCDOT | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 1 | MID-EAST RPO | R-5879 | REGION A | NHP | 2025 | 100000 | 2025 | 200000 | 2027 | 2350000 |  |  | 2650000
MARTIN | MARTIN COUNTY | MARTIN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1 | MID-EAST RPO | TK-6144 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 724000 | 724000 | FUNDS AUTHORIZED IN PROGRESS
MARTIN, BEAUFORT | US 17 | NCDOT | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 1, 2 | MID-EAST RPO | R-2511 | DIVISION 1, 2 | T | 2019 | 10471000 | 2019 | 2200000 | 2022 | 99343000 |  |  | 112014000 | UNDER CONSTRUCTION.
MARTIN, BERTIE | US 13, US 17, NC 171 | NCDOT | UPGRADE CURVE WARNING SIGNS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | MID-EAST RPO, PEANUT BELT RPO | HS-2001B | REGION A | HSIP |  |  |  |  | 2023 | 35000 |  |  | 35000 | UNDER CONSTRUCTION.
MARTIN, EDGECOMBE, WASHINGTON, DARE, TYRRELL, NASH | US 64 | NCDOT | BROADBAND AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | HIGHWAY | OTHER | 1, 4 | ALBEMARLE RPO, MID-EAST RPO, UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | HB-0001A | STATEWIDE MOBILITY | DP, HSIP, T |  |  |  |  | 2026 | 26500000 |  |  | 26500000
McDOWELL | SR 1703 (BALDWIN AVENUE) | NCDOT | PERRY STREET TO US 70 (E COURT ST). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | BIKE/PED | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | EB-5753 | DIVISION 13 | L, TA5200 | 2023 | 100000 |  |  | 2024 | 312000 | 2021 | 25000 | 437000
McDOWELL | FONTA FLORA TRAIL | MCDOWELL COUNTY | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | EB-5916 | DIVISION 13 | L, TA5200 | 2023 | 75000 |  |  | 2024 | 3063000 | 2021 | 560000 | 3698000
McDOWELL | SR 1781 (POLLY SPOUT ROAD) | NCDOT | REPLACE BRIDGE 580312 OVER SECOND BROAD RIVER. | HIGHWAY | BRIDGES | 13 | FOOTHILLS RPO | B-6014 | DIVISION 13 | BGOFF | 2022 | 100000 |  |  | 2022 | 4831000 |  |  | 4931000 | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION.
McDOWELL | I-40 | NCDOT | SR 1001 (SUGAR HILL ROAD)/MILE MARKER 81 TO NC 226/MILE MARKER 86. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FOOTHILLS RPO | HI-0009 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2028 | 14900000 |  |  | 14900000
McDOWELL | I-40 | NCDOT | MILE MARKER 67 TO MILE MARKER 73 (OLD FORT MOUNTAIN). CONSTRUCT SAFETY AND DRAINAGE IMPROVEMENTS, REHABILITATE PAVEMENT, AND RECONSTRUCT MEDIAN BARRIER. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FOOTHILLS RPO | HI-0010 | STATEWIDE MOBILITY | HSIP, NHPIM |  |  |  |  | 2023 | 17500000 |  |  | 17500000 | UNDER CONSTRUCTION.
McDOWELL | US 221 | NCDOT | NC 226/ US 221 BUS TO US 70. IMPROVE PAVEMENT. | HIGHWAY | SAFETY | 13 | FOOTHILLS RPO | HS-2013H | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 530000 |  |  | 530000 | UNDER CONSTRUCTION.
McDOWELL | SR 1135 (OLD FORT/ SUGARHILL ROAD) | NCDOT | SR 1103 TO SR 1001 NEAR OLD FORT. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 13 | FOOTHILLS RPO | HS-2013M | DIVISION 13 | HSIP |  |  |  |  | 2023 | 717000 |  |  | 717000
McDOWELL | I-40 | NCDOT | MILE MARKER 73 TO MILE MARKER 81. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 13 | FOOTHILLS RPO | I-5900 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2027 | 25099000 |  |  | 25099000
McDOWELL | US 221 - NC 226 | NCDOT | SR 1434 TO SR 1153. WIDEN TO MULTI-LANES, WITH A BYPASS OF MARION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-0204
McDOWELL | US 221 - NC 226 | NCDOT | SR 1434 NORTH OF MARION TO US 221-NC 226 BUSINESS | HIGHWAY | PRE-STI (HISTORIC) | 13 | FOOTHILLS RPO | R-0204A | [11 empty] | COMPLETE
McDOWELL | US 221 (MARION BYPASS) | NCDOT | US 221-NC 226 BUSINESS TO SOUTH OF SOUTHERN RAILWAY. | HIGHWAY | PRE-STI (HISTORIC) | 13 | FOOTHILLS RPO | R-0204B | [11 empty] | COMPLETE
McDOWELL | US 221 (MARION BYPASS) | NCDOT | SOUTH OF SOUTHERN RAILWAY TO US 221-NC 226 INTERSECTION SOUTH OF MARION | HIGHWAY | PRE-STI (HISTORIC) | 13 | FOOTHILLS RPO | R-0204C | [11 empty] | COMPLETE
McDOWELL | US 221 | NCDOT | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-0204D | NOT FUNDED | T | NOT FUNDED | 3000000 | NOT FUNDED | 500000 | NOT FUNDED | 32500000 |  |  | 36000000
McDOWELL | US 221 | NCDOT | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-0204E | DIVISION 13 | T | 2025 | 7999000 | 2025 | 1200000 | 2028 | 38698000 |  |  | 47897000
McDOWELL | US 221 | NCDOT | SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION TO SR 1153 (GOOSE CREEK ROAD). | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-2597C | NOT FUNDED | NHP | NOT FUNDED | 9800000 | NOT FUNDED | 5800000 | NOT FUNDED | 117500000 |  |  | 133100000
McDOWELL | NC 226 | NCDOT | US 221 TO NC 226A. WIDEN ROADWAY TO THREE LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-5923 | NOT FUNDED | BGLT5 | NOT FUNDED | 100000 | NOT FUNDED | 600000 | NOT FUNDED | 4300000 |  |  | 5000000
McDOWELL | NEW ROUTE | NCDOT | CONSTRUCT ACCESS ROAD TO UNIVERSAL PROPERTY. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | FOOTHILLS RPO | R-5964 | EXEMPT | ADHSL |  |  |  |  | 2021 | 922000 |  |  | 922000 | UNDER CONSTRUCTION. ARC # 19098; AWARD AMOUNT = $987,112
McDOWELL | SR 1001 (SUGAR HILL ROAD) | NCDOT | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | U-5818 | DIVISION 13 | T | 2020 | 90000 |  |  | 2020 | 13230000 | 2020 | 1710000 | 15030000 | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
McDOWELL | US 221 BUSINESS | NCDOT | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | U-5835 | DIVISION 13 | BGANY | 2023 | 6600000 | 2023 | 2000000 | 2025 | 14800000 |  |  | 23400000 | RIGHT-OF-WAY IN PROGRESS.
McDOWELL, RUTHERFORD | US 221 | NCDOT | (1) US 221 IN RUTHERFORD COUNTY FROM US 64 TO THE MCDOWELL COUNTY LINE. (2) US 221 IN MCDOWELL COUNTY ROM THE RUTHERFOD COUNTY LINE TO I-40. INSTALL SINUSIODAL CENTERLINE RUMBLESTRIPES WITH LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 13 | FOOTHILLS RPO | W-5813J | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2022 | 501000 |  |  | 501000 | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. | AVIATION | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | AV-5879 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 607500000 |  |  | 607500000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND WEST RAMP NEAR CONCOURSE A - PHASE II. | AVIATION | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | AV-5881 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2021 | 40100000 |  |  | 40100000 | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). | AVIATION | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | AV-5893 | REGION E | O, T |  |  |  |  | 2025 | 202500000 |  |  | 202500000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | DAVIDSON | DAVIDSON | WEST BRANCH NATURE PRESERVE. CONSTRUCT GREENWAY. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0003 | DIVISION 10 | BGDA, L | [6 empty] | 2023 | 151000 | 151000
MECKLENBURG | THE PARK - HUNTERSVILLE GREENWAY | HUNTERSVILLE | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0010 | DIVISION 10 | BGDA, L, TADA | 2024 | 516000 |  |  | 2026 | 2600000 | 2023 | 376000 | 3492000
MECKLENBURG | IRWIN CREEK GREENWAY | MECKLENBURG COUNTY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0057 | DIVISION 10 | BGDA, CMAQ, L |  |  |  |  | 2025 | 6090000 |  |  | 6090000 | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | RAIL TRAIL PEDESTRIAN BRIDGE | CHARLOTTE | SR 3815 (EAST MOREHEAD STREET) TO BROOKLYN VILLAGE LIGHT RAIL STATION. CONSTRUCT RAIL TRAIL PEDESTRIAN BRIDGE OVER I-277 (BELK FREEWAY). | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0058 | DIVISION 10 | BGDA, L |  |  |  |  | 2023 | 6343000 |  |  | 6343000
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | INSTALL GREENWAY CULVERT UNDER US 21. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0080 | DIVISION 10 | L, TADA |  |  |  |  | 2025 | 3250000 |  |  | 3250000
MECKLENBURG | LEBANON ROAD AND MARGARET WALLACE ROAD | MINT HILL | MARGARET WALLACE ROAD TO GRISTMILL LANE. INSTALL SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. INSTALL SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0081 | DIVISION 10 | L, TADA | 2026 | 133000 |  |  | 2027 | 1081000 | 2024 | 434000 | 1648000
MECKLENBURG | SUGAR CREEK ROAD | CHARLOTTE | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. INSTALL SIDEWALK. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0083 | DIVISION 10 | L, TADA | 2025 | 686000 |  |  | 2026 | 3724000 |  |  | 4410000
MECKLENBURG | ALBEMARLE ROAD AND WILORA LAKE ROAD | CHARLOTTE | REDMAN ROAD TO CENTRAL AVENUE. INSTALL SIDEWALK. ALBEMARKLE ROAD TO 100 FEET NORTH OF BARR DRIVE. INSTALL SIDEWALK. INSTALL PEDESTRIAN IMPROVEMENTS AT VARIOUS INTERSECTIONS. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0084 | DIVISION 10 | L, TADA |  |  |  |  | 2026 | 3192000 |  |  | 3192000
MECKLENBURG | BEATY STREET | DAVIDSON | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED USE PATH. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0085 | DIVISION 10 | L, TADA | 2027 | 601000 |  |  | 2029 | 2561000 | 2025 | 330000 | 3492000
MECKLENBURG | BEATY STREET | DAVIDSON | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). INSTALL SHARED USE PATH. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0096 | DIVISION 10 | L, TADA | 2026 | 601000 |  |  | 2028 | 2561000 | 2024 | 330000 | 3492000
MECKLENBURG | CORNELIUS | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY; CONSTRUCT GREENWAY FROM SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5777 | DIVISION 10 | CMAQ, L | 2021 | 960000 |  |  | 2024 | 2040000 |  |  | 3000000 | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | CHARLOTTE | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | EB-5781 | DIVISION 10 | BGDA, CMAQ, L |  |  |  |  | 2021 | 3159000 |  |  | 3159000 | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | GREENWAY MCALPINE CREEK | MECKLENBURG COUNTY | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | EB-5782 | DIVISION 10 | CMAQ, L, TAANY |  |  |  |  | 2023 | 7876000 |  |  | 7876000 | $3.926M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | MATTHEWS | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5783 | DIVISION 10 | BGANY, BGDA, L | 2022 | 335000 |  |  | 2024 | 1526000 | 2021 | 231000 | 2092000 | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | UPPER MCDOWELL CREEK GREENWAY, CHILGROVE LANE TO NC 73. CONSTRUCT GREENWAY. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5785 | DIVISION 10 | CMAQ, L |  |  |  |  | 2023 | 5339000 |  |  | 5339000 | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | CORNELIUS | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5817 | DIVISION 10 | BGDA, L, TADA |  |  |  |  | 2020 | 3882000 |  |  | 3882000 | COMPLETE.
MECKLENBURG | CHARLOTTE | CHARLOTTE | CHARLOTTE BICYCLE EXPANSION. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5820 | DIVISION 10 | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | MATTHEWS | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5829 | DIVISION 10 | L, TADA |  |  |  |  | 2022 | 2899000 |  |  | 2899000 | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | BIKE/PED | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | EB-5832 | DIVISION 10 | BGDA, L, TAANY |  |  |  |  | 2022 | 1678000 |  |  | 1678000 | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | CHARLOTTE | BELK GREENWAY CONNECTOR PHASE ONE. EAST STONEWALL STREET AT SOUTH DAVIDSON STREET TO SOUTH KINGS DRIVE. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5929 | DIVISION 10 | CMAQ, L | 2021 | 99000 |  |  | 2025 | 1557000 |  |  | 1656000 | $1.159M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | DAVIDSON | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5933 | DIVISION 10 | BGDA, L |  |  |  |  | 2024 | 878000 |  |  | 878000
MECKLENBURG | NC 51 MULTI-USE PATH | MATTHEWS | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | BIKE/PED | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | EB-5969 | DIVISION 10 | L, TAANY, TADA | 2025 | 865000 |  |  | 2027 | 1171000 | 2023 | 464000 | 2500000
MECKLENBURG | IRWIN CREEK GREENWAY EASTERN EXTENSION | MECKLENBURG COUNTY | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | EB-5970 | DIVISION 10 | L, TAANY |  |  |  |  | 2028 | 4637000 |  |  | 4637000
MECKLENBURG | JETTON STREET | DAVIDSON | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | BIKE/PED | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | EB-5971 | DIVISION 10 | L, TAANY |  |  |  |  | 2025 | 290000 |  |  | 290000
MECKLENBURG | CHARLOTTE | CHARLOTTE | HORNETS NEST PARK ACCESS IMPROVEMENTS INCLUDING SIDEWALKS, A MULTI-USE PATH, AND A TRAFFIC SIGNAL WITH LEFT TURN LANES. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-6036 | DIVISION 10 | BGDA, L |  |  |  |  | 2023 | 1875000 |  |  | 1875000
MECKLENBURG | NC 24 (W.T. HARRIS BOULEVARD) | CHARLOTTE | PLAZA ROAD TO GRIER ROAD. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-6050 | DIVISION 10 | L, TADA | 2023 | 120000 |  |  | 2025 | 1918000 | 2023 | 10000 | 2048000
MECKLENBURG | LAWYERS ROAD, WILGROVE-MINT HILL ROAD, WILSON GROV | MINT HILL | EXTEND EXISTING SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-6051 | DIVISION 10 | L, TADA | 2023 | 60000 |  |  | 2024 | 2574000 | 2022 | 376000 | 3010000
MECKLENBURG | W.T. HARRIS BOULEVARD | CHARLOTTE | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-6052 | DIVISION 10 | L, TADA | 2023 | 400000 |  |  | 2025 | 1252000 | 2023 | 10000 | 1662000
MECKLENBURG | MICHAEL BAKER ROAD | CHARLOTTE | REPLACE BRIDGE 590210 OVER BRIAR CREEK IN CHARLOTTE. | HIGHWAY | MUNICIPAL BRIDGE | 10 | CHARLOTTE REGIONAL TPO | B-5378 | DIVISION 10 | [10 empty] | PROJECT ADMINISTERED BY CITY OF CHARLOTTE - MUNICIPAL BRIDGE. UNDER CONSTRUCTION
MECKLENBURG | SARDIS LANE | CHARLOTTE | REPLACE BRIDGE 590433 OVER MCALPINE CREEK. | HIGHWAY | MUNICIPAL BRIDGE | 10 | CHARLOTTE REGIONAL TPO | B-5930 | DIVISION 10 | BGOFF, L |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | PROJECT ADMINISTERED BY CITY OF CHARLOTTE
MECKLENBURG | MORRIS FIELD DRIVE | CHARLOTTE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | HIGHWAY | MUNICIPAL BRIDGE | 10 | CHARLOTTE REGIONAL TPO | B-5931 | DIVISION 10 | BGOFF, L |  |  |  |  | 2023 | 2750000 |  |  | 2750000 | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE.
MECKLENBURG | SR 1138 WESTBOUND | NCDOT | REPLACE BRIDGE 590001 OVER SUGAR CREEK. | HIGHWAY | BRIDGES | 10 | CHARLOTTE REGIONAL TPO | B-5990 | DIVISION 10 | BFP | 2024 | 174000 | 2024 | 174000 | 2026 | 4000000 |  |  | 4348000
MECKLENBURG | CHARLOTTE | CHARLOTTE | TOBY CREEK GREENWAY (PHASE II). CONNECT UNCC TO NEARBY RETAIL AND RESIDENTIAL DEVELOPMENT. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | C-5225
MECKLENBURG | CHARLOTTE | CHARLOTTE | TOBY CREEK GREENWAY, UNIVERSTIY CITY BOULEVARD TO ROCKLAND DRIVE. | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | C-5225A | EXEMPT | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | CHARLOTTE | CHARLOTTE | TOBY CREEK GREENWAY, ROCKLAND DRIVE TO BLUE ROCK DRIVE. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | C-5225B | EXEMPT | [10 empty] | COMPLETE
MECKLENBURG | CHARLOTTE | CHARLOTTE | SR 4979 (BALLANTYNE COMMONS PARKWAY-MCKEE ROAD) AND NC 16 (PROVIDENCE ROAD) IN CHARLOTTE. CONSTRUCT AN ADDITIONAL LEFT TURN LANE ON SR 4979 AND A SECOND LEFT TURN LANE ON SOUTHBOUND NC 16. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | C-5534 | EXEMPT | BGDA |  |  |  |  | 2020 | 640000 |  |  | 640000 | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES.
MECKLENBURG | CHARLOTTE | CHARLOTTE | MECKLENBURG COUNTY AIR QUALITY -GRADE (GRANTS TO REPLACE AGING DIESEL ENGINES). REPLACE, REPOWER OR RETROFIT AGING DIESEL VEHICLES AND EQUIPMENT. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | C-5536 | EXEMPT | CMAQ |  |  |  |  | 2021 | 139000 |  |  | 139000 | COMPLETE.
MECKLENBURG | CHARLOTTE | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | C-5538 | DIVISION 10 | CMAQ, L |  |  |  |  | 2021 | 3676000 |  |  | 3676000 | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | SR 1138 (ARROWOOD ROAD) | CHARLOTTE | NC 49 (SOUTH TRYON) TO SOUTH BOULEVARD. ITS UPGRADES. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | C-5613BD | EXEMPT | CMAQ, L |  |  |  |  | 2022 | 614000 |  |  | 614000 | UNDER CONSTRUCTION.
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | CHARLOTTE | NC 24 (HARRIS BOULEVARD) TO GOVERNOR HUNT ROAD. ITS AND TRAFFIC MANAGEMENT UPGRADES. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | C-5613BE | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 200000 |  |  | 200000 | UNDER CONSTRUCTION.
MECKLENBURG | NC 115 | NCDOT | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | C-5613J | EXEMPT | CMAQ, L | 2022 | 75000 |  |  | 2024 | 1227000 |  |  | 1302000 | RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | US 21 | NCDOT | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | C-5621 | EXEMPT | BA, CMAQ, S(M) | 2020 | 2093000 |  |  | 2023 | 9344000 | 2020 | 1002000 | 12439000 | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | PINEVILLE | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5949 | DIVISION 10 | BGDA, L, O |  |  |  |  | 2022 | 4404000 |  |  | 4404000 | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH
MECKLENBURG | REA ROAD | CHARLOTTE | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0023 | EXEMPT | BA, O | 2023 | 1557000 |  |  | 2025 | 5469000 |  |  | 7026000 | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | SR 3468 (WEDDINGTON ROAD) | NCDOT | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0024 | EXEMPT | BA, T | 2023 | 1500000 | 2023 | 800000 | 2025 | 5923000 | 2021 | 1211000 | 9434000 | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN T FOR CON AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | GREYLOCK RIDGE ROAD | NCDOT | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0025 | EXEMPT | BA | 2023 | 701000 |  |  | 2024 | 5892000 | 2022 | 1016000 | 7609000 | RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | VARIOUS | NCDOT | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, PAVEMENT RESTRIPING AND MARKERS, AND SIGN REPLACEMENT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0038 |  | BGDACV | [6 empty] | 2022 | 5000 | 5000
MECKLENBURG | US 29/74 (WILKINSON BLVD) AND US 29 (N TRYON ST) | NCDOT | US 29/74 (WILKINSON BLVD) FROM GASTON COUNTY LINE TO FIELD RIDGE ROAD AND US 29 (NORTH TRYON STREET) FROM WEST SUGAR CREEK ROAD TO OLD CONCORD ROAD. RESURFACE ROADWAYS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0038A | EXEMPT | BGDACV |  |  |  |  | 2022 | 2596000 |  |  | 2596000 | COMPLETE.
MECKLENBURG | VARIOUS | NCDOT | REPLACE PAVEMENT MARKINGS AND SNOW PLOWABLE MARKERS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0038B | EXEMPT | BGDACV |  |  |  |  | 2022 | 2318000 |  |  | 2318000 | UNDER CONSTRUCTION.
MECKLENBURG | VARIOUS | NCDOT | REPLACE TRAFFIC SIGNAL LOOPS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0038C | EXEMPT | BGDACV |  |  |  |  | 2022 | 90000 |  |  | 90000 | COMPLETE.
MECKLENBURG | I-485 | NCDOT | REPLACE OVERHEAD SIGNS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0038D | EXEMPT | BGDACV |  |  |  |  | 2022 | 705000 |  |  | 705000 | UNDER CONSTRUCTION.
MECKLENBURG | SR 2822 (ROBINSON CHURCH ROAD) | CHARLOTTE | NC 24 TO PLOTT ROAD. WIDEN TO THREE LANES. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0053 | DIVISION 10 | L, T(DA) |  |  |  |  | 2025 | 12454000 |  |  | 12454000 | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG | NC 115 | HUNTERSVILLE | SR 2427 (MCCORD ROAD) TO SAM FURR ROAD. IMPROVE CORRIDOR. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0056 | EXEMPT | L, T(DA) | 2025 | 2852000 |  |  | 2027 | 4938000 | 2024 | 751000 | 8541000 | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP.
MECKLENBURG | NC 24 WT HARRIS BOULEVARD | CHARLOTTE | SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO I-85 NORTH RAMP. INSTALL OVERHEAD STREET LIGHTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0057 | DIVISION 10 | BA, L |  |  |  |  | 2023 | 1535000 |  |  | 1535000
MECKLENBURG | BEATY STREET | DAVIDSON | MAIN STREET. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0111 | EXEMPT | CMAQ, L | 2027 | 339000 |  |  | 2029 | 2742000 | 2025 | 358000 | 3439000
MECKLENBURG | DEARMON ROAD | CHARLOTTE | BENFIELD ROAD TO BROWNE ROAD. COMPLETE STREET IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0112 | DIVISION 10 | BGDA, L |  |  |  |  | 2024 | 15675000 |  |  | 15675000
MECKLENBURG | LANCASTER HIGHWAY | CHARLOTTE | PROVIDENCE ROAD W. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0113 | EXEMPT | CMAQ, L |  |  |  |  | 2026 | 1693000 |  |  | 1693000
MECKLENBURG | STUMPTOWN ROAD | HUNTERSVILLE | NC 115. EXTEND ROADWAY APPROXIMATELY 800 FEET. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0118 | REGION E | BGDA, L | 2025 | 1980000 |  |  | 2027 | 4280000 | 2025 | 185000 | 6445000
MECKLENBURG | NC 24, NC 27 | NCDOT | SR 3110 (ARLINGTON CHURCH ROAD) NEAR CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | HS-2010A | REGION E | HSIP | 2022 | 175000 |  |  | 2023 | 1350000 |  |  | 1525000 | UNDER CONSTRUCTION.
MECKLENBURG | I-277 | NCDOT | INSTALL SMART CUSHIONS AT VARIOUS EXITS. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | HS-2010B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 144000 |  |  | 144000
MECKLENBURG | NC 49 (SOUTH TRYON STREET) | NCDOT | NC 49 (SOUTH TRYON STREET) AT GENERAL DRIVE; AND, NC 49 (SOUTH TRYON STREET) AT SR 1347 (NEVADA BOULEVARD). INSTALL TRAFFIC SIGNAL AT NC 49 AND GENERAL DRIVE, AND CONVERT NC 49 AT SR 1347 (NEVADA BOULEVARD) TO A DIRECTIONAL CROSSOVER. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | HS-2010E | REGION E | HSIP |  |  | 2025 | 25000 | 2025 | 534000 |  |  | 559000
MECKLENBURG | NC 51 | NCDOT | NC 51 AND POLK STREET. INSTALL PEDESTRIAN SIGNALS AND ACCOMMODATIONS. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | HS-2010G | REGION E | HSIP |  |  |  |  | 2024 | 144000 |  |  | 144000
MECKLENBURG | NC 73 (SAM FURR ROAD) | NCDOT | SR 5544 (CATAWBA AVENUE) INTERSECTION. INSTALL PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | HS-2010J | REGION E | HSIP |  |  |  |  | 2023 | 108000 |  |  | 108000 | UNDER CONSTRUCTION.
MECKLENBURG | SR 5901 (BILLY GRAHAM PARKWAY) | NCDOT | NC 49 (TRYON ROAD) TO I-85. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | HS-2010L | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 960000 |  |  | 960000
MECKLENBURG | I-77 | NCDOT | I-77/EXIT 30 (GRIFFITH STREET) INTERCHANGE. CONSTRUCT ROUNDABOUTS AT NORTHBOUND AND SOUTHBOUND RAMP TERMINI. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | I-4750AC | EXEMPT | [10 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | I-485, I-77 SOUTH OF CHARLOTTE TO US 74 (INDEPENDENCE BOULEVARD). ADD ONE EXPRESS LANE IN EACH DIRECTION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-5507 | STATEWIDE MOBILITY | T |  |  |  |  | 2019 | 458656000 |  |  | 458656000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT
MECKLENBURG | I-77 | NCDOT | SR 2136 (GILEAD ROAD) INTERCHANGE. UPGRADE EXISTING INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-5714 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | I-77 | NCDOT | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-5715 | STATEWIDE MOBILITY | NHP | 2023 | 19000000 | 2023 | 3000000 | 2026 | 61800000 |  |  | 83800000 | RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | I-77 | NCDOT | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-277 INTERCHANGES, AND INSTALL RAMP METERS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-5718
MECKLENBURG | I-77 | NCDOT | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-5718A | STATEWIDE MOBILITY | BOND R, NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 660000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000000 |  |  | 1390900000
MECKLENBURG | I-77 | NCDOT | I-277/US 74 (BELK FREEWAY) TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BROOKSHIRE FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-5718B | NOT FUNDED
MECKLENBURG | I-277 | NCDOT | I-77 TO EAST 10TH STREET. RESURFACING AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5746
MECKLENBURG | I-277 (BELK FRWY) | NCDOT | I-77 TO EAST STONEWALL STREET. BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5746A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
MECKLENBURG | I-277 (BELK FRWY) | NCDOT | EAST STONEWALL STREET TO EAST 10TH STREET. BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5746B | STATEWIDE MOBILITY | [10 empty] | COMPLETE
MECKLENBURG | I-277 (BROOKSHIRE FRWY) | NCDOT | I-77 TO EAST 10TH STREET. RESURFACE ROADWAY AND REHABILITATE BRIDGES FROM JOHNSON STREET TO EAST 10TH STREET. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5746C | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 29400000 |  |  | 29400000 | UNDER CONSTRUCTION.
MECKLENBURG | I-77 | NCDOT | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5769 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 15297000 |  |  | 15297000 | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-85 | NCDOT | CONCRETE PAVEMENT JOINT 0.3 MILES SOUTH OF NC 16 TO CONCRETE PAVEMENT JOINT SOUTH OF SR 1601 (MOORES CHAPEL ROAD). PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5770 | STATEWIDE MOBILITY | [10 empty] | PROJECT COMBINED WITH I-5796 - UNDER CONSTRUCTION
MECKLENBURG | I-85 | NCDOT | 0.1 MILE NORTH OF SR 5901 (BILLY GRAHAM PKWY) TO 0.3 MILE SOUTH OF NC 16 AT MILE MARKER 35.93. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5796 | STATEWIDE MOBILITY | [10 empty] | TO BE LET WITH I-5770 - UNDER CONSTRUCTION
MECKLENBURG | I-485 | NCDOT | I-85 TO ROCKY RIVER ROAD. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5798 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
MECKLENBURG | I-85 | NCDOT | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5826 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 8940000 |  |  | 8940000 | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-485 | NCDOT | I-77 TO NC 49. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5828 | STATEWIDE MOBILITY | HFB, NHPIM |  |  |  |  | 2025 | 11950000 |  |  | 11950000 | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS
MECKLENBURG | I-85 | NCDOT | GASTON COUNTY LINE TO 0.7 MILES NORTH OF GASTON COUNTY LINE. INCLUDES RAMPS FROM GASTON COUNTY LINE TO GLENWOOD AVENUE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5837 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 3368000 |  |  | 3368000 | UNDER CONSTRUCTION.
MECKLENBURG | I-85 | NCDOT | REHABIILITATE BRIDGES 590203 (I-85 NB) AND 590204 (I-85 SB) OVER SEABOARD COASTLINE RAILROAD. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5838 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 900000 |  |  | 900000 | UNDER CONSTRUCTION.
MECKLENBURG | I-485 | NCDOT | PAVEMENT AND BRIDGE REHABILITATION AT OAKDALE ROAD INTERCHANGE AT MILEMARKER 17.2. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5861 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION.
MECKLENBURG | I-485 | NCDOT | BLAIR ROAD TO IDLEWILD ROAD. PAVEMENT REHABILITATION | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5904 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 9801000 |  |  | 9801000 | COMPLETED - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-85 | NCDOT | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-5905 | STATEWIDE MOBILITY | BGDA, NHPIM, S(M) |  |  |  |  | 2021 | 17588000 |  |  | 17588000 | COMBINED WITH I-5906. UNDER CONSTRUCTION.
MECKLENBURG | I-485 | NCDOT | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-5963 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28899000 |  |  | 41299000
MECKLENBURG | I-485 | NCDOT | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-5973 | REGION E | T |  |  | 2022 | 195000 | 2023 | 8000000 |  |  | 8195000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3.5M FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE)
MECKLENBURG | I-85 | NCDOT | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6012 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11500000 |  |  | 13500000
MECKLENBURG | I-85 | NCDOT | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6013 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16000000 |  |  | 17100000
MECKLENBURG | I-77 | NCDOT | I-85 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6014 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 96100000 |  |  | 97700000
MECKLENBURG | I-485 | NCDOT | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHNAGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6015 | NOT FUNDED | T | NOT FUNDED | 8400000 | NOT FUNDED | 1100000 | NOT FUNDED | 9999000 |  |  | 19499000
MECKLENBURG | I-85 | NCDOT | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6016 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31900000 |  |  | 35900000
MECKLENBURG | I-85 | NCDOT | SR 2472 (MALLARD CREEK CHURCH ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6017 | NOT FUNDED | NHP | NOT FUNDED | 1100000 | NOT FUNDED | 1800000 | NOT FUNDED | 13099000 |  |  | 15999000
MECKLENBURG | I-485 | NCDOT | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6019 | NOT FUNDED | NHP | NOT FUNDED | 14900000 | NOT FUNDED | 4700000 | NOT FUNDED | 20701000 |  |  | 40301000
MECKLENBURG | I-85 | NCDOT | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6020 | NOT FUNDED | NHP | NOT FUNDED | 10000000 | NOT FUNDED | 2000000 | NOT FUNDED | 15299000 |  |  | 27299000
MECKLENBURG | I-277 | NCDOT | KENILWORTH AVENUE TO GRAHAM STREET. UPGRADE INTERCHANGES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6022 | [11 empty] | COORDINATE WITH U-6013
MECKLENBURG | I-277 | NCDOT | KENILWORTH AVENUE TO NORTH DAVIDSON STREET AND US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO PECAN AVENUE. UPGRADE INTERCHANGES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6022A | NOT FUNDED | NHP | NOT FUNDED | 55600000 | NOT FUNDED | 1100000 | NOT FUNDED | 250401000 |  |  | 307101000
MECKLENBURG | I-277 | NCDOT | NORTH DAVIDSON STREET TO GRAHAM STREET. UPGRADE INTERCHANGES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6022B | NOT FUNDED | NHP |  |  | NOT FUNDED | 200000 | NOT FUNDED | 148900000 |  |  | 149100000
MECKLENBURG | I-277 (BROOKSHIRE FREEWAY) | NCDOT | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | I-6052 | STATEWIDE MOBILITY | BGDA, NHFP, S(M) |  |  |  |  | 2023 | 14800000 |  |  | 14800000 | $5M IN NHPIM FUNDS SWITCHED WITH $5M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION.
MECKLENBURG | I-85 | NCDOT | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6053 | NOT FUNDED | NHP | NOT FUNDED | 26973000 | NOT FUNDED | 655000 | NOT FUNDED | 24300000 |  |  | 51928000
MECKLENBURG | I-77 | NCDOT | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | I-6056 | NOT FUNDED | NHP | NOT FUNDED | 300000 | NOT FUNDED | 200000 | NOT FUNDED | 8200000 |  |  | 8700000
MECKLENBURG | I-485 (CHARLOTTE SOUTHERN OUTER LOOP) | NCDOT | WEST OF I-77 TO US 74. MULTI-LANE FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | R-0211 | [11 empty] | UNDER CONSTRUCTION. PROJECT LET WITH I-5507.
MECKLENBURG | I-485 | NCDOT | SR 3468 (WEDDINGTON ROAD). CONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | R-0211EC | DIVISION 10 | T |  |  |  |  | 2019 | 9000000 |  |  | 9000000
MECKLENBURG | I-485 (CHARLOTTE WESTERN OUTER LOOP) | NCDOT | WEST OF I-77 TO I-85 NORTH. FREEWAY ON NEW LOCATION. | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248 | [11 empty] | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2010-2021
MECKLENBURG | I-485 | NCDOT | WEST OF I-77 SOUTH TO US 29-74 | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248A | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | NORTH OF US 29/US 74 (WILKINSON BOULEVARD) TO NORTH OF I-85 | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248BA | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | NORTH OF I-85 TO NORTH OF NC 27 | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248BB | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | NORTH OF NC 27 (MOUNT HOLLY ROAD) TO EAST OF SR 2042 (OAKDALE ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248C | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | EAST OF SR 2042 (OAKDALE ROAD) TO EAST OF NC 115 (OLD STATESVILLE ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248D | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | EAST OF NC 115 (OLD STATESVILLE ROAD) TO I-85 NORTH | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248E | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2010 | 10968000 |  |  | 10968000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
MECKLENBURG | I-485 | NCDOT | ITS FOR R-2248 E | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | R-2248EA | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | EDINMEADOW DRIVE NEPA STUDY | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248EB
MECKLENBURG | I-485 | NCDOT | I-485, WEST OF I-77 TO ARROWOOD ROAD-BROWN GRIER ROAD | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248F | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | I-485 INTERCHANGE WITH SR 2042 (OAKDALE ROAD) | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | R-2248G | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | I-485 | NCDOT | I-485 INTERCHANGE WITH SR 1148 (GARRISON ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2248H | [11 empty] | COMPLETE
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NCDOT | NC 73 (SAM FURR ROAD) TO EAST OF SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | R-2555
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NCDOT | SR 2151 (JETTON ROAD) TO SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | R-2555A | [11 empty] | COMPLETE
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NCDOT | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | R-2555B | DIVISION 10 | L, T |  |  |  |  | 2025 | 28749000 |  |  | 28749000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 5/6 SALE).
MECKLENBURG | NC 73 | NCDOT | US 21 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | R-2632 | [11 empty] | COORDINATE WITH R-5706A & B. $7.273M IN NHP FUNDS SWITCHED WITH $7.237M IN BGDA AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | NC 73 | NCDOT | US 21 TO NC 115. WIDEN TO MULTI-LANES. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | R-2632AA | [11 empty] | COMPLETE
MECKLENBURG | NC 73 | NCDOT | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | R-2632AB | REGION E | BGDA, NHP, S(M) | 2023 | 8300000 | 2023 | 5100000 | 2026 | 58400000 |  |  | 71800000 | RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | NC 73 | NCDOT | NC 73 AT NC 115. CONVERT RIGHT TURN LANE ON NC 115 SOUTHBOUND TO A THROUGH LANE AND WIDEN FOR MERGING TAPER. | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | R-2632AC | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | NC 73 | NCDOT | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | R-5721B | REGION E | BA, T | 2023 | 15436000 | 2023 | 3000000 | 2026 | 28100000 |  |  | 46536000 | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | BROOKSHIRE FREEWAY TO IDLEWILD ROAD IN CHARLOTTE. ADD ADDITIONAL LANES AND CONSTRUCT INTERCHANGES WITH SHARON AMITY ROAD AND IDLEWILD ROAD AND SAFETY IMPROVEMENTS. | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | U-0209 | [11 empty] | COMPLETE - GARVEE BOND FUNDING: $50M FOR RIGHT-OF-WAY, PAYBACK FY 2010-2021; $2M FOR CONSTRUCTION, PAYBACK FY 2013-2024
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | NC 24/NC 27 (ALBEMARLE ROAD) TO IDLEWILD ROAD | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | U-0209B | PRE-STI (TRANSITION) | NHP | 2010 | 10968000 |  |  | 2013 | 1025000 |  |  | 11993000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | SEPARATE ITS CONTRACT FOR U-209 B | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | U-0209BA | PRE-STI (TRANSITION) | [10 empty] | WORK TO BE CONSTRUCTED BY PROJECT U-6103
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | NCDOT | SR 2480 (SUGAR CREEK ROAD) TO SR 2472 (MALLARD CREEK CHURCH ROAD) IN CHARLOTTE. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | U-2507
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | NCDOT | SR 2480 (SUGAR CREEK ROAD) TO SR 2665 (HARRIS BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | U-2507A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | NEW ROUTE | NCDOT | SR 2467 (MALLARD CREEK ROAD) TO IBM DRIVE. CONSTRUCT NEW CONNECTOR ROAD AND MULTI-USE PATH. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | U-2507AA | PRE-STI (TRANSITION) | [10 empty] | IMPROVEMENTS CONSTRUCTED UNDER U-2507A
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | NCDOT | SR 2665 (W.T. HARRIS BOULEVARD) TO SR 2472 (MALLARD CREEK CHURCH ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO | U-2507B | [11 empty] | COMPLETE
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | WEST OF IDLEWILD ROAD TO I-485. UPGRADE ROADWAY TO EXPRESSWAY WITH EXPRESS LANES AND CONSTRUCT IMPROVEMENTS ON PARALLEL ROUTES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509
MECKLENBURG | US 74 | NCDOT | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509AA | STATEWIDE MOBILITY | NHP | 2024 | 64401000 | 2024 | 1800000 | 2028 | 40401000 |  |  | 106602000 | SEGMENTS C1, C2
MECKLENBURG | US 74 | NCDOT | SARDIS ROAD AND SR 3473 (SAM NEWELL ROAD) INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROAD NORTH EXTENSION TO SAM NEWELL ROAD. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509AB | STATEWIDE MOBILITY | NHP | 2024 | 66499000 | 2024 | 2700000 | 2028 | 45306000 |  |  | 114505000 | SEGMENTS C6, C7A, C8
MECKLENBURG | US 74 | NCDOT | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509AC | STATEWIDE MOBILITY | NHP | 2024 | 18201000 | 2024 | 3000000 | 2028 | 11199000 |  |  | 32400000 | SEGMENT C11
MECKLENBURG | US 74 | NCDOT | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509AD | STATEWIDE MOBILITY | NHP | 2024 | 51601000 | 2024 | 1800000 | 2028 | 26999000 |  |  | 80400000 | SEGMENT C10, C13
MECKLENBURG | US 74 | NCDOT | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509B | STATEWIDE MOBILITY | NHP | 2025 | 26001000 | 2025 | 0 | 2028 | 25250000 |  |  | 51251000 | SEGMENT M1
MECKLENBURG | US 74 | NCDOT | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509C | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 70350000 |  |  | 115150000 | SEGMENT M2
MECKLENBURG | US 74 | NCDOT | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509D | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 92300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 202205000 |  |  | 304805000 | SEGMENTS C14, M3
MECKLENBURG | US 74 PARALLEL ROUTES | NCDOT | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509E | NOT FUNDED | T | NOT FUNDED | 43200000 | NOT FUNDED | 3500000 | NOT FUNDED | 61200000 |  |  | 107900000 | SEGMENTS C3, C4, C5, C7B, C12
MECKLENBURG | SR 3156 (MARGARET WALLACE ROAD) | NCDOT | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509EA | DIVISION 10 | L, T(DA) | 2026 | 8568000 |  |  | 2029 | 5796000 |  |  | 14364000 | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP.
MECKLENBURG | INDEPENDENCE POINTE PARKWAY | NCDOT | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-2509EB | DIVISION 10 | T | 2026 | 12600000 | 2026 | 600000 | 2029 | 8200000 |  |  | 21400000 | SEGMENT C9
MECKLENBURG | NEW ROUTE | NCDOT | SR 3457 (CAMPUS RIDGE ROAD) TO SR 3448 (PLEASANT PLAINS ROAD) IN MATTHEWS. CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4713 | [11 empty] | OTHER FUNDS PROVIDED BY TOWN OF MATTHEWS. U-4713A TO BE LET WITH U-4714AC AND B.
MECKLENBURG | SR 3440 (MCKEE ROAD) EXTENSION | NCDOT | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4713A | DIVISION 10 | L, T | 2020 | 2680000 | 2021 | 500000 | 2024 | 8260000 | 2020 | 1155000 | 12595000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
MECKLENBURG | CAMPUS RIDGE ROAD REALIGNMENT | NCDOT | SR 1009 (JOHN STREET) TO SR 3457 (CAMPUS RIDGE ROAD) | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | U-4713B | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4714AA | DIVISION 10 | BGANY, T | 2028 | 9149000 | 2028 | 1900000 | 2030 | 14300000 |  |  | 25349000
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | I-485. IMPROVE INTERCHANGE | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4714AB | DIVISION 10 | [10 empty] | LET WITH I-5507
MECKLENBURG | SR 3174) (IDLEWILD ROAD) | NCDOT | SR 3175 (STALLINGS ROAD) TO I-485. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4913A | DIVISION 10 | T | 2026 | 750000 | 2026 | 250000 | 2028 | 4400000 |  |  | 5400000
MECKLENBURG | NC 51 | NCDOT | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5007 | REGION E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39201000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 68000000 |  |  | 117901000
MECKLENBURG | SR 2975 (SUGAR CREEK ROAD) | NCDOT | CONSTRUCT GRADE SEPARATION OVER NORTH CAROLINA RAILROAD/NORFOLK SOUTHERN RAILWAY CROSSING 715 352H AND THE CLOSURE OF CRAIGHEAD ROAD CROSSING 715 355D. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | U-5008 | [11 empty] | DP ARE FEDERAL RAILROAD ADMINISTRATION (FRA) PRIIA GRANT, NCRR, NSR AND CITY OF CHARLOTTE FUNDS
MECKLENBURG | NORTH DAVIDSON STREET | NCDOT | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | HIGHWAY | OTHER | 10 | CHARLOTTE REGIONAL TPO | U-5008A | PRE-STI (TRANSITION) | DP | 2022 | 1000000 | 2022 | 25000 | 2023 | 1200000 |  |  | 2225000 | UNDER CONSTRUCTION.
MECKLENBURG | NORTHCROSS DRIVE EXTENSION | NCDOT | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | U-5108 | PRE-STI (TRANSITION) | BA, BGANY, L, S(M) | 2020 | 3500000 |  |  | 2024 | 15900000 | 2020 | 960000 | 20360000 | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | HUNTERSVILLE | NCDOT | INTERSECTION OF US 21 AND GILEAD ROAD IN HUNTERSVILLE. CONSTRUCT INTERSECTION IMPROVEMENTS, INCLUDING BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | U-5114 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | NCDOT | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5763 | REGION E | T | 2026 | 16000000 | 2026 | 5600000 | 2029 | 21700000 |  |  | 43300000
MECKLENBURG | NC 73 (SAM FURR ROAD) | NCDOT | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5765 | REGION E | T | 2023 | 58430000 | 2023 | 7500000 | 2026 | 31500000 |  |  | 97430000 | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | NC 160 | NCDOT | SOUTH CAROLINA LINE TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5766
MECKLENBURG | NC 160 | NCDOT | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5766A | REGION E | T | 2025 | 20500000 | 2025 | 4100000 | 2028 | 65399000 |  |  | 89999000
MECKLENBURG | NC 160 | NCDOT | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5766B | REGION E | T | 2025 | 59400000 | 2025 | 6500000 | 2029 | 65800000 |  |  | 131700000
MECKLENBURG | US 21 (STATESVILLE ROAD) | NCDOT | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5767 | REGION E | T | 2026 | 39080000 | 2026 | 4400000 | 2029 | 27303000 |  |  | 70783000 | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE)
MECKLENBURG | NC 49 & BACK CREEK CHURCH ROAD | NCDOT | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5768 | REGION E | L, T | 2026 | 29400000 | 2026 | 4000000 | 2029 | 56300000 |  |  | 89700000 | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE
MECKLENBURG | US 21 | NCDOT | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5771 | REGION E | BA, T | 2022 | 53050000 | 2022 | 1600000 | 2025 | 22401000 |  |  | 77051000 | RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | NC 115 (OLD STATESVILLE ROAD) | NCDOT | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5772 | REGION E | T | 2028 | 6500000 | 2028 | 4300000 | 2031 | 33700000 |  |  | 44500000
MECKLENBURG | CHARLOTTE | NCDOT | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5803 | DIVISION 10 | L, T, T(DA) | 2024 | 3000000 |  |  | 2025 | 25638000 |  |  | 28638000 | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | NCDOT | FULLWOOD LANE TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5804
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | NCDOT | FULLWOOD LANE TO FOUR MILE CREEK. WIDEN TO FOUR-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5804A | [11 empty] | COMPLETE - BY TOWN OF MATTHEWS USING TOWN FUNDS.
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | NCDOT | FOUR MILE CREEK TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5804B | DIVISION 10 | T |  |  |  |  | 2019 | 1470000 |  |  | 1470000 | COMPLETE. BUILD NC BOND FUNDING: $1.134 M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE).
MECKLENBURG | SR 1009 (MONROE ROAD) | NCDOT | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5805 | DIVISION 10 | BGANY, L, T | 2020 | 750000 |  |  | 2023 | 7440000 |  |  | 8190000 | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | SR 2136 (GILEAD ROAD) | NCDOT | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5807 | DIVISION 10 | T | 2028 | 38295000 | 2028 | 2000000 | 2028 | 10073000 |  |  | 50368000 | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE)
MECKLENBURG | CORNELIUS NC 115 | NCDOT | POTTS STREET. CONSTRUCT IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5873 | EXEMPT | BA, CMAQ, S(M) | 2020 | 1700000 |  |  | 2024 | 3416000 | 2020 | 100000 | 5216000 | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | CHARLOTTE | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5874 | DIVISION 10 | BGANY, BGDA, L, O | 2020 | 3346000 |  |  | 2022 | 31421000 |  |  | 34767000 | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES.
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | CHARLOTTE | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5905 | [11 empty] | SEGMENTS A AND B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | CHARLOTTE | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5905A | DIVISION 10 | BA, BGDA |  |  |  |  | 2021 | 8661000 |  |  | 8661000 | RIGHT-OF-WAY IN PROGRESS
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | CHARLOTTE | IMPROVE INTERSECTIONS OF SR 2112 (LAKEVIEW ROAD)/NC 24 (HARRIS BOULEVARD) AND SR 2112 (LAKEVIEW ROAD)/US 21 (STATESVILLE ROAD). | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5905B | EXEMPT | BA, BGDA |  |  |  |  | 2021 | 3162000 |  |  | 3162000
MECKLENBURG | CHAPEL ROAD) CORNELIUS SR 2195 (TORRENCE | NCDOT | SR 5544 (WEST CATAWBA AVENUE). INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5906 | DIVISION 10 | BA, T(DA) | 2020 | 9153000 |  |  | 2024 | 3741000 | 2020 | 949000 | 13843000 | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | DAVIDSON | NCDOT | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5907 | DIVISION 10 | BA, BGDA, L, T(DA) | 2020 | 2083000 |  |  | 2024 | 7489000 | 2021 | 544000 | 10116000 | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES.
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5908 | [11 empty] | RIGHT-OF-WAY IN PROGRESS; SEGMENTS A & B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADD'L FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5908A | DIVISION 10 | BGANY, BGDA, L | 2020 | 825000 |  |  | 2021 | 4653000 |  |  | 5478000 | UNDER CONSTRUCTION.
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5908B | EXEMPT | BGANY, BGDA, L | 2020 | 825000 |  |  | 2021 | 9204000 |  |  | 10029000 | UNDER CONSTRUCTION.
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NCDOT |  | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5955 | REGION E
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NCDOT | IMPROVE I-85 NORTHBOUND RAMP TO EASTBOUND NC 16. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5955A | REGION E | T |  |  |  |  | 2023 | 2100000 |  |  | 2100000 | UNDER CONSTRUCTION.
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NCDOT | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. CONVERT NC 16 AND IDAHO DRIVE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5955B | REGION E | T | 2025 | 4300000 | 2025 | 345000 | 2028 | 12699000 |  |  | 17344000
MECKLENBURG | NC 27 (FREEDOM DRIVE) | NCDOT | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5957 | REGION E | T | 2026 | 13100000 | 2026 | 500000 | 2029 | 17900000 |  |  | 31500000
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | NCDOT | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6028 | DIVISION 10 | T | 2027 | 7700000 | 2027 | 4000000 | 2030 | 20400000 |  |  | 32100000
MECKLENBURG | SR 4979 (BALLANTYNE COMMONS PARKWAY) | NCDOT | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6030 | NOT FUNDED | T | NOT FUNDED | 22700000 | NOT FUNDED | 4610000 | NOT FUNDED | 24298000 |  |  | 51608000
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NCDOT | NC 16 (BROOKSHIRE BOULEVARD) AT SR 2004 (MOUNT HOLLY HUNTERSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | ECONOMIC DEVELOPMENT | 10 | CHARLOTTE REGIONAL TPO | U-6084 | REGION E | T |  |  |  |  | 2018 | 1963000 |  |  | 1963000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE.
MECKLENBURG | NC 51 | NCDOT | PARK ROAD TO CARMEL ROAD IN PINEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6086 | EXEMPT | BGANY, L |  |  |  |  | 2025 | 7553000 |  |  | 7553000 | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP
MECKLENBURG | DAVIDSON | NCDOT | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6092 | EXEMPT | BGDA, CMAQ, L | 2022 | 795000 |  |  | 2024 | 2471000 | 2020 | 150000 | 3416000 | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6103 | STATEWIDE MOBILITY | NHP | 2025 | 10500000 | 2025 | 1100000 | 2028 | 93200000 |  |  | 104800000
MECKLENBURG | CORNELIUS | NCDOT | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6105 | DIVISION 10 | BGANY, BGDA, L | 2023 | 2064000 |  |  | 2024 | 4633000 |  |  | 6697000 | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6106 | DIVISION 10 | BGANY, BGDA, L | 2022 | 3134000 |  |  | 2025 | 10684000 |  |  | 13818000 | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP.
MECKLENBURG | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | NCDOT | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6109 | REGION E | NHP | 2025 | 5000000 | 2025 | 1700000 | 2028 | 47400000 |  |  | 54100000
MECKLENBURG | SR 3687 (PARK ROAD) | NCDOT | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6165 | NOT FUNDED | BGANY | NOT FUNDED | 21255000 | NOT FUNDED | 2000000 | NOT FUNDED | 9400000 |  |  | 32655000
MECKLENBURG | NEW ROUTE | NCDOT | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6166 | NOT FUNDED | T | NOT FUNDED | 6600000 | NOT FUNDED | 500000 | NOT FUNDED | 8498000 |  |  | 15598000
MECKLENBURG | ARDREY KELL ROAD | NCDOT | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6167 | NOT FUNDED | BGANY | NOT FUNDED | 94300000 | NOT FUNDED | 1500000 | NOT FUNDED | 31401000 |  |  | 127201000
MECKLENBURG | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NCDOT | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6168 | NOT FUNDED | T | NOT FUNDED | 9700000 | NOT FUNDED | 1600000 | NOT FUNDED | 18800000 |  |  | 30100000
MECKLENBURG | BAILEY ROAD EXTENSION | NCDOT | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6171 | NOT FUNDED | T | NOT FUNDED | 900000 | NOT FUNDED | 2300000 | NOT FUNDED | 19500000 |  |  | 22700000
MECKLENBURG | MECKLENBURG COUNTY | NCDOT | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | W-5710X | DIVISION 10 | BGANY, HSIP, L |  |  |  |  | 2025 | 9214000 |  |  | 9214000 | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP.
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TA-4710 | PUBLIC TRANSIT | 5307, 5339, L, S | [6 empty] | 2021 | 27252000 | 27252000 | "L" REFLECTS CATS CAPITAL PROGRAM
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TA-4711 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 11762000 | 11762000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TA-4960 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 3279000 | 3279000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | MECKLENBURG COUNTY | MECKLENBURG COUNTY | EXPAND PARATRANSIT FLEET BY PURCHASING ADDITIONAL BUSES. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | TA-6673 | DIVISION 10 | O, T | [6 empty] | 2021 | 2500000 | 2500000 | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS
MECKLENBURG | CHARLOTTE REGIONAL | CHARLOTTE REGIONAL | INNOVATIVE COORDINATED ACCESS AND MOBILITY PILOT PROGRAM VEHICLES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TA-6706 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 140000 | 140000 | ADD PROJECT TA-6706 TO STIP FOR FY 20. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF CRTPO MPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | TA-6724 | DIVISION 10 | BGDA, CMAQ, L, S(M) | 2022 | 1257000 |  |  | 2023 | 9905000 | 2022 | 1510000 | 12672000 | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | EXPANSION VANPOOL | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TC-0014 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 174000 | 174000 | "L" REFLECTS CATS CAPITAL FUND
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | CITY LYNX GOLD LINE - AMERICAN RESCUE PLAN SMALL STARTS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TC-0024 | PUBLIC TRANSIT | 5309 | [6 empty] | 2022 | 11122000 | 11122000
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TD-4701 | PUBLIC TRANSIT | 5307, L, S |  |  |  |  | 2020 | 21961000 |  |  | 21961000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | FACILITY - TRANSIT CENTER - UPGRADES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TD-4702 | PUBLIC TRANSIT | 5307, L, S |  |  |  |  | 2020 | 720000 |  |  | 720000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TE-4901 | PUBLIC TRANSIT | 5309, L, S |  |  |  |  | 2020 | 66328000 |  |  | 66328000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | RAPID TRANSIT CORRIDOR STUDIES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TE-4902 | PUBLIC TRANSIT | 5307, FED, L, S |  |  |  |  | 2021 | 200000 |  |  | 200000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE BATTERY ELECTRIC BUSES, CHARGING STATIONS, ONSITE TRAINING AND STARTUP SUPPORT AND TESTING | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TG-0010 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 7448000 | 7448000
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TG-4726 | PUBLIC TRANSIT | 5307, FMOD, L | [6 empty] | 2020 | 17699000 | 17699000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | ROUTINE CAPITAL - SERVICE VEHICLE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TG-4827 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2661000 | 2661000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - RAIL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TG-5118A | PUBLIC TRANSIT | 5337, L, S | [6 empty] | 2020 | 55592000 | 55592000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | LIGHT RAIL VEHICLE OVERHAUL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TG-5118B | PUBLIC TRANSIT | 5307, 5337, L | [6 empty] | 2020 | 14178000 | 14178000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PREVENTIVE MAINTENANCE - RAIL, BUS AND FACILITIES | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TG-5119 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 47589000 | 47589000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | MECKLENBURG TRANSPORTATION | MECKLENBURG TRANSPORTATION | 5307 FUNDING FOR FY20-21 (20-LU-051) | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TG-6790 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1580000 | 1580000 | ADDING FFY20-21
MECKLENBURG | MECKLENBURG TRANSPORTATION | MECKLENBURG TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TK-6145 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1020000 | 1020000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | INSTALL ELECTRIC BUS CHARGERS AT NORTH DAVIDSON AND SOUTH TRYON BUS GARAGES. | PUBLIC TRANSIT | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | TL-0032 | DIVISION 10 | CRPDA, L |  |  |  |  | 2023 | 8183000 |  |  | 8183000
MECKLENBURG | CHARLOTTE TRANSIT AREA | CHARLOTTE AREA TRANSIT SYSTEM | FIRST MILE-LAST MILE PROJECT WILL PLAN NEW AND REPLACEMENT CIRCULATOR ROUTES WITH A NEW ON-DEMAND STRATEGY OF MICRO-TRANSIT ZONES TO REDUCE TRAVEL TIMES AND IMPROVE CONNECTIVITY TO HIGH-FREQUENCY ROUTES AT MOBILITY HUBS. | PUBLIC TRANSIT |  | 10 | CHARLOTTE REGIONAL TPO | TM-0040 | PUBLIC TRANSIT | ARP | [6 empty] | 2023 | 750000 | 750000
MECKLENBURG | CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. | PUBLIC TRANSIT |  | 10 | CHARLOTTE REGIONAL TPO | TM-0041 | PUBLIC TRANSIT | CMAQ, DP, L |  |  |  |  | 2024 | 85718000 | 2023 | 2708000 | 88426000 | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000.
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. | PUBLIC TRANSIT |  | 10 | CHARLOTTE REGIONAL TPO | TM-0042 | PUBLIC TRANSIT | CMAQ, L, S | [6 empty] | 2023 | 2739000 | 2739000
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 10 | CHARLOTTE REGIONAL TPO | TO-5137 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 75312000 | 75312000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | MECKLENBURG TRANSPORTATION | MECKLENBURG TRANSPORTATION | OPERATING ASSISTANCE FY20-21 (20-LU-051) | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 10 | CHARLOTTE REGIONAL TPO | TO-6159 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3074000 | 3074000 | ADDING CURRENT YEAR TO THE STIP
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE | PUBLIC TRANSIT | PLANNING | 10 | CHARLOTTE REGIONAL TPO | TP-5114 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 2598000 | 2598000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | ADD A LIGHT RAIL STATION ON THE LYNX BLUE LINE NEAR IVERSON WAY IN SOUTH CHARLOTTE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TP-5156 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 7582000 | 7582000 | "L" REFLECTS CATS CAPITAL FUND, CITY OF CHARLOTTE CAPITAL FUNDS, PRIVATE DEVELOPER PARTICIPATION.
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE TOD PLANNING IN COOPERATION WITH CATS, CRTPO AND GCLMPO. | PUBLIC TRANSIT | PLANNING | 10 | CHARLOTTE REGIONAL TPO | TP-5159 | PUBLIC TRANSIT | 5303, L | [6 empty] | 2023 | 507000 | 507000
MECKLENBURG | CHARLOTTE REGIONAL | CHARLOTTE REGIONAL | OPERATING PROJECTS FOR ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TQ-6597 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 2790000 | 2790000 | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING PROJECT FOR ENHANCED MOBILITY OF SENIORS AND INDIVIDUALS WITH DISABILITIES | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TQ-6957 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 2790000 | 2790000 | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | ADMINISTRATIVE OVERSIGHT FOR 5310 | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 10 | CHARLOTTE REGIONAL TPO | TQ-7009 | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 463000 | 463000 | CORRECTED FUNDING LEVEL TO FY 20-25 FOR THE ADMINISTRATIVE OVERSIGHT OF THE 5310 PROGRAM AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TQ-9033 | PUBLIC TRANSIT | 5310, L, S | [6 empty] | 2020 | 5292000 | 5292000 | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TS-5107 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3710000 | 3710000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE LIGHT RAIL PROJECT | PUBLIC TRANSIT | PLANNING | 10 | CHARLOTTE REGIONAL TPO | TU-0001 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 50000000 | 50000000
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | NCDOT | STATE OF GOOD REPAIR - BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TW-4901 | PUBLIC TRANSIT | 5337, FMOD, L, S | [6 empty] | 2020 | 7854000 | 7854000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | NCDOT | BRIDGE INSPECTIONS AND REPAIRS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TW-5102A | PUBLIC TRANSIT | 5307, L, S |  |  |  |  | 2020 | 1800000 |  |  | 1800000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | NCDOT | FIXED GUIDEWAY MODERNIZATION - BRIDGE INSPECTION & EMERGENCY REPAIRS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TW-5102B | PUBLIC TRANSIT | FMOD, L |  |  |  |  | 2020 | 1160000 |  |  | 1160000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | NCDOT | STATE OF GOOD REPAIR - BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TW-5104B | PUBLIC TRANSIT | 5307, 5337, L, S | [6 empty] | 2020 | 13890000 | 13890000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | PIEDMONT CORRIDOR | NCDOT | CRISP CHARLOTTE MAINTENANCE FACILITY - TRACK EXTENSION AND SHOP BUILDING | RAIL | OTHER | 10 | CHARLOTTE REGIONAL TPO | P-2918F | [11 empty] | IN PROGRESS
MECKLENBURG | P & N CORRIDOR REACTIVATION | NCDOT | THRIFT DEPOT RELOCATION. | RAIL | OTHER | 10 | CHARLOTTE REGIONAL TPO | P-5200EA | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | P & N CORRIDOR REACTIVATION | NCDOT | THRIFT DEPOT STABILIZATION. | RAIL | OTHER | 10 | CHARLOTTE REGIONAL TPO | P-5200EB | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | NORFOLK SOUTHERN MAIN LINE (TRACK MILEPOST 376) | NSR RR | ESTABLISH A NEW THOROUGHBRED BULK TRANSFER (TBT) FACILITY IN CHARLOTTE. | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5702 | DIVISION 10 | O, T |  |  |  |  | 2021 | 976000 |  |  | 976000 | OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN CORPORATION
MECKLENBURG | CHARLOTTE | NCDOT | CHARLOTTE GATEWAY STATION. | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5705 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
MECKLENBURG | CHARLOTTE | NCDOT | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5705A | STATEWIDE MOBILITY | DP, T | 2021 | 500000 |  |  | 2023 | 10998000 |  |  | 11498000 | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | NCDOT | CHARLOTTE GATEWAY STATION - RIGHT-OF-WAY | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5705B | REGION E | [10 empty] | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | NCDOT | CHARLOTTE GATEWAY STATION - TRACK, STRUCTURE, AND SIGNALS | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5705BA | REGION E | [10 empty] | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | NCDOT | CHARLOTTE GATEWAY STATION - PLATFORM AND CANOPY | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5705BB | REGION E | [10 empty] | UNDER CONSTRUCTION.
MECKLENBURG | CLANTON ROAD | NCDOT | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5730 | REGION E | O, T | 2024 | 4400000 |  |  | 2025 | 16700000 |  |  | 21100000
MECKLENBURG | SR 2623 (TRAILER DRIVE) | NCDOT | IMPROVE AT-GRADE CROSSING WITH NORFOLK SOUTHERN RAILROAD (CROSSING NUMBER 910 618A, MP O4.11) | RAIL | OTHER | 10 | CHARLOTTE REGIONAL TPO | P-5754 | EXEMPT | O |  |  |  |  | 2022 | 1200000 | 2020 | 50000 | 1250000 | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN
MECKLENBURG | CHARLOTTE RAILYARD PINEVILLE RAILYARD | NCDOT | GRANTS TO REPLACE AGING DIESEL ENGINES (GRADE). | RAIL | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | RL-0002 | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 5450000 |  |  | 5450000
MECKLENBURG, ALAMANCE, CABARRUS, CUMBERLAND, DAVIDSON, GUILFORD, HARNETT, HOKE, IREDELL, ORANGE, UNION | STATEWIDE | NCDOT | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS – CAPITAL PROGRAM | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 6, 7, 8, 9, 10, 12 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO, BURLINGTON-GRAHAM MPO, FAYETTEVILLE AREA MPO, HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | TG-6187 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2438000 | 2438000
MECKLENBURG, CABARRUS | I-85 | NCDOT | US 29/NC 49 CONNECTOR, MECKLENBURG COUNTY TO NC 73 IN CABARRUS COUNTY. WIDEN TO 8-LANES. (COORDINATE WITH U-3415). | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | I-3803 | [11 empty] | GARVEE BOND FUNDING - SEGMENT B: $103M FOR CONSTRUCTION, PAYBACK FY 2010-2021
MECKLENBURG, CABARRUS | I-85 | NCDOT | SOUTH OF US 29/NC 49 CONNECTOR TO SR 2894 (CONCORD MILLS - BRUTON SMITH BOULEVARD). WIDEN TO 8-LANES. | HIGHWAY | PRE-STI (HISTORIC) | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | I-3803A | [11 empty] | COMPLETE
MECKLENBURG, CABARRUS | NC 73 (DAVIDSON HIGHWAY) | NCDOT | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | R-5706A | REGION E | NHP | 2024 | 9700000 | 2024 | 2000000 | 2026 | 31999000 |  |  | 43699000
MECKLENBURG, CABARRUS | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | NCDOT | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | U-6032 | DIVISION 10 | T | 2022 | 14400000 | 2022 | 2600000 | 2025 | 27525000 |  |  | 44525000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE)
MECKLENBURG, CABARRUS | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE 6 BUSES FOR THE UNIVERSITY TO CONCORD MILLS BUS ROUTE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | TA-6672 | REGION E | O, T | [6 empty] | 2020 | 3000000 | 3000000 | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS
MECKLENBURG, IREDELL | I-77 | NCDOT | MILE MARKER 11 TO MILE MARKER 20 AND MILE MARKER 24.5 TO MILE MARKER 37. REHABILITATE PAVEMENT. | HIGHWAY | INTERSTATE MAINTENANCE | 10, 12 | CHARLOTTE REGIONAL TPO | I-5992 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG, IREDELL | I-77 | NCDOT | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | HIGHWAY | LOCALLY SELECTED | 10, 12 | CHARLOTTE REGIONAL TPO | I-6065 | EXEMPT | BA, BGDA, S(M), T(DA) | 2024 | 100000 |  |  | 2025 | 45830000 | 2020 | 1070000 | 47000000 | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG, IREDELL, UNION | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | HIGHWAY | LOCALLY SELECTED | 10, 12 | CHARLOTTE REGIONAL TPO | C-5613 | EXEMPT | CMAQ, L | 2020 | 518000 |  |  | 2020 | 3108000 | 2020 | 1554000 | 5180000 | IN PROGRESS.
MECKLENBURG, LINCOLN | NC 73 | NCDOT | NC 16 IN LINCOLN COUNTY TO SR 5544 (WEST CATAWBA AVENUE) IN MECKLENBURG COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10, 12 | CHARLOTTE REGIONAL TPO, GASTON-CLEVELAND-LINCOLN MPO | R-5721 | [11 empty] | COORDINATE WITH U-5765.
MECKLENBURG, UNION, IREDELL | VARIOUS | NCDOT | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | BIKE/PED | LOCALLY SELECTED | 10, 12 | CHARLOTTE REGIONAL TPO | U-5544 | DIVISION 10, 12 | L, TADA |  |  |  |  | 2024 | 22959000 |  |  | 22959000
MECKLENBURG, UNION, IREDELL | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 10, 12 | CHARLOTTE REGIONAL TPO | HL-0092 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 7822000 |  |  | 7822000
MECKLENBURG, UNION, IREDELL | VARIOUS | NCDOT | STBG-DA IN CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO). | HIGHWAY | LOCALLY SELECTED | 10, 12 | CHARLOTTE REGIONAL TPO | U-4744 | DIVISION 10, 12 | BGDA, L |  |  |  |  | 2020 | 230952000 |  |  | 230952000
MECKLENBURG, UNION, IREDELL | VARIOUS | NCDOT | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. | HIGHWAY | LOCALLY SELECTED | 10, 12 | CHARLOTTE REGIONAL TPO | U-4950 | DIVISION 10, 12 | BGDA, L | [6 empty] | 2020 | 15565000 | 15565000 | FORMERLY U-9999C - IN PROGRESS
MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, LINCOLN, NASH, CHATHAM, DAVIE, EDGECOMBE, FRANKLIN, GRANVILLE, HAYWOOD, PERSON, SWAIN | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NCDOT | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. | HIGHWAY | OTHER | 4, 5, 7, 8, 9, 10, 12, 14 | CHARLOTTE REGIONAL TPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, CABARRUS-ROWAN MPO, WINSTON-SALEM URBAN AREA MPO, GASTON-CLEVELAND-LINCOLN MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, GREATER HICKORY MPO, KERR-TAR RPO, ROCKY MOUNT | HO-0009 | EXEMPT | CMAQ, L, S | [6 empty] | 2022 | 1604000 | 1604000 | "S" FUNDING REFLECTS PARTICIPATION BY DAQ
MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, NASH, DAVIE, EDGECOMBE, GRANVILLE, HAYWOOD | VARIOUS | NCDOT | NCDOT TRAFFIC SYSTEMS OPERATIONS. INSTALL STATEWIDE ITS DEVICE OPERATIONS. | HIGHWAY | OTHER | 4, 5, 7, 9, 10, 12, 14 | CHARLOTTE REGIONAL TPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO, CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, ROCKY MOUNT URBAN AREA MP | HO-0005 | EXEMPT | CMAQ, S(M) |  |  |  |  | 2022 | 21605000 |  |  | 21605000 | UNDER CONSTRUCTION.
MITCHELL | SR 1106 (LYNN GAP ROAD) | NCDOT | REPLACE BRIDGE 600207 OVER GRASSY CREEK. | HIGHWAY | BRIDGES | 13 | HIGH COUNTRY RPO | B-6013 | DIVISION 13 | BGOFF | 2022 | 40000 |  |  | 2022 | 800000 |  |  | 840000 | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016
MITCHELL | NC 226 | NCDOT | US 19E TO SR 1250 (SNOW CREEK ROAD). UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO | HS-2013B | REGION G | HSIP |  |  |  |  | 2021 | 290000 |  |  | 290000 | COMPLETE
MITCHELL | NC 226 | NCDOT | SR 1250 (SNOW CREEK ROAD) TO NC 261. UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO | HS-2013D | REGION G | HSIP |  |  |  |  | 2021 | 272000 |  |  | 272000 | COMPLETE
MITCHELL | NC 226 | NCDOT | US 19 TO SR 1164/ SR 1250 (SNOW CREEK ROAD) NEAR SPRUCE PINE. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO | HS-2013L | REGION G | HSIP |  |  |  |  | 2023 | 925000 |  |  | 925000
MITCHELL | NC 226 | NCDOT | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | HIGH COUNTRY RPO | R-5804 | NOT FUNDED | T | NOT FUNDED | 15900000 | NOT FUNDED | 3200000 | NOT FUNDED | 33298000 |  |  | 52398000
MITCHELL | MITCHELL COUNTY TRANSPORTATION | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 13 | HIGH COUNTRY RPO | TK-6146 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
MONTGOMERY | NC 134 (NORTH MAIN STREET); SR 1005 (SOUTH MAIN ST | TROY | SR 1323 (OKEEWEMEE ROAD) TO BARNHILL STREET IN TROY. CONSTRUCT SIDEWALKS. | BIKE/PED | TRANSITION | 8 | PIEDMONT TRIAD RPO | EB-5521 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF TROY
MONTGOMERY | NC 731 (EAST ALLENTON STREET) | MOUNT GILEAD | EXISTING SIDEWALK ON NC 731 TO STANBECK PARK IN MT. GILEAD. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | EB-5899 | DIVISION 8 | L, TALT5 |  |  |  |  | 2023 | 277000 |  |  | 277000
MONTGOMERY | I-73 / I-74 / US 220 | NCDOT | MONTGOMERY COUNTY LINE TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | PIEDMONT TRIAD RPO | I-5947
MONTGOMERY | I-73/74 | NCDOT | MONTGOMERY COUNTY LINE TO NC 211. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | PIEDMONT TRIAD RPO | I-5947A | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2025 | 15901000 |  |  | 15901000
MONTGOMERY | I-73/74 | NCDOT | NC 211 TO NC 24/27. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | PIEDMONT TRIAD RPO | I-5947B | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2023 | 6900000 |  |  | 6900000 | UNDER CONSTRUCTION - LET WITH I-5946A
MONTGOMERY | I-73/74 | NCDOT | NC 24/27 TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | PIEDMONT TRIAD RPO | I-5947C | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2026 | 13600000 |  |  | 13600000
MONTGOMERY | NC 24 / NC 27 | NCDOT | TROY BYPASS, WEST OF SR 1138 (DAIRY ROAD) TO EAST OF LITTLE RIVER. FOUR LANES, PART ON NEW LOCATION. | HIGHWAY | TRANSITION | 8 | PIEDMONT TRIAD RPO | R-0623 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
MONTGOMERY | NC 24 / NC 27 | NCDOT | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-2527 | REGION E | BGLT5, T | 2019 | 854000 |  |  | 2025 | 106600000 | 2019 | 7802000 | 115256000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
MONTGOMERY | NC 109 | NCDOT | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO NC 24 / NC 27. UPGRADE ROADWAY, INCLUDING PAVED SHOULDERS, TURN LANES AND SIGNALS. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5826
MONTGOMERY | NC 109 | NCDOT | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5826A | NOT FUNDED | T | NOT FUNDED | 3700000 | NOT FUNDED | 250000 | NOT FUNDED | 9200000 |  |  | 13150000
MONTGOMERY | NC 109 | NCDOT | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5826B | DIVISION 8 | T | 2023 | 438000 | 2023 | 240000 | 2026 | 11000000 |  |  | 11678000 | RIGHT-OF-WAY IN PROGRESS
MONTGOMERY | NC 109 | NCDOT | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5826C | NOT FUNDED | T | NOT FUNDED | 3000000 | NOT FUNDED | 299000 | NOT FUNDED | 18000000 |  |  | 21299000
MONTGOMERY | RANDOLPH- MONTGOMERY RESTORE | RANDOLPH- MONTGOMERY RESTORE | PURCHASE 20-FT LIGHT TRANSIT VEHICLES FOR SERVICE EXPANSION. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 8 | PIEDMONT TRIAD RPO | TA-6671 | REGION E | [10 empty] | IN ACQUISITION
MONTGOMERY, RANDOLPH | REGIONAL COORDINATED AREA TRANSPORTION | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 8 | PIEDMONT TRIAD RPO | TK-6156 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1392000 | 1392000 | FUNDS AUTHORIZED IN PROGRESS
MOORE | MOORE COUNTY AIRPORT (SOP) | MOORE COUNTY AIRPORT (SOP) | CONSTRUCT HANGAR TAXIWAYS AND INTERNAL AIRFIELD SERVICE ROAD. | AVIATION | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | AV-5855 | DIVISION 8 | T |  |  |  |  | 2021 | 2900000 |  |  | 2900000 | UNDER CONSTRUCTION
MOORE | US 1 / US 15 / US 501 (SANDHILLS BOULEVARD) | NCDOT | MAPLE AVENUE IN ABERDEEN. CONSTRUCT MID-BLOCK CROSSWALK, MEDIAN REFUGE ISLAND, AND INSTALL PEDESTRIAN SIGNAL. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5741 | DIVISION 8 | L, TA5200 |  |  |  |  | 2023 | 280000 |  |  | 280000
MOORE | KNOLL ROAD | SOUTHERN PINES | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5864 | DIVISION 8 | L, TA5200 |  |  |  |  | 2024 | 1900000 | 2023 | 190000 | 2090000
MOORE | SR 1203 (JOHNSON STREET) | ABERDEEN | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-5869 | DIVISION 8 | L, TA5200 | 2023 | 30000 |  |  | 2024 | 300000 |  |  | 330000 | RIGHT-OF-WAY IN PROGRESS.
MOORE | SR 2055 (NORTH POPLAR STREET) | ABERDEEN | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-6001 | DIVISION 8 | L, TA5200 | 2024 | 34000 |  |  | 2025 | 340000 | 2023 | 26000 | 400000 | COORDINATE WITH U-5815
MOORE | VARIOUS | ABERDEEN | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | BIKE/PED | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | EB-6005 | NOT FUNDED | L, TA5200 |  |  |  |  | NOT FUNDED | 184000 | NOT FUNDED | 29000 | 213000
MOORE | NC 22 | NCDOT | REPLACE BRIDGE 620062 OVER NICKS CREEK IN CARTHAGE. | HIGHWAY | BRIDGES | 8 | TRIANGLE AREA RPO | BR-0035 | REGION E | NHPB |  |  |  |  | 2022 | 4100000 |  |  | 4100000 | PROJECT WILL BE COMPLETED UNDER THE STATE BRIDGE PROGRAM. PROJECT TO NO LONGER UTILIZE BUILD NC BONDS. UNDER CONSTRUCTION
MOORE | NC 5 | NCDOT | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | HIGHWAY | SAFETY | 8 | TRIANGLE AREA RPO | HS-2008F | REGION E | HSIP, T | 2023 | 500000 | 2023 | 250000 | 2024 | 900000 |  |  | 1650000
MOORE | NC 211 | NCDOT | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5726 | REGION E | T |  |  |  |  | 2025 | 32499000 |  |  | 32499000 | RIGHT-OF-WAY IN PROGRESS
MOORE | NC 211 | NCDOT | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). CLEARING, GRUBBING, AND EROSION CONTROL. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5726A | REGION E | T |  |  |  |  | 2022 | 5404000 |  |  | 5404000
MOORE | NC 690 (LOBELIA ROAD) | NCDOT | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5824 | REGION E | T | 2024 | 2400000 | 2024 | 1100000 | 2027 | 30999000 |  |  | 34499000
MOORE | US 15 / US 501 / NC 211 | NCDOT | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5891 | REGION E | T | 2028 | 1900000 | 2028 | 1180000 | 2031 | 20600000 |  |  | 23680000
MOORE | NC 5 (BEULAH HILL ROAD) | NCDOT | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5892 | REGION E | T | 2028 | 6300000 | 2028 | 1892000 | 2030 | 22000000 |  |  | 30192000
MOORE | US 15 / US 501 | NCDOT | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5927 | DIVISION 8 | T | 2026 | 1200000 | 2026 | 4100000 | 2029 | 43700000 |  |  | 49000000
MOORE | NC 24 / NC 27 | NCDOT | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | R-5929 | DIVISION 8 | T | 2026 | 200000 | 2026 | 1100000 | 2028 | 6100000 |  |  | 7400000 | COORDINATE WITH U-3628
MOORE | NC 24 / NC 27 | NCDOT | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-3628 | REGION E | T | 2023 | 2950000 |  |  | 2025 | 4600000 |  |  | 7550000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929
MOORE | NC 5 | NCDOT | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5756 | REGION E | T | 2023 | 4600000 | 2023 | 8200000 | 2025 | 33999000 |  |  | 46799000
MOORE | US 15 / US 501 / NC 211 | NCDOT | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5814 | REGION E | T | 2023 | 11500000 | 2023 | 1250000 | 2025 | 24000000 |  |  | 36750000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5815
MOORE | US 1 (SANDHILLS BOULEVARD) | NCDOT | SR 1112 (ROSELAND ROAD) IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5815 | REGION E | [10 empty] | COORDINATE WITH U-5814
MOORE | US 1 (SANDHILLS BOULEVARD) | NCDOT | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5815A | REGION E | T | 2025 | 700000 | 2025 | 1600000 | 2027 | 4401000 |  |  | 6701000
MOORE | US 1 (SANDHILLS BOULEVARD) | NCDOT | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5815B | REGION E | T | 2023 | 6650000 |  |  | 2025 | 37600000 |  |  | 44250000 | RIGHT-OF-WAY IN PROGRESS
MOORE | US 1 (SANDHILLS BOULEVARD) | NCDOT | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. RELOCATE WATER TRANSMISSION LINE. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5815BA | REGION E | T |  |  |  |  | 2023 | 17900000 |  |  | 17900000
MOORE | US 15 / US 501 | NCDOT | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO | U-5976 | DIVISION 8 | T | 2028 | 25800000 | 2028 | 630000 | 2030 | 30971000 |  |  | 57401000 | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE)
MOORE | SR 2055 (NORTH POPLAR STREET) | NCDOT | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | HIGHWAY | SAFETY | 8 | TRIANGLE AREA RPO | W-5808C | DIVISION 8 | HSIP | 2021 | 2000 |  |  | 2021 | 15000 |  |  | 17000 | UNDER CONSTRUCTION.
MOORE | MOORE COUNTY | MOORE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 8 | TRIANGLE AREA RPO | TK-6147 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 964000 | 964000 | FUNDS AUTHORIZED IN PROGRESS
MOORE | LS (SOUTH STREET) | NCDOT | ACWR CROSSING 722526U IN ABERDEEN. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 8 | TRIANGLE AREA RPO | RX-2008B | DIVISION 8 | RR |  |  |  |  | 2024 | 1832000 |  |  | 1832000
MOORE, HOKE, LEE | VARIOUS | NCDOT | VARIOUS NHS AND PRIMARY ROUTES IN DIVISION 8, DISTRICT 2. UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 8 | TRIANGLE AREA RPO, LUMBER RIVER RPO | HS-2008B | REGION E | HSIP |  |  |  |  | 2021 | 250000 |  |  | 250000 | UNDER CONSTRUCTION
MOORE, MONTGOMERY | NC 24 / NC 27 | NCDOT | I-73 / I-74 / US 220 TO SR 1644 (OLD GLENDON ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 8 | TRIANGLE AREA RPO, PIEDMONT TRIAD RPO | R-5932 | NOT FUNDED | T | NOT FUNDED | 5800000 | NOT FUNDED | 14400000 | NOT FUNDED | 50200000 |  |  | 70400000
NASH | ROCKY MOUNT WILSON AIRPORT (RWI) | ROCKY MOUNT WILSON AIRPORT (RWI) | CONSTRUCT TAXIWAY AND T HANGARS. | AVIATION | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | AV-5845 | DIVISION 4 | T |  |  |  |  | 2019 | 3050000 |  |  | 3050000 | UNDER CONSTRUCTION.
NASH | US 64 BUSINESS (SUNSET AVENUE) | ROCKY MOUNT | SR 1836 (MAY DRIVE) TO US 301 BUSINESS, NORTH BOUND (CHURCH STREET). INSTALL PEDESTRIAN SIGNALS. | BIKE/PED | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5711 | DIVISION 4 | L, TA5200 |  |  |  |  | 2023 | 580000 |  |  | 580000
NASH | US 301 BUSINESS (CHURCH STREET) | ROCKY MOUNT | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | BIKE/PED | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5761 | DIVISION 4 | L, TA5200 | 2024 | 50000 |  |  | 2025 | 2500000 | 2023 | 200000 | 2750000
NASH | US 64 BUSINESS (THOMAS STREET) | ROCKY MOUNT | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. | BIKE/PED | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5905 | DIVISION 4 | BG5200, L |  |  |  |  | 2027 | 120000 |  |  | 120000
NASH | NC 581 | NCDOT | REPLACE BRIDGE 630091 OVER TAR RIVER. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-5947 | REGION A | NHPB | 2021 | 400000 | 2021 | 123000 | 2023 | 6400000 |  |  | 6923000 | UNDER CONSTRUCTION.
NASH | SR 1522 (HALIFAX ROAD) | NCDOT | REPLACE BRIDGE 630203 OVER I-95. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-5980 | STATEWIDE MOBILITY | NHPB | 2020 | 2100000 |  |  | 2021 | 16564000 |  |  | 18664000 | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039.
NASH | NC 33 | NCDOT | REPLACE BRIDGE 630041 OVER I-95. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | BR-0036 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 4700000 |  |  | 4700000 | UNDER CONSTRUCTION.
NASH | SR 1510 | NCDOT | REPLACE BRIDGE 630224 OVER I-95. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | BR-0039 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 5200000 |  |  | 5200000 | UNDER CONSTRUCTION.
NASH | SR 1403 (COOPER ROAD) | NCDOT | REPLACE BRIDGE 630080 OVER GIDEON SWAMP. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | BR-0116 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION.
NASH | ROCKY MOUNT | ROCKY MOUNT | BENVENUE ROAD (NC 43/NC 48) AT JEFFREYS ROAD. INTERSECTION IMPROVEMENTS. | HIGHWAY | TRANSITION | 4 | ROCKY MOUNT URBAN AREA MPO | C-5546 | EXEMPT | CMAQ |  |  |  |  | 2023 | 130000 |  |  | 130000 | UNDER CONSTRUCTION.
NASH | ROCKY MOUNT | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | HIGHWAY | LOCALLY SELECTED | 4 | ROCKY MOUNT URBAN AREA MPO | C-5549 | EXEMPT | CMAQ |  |  |  |  | 2023 | 688000 |  |  | 688000 | UNDER CONSTRUCTION.
NASH | SR 1745 (BEND OF THE RIVER ROAD) | NCDOT | REPLACE BRIDGE 630110 OVER TAR RIVER RESERVOIR. | HIGHWAY | BRIDGES | 4 | ROCKY MOUNT URBAN AREA MPO | HB-0038 | DIVISION 4 | BGOFF | 2026 | 310000 | 2026 | 310000 | 2027 | 6200000 |  |  | 6820000
NASH | NC 97 | NCDOT | INSTALL LEFT TURN LANE AT NC 97 AND SR 1603 (OLD CARRIAGE ROAD). | HIGHWAY | SAFETY | 4 | ROCKY MOUNT URBAN AREA MPO | HS-2004B | REGION A | HSIP | 2022 | 86000 |  |  | 2022 | 205000 |  |  | 291000 | UNDER CONSTRUCTION.
NASH | SR 1001 (OLD BAILEY HIGHWAY) | NCDOT | INSTALL ALL WAY STOP AT SR 1001 (OLD BAILEY HIGHWAY) AND SR 1717 (MACEDONIA ROAD / SANDY CROSS ROAD). | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | HS-2004H | DIVISION 4 | HSIP |  |  |  |  | 2022 | 25000 |  |  | 25000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004G.
NASH | NC 48 | NCDOT | INSTALL MINI ROUNDABOUTS ALONG NC 48 (GOLDROCK ROAD) AT WATERLOO DRIVE / ROUNDTREE DRIVE AND AT GREYSON ROAD / CUNNINGHAM DRIVE. | HIGHWAY | SAFETY | 4 | ROCKY MOUNT URBAN AREA MPO | HS-2004M | REGION A | HSIP |  |  |  |  | 2023 | 1210000 |  |  | 1210000 | UNDER CONSTRUCTION.
NASH | SR 1700 (OAK LEVEL ROAD) | NCDOT | SR 1700 (OAK LEVEL ROAD) AT SR 1603 (OLD CARRIAGE ROAD). REVISE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 4 | ROCKY MOUNT URBAN AREA MPO | HS-2004N | DIVISION 4 | HSIP |  |  |  |  | 2023 | 29000 |  |  | 29000 | UNDER CONSTRUCTION.
NASH | US 64 | NCDOT | US 64 AT BRIDGES 630019 AND 630020 OVER TAR RIVER. PAVEMENT IMPROVEMENTS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | HS-2004Q | REGION A | HSIP |  |  |  |  | 2023 | 521000 |  |  | 521000 | UNDER CONSTRUCTION.
NASH | I-95 | NCDOT | SR 1770 (SUNSET AVENUE) (MILE MARKER 137.4) TO SR 1544 (NORTH HALIFAX ROAD) (MILE MARKER 142.1). PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | I-5934 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2024 | 5450000 |  |  | 5450000
NASH | US 64 (FUTURE I-87) | NCDOT | SR 1306 (SOUTH OLD FRANKLIN ROAD) TO SR 1603 (OLD CARRIAGE ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | I-6045 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2023 | 19310000 |  |  | 19310000 | UNDER CONSTRUCTION.
NASH | US 64 (FUTURE I-87) | NCDOT | BRIDGE REHABILITATION FOR 630072 AND 630074. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | I-6045A | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 520000 |  |  | 520000 | UNDER CONSTRUCTION.
NASH | SR 1770 (EASTERN AVENUE) | NCDOT | SR 1003 (RED OAK ROAD) TO SR 1603 (OLD CARRIAGE ROAD) IN ROCKY MOUNT. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | R-5720 | DIVISION 4 | T | 2020 | 12252000 | 2020 | 1470000 |  |  |  |  | 13722000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTION FUNDS SHOWN UNDER U-5026.
NASH | NC 43 | NCDOT | SR 1613 (WOODRUFF AVENUE) TO I-95. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | U-2561 | DIVISION 4
NASH | NC 43 | NCDOT | SR 1613 (WOODRUFF AVENUE) TO I-95. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | U-2561C | DIVISION 4 | BGLT5 | 2026 | 3131000 | 2026 | 2968000 | 2028 | 7601000 |  |  | 13700000
NASH | I-95 | NCDOT | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | U-5026 | DIVISION 4 | L, T | 2020 | 32058000 | 2020 | 336000 | 2020 | 76136000 |  |  | 108530000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
NASH | NC 48 | NCDOT | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | U-5911 | DIVISION 4 | T | 2025 | 69000 | 2025 | 2136000 | 2027 | 5625000 |  |  | 7830000
NASH | NC 43 (BENVENUE ROAD) | NCDOT | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | U-5947 | REGION A | T | 2022 | 80000 | 2022 | 800000 | 2022 | 4600000 |  |  | 5480000 | UNDER CONSTRUCTION.
NASH | SR 1603 (OLD CARRIAGE ROAD) | NCDOT | WIDEN TO FOUR LANES FROM GREEN HILLS ROAD THROUGH US 64 BRIDGE. WIDEN TO THREE LANES FROM SOUTH OF US 64 BRIDGE TO SR 1770 (EASTERN AVENUE). | HIGHWAY | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | U-5996 | DIVISION 4 | T | 2020 | 529000 |  |  | 2022 | 23940000 |  |  | 24469000 | UNDER CONSTRUCTION.
NASH | NC 43 | NCDOT | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | W-5804B | REGION A | HSIP | 2023 | 45000 |  |  | 2023 | 651000 |  |  | 696000 | UNDER CONSTRUCTION.
NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | ENLARGE DRIVERS BREAKROOM | PUBLIC TRANSIT | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | TD-5281 | DIVISION 4 | T | [6 empty] | 2025 | 15000 | 15000
NASH, EDGECOMBE | US 64 | NCDOT | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 4 | ROCKY MOUNT URBAN AREA MPO | U-6149 | NOT FUNDED | NHP | NOT FUNDED | 11800000 | NOT FUNDED | 2200000 | NOT FUNDED | 137000000 |  |  | 151000000
NASH, EDGECOMBE, WILSON | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE ROCKY MOUNT PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 4 | ROCKY MOUNT URBAN AREA MPO | HL-0106 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 971000 |  |  | 971000
NASH, HALIFAX | NC 43 | NCDOT | NC 43 FROM 0.5 MILES NORTH OF SR 1425 (CASTALIA ROAD) IN NASH COUNTY TO NC 561 IN HALIFAX COUNTY. INSTALL RUMBLE STRIPS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, PEANUT BELT RPO | HS-2004X | REGION A | HSIP |  |  |  |  | 2023 | 361000 |  |  | 361000 | UNDER CONSTRUCTION.
NASH, WAKE, JOHNSTON | US 264 | NCDOT | US 264 FROM THE US 64 / US 264 SPLIT TO THE WILSON COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4, 5 | UPPER COASTAL PLAIN RPO, CAPITAL AREA MPO | HI-0013 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2027 | 16500000 |  |  | 16500000
NASH, WILSON | NC 58 | NCDOT | NC 58 FROM NORTHERN STATONSBURG TOWN LIMITS TO 0.3 MILES NORTH OF SR 1622 (EVANSDALE ROAD) IN WILSON COUNTY. NC 58 FROM SOUTH OF SR 1314 (THOMPSON CHAPEL CHURCH ROAD) IN WILSON COUNTY TO SOUTHERN NASHVILLE TOWN LIMIT IN NASH COUNTY. NC 58 FROM SOUTH OF SR 1004 (TAYLORS STORE ROAD) TO SOUTHERN CASTALIA TOWN LIMIT IN NASH COUNTY. INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | HS-2004U | REGION A | HSIP |  |  |  |  | 2023 | 301000 |  |  | 301000 | UNDER CONSTRUCTION.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | UPGRADE AIRFIELD LIGHTING VAULT. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5704 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | EXTEND RUNWAY 6-24 PHASE 1. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5730 | NOT FUNDED | O, T |  |  |  |  | NOT FUNDED | 5000000 |  |  | 5000000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | EXPAND THE GENERAL AVIATION APRON. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5795 | STATEWIDE MOBILITY | O, T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 |  |  | 1300000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | INTERNATIONAL (ILM) WILMINGTON | INTERNATIONAL (ILM) WILMINGTON | INCREASE WIDTH OF ALL TAXIWAYS. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5796 | NOT FUNDED | O, T |  |  |  |  | NOT FUNDED | 3800000 |  |  | 3800000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | TAXIWAY IMPROVEMENTS. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5798 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2028 | 5600000 |  |  | 5600000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | WIDEN NORTH-SOUTH TAXIWAY SYSTEM. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5799 | NOT FUNDED | O, T |  |  |  |  | NOT FUNDED | 6500000 |  |  | 6500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | EXPANSION OF AIR CARRIER APRON. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5801 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2021 | 3940000 |  |  | 3940000 | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL AIRPORT (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5885 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 7500000 |  |  | 7500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILIMINGTON INTERNATION (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | TAXIWAY J IMPROVEMENTS. | AVIATION | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | AV-5886 | NOT FUNDED | O, T |  |  |  |  | NOT FUNDED | 5600000 |  |  | 5600000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | VARIOUS | NEW HANOVER COUNTY | MIDDLE SOUND LOOP CONNECTOR CONSTRUCTION AND PORTERS NECK WALMART CONNECTOR. CONSTRUCT MULTI-USE PATH. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | BL-0040 | DIVISION 3 | BGDA, L |  |  |  |  | 2023 | 692000 |  |  | 692000 | UNDER CONSTRUCTION.
NEW HANOVER | WILMINGTON | WILMINGTON | WILMINGTON RAIL TRAIL. CONSTRUCT MULTI-USE PATH FROM 3RD STREET IN DOWNTOWN WILMINGTON TO THE LOVE GROVE BRIDGE MULTI-USE PATH FACILITY. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | BL-0045 | DIVISION 3 | BGDACV | [6 empty] | 2022 | 680000 | 680000
NEW HANOVER | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | KURE BEACH | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | BL-0059 | DIVISION 3 | BGDACV, L | 2023 | 53000 |  |  | 2024 | 302000 | 2023 | 57000 | 412000 | RIGHT-OF-WAY IN PROGRESS.
NEW HANOVER | WRIGHTSVILLE BEACH | WRIGHTSVILLE BEACH | INSTALLATION OF ON-STREET BICYCLE LANES AND PEDESTRIAN CROSSWALKS ALONG US 76 (CAUSEWAY DRIVE) AND US 74 (WEST SALISBURY STREET) IN WRIGHTSVILLE BEACH. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | BL-0075 | DIVISION 3 | BGDA, L |  |  |  |  | 2024 | 337000 |  |  | 337000
NEW HANOVER | SR 1219 (SOUTH 17TH STREET) | WILMINGTON | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | EB-5600 | DIVISION 3 | BGANY, L | 2024 | 30000 |  |  | 2024 | 738000 | 2022 | 150000 | 918000 | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON.
NEW HANOVER | SR 1403 (MIDDLE SOUND LOOP) | New Hanover County | CONSTRUCT MULTI-USE PATH SOUTH OF MARKET STREET FROM RED CEDAR ROAD TO EXISTING TRAIL AT CORNER OF MARKET STREET AND MIDDLE SOUND LOOP ROAD. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | EB-6027 | DIVISION 3 | L | 2021 | 500000 |  |  | 2023 | 1000000 |  |  | 1500000 | UNDER CONSTRUCTION.
NEW HANOVER | WILMINGTON | WILMINGTON | CONSTRUCT SIGNALIZED PEDESTRIAN CROSSING AT US 17 BUSINESS (MARKET STREET) AND 21ST STREET. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | EB-6028 | DIVISION 3 | L, TADA |  |  |  |  | 2023 | 164000 |  |  | 164000
NEW HANOVER | CAROLINA BEACH | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | EB-6039 | DIVISION 3 | BGDA, L |  |  |  |  | 2024 | 498000 | 2021 | 74000 | 572000
NEW HANOVER | US 17/76/421 | NCDOT | REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. | HIGHWAY | BRIDGES | 3 | WILMINGTON URBAN AREA MPO | HB-0039 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY.
NEW HANOVER | US 76 AND US 74 | NCDOT | REPLACE BRIDGES 640021, 640022, AND 640024 IN NEW HANOVER COUNTY. | HIGHWAY | BRIDGES | 3 | WILMINGTON URBAN AREA MPO | HB-0040 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY.
NEW HANOVER | WILMINGTON | WILMINGTON | CONSTRUCT A NEW NORTH GATE ON NORTH CAROLINA PORTS AUTHORITY PROPERTY. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | HL-0040 | DIVISION 3 | BGDA, L | [6 empty] | 2022 | 313000 | 313000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY.
NEW HANOVER | SOUTH 3RD STREET | WILMINGTON | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | HL-0109 | DIVISION 3 | BGDA, L | 2024 | 61000 |  |  | 2025 | 664000 | 2023 | 489000 | 1214000
NEW HANOVER | SOUTH 3RD STREET | WILMINGTON | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | HL-0110 | DIVISION 3 | BGDA, HF | 2024 | 296000 |  |  | 2025 | 274000 | 2023 | 59000 | 629000 | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY.
NEW HANOVER | SR 1217 (17TH STREET) | NCDOT | INSTALL NEAR SIDE SIGNAL HEADS ON PEDESTAL ON BOTH SIDES OF SR 1217 (17TH STREET) AT DOCK STREET IN WILMINGTON. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003A | DIVISION 3 | HSIP |  |  |  |  | 2023 | 34000 |  |  | 34000 | UNDER CONSTRUCTION.
NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) | NCDOT | US 117 / NC 132 (COLLEGE ROAD) AT LAKE AVENUE-HUGH MCRAE PARK IN WILMINGTON. REVISE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003H | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2025 | 66000 |  |  | 66000
NEW HANOVER | US 17 (OLEANDER DRIVE) | NCDOT | US 17 (OLEANDER DRIVE) AT 42ND STREET IN WILMINGTON. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003J | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2025 | 59000 |  |  | 59000
NEW HANOVER | US 74 WESTBOUND ON-RAMP | NCDOT | US 74 WESTBOUND ON-RAMP AND SR 1627 (3RD STREET / MARTIN LUTHER KING JUNIOR BOULEVARD) IN WILMINGTON. REVISE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003K | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2025 | 16000 |  |  | 16000
NEW HANOVER | US 17-76 (OLEANDER DRIVE) | NCDOT | US 17-76 (OLEANDER DRIVE) AND SR 1421 (GREENVILLE LOOP ROAD) / GREENVILLE AVENUE IN WILMINGTON. REVISE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003L | REGION B | HSIP |  |  |  |  | 2025 | 84000 |  |  | 84000
NEW HANOVER | US 117 (SHIPYARD BOULEVARD) | NCDOT | US 117 (SHIPYARD BOULEVARD) AT CONVERSE ROAD / LONGSTREET DRIVE IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND ADD PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003P | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2026 | 271000 |  |  | 271000
NEW HANOVER | US 17 (DAWSON STREET) | NCDOT | US 17 (DAWSON STREET) AT US 421 (3RD STREET) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL, UPGRADE PAVEMENT MARKINGS, AND ADD PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003Q | REGION B | HSIP |  |  |  |  | 2026 | 184000 |  |  | 184000
NEW HANOVER | US 421 | NCDOT | US 421 AT SR 1573 (DOW ROAD) IN CAROLINA BEACH. UPGRADE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003R | REGION B | HSIP |  |  |  |  | 2026 | 23000 |  |  | 23000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | US 17 BUSINESS (MARKET STREET) AND SR 1272 (NEW CENTRE DRIVE). INSTALL CROSSWALKS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003S | REGION B | HSIP |  |  |  |  | 2026 | 114000 |  |  | 114000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | US 17 BUSINESS (MARKET STREET) AT SR 2219 (GREEN MEADOWS DRIVE) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003T | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2026 | 32000 |  |  | 32000
NEW HANOVER | SR 2048 (GORDON ROAD) | NCDOT | SR 2048 (GORDON ROAD) JUST WEST OF I-40. INSTALL SIX INCH PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003U | DIVISION 3 | HSIP |  |  |  |  | 2023 | 37000 |  |  | 37000 | UNDER CONSTRUCTION.
NEW HANOVER | US 17/76 (OLEANDER DRIVE) | NCDOT | US 17/76 (OLEANDER DRIVE) AT SR 1209 (INDEPENDENCE BOULEVARD) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003V | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2026 | 23000 |  |  | 23000
NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) | NCDOT | AT SR 2313 (WILSHIRE BOULEVARD) IN WILMINGTON. INSTALL PEDESTRIAN COUNTDOWN HEADS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003Y | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2026 | 63000 |  |  | 63000
NEW HANOVER | US 17/76 (WOOSTER STREET) | NCDOT | AT SR 1217 (17TH STREET) IN WILMINGTON. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN COUNTDOWN HEADS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | HS-2003Z | REGION B | HSIP |  |  |  |  | 2026 | 114000 |  |  | 114000
NEW HANOVER | I-140 | NCDOT | US 421 TO I-40. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | I-6037 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 7300000 |  |  | 7300000
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | WEST OF US 421 NORTH OF WILMINGTON TO WEST OF NC 133. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633CA | [11 empty] | COMPLETED.
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | WEST OF NC 133 TO US 117. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633CB | [11 empty] | COMPLETED.
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | US 117 TO EAST OF I-40 SOUTH OF CASTLE HAYNE. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633CC | [11 empty] | COMPLETED.
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-3338
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY). | HIGHWAY | TRANSITION | 3 | WILMINGTON URBAN AREA MPO | U-3338B | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | SR 1175 (KERR AVENUE) INTERCHANGE AT US 74 (MARTIN LUTHER KING, JR. PARKWAY). | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-3338C | REGION B | BGANY |  |  |  |  | 2028 | 26800000 |  |  | 26800000 | RIGHT-OF-WAY IN PROGRESS.
NEW HANOVER | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | NCDOT | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-4434 | DIVISION 3 | BGANY | 2027 | 88701000 | 2027 | 3632000 | 2031 | 128601000 |  |  | 220934000
NEW HANOVER | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | NCDOT | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-4751 | STATEWIDE MOBILITY | T |  |  |  |  | 2018 | 64625000 | 2021 | 14850000 | 79475000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
NEW HANOVER | LENDIRE ROAD | NCDOT | LENDIRE ROAD, WEST OF US 17 BUSINESS (MARKET STREET) TO US 17 BUSINESS (MARKET STREET)/SR 1403 (MIDDLE SOUND LOOP ROAD). REALIGN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-4751A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION.
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | COLONIAL DRIVE TO SR 1402 (PORTERS NECK ROAD). ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-4902
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | SR 1272 (NEW CENTRE DRIVE) TO MARTIN LUTHER KING JR., BOULEVARD. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | U-4902A | [11 empty] | COMPLETED.
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-4902B | NOT FUNDED | T | NOT FUNDED | 10000000 | NOT FUNDED | 2900000 | NOT FUNDED | 9700000 |  |  | 22600000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-4902C | STATEWIDE MOBILITY | T | 2028 | 46088000 | 2028 | 10811000 | 2030 | 55101000 |  |  | 112000000 | INCLUDES U-5880.
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-4902D | STATEWIDE MOBILITY | T |  |  |  |  | 2019 | 24609000 | 2021 | 4290000 | 28899000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
NEW HANOVER | NC 132 (COLLEGE ROAD) | NCDOT | SR 1272 (NEW CENTRE DRIVE) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5702
NEW HANOVER | NC 132 (COLLEGE ROAD) | NCDOT | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5702A | STATEWIDE MOBILITY | NHP | 2028 | 15149000 | 2028 | 5380000 | 2030 | 15999000 |  |  | 36528000 | PLANNING/DESIGN IN PROGRESS.
NEW HANOVER | NC 132 (COLLEGE ROAD) | NCDOT | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5702B | NOT FUNDED | NHP | NOT FUNDED | 14240000 | NOT FUNDED | 8592000 | NOT FUNDED | 33800000 |  |  | 56632000
NEW HANOVER | NC 132 (COLLEGE ROAD) | NCDOT | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5704 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21182000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2422000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14100000 |  |  | 37704000
NEW HANOVER | US 74 (EASTWOOD ROAD) | NCDOT | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5710 | STATEWIDE MOBILITY | NHP | 2023 | 16900000 | 2023 | 4000000 | 2026 | 45000000 |  |  | 65900000 | RIGHT-OF-WAY IN PROGRESS.
NEW HANOVER | NEW LOCATION | NCDOT | FROM SR 1409 (MILITARY CUTOFF ROAD) AT DRYSDALE DRIVE TO US 74 (EASTWOOD ROAD). ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5710A | STATEWIDE MOBILITY | BGANY, T | 2019 | 2575000 |  |  | 2022 | 8200000 |  |  | 10775000 | UNDER CONSTRUCTION.
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NCDOT | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5729
NEW HANOVER | US 421 | NCDOT | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5729REG | REGION B | T | 2028 | 21200000 | 2028 | 6560000 | 2030 | 16160000 |  |  | 43920000
NEW HANOVER | US 421 | NCDOT | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5729SW | STATEWIDE MOBILITY | T | 2028 | 5300000 | 2028 | 1640000 | 2030 | 4040000 |  |  | 10980000
NEW HANOVER | US 74 | NCDOT | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5731 | STATEWIDE MOBILITY | BGLT5 | 2027 | 5200000 | 2027 | 241000 | 2029 | 31500000 |  |  | 36941000
NEW HANOVER | US 421 (SOUTH FRONT STREET) | NCDOT | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5734 | REGION B | T | 2025 | 13940000 | 2025 | 1032000 | 2027 | 10300000 |  |  | 25272000
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NCDOT | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5790 | DIVISION 3 | T | 2027 | 6064000 | 2027 | 6428000 | 2029 | 20500000 |  |  | 32992000
NEW HANOVER | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | NCDOT | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5792 | DIVISION 3 | T | 2025 | 22701000 | 2025 | 8910000 | 2027 | 106300000 |  |  | 137911000
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | NCDOT | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5863 | NOT FUNDED | T | NOT FUNDED | 4800000 | NOT FUNDED | 4600000 | NOT FUNDED | 26800000 |  |  | 36200000
NEW HANOVER | NC 132 (COLLEGE ROAD) | NCDOT | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5881 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3081000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1912000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33800000 |  |  | 38793000
NEW HANOVER | NEW ROUTE | NCDOT | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | HIGHWAY | ECONOMIC DEVELOPMENT | 3 | WILMINGTON URBAN AREA MPO | U-5926 | DIVISION 3 | L, T | 2024 | 1406000 | 2024 | 344000 |  |  |  |  | 1750000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434.
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | NCDOT | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5954 | REGION B | BGLT5 | 2025 | 721000 | 2025 | 507000 | 2027 | 3800000 |  |  | 5028000
NEW HANOVER | US 76 (OLEANDER DRIVE) | NCDOT | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-6128 | REGION B | BGANY | 2027 | 3700000 | 2027 | 600000 | 2029 | 3600000 |  |  | 7900000
NEW HANOVER | WILMINGTON | NCDOT | WILMINGTON CITYWIDE SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-6199 | DIVISION 3 | T | 2028 | 100000 | 2028 | 950000 | 2030 | 15360000 |  |  | 16410000
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-6201 | DIVISION 3 | T | 2028 | 4200000 | 2028 | 400000 | 2030 | 4498000 |  |  | 9098000
NEW HANOVER | SR 2048 (GORDON ROAD) | NCDOT | US 17 (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-6202 | DIVISION 3 | T | 2022 | 12835000 | 2022 | 5300000 | 2025 | 33601000 |  |  | 51736000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE).
NEW HANOVER | CAROLINA BEACH | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | U-6233 | DIVISION 3 | BGDA, S | 2022 | 40000 |  |  | 2023 | 256000 | 2021 | 18000 | 314000 | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS.
NEW HANOVER | WILMINGTON | WILMINGTON | WILMINGTON MULTI-MODAL TRANSPORTATION CENTER PHASE 1B. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | U-6234 | DIVISION 3 | BGDA, L |  |  |  |  | 2022 | 6450000 | 2020 | 317000 | 6767000 | UNDER CONSTRUCTION.
NEW HANOVER | WILMINGTON | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | U-6235 | DIVISION 3 | BGDA, L |  |  |  |  | 2024 | 784000 | 2020 | 487000 | 1271000
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NCDOT | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | W-5703C | REGION B | BGDA, HSIP, L, T | 2023 | 600000 | 2023 | 127000 | 2024 | 4278000 |  |  | 5005000 | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT.
NEW HANOVER | US 74 | NCDOT | US 74 (EASTWOOD ROAD) AT US 17 (MILITARY CUTOFF ROAD), AND US 74 (EASTWOOD ROAD) AT CAVALIER DRIVE IN WILMINGTON. UPGRADE PEDESTRIAN SIGNALS. | HIGHWAY | SAFETY | 3 | WILMINGTON URBAN AREA MPO | W-5803A | REGION B | HSIP |  |  |  |  | 2023 | 42000 |  |  | 42000
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | WILMINGTON URBAN AREA MPO | TA-5221 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 365000 | 365000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | WILMINGTON URBAN AREA MPO | TA-5222 | PUBLIC TRANSIT | 5339, L, S | [6 empty] | 2020 | 624000 | 624000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | WILMINGTON URBAN AREA MPO | TA-5223 | PUBLIC TRANSIT | 5339, L, S | [6 empty] | 2020 | 3234000 | 3234000
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT TROLLEY | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | WILMINGTON URBAN AREA MPO | TA-5224 | PUBLIC TRANSIT | 5339 | [6 empty] | 2020 | 700000 | 700000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADA | PUBLIC TRANSIT | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | TA-6700 | DIVISION 3 | BGDA, L |  |  |  |  | 2020 | 180000 |  |  | 180000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. | PUBLIC TRANSIT |  | 3 | WILMINGTON URBAN AREA MPO | TC-0027 | PUBLIC TRANSIT | BGDA, L | [6 empty] | 2023 | 424000 | 424000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE PREVENTATIVE MAINTENACE PROJECT WILL ENSURE THE FTA FUNDED ASSESTS ARE MAINTAINED TO THE FTA STATE OF GOOD REPAIR REQUIREMENTS AND THAT SERVICE CONTINUES WITHOUT DISRUPTION. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | TG-5243 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 1125000 | 1125000
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | TG-5245 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 314000 | 314000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS | PUBLIC TRANSIT | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | TG-6177 | PUBLIC TRANSIT | 5307, L, T |  |  |  |  | 2023 | 66000 |  |  | 66000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | TG-6784 | DIVISION 3 | BGDA, L |  |  |  |  | 2020 | 420000 |  |  | 420000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | TK-6176 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 872000 | 872000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPITAL IMPROVEMENT PROJECT TO SECURE AUTOMATIC PASSENGER COUNTER (APC) TECHNOLOGY FOR THE PURPOSE OF COLLECTING STOP LEVEL BOARDINGS AND ALIGHTINGS FOR FIXED ROUTE PUBLIC TRANSPORTATION SERVICES. | PUBLIC TRANSIT | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | TL-0017 | DIVISION 3 | BGDA, L | [6 empty] | 2022 | 200000 | 200000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 3 | WILMINGTON URBAN AREA MPO | TO-4751 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2022 | 9327000 | 9327000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | WILMINGTON URBAN AREA MPO | TP-5110 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2023 | 190000 | 190000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | PLANNING | 3 | WILMINGTON URBAN AREA MPO | TP-5111 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 1648000 | 1648000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT PROVIDES OPERATING SUPPORT FOR FIXED BUS ROUTE 205 LONG LEAF PARK WHICH SERVICES NOVANT HOSPITAL AND THE MEDICAL CENTER. THIS ROUTE CARRIES A HIGH CONCENTRATION OF INDIVIDUALS WITH DISABILITIES AS IDENTIFIED THROUGH AN EXTENSIVE ONBOARD SURVEY EFFORT CONDUCTED IN FY17. A SURVEY EFFORT IS SLATED FOR FY23. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | TQ-6513 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2023 | 346000 | 346000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT IS FOR ADMINISTRATIVE SUPPORT REQUIRED TO EFFECTVELY MANAGE THE SECTION 5310 PROGRAM AND ANNUAL FUNDING ALLOCATION FROM FTA. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | TQ-7005 | PUBLIC TRANSIT | 5310 | [6 empty] | 2021 | 105000 | 105000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | MOBILITY MANAGER PROVIDES OVERSIGHT AND MANAGEMENT OF SECTION 5310 FUNDS AND ADMINISTERS THE PROGRAMS AND PROJECTS SUPPORTED BY THESE FUNDS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | WILMINGTON URBAN AREA MPO | TQ-8019 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2023 | 150000 | 150000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECTS FULFILLS THE ALLOCATION FOR NON-TRADITIONAL TRANSPORTATION PROJECTS AS DEFINED IN THE GRANT. THE PROJECT SUPPORTS THE COMMUNITY GRANT OFFERING TO NON-PROFITS AND GOVERNMENTAL ORGANIZAIONS TO REMOVE TRANSPORTATION BARRIERS AND CONNECT ELDERS AND INDIVIDUALS WITH DISABILITIES TO NEEDED RESOURCES. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | WILMINGTON URBAN AREA MPO | TQ-9001 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2022 | 278000 | 278000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | WILMINGTON URBAN AREA MPO | TS-5103 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 96000 | 96000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CSX SE LINE | NCDOT | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. | RAIL | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | P-5740B | STATEWIDE MOBILITY | DP, T | 2023 | 600000 |  |  | 2024 | 4349000 |  |  | 4949000 | RIGHT-OF-WAY IN PROGRESS.
NEW HANOVER, BRUNSWICK | I-140/US 17 WILMINGTON BYPASS | NCDOT | SR 1430 (CEDAR HILL ROAD) TO WEST OF US 421 NORTH OF WILMINGTON. | HIGHWAY | PRE-STI (HISTORIC) | 3 | WILMINGTON URBAN AREA MPO | R-2633BB | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2013 | 51250000 |  |  | 51250000 | COMPLETED. GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK 2013 - 2024.
NEW HANOVER, BRUNSWICK | CSX SE LINE | CSXT RR | WILMINGTON BELTLINE SPEED IMPROVEMENT PROJECT. | RAIL | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | P-5740 | STATEWIDE MOBILITY | [10 empty] | DP FUNDS REPRESENT FEDERAL CRISI GRANT.
NEW HANOVER, BRUNSWICK | CSX SE LINE | WILMINGTON | TIE AND RAIL REHABILITATION, CURVE REALIGNMENT, AND UPGRADE RAIL BRIDGES. | RAIL | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | P-5740A | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2023 | 33000000 |  |  | 33000000 | UNDER CONSTRUCTION.
NEW HANOVER, BRUNSWICK | CSX SE LINE | WILMINGTON | INSTALLATION OF RAILROAD GRADE CROSSING SIGNALS AND GATES AT VARIOUS AT-GRADE CROSSINGS. | RAIL | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | P-5740C | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2023 | 9900000 |  |  | 9900000 | UNDER CONSTRUCTION.
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | WILMINGTON URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. | BIKE/PED | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | U-5527 | DIVISION 3 | TADA |  |  |  |  | 2022 | 11914000 |  |  | 11914000 | IN PROGRESS.
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WILMINGTON PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | HL-0107 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 3128000 |  |  | 3128000
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | U-5525 | DIVISION 3 | BGDA, L | [6 empty] | 2020 | 19340000 | 19340000
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | U-5534 | DIVISION 3 | BGANY, BGDA, BGDACV, L | 2022 | 220000 |  |  | 2020 | 10738000 |  |  | 10958000 | IN PROGRESS
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | WILMINGTON URBAN METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | HIGHWAY | LOCALLY SELECTED | 3 | WILMINGTON URBAN AREA MPO | U-5989 | DIVISION 3 | BGDA |  |  |  |  | 2022 | 84016000 |  |  | 84016000
NEW HANOVER, PENDER | I-40 | NCDOT | I-40 FROM END I-40 (MILE MARKER 420) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 3 | WILMINGTON URBAN AREA MPO | I-6039 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 13200000 |  |  | 13200000 | UNDER CONSTRUCTION.
NEW HANOVER, PENDER | US 17 (HAMPSTEAD BYPASS) | NCDOT | US 17 BYPASS SOUTH OF HAMPSTEAD TO US 17 NORTH OF HAMPSTEAD. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | R-3300
NORTHAMPTON | US 158/NC 46 | NCDOT | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. WIDEN TO MULTI-LANES WITH BYPASS OF JACKSON, SOME NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-2582
NORTHAMPTON | US 158/NC 46 | NCDOT | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-2582A | DIVISION 1 | T | 2020 | 3345000 |  |  | 2020 | 106809000 | 2020 | 8820000 | 118974000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
NORTHAMPTON | US 158/NC 46 | NCDOT | SR 1312 (ST. JOHN CHURCH ROAD) TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-2582B | NOT FUNDED | T | NOT FUNDED | 5400000 |  |  | NOT FUNDED | 61400000 |  |  | 66800000
NORTHAMPTON | NC 46 | NCDOT | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5739 | DIVISION 1 | T | 2022 | 2765000 | 2022 | 10800000 | 2025 | 28099000 |  |  | 41664000 | RIGHT-OF-WAY IN PROGRESS.
NORTHAMPTON | NC 305 | NCDOT | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5757 | DIVISION 1 | BGLT5 | 2023 | 3200000 | 2023 | 4122000 |  |  |  |  | 7322000 | RIGHT-OF-WAY IN PROGRESS.
NORTHAMPTON | NC 305 | NCDOT | HERTFORD COUNTY LINE TO NORTH OF SR 1503 (LASKER ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5757A | DIVISION 1 | BGLT5 |  |  |  |  | 2025 | 19000000 |  |  | 19000000
NORTHAMPTON | NC 305 | NCDOT | NORTH OF SR 1503 (LASKER ROAD) TO SEABOARD TOWN LIMITS. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | PEANUT BELT RPO | R-5757B | DIVISION 1 | BGLT5 |  |  |  |  | 2025 | 20700000 |  |  | 20700000
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ALBERT J. ELLIS AIRPORT (OAJ) | DESIGN AND CONSTRUCT RUNWAY 23 HOLDING APRON. | AVIATION | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | AV-5733 | REGION B | O, T |  |  |  |  | 2022 | 750000 |  |  | 750000 | UNDER CONSTRUCTION.
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR ROADWAY RELOCATION, RPZ AND RUNWAY EXTENSION. | AVIATION | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | AV-5804 | REGION B | O, T | 2023 | 697000 | [6 empty] | 697000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS.
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR RUNWAY EXTENSION AND ROADWAY RELOCATION. | AVIATION | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | AV-5805 | REGION B | O, T | 2023 | 361000 | [6 empty] | 361000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS.
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. | AVIATION | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | AV-5806 | REGION B | O, T |  |  |  |  | 2025 | 12880000 |  |  | 12880000 | OTHER FUNDS ARE AIRPORT FUNDS
ONSLOW | SR 1308 (GUM BRANCH ROAD) | JACKSONVILLE | CONSTRUCT 1000 FEET OF SIDEWALK FROM INTERSECTION OF NC 53 (WESTERN BOULEVARD) AND GUM BRANCH ROAD TO THE CITY OF JACKSONVILLE LIMITS. CONSTRUCT 1600 FEET OF SIDEWALK FROM ONSVILLE DRIVE TO ONSVILLE DRIVE. | BIKE/PED | LOCALLY SELECTED | 3 | JACKSONVILLE URBAN AREA MPO | BL-0073 | DIVISION 3 | CRPDA, L | [6 empty] | 2024 | 320000 | 320000
ONSLOW | DOWNTOWN GREENWAY | JACKSONVILLE | CHANEY AVENUE TO WARDOLA DRIVE IN JACKSONVILLE. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | EB-6012 | DIVISION 3 | L, TA5200 |  |  |  |  | 2022 | 1367000 |  |  | 1367000 | UNDER CONSTRUCTION.
ONSLOW | SR 1509 (QUEENS CREEK ROAD) | NCDOT | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | HIGHWAY | BRIDGES | 3 | JACKSONVILLE URBAN AREA MPO | B-5944 | DIVISION 3 | BFP | 2028 | 500000 |  |  | 2030 | 10099000 |  |  | 10599000
ONSLOW | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE JACKSONVILLE PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 3 | JACKSONVILLE URBAN AREA MPO | HL-0102 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 1499000 |  |  | 1499000
ONSLOW | NC 24 | NCDOT | AT SR 1514 (PHILLIPS LOOP ROAD) IN SWANSBORO. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNALS AND ADVANCE FLASHERS. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO | HS-2003X | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2026 | 202000 |  |  | 202000
ONSLOW | US 17 | NCDOT | MULTI-LANE SECTION NORTH OF JACKSONVILLE TO SOUTH OF BELGRADE. | HIGHWAY | PRE-STI (HISTORIC) | 3 | JACKSONVILLE URBAN AREA MPO | R-2514A | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
ONSLOW | NC 24 (WEST CORBETT AVENUE) | NCDOT | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | R-5885 | NOT FUNDED | NHP | NOT FUNDED | 15304000 | NOT FUNDED | 802000 | NOT FUNDED | 28699000 |  |  | 44805000
ONSLOW | NC 24 (WEST CORBETT AVENUE) | NCDOT | REPLACE CULVERT EAST OF WEST SHORE DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | R-5885A | REGION B | NHP | 2025 | 115000 | 2025 | 84000 | 2027 | 1500000 |  |  | 1699000
ONSLOW | SR 1509 (QUEENS CREEK ROAD) | NCDOT | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | R-5948 | NOT FUNDED | T | NOT FUNDED | 4600000 | NOT FUNDED | 10300000 | NOT FUNDED | 12600000 |  |  | 27500000
ONSLOW | NC 53 | NCDOT | SR 1109 (HOLLY SHELTER ROAD). REALIGNMENT AND LANE CONSTRUCTION. | HIGHWAY | TRANSITION | 3 | JACKSONVILLE URBAN AREA MPO | SF-4903F | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-5023B AND C.
ONSLOW | US 17 | NCDOT | US 17 BUSINESS TO SR 1326 (DRUMMER KELLUM ROAD) IN JACKSONVILLE. ADD ADDITIONAL LANES AND CONSTRUCT ROUTES ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-4007
ONSLOW | SR 1702 (WEST HUFF DRIVE) | NCDOT | SR 1308 (BELL FORK ROAD) TO EAST OF SR 1470 (WESTERN BOULEVARD). | HIGHWAY | PRE-STI (HISTORIC) | 3 | JACKSONVILLE URBAN AREA MPO | U-4007A | [11 empty] | COMPLETED.
ONSLOW | JACKSONVILLE PARKWAY | NCDOT | COUNTRY CLUB ROAD TO SR 1470 (WESTERN BOULEVARD). | HIGHWAY | PRE-STI (HISTORIC) | 3 | JACKSONVILLE URBAN AREA MPO | U-4007B | [11 empty] | COMPLETED.
ONSLOW | US 17 | NCDOT | WESTERN BOULEVARD TO FAIRWAY DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-4007C | NOT FUNDED | NHP | NOT FUNDED | 34775000 |  |  | NOT FUNDED | 26300000 |  |  | 61075000
ONSLOW | US 17 | NCDOT | FAIRWAY DRIVE TO DRUMMER KELLUM ROAD. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-4007D | NOT FUNDED | NHP | NOT FUNDED | 32345000 |  |  | NOT FUNDED | 16600000 |  |  | 48945000
ONSLOW | NC 53 | NCDOT | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-4007E | STATEWIDE MOBILITY | T | 2028 | 8099000 | 2028 | 400000 | 2030 | 7200000 |  |  | 15699000 | COMBINED WITH U-5736 AND U-5508.
ONSLOW | SR 1308 (GUM BRANCH ROAD) | NCDOT | WEST OF SR 1313 (MILLS FIELDS ROAD) TO EAST OF SR 1324 (RAMSEY ROAD) IN JACKSONVILLE. WIDENING. | HIGHWAY | TRANSITION | 3 | JACKSONVILLE URBAN AREA MPO | U-4906 | PRE-STI (TRANSITION) | BGANY |  |  |  |  | 2021 | 15953000 |  |  | 15953000 | UNDER CONSTRUCTION.
ONSLOW | SR 1308 (GUM BRANCH ROAD) | NCDOT | SR 1470 (WESTERN BOULEVARD) IN JACKSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | TRANSITION | 3 | JACKSONVILLE URBAN AREA MPO | U-5319 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NCDOT | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5508 | STATEWIDE MOBILITY | T | 2028 | 799000 | 2028 | 150000 | 2030 | 1650000 |  |  | 2599000 | COMBINE WITH U-5736 AND U-4007E.
ONSLOW | NC 24 | NCDOT | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5716 | STATEWIDE MOBILITY | T | 2028 | 26700000 | 2028 | 2700000 | 2030 | 40700000 |  |  | 70100000 | PROJECT BEING LET WITH U-5739.
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | NCDOT | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5728 | REGION B | T |  |  |  |  | 2025 | 4800000 |  |  | 4800000 | RIGHT-OF-WAY IN PROGRESS.
ONSLOW | US 17 (WILMINGTON HIGHWAY) | NCDOT | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5735 | REGION B | T | 2027 | 28864000 | 2027 | 8328000 | 2031 | 51624000 |  |  | 88816000
ONSLOW | US 17 (WILMINGTON HIGHWAY) | NCDOT | ROADWAY IMPROVEMENTS TO DOUGLAS GATE ENTRANCE. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5735A | EXEMPT | O |  |  |  |  | 2021 | 1075000 |  |  | 1075000 | COMPLETED. OTHER FUNDS REPRESENT DEPARTMENT OF DEFENSE FUNDS.
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5736 | REGION B | T | 2028 | 10501000 | 2028 | 2440000 | 2030 | 31300000 |  |  | 44241000 | COMBINED WITH U-4007E AND U-5508.
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | NCDOT | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5739 | REGION B | T | 2028 | 3500000 | 2028 | 2900000 | 2030 | 19800000 |  |  | 26200000 | PROJECT BEING LET WITH WITH U-5716.
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NCDOT | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5741 | REGION B | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7368000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3664000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 49600000 |  |  | 60632000 | PROJECT INCLUDES B-5650.
ONSLOW | SR 2715 (TRADE STREET) | NCDOT | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5787 | DIVISION 3 | T | 2024 | 11700000 | 2024 | 1500000 | 2026 | 5900000 |  |  | 19100000 | RIGHT-OF-WAY IN PROGRESS.
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5789 | REGION B | T |  |  |  |  | 2025 | 4550000 |  |  | 4550000 | RIGHT-OF-WAY IN PROGRESS.
ONSLOW | SR 2714 (JACKSONVILLE PARKWAY EXTENSION) | NCDOT | NC 53 (WESTERN BOULEVARD) TO US 17 (NEW BERN HIGHWAY). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5791 | DIVISION 3
ONSLOW | SR 2714 | NCDOT | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5791A | DIVISION 3 | T | 2026 | 6709000 | 2026 | 1964000 | 2028 | 42428000 |  |  | 51101000 | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2026 / YR 8 SALE).
ONSLOW | SR 2714 | NCDOT | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5791B | NOT FUNDED | T | NOT FUNDED | 7900000 | NOT FUNDED | 2300000 | NOT FUNDED | 22600000 |  |  | 32800000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | NCDOT | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5793
ONSLOW | SR 1308 (GUM BRANCH ROAD) | NCDOT | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5793A | DIVISION 3 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9199000 |  |  | 16999000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | NCDOT | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5793B | DIVISION 3 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40100000 |  |  | 62800000
ONSLOW | COMMERCE DRIVE EXTENSION | NCDOT | COMMERCE DRIVE TO SR 1406 (PINEY GREEN ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5878 | DIVISION 3 | T |  |  |  |  | 2022 | 3417000 |  |  | 3417000 | UNDER CONSTRUCTION.
ONSLOW | SR 1336 (HENDERSON ROAD) | NCDOT | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5903 | DIVISION 3 | T | 2028 | 7400000 | 2028 | 4400000 | 2030 | 43600000 |  |  | 55400000
ONSLOW | NC 210 | NCDOT | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5949 | REGION B | T | 2028 | 8344000 | 2028 | 17594000 | 2032 | 69901000 |  |  | 95839000
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | NCDOT | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5950 | REGION B | BG5200 | 2025 | 75000 | 2025 | 154000 | 2027 | 825000 |  |  | 1054000
ONSLOW | US 17 | NCDOT | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-5951 | REGION B | T | 2026 | 400000 | 2026 | 69000 | 2028 | 14200000 |  |  | 14669000
ONSLOW | US 17 | NCDOT | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-6065 | STATEWIDE MOBILITY | HSIP, T | 2025 | 1000000 | 2025 | 1178000 | 2027 | 8701000 |  |  | 10879000
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-6081 | NOT FUNDED | T | NOT FUNDED | 2400000 | NOT FUNDED | 1000000 | NOT FUNDED | 50800000 |  |  | 54200000
ONSLOW | SR 1308 (BELL FORK ROAD) | NCDOT | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-6082 | DIVISION 3 | BG5200 | 2025 | 1300000 | 2025 | 900000 | 2028 | 4300000 |  |  | 6500000
ONSLOW | US 17 | NCDOT | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-6107 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 |  |  | 4100000
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | NCDOT | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-6148 | NOT FUNDED | NHP | NOT FUNDED | 329000 | NOT FUNDED | 140000 | NOT FUNDED | 750000 |  |  | 1219000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | NCDOT | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | U-6200 | NOT FUNDED | T | NOT FUNDED | 2127000 | NOT FUNDED | 1137000 | NOT FUNDED | 8800000 |  |  | 12064000
ONSLOW | VARIOUS | NCDOT | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO | W-5203REG | REGION B
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | NC 53 (WESTERN BOULEVARD) AT SR 1336 (HENDERSON DRIVE). INTERSECTION IMPROVEMENTS. | HIGHWAY | TRANSITION | 3 | JACKSONVILLE URBAN AREA MPO | W-5203U | REGION B | HSIP |  |  | 2023 | 23000 | 2023 | 1550000 |  |  | 1573000 | UNDER CONSTRUCTION.
ONSLOW | NC 172 | NCDOT | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO | W-5602 | REGION B | T |  |  |  |  | 2019 | 12183000 |  |  | 12183000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
ONSLOW | US 17 BUSINESS | NCDOT | US 17 BUSINESS (MARINE BOULEVARD) AND SR 1402 (OLD BRIDGE STREET). UPGRADE TRAFFIC SIGNAL, PAVEMENT MARKINGS, AND IMPROVE SIGHT DISTANCE. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO | W-5803C | REGION B | HSIP |  |  |  |  | 2023 | 85000 |  |  | 85000 | UNDER CONSTRUCTION.
ONSLOW | NC 24 | NCDOT | NC 24 (WEST CORBETT AVENUE) AND SR 1512 (OLD HAMMOCKS ROAD). UPGRADE PEDESTRIAN SIGNALS. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO | W-5803D | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2022 | 17000 |  |  | 17000 | COMPLETED.
ONSLOW | NC 53 | NCDOT | NC 53 (WESTERN BOULEVARD) AND CENTER STREET / LIBERTY DRIVE. UPGRADE TRAFFIC SIGNAL AND ADD ADDITIONAL SPEED LIMIT SIGNS. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO | W-5803E | REGION B | HSIP |  |  |  |  | 2022 | 57000 |  |  | 57000 | COMPLETED.
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | JACKSONVILLE URBAN AREA MPO | TA-4943 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1587000 | 1587000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | REPLACEMENT BUS - FIXED ROUTE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | JACKSONVILLE URBAN AREA MPO | TA-4944 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2516000 | 2516000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN | PUBLIC TRANSIT | STI (PRIORITIZATION) | 3 | JACKSONVILLE URBAN AREA MPO | TD-4904 | DIVISION 3 | 5307, 5309, L, T |  |  |  |  | 2020 | 11055000 |  |  | 11055000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | NON-FIXED ROUTE ADA PARATRANSIT | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 3 | JACKSONVILLE URBAN AREA MPO | TG-4952 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 761000 | 761000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 3 | JACKSONVILLE URBAN AREA MPO | TG-5109 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2076000 | 2076000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 3 | JACKSONVILLE URBAN AREA MPO | TG-5220 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 312000 | 312000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | ROUTINE CAPITAL-BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 3 | JACKSONVILLE URBAN AREA MPO | TG-5225 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 149000 | 149000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | MOBILITY MANAGEMENT | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 3 | JACKSONVILLE URBAN AREA MPO | TG-5225C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 653000 | 653000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | CONSTRUCT AN URBAN FIXED-ROUTE SATELLITE TRANSFER FACILITY FOR JACKSONVILLE TRANSIT TO INCLUDE PUBLIC PARKING, SHELTERS, RESTROOMS AND PESSENGER TERMINAL | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | JACKSONVILLE URBAN AREA MPO | TL-0001 | PUBLIC TRANSIT | 5307 |  |  |  |  | 2020 | 1000000 |  |  | 1000000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | CONSTRUCT PEDESTRIAN ACCESS AND SAFETY IMPROVEMENTS FOR JACKSONVILLE TRANSIT WITHIN 1/2 MILE OF HIGH VOLUME URBAN FIXED ROUTE BUS STOPS. IMPROVEMENTS WILL INCLUDE NEW SIDE WALK CONNECTIONS, ADA RETROFIT OF EXISTING SIDE WALKS AND CONSTRUCTION OF HIGH VISIBILITY CROSSWALKS AT KEY ROADWAY INTERSECTIONS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | JACKSONVILLE URBAN AREA MPO | TL-0002 | PUBLIC TRANSIT | 5307 |  |  |  |  | 2020 | 900000 |  |  | 900000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 3 | JACKSONVILLE URBAN AREA MPO | TO-4923 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 7990000 | 7990000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 | PUBLIC TRANSIT | PLANNING | 3 | JACKSONVILLE URBAN AREA MPO | TP-4908 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 745000 | 745000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | PLANNING | 3 | JACKSONVILLE URBAN AREA MPO | TP-5102 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 335000 | 335000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | JACKSONVILLE URBAN AREA MPO | TS-5114 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 116000 | 116000 | FUNDS AUTHORIZED IN PROGRESS
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | TECHNOLOGY - VEHICLE TRACKING, FARE COLLECTION, PASSENGER INFORMATION, DATA COMMUNICATIONS, TRAFFIC SIGNAL PRIORITY | PUBLIC TRANSIT | CAPITAL (NON-STI) | 3 | JACKSONVILLE URBAN AREA MPO | TT-4907 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1140000 | 1140000
ONSLOW, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY, WILMINGTON URBAN AREA MPO | W-5203DIV | DIVISION 3
ONSLOW, JONES | US 17 | NCDOT | SOUTH OF BELGRADE TO NORTH OF MAYSVILLE. | HIGHWAY | TRANSITION | 2, 3 | JACKSONVILLE URBAN AREA MPO, DOWN EAST RPO | R-2514B | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
ONSLOW, PENDER | US 17 | NCDOT | US 17 BETWEEN NEW HANOVER / PENDER COUNTY LINE AND MILE POST 19.3 IN ONSLOW COUNTY. INSTALL SHOULDER RUMBLE STRIPS. | HIGHWAY | SAFETY | 3 | JACKSONVILLE URBAN AREA MPO, WILMINGTON URBAN AREA MPO, CAPE FEAR RPO | W-5803B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 438000 |  |  | 438000 | UNDER CONSTRUCTION.
ORANGE | NC 54 | NCDOT | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | BIKE/PED | LOCALLY SELECTED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0044 | DIVISION 7 | BGDA, L, S |  |  |  |  | 2023 | 1311000 | 2022 | 175000 | 1486000 | “S” FUNDING REFLECTS SPOT SAFETY ALLOCATION.
ORANGE | MORGAN CREEK GREENWAY | CHAPEL HILL | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. | BIKE/PED | OTHER | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | BO-2415 | DIVISION 7 | BGDA, L, TADA | 2023 | 1173000 |  |  | 2024 | 1197000 |  |  | 2370000
ORANGE | ORANGE COUNTY BICYCLE ROUTE 1 | CHAPEL HILL | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | BIKE/PED | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5721 | DIVISION 7 | L, TADA |  |  |  |  | 2023 | 1571000 |  |  | 1571000
ORANGE | SR 1005 (JONES FERRY ROAD) | CARRBORO | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5880 | DIVISION 7 | L, TAANY | 2024 | 31000 |  |  | 2025 | 441000 | 2023 | 89000 | 561000
ORANGE | SR 1780 (ESTES DRIVE) | CHAPEL HILL | SR 1772 (NORTH GREENSBORO STREET) IN CARRBORO TO NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | BIKE/PED | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886 | DIVISION 7
ORANGE | SR 1780 (ESTES DRIVE) | NCDOT | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | BIKE/PED | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886A | DIVISION 7 | L, TAANY | 2024 | 46000 |  |  | 2026 | 848000 | 2022 | 170000 | 1064000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7.
ORANGE | SR 1780 (ESTES DRIVE) | NCDOT | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | BIKE/PED | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886B | DIVISION 7 | L, TAANY | 2023 | 864000 |  |  | 2025 | 3104000 | 2022 | 534000 | 4502000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7.
ORANGE | BARNES STREET | CARRBORO | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5890 | DIVISION 7 | L, TAANY | 2024 | 16000 |  |  | 2025 | 230000 | 2023 | 46000 | 292000
ORANGE | NC 54 | CARRBORO | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTI-USE PATH ON NORTH SIDE OF NC 54. | BIKE/PED | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5994 | DIVISION 7 | L, TAANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 43000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1188000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 238000 | 1469000
ORANGE | US 15 / US 501 | CHAPEL HILL | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | BIKE/PED | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5998 | DIVISION 7 | L, TAANY |  |  |  |  | 2026 | 3500000 | 2023 | 204000 | 3704000 | COORDINATE WITH U-5304
ORANGE | MORGAN CREEK GREENWAY | CARRBORO | WESTERN SECTION, SR 1919 (SMITH LEVEL ROAD) TO UNIVERSITY LAKE IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | BIKE/PED | TRANSITION | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EL-4828 | PRE-STI (TRANSITION) | [10 empty] | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY TOWN OF CARRBORO
ORANGE | MORGAN CREEK GREENWAY (CARRBORO) | CARRBORO | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | BIKE/PED | PRE-STI (HISTORIC) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EL-4828A | PRE-STI (TRANSITION) | BGDA, L, TADA |  |  |  |  | 2023 | 1568000 |  |  | 1568000
ORANGE | VARIOUS | DURHAM | BICYCLE DETECTION AT SIGNALIZED INTERSECTIONS. | BIKE/PED | LOCALLY SELECTED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4726DF | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 36000 |  |  | 36000
ORANGE | SR 1777 (HOMESTEAD ROAD) | DURHAM | SR 1843 (SEAWELL SCHOOL ROAD) TO SR 1733 (WEAVER DAIRY ROAD EXTENSION). | BIKE/PED | LOCALLY SELECTED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4726IK | DIVISION 7 | BGDA, L |  |  |  |  | 2023 | 1300000 |  |  | 1300000
ORANGE | SR 1005 (OLD GREENSBORO ROAD) | NCDOT | REPLACE BRIDGE 670085 OVER PHIL'S CREEK. | HIGHWAY | BRIDGES | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | B-5348 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
ORANGE | NC 86 | NCDOT | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | B-6037 | REGION D | BFP | 2024 | 250000 |  |  | 2025 | 2500000 |  |  | 2750000
ORANGE | SR 1750 (NORTH ESTES DRIVE) | CHAPEL HILL | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | HIGHWAY | LOCALLY SELECTED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5179 | EXEMPT | BGDA, BGDACV, CMAQ, L |  |  |  |  | 2020 | 5058000 |  |  | 5058000 | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
ORANGE | JONES CREEK GREENWAY | CARRBORO | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | HIGHWAY | TRANSITION | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5181 | EXEMPT | BGDA, CMAQ, L |  |  |  |  | 2023 | 910000 | 2022 | 12000 | 922000
ORANGE | RIVERWALK TRAIL | HILLSBOROUGH | RIVERWALK TRAIL, PHASE III IN HILLSBOROUGH. CONSTRUCT A PAVED OFF-ROAD TAIL ALONG ENO RIVER CONNECTING RIVER PARK, GOLD PARK AND THE OCCONEECHEE MOUNTAIN STATE NATURAL AREA, AND CONSTRUCT SIDEWALK TO PROVIDE PEDESTRIAN AND BICYCLE CONNECTIONS TO THE GREE | HIGHWAY | TRANSITION | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5184 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY TOWN OF HILLSBOROUGH
ORANGE | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | CARRBORO | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | HIGHWAY | LOCALLY SELECTED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5650 | DIVISION 7 | BGANY, BGDACV, CMAQ, L | 2023 | 125000 |  |  | 2024 | 2624000 |  |  | 2749000
ORANGE | EXCHANGE PARK LANE | HILLSBOROUGH | SOUTH CHURTON STREET TO FARIBAULT LANE IN HILLSBOROGH. REPAIR BRIDGE 670241 OVER ENO RIVER. | HIGHWAY | LOCALLY SELECTED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | HL-0045 | DIVISION 7 | BGDACV, L |  |  |  |  | 2023 | 153000 | 2021 | 20000 | 173000
ORANGE | I-40 | NCDOT | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306A | STATEWIDE MOBILITY | NHP, S(M) | 2021 | 10724000 | 2021 | 628000 | 2021 | 303565000 |  |  | 314917000 | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035
ORANGE | I-40 | NCDOT | NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTIONS FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306AC | REGION D | NHP | 2024 | 550000 | 2024 | 450000 | 2026 | 4350000 |  |  | 5350000
ORANGE | I-40 | NCDOT | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. TOWING CONTRACT FOR I-3306A CONSTRUCTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306AD | STATEWIDE MOBILITY | T |  |  |  |  | 2023 | 2280000 |  |  | 2280000 | UNDER CONSTRUCTION
ORANGE | I-40 / I-85 | NCDOT | WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1006 (ORANGE GROVE ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO | I-5958 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2027 | 9500000 |  |  | 9500000
ORANGE | I-85 | NCDOT | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5967 | STATEWIDE MOBILITY | NHP | 2028 | 52800000 | 2028 | 1200000 | 2031 | 57200000 |  |  | 111200000
ORANGE | I-85 | NCDOT | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5984 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 58200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 44099000 |  |  | 104399000 | COORDINATE WITH I-305
ORANGE | NC 54 | NCDOT | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS, AND IMPROVE SR 1006 INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO, TRIANGLE AREA RPO | R-5821
ORANGE | NC 54 | NCDOT | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5821A | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 |  |  | 17100000
ORANGE | NC 54 | NCDOT | SR 1006 (ORANGE GROVE ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5821B | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ORANGE | US 15 / US 501 | NCDOT | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304A | NOT FUNDED | T | NOT FUNDED | 10000000 | NOT FUNDED | 1040000 | NOT FUNDED | 22001000 |  |  | 33041000
ORANGE | US 15 / US 501 | NCDOT | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304B | NOT FUNDED | T | NOT FUNDED | 6000000 | NOT FUNDED | 285000 | NOT FUNDED | 22001000 |  |  | 28286000
ORANGE | US 15 / US 501 | NCDOT | SR 1742 (EPHESUS CHURCH ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | PRE-STI (HISTORIC) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304C | [11 empty] | WORK COMPLETED UNDER U-5550.
ORANGE | US 15 / US 501 | NCDOT | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304D | NOT FUNDED | T | NOT FUNDED | 5000000 | NOT FUNDED | 344000 | NOT FUNDED | 30001000 |  |  | 35345000
ORANGE | US 15 / US 501 | NCDOT | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304E | NOT FUNDED | T | NOT FUNDED | 12000000 | NOT FUNDED | 446000 | NOT FUNDED | 25000000 |  |  | 37446000
ORANGE | US 15 / US 501 (FORDHAM BOULEVARD) | NCDOT | SR 1742 (EPHESUS CHURCH ROAD) IN CHAPEL HILL. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5550 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
ORANGE | NC 54 | NCDOT | US 15 / US 501. UPGRADE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774A | NOT FUNDED | T | NOT FUNDED | 2800000 | NOT FUNDED | 140000 | NOT FUNDED | 16100000 |  |  | 19040000
ORANGE | SR 1009 (SOUTH CHURTON STREET) | NCDOT | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5845 | DIVISION 7 | T | 2028 | 10200000 | 2028 | 1200000 | 2031 | 24001000 |  |  | 35401000
ORANGE | SR 1772 (GREENSBORO STREET) | NCDOT | SR 1780 (ESTES DRIVE) IN CARRBORO. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5846 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ORANGE | SR 1008 (MT. CARMEL CHURCH ROAD) | NCDOT | SR 1913 (BENNETT ROAD) IN CHAPEL HILL. CONSTRUCT ROUNDABOUT AND RELATED SAFETY IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5854 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ORANGE | SR 1146 (WEST TEN ROAD) | NCDOT | SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1137 (BUSHY COOK ROAD). CONSTRUCT OVERLAY, PAVED SHOULDERS AND TURN LANES. | HIGHWAY | ECONOMIC DEVELOPMENT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6245 | DIVISION 7 | T |  |  |  |  | 2021 | 829000 | 2020 | 109000 | 938000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE.
ORANGE | SR 1004 (EFLAND-CEDAR GROVE ROAD) | NCDOT | NORTH OF INTERSECTION WITH SR 1332 (HIGHLAND FARM ROAD). IMPROVE HORIZONTAL ALIGNMENT OF CURVE TO PROVIDE A MINIMUM OF 60 MPH DESIGN SPEED. | HIGHWAY | TRANSITION | 7 | TRIANGLE AREA RPO | W-5143 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT BUSES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4726 | PUBLIC TRANSIT | 5307, 5339, L, S | [6 empty] | 2020 | 9692000 | 9692000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | 3 REPLACEMENT BUSES. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4726A | DIVISION 7 | [10 empty] | IN PROGRESS BY CHAPEL HILL TRANSIT
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT - PARATRANSIT VEHICLE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4748 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 788000 | 788000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT VAN | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4979 | PUBLIC TRANSIT | 5307 | [6 empty] | 2023 | 792000 | 792000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | ORANGE PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | PURCHASE TWO (2) LIGHT TRANSIT VEHICLES | PUBLIC TRANSIT | STI (PRIORITIZATION) | 7 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6721 | DIVISION 7 | L, T | [6 empty] | 2022 | 109000 | 109000
ORANGE | ORANGE PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | PURCHASE NEW BUS < 30'. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6731 | PUBLIC TRANSIT | FED, L | [6 empty] | 2020 | 56000 | 56000
ORANGE | ORANGE PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | 1 REPLACEMENT LTV (25') AND RADIO, VEHICLE LETTERING AND LOGOS, AND ON-BOARD CAMERA. | PUBLIC TRANSIT | LOCALLY SELECTED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5155 | DIVISION 7 | BGDA, L | [6 empty] | 2022 | 77000 | 77000 | IN PROGRESS BY ORANGE PUBLIC TRANSIT
ORANGE | GO TRIANGLE | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX | PUBLIC TRANSIT | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5284 | REGION D | 5307, L, T |  |  |  |  | 2024 | 360000 |  |  | 360000
ORANGE | GO TRIANGLE | GO TRIANGLE | TOWN OF HILLSBOROUGH. CONSTRUCT PARK-AND-RIDE LOT. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5295 | REGION D | L, S |  |  |  |  | 2023 | 920000 |  |  | 920000 | UNDER CONSTRUCTION BY GO TRIANGLE
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4731B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 5372000 | 5372000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4732A | PUBLIC TRANSIT | 5307, S | [6 empty] | 2020 | 1080000 | 1080000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4732B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 196000 | 196000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | ORANGE PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | TRIANGLE AREA RPO | TK-6151 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 744000 | 744000
ORANGE | GOTRIANGLE | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TL-0018 | PUBLIC TRANSIT | CMAQ, L |  |  |  |  | 2023 | 400000 |  |  | 400000
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TO-5133 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 14280000 | 14280000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | DURHAM | DURHAM | 5307 OPERATING FUNDS NC 2019-060-01-P11 | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TO-5206 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 311000 | 311000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
ORANGE | BURLINGTON -GRAHAM | BURLINGTON -GRAHAM | 5307 OPERATING FUNDS NC-2019-060-01-P10 | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7 | BURLINGTON-GRAHAM MPO | TO-5220 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 282000 | 282000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY 2020 GRANTS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | ALTERNATIVE ANALYSIS - ENVIRONMENTAL ASSESSMENT, DESIGN, AND ENGINEERING | PUBLIC TRANSIT | PLANNING | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5119A | PUBLIC TRANSIT | FED, L | [6 empty] | 2020 | 200000 | 200000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | NORFOLK SOUTHERN H LINE | NCDOT | MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PLATFORM, PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. | RAIL | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5701 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION. "OTHER" FUNDING REFLECTS PARTICIPATION BY TRIANGLE TRANSIT.
ORANGE | NORFOLK SOUTHERN H LINE | NCDOT | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. | RAIL | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5701A | DIVISION 7 | O, T |  |  |  |  | 2022 | 6860000 |  |  | 6860000
ORANGE | NORFOLK SOUTHERN H LINE | NCDOT | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT STATION PLATFORM AND REALIGN CURVE AT MILEPOST 41.4. | RAIL | STI (PRIORITIZATION) | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5701B | DIVISION 7 | T |  |  |  |  | 2023 | 1000000 |  |  | 1000000
ORANGE | SR 1120 (MOUNT WILLING ROAD) | NCDOT | NORFOLK SOUTHERN RAILROAD CROSSING 735145T NEAR EFLAND. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | RX-2007B | DIVISION 7 | RR |  |  |  |  | 2024 | 800000 |  |  | 800000
ORANGE, DURHAM | SR 1838 / SR 2220 | NCDOT | US 15 / US 501 IN ORANGE COUNTY TO SR 1113 (POPE ROAD) IN DURHAM COUNTY | HIGHWAY | TRANSITION | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-4707A | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ORANGE, DURHAM | I-85 | NCDOT | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-0305 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 120898000 |  |  | 139998000 | COORDINATE WITH I-5967, I-5984 AND U-5845
ORANGE, DURHAM | I-40 | NCDOT | I-85 IN ORANGE COUNTY TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM COUNTY. WIDEN TO SIX LANES AND INSTALL ITS. | HIGHWAY | STI (PRIORITIZATION) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306
ORANGE, DURHAM | US 15 / US 501 (FORDHAM BOULEVARD) | NCDOT | NC 86 (SOUTH COLUMBIA STREET) TO I-40 IN CHAPEL HILL. UPGRADE CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304 | [11 empty] | COORDINATE WITH EB-5998 AND U-5774
ORANGE, DURHAM | US 15 / US 501 | NCDOT | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304F | REGION C, D | T | 2028 | 6000000 | 2028 | 726000 | 2030 | 26999000 |  |  | 33725000
ORANGE, DURHAM | VARIOUS | CHAPEL HILL | VARIABLE MESSAGE SIGNS FOR TRAFFIC MANAGEMENT ON MAJOR CORRIDORS IN CHAPEL HILL. | HIGHWAY | LOCALLY SELECTED | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5543 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
ORANGE, DURHAM | NC 54 | NCDOT | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774B | REGION C, D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 43001000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 23300000 |  |  | 66375000
PAMLICO | NC 55 | NCDOT | REPLACE BRIDGE 680038 OVER TRENT CREEK. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-4593 | REGION B | NHPB |  |  |  |  | 2022 | 5837000 |  |  | 5837000 | UNDER CONSTRUCTION.
PAMLICO | SR 1302 (JANIERO ROAD) | NCDOT | REPLACE BRIDGE 680057 OVER DAWSON CREEK. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO | B-5995 | DIVISION 2 | BGOFF | 2022 | 600000 |  |  | 2023 | 3850000 |  |  | 4450000 | UNDER CONSTRUCTION.
PAMLICO, CARTERET, CRAVEN | US 70, NC 55 | NCDOT | US 70 BETWEEN NUNN STREET AND SR 1605 (FRIENDLY ROAD) IN MOREHEAD CITY, AND NC 55 BETWEEN US 17 IN BRIDGETON AND SR 1210 (1ST STREET) IN BAYBORO. INSTALL 6 INCH LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 2 | DOWN EAST RPO | W-5802E | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 865000 |  |  | 865000 | COMPLETED.
PASQUOTANK | PROVIDENCE ROAD | ELIZABETH CITY | REPLACE BRIDGE 690034 OVER KNOBBS CREEK TRIBUTARY IN ELIZABETH CITY. | HIGHWAY | BRIDGES | 1 | ALBEMARLE RPO | B-6053 | DIVISION 1 | BGOFF, L |  |  | 2021 | 135000 | 2022 | 1725000 |  |  | 1860000 | COMPLETED. MUNICIPAL BRIDGE.
PASQUOTANK | SR 1354 (MILLPOND ROAD) | NCDOT | SR 1354 (MILLPOND ROAD) BETWEEN US 158 AND SR 1001 (TURNPIKE ROAD). UPGRADE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO | HS-2001C | DIVISION 1 | HSIP |  |  |  |  | 2024 | 40000 |  |  | 40000
PASQUOTANK | US 17 (FUTURE I-87) | NCDOT | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 1 | ALBEMARLE RPO | I-6029 | STATEWIDE MOBILITY | NHP, NHPIM, S(M) |  |  |  |  | 2020 | 11886000 |  |  | 11886000 | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034.
PASQUOTANK | US 17 BUSINESS | NCDOT | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | U-5939 | REGION A | BG5T50 | 2024 | 2808000 | 2024 | 299000 | 2025 | 9100000 |  |  | 12207000
PASQUOTANK | US 17 (HUGHES BOULEVARD) | NCDOT | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | U-5940 | REGION A | T | 2025 | 15989000 | 2025 | 476000 | 2027 | 12900000 |  |  | 29365000
PASQUOTANK | ELIZABETH CITY | NCDOT | ELIZABETH CITY SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | U-5942 | REGION A | BG5200, HP |  |  |  |  | 2021 | 5059000 |  |  | 5059000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368.
PASQUOTANK | SR 1333 (WEST MAIN STREET EXTENSION) | NCDOT | FROM 0.6 MILES NORTH OF SR 1338 (BEREA CHURCH ROAD) TO 0.2 MILES SOUTH OF SR 1338 (BEREA CHURCH ROAD). | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO | W-5701C | DIVISION 1 | HSIP | 2023 | 170000 |  |  | 2024 | 1025000 |  |  | 1195000 | RIGHT-OF-WAY IN PROGRESS.
PASQUOTANK, CAMDEN, PERQUIMANS | VARIOUS | NCDOT | UPGRADE WARNING SIGNS AT CURVES AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 1 | ALBEMARLE RPO | HS-2001D | DIVISION 1 | HSIP |  |  |  |  | 2023 | 41000 |  |  | 41000 | UNDER CONSTRUCTION.
PENDER | HENDERSON FIELD (ACZ) | HENDERSON FIELD (ACZ) | EXTEND RUNWAY TO 5500 FEET. | AVIATION | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | AV-5744 | DIVISION 3 | T | 2022 | 1978000 |  |  | 2024 | 13105000 |  |  | 15083000 | RIGHT-OF-WAY IN PROGRESS.
PENDER | HENDERSON FIELD (ACZ) | HENDERSON FIELD (ACZ) | APRON EXPANSION. | AVIATION | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | AV-5815 | DIVISION 3 | T |  |  |  |  | 2024 | 6100000 |  |  | 6100000
PENDER | US 17 | NCDOT | US 17 AND NC 210 WEST OF SNEADS FERRY. REVISE TRAFFIC SIGNAL AND INSTALL BE PREPARED TO STOP SIGNS. | HIGHWAY | SAFETY | 3 | CAPE FEAR RPO | HS-2003F | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2026 | 194000 |  |  | 194000
PENDER | I-40 | NCDOT | WEST OF US 117 (MILE MARKER 388) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 3 | CAPE FEAR RPO | I-6040 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 19768000 |  |  | 19768000 | UNDER CONSTRUCTION.
PENDER | US 17 | NCDOT | NC 210 TO US 17 NORTH OF HAMPSTEAD. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | R-3300B | REGION B | T |  |  |  |  | 2022 | 229552000 |  |  | 229552000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE).
PENDER | NC 53 | NCDOT | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | R-5701 | REGION B | L, T | 2025 | 55000 | 2025 | 172000 | 2027 | 1450000 |  |  | 1677000
PENDER | NC 53 | NCDOT | US 117 BYPASS TO SR 1509 (STAG PARK ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | R-5850 | NOT FUNDED | BGLT5 | NOT FUNDED | 5900000 | NOT FUNDED | 1908000 | NOT FUNDED | 6300000 |  |  | 14108000
PENDER | US 17 | NCDOT | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | R-5877 | NOT FUNDED | NHP | NOT FUNDED | 6000000 | NOT FUNDED | 2100000 | NOT FUNDED | 11900000 |  |  | 20000000
PENDER | NC 210 | NCDOT | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | R-5899 | DIVISION 3 | T | 2025 | 1044000 | 2025 | 117000 | 2027 | 2600000 |  |  | 3761000
PENDER | NC 50/NC 210 | NCDOT | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 3 | CAPE FEAR RPO | R-5900 | DIVISION 3 | T | 2025 | 5000000 | 2025 | 800000 | 2028 | 1300000 |  |  | 7100000
PENDER | US 17 | NCDOT | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5732 | REGION B | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19536000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35900000 |  |  | 55436000
PENDER | DAN OWEN DRIVE EXTENSION | NCDOT | SR 1570 (FACTORY ROAD) TO DAN OWEN DRIVE. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | U-5732A | REGION B | [10 empty] | COMPLETED.
PENDER | PENDER ADULT SERVICES, INC. | PENDER ADULT SERVICES, INC. | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 3 | CAPE FEAR RPO | TK-6152 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
PENDER, NEW HANOVER | US 17 | NCDOT | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | HIGHWAY | STI (PRIORITIZATION) | 3 | WILMINGTON URBAN AREA MPO | R-3300A | REGION B | T |  |  |  |  | 2026 | 149440000 |  |  | 149440000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
PERQUIMANS | SR 1338 (WYNNE FORK ROAD) | NCDOT | REPLACE BRIDGE 710011 OVER RACOON CREEK. | HIGHWAY | BRIDGES | 1 | ALBEMARLE RPO | B-5606 | DIVISION 1 | T |  |  |  |  | 2021 | 1545000 |  |  | 1545000 | COMPLETED. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
PERQUIMANS | US 17 (FUTURE I-87) | NCDOT | SR 1101 (EAST BEAR SWAMP ROAD) TO US 17 BUSINESS NORTH OF HERTFORD. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 1 | ALBEMARLE RPO | I-6030 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 5000000 |  |  | 5000000
PERQUIMANS | US 17 BUSINESS/ NC 37 | NCDOT | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | HIGHWAY | PRE-STI (HISTORIC) | 1 | ALBEMARLE RPO | R-4467 | REGION A | T |  |  |  |  | 2019 | 65512000 | 2021 | 2415000 | 67927000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
PERQUIMANS | SR 1329 (WOODVILLE ROAD) | NCDOT | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5740 | DIVISION 1 | T | 2019 | 765000 |  |  | 2021 | 5841000 | 2020 | 1035000 | 7641000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
PERQUIMANS | SR 1336 (HARVEY POINT ROAD) | NCDOT | US 17 TO SR 1350 (CHURCHES LANE). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5806 | DIVISION 1 | BGLT5 |  |  |  |  | 2022 | 3900000 |  |  | 3900000 | UNDER CONSTRUCTION.
PERQUIMANS | US 17 | NCDOT | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY AND CONVERT INTERSECTIONS TO INTERCHANGES. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5869
PERQUIMANS | US 17 | NCDOT | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5869A | DIVISION 1 | NHP | 2028 | 6000000 | 2028 | 900000 | 2031 | 30000000 |  |  | 36900000
PERQUIMANS | US 17 | NCDOT | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5869B | DIVISION 1 | NHP | 2028 | 4200000 | 2028 | 2000000 | 2032 | 30000000 |  |  | 36200000
PERQUIMANS | US 17 | NCDOT | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5869C | NOT FUNDED | NHP | NOT FUNDED | 3500000 | NOT FUNDED | 1000000 | NOT FUNDED | 135000000 |  |  | 139500000 | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY.
PERQUIMANS | SR 1300 (NEW HOPE ROAD) | NCDOT | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5939 | DIVISION 1 | T | 2028 | 5400000 | 2028 | 1400000 | 2030 | 14100000 |  |  | 20900000
PERSON | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). | AVIATION | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | AV-5818 | DIVISION 5 | T |  |  |  |  | 2028 | 15160000 |  |  | 15160000
PERSON | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | ROXBORO | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | HIGHWAY | LOCALLY SELECTED | 5 | KERR-TAR RPO | BL-0061 | EXEMPT | CMAQ, L | 2024 | 65000 |  |  | 2024 | 450000 | 2023 | 130000 | 645000
PERSON | US 501 | NCDOT | US 501 AT NC 57 (HILLSBOROUGH ROAD). INSTALL TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO | HS-2005P | REGION C | HSIP |  |  |  |  | 2024 | 260000 |  |  | 260000
PERSON | US 501 | NCDOT | SOUTH OF US 158 TO SR 1601 (NORTH MAIN STREET) IN ROXBORO. CONVERT TO 4-LANE MEDIAN DIVIDED FACILITY, IMPROVE VARIOUS INTERSECTIONS WITH SOME CONSOLIDATION OF INTERSECTIONS, AND FILL IN SIDEWALK GAPS. | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | U-5969
PERSON | US 501 | NCDOT | SOUTH OF US 158 TO NC 157. | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | U-5969A | DIVISION 5 | T | 2027 | 7200000 | 2027 | 1288000 | 2029 | 4400000 |  |  | 12888000
PERSON | US 501 | NCDOT | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | U-5969B | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 917000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9200000 |  |  | 16817000
PERSON | US 501 / NC 49 | NCDOT | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | U-5969C | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1346000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6600000 |  |  | 14246000
PERSON | PERSON COUNTY | PERSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | KERR-TAR RPO | TK-6153 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 664000 | 664000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE | GREENVILLE | SOUTH TAR RIVER GREENWAY. PHASE 3: PITT STREET TO NASH STREET. CONSTRUCT GREENWAY USING EXISTING SIDEWALKS, ROADS AND ON NEW LOCATION ALONG THE RIVER. | BIKE/PED | TRANSITION | 2 | GREENVILLE URBAN AREA MPO | EB-5539 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION.
PITT | US 264-A (GREENVILLE BOULEVARD) | NCDOT | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | EB-5980 | NOT FUNDED | L, TA5200 | NOT FUNDED | 50000 |  |  | NOT FUNDED | 787000 | NOT FUNDED | 34000 | 871000
PITT | NC 11 (MEMORIAL DRIVE) | NCDOT | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | EB-5981 | NOT FUNDED | L, TA5200 | NOT FUNDED | 40000 |  |  | NOT FUNDED | 2044000 | NOT FUNDED | 83000 | 2167000
PITT | GREENVILLE | GREENVILLE | CONSTRUCT MULTI-USE PATH AT VARIOUS LOCATIONS INCLUDING ALONG THE TAR RIVER, MOYE BOULEVARD, THE NORFOLK SOUTHERN RAIL CORRIDOR, AND TOWN CREEK IN GREENVILLE. | BIKE/PED | LOCALLY SELECTED | 2 | GREENVILLE URBAN AREA MPO | EB-6042 | EXEMPT | DP, L |  |  |  |  | 2022 | 7069000 |  |  | 7069000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | SR 1777 (BLACK JACK / GRIMESLAND ROAD) | NCDOT | REPLACE BRIDGE 730005 OVER CHICOD CREEK. | HIGHWAY | BRIDGES | 2 | MID-EAST RPO | B-4605 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1100000 |  |  | 1100000 | UNDER CONSTRUCTION.
PITT | SR 1923 (GARDENVILLE ROAD) | NCDOT | REPLACE BRIDGE 730043 OVER SWIFT CREEK. | HIGHWAY | BRIDGES | 2 | DOWN EAST RPO, MID-EAST RPO | B-4607 | DIVISION 2 | BGOFF | 2022 | 260000 |  |  | 2022 | 1775000 |  |  | 2035000 | UNDER CONSTRUCTION.
PITT | US 13 | NCDOT | REPLACE BRIDGE 730038 OVER TAR RIVER IN GREENVILLE. | HIGHWAY | BRIDGES | 2 | GREENVILLE URBAN AREA MPO | B-4786 | REGION B | NHPB |  |  |  |  | 2022 | 8200000 |  |  | 8200000 | UNDER CONSTRUCTION.
PITT | NC 222 | NCDOT | REPLACE BRIDGE 730024 OVER TAR RIVER. | HIGHWAY | BRIDGES | 2 | MID-EAST RPO | B-5612 | REGION B | T | 2019 | 950000 |  |  | 2028 | 14000000 |  |  | 14950000 | RIGHT-OF-WAY IN PROGRESS.
PITT | OXFORD ROAD | NCDOT | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | HIGHWAY | MUNICIPAL BRIDGE | 2 | GREENVILLE URBAN AREA MPO | HB-0021 | DIVISION 2 | BGOFF | 2023 | 50000 | 2024 | 143000 | 2024 | 1668000 |  |  | 1861000
PITT | ROCK SPRINGS ROAD | NCDOT | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | HIGHWAY | MUNICIPAL BRIDGE | 2 | GREENVILLE URBAN AREA MPO | HB-0022 | DIVISION 2 | BGOFF | 2029 | 100000 | 2029 | 126000 | 2030 | 2277000 |  |  | 2503000
PITT | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENVILLE PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 2 | GREENVILLE URBAN AREA MPO | HL-0099 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 1674000 |  |  | 1674000
PITT | SR 1703 (14TH STREET) | NCDOT | INSTALL CROSSWALK, WHEELCHAIR RAMPS, SIDEWALK, AND FENCING ALONG SR 1703 (14TH STREET) FROM HASKETT WAY AND BERKLEY ROAD. REMOVE TWO EXISTING OBSOLETE CROSSWALKS. | HIGHWAY | SAFETY | 2 | GREENVILLE URBAN AREA MPO | HS-2002A | DIVISION 2 | HSIP |  |  |  |  | 2021 | 50000 |  |  | 50000 | COMPLETED.
PITT | US 264 ALTERNATE | NCDOT | US 264 ALTERNATE (GREENVILLE BOULEVARD) AT SR 1534 (OLD PACTOLUS ROAD). CONSTRUCT RESTRICTED-CROSSING INTERSECTION. | HIGHWAY | SAFETY | 2 | GREENVILLE URBAN AREA MPO | HS-2002E | REGION B | HSIP |  |  |  |  | 2023 | 732000 |  |  | 732000 | UNDER CONSTRUCTION.
PITT | NC 33 | NCDOT | NC 33 FROM US 13/NC 11 (MEMORIAL DRIVE) TO DAUGHTRIDGE DRIVE IN GREENVILLE. INSTALL MEDIAN ISLAND AND REVISE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 2 | GREENVILLE URBAN AREA MPO | HS-2002J | REGION B | HSIP |  |  |  |  | 2023 | 120000 |  |  | 120000 | UNDER CONSTRUCTION.
PITT | US 264 ALTERNATE | NCDOT | US 264 ALTERNATE/NC 43 (GREENVILLE BOULEVARD) AT NC 11/NC 43/NC 903 (MEMORIAL DRIVE) AND NC 11/NC 903 (MEMORIAL DRIVE) AT MALL DRIVE IN GREENVILLE. REVISE AND CONSTRUCT TURN LANES. | HIGHWAY | SAFETY | 2 | GREENVILLE URBAN AREA MPO | HS-2002L | REGION B | HSIP |  |  |  |  | 2024 | 430000 |  |  | 430000
PITT | SR 1598 (10TH STREET) | NCDOT | SR 1598 (10TH STREET) AT COLLEGE HILL DRIVE AND SR 1598 (10TH STREET) AT ELM STREET IN GREENVILLE. UPGRADE TRAFFIC SIGNALS. | HIGHWAY | SAFETY | 2 | GREENVILLE URBAN AREA MPO | HS-2002M | DIVISION 2 | HSIP |  |  |  |  | 2023 | 55000 |  |  | 55000 | UNDER CONSTRUCTION.
PITT | SR 1702 (EVANS STREET) | NCDOT | SR 1702 (EVANS STREET) AT HOWELL STREET IN GREENVILLE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | SAFETY | 2 | GREENVILLE URBAN AREA MPO | HS-2002R | DIVISION 2 | HSIP |  |  | 2023 | 65000 | 2023 | 400000 |  |  | 465000 | UNDER CONSTRUCTION.
PITT | SR 1725 (COUNTY HOME ROAD) | NCDOT | AT EXISTING CROSSWALK JUST SOUTH OF DISTRICT PARK DRIVE IN GREENVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS. | HIGHWAY | SAFETY | 2 | GREENVILLE URBAN AREA MPO | HS-2002X | DIVISION 2 | HSIP |  |  |  |  | 2023 | 35000 |  |  | 35000 | UNDER CONSTRUCTION.
PITT | US 264/US 258 (FUTURE I-587) | NCDOT | GREENE COUNTY LINE TO SR 1467 (STANTONSBURG ROAD) INTERCHANGE (GREENVILLE SOUTHWEST BYPASS). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 2 | MID-EAST RPO, GREENVILLE URBAN AREA MPO | I-6035 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 14420000 |  |  | 14420000 | UNDER CONSTRUCTION. TO BE LET WITH I-6032. GARVEE BOND FUNDING $12M FOR CON, PAYBACK FY 2019-2033.
PITT | NC 11/NC 903 (GREENVILLE SOUTHWEST BYPASS) | NCDOT | NC 11 TO US 264 (GREENVILLE BYPASS). CONSTRUCT FOUR LANE DIVIDED FACILITY ON NEW LOCATION WITH BYPASS OF WINTERVILLE. | HIGHWAY | PRE-STI (HISTORIC) | 2 | GREENVILLE URBAN AREA MPO | R-2250 | PRE-STI (TRANSITION) | T |  |  |  |  | 2023 | 750000 |  |  | 750000 | UNDER CONSTRUCTION.
PITT | SR 1700 (EVANS STREET/ OLD TAR ROAD) | NCDOT | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-2817 | DIVISION 2 | BG5200 | 2019 | 22800000 | 2019 | 3972000 | 2025 | 67545000 |  |  | 94317000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1598 (DICKINSON AVENUE) | NCDOT | NC 11 TO READE CIRCLE. IMPROVE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-5606 | DIVISION 2 | BG5200 |  |  |  |  | 2022 | 18365000 |  |  | 18365000 | UNDER CONSTRUCTION.
PITT | US 13 (MEMORIAL DRIVE) | NCDOT | NC 43 (5TH STREET). UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-5730 | REGION B | T |  |  | 2023 | 125000 | 2025 | 1200000 |  |  | 1325000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1708 (FIRETOWER ROAD) | NCDOT | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-5785 | DIVISION 2 | T | 2024 | 17620000 | 2024 | 1000000 | 2026 | 20500000 |  |  | 39120000 | TO BE LET WITH U-5917.
PITT | SR 1708 (FIRETOWER ROAD) | NCDOT | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-5870 | DIVISION 2 | T | 2024 | 12616000 | 2024 | 1600000 | 2026 | 28199000 |  |  | 42415000
PITT | SR 1203 (ALLEN ROAD) | NCDOT | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-5875 | DIVISION 2 | T |  |  |  |  | 2024 | 40100000 |  |  | 40100000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1704 (FOURTEENTH STREET) | NCDOT | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-5917 | DIVISION 2 | T | 2019 | 952000 | 2024 | 2772000 | 2026 | 14902000 | 2020 | 1740000 | 20366000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5785. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
PITT | GREENVILLE | NCDOT | GREENVILLE SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-5952 | REGION B | BG5200 |  |  | 2026 | 750000 | 2028 | 12000000 |  |  | 12750000
PITT | NC 43 | NCDOT | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-5991 | DIVISION 2 | T | 2027 | 14000000 | 2027 | 7500000 | 2029 | 30200000 |  |  | 51700000
PITT | NC 33 (10TH STREET) | NCDOT | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-6125 | NOT FUNDED | T | NOT FUNDED | 6800000 | NOT FUNDED | 3500000 | NOT FUNDED | 14199000 |  |  | 24499000
PITT | NC 43 (CHARLES BOULEVARD) | NCDOT | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-6147 | NOT FUNDED | T | NOT FUNDED | 5900000 | NOT FUNDED | 800000 | NOT FUNDED | 12001000 |  |  | 18701000
PITT | SR 1467 (STANTONSBURG ROAD) | NCDOT | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-6195 | NOT FUNDED | T | NOT FUNDED | 9000000 | NOT FUNDED | 2100000 | NOT FUNDED | 21601000 |  |  | 32701000
PITT | SR 1702 (EVANS STREET) | NCDOT | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-6196 | NOT FUNDED | T | NOT FUNDED | 9500000 | NOT FUNDED | 2900000 | NOT FUNDED | 9300000 |  |  | 21700000
PITT | SR 1711 (WORTHINGTON ROAD) | NCDOT | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO | U-6197 | DIVISION 2 | T | 2027 | 900000 | 2027 | 500000 | 2029 | 1600000 |  |  | 3000000
PITT | NC 33 | NCDOT | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 2 | GREENVILLE URBAN AREA MPO, MID-EAST RPO | U-6215 | NOT FUNDED | T | NOT FUNDED | 30100000 | NOT FUNDED | 2900000 | NOT FUNDED | 70099000 |  |  | 103099000
PITT | SR 1571 (WEST 5TH STREET) | GREENVILLE | REHABILITATION AND REALIGNMENT OF SR 1571 (WEST 5TH STREET) FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. | HIGHWAY | LOCALLY SELECTED | 2 | GREENVILLE URBAN AREA MPO | U-6240 | DIVISION 2 | DP, L |  |  |  |  | 2022 | 18480000 |  |  | 18480000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 2 | GREENVILLE URBAN AREA MPO | TG-4767 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2404000 | 2404000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 2 | GREENVILLE URBAN AREA MPO | TG-5107B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2700000 | 2700000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 2 | GREENVILLE URBAN AREA MPO | TG-5107C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 600000 | 600000 | FUNDS AUTHORIZED IN PROGRESS
PITT | PITT COUNTY | PITT COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 2 | MID-EAST RPO | TK-6154 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 720000 | 720000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | FLEET SERVICE BUILDING EXPANSION. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 2 | GREENVILLE URBAN AREA MPO | TL-0009 | PUBLIC TRANSIT | CARES, L |  |  |  |  | 2021 | 976000 |  |  | 976000
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 2 | GREENVILLE URBAN AREA MPO | TO-4726 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 5420000 | 5420000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | PLANNING | 2 | GREENVILLE URBAN AREA MPO | TP-5107 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 132000 | 132000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | SAFETY & SECURITY | PUBLIC TRANSIT | CAPITAL (NON-STI) | 2 | GREENVILLE URBAN AREA MPO | TS-5112 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 15000 | 15000 | FUNDS AUTHORIZED IN PROGRESS
PITT | EAST STREET | NCDOT | CLOSURE OF EAST STREET AT CSX (CROSSING 628 794Y) IN BETHEL. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 2 | MID-EAST RPO | RC-2002A | DIVISION 2 | RR |  |  |  |  | 2024 | 560000 |  |  | 560000
PITT | SR 1726 (PORTERTOWN ROAD) | NCDOT | CLNA CROSSING 465482M IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 2 | GREENVILLE URBAN AREA MPO | RX-2002A | DIVISION 2 | RR |  |  |  |  | 2024 | 362000 |  |  | 362000
PITT | SR 1704 (FOURTEENTH STREET) | NCDOT | CLNA CROSSING 465488D IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 2 | GREENVILLE URBAN AREA MPO | RX-2002B | DIVISION 2 | RR |  |  |  |  | 2024 | 345000 |  |  | 345000
PITT | US 264 ALTERNATE (GREENVILLE BOULEVARD) | NCDOT | CLNA CROSSING 465489K IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 2 | GREENVILLE URBAN AREA MPO | RX-2002C | DIVISION 2 | RR |  |  |  |  | 2024 | 345000 |  |  | 345000
PITT | SR 1530 (AIRPORT ROAD) | NCDOT | CSX CROSSING 641860P IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 2 | GREENVILLE URBAN AREA MPO | RX-2002E | DIVISION 2 | RR |  |  |  |  | 2027 | 530000 |  |  | 530000
PITT, CRAVEN, EDGECOMBE | NC 43 | NCDOT | NC 43 BETWEEN NC 118 IN CRAVEN COUNTY AND SR 1730 (HERMAN GARRIS ROAD) IN PITT COUNTY, NC 43 BETWEEN SR 1205 (ROCK SPRING ROAD) AND THE SOUTHERN LIMITS OF FALKLAND, AND NC 43 BETWEEN THE NORTHERN LIMITS OF FALKLAND IN PITT COUNTY AND NC 42 IN EDGECOMBE COUNTY. INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 2, 4 | MID-EAST RPO, GREENVILLE URBAN AREA MPO, DOWN EAST RPO, UPPER COASTAL PLAIN RPO | HS-2002S | REGION A, B | HSIP |  |  |  |  | 2024 | 760000 |  |  | 760000
PITT, GREENE | US 264 | NCDOT | US 264 BETWEEN THE WILSON COUNTY LINE AND SR 1128 (DAVENPORT FARM ROAD) / SR 1206 (BELL ARTHUR ROAD) IN PITT COUNTY. INSTALL RUMBLE STRIPES. | HIGHWAY | SAFETY | 2 | MID-EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO | HS-2002T | REGION B | HSIP |  |  |  |  | 2023 | 378000 |  |  | 378000 | UNDER CONSTRUCTION.
POLK | SR 1004 (POORS FORD ROAD) | NCDOT | REPLACE BRIDGE 740087 OVER BROAD RIVER. | HIGHWAY | BRIDGES | 14 | FOOTHILLS RPO | HB-0025 | DIVISION 14 | BGOFF | 2024 | 260000 | 2024 | 260000 | 2027 | 5200000 |  |  | 5720000
POLK | I-26 | NCDOT | US 74/NC 108 INTERCHANGE (EXIT 67). REVISE INTERCHANGE AND CONSTRUCT IMPROVEMENTS TO NC 108. | HIGHWAY | STI (PRIORITIZATION) | 14 | FOOTHILLS RPO | I-4729
POLK | I-26 | NCDOT | REVISE THE I-26/US 74/NC 108 INTERCHANGE. CONSTRUCT RAMPS FROM I-26 WESTBOUND TO US 74 EASTBOUND, AND FROM US 74 WESTBOUND TO I-26 EASTBOUND. | HIGHWAY | STI (PRIORITIZATION) | 14 | FOOTHILLS RPO | I-4729A | REGION G | [10 empty] | COMPLETE
POLK | I-26 | NCDOT | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. | HIGHWAY | STI (PRIORITIZATION) | 14 | FOOTHILLS RPO | I-4729B | REGION G | T | 2019 | 10200000 | 2019 | 2000000 | 2029 | 22598000 |  |  | 34798000 | RIGHT-OF-WAY IN PROGRESS
POLK | I-26 | NCDOT | HENDERSON COUNTY LINE TO MILE MARKER 65. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 14 | FOOTHILLS RPO | I-5926 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 13999000 |  |  | 13999000
POLK | I-26 | NCDOT | MILE MARKER 65 TO SOUTH CAROLINA STATE LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 14 | FOOTHILLS RPO | I-5927 | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2023 | 19600000 |  |  | 19600000 | UNDER CONSTRUCTION.
POLK | NC 9 | NCDOT | US 74 TO NC 108. ADD PAVED SHOULDERS. | HIGHWAY | STI (PRIORITIZATION) | 14 | FOOTHILLS RPO | R-5840 | DIVISION 14 | T | 2022 | 2200000 | 2022 | 1400000 | 2025 | 8600000 |  |  | 12200000 | RIGHT-OF-WAY IN PROGRESS.
POLK | US 74 | NCDOT | NC 108 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 14 | FOOTHILLS RPO | R-5873 | STATEWIDE MOBILITY | NHP |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 |  |  | 3400000
POLK | US 74 WB | NCDOT | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | HIGHWAY | SAFETY | 14 | FOOTHILLS RPO | W-5814B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 199000 |  |  | 199000 | COMPLETE
POLK | US 74 EB | NCDOT | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | HIGHWAY | SAFETY | 14 | FOOTHILLS RPO | W-5814C | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 179000 |  |  | 179000 | COMPLETE
POLK | POLK COUNTY TRANSPORTATION | POLK COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | FOOTHILLS RPO | TK-6155 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 736000 | 736000 | FUNDS AUTHORIZED IN PROGRESS
RANDOLPH | REGIONAL AIRPORT (HBI) ASHEBORO | REGIONAL AIRPORT (HBI) ASHEBORO | CONSTRUCT TAXILANE EXTENSION, EXTEND ACCESS ROAD, AND CONSTRUCT NEW ACCESS ROAD. | AVIATION | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | AV-5858 | DIVISION 8 | T |  |  |  |  | 2031 | 5500000 |  |  | 5500000
RANDOLPH | SR 1950 (WEST ACADEMY STREET) | RANDLEMAN | SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | EB-5744 | DIVISION 8 | L, TA5200 |  |  |  |  | 2023 | 800000 |  |  | 800000
RANDOLPH | INDUSTRIAL PARK AVENUE | ASHEBORO | RANDOLPH COMMUNITY COLLEGE ENTRANCE TO CONTINUING EDUCATION AND INDUSTRIAL CENTER IN ASHEBORO. CONSTRUCT SIDEWALK ON SOUTH SIDE. | BIKE/PED | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | EB-5862 | DIVISION 8 | L, TA5200 |  |  |  |  | 2022 | 147000 |  |  | 147000
RANDOLPH | SR 1950 (WEST NAOMI STREET) | RANDLEMAN | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | BIKE/PED | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | EB-5898 | DIVISION 8 | L, TA5200 | 2024 | 25000 |  |  | 2024 | 258000 |  |  | 283000
RANDOLPH | US 64 / NC 49 (EAST DIXIE DRIVE) | ASHEBORO | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | EB-6004 | DIVISION 8 | L, TA5200 |  |  |  |  | 2024 | 130000 |  |  | 130000
RANDOLPH | SR 2481 (LOW BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 750374 OVER SANDY CREEK. | HIGHWAY | BRIDGES | 8 | PIEDMONT TRIAD RPO | B-5360 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION - LET WITH B-5546; PRIOR YEARS COST INCLUDES B-5546 CONSTRUCTION
RANDOLPH | SR 2481 (LOW BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 750307 OVER MOUNT PLEASANT CREEK. | HIGHWAY | BRIDGES | 8 | PIEDMONT TRIAD RPO | B-5546 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION - LET WITH B-5360; CONSTRUCTION COST IS INCLUDED IN THAT PROJECT
RANDOLPH | SR 2621 (FOUSHEE ROAD) | NCDOT | REPLACE BRIDGE 750170 OVER REED CREEK. | HIGHWAY | BRIDGES | 8 | PIEDMONT TRIAD RPO | B-5739 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | SR 2407 (STARMOUNT ROAD) | NCDOT | REPLACE BRIDGE 750129 OVER BRANCH OF SANDY CREEK. | HIGHWAY | BRIDGES | 8 | PIEDMONT TRIAD RPO | B-5763 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | VARIOUS | NCDOT | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | HIGHWAY | ECONOMIC DEVELOPMENT | 8 | PIEDMONT TRIAD RPO | HE-0004 | DIVISION 8 | S, T | 2022 | 5000000 | 2022 | 2000000 | 2023 | 37000000 | 2023 | 1000000 | 45000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
RANDOLPH | I-73 / US 220 | NCDOT | SR 1009 (OLD US HIGHWAY 311) TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO | HI-0003 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2029 | 8120000 |  |  | 8120000
RANDOLPH | I-74 | NCDOT | SR 1928 (CEDAR SQUARE ROAD) TO I-73 / US 220. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | HIGH POINT URBAN AREA MPO, PIEDMONT TRIAD RPO | HI-0004 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2029 | 8140000 |  |  | 8140000
RANDOLPH | US 421 | NCDOT | CHATHAM COUNTY LINE TO THE GUILFORD COUNTY LINE. INSTALL 1 MILE AND .5 MILE MARKERS AND REVISE EXIT NUMBER SIGNS. | HIGHWAY | SAFETY | 8 | PIEDMONT TRIAD RPO | HS-2008D | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 50000 |  |  | 50000
RANDOLPH | I-73 | NCDOT | SOUTH OF SR 2269 (VISION DRIVE) TO NORTH OF SR 1712 (PINEVIEW STREET). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | PIEDMONT TRIAD RPO | I-5737 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | I-85 | NCDOT | SOUTH OF SR 1009 (MAIN STREET) TO NORTH OF SR 1912 (LUNAR DRIVE) IN ARCHDALE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | HIGH POINT URBAN AREA MPO | I-5738 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789
RANDOLPH | I-73 | NCDOT | US 311 TO 0.6 MILE NORTH OF SR 1938 (HOCKETT DAIRY ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO | I-5763 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | I-73 / I-74 / US 220 | NCDOT | MONTGOMERY COUNTY LINE TO NORTH OF SR 1462 (PARK DRIVE) IN ASHEBORO. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | PIEDMONT TRIAD RPO | I-5948 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 17001000 |  |  | 17001000
RANDOLPH | US 64 | NCDOT | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-2220DA | REGION E | T | 2028 | 6797000 | 2028 | 7554000 | 2031 | 52800000 |  |  | 67151000
RANDOLPH | US 64 | NCDOT | ASHEBORO SOUTHERN BYPASS, US 64 WEST TO US 64 EAST. FOUR-LANE FREEWAY ON NEW LOCATION WITH INTERCHANGES AT US 220, NC 49 AND ZOO ACCESS AT NC 159. | HIGHWAY | PRE-STI (HISTORIC) | 8 | PIEDMONT TRIAD RPO | R-2536 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT
RANDOLPH | NC 49 | NCDOT | SR 1174 (WAYNICK MEADOW ROAD) TO SOUTH OF SR 1193 (OLD NC 49). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5931 | NOT FUNDED | T | NOT FUNDED | 2964000 | NOT FUNDED | 5766000 | NOT FUNDED | 79999000 |  |  | 88729000
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | NCDOT | SR 2269 (VISION DRIVE) ITO SR 2123 (CAUDLE ROAD) IN ASHEBORO. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5956 | DIVISION 8 | [10 empty] | COORDINATE WITH U-6006
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | NCDOT | SR 2269 (VISION DRIVE) TO SR 2149 (HUB MORRIS ROAD). WIDEN TO MULTILANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5956A | NOT FUNDED | T | NOT FUNDED | 6200000 | NOT FUNDED | 5300000 | NOT FUNDED | 18200000 |  |  | 29700000
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | NCDOT | SR 2149 (HUB MORRIS ROAD) TO SR 2123 (CAUDLE ROAD). WIDEN TO MULTILANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5956B | NOT FUNDED | T | NOT FUNDED | 3200000 | NOT FUNDED | 6005000 | NOT FUNDED | 9399000 |  |  | 18604000
RANDOLPH | NC 42 (EAST SALISBURY STREET) | NCDOT | SR 2189 (MARTIN LUTHER KING, JR. DRIVE) / NORTH RANDOLPH AVENUE TO SR 2237 (EAST SALISBURY STREET) IN ASHEBORO. IMPROVE CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5957 | NOT FUNDED | T | NOT FUNDED | 2100000 | NOT FUNDED | 700000 | NOT FUNDED | 3400000 |  |  | 6200000
RANDOLPH | NC 159 (ZOO PARKWAY) | NCDOT | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | R-5958 | DIVISION 8 | T | 2024 | 320000 | 2024 | 265000 | 2026 | 1450000 |  |  | 2035000
RANDOLPH | SR 1547 (FINCH FARM ROAD) | NCDOT | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | HIGH POINT URBAN AREA MPO | U-5308 | DIVISION 8 | T | 2019 | 2459000 | 2019 | 3500000 | 2027 | 26800000 | 2020 | 2703000 | 35462000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
RANDOLPH | SR 1712 (PINEVIEW STREET) | NCDOT | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | U-5711 | DIVISION 8 | T |  |  |  |  | 2024 | 7900000 |  |  | 7900000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | NC 42 | NCDOT | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | U-5743 | REGION E | T | 2022 | 2006000 | 2022 | 900000 | 2025 | 8099000 |  |  | 11005000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | US 220 BUSINESS (FAYETTEVILLE STREET) | NCDOT | INTERSECTION OF US 220 BUSINESS (FAYETTEVILLE STREET) AND PRESNELL STREET IN ASHEBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | U-5758 | REGION E | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | I-85 | NCDOT | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 8 | HIGH POINT URBAN AREA MPO | U-5770 | REGION E | T | 2022 | 6358000 | 2022 | 2200000 |  |  |  |  | 8558000 | “S” FUNDING REFLECTS CONTRACT RESURFACING FUNDS.
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | NCDOT | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | HIGHWAY | STI (PRIORITIZATION) | 8 | HIGH POINT URBAN AREA MPO | U-5770A | REGION E | S, T |  |  |  |  | 2023 | 1693000 |  |  | 1693000
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | NCDOT | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCI IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 8 | HIGH POINT URBAN AREA MPO | U-5770B | REGION E | T |  |  |  |  | 2026 | 17500000 |  |  | 17500000
RANDOLPH | US 64 | NCDOT | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | U-5813 | REGION E | NHP | 2021 | 15934000 | 2021 | 399000 | 2024 | 46299000 |  |  | 62632000 | RIGHT OF WAY IN PROGRESS.
RANDOLPH | US 220 BUSINESS | NCDOT | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | U-6006 | DIVISION 8 | T | 2024 | 1000000 | 2024 | 2748000 | 2027 | 8500000 |  |  | 12248000 | COORDINATE WITH R-5956
RANDOLPH | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | NCDOT | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF SR 1453. | HIGHWAY | STI (PRIORITIZATION) | 8 | PIEDMONT TRIAD RPO | U-6007 | DIVISION 8 | T |  |  | 2022 | 300000 | 2023 | 1400000 |  |  | 1700000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | NC 62 | NCDOT | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 8 | HIGH POINT URBAN AREA MPO | U-6191 | DIVISION 8 | T | 2028 | 5701000 | 2028 | 4700000 | 2030 | 12400000 |  |  | 22801000
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | NCDOT | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) FROM BEASLEY STREET TO BALFOUR AVENUE IN ASHEBORO. | HIGHWAY | SAFETY | 8 | PIEDMONT TRIAD RPO | W-5708L | REGION E | HSIP |  |  |  |  | 2026 | 320000 |  |  | 320000
RANDOLPH | RANDOLPH- MONTGOMERY RESTORE | RANDOLPH- MONTGOMERY RESTORE | PURCHASE ADDITIONAL 20-FOOT LIGHT TRANSIT VEHICLES. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 8 | PIEDMONT TRIAD RPO | TA-6670 | REGION E | [10 empty] | IN ACQUISITION
RANDOLPH | SR 2502 (JULIAN AIRPORT ROAD) | NCDOT | NORFOLK SOUTHERN CROSSING 720943W IN LIBERTY. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 8 | PIEDMONT TRIAD RPO | RX-2008F | DIVISION 8 | RR |  |  |  |  | 2026 | 411000 |  |  | 411000
RANDOLPH, DAVIDSON | I-85 | NCDOT | NC 109 IN THOMASVILLE TO SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8, 9 | HIGH POINT URBAN AREA MPO | HI-0002 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 15392000 |  |  | 15392000
RANDOLPH, DAVIDSON | US 64 | NCDOT | NC 109 TO SR 1409 (LAKE PARK ROAD) | HIGHWAY | STI (PRIORITIZATION) | 8, 9 | HIGH POINT URBAN AREA MPO | R-2220C | NOT FUNDED | T | NOT FUNDED | 13746000 | NOT FUNDED | 1650000 | NOT FUNDED | 56452000 |  |  | 71848000
RANDOLPH, DAVIDSON, GUILFORD | HIGH POINT TRANSIT SYSTEM / HI-TRAN | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 7, 8, 9 | HIGH POINT URBAN AREA MPO | TO-4790 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 11516000 | 11516000 | FUNDS AUTHORIZED IN PROGRESS
RANDOLPH, GUILFORD | SR 1577 / SR 1004 (ARCHDALE ROAD) | NCDOT | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 7, 8 | HIGH POINT URBAN AREA MPO | U-3400 | DIVISION 7, 8 | T | 2024 | 7901000 | 2024 | 12126000 | 2029 | 18600000 |  |  | 38627000
RANDOLPH, GUILFORD | SR 1595 / SR 4053 (SURRETT DRIVE) | NCDOT | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 7, 8 | HIGH POINT URBAN AREA MPO | U-5864 | DIVISION 7, 8 | BGANY | 2026 | 5063000 | 2026 | 5100000 | 2029 | 23701000 |  |  | 33864000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | RICHMOND COUNTY AIRPORT (RCZ) | CLEAR OBSTRUCTIONS IN RUNWAY 14 APPROACH. | AVIATION | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | AV-5761 | DIVISION 8 | T |  |  |  |  | 2026 | 570000 |  |  | 570000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | RICHMOND COUNTY AIRPORT (RCZ) | EXTEND RUNWAY 14-32 TO 5500 FEET. | AVIATION | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | AV-5763 | DIVISION 8 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5065000 |  |  | 5065000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | RICHMOND COUNTY AIRPORT (RCZ) | CONSTRUCT EAST RAMP EXPANSION. | AVIATION | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | AV-5853 | DIVISION 8 | T |  |  |  |  | 2024 | 2000000 |  |  | 2000000
RICHMOND | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | HAMLET | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | EB-6018 | DIVISION 8 | L, TA5200 | 2024 | 72000 | 2024 | 55000 | 2025 | 720000 | 2023 | 28000 | 875000
RICHMOND | I-73 / I-74 | NCDOT | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | LUMBER RIVER RPO | I-5946
RICHMOND | I-73/I-74 | NCDOT | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO SR 1455 (FIRE TOWER ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | LUMBER RIVER RPO | I-5946A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - LET WITH I-5947B
RICHMOND | I-73/I-74 | NCDOT | SR 1455 (FIRE TOWER ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 8 | LUMBER RIVER RPO | I-5946B | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2022 | 6812000 |  |  | 6812000 | UNDER CONSTRUCTION
RICHMOND | US 74 / FUTURE I-74 | NCDOT | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | I-5979 | DIVISION 8 | NHP | 2022 | 500000 | 2022 | 210000 | 2024 | 6700000 |  |  | 7410000 | RIGHT-OF-WAY IN PROGRESS
RICHMOND | US 1 | NCDOT | SOUTH CAROLINA STATE LINE TO SR 1001 (MARSTON ROAD). WIDEN TO FOUR LANES WITH VARIABLE WIDTH MEDIAN WITH BYPASS OF ROCKINGHAM ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-2501
RICHMOND | US 1 | NCDOT | SOUTH CAROLINA STATE LINE TO SR 1104 (OSBORNE ROAD) | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-2501A | NOT FUNDED | T | NOT FUNDED | 4500000 |  |  | NOT FUNDED | 25700000 |  |  | 30200000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | NCDOT | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-2501BA | NOT FUNDED | T | NOT FUNDED | 5519000 | NOT FUNDED | 908000 | NOT FUNDED | 40500000 |  |  | 46927000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | NCDOT | US 74 BYPASS TO US 74 BUSINESS | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-2501BB | NOT FUNDED | T | NOT FUNDED | 13300000 | NOT FUNDED | 2523000 | NOT FUNDED | 67700000 |  |  | 83523000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | NCDOT | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-2501BC | NOT FUNDED | T | NOT FUNDED | 24248000 | NOT FUNDED | 6950000 | NOT FUNDED | 101101000 |  |  | 132299000 | COORDINATE WITH R-5928
RICHMOND | US 1 | NCDOT | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-2501C | DIVISION 8 | T |  |  |  |  | 2019 | 12975000 | 2021 | 217000 | 13192000 | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 220 / FUTURE I-73 / FUTURE I-74 | NCDOT | ROCKINGHAM BYPASS. FOUR LANES DIVIDED ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-3421 | [11 empty] | BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | NCDOT | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-3421A | REGION E | T | 2020 | 5495000 |  |  | 2020 | 106857000 |  |  | 112352000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | NCDOT | ROCKINGHAM BYPASS, SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) TO SOUTHWEST OF SR 1304 (HARRINGTON ROAD) | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-3421B | REGION E | T |  |  |  |  | 2020 | 83679000 |  |  | 83679000 | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | NCDOT | ROCKINGHAM BYPASS, 0.2 MILES SOUTHWEST OF SR 1304 (HARRINGTON ROAD) TO I-73 / I-74 INTERCHANGE SOUTH OF ELLERBE | HIGHWAY | TRANSITION | 8 | LUMBER RIVER RPO | R-3421C | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
RICHMOND | US 220/I-73/I-74 | NCDOT | SR 1336 (BILLY COVINGTON ROAD) | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-3421CA | STATEWIDE MOBILITY | T | 2023 | 75000 | 2023 | 25000 | 2024 | 532000 |  |  | 632000 | RIGHT-OF-WAY IN PROGRESS
RICHMOND | US 1 | NCDOT | SR 1640 (WIREGRASS ROAD) TO LOCH LAURIN LANE. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | R-5928 | DIVISION 8 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28901000 |  |  | 36801000 | COORDINATE WITH R-2501BC
RICHMOND | VARIOUS | NCDOT | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | U-5706 | DIVISION 8 | T | 2025 | 8600000 | 2025 | 1800000 | 2027 | 31070000 |  |  | 41470000 | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
RICHMOND | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | NCDOT | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | U-6027 | DIVISION 8 | T | 2024 | 1700000 | 2024 | 2000000 | 2027 | 4700000 |  |  | 8400000
RICHMOND | SR 1925 (BILTMORE DRIVE) | NCDOT | CSX CROSSING 630856U IN ROCKINGHAM. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 8 | LUMBER RIVER RPO | RX-2008C | DIVISION 8 | RR |  |  |  |  | 2024 | 446000 |  |  | 446000
ROBESON | LUMBERTON REGIONAL AIRPORT (LBT) | LUMBERTON REGIONAL AIRPORT (LBT) | PARTIAL PARALLEL TAXIWAY RUNWAY 5. | AVIATION | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | AV-5747 | DIVISION 6 | T |  |  |  |  | 2022 | 2600000 |  |  | 2600000 | UNDER CONSTRUCTION.
ROBESON | LUMBERTON REGIONAL AIRPORT (LBT) | LUMBERTON REGIONAL AIRPORT (LBT) | RUNWAY 13-31. CONSTRUCT TAXIWAYS. | AVIATION | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | AV-5901 | DIVISION 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4500000 |  |  | 4500000
ROBESON | NC 711 (THIRD STREET) | PEMBROKE | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | EB-6013 | DIVISION 6 | L, TA5200 | 2028 | 168000 |  |  | 2029 | 848000 | 2027 | 170000 | 1186000
ROBESON | SR 1924 (CURRIE ROAD) | NCDOT | REPLACE BRIDGE 770059 OVER BIG MARSH SWAMP. | HIGHWAY | BRIDGES | 6 | LUMBER RIVER RPO | B-5693 | DIVISION 6 | [10 empty] | COMPLETED.
ROBESON | NC 41/NC 72/SR 1600 | NCDOT | REPLACE BRIDGE 770125 AND 770175 OVER LUMBER RIVER. | HIGHWAY | BRIDGES | 6 | LUMBER RIVER RPO | B-5985 | REGION C | NHPB | 2022 | 395000 | 2022 | 485000 |  |  |  |  | 880000 | RIGHT-OF-WAY IN PROGRESS.
ROBESON | NC 41/NC 72/SR 1600 | NCDOT | REPLACE BRIDGE 770125 OVER LUMBER RIVER. | HIGHWAY | BRIDGES | 6 | LUMBER RIVER RPO | B-5985A | REGION C | BFP |  |  |  |  | 2023 | 8500000 |  |  | 8500000 | UNDER CONSTRUCTION.
ROBESON | NC 41/NC 72/SR 1600 | NCDOT | REPLACE BRIDGE 770175 OVER LUMBER RIVER. | HIGHWAY | BRIDGES | 6 | LUMBER RIVER RPO | B-5985B | REGION C | BFP |  |  |  |  | 2024 | 8175000 |  |  | 8175000
ROBESON | SR 2269 (BLOOMINGDALE ROAD) | NCDOT | REPLACE BRIDGE 770108 OVER INDIAN SWAMP. | HIGHWAY | BRIDGES | 6 | LUMBER RIVER RPO | B-6007 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION.
ROBESON | CHURCH ROAD) SR 1529 (MOUNT OLIVE | NCDOT | REPLACE BRIDGE 770299 AND 770300 OVER SADDLE TREE SWAMP. | HIGHWAY | BRIDGES | 6 | LUMBER RIVER RPO | HB-0007 | DIVISION 6 | BGOFF | 2023 | 170000 | 2023 | 170000 | 2024 | 1700000 |  |  | 2040000 | RIGHT-OF-WAY IN PROGRESS.
ROBESON | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM EAST OF NC 41 TO THE COLUMBUS COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO | HI-0016 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2024 | 10000000 |  |  | 10000000
ROBESON | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM THE SCOTLAND COUNTY LINE TO I-74/US 74 BUSINESS. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO | HI-0017 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2024 | 6800000 |  |  | 6800000
ROBESON | PEMBROKE | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | HIGHWAY | LOCALLY SELECTED | 6 | LUMBER RIVER RPO | HL-0009 | EXEMPT | DP, L, S | 2022 | 100000 | 2022 | 930000 | 2023 | 5310000 | 2021 | 350000 | 6690000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. S FUNDS REPRESENT STATE HIGHWAY FUNDS.
ROBESON | SR 1935 (HOWELL ROAD) | NCDOT | CONVERT INTERSECTION OF SR 1924 (BARKER TEN MILE ROAD) AND SR 1935 (HOWELL ROAD) TO AN ALL WAY STOP. REALIGN NORTH LEG OF SR 1005 (TOLARSVILLE ROAD) AT SR 1935 (HOWELL ROAD) AND REMOVE SOUTH LEG. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | HS-2006D | DIVISION 6 | HSIP | 2022 | 15000 |  |  | 2023 | 428000 |  |  | 443000 | UNDER CONSTRUCTION.
ROBESON | NC 710 | NCDOT | NC 710 AT SR 1340 (PROSPECT ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | HS-2006I | REGION C | HSIP | 2024 | 80000 |  |  | 2025 | 2262000 |  |  | 2342000
ROBESON | US 501/NC 130 | NCDOT | US 501/NC 130 NEAR SR 1134 (KITCHEN ROAD). CURVE IMPROVEMENTS. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | HS-2006J | REGION C | HSIP |  |  |  |  | 2025 | 410000 |  |  | 410000
ROBESON | I-95 | NCDOT | I-95 FROM MILEMARKER 2.0 TO MILEMARKER 12.45. INSTALL CABLE MEDIAN BARRIER. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | HS-2006R | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2024 | 815000 |  |  | 815000
ROBESON | US 501 | NCDOT | FROM NC 130 TO THE SCOTLAND COUNTY LINE. INSTALL RUMBLE STRIPES. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | HS-2006S | REGION C | HSIP |  |  |  |  | 2023 | 222000 |  |  | 222000 | UNDER CONSTRUCTION.
ROBESON | NC 72 | NCDOT | FROM US 74 TO NC 41 / NC 211. INSTALL RUMBLE STRIPES AND RAISED PAVEMENT MARKERS. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | HS-2006T | REGION C | HSIP |  |  |  |  | 2023 | 427000 |  |  | 427000 | UNDER CONSTRUCTION.
ROBESON | NC 72 | NCDOT | FROM NC 711 TO NC 710. INSTALL RUMBLE STRIPES AND RAISED PAVEMENT MARKERS. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | HS-2006U | REGION C | HSIP |  |  |  |  | 2023 | 505000 |  |  | 505000 | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | NORTH OF US 301 (MILE MARKER 22) TO CUMBERLAND COUNTY LINE (MILE MARKER 40). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5850 | STATEWIDE MOBILITY
ROBESON | I-95 | NCDOT | BRIDGE REHABILITATION, MEDIAN DRAINAGE, AND CONTROL OF ACCESS FENCE. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5850A | STATEWIDE MOBILITY | [10 empty] | COMPLETED.
ROBESON | I-95 | NCDOT | PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5850B | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | SR 1536 (CARTHAGE ROAD/WEST CARTHAGE ROAD) (EXIT 19). IMPROVE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | I-5879 | DIVISION 6 | NHP |  |  |  |  | 2021 | 15028000 |  |  | 15028000 | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C.
ROBESON | I-74 | NCDOT | NC 710 TO NC 41. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO | I-5938 | STATEWIDE MOBILITY
ROBESON | I-74 | NCDOT | BRIDGE REHABILITATION | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO | I-5938A | STATEWIDE MOBILITY | [10 empty] | COMPLETED.
ROBESON | I-74 | NCDOT | PAVEMENT REHABILITATION | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO | I-5938B | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | SOUTH CAROLINA STATE LINE (MILE MARKER 0.0) TO I-74 (MILE MARKER 13). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO | I-5939 | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2022 | 20098000 |  |  | 20098000 | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | SOUTH OF US 301 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5987 | REGION C | [10 empty] | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
ROBESON | I-95 | NCDOT | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | I-5987A | REGION C | T | 2021 | 3395000 | 2022 | 3075000 | 2023 | 307329000 |  |  | 313799000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE).
ROBESON | I-95 | NCDOT | CONSTRUCT WEIGH IN MOTION STATION. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | I-5987AA | REGION C | O |  |  |  |  | 2025 | 2400000 |  |  | 2400000 | O FUNDS REPRESENT STATE PRIMARY MAINTENANCE FUNDS FOR WEIGH STATIONS.
ROBESON | I-95 | NCDOT | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5987B | REGION C | T | 2021 | 3581000 | 2021 | 2300000 | 2023 | 348619000 |  |  | 354500000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE).
ROBESON | I-95 | NCDOT | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5987C | REGION C | DP, T | [6 empty] | 2022 | 315000 | 315000
ROBESON | US 74 | NCDOT | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | I-6011A | DIVISION 6 | BGLT5 | 2025 | 55000 | 2025 | 352000 | 2027 | 7400000 |  |  | 7807000
ROBESON | I-95 | NCDOT | MILE MARKER 13 TO MILE MARKER 22. WIDEN TO EIGHT LANES AND PAVEMENT REHABILITATION. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | I-6064 | [11 empty] | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. PROJECT LET WITH I-5879.
ROBESON | I-95 | NCDOT | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | I-6064A | REGION C | DP, T | 2021 | 3087000 | 2021 | 3250000 | 2021 | 218371000 |  |  | 224708000 | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | I-6064B | STATEWIDE MOBILITY | T | 2022 | 7429000 | 2022 | 2025000 | 2022 | 85946000 |  |  | 95400000 | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | MILE MARKER 13 TO MILE MARKER 22. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 6 | LUMBER RIVER RPO | I-6064C | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2021 | 131492000 |  |  | 131492000 | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | HIGHWAY | OTHER | 6 | LUMBER RIVER RPO | I-6064D | STATEWIDE MOBILITY | DP, T | [6 empty] | 2022 | 315000 | 315000
ROBESON | NC 711 | NCDOT | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | R-4428 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9263000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1220000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11601000 |  |  | 22084000
ROBESON | US 74 | NCDOT | NC 72/NC 130. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | R-5751 | REGION C | T | 2021 | 325000 |  |  | 2023 | 28285000 |  |  | 28610000 | UNDER CONSTRUCTION.
ROBESON | NC 41 (EAST ELIZABETHTOWN ROAD) | NCDOT | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | R-5888 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 |  |  | 7000000
ROBESON | NC 20 | NCDOT | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | R-5904 | NOT FUNDED | T | NOT FUNDED | 5400000 | NOT FUNDED | 3400000 | NOT FUNDED | 18800000 |  |  | 27600000
ROBESON | NC 41 (MARTIN LUTHER KING DRIVE) | NCDOT | US 74 TO MARION ROAD. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | R-5951 | NOT FUNDED | T | NOT FUNDED | 10500000 | NOT FUNDED | 3200000 | NOT FUNDED | 18600000 |  |  | 32300000
ROBESON | SR 1945 (MEADOW ROAD) | NCDOT | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | R-5954 | NOT FUNDED | T | NOT FUNDED | 100000 | NOT FUNDED | 300000 | NOT FUNDED | 2000000 |  |  | 2400000
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | NCDOT | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | R-5955 | NOT FUNDED | T | NOT FUNDED | 16000000 | NOT FUNDED | 6900000 | NOT FUNDED | 16300000 |  |  | 39200000
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | NCDOT | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | U-5797 | DIVISION 6 | T | 2023 | 9200000 | 2023 | 2208000 | 2024 | 29100000 |  |  | 40508000 | RIGHT-OF-WAY IN PROGRESS.
ROBESON | SR 1340 (PROSPECT STREET/ NORTH ODUM ROAD) | NCDOT | SR 1566 (CORINTH ROAD) TO NC 711 (THIRD STREET). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | PRE-STI (HISTORIC) | 6 | LUMBER RIVER RPO | U-5925 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION.
ROBESON | NC 710 | NCDOT | AT SR 1339 (DEEP BRANCH ROAD) IN PEMBROKE. CONVERT SIGNALIZED INTERSECTION TO A ROUNDABOUT. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | W-5706N | REGION C | HSIP |  |  |  |  | 2024 | 2850000 |  |  | 2850000 | RIGHT-OF-WAY IN PROGRESS.
ROBESON | NC 41 (MARTIN LUTHER KING JR DRIVE) | NCDOT | NC 41 (MARTIN LUTHER KING JR DRIVE) AT NC 72 (WEST SECOND STREET) AND SR 1599 (MARTIN LUTHER KING JR DRIVE). CONSTRUCT SIGNALIZED PEDESTRIAN CROSSINGS. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO | W-5806E | REGION C | HSIP |  |  |  |  | 2022 | 315000 |  |  | 315000 | UNDER CONSTRUCTION.
ROBESON | ROBESON COUNTY | ROBESON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 6 | LUMBER RIVER RPO | TK-6158 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 800000 | 800000 | FUNDS AUTHORIZED IN PROGRESS
ROBESON | SR 1154 (UNION SCHOOL ROAD) | NCDOT | CSX CROSSING 629606K NEAR PEMBROKE. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | LUMBER RIVER RPO | RX-2006B | DIVISION 6 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
ROBESON | NC 41 (MARTIN LUTHER KING JR. DRIVE) | NCDOT | CSX CROSSING 631029P IN LUMBERTON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | LUMBER RIVER RPO | RX-2006E | DIVISION 6 | RR |  |  |  |  | 2026 | 446000 |  |  | 446000
ROBESON | SR 1748 (CRENSHAW ROAD) | NCDOT | CSX CROSSING 629581S IN REX. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 6 | LUMBER RIVER RPO | RX-2006G | DIVISION 6 | RR |  |  |  |  | 2027 | 417000 |  |  | 417000
ROBESON, CUMBERLAND | I-295 | NCDOT | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 6 | LUMBER RIVER RPO | U-2519AA | REGION C | NHP, S(M) |  |  |  |  | 2018 | 260442000 |  |  | 260442000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032.
ROBESON, CUMBERLAND, JOHNSTON, NASH, HALIFAX, WILSON, HARNETT, NORTHAMPTON | I-95 | NCDOT | INSTALL BROADBAND FIBER ALONG I-95 FROM SOUTH CAROLINA LINE TO VIRGINIA STATE LINE. | HIGHWAY | OTHER | 1, 4, 6 | UPPER COASTAL PLAIN RPO, LUMBER RIVER RPO, PEANUT BELT RPO, FAYETTEVILLE AREA MPO, MID-CAROLINA RPO, ROCKY MOUNT URBAN AREA MPO | I-5986C | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2021 | 27667000 |  |  | 27667000 | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
ROBESON, HARNETT | VARIOUS | NCDOT | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 6 | LUMBER RIVER RPO, MID-CAROLINA RPO | W-5206REG | REGION C
ROCKINGHAM | (SIF) ROCKINGHAM COUNTY AIRPORT | ROCKINGHAM COUNTY AIRPORT (SIF) | EXTEND RUNWAY TO 5500 FT. | AVIATION | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | AV-5852 | DIVISION 7 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2600000 |  |  | 2600000
ROCKINGHAM | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | CONSTRUCT T-HANGAR TAXILANES FOR ADDITION OF T-HANGARS. | AVIATION | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | AV-5898 | DIVISION 7 | T |  |  |  |  | 2025 | 770000 |  |  | 770000
ROCKINGHAM | SR 1747 (EAST STADIUM DRIVE) | NCDOT | SR 1962 (NORTH PIERCE STREET) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | EB-5888 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 443000 |  |  | 443000
ROCKINGHAM | US 220 BUSINESS | MAYODAN | EAST JACKSON STREET IN MAYODAN TO MAYO RIVER STATE PARK. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | EB-5891 | DIVISION 7 | L, TALT5 |  |  |  |  | 2024 | 652000 |  |  | 652000
ROCKINGHAM | SR 1925 (WORSHAM MILL ROAD) | NCDOT | REPLACE BRIDGE 780097 OVER WOLF ISLAND CREEK. | HIGHWAY | TRANSITION | 7 | PIEDMONT TRIAD RPO | B-4803 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | SR 2600 (MIZPAH CHURCH ROAD) | NCDOT | REPLACE BRIDGE 780085 OVER SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 7 | PIEDMONT TRIAD RPO | B-4964 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | US 220 (NORTHBOUND) | NCDOT | REPLACE BRIDGE 780131 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 7 | PIEDMONT TRIAD RPO | B-5352 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | SR 2351 (WITTY ROAD) | NCDOT | REPLACE BRIDGE 780017 OVER HAW RIVER. | HIGHWAY | BRIDGES | 7 | GREENSBORO URBAN AREA MPO, PIEDMONT TRIAD RPO | B-5715 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | SR 1138 (LINDSEY BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 780140 OVER DAN RIVER | HIGHWAY | BRIDGES | 7 | PIEDMONT TRIAD RPO | B-5716 | DIVISION 7 | BGOFF | 2023 | 610000 |  |  | 2024 | 6101000 |  |  | 6711000 | RIGHT-OF-WAY IN PROGRESS
ROCKINGHAM | SR 2177 (DAN VALLEY ROAD) | NCDOT | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | HIGHWAY | BRIDGES | 7 | PIEDMONT TRIAD RPO | B-5721 | DIVISION 7 | BGLT5 | 2022 | 188000 | 2022 | 336000 | 2023 | 3800000 |  |  | 4324000 | UNDER CONSTRUCTION
ROCKINGHAM | SR 1169 (ISLAND DRIVE) | NCDOT | REPLACE BRIDGE 780277 OVER BEAVER CREEK | HIGHWAY | BRIDGES | 7 | PIEDMONT TRIAD RPO | B-5722 | DIVISION 7 | BGOFF | 2023 | 200000 |  |  | 2024 | 2000000 |  |  | 2200000
ROCKINGHAM | NC 14 / NC 87 | NCDOT | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | BRIDGES | 7 | PIEDMONT TRIAD RPO | B-6038 | REGION D | BFP, NHPB | 2027 | 390000 | 2027 | 163000 | 2028 | 3900000 |  |  | 4453000
ROCKINGHAM | SR 1535 (PRICE ROAD) | NCDOT | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | HIGHWAY | BRIDGES | 7 | PIEDMONT TRIAD RPO | HB-0035 | DIVISION 7 | BGOFF | 2025 | 180000 | 2025 | 180000 | 2026 | 3600000 |  |  | 3960000
ROCKINGHAM | FUTURE I-73 / US 220 | NCDOT | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | I-5898 | REGION D | T | 2022 | 1500000 | 2022 | 1600000 | 2025 | 14000000 |  |  | 17100000 | RIGHT-OF-WAY IN PROGRESS
ROCKINGHAM | US 220 / FUTURE I-73 | NCDOT | NC 68 INTERSECTION - CONVERT AT-GRADE INTERSECTION TO INTERCHANGE | HIGHWAY | PRE-STI (HISTORIC) | 7 | PIEDMONT TRIAD RPO | R-2413CA | PRE-STI (TRANSITION) | [10 empty] | IN PROGRESS
ROCKINGHAM | NC 87 | NCDOT | SR 1998 (WENTWORTH STREET) / SR 1001 (SANDY CROSS ROAD). INTERSECTION REALIGNMENT. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | R-5704 | REGION D | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | NC 65 / NC 87 | NCDOT | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO US 158 / US 29 BUSINESS (FREEWAY DRIVE) IN REIDSVILLE. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | R-5766
ROCKINGHAM | NC 65 / NC 87 | NCDOT | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | R-5766A | DIVISION 7 | T | 2024 | 8700000 | 2024 | 2200000 | 2026 | 13101000 |  |  | 24001000
ROCKINGHAM | NC 65 / NC 87 | NCDOT | SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) TO SR 2413 (VANCE STREET EXTENSION) | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | R-5766B | DIVISION 7 | T | 2024 | 4000000 | 2024 | 900000 | 2026 | 8800000 |  |  | 13700000
ROCKINGHAM | NC 65 / NC 87 | NCDOT | SR 2413 (VANCE STREET EXTENSION) TO US 158 / US 29 BUSINESS IN REIDSVILLE | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | R-5766C | DIVISION 7 | T | 2024 | 5900000 | 2024 | 1700000 | 2026 | 14900000 |  |  | 22500000
ROCKINGHAM | US 29 BUSINESS/US 158 (FREEWAY DRIVE) | NCDOT | SOUTH SCALES STREET TO NC 14 IN REIDSVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | PRE-STI (HISTORIC) | 7 | PIEDMONT TRIAD RPO | U-3326
ROCKINGHAM | US 29 BUSINESS (FREEWAY DRIVE) | NCDOT | SOUTH SCALES STREET TO SR 2686 (RICHARDSON DRIVE) | HIGHWAY | PRE-STI (HISTORIC) | 7 | PIEDMONT TRIAD RPO | U-3326A | [11 empty] | COMPLETE
ROCKINGHAM | US 29 BUSINESS / US 158 (FREEWAY DRIVE) | NCDOT | SR 2686 (RICHARDSON DRIVE) TO NC 14 | HIGHWAY | PRE-STI (HISTORIC) | 7 | PIEDMONT TRIAD RPO | U-3326B | [11 empty] | UNDER CONSTRUCTION
ROCKINGHAM | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | NCDOT | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO | U-5893 | REGION D | BG5T50 | 2024 | 1643000 | 2024 | 717000 | 2026 | 12199000 |  |  | 14559000
ROCKINGHAM | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 7 | PIEDMONT TRIAD RPO | TK-6159 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 708000 | 708000 | FUNDS AUTHORIZED IN PROGRESS
ROCKINGHAM, GUILFORD | US 220 / FUTURE I-73 | NCDOT | HAW RIVER TO NC 68-US 220 INTERSECTION | HIGHWAY | PRE-STI (HISTORIC) | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-2413C | [11 empty] | UNDER CONSTRUCTION
ROCKINGHAM, GUILFORD | NC 65 / NC 68 | NCDOT | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5823 | DIVISION 7 | BGLT5 | 2024 | 10500000 | 2024 | 424000 | 2026 | 28200000 |  |  | 39124000
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | NCDOT | NORTH OF I-785 IN GREENSBORO TO US 158 / NC 14 IN REIDSVILLE. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5889 | REGION D
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | NCDOT | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE TO INTERSTATE STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5889B | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9364000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5430000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 116450000 |  |  | 131244000
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | ADMINISTRATION OF 5310 PROGRAM | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CABARRUS-ROWAN MPO | TA-5128C | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 200000 | 200000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | 5339 BUS AND BUS FACILITIES - EXPANSION VEHICLES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CABARRUS-ROWAN MPO | TA-5130B | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT/ CONCORD | RIDER TRANSIT / CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CABARRUS-ROWAN MPO | TA-5173 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 8500000 | 8500000
CABARRUS | CABARRUS COUNTY | CABARRUS COUNTY | CAPITAL FOR CABARRUS COUNTY THROUGH THE CITY OF CONCORD | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 10 | CABARRUS-ROWAN MPO | TG-6789 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2256000 | 2256000
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 10 | CABARRUS-ROWAN MPO | TO-5138 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 10852000 | 10852000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CABARRUS-ROWAN MPO | TP-5118 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 304000 | 304000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CABARRUS-ROWAN MPO | TS-5116 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 100000 | 100000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS, MECKLENBURG | NC 73 (DAVIDSON HIGHWAY) | NCDOT | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO US 29. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | R-5706 | [11 empty] | COORDINATE WITH R-2632AB.
CABARRUS, MECKLENBURG | PIEDMONT CORRIDOR | NCDOT | PIEDMONT CORRIDOR, RESTORE DOUBLE TRACK, HAYDOCK TO JUNKER. | RAIL | PRE-STI (HISTORIC) | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | P-5208 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
CABARRUS, ROWAN | I-85 | NCDOT | NC 73 IN CABARRUS COUNTY (EXIT 55) TO US 29 / US 601 CONNECTOR (EXIT 68) IN ROWAN COUNTY. WIDEN TO EIGHT LANES. | HIGHWAY | STI (PRIORITIZATION) | 9, 10 | CABARRUS-ROWAN MPO | I-3802 | [11 empty] | SEGMENT B INCLUDES B-5365 AND I-3610
CABARRUS, ROWAN | I-85 | NCDOT | NC 73 IN CABARRUS COUNTY (EXIT 55) TO SR 2180 (LANE STREET) IN CABARRUS COUNTY. | HIGHWAY | TRANSITION | 9, 10 | CABARRUS-ROWAN MPO | I-3802A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CABARRUS, ROWAN | CONCORD KANNAPOLIS AREA TRANSIT | CONCORD KANNAPOLIS AREA TRANSIT | TO SUPPORT THE PURCHASE OF ROUTINE CAPITAL: BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, VEHICLES ETC USING SECTION 5339 FUNDS AT A FEDERAL SHARE OF $200,000 AND LOCAL SHARE OF $50,000. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9, 10 | CABARRUS-ROWAN MPO | TA-5130A | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 1000000 | 1000000
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9, 10 | CABARRUS-ROWAN MPO | TG-5103A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2500000 | 2500000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - ADA SERVICES | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9, 10 | CABARRUS-ROWAN MPO | TG-5103B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1563000 | 1563000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9, 10 | CABARRUS-ROWAN MPO | TG-5103C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 6750000 | 6750000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON, ROWAN | I-85 | NCDOT | IMPLEMENTATION OF INTELLIGENT TRANSPORTATION SYSTEM (ITS) | HIGHWAY | TRANSITION | 9 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO | I-2304AF | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. | RAIL | OTHER | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918 | EXEMPT | CMAQ, S | [6 empty] | 2021 | 17586000 | 17586000 | "S" FUNDING REFLECTS STATE RAIL FUNDS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | EQUIPMENT REBUILD - 2 F59PHI LOCOMOTIVES | RAIL | OTHER | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918A | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | PURCHASE 2 USED LOCOMOTIVES | RAIL | OTHER | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918B | [11 empty] | COMPLETE
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | EQUIPMENT REHABILITATION - 3 LOCOMOTIVES | RAIL | OTHER | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918C | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | EQUIPMENT REHABILITATION - 3 PASSENGER CARS | RAIL | OTHER | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918D | [11 empty] | COMPLETE
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | PASSENGER TRAIN SECURITY SYSTEM, CCTV DATA NETWORK AND GENERATORS | RAIL | OTHER | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918E | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | PURCHASE 4 USED PASSENGER CARS AND REHABILITATE 7 PASSENGER CARS | RAIL | OTHER | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918G | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | EQUIP 9 STATIONS AND PLATFORMS WITH ADA/FRA PIDS | RAIL | OTHER | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918I | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | PURCHASE AND REFURBISH RAIL CARS FOR PIEDMONT SERVICE EXPANSION. | RAIL | STI (PRIORITIZATION) | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-5719 | [11 empty] | "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP FOR STATE OF GOOD REPAIR GRANT
ROWAN | GRANTS CREEK GREENWAY | SALISBURY | KELSEY SCOTT PARK TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT MULTI-USE PATH. | BIKE/PED | OTHER | 9 | CABARRUS-ROWAN MPO | EB-5619 | DIVISION 9 | [10 empty] | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SALISBURY
ROWAN | GRANTS CREEK GREENWAY | SALISBURY | VICINITY OF FORESTDALE DRIVE TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT LOW-WATER BRIDGE GREENWAY CONNECTION. | BIKE/PED | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | EB-5619A | DIVISION 9 | [10 empty] | COMPLETE
ROWAN | SR 1986 (MT. VERNON ROAD) | NCDOT | REPLACE BRIDGE 790050 OVER NAILS BRANCH. | HIGHWAY | BRIDGES | 9 | CABARRUS-ROWAN MPO | B-5160 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | US 29; NC 152 | NCDOT | REPLACE BRIDGE 790021 AND BRIDGE 790034 OVER NORFOLK SOUTHERN RAILROAD AND US 29 IN CHINA GROVE. | HIGHWAY | BRIDGES | 9 | CABARRUS-ROWAN MPO | B-5365 | [11 empty] | INCLUDED IN I-3802
ROWAN | SR 2539 (PEACH ORCHARD ROAD) | NCDOT | REPLACE BRIDGE 790200 OVER TOWN CREEK. | HIGHWAY | BRIDGES | 9 | CABARRUS-ROWAN MPO | B-5769 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | NC 801 | NCDOT | REPLACE BRIDGE 790061 OVER FOURTH CREEK. | HIGHWAY | BRIDGES | 9 | CABARRUS-ROWAN MPO | B-5778 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
ROWAN | VARIOUS | SALISBURY | CONSTRUCT SIDEWALKS AT SELECTED LOCATIONS IN SALISBURY. | HIGHWAY | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | C-4908 | EXEMPT
ROWAN | HORAH STREET | SALISBURY | BRENNER AVENUE TO PARTEE STREET | HIGHWAY | OTHER | 9 | CABARRUS-ROWAN MPO | C-4908A | EXEMPT | [10 empty] | PROJECT DELETED AT MPO REQUEST
ROWAN | VARIOUS | SALISBURY | SPORTS COMPLEX, RYAN STREET TO CELEBRATION DRIVE AND SOUTH BOUNDARY STREET, HILLBORO STREET TO HILLS STREET | HIGHWAY | PRE-STI (HISTORIC) | 9 | CABARRUS-ROWAN MPO | C-4908B | EXEMPT | [10 empty] | COMPLETE
ROWAN | VARIOUS | SALISBURY | SALISBURY HIGH SCHOOL, ON VARIOUS STREETS AROUND HIGH SCHOOL | HIGHWAY | PRE-STI (HISTORIC) | 9 | CABARRUS-ROWAN MPO | C-4908C | EXEMPT | [10 empty] | COMPLETE
ROWAN | ARLINGTON AVENUE | SALISBURY | ARLINGTON AVENUE TO WALMART PARKING LOT | HIGHWAY | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | C-4908D | EXEMPT | [10 empty] | COMPLETE
ROWAN | SR 1002 (BRINGLE FERRY ROAD) | SALISBURY | LONG STREET TO NEWSOME ROAD | HIGHWAY | TRANSITION | 9 | CABARRUS-ROWAN MPO | C-4908E | EXEMPT | [10 empty] | COMPLETE
ROWAN | NEWSOME ROAD | SALISBURY | SR 1002 (BRINGLE FERRY ROAD) TO SR 1004 (STOKES FERRY ROAD) | HIGHWAY | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | C-4908F | EXEMPT | [10 empty] | PROJECT DELETED AT MPO REQUEST
ROWAN | US 70 (STATESVILLE BOULEVARD) | SALISBURY | US 601 (JAKE ALEXANDER BOULEVARD) | HIGHWAY | TRANSITION | 9 | CABARRUS-ROWAN MPO | C-4908G | EXEMPT | [10 empty] | UNDER CONSTRUCTION
ROWAN | MAIN STREET | SALISBURY | "D" AVENUE TO SUNSET DRIVE | HIGHWAY | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | C-4908H | EXEMPT | [10 empty] | UNDER CONSTRUCTION
ROWAN | NEWSOME ROAD | SALISBURY | CITY OF SALISBURY - CONSTRUCT BIKE LANES. | HIGHWAY | TRANSITION | 9 | CABARRUS-ROWAN MPO | C-5160 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY CITY OF SALISBURY
ROWAN | NC 152 | NCDOT | WEST OF US 29 / US 601 TO EAST OF I-85 IN CHINA GROVE. REVISE INTERCHANGES WITH US 29 / US 601 AND WITH I-85, AND IMPROVE CORRIDOR. | HIGHWAY | PRE-STI (HISTORIC) | 9 | CABARRUS-ROWAN MPO | I-3610 | [11 empty] | INCLUDED IN I-3802 - UNDER CONSTRUCTION
ROWAN | I-85 | NCDOT | SR 2180 (LANE STREET) IN CABARRUS COUNTY TO US 29 / US 601 CONNECTOR IN ROWAN COUNTY | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | I-3802B | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT
ROWAN | I-85 | NCDOT | SR 1221 (OLD BEATTY FORD ROAD) NEAR LANDIS. CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | I-3804 | DIVISION 9 | [10 empty] | INCLUDED IN I-3802B - DESIGN-BUILD PROJECT
ROWAN | I-85 | NCDOT | US 52 (INNES STREET) AND US 601 (JAKE ALEXANDER BOULEVARD) INTERCHANGES. STABILIZE SLOPES, REPLACE EMERGENCY LANE / SHOULDER , AND RESEAL JOINTS. | HIGHWAY | PRE-STI (HISTORIC) | 9 | CABARRUS-ROWAN MPO | I-5505 | [11 empty] | CONSTRUCTION INCLUDED WITH I-5741
ROWAN | NEW ROUTE | NCDOT | SR 1211 (KIMBALL ROAD) EXTENSION, NORTH CHAPEL STREET TO SR 1221 (BOSTIAN ROAD) IN LANDIS. CONSTRUCT TWO-LANE CONNECTOR ON NEW LOCATION. | HIGHWAY | LOCALLY SELECTED | 9 | CABARRUS-ROWAN MPO | U-5608 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | NEW ROUTE | NCDOT | SR 2576 (BENDIX DRIVE) TO US 52 (EAST INNES STREET) AT NEWSOME ROAD IN SALISBURY. CONSTRUCT A NEW MULTI-LANE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | U-5820 | [11 empty] | FUNDING FOR PART B REFLECTS REIMBURSEMENT TO CITY OF SALISBURY
ROWAN | SR 1004 (STOKES FERRY ROAD) | NCDOT | SR 2380 (ODDIE ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | SAFETY | 9 | CABARRUS-ROWAN MPO | W-5303 | [11 empty] | UNDER CONSTRUCTION - LET WITH B-4257
ROWAN | NC 801; SR 1951 (PARKS ROAD) | NCDOT | NC 801 AT SR 2048 (COOL SPRINGS ROAD / WOODLEAF ROAD), SR 1951 (PARKS ROAD) AT SR 2048 (WOODLEAF ROAD) AND NC 801 AT SR 2004 (WOODLEAF BARBER ROAD / QUARRY ROAD). WIDENING, INTERSECTION REALIGNMENT, TURN LANES AND GEOMETRIC IMPROVEMENTS. | HIGHWAY | TRANSITION | 9 | CABARRUS-ROWAN MPO | W-5314 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ROWAN | SR 1221 (OLD BEATTY FORD ROAD) | NCDOT | SR 1210 (OLD BEATTY FORD ROAD) / SR 1221 (BOSTIAN ROAD) TO SR 1337 (LENTZ ROAD). RELOCATE EXISTING ROAD WITH GRADE SEPARATION OVER I-85. | HIGHWAY | SAFETY | 9 | CABARRUS-ROWAN MPO | W-5516 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | REPLACMENT BUSES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | CABARRUS-ROWAN MPO | TA-5181 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 8235000 | 8235000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | EXPANSION VEHICLE (ADA PARATRANSIT, ADMINISTRATION) | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | CABARRUS-ROWAN MPO | TA-5182 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | SALISBURY TRANSIT ( CITY OF SALISBURY) | SALISBURY TRANSIT ( CITY OF SALISBURY) | REPLACE FOUR TRANSIT BUSES THAT HAVE EXCEEDED THEIR USEFUL LIFE, AND REPLACE VEHICLE RELATED EQUIPMENT SUCH AS FARE BOXES, DESTINATION SIGNS, CAMERA SYSTEMS, AND AUTOMATED VOICE ANNUNCIATION SYSTEMS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | CABARRUS-ROWAN MPO | TC-0023 | PUBLIC TRANSIT | 5339(b), L | [6 empty] | 2021 | 4560000 | 4560000
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | PREVENTIVE MAINTENANCE FOR BUS AND BUS FACILITY, FACILITY IMPROVEMENTS AND REPAIRS, AUTOMATIC BUS WASHER, SHOP EQUIPMENT, FUELING SYSTEM, SECURITY GATE UPGRADE, | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | CABARRUS-ROWAN MPO | TD-5302 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 2025000 | 2025000
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | PREVENTIVE MAINTENANCE - BUS, FACILITIES | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | CABARRUS-ROWAN MPO | TG-5232 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3336000 | 3336000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | CABARRUS-ROWAN MPO | TG-5233 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1120000 | 1120000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | ROUTINE CAPITAL - ADA SERVICES | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | CABARRUS-ROWAN MPO | TG-5260 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 704000 | 704000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | AVL SYSTEM | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 9 | CABARRUS-ROWAN MPO | TG-6179 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 1400000 | 1400000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | ROWAN COUNTY | ROWAN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 9 | CABARRUS-ROWAN MPO | TK-6160 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | OPERATING | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 9 | CABARRUS-ROWAN MPO | TO-5135 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 3560000 | 3560000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | OPERATING - FREE FARE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 9 | CABARRUS-ROWAN MPO | TO-5139 | PUBLIC TRANSIT | CMAQ, L | [6 empty] | 2020 | 336000 | 336000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 9 | CABARRUS-ROWAN MPO | TO-5201 | PUBLIC TRANSIT | CMAQ, SMAP | [6 empty] | 2020 | 904000 | 904000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | PLANNING | 9 | CABARRUS-ROWAN MPO | TP-5150 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 170000 | 170000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | SAFETY & SECURITY MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 9 | CABARRUS-ROWAN MPO | TS-5133 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 28000 | 28000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN, CABARRUS | US 52 | NCDOT | PROPOSED MISENHEIMER BYPASS TO GRANITE QUARRY BYPASS. | HIGHWAY | STI (PRIORITIZATION) | 9, 10 | CABARRUS-ROWAN MPO | R-5860 | DIVISION 9, 10
CABARRUS | NC 73 (DAVIDSON HIGHWAY) | NCDOT | EAST OF SR 1394 (POPLAR TENT ROAD) TO I-85. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | R-5706BA | REGION E | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 139000000 |  |  | 171500000
CABARRUS | NC 73 (DAVIDSON HIGHWAY) | NCDOT | I-85 TO US 29. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | R-5706BB | REGION E | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 50700000 |  |  | 75200000
ROWAN | US 29 | NCDOT | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | U-6130 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 |  |  | 4800000
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONCORD REGIONAL AIRPORT (JQF) | EXTEND RUNWAY SAFETY AREA. | AVIATION | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | AV-5889 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 300000 |  |  | 300000
CABARRUS | SR 1394 (POPLAR TENT ROAD) | NCDOT | GEORGE LILES PARKWAY TO US 29/601. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO | U-3415B | NOT FUNDED | T | NOT FUNDED | 9900000 | NOT FUNDED | 13200000 | NOT FUNDED | 32900000 |  |  | 56000000
CABARRUS, MECKLENBURG | POPLAR TENT ROAD | NCDOT | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | U-6029 | NOT FUNDED | T | NOT FUNDED | 43403000 | NOT FUNDED | 1085000 | NOT FUNDED | 80200000 |  |  | 124688000
ROWAN | US 52 | NCDOT | PROPOSED ROCKWELL BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | R-5860B | NOT FUNDED | T | NOT FUNDED | 8200000 | NOT FUNDED | 500000 | NOT FUNDED | 22300000 |  |  | 31000000
ROWAN | US 52 | NCDOT | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 9 | CABARRUS-ROWAN MPO | R-5860C | NOT FUNDED | T | NOT FUNDED | 5500000 | NOT FUNDED | 900000 | NOT FUNDED | 36500000 |  |  | 42900000
RUTHERFORD | RICEVILLE ROAD | NCDOT | US 70 TO NORTH OF THE VA HOSPITAL DRIVEWAY. IMPROVE SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 13 | FRENCH BROAD RIVER MPO | BL-0076 | DIVISION 13 | L, TADA |  |  |  |  | 2023 | 1038000 |  |  | 1038000
RUTHERFORD | THERMAL BELT RAIL TRAIL | NCDOT | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | BIKE/PED | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | EB-5915 | DIVISION 13 | L, TA5200 |  |  |  |  | 2022 | 455000 |  |  | 455000 | UNDER CONSTRUCTION.
RUTHERFORD | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | NCDOT | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | BIKE/PED | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | EB-5966 | DIVISION 13 | L, TA5200 | 2025 | 300000 |  |  | 2026 | 750000 | 2024 | 150000 | 1200000
RUTHERFORD | SR 1306 (BILLS CREEK ROAD) | NCDOT | REPLACE BRIDGE 800628 OVER LAKE LURE DAM AND BROAD RIVER. | HIGHWAY | BRIDGES | 13 | FOOTHILLS RPO | B-5871 | DIVISION 13 | BGOFF | 2023 | 250000 |  |  | 2027 | 5000000 |  |  | 5250000 | RIGHT-OF-WAY IN PROGRESS.
RUTHERFORD | US 74 | NCDOT | REPLACE BRIDGE 800083 AND BRIDGE 800084 OVER SECOND BROAD RIVER. | HIGHWAY | BRIDGES | 13 | FOOTHILLS RPO | B-5876 | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2025 | 9798000 |  |  | 9798000 | RIGHT-OF-WAY IN PROGRESS
RUTHERFORD | SR 2125 (HARRIS HENRIETTA ROAD) | NCDOT | REPLACE BRIDGE 800145 OVER FLOYDS CREEK. | HIGHWAY | BRIDGES | 13 | FOOTHILLS RPO | B-6047 | DIVISION 13 | BGOFF | 2023 | 210000 |  |  | 2024 | 2100000 |  |  | 2310000 | RIGHT-OF-WAY IN PROGRESS.
RUTHERFORD | NEW ROUTE | NCDOT | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 13 | FOOTHILLS RPO | HA-0005 | EXEMPT | ADHSL | 2023 | 15000 |  |  | 2023 | 900000 | 2022 | 15000 | 930000 | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045
RUTHERFORD | US-221A (CHARLOTTE ROAD / MAIN STREET) | NCDOT | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | HIGHWAY | LOCALLY SELECTED | 13 | FOOTHILLS RPO | HL-0065 | DIVISION 13 | DP, L, O, S(M) | 2024 | 1050000 | 2024 | 2110000 | 2025 | 20110000 | 2023 | 1140000 | 24410000 | "DP" = RAISE GRANT; "O" = OTHER FEDERAL; S(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT
RUTHERFORD | SR 1510 (HUDLOW ROAD) | NCDOT | US 221A TO NC 64. UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 13 | FOOTHILLS RPO | HS-2013G | DIVISION 13 | HSIP |  |  |  |  | 2023 | 497000 |  |  | 497000 | UNDER CONSTRUCTION.
RUTHERFORD | SR 1006 (BOSTIC-SUNSHINE HIGHWAY) | NCDOT | SR 1007 TO NC 226 NEAR BOSTIC. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 13 | FOOTHILLS RPO | HS-2013N | DIVISION 13 | HSIP |  |  |  |  | 2024 | 951000 |  |  | 951000
RUTHERFORD | US 221 | NCDOT | SOUTH CAROLINA STATE LINE TO NORTH OF SR 1366 (ROPER LOOP ROAD). WIDEN TO MULTI-LANES WITH BYPASS OF RUTHERFORDTON ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-2233
RUTHERFORD | US 221 | NCDOT | SOUTH CAROLINA STATE LINE TO SOUTH OF FLOYD'S CREEK | HIGHWAY | PRE-STI (HISTORIC) | 13 | FOOTHILLS RPO | R-2233AA | DIVISION 13 | [10 empty] | COMPLETE
RUTHERFORD | US 221 | NCDOT | SOUTH OF FLOYD'S CREEK TO NORTH OF US 74 BYPASS | HIGHWAY | PRE-STI (HISTORIC) | 13 | FOOTHILLS RPO | R-2233AB | [11 empty] | COMPLETE
RUTHERFORD | US 221 | NCDOT | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-2233BA | DIVISION 13 | T | 2024 | 14799000 | 2024 | 3200000 | 2027 | 108374000 |  |  | 126373000 | BUILD NC BONDS: $21.5M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE).
RUTHERFORD | US 221 | NCDOT | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-2233BB | DIVISION 13 | T | 2021 | 20000000 |  |  | 2022 | 132797000 |  |  | 152797000 | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
RUTHERFORD | US 221 | NCDOT | NORTH OF SR 1366 (ROPER LOOP ROAD) IN RUTHERFORD COUNTY TO SR 1153 (GOOSE CREEK ROAD) IN MCDOWELL COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-2597
RUTHERFORD | US 221 | NCDOT | NORTH OF SR 1366 (ROPER LOOP ROAD) TO SR 1325 (NANNEY TOWN ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-2597A | NOT FUNDED | NHP | NOT FUNDED | 12600000 | NOT FUNDED | 3400000 | NOT FUNDED | 69201000 |  |  | 85201000
RUTHERFORD | US 221 | NCDOT | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-5880 | NOT FUNDED | NHP | NOT FUNDED | 500000 | NOT FUNDED | 400000 | NOT FUNDED | 2500000 |  |  | 3400000
RUTHERFORD | NC 108 (CHARLOTTE STREET) | NCDOT | NC 108 (MAPLE STREET), SOUTH WASHINGTON STREET, MONFREDO STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-5916 | NOT FUNDED | BG5200 | NOT FUNDED | 5200000 | NOT FUNDED | 300000 | NOT FUNDED | 1600000 |  |  | 7100000
RUTHERFORD | US 64 (EAST MOUNTAIN STREET) | NCDOT | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-5917 | NOT FUNDED | BG5200 | NOT FUNDED | 1600000 | NOT FUNDED | 300000 | NOT FUNDED | 900000 |  |  | 2800000
RUTHERFORD | US 221A (EAST MAIN STREET) | NCDOT | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-5918 | NOT FUNDED | BG5200 | NOT FUNDED | 3100000 | NOT FUNDED | 400000 | NOT FUNDED | 3100000 |  |  | 6600000
RUTHERFORD | SR 2241 (OAK STREET) | NCDOT | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | U-5833 | DIVISION 13 | T | 2020 | 435000 |  |  | 2020 | 7530000 | 2020 | 1050000 | 9015000 | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
RUTHERFORD | RUTHERFORD COUNTY | RUTHERFORD COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 13 | FOOTHILLS RPO | TK-6161 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 788000 | 788000 | FUNDS AUTHORIZED IN PROGRESS
RUTHERFORD, BURKE, MITCHELL, YANCEY | VARIOUS | NCDOT | VARIOUS SR LOCATIONS. INSTALL LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 13 | FOOTHILLS RPO, GREATER HICKORY MPO, HIGH COUNTRY RPO | W-5813B | DIVISION 13 | HSIP |  |  |  |  | 2022 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION.
RUTHERFORD, McDOWELL | US 221 | NCDOT | SR 1325 (NANNEY TOWN ROAD) TO SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 13 | FOOTHILLS RPO | R-2597B | NOT FUNDED | NHP | NOT FUNDED | 7700000 | NOT FUNDED | 1800000 | NOT FUNDED | 42400000 |  |  | 51900000
SAMPSON | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | REHABILITATE RUNWAY. | AVIATION | STI (PRIORITIZATION) | 3 | MID-CAROLINA RPO | AV-5823 | DIVISION 3 | T |  |  |  |  | 2025 | 2200000 |  |  | 2200000
SAMPSON | BEAMAN STREET | CLINTON | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 3 | MID-CAROLINA RPO | EB-6011 | NOT FUNDED | L, TA5200 | NOT FUNDED | 10000 |  |  | NOT FUNDED | 105000 | NOT FUNDED | 18000 | 133000
SAMPSON | US 13 | NCDOT | REPLACE BRIDGE 810009 OVER SOUTH RIVER OVERFLOW. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | B-4635 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2250000 |  |  | 2250000 | UNDER CONSTRUCTION.
SAMPSON | NC 24 | NCDOT | REPLACE BRIDGE 810056 OVER SIX RUNS CREEK. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | B-4636 | STATEWIDE MOBILITY | BFP, HFB | 2020 | 390000 |  |  | 2029 | 5900000 |  |  | 6290000 | RIGHT-OF-WAY IN PROGRESS.
SAMPSON | SR 1817 (BRADSHAW ROAD) | NCDOT | REPLACE BRIDGE 810188 OVER WARD SWAMP. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | B-5310 | DIVISION 3 | BGOFF | 2023 | 100000 |  |  | 2024 | 1500000 |  |  | 1600000 | RIGHT-OF-WAY IN PROGRESS.
SAMPSON | SR 1904 (PINE RIDGE ROAD) | NCDOT | REPLACE BRIDGE 810248 OVER SIX RUNS CREEK. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | B-5621 | DIVISION 3 | BGOFF | 2021 | 154000 |  |  | 2022 | 2500000 |  |  | 2654000 | UNDER CONSTRUCTION.
SAMPSON | SR 1620 (TIMOTHY ROAD) | NCDOT | REPLACE BRIDGE 810169 OVER BIG JUNIPER RUN. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | B-5631 | DIVISION 3 | BGOFF |  |  |  |  | 2022 | 1320000 |  |  | 1320000 | UNDER CONSTRUCTION.
SAMPSON | SR 1706 (KORNEGAY TOWN ROAD) | NCDOT | REPLACE BRIDGE 810214 OVER KILL SWAMP. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | B-5651 | DIVISION 3 | [10 empty] | UNDER CONSTRUCTION.
SAMPSON | SR 1206 (WRIGHT BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 810072 OVER GREAT COHARIE CREEK. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | B-6049 | DIVISION 3 | BGOFF | 2023 | 340000 |  |  | 2023 | 3400000 |  |  | 3740000 | UNDER CONSTRUCTION.
SAMPSON | SR 1804 (HOUSES MILL ROAD) | NCDOT | REPLACE BRIDGE 810178 OVER SEVENMILE SWAMP. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | BR-0121 | DIVISION 3 | DP |  |  |  |  | 2021 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
SAMPSON | SR 1703 (OLD GOLDSBORO ROAD) | NCDOT | REPLACE BRIDGE 810348 OVER BEAVERDAM CREEK. | HIGHWAY | BRIDGES | 3 | MID-CAROLINA RPO | BR-0122 | DIVISION 3 | DP |  |  |  |  | 2021 | 727000 |  |  | 727000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
SAMPSON | I-40 | NCDOT | I-40 FROM THE JOHNSTON COUNTY LINE (MILE MARKER 340) TO THE DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 3 | MID-CAROLINA RPO | HI-0011 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 22400000 |  |  | 22400000
SAMPSON | I-40 | NCDOT | JOHNSTON COUNTY LINE (MILE MARKER 340) TO DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 3 | MID-CAROLINA RPO | I-5780 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2019 | 10166000 |  |  | 10166000 | UNDER CONSTRUCTION.
SAMPSON | NC 24 | NCDOT | SR 1404 (DOWDY ROAD) TO SR 1303 (MITCHELL LOOP ROAD). | HIGHWAY | TRANSITION | 3 | MID-CAROLINA RPO | R-2303C | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
SAMPSON | NC 24 | NCDOT | SR 1303 (MITCHELL LOOP ROAD) TO US 421/US 701/SR 1296 (SUNSET AVENUE). | HIGHWAY | TRANSITION | 3 | MID-CAROLINA RPO | R-2303D | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
SAMPSON | NC 24 | NCDOT | WEST OF SR 1262 (AIRPORT ROAD) TO EAST OF US 421. | HIGHWAY | PRE-STI (HISTORIC) | 3 | MID-CAROLINA RPO | R-2303DA | [11 empty] | COMPLETED.
SAMPSON | NC 24 | NCDOT | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 3 | MID-CAROLINA RPO | R-2303E | DIVISION 3 | T | 2020 | 4395000 |  |  | 2020 | 36896000 | 2020 | 5055000 | 46346000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
SAMPSON | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | NCDOT | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 3 | MID-CAROLINA RPO | U-6126 | NOT FUNDED | NHP | NOT FUNDED | 302000 | NOT FUNDED | 126000 | NOT FUNDED | 2500000 |  |  | 2928000
SAMPSON | SAMPSON COUNTY | SAMPSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 3 | MID-CAROLINA RPO | TK-6162 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 632000 | 632000 | FUNDS AUTHORIZED IN PROGRESS
SAMPSON, CUMBERLAND | NC 24 | NCDOT | SR 1853 (JOHN NUNNERY ROAD) IN CUMBERLAND COUNTY TO SR 1404 (DOWDY ROAD) IN SAMPSON COUNTY. | HIGHWAY | PRE-STI (HISTORIC) | 3, 6 | MID-CAROLINA RPO | R-2303B | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
SAMPSON, CUMBERLAND, DUPLIN | NC 24 | NCDOT | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO I-40 IN DUPLIN COUNTY AT WARSAW. FOUR LANES DIVIDED, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3, 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, EASTERN CAROLINA RPO | R-2303
SAMPSON, DUPLIN | NC 24 | NCDOT | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | HIGHWAY | STI (PRIORITIZATION) | 3 | MID-CAROLINA RPO, EASTERN CAROLINA RPO | R-2303F | NOT FUNDED | T | NOT FUNDED | 16800000 | NOT FUNDED | 1960000 | NOT FUNDED | 276700000 |  |  | 295460000 | PLANNING/DESIGN IN PROGRESS.
SCOTLAND | LAURINBURG- MAXTON AIRPORT (MEB) | LAURINBURG- MAXTON AIRPORT (MEB) | CONSTRUCT 1500 FT RUNWAY EXTENSION. | AVIATION | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | AV-5854 | DIVISION 8 | T |  |  |  |  | 2033 | 6390000 |  |  | 6390000
SCOTLAND | SR 1107 (ATKINSON STREET) | NCDOT | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | EB-5865 | DIVISION 8 | L, TA5200 | 2023 | 100000 | 2023 | 90000 | 2024 | 930000 | 2022 | 76000 | 1196000
SCOTLAND | SR 1108 (WEST BOULEVARD) | LAURINBURG | SR 1105 (TURNPIKE ROAD) TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE, AND PROVIDE PEDESTRIAN ACCOMMODATIONS AT US 15 / US 401 / US 501 INTERSECTION AND ACROSS US 74. | BIKE/PED | LOCALLY SELECTED | 8 | LUMBER RIVER RPO | EB-5872 | DIVISION 8 | [10 empty] | PROJECT LENGTH REFLECTS PARTS A ONLY- PART B IS NON-STI PROJECT; EB 5872C PROJECT BREAK DELETED WORK TO BE ACCOMPLISHED UNDER EB-5872A.
SCOTLAND | SR 1108 (WEST BOULEVARD) | NCDOT | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | BIKE/PED | LOCALLY SELECTED | 8 | LUMBER RIVER RPO | EB-5872A | DIVISION 8 | L, TA5200 | 2024 | 166000 |  |  | 2024 | 436000 |  |  | 602000
SCOTLAND | SR 1108 (WEST BOULEVARD) | LAURINBURG | GLASGOW DRIVE TO EAST OF US 15 / US 401 / US 501 (MCCOLL ROAD) IN LAURINBURG. | BIKE/PED | LOCALLY SELECTED | 8 | LUMBER RIVER RPO | EB-5872B | EXEMPT
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) | LAURINBURG | SR 1674 (LAUCHWOOD DRIVE) TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS. | BIKE/PED | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | EB-6015
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) | NCDOT | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | BIKE/PED | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | EB-6015A | DIVISION 8 | L, TA5200 | 2023 | 76000 |  |  | 2024 | 660000 | 2022 | 66000 | 802000
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET | LAURINBURG | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | BIKE/PED | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | EB-6015B | DIVISION 8 | L, TA5200 | 2024 | 52000 |  |  | 2025 | 460000 | 2023 | 55000 | 567000
SCOTLAND | COMMONWEALTH AVENUE | LAURINBURG | REPLACE BRIDGE 820081 OVER LEITH CREEK WITH CULVERT IN LAURINBURG. | HIGHWAY | TRANSITION | 8 | LUMBER RIVER RPO | B-5003 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF LAURINBURG - MUNICIPAL BRIDGE
SCOTLAND | US 15/501 (ABERDEEN ROAD) | NCDOT | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE | HIGHWAY | ECONOMIC DEVELOPMENT | 8 | LUMBER RIVER RPO | HE-0013 | DIVISION 8 | T | 2024 | 50000 | 2024 | 250000 | 2024 | 1500000 | 2023 | 500000 | 2300000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO.
SCOTLAND | SCOTLAND COUNTY INDUSTRIAL PARK ACCESS ROAD | NCDOT | IMPROVE THE EXISTING ACCESS ROAD INTO THE SCOTLAND COUNTY INDUSTRIAL PARK. | HIGHWAY | ECONOMIC DEVELOPMENT | 8 | LUMBER RIVER RPO | HE-0013A | DIVISION 8 | T |  |  |  |  | 2023 | 200000 |  |  | 200000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO.
SCOTLAND | US 74 | NCDOT | RICHMOND COUNTY LINE TO SR 1363. UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO | HS-2008A | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 360000 |  |  | 360000 | UNDER CONSTRUCTION
SCOTLAND | US 74 | NCDOT | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO | HS-2008E | STATEWIDE MOBILITY | HSIP, T | 2023 | 100000 | 2023 | 50000 | 2023 | 620000 |  |  | 770000
SCOTLAND | US 15 / US 401 | NCDOT | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | U-5977 | REGION E | T | 2028 | 4800000 | 2028 | 2900000 | 2030 | 19400000 |  |  | 27100000
SCOTLAND | US 15 / US 501 | NCDOT | NC 144 INTERSECTION. CONSTRUCT ROUNDABOUT | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO | W-5208MA | REGION E | [10 empty] | UNDER CONSTRUCTION
SCOTLAND | US 74 / FUTURE I-74 WESTBOUND | NCDOT | EXITS 183 AND 184 IN LAURINBURG. UPGRADE SIGNING AND PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 8 | LUMBER RIVER RPO | W-5808A | STATEWIDE MOBILITY | [10 empty] | PROJECT DELETED AT REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. PROJECT WILL UTILZE NON-STIP FUNDS.
SCOTLAND | SCOTLAND COUNTY | SCOTLAND COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 8 | LUMBER RIVER RPO | TK-6163 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 460000 | 460000 | FUNDS AUTHORIZED IN PROGRESS
SCOTLAND | CSX | CSXT RR | RAIL SPUR FOR INDUSTRIAL ACCESS. CONSTRUCT SPINE TRACK AND TURNOUTS, AND REHABILITATE EXISTING TRACK SECTIONS. | RAIL | ECONOMIC DEVELOPMENT | 8 | LUMBER RIVER RPO | P-5724 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CSX; "O" FUNDING INCLUDES PARTICIPATION BY NORTH CAROLINA RAILROAD, LAURINBURG-MAXTON AIRPORT, RAIL INDUSTRIIAL ACCESS PROGRAM, AND COMMUNITY DEVELOPMENT BLOCK GRANT PROGRAM
SCOTLAND, RICHMOND | US 74 / FUTURE I-74 | NCDOT | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 8 | LUMBER RIVER RPO | I-6055 | REGION E | T | 2028 | 27600000 | 2028 | 8584000 | 2031 | 187500000 |  |  | 223684000
STANLY | STANLY COUNTY AIRPORT (VUJ) | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBB LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. | AVIATION | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | AV-5817 | DIVISION 10 | T | 2025 | 4400000 |  |  | 2027 | 2500000 |  |  | 6900000
STANLY | ALBEMARLE | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | BIKE/PED | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | EB-5841 | DIVISION 10 | L, TA5200 | 2025 | 250000 |  |  | 2026 | 250000 | 2024 | 50000 | 550000
STANLY | STANFIELD | NCDOT | NC 200, NORTH LOVE CHAPEL TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | BIKE/PED | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | EB-5857 | DIVISION 10 | L, TALT5 | 2022 | 290000 |  |  | 2023 | 740000 | 2021 | 95000 | 1125000 | UNDER CONSTRUCTION.
STANLY | NORTH SECOND AVENUE | ALBEMARLE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | BIKE/PED | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | EB-5972 | DIVISION 10 | L, TA5200 | 2026 | 130000 |  |  | 2027 | 450000 | 2024 | 10000 | 590000
STANLY | SALISBURY AVENUE | ALBEMARLE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | BIKE/PED | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | EB-5973 | DIVISION 10 | L, TA5200 |  |  |  |  | 2025 | 120000 | 2024 | 12000 | 132000
STANLY | US 52 BUSINESS RAMP | ALBEMARLE | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | BIKE/PED | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | EB-5974 | NOT FUNDED | L, TA5200 | NOT FUNDED | 30000 |  |  | NOT FUNDED | 200000 | NOT FUNDED | 30000 | 260000
STANLY | SR 1434 (ROGERS ROAD) | NCDOT | REPLACE BRIDGE 830042 OVER BIG BEAR CREEK. | HIGHWAY | BRIDGES | 10 | ROCKY RIVER RPO | B-5811 | DIVISION 10 | BGOFF | 2025 | 15000 |  |  | 2030 | 600000 |  |  | 615000
STANLY | SR 1917 (BETHLEHEM CHURCH ROAD) | NCDOT | REPLACE BRIDGE 830102 OVER LONG CREEK. | HIGHWAY | BRIDGES | 10 | ROCKY RIVER RPO | B-6046 | DIVISION 10 | BGOFF | 2022 | 145000 |  |  | 2024 | 1700000 |  |  | 1845000 | RIGHT-OF-WAY IN PROGRESS.
STANLY | NC 24/NC 27 | NCDOT | LEONARD AVENUE. INSTALL AUDIBLE PEDESTRIAN SIGNALS. | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO | HS-2010K | REGION E | HSIP |  |  |  |  | 2023 | 15000 |  |  | 15000
STANLY | NC 24/NC 27 | NCDOT | SR 1963 (ST. MARTIN ROAD) IN ALBEMARLE TO NC 73. WIDEN TO MULTI- LANES. (COORDINATE WITH B-4974). | HIGHWAY | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | R-2530
STANLY | NC 24-27 | NCDOT | SR 1963 (ST. MARTIN ROAD) TO BIRD ROAD IN ALBEMARLE | HIGHWAY | SAFETY | 10 | ROCKY RIVER RPO | R-2530A | [11 empty] | COMPLETE
STANLY | NC 24-27 | NCDOT | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | HIGHWAY | STI (PRIORITIZATION) | 10 | ROCKY RIVER RPO | R-2530B | REGION E | T | 2020 | 5700000 | 2020 | 3600000 | 2020 | 90569000 | 2020 | 8040000 | 107909000 | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
STANLY | VARIOUS | NCDOT | VARIOUS IMPROVEMENTS AROUND TOWN OF OAKBORO. | HIGHWAY | ECONOMIC DEVELOPMENT | 10 | ROCKY RIVER RPO | R-5965 | [11 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. TOTAL AWARD AMOUNT = $4,400,279
STANLY | VARIOUS | NCDOT | NC 205/SR 1108 (LIGHTHOUSE ROAD)/SR 1109 (BUSTER ROAD) INTERSECTION AND SR 1110 (SWIFT ROAD) AT CHARLOTTE PIPE FACILITY. IMPROVE INTERSECTIONS. | HIGHWAY | ECONOMIC DEVELOPMENT | 10 | ROCKY RIVER RPO | R-5965A | DIVISION 10 | T | 2021 | 120000 |  |  | 2021 | 2405000 |  |  | 2525000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION.
STANLY | VARIOUS | NCDOT | SR 1107 (SILVER ROAD)/SR 1108 (LIGHTHOUSE ROAD) AND SR 1107 (SILVER ROAD)/SR 1110 (SWIFT ROAD) INTERSECTIONS. IMPROVE INTERSECTIONS. SR 1107 (SILVER ROAD), SR 1108 (LIGHTHOUSE ROAD) AND SR 1110 (SWIFT ROAD). VARIOUS ROADWAY IMPROVEMENTS INCLUDING FULL DEPTH RECLAMATION. | HIGHWAY | ECONOMIC DEVELOPMENT | 10 | ROCKY RIVER RPO | R-5965B | DIVISION 10 | T | 2021 | 250000 |  |  | 2023 | 1586000 |  |  | 1836000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION.
STANLY | SCUSA TRANSPORTATION | SCUSA TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 10 | ROCKY RIVER RPO | TK-6164 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 904000 | 904000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NATIONAL RECREATIONAL TRAILS. | BIKE/PED | OTHER | 99 | STATEWIDE PROJECT | E-4018 | DIVISION SW | TA |  |  |  |  | 2020 | 19200000 |  |  | 19200000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PEDESTRIAN FACILITIES PROGRAM. | BIKE/PED | PRE-STI (HISTORIC) | 99 | STATEWIDE PROJECT | EB-3314 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
STATEWIDE | VARIOUS | NCDOT | ROADWAY IMPROVEMENTS FOR BICYCLE SAFETY ON STATE AND LOCAL DESIGNATED BIKE ROUTES. | BIKE/PED | OTHER | 99 | STATEWIDE PROJECT | EB-4411 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | SAFE ROUTES TO SCHOOL EDUCATION. | BIKE/PED | OTHER | 99 | STATEWIDE PROJECT | EB-6033 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | RAILS TO TRAILS PROGRAM | BIKE/PED | OTHER | 99 | STATEWIDE PROJECT | EB-6037 | DIVISION SW | [10 empty] | LOCAL FUNDS REPRESENT LOCAL MATCH FOR RIGHT-OF-WAY AND CONSTRUCTION OF TRAILS BY LOCAL GOVERNMENTS.
STATEWIDE | VARIOUS | NCDOT | SIDEWALK PROGRAM IN ALL FOURTEEN HIGHWAY DIVISIONS. | BIKE/PED | PRE-STI (HISTORIC) | 99 | STATEWIDE PROJECT | ER-2971 | PRE-STI (TRANSITION) | [10 empty] | IN PROGRESS - $182,000 IN STPDA FUNDS ALLOCATED TO ER-2971E
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | B-8888 | DIVISION SW | BGOFF |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | B-8888DIV | DIVISION SW | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | B-8888REG | REGION SW | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | B-8888SW | STATEWIDE MOBILITY | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | B-9999 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | B-9999DIV | DIVISION SW | BG | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | B-9999REG | REGION SW | BG | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | B-9999SW | STATEWIDE MOBILITY | BG | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | NCDOT | ESTABLISH BRIDGE MANAGEMENT SYSTEM. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | BK-5100 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | DECK PRESERVATION AT 15 SELECTED LOCATIONS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | BK-5101 | DIVISION SW | [10 empty] | UNDER CONSTRUCTION
STATEWIDE | VARIOUS | NCDOT | BRIDGE PAINTING AT 19 SELECTED LOCATIONS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | BK-5102 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | BP-5500
STATEWIDE | VARIOUS | NCDOT | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | BP-5500DIV | DIVISION SW
STATEWIDE | VARIOUS | NCDOT | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | BP-5500REG | REGION SW
STATEWIDE | VARIOUS | NCDOT | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | BP-5500SW | STATEWIDE MOBILITY
STATEWIDE | VARIOUS | NCDOT | DEPARTMENT OF MOTOR VEHICLES (DMV), VEHICLE EMISSION COMPLIANCE SYSTEM. UPGRADE NORTH CAROLINA'S MOTOR VEHICLE EMISSIONS INSPECTION AND MAINTENANCE (I/M) PROGRAM. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-3600 | EXEMPT | [10 empty] | IN PROGRESS BY DEPARTMENT OF MOTOR VEHICLES
STATEWIDE | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY SOLAR CENTER CLEAN TRANSPORTATION PROGRAM. DEVELOP AND ADMINISTER A SEVEN YEAR CLEAN FUEL-ADVANCED TECHNOLOGY REBATE PROGRAM IN ALL CMAQ ELIGIBLE COUNTIES TO REDUCE EMISSIONS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-4902 | EXEMPT | [10 empty] | IN PROGRESS BY NORTH CAROLINA STATE UNIVERSITY
STATEWIDE | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY | PHASE 2 OF IMPLEMENTATION | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-4902A | EXEMPT
STATEWIDE | VARIOUS | NCDOT | STATEWIDE CMAQ PROJECTS TO IMPROVE AIR QUALITY WITHIN NONATTAINMENT AND MAINTENANCE AREAS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-5600 | EXEMPT
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM, INCLUDING EMISSIONS-REDUCING SUB-AWARDS, IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-5702 | EXEMPT
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-5702A | EXEMPT | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-5702B | EXEMPT | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-5702C | EXEMPT
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-5702D | EXEMPT | CMAQ, L | [6 empty] | 2022 | 3258000 | 3258000
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | C-5702E | EXEMPT | CMAQ, L | [6 empty] | 2022 | 5584000 | 5584000
STATEWIDE | VARIOUS | NCDOT | VEGETATION MANAGEMENT - CLEAR ZONE IMPROVEMENT AND MANAGEMENT STATEWIDE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | ER-5600 | DIVISION SW | STPE |  |  |  |  | 2022 | 4000000 |  |  | 4000000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-8888 | DIVISION SW | BGOFF |  |  |  |  | 2024 | 353413000 |  |  | 353413000
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-8888DIV | DIVISION SW | BFP |  |  |  |  | 2024 | 155544000 |  |  | 155544000
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-8888REG | REGION SW | BFP |  |  |  |  | 2024 | 155544000 |  |  | 155544000
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-8888SW | STATEWIDE MOBILITY | BFP |  |  |  |  | 2024 | 207391000 |  |  | 207391000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999A
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999ADIV | DIVISION SW | T | [6 empty] | 2021 | 117000000 | 117000000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999AREG | REGION SW | T | [6 empty] | 2021 | 117000000 | 117000000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999ASW | STATEWIDE MOBILITY | T | [6 empty] | 2021 | 156000000 | 156000000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999B
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999BDIV | DIVISION SW | T | [6 empty] | 2021 | 9000000 | 9000000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999C
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999CDIV | DIVISION SW | T | [6 empty] | 2021 | 11700000 | 11700000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999CREG | REGION SW | T | [6 empty] | 2021 | 11700000 | 11700000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | HB-9999CSW | STATEWIDE MOBILITY | T | [6 empty] | 2021 | 15600000 | 15600000
STATEWIDE | VARIOUS | NCDOT | INTERSTATE MAINTENANCE PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | INTERSTATE MAINTENANCE | 99 | STATEWIDE PROJECT | HI-9999 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 760210000 |  |  | 760210000
STATEWIDE | STATEWIDE TRAFFIC OPERATIONS | NCDOT | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | HO-0010 | STATEWIDE MOBILITY
STATEWIDE | STATEWIDE TRAFFIC OPERATIONS | NCDOT | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT ACROSS THE ENTIRE STATE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | HO-0010B | STATEWIDE MOBILITY | CRPANY, S(M) | [6 empty] | 2024 | 10000000 | 10000000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | HS-9999
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | HS-9999DIV | DIVISION SW | HSIP |  |  |  |  | 2024 | 224403000 |  |  | 224403000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | HS-9999REG | REGION SW | HSIP |  |  |  |  | 2024 | 224453000 |  |  | 224453000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | HS-9999SW | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2024 | 299269000 |  |  | 299269000
STATEWIDE | VARIOUS | NCDOT | CONSTRUCTION OF ELECTRIC VEHICLE SUPPLY EQUIPMENT ALONG NORTH CAROLINA'S ALTERNATIVE CORRIDORS AND NEVI PLANNING. | HIGHWAY | NATIONAL ELECTRIC VEHICLE INFRASTRUCTURE | 99 | STATEWIDE PROJECT | HV-0001 | DIVISION SW | NEVI | [6 empty] | 2023 | 1221000 | 1221000
STATEWIDE | VARIOUS | NCDOT | NATIONAL ELECTRIC VEHICLE INFRASTRUCTURE PROGRAM (NEVI) - UNPROGRAMMED BALANCE. | HIGHWAY | NATIONAL ELECTRIC VEHICLE INFRASTRUCTURE | 99 | STATEWIDE PROJECT | HV-9999 | DIVISION SW | NEVI |  |  |  |  | 2023 | 271079000 |  |  | 271079000
STATEWIDE | VARIOUS | NCDOT | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0219 | STATEWIDE MOBILITY
STATEWIDE | VARIOUS | NCDOT | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0219DIV | DIVISION SW | T | [6 empty] | 2020 | 1200000 | 1200000
STATEWIDE | VARIOUS | NCDOT | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0219REG | REGION SW | T | [6 empty] | 2020 | 1200000 | 1200000
STATEWIDE | VARIOUS | NCDOT | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0219SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 1600000 | 1600000
STATEWIDE | VARIOUS | NCDOT | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0360 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0360DIV | DIVISION SW | T | [6 empty] | 2020 | 1200000 | 1200000
STATEWIDE | VARIOUS | NCDOT | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0360REG | REGION SW | T | [6 empty] | 2020 | 1200000 | 1200000
STATEWIDE | VARIOUS | NCDOT | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0360SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 1600000 | 1600000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0376 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0376DIV | DIVISION SW | T | [6 empty] | 2020 | 4320000 | 4320000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0376REG | REGION SW | T | [6 empty] | 2020 | 4320000 | 4320000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0376SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 5670000 | 5670000
STATEWIDE | VARIOUS | NCDOT | SCOUR EVALUATION PROGRAM OF EXISTING BRIDGES. | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | M-0379 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0391 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0391DIV | DIVISION SW | T | [6 empty] | 2020 | 1920000 | 1920000
STATEWIDE | VARIOUS | NCDOT | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0391REG | REGION SW | T | [6 empty] | 2020 | 1920000 | 1920000
STATEWIDE | VARIOUS | NCDOT | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0391SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 2560000 | 2560000
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0392 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0392DIV | DIVISION SW | T | [6 empty] | 2020 | 768000 | 768000
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0392REG | REGION SW | T | [6 empty] | 2020 | 768000 | 768000
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0392SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 1024000 | 1024000
STATEWIDE | VARIOUS | NCDOT | MUNICIPAL BRIDGE INSPECTION PROGRAM | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | M-0414 |  | BGOFF, L | [6 empty] | 2020 | 16000000 | 16000000
STATEWIDE | VARIOUS | NCDOT | STORM WATER RUNOFF. RESEARCH, DESIGN, CONSTRUCT, MAINTAIN AND MONITOR STORM WATER DRAINAGE FROM 50 BRIDGES OVER WATERWAYS. (HB 2346, SECTION 25.18) | HIGHWAY | BRIDGES | 99 | STATEWIDE PROJECT | M-0418 | DIVISION SW | [10 empty] | UNDER CONSTRUCTION
STATEWIDE | VARIOUS | NCDOT | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0451
STATEWIDE | VARIOUS | NCDOT | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0451DIV | DIVISION SW | T | [6 empty] | 2020 | 336000 | 336000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0451REG | REGION SW | T | [6 empty] | 2020 | 336000 | 336000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0451SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 448000 | 448000
STATEWIDE | VARIOUS | NCDOT | TOLLING/FINANCIAL FEASIBILITY STUDIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0452 | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 3200000 | 3200000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479A
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479ADIV | DIVISION SW | T | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479AREG | REGION SW | T | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479ASW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479B
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479BDIV | DIVISION SW | T | [6 empty] | 2020 | 2400000 | 2400000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479BREG | REGION SW | T | [6 empty] | 2020 | 2400000 | 2400000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479BSW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 3200000 | 3200000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479DIV | DIVISION SW | T | [6 empty] | 2020 | 24000000 | 24000000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479REG | REGION SW | T | [6 empty] | 2020 | 24000000 | 24000000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0479SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 32000000 | 32000000
STATEWIDE | VARIOUS | NCDOT | FEDERAL STATE TRANSPORTATION INNOVATION COUNCIL (STIC) INCENTIVE FUNDED PROJECTS | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0482 | EXEMPT | DP, S(M) | [6 empty] | 2023 | 500000 | 500000 | DP FUNDS REPRESENT FEDERAL STIC FUNDS.
STATEWIDE | VARIOUS | NCDOT | TRANSPORTATION PROGRAM MANAGEMENT UNIT (TPMU) OVERSIGHT FOR LOCALLY-ADMINISTERED PROJECTS INCLUDING PREPARATION OF AGREEMENTS AND FUNDING AUTHORIZATION REQUESTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0505 | DIVISION SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | NCDOT | RIGHT-OF-WAY BRANCH, REVIEW OF LOCAL PUBLIC AGENCY (LPA) PROJECTS BY THE APPRAISAL SECTION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0515 | DIVISION SW | T | 2020 | 4000000 | [6 empty] | 4000000
STATEWIDE | VARIOUS | NCDOT | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0521 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE DIVISION TIER. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0521DIV | DIVISION SW | T | [6 empty] | 2020 | 100000 | 100000
STATEWIDE | VARIOUS | NCDOT | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE REGIONAL TIER. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0521REG | REGION SW | T | [6 empty] | 2020 | 100000 | 100000
STATEWIDE | VARIOUS | NCDOT | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE STATEWIDE TIER. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0521SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 100000 | 100000
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0534 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0534DIV | DIVISION SW | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | NCDOT | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0534REG | REGION SW | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | NCDOT | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0534SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 12800000 | 12800000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0539
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0539DIV | DIVISION SW | T | [6 empty] | 2020 | 43200000 | 43200000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0539REG | REGION SW | T | [6 empty] | 2020 | 43200000 | 43200000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0539SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 57600000 | 57600000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552A
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552ADIV | DIVISION SW | T | [6 empty] | 2022 | 150000 | 150000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552AREG | REGION SW | T | [6 empty] | 2022 | 150000 | 150000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552ASW | STATEWIDE MOBILITY | T | [6 empty] | 2022 | 200000 | 200000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552B
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552BDIV | DIVISION SW | T | [6 empty] | 2022 | 324000 | 324000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552BREG | REGION SW | T | [6 empty] | 2022 | 324000 | 324000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552BSW | STATEWIDE MOBILITY | T | [6 empty] | 2022 | 432000 | 432000
STATEWIDE | VARIOUS | NCDOT | DIGITAL DELIVERY INITIATIVE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552C
STATEWIDE | VARIOUS | NCDOT | DIGITAL DELIVERY INITIATIVE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552CDIV | DIVISION SW | T | [6 empty] | 2023 | 150000 | 150000
STATEWIDE | VARIOUS | NCDOT | DIGITAL DELIVERY INITIATIVE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552CREG | REGION SW | T | [6 empty] | 2023 | 150000 | 150000
STATEWIDE | VARIOUS | NCDOT | DIGITAL DELIVERY INITIATIVE. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0552CSW | STATEWIDE MOBILITY | T | [6 empty] | 2023 | 200000 | 200000
STATEWIDE | VARIOUS | NCDOT | TECHNICAL SERVICES. PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0553 | EXEMPT
STATEWIDE | VARIOUS | NCDOT | INTEGRATED PROJECT DELIVERY | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0553A | EXEMPT | T | [6 empty] | 2022 | 10500000 | 10500000
STATEWIDE | VARIOUS | NCDOT | TRAINING AND SPECIAL PROJECTS | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0553B | EXEMPT | T | [6 empty] | 2022 | 2000000 | 2000000
STATEWIDE | VARIOUS | NCDOT | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0554
STATEWIDE | VARIOUS | NCDOT | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0554DIV | DIVISION SW | T | [6 empty] | 2022 | 105000000 | 105000000
STATEWIDE | VARIOUS | NCDOT | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0554REG | REGION SW | T | [6 empty] | 2022 | 105000000 | 105000000
STATEWIDE | VARIOUS | NCDOT | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0554SW | STATEWIDE MOBILITY | T | [6 empty] | 2022 | 140000000 | 140000000
STATEWIDE | VARIOUS | NCDOT | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0555
STATEWIDE | VARIOUS | NCDOT | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0555DIV | DIVISION SW | T |  |  | 2023 | 1365000 |  |  |  |  | 1365000
STATEWIDE | VARIOUS | NCDOT | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0555REG | REGION SW | T |  |  | 2023 | 1365000 |  |  |  |  | 1365000
STATEWIDE | VARIOUS | NCDOT | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0555SW | STATEWIDE MOBILITY | T |  |  | 2023 | 1820000 |  |  |  |  | 1820000
STATEWIDE | STATEWIDE | NCDOT | PROTECT FORMULA PLANNING FUNDING FOR RESILIENCE PROGRAM. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0557
STATEWIDE | STATEWIDE | NCDOT | HAZARD CHARACTERIZATION AND WARNING TOOLS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0557A | STATEWIDE MOBILITY | PROTCT | [6 empty] | 2023 | 3360000 | 3360000
STATEWIDE | STATEWIDE | NCDOT | HAZARD CORRIDOR VULNERABILITY ASSESSMENTS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0557B | STATEWIDE MOBILITY | PROTCT | [6 empty] | 2023 | 1400000 | 1400000
STATEWIDE | STATEWIDE | NCDOT | GEOTECHNICAL ASSET MANAGEMENT (GAM) DATABASE AND LANDSLIDE MITIGATION PLANNING | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-0557C | STATEWIDE MOBILITY | PROTCT | [6 empty] | 2023 | 2240000 | 2240000
STATEWIDE | STATEWIDE | NCDOT | ADVANCED RIGHT-OF-WAY ACQUISITION ACCOUNT. REVOLVING ACCOUNT TO FUND ADVANCED RIGHT-OF-WAY ACQUISITION. FUNDS TO BE REPAID FROM THE STIP PROJECT AT THE TIME THE PROJECT IS FUNDED. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | M-556
STATEWIDE | VARIOUS | NCDOT | ASPHALT MATERIALS TESTING LABORATORIES CORRECTIVE ACTION PLAN FOR GROUNDWATER CLEAN-UP AT 54 SITES. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-4073 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-4436 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-4436DIV | DIVISION SW | BG |  |  |  |  | 2020 | 900000 |  |  | 900000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-4436REG | REGION SW | BG |  |  |  |  | 2020 | 900000 |  |  | 900000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-4436SW | STATEWIDE MOBILITY | BG |  |  |  |  | 2020 | 1200000 |  |  | 1200000 | IN PROGRESS
STATEWIDE | VARIOUS | FHWA | FEDERAL LANDS TRANSPORTATION PROGRAM (FLTP) AND EMERGENCY RELIEF FOR FEDERALLY OWNED ROADS (ERFO). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO FEDERAL LANDS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-5753 | EXEMPT | ERFO, FLTP |  |  |  |  | 2020 | 90255000 |  |  | 90255000 | PROGRAM IN PROGRESS
STATEWIDE | VARIOUS | FHWA | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-5966 | EXEMPT | FTTP |  |  |  |  | 2023 | 16914000 |  |  | 16914000 | PROGRAM IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-5968
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-5968DIV | DIVISION SW | BGANY |  |  |  |  | 2020 | 14400000 |  |  | 14400000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-5968REG | REGION SW | BGANY |  |  |  |  | 2020 | 14400000 |  |  | 14400000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-5968SW | STATEWIDE MOBILITY | BGANY |  |  |  |  | 2020 | 19200000 |  |  | 19200000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-9999WM | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-9999WMDIV | DIVISION SW | NHP, T | [6 empty] | 2020 | 300000 | 300000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-9999WMREG | REGION SW | NHP, T | [6 empty] | 2020 | 300000 | 300000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | R-9999WMSW | STATEWIDE MOBILITY | NHP, T | [6 empty] | 2020 | 400000 | 400000
STATEWIDE | VARIOUS | NCDOT | SAFE ROUTES TO SCHOOL PROGRAM. EDUCATIONAL,TRAINING AND OTHER NON-INFRASTRUCTURE NEEDS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | SR-5000 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | SAFE ROUTES TO SCHOOL PROGRAM. PROJECTS TO IMPROVE SAFETY, REDUCE TRAFFIC, FUEL CONSUMPTION AND AIR POLLUTION IN VICINITY OF SCHOOLS. | HIGHWAY | OTHER | 99 | STATEWIDE PROJECT | SR-5001 | DIVISION SW | [10 empty] | IN PROGRESS - $200,800 IN STPDA FUNDS ALLOCATED TO SR-5001C
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. TRAFFIC ENGINEERING BRANCH TO PARTICIPATE IN A THREE YEAR DATA COLLECTION PROGRAM. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5508
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5517
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5517DIV | DIVISION SW
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5517REG | REGION SW
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5517SW | STATEWIDE MOBILITY
STATEWIDE | VARIOUS | NCDOT | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5601 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON DIVISION CATEGORY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5601DIV | DIVISION SW | HSIP | 2021 | 68000 |  |  | 2020 | 3670000 |  |  | 3738000
STATEWIDE | VARIOUS | NCDOT | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON REGIONAL CATEGORY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5601REG | REGION SW | HSIP | 2021 | 68000 |  |  | 2021 | 6170000 |  |  | 6238000
STATEWIDE | VARIOUS | NCDOT | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON STATWIDE CATEGORY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5601SW | STATEWIDE MOBILITY | HSIP | 2021 | 90000 |  |  | 2021 | 3360000 |  |  | 3450000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING TO IMPROVE SAFETY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5700 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING TO IMPROVE SAFETY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5700DIV | DIVISION SW
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING TO IMPROVE SAFETY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5700REG | REGION SW
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING TO IMPROVE SAFETY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5700SW | STATEWIDE MOBILITY
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5715
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5715DIV | DIVISION SW | HSIP | [6 empty] | 2020 | 9180000 | 9180000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5715REG | REGION SW | HSIP | [6 empty] | 2020 | 9180000 | 9180000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5715SW | STATEWIDE MOBILITY | HSIP | [6 empty] | 2020 | 12240000 | 12240000
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5716
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5716DIV | DIVISION SW | HSIP | [6 empty] | 2020 | 26400000 | 26400000
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5716REG | REGION SW | HSIP | [6 empty] | 2020 | 26400000 | 26400000
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5716SW | STATEWIDE MOBILITY | HSIP | [6 empty] | 2020 | 35200000 | 35200000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5717
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5717DIV | DIVISION SW | HSIP | [6 empty] | 2020 | 10200000 | 10200000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5717REG | REGION SW | HSIP | [6 empty] | 2020 | 10200000 | 10200000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-5717SW | STATEWIDE MOBILITY | HSIP | [6 empty] | 2020 | 13600000 | 13600000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-9999
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-9999DIV | DIVISION SW | HSIP |  |  |  |  | 2020 | 45163000 |  |  | 45163000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-9999REG | REGION SW | HSIP |  |  |  |  | 2020 | 55935000 |  |  | 55935000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | HIGHWAY | SAFETY | 99 | STATEWIDE PROJECT | W-9999SW | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2020 | 74580000 |  |  | 74580000
STATEWIDE | STATEWIDE | FTA | 5311 CAPITAL PROJECTS FOR RURAL AREAS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TA-6665 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2021 | 16554000 | 16554000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5339 BUS AND BUS FACILITIES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TA-6666 | PUBLIC TRANSIT | 5339 | [6 empty] | 2021 | 6750000 | 6750000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | NCDOT | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0003 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2023 | 1371000 | 1371000
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0005 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2022 | 2650000 |  |  | 2650000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0006 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2021 | 1819000 |  |  | 1819000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR CONSTRUCTION PROJECT | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0007 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 3976000 | 3976000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0008 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 10900000 | 10900000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0010 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2021 | 4069000 |  |  | 4069000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | NCDOT | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0011 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2023 | 719000 | 2021 | 8689000 | 9408000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT TO PURCHASE ELECTRIC BUSES AND CHARGING STATIONS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0012 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 3767000 | 3767000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | MOBILITY FROM ALL GRANT OPPORTUNITY FROM THE FTA.5310 DISCRETIONARY GRANT AWARDED BY FTA. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0013 | PUBLIC TRANSIT | 5310, S | [6 empty] | 2021 | 350000 | 350000
STATEWIDE | NCDOT | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL AND URBAN AREAS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0018 | PUBLIC TRANSIT | 5310, L, S | [6 empty] | 2022 | 7955000 | 7955000
STATEWIDE | NCDOT | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0019 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2022 | 17147000 | 17147000
STATEWIDE | NCDOT | FTA | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON FY 24 GRANTS | PUBLIC TRANSIT |  | 99 | STATEWIDE PROJECT | TC-0020 | PUBLIC TRANSIT | 5309, L, S | [6 empty] | 2023 | 425000 | 425000
STATEWIDE | NCDOT | NCDOT | 5339 STATEWIDE RURAL | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0021 | PUBLIC TRANSIT | 5339, BGDA, L, S | [6 empty] | 2022 | 9178000 | 9178000
STATEWIDE | NCDOT | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0022 | PUBLIC TRANSIT | ADTAP, L, S | [6 empty] | 2022 | 1880000 | 1880000
STATEWIDE | NCDOT | NCDOT | FEDERAL AMERICAN RESCUE PLAN (ARP) FUNDS FOR CAPITAL | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-0026 | PUBLIC TRANSIT | ARP | [6 empty] | 2023 | 500000 | 500000
STATEWIDE | STATEWIDE | FTA | 5311 ADTAP | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TC-5004 | PUBLIC TRANSIT | ADTAP | [6 empty] | 2021 | 3392000 | 3392000 | FUMODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | FY21 5307 SBUS CAPITAL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 99 | STATEWIDE PROJECT | TG-0002 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 21000 | 21000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | FY21 5307 SBUS CAPITAL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 99 | STATEWIDE PROJECT | TG-0004 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 168000 | 168000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | FY21 5307 SBUS CAPITAL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 99 | STATEWIDE PROJECT | TG-0005 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 168000 | 168000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | FY21 5307 SBUS CAPITAL | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 99 | STATEWIDE PROJECT | TG-0006 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 381000 | 381000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5311(F) INTERCITY BUS FUNDS FOR FTA GANTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TI-6109 | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 2698000 | 2698000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5311 STATE ADMINISTRATION AND 5311 STATE ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TK-4900Z | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 3080000 | 3080000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | STATE ADMINISTRATION OF APPALACHIAN DEVELOPMENT TRANSPORTATION ASSISTANCE PROGRAM | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TK-4902 | PUBLIC TRANSIT | ADTAP | [6 empty] | 2021 | 235000 | 235000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5311 ADMINISTRATIVE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TK-6181 | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 15025000 | 15025000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | NCDOT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311 ADMIN/OPERATING/CAPITAL AND 5311(F) | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0002 | PUBLIC TRANSIT | 5311 | [6 empty] | 2023 | 3950000 | 3950000
STATEWIDE | NCDOT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311CAPITAL-ADTAP) | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0004 | PUBLIC TRANSIT | 5311 | [6 empty] | 2023 | 150000 | 150000
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0010 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 142000 | 142000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0012 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 129000 | 129000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0014 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 75000 | 75000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0015 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 145000 | 145000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0020 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 2191000 | 2191000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0022 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 18000 | 18000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | NCDOT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5310 ADMIN/OPERATING/CAPITAL PURCHASE SERVICE) | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0023 | PUBLIC TRANSIT | 5310 | [6 empty] | 2023 | 1022000 | 1022000
STATEWIDE | STATEWIDE | FTA | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0024 | PUBLIC TRANSIT | 5312, L | [6 empty] | 2021 | 313000 | 313000
STATEWIDE | NCDOT | NCDOT | 5310 OPERATING PROJECTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0025 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2022 | 4212000 | 4212000
STATEWIDE | NCDOT | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0027 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2022 | 45430000 | 45430000
STATEWIDE | NCDOT | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0028 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2022 | 4348000 | 4348000
STATEWIDE | NCDOT | NCDOT | 5311 STATE ADMINISTRATIVE FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0029 | PUBLIC TRANSIT | 5311 | [6 empty] | 2022 | 3361000 | 3361000
STATEWIDE | NCDOT | NCDOT | 5311 ADTAP STATE ADMINISTRATIVE FUNDS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0030 | PUBLIC TRANSIT | ADTAP | [6 empty] | 2022 | 177000 | 177000
STATEWIDE | NCDOT | NCDOT | RTAP STATEWIDE FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0031 | PUBLIC TRANSIT | RTAP | [6 empty] | 2022 | 1628000 | 1628000
STATEWIDE | NCDOT | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0032 | PUBLIC TRANSIT | 5311, S | [6 empty] | 2022 | 29441000 | 29441000
STATEWIDE | NCDOT | NCDOT | 5311(F) INTERCITY BUS - STATE ADMIN | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0033 | PUBLIC TRANSIT | 5311 | [6 empty] | 2022 | 494000 | 494000
STATEWIDE | STATEWIDE | FTA | 5310 STATE ADMINISTRATIVE FUNDS. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0036 | PUBLIC TRANSIT | 5310 | [6 empty] | 2022 | 567000 | 567000
STATEWIDE | NCDOT | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS. (ARP/CRRSAA 5301 OPERATING) | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-0038 | PUBLIC TRANSIT | FEDT, S | [6 empty] | 2023 | 1501000 | 1501000
STATEWIDE | SUB REGIONAL | FTA | STATE ADMINISTRATION - JOB ACCESS NON-URBAN | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TM-5301 | PUBLIC TRANSIT | 5316 | [6 empty] | 2020 | 500000 | 500000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | SUB REGIONAL | FTA | STATE ADMINISTRATION - NEW FREEDOM - 5317 | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TN-5112 | PUBLIC TRANSIT | 5317 | [6 empty] | 2020 | 350000 | 350000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | STATEWIDE | FTA | 5317 NEW FREEDOM | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TN-6125 | PUBLIC TRANSIT | FEP, L | [6 empty] | 2020 | 4272000 | 4272000
STATEWIDE | STATEWIDE | FTA | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIGNS OF HUMAN TRAFFICKING. THE DEPARTMENT ALSO WILL DEVELOP HUMAN TRAFFICKING AWARENESS EDUCATIONAL MATERIALS TO BE POSTED ON TRANSIT VEHICLES AND STATIONS. | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 99 | STATEWIDE PROJECT | TO-0003 | PUBLIC TRANSIT | 5307, 5312 | [6 empty] | 2021 | 150000 | 150000
STATEWIDE | STATEWIDE | FTA | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 99 | STATEWIDE PROJECT | TO-0004 | PUBLIC TRANSIT | S, SSO | [6 empty] | 2021 | 880000 | 880000 | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD.
STATEWIDE | STATEWIDE | FTA | 5311 OPERATING FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 99 | STATEWIDE PROJECT | TO-6135 | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 947000 | 947000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS - OPERATING | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 99 | BURLINGTON-GRAHAM MPO, CHARLOTTE REGIONAL TPO, FAYETTEVILLE AREA MPO, HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | TO-6142 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 11230000 | 11230000
STATEWIDE | STATEWIDE | FTA | 5311 OPERATING AND 5311 OPERATING F | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 99 | STATEWIDE PROJECT | TO-6155 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 154320000 | 154320000
STATEWIDE | REGIONAL COORDINATED AREA TRANSPORTION | REGIONAL COORDINATED AREA TRANSPORTION | PLANNING ASSISTANCE - RESEARCH SUPPORT ACTIVITIES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TP-4901 | PUBLIC TRANSIT | FSPR, S | [6 empty] | 2020 | 720000 | 720000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | STATEWIDE | FTA | 5304 PLANNING | PUBLIC TRANSIT | PLANNING | 99 | STATEWIDE PROJECT | TP-5154 | PUBLIC TRANSIT | 5303, L | [6 empty] | 2020 | 5136000 | 5136000
STATEWIDE | STATEWIDE | FTA | 5310 OPERATING PROJECTS FOR RURAL AREAS | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TQ-6954 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2021 | 8935000 | 8935000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5310 CAPITAL PROJECTS FOR RURAL AREAS AND SMALL URBAN AREAS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 99 | STATEWIDE PROJECT | TQ-9038 | PUBLIC TRANSIT | 5310 | [6 empty] | 2021 | 2850000 | 2850000 | MODIFYING THE FEDERAL FUND S RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | STATEWIDE RTAP | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TS-4900Z | PUBLIC TRANSIT | RTAP | [6 empty] | 2021 | 480000 | 480000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5329 STATE SAFETY AND OVERSIGHT | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TS-7001 | PUBLIC TRANSIT | FED, L, S | [6 empty] | 2020 | 4676000 | 4676000
STATEWIDE | NCDOT | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. | PUBLIC TRANSIT | PLANNING | 99 | STATEWIDE PROJECT | TU-0003 | PUBLIC TRANSIT | 5303, 5312, S | [6 empty] | 2021 | 222000 | 222000 | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD.
STATEWIDE | NCDOT | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | PLANNING | 99 | STATEWIDE PROJECT | TU-0005 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2022 | 10809000 | 10809000
STATEWIDE | NCDOT | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. | PUBLIC TRANSIT | PLANNING | 99 | STATEWIDE PROJECT | TU-0008 | PUBLIC TRANSIT | 5311, S | [6 empty] | 2022 | 588000 | 588000
STATEWIDE | NCDOT | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. | PUBLIC TRANSIT | PLANNING | 99 | STATEWIDE PROJECT | TU-0009 | PUBLIC TRANSIT | RTAP | [6 empty] | 2022 | 765000 | 765000
STATEWIDE | NCDOT | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TU-0011 | PUBLIC TRANSIT | 5303, L | [6 empty] | 2022 | 3431000 | 3431000
STATEWIDE | NCDOT | NCDOT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY. PLANNING STUDY ON THE TRANSITION TO ZERO EMISSIONS LIGHT AND HEAVY DUTY PASSENGER VEHICLES. THE TRANSITION PLAN IS AREQUIREMENT BY FTA TO APPLY FOR GRANT FUNDS SUPPORTING ANY ZEV PROJECTS, INCLUDING VEHICLES AND ALL RELATED INFRASTRUCTURE. | PUBLIC TRANSIT | PLANNING | 99 | STATEWIDE PROJECT | TU-0012 | PUBLIC TRANSIT | 5303, L | [6 empty] | 2023 | 100000 | 100000
STATEWIDE | NCDOT | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. | PUBLIC TRANSIT | PLANNING | 99 | STATEWIDE PROJECT | TU-0014 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2023 | 634000 | 634000
STATEWIDE | NCDOT | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO THE DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. | PUBLIC TRANSIT | PLANNING | 99 | STATEWIDE PROJECT | TU-0015 | PUBLIC TRANSIT | RTAP | [6 empty] | 2023 | 73000 | 73000
STATEWIDE | SUB REGIONAL | FTA | 5310 STATE ADMIN | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 99 | STATEWIDE PROJECT | TV-4903 | PUBLIC TRANSIT | 5310 | [6 empty] | 2021 | 450000 | 450000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STATEWIDE RAIL PRELIMINARY ENGINEERING | RAIL | OTHER | 99 | STATEWIDE PROJECT | P-5602 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STATEWIDE RAIL PRELIMINARY ENGINEERING | RAIL | OTHER | 99 | STATEWIDE PROJECT | P-5602DIV | DIVISION SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE RAIL PRELIMINARY ENGINEERING | RAIL | OTHER | 99 | STATEWIDE PROJECT | P-5602REG | REGION SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE RAIL PRELIMINARY ENGINEERING | RAIL | OTHER | 99 | STATEWIDE PROJECT | P-5602SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 6400000 | 6400000
STATEWIDE | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES PROGRAM ADMINISTRATION | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 99 | STATEWIDE PROJECT | RC-2000 | STATEWIDE MOBILITY | [10 empty] | PROGRAMMED FOR PLANNING ONLY.
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS PROGRAM ADMINISTRATION. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 99 | STATEWIDE PROJECT | RX-2000 | STATEWIDE MOBILITY | [10 empty] | PROGRAMMED FOR PLANNING ONLY.
STATEWIDE | VARIOUS | NCDOT | PASSENGER RAIL CROSSING SAFETY IMPROVEMENT INVENTORY PROGRAM | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 99 | STATEWIDE PROJECT | RX-2100 | DIVISION SW | RR | [6 empty] | 2021 | 2500000 | 2500000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY
STATEWIDE | VARIOUS | NCDOT | RAILWAY-HIGHWAY CROSSINGS PROGRAM - UNPROGRAMMED BALANCE | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 99 | STATEWIDE PROJECT | RX-9999 | DIVISION SW | RR |  |  |  |  | 2024 | 85008000 |  |  | 85008000
STATEWIDE | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 99 | STATEWIDE PROJECT | Y-5500 | DIVISION SW | RR | 2021 | 1500000 |  |  | 2020 | 7560000 |  |  | 9060000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 99 | STATEWIDE PROJECT | Z-5400 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 99 | STATEWIDE PROJECT | Z-5700 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 99 | STATEWIDE PROJECT | Z-5800 | DIVISION SW | RR | 2021 | 500000 |  |  | 2020 | 3280000 |  |  | 3780000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS - UNPROGRAMMED BALANCE. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 99 | STATEWIDE PROJECT | Z-9999 | DIVISION SW | RR | 2023 | 500000 |  |  | 2023 | 3000000 |  |  | 3500000
STOKES | US 311 | NCDOT | NC 65 IN WALNUT COVE. UPGRADE INTERSECTION AND IMPROVE RAILROAD CROSSING. | HIGHWAY | STI (PRIORITIZATION) | 9 | NORTHWEST PIEDMONT RPO | R-5768 | DIVISION 9 | BGLT5, T |  |  |  |  | 2023 | 3800000 |  |  | 3800000 | UNDER CONSTRUCTION
STOKES | US 311 (NORTH MAIN STREET) | NCDOT | SR 1918 (FIRST STREET) IN WALNUT COVE. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 9 | NORTHWEST PIEDMONT RPO | R-5828 | DIVISION 9 | T |  |  |  |  | 2022 | 3050000 |  |  | 3050000 | UNDER CONSTRUCTION
SURRY | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | CONSTRUCT GENERAL AVIATION APRON AND AIRCRAFT STORAGE HANGARS. | AVIATION | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | AV-5859 | DIVISION 11 | T |  |  |  |  | 2020 | 4000000 |  |  | 4000000 | COMPLETE.
SURRY | MOUNT AIRY | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | EB-5845 | DIVISION 11 | L, TA5200 | 2023 | 161000 |  |  | 2024 | 430000 | 2022 | 192000 | 783000
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | ELKIN | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | BIKE/PED | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | EB-5961 | DIVISION 11 | L, TA5200 | 2023 | 53000 |  |  | 2024 | 175000 | 2022 | 63000 | 291000
SURRY | I-77 NORTHBOUND | NCDOT | REPLACE BRIDGE 850006 OVER NC 268, NORFOLK SOUTHERN RAILROAD, AND THE YADKIN RIVER. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | B-5831 | STATEWIDE MOBILITY | BFP | 2024 | 260000 |  |  | 2031 | 15300000 |  |  | 15560000
SURRY | SR 2080 (QUAKER CHURCH ROAD) | NCDOT | REPLACE BRIDGE 850152 OVER ARARAT RIVER. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | B-5832 | DIVISION 11 | BGOFF | 2024 | 200000 |  |  | 2030 | 3600000 |  |  | 3800000
SURRY | SR 1149 (ELK SPUR STREET) | NCDOT | REPLACE BRIDGE 850387 OVER ELKIN CREEK. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | B-5971 | DIVISION 11 | BGOFF | 2026 | 300000 |  |  | 2027 | 6400000 |  |  | 6700000
SURRY | SR 2081 | NCDOT | REPLACE BRIDGE 850153 OVER HOGAN CREEK. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | BR-0210 | HIGHWAY FUND | DP |  |  |  |  | 2020 | 875000 |  |  | 875000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING
SURRY | I-77 | NCDOT | MILE MARKER 91 TO MILE MARKER 95. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 11 | NORTHWEST PIEDMONT RPO | I-5829 | [11 empty] | UNDER CONSTRUCTION
SURRY | I-77 | NCDOT | MILE MARKER 91 TO MILE MARKER 95. DIAMOND GRINDING | HIGHWAY | INTERSTATE MAINTENANCE | 11 | NORTHWEST PIEDMONT RPO | I-5829A | STATEWIDE MOBILITY | T |  |  |  |  | 2022 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION.
SURRY | I-74 | NCDOT | I-77 TO US 601. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 11 | NORTHWEST PIEDMONT RPO | I-5907 | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2022 | 5543000 |  |  | 5543000 | UNDER CONSTRUCTION.
SURRY | US 601 | NCDOT | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5714 | REGION F | T | 2019 | 1615000 |  |  | 2025 | 11700000 |  |  | 13315000 | RIGHT-OF-WAY IN PROGRESS
SURRY | US 601 | NCDOT | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5836 | DIVISION 11 | BGANY, T | 2024 | 3100000 | 2024 | 1700000 | 2026 | 81968000 |  |  | 86768000 | BUILD NC BONDS: $16M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE)
SURRY | NC 103 (EAST PINE STREET) | NCDOT | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5895 | NOT FUNDED | T | NOT FUNDED | 2700000 | NOT FUNDED | 390000 | NOT FUNDED | 1600000 |  |  | 4690000
SURRY | NC 89 (WEST PINE STREET) | NCDOT | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5901 | REGION F | BGLT5 | 2024 | 500000 | 2024 | 100000 | 2026 | 5200000 |  |  | 5800000
SURRY | NC 89 (WEST PINE STREET) | NCDOT | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5905 | DIVISION 11 | BG5200 | 2025 | 5899000 | 2025 | 5800000 | 2027 | 38501000 |  |  | 50200000
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | NCDOT | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5910 | DIVISION 11 | BG5200 | 2022 | 400000 | 2022 | 400000 | 2023 | 1800000 |  |  | 2600000 | UNDER CONSTRUCTION.
SURRY, YADKIN | US 21 BUSINESS | NCDOT | BRIDGE #850021 OVER YADKIN RIVER. REHABILITATE STRUCTURE AND WIDEN SIDEWALKS. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | R-5913B | HIGHWAY FUND | HFB |  |  |  |  | 2025 | 1400000 |  |  | 1400000
SWAIN | NC 28 | NCDOT | SR 1121 (WATTIA ROAD) AT ALMONDS TO EXISTING US 19/NC 28 | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009DA | [11 empty] | COMPLETE
SWAIN | GREAT SMOKY MOUNTAINS NATIONAL PARK | NCDOT | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. | HIGHWAY | OTHER | 14 | SOUTHWESTERN RPO | HO-0004 | EXEMPT | CMAQ, L | [6 empty] | 2022 | 250000 | 250000
SWAIN | US 19 | NCDOT | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-4751 | NOT FUNDED | T | NOT FUNDED | 25000000 | NOT FUNDED | 4900000 | NOT FUNDED | 75000000 |  |  | 104900000
SWAIN | NC 28 | NCDOT | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5839A | NOT FUNDED | T | NOT FUNDED | 1520000 | NOT FUNDED | 200000 | NOT FUNDED | 312700000 |  |  | 314420000
SWAIN | SR 1321 (BRYSON WALK), SR 1336 (DEPOT STREET) | NCDOT | SR 1323 (SLOPE STREET) TO SR 1336 (DEEP CREEK ROAD). IMPROVE INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 14 | SOUTHWESTERN RPO | R-5843 | DIVISION 14 | T |  |  |  |  | 2022 | 3629000 |  |  | 3629000 | UNDER CONSTRUCTION.
SWAIN | SWAIN COUNTY FOCAL POINT ON AGING, INC. | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | SOUTHWESTERN RPO | TK-6165 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 508000 | 508000 | FUNDS AUTHORIZED IN PROGRESS
SWAIN, GRAHAM | NC 28 | NCDOT | EAST OF CALFPEN GAP IN GRAHAM COUNTY TO SR 1121 (WATTIA ROAD) AT ALMONDS IN SWAIN COUNTY | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | SOUTHWESTERN RPO | A-0009DB | [11 empty] | COMPLETE
TRANSYLVANIA | ECUSTA TRAIL | NCDOT | TRANSYLVANIA COUNTY LINE TO LAMB CREEK. CONSTRUCT GREENWAY. | BIKE/PED | FEDERAL LANDS ACCESS PROGRAM | 14 | LAND-OF-SKY RPO | BF-0002 | EXEMPT | FLAP | [6 empty] | 2023 | 1000000 | 1000000 | FLAP PROJECT NC 61. PE AWARDED $1.0M.
TRANSYLVANIA | BREVARD | NCDOT | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | BIKE/PED | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO | EB-5858 | DIVISION 14 | L, TA5200 | 2022 | 20000 | 2022 | 140000 | 2022 | 1200000 | 2022 | 820000 | 2180000 | UNDER CONSTRUCTION.
TRANSYLVANIA | SR 1532 (ISLAND COVE ROAD) | NCDOT | REPLACE BRIDGE 870196 OVER CRAB CREEK. | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | B-5403 | DIVISION 14 | [10 empty] | COMPLETE
TRANSYLVANIA | BREVARD | BREVARD | REPLACE BRIDGE 870102 ON RAILROAD AVENUE OVER KINGS CREEK. | HIGHWAY | MUNICIPAL BRIDGE | 14 | LAND-OF-SKY RPO | B-5550 | DIVISION 14 | BFPOFF |  |  |  |  | 2023 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF BREVARD
TRANSYLVANIA | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | NCDOT | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | HIGHWAY | APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM | 14 | LAND-OF-SKY RPO | HA-0002 | EXEMPT | ADHSL | 2022 | 10000 |  |  | 2023 | 686000 | 2021 | 200000 | 896000 | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610
TRANSYLVANIA | SR 1533 (EVERETT ROAD) | NCDOT | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | HIGHWAY | BRIDGES | 14 | LAND-OF-SKY RPO | HB-0026 | DIVISION 14 | BGOFF | 2024 | 200000 | 2024 | 200000 | 2028 | 4000000 |  |  | 4400000
TRANSYLVANIA | (FISH HATCHERY ROAD) SR 1408 | NCDOT | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | HIGHWAY | FEDERAL LANDS ACCESS PROGRAM | 14 | LAND-OF-SKY RPO | HF-0002 | EXEMPT | FLAP, S(M) |  |  |  |  | 2023 | 230000 | 2022 | 10000 | 240000 | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS.
TRANSYLVANIA | US 276 | NCDOT | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | HIGHWAY | FEDERAL LANDS ACCESS PROGRAM | 14 | LAND-OF-SKY RPO | HF-0004 | EXEMPT | FLAP, S(M) |  |  |  |  | 2024 | 495000 | 2022 | 30000 | 525000 | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. STATE MATCH ARE HIGHWAY FUNDS.
TRANSYLVANIA | US 64 (ASHEVILLE HIGHWAY) | NCDOT | SR 1592 (HOSPITAL DRIVE)/ STRAUS PARKWAY. UPGRADE INTERSECTION. | HIGHWAY | SAFETY | 14 | LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO | HS-2014M | REGION G | HSIP |  |  |  |  | 2023 | 225000 |  |  | 225000
TRANSYLVANIA | US 64 | NCDOT | WEST OF NC 281 N NEAR LAKE TOXAWAY TO INDIAN CREEK. WIDENING AND REALIGNMENT. | HIGHWAY | TRANSITION | 14 | LAND-OF-SKY RPO | R-2409C | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
TRANSYLVANIA | US 64 | NCDOT | INDIAN CREEK TO FLAT CREEK VALLEY ROAD. WIDENING AND REALIGNMENT | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO | R-2409D | NOT FUNDED | BGLT5 | NOT FUNDED | 1000000 |  |  | NOT FUNDED | 5000000 |  |  | 6000000
TRANSYLVANIA | DAVIDSON RIVER VILLAGE CONNECTOR | NCDOT | US 64 TO US 276/US 64 IN PISGAH FOREST. | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO | R-5605 | DIVISION 14 | T |  |  |  |  | 2020 | 3345000 |  |  | 3345000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2.592M FOR CON, PAYBACK FY 2020-2034 (FY 2019/ YR 1 SALE)
TRANSYLVANIA | SR 1540 (WILSON ROAD) | NCDOT | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO | R-5763 | DIVISION 14 | T | 2022 | 17400000 | 2022 | 2400000 | 2025 | 40200000 |  |  | 60000000 | RIGHT-OF-WAY IN PROGRESS
TRANSYLVANIA | US 64 | NCDOT | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO | R-5799 | REGION G | T | 2022 | 5890000 | 2022 | 600000 | 2024 | 16000000 |  |  | 22490000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
TRANSYLVANIA | US 64, US 276 | NCDOT | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO | R-5800 | REGION G | T | 2023 | 14799000 | 2023 | 3900000 | 2025 | 17802000 |  |  | 36501000 | RIGHT-OF-WAY IN PROGRESS
TRANSYLVANIA | US 276 | NCDOT | US 64 TO AVERY CREEK TRAIL HEAD. WIDEN TO 3-LANES WITH BICYCLE LANES. NC FLAP DOT 276(1). | HIGHWAY | FEDERAL LANDS ACCESS PROGRAM | 14 | LAND-OF-SKY RPO | R-5865 | EXEMPT | FLAP, S(M) |  |  |  |  | 2034 | 3147000 |  |  | 3147000 | STATE MATCHING FUNDS FROM DIVISION 14 MAINTENANCE FUNDING; FLAP PROJECT NC 35.
TRANSYLVANIA | US 64 (SOUTH BROAD STREET) | NCDOT | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO | R-5882 | NOT FUNDED | T | NOT FUNDED | 4400000 | NOT FUNDED | 1200000 | NOT FUNDED | 1900000 |  |  | 7500000
TRANSYLVANIA | US 178 | NCDOT | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO | R-5919 | DIVISION 14 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 710000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 280000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22400000 |  |  | 23390000
TRANSYLVANIA | TRANSYLVANIA COUNTY | TRANSYLVANIA COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 14 | LAND-OF-SKY RPO | TK-6167 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 644000 | 644000 | FUNDS AUTHORIZED IN PROGRESS
TRANSYLVANIA, JACKSON | US 64 | NCDOT | NC 107 AT CASHIERS TO US 178 AT ROSMAN. SAFETY IMPROVEMENTS AND CLIMBING LANES AT SELECTED LOCATIONS. | HIGHWAY | STI (PRIORITIZATION) | 14 | LAND-OF-SKY RPO, SOUTHWESTERN RPO | R-2409 | [11 empty] | DIVISION PROJECT
TYRRELL | US 64 | NCDOT | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | HIGHWAY | BRIDGES | 1 | ALBEMARLE RPO | HB-0001 | STATEWIDE MOBILITY | BFP, DP, HFB, T | 2023 | 500000 | 2023 | 500000 | 2024 | 262000000 |  |  | 263000000 | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS.
TYRRELL | US 64 | NCDOT | EAST OF COLUMBIA TO WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2545AA | NOT FUNDED | T | NOT FUNDED | 1825000 | NOT FUNDED | 1395000 | NOT FUNDED | 24800000 |  |  | 28020000
TYRRELL | US 64 | NCDOT | WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER TO WEST OF ALLIGATOR RIVER. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2545AB | NOT FUNDED | T | NOT FUNDED | 2025000 | NOT FUNDED | 1611000 | NOT FUNDED | 72500000 |  |  | 76136000
TYRRELL | US 64 | NCDOT | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5940 | DIVISION 1 | NHP | 2028 | 900000 | 2028 | 9100000 | 2032 | 47100000 |  |  | 57100000
TYRRELL | TYRELL COUNTY | TYRELL COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1 | ALBEMARLE RPO | TK-6168 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 88000 | 88000 | FUNDS AUTHORIZED IN PROGRESS
TYRRELL, DARE | US 64 | NCDOT | EAST OF COLUMBIA TO EAST OF THE ALLIGATOR RIVER. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-2545 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
UNION | CHARLOTTE-MONROE EXECUTIVE AIRPORT (EQY) | CHARLOTTE-MONROE EXECUTIVE AIRPORT (EQY) | RELOCATE AND WIDEN THE EXISTING PARALLEL TAXIWAY SECTION BETWEEN THE EXISTING RAMP AND THE RUNWAY 5 TAXIWAY EXTENSION. | AVIATION | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | AV-5814 | DIVISION 10 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8800000 |  |  | 8800000
UNION | MARSHVILLE | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0011 | DIVISION 10 | BGDA, L |  |  |  |  | 2024 | 335000 | 2023 | 63000 | 398000
UNION | MARVIN LOOP TRAIL | MARVIN | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | BL-0012 | DIVISION 10 | BGDA, L, TADA | 2024 | 157000 |  |  | 2025 | 1309000 | 2023 | 244000 | 1710000
UNION | US 74 | INDIAN TRAIL | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). CONSTRUCT A MULTI-USE PATH. SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | EB-5723 | DIVISION 10 | CMAQ, L, TAANY | 2023 | 125000 |  |  | 2023 | 3930000 |  |  | 4055000 | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | WAXHAW | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5819 | DIVISION 10 | BGDA, L |  |  |  |  | 2023 | 766000 |  |  | 766000 | UNDER CONSTRUCTION.
UNION | INDIAN TRAIL | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). | BIKE/PED | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5931 | DIVISION 10 | BGDA, CMAQ, L | 2023 | 260000 |  |  | 2023 | 6622000 | 2020 | 391000 | 7273000 | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
UNION | SR 1681 (OLD CAMDEN ROAD) | NCDOT | REPLACE BRIDGE 890021 OVER STEWART'S CREEK. | HIGHWAY | BRIDGES | 10 | CHARLOTTE REGIONAL TPO | B-5376 | DIVISION 10 | BGOFF | 2023 | 210000 |  |  | 2028 | 2100000 |  |  | 2310000 | RIGHT-OF-WAY IN PROGRESS.
UNION | SR 2111 (BELK MILL ROAD) | NCDOT | REPLACE BRIDGE 890129 OVER LANES CREEK. | HIGHWAY | BRIDGES | 10 | ROCKY RIVER RPO | B-5806 | DIVISION 10 | BGOFF |  |  |  |  | 2022 | 1242000 |  |  | 1242000 | UNDER CONSTRUCTION.
UNION | NC 200 | NCDOT | REPLACE BRIDGE 890053 OVER STEWARTS CREEK. | HIGHWAY | BRIDGES | 10 | CHARLOTTE REGIONAL TPO | B-5949 | REGION E | BFP | 2024 | 120000 |  |  | 2027 | 2500000 |  |  | 2620000
UNION | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | HIGHWAY | OTHER | 10 | ROCKY RIVER RPO | C-5617 | EXEMPT | CMAQ, L | 2020 | 6000 |  |  | 2020 | 38000 | 2020 | 18000 | 62000
UNION | WAXHAW | WAXHAW | NC 16 TO SUNSET HILL ROAD. KENSINGTON DRIVE CORRIDOR IMPROVEMENT PROJECT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | EB-5950 | DIVISION 10 | BGDA, L | 2022 | 591000 |  |  | 2024 | 3818000 |  |  | 4409000 | RIGHT-OF-WAY IN PROGRESS.
UNION | VARIOUS | NCDOT | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, AND PAVEMENT RESTRIPING. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0039
UNION | NORTH CHARLOTTE AVENUE AND NEW TOWN ROAD | NCDOT | NORTH CHARLOTTE AVENUE FROM WALNUT STREET TO NC 200 AND NEW TOWN ROAD FROM CUTHBERTSON ROAD TO ENNIS ROAD. RESURFACE ROADWAYS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0039A | DIVISION 10 | BGDACV |  |  |  |  | 2022 | 938000 |  |  | 938000 | UNDER CONSTRUCTION.
UNION | VARIOUS | NCDOT | REPLACE PAVEMENT MARKINGS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0039B | EXEMPT | BGDACV |  |  |  |  | 2022 | 126000 |  |  | 126000 | COMPLETE.
UNION | VARIOUS | NCDOT | REPLACE TRAFFIC SIGNAL LOOPS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0039C | EXEMPT | BGDACV |  |  |  |  | 2023 | 189000 |  |  | 189000 | UNDER CONSTRUCTION.
UNION | SR 1357 (POTTER ROAD) | NCDOT | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0055 | DIVISION 10 | L, T(DA) | 2024 | 643000 |  |  | 2025 | 1373000 | 2023 | 475000 | 2491000 | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP.
UNION | STREET) NC 16 (NORTH BROOME | WAXHAW | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMRPOVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0115 | DIVISION 10 | BGDA, L | 2027 | 517000 |  |  | 2029 | 3099000 | 2025 | 461000 | 4077000
UNION | BONDS GROVE CHURCH ROAD | UNION COUNTY | WAXAHW MARVIN ROAD. INSTALL ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0116 | EXEMPT | CMAQ, L | 2026 | 595000 |  |  | 2028 | 4427000 | 2024 | 438000 | 5460000
UNION | NC 218 | UNION COUNTY | LOVE MILL ROAD. INSTALL ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | HL-0117 | EXEMPT | CMAQ, L | 2024 | 308000 |  |  | 2026 | 2349000 | 2023 | 200000 | 2857000
UNION | NC 16 (PROVIDENCE ROAD) | NCDOT | SR 1307 (BONDS GROVE CHURCH ROAD) INTERSECTION NEAR MARVIN. WIDEN ROAD, ADD TURN LANE, AND INSTALL TRAFFIC SIGNAL. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | HS-2010I | REGION E | HSIP | 2024 | 120000 | 2024 | 120000 | 2025 | 859000 |  |  | 1099000
UNION | NC 84 | NCDOT | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-3467 | REGION E | BGANY | 2024 | 70000000 | 2024 | 3000000 | 2027 | 44899000 |  |  | 117899000
UNION | US 601 | NCDOT | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4024 | REGION E | T | 2028 | 3300000 | 2028 | 400000 | 2030 | 13699000 |  |  | 17399000 | COORDINATE WITH U-5723
UNION | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4714B | DIVISION 10 | BGANY, BGDA, O, S(M), T | 2021 | 46000000 | 2021 | 2300000 | 2025 | 51675000 |  |  | 99975000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE).
UNION | STALLINGS | NCDOT | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | HIGHWAY | TRANSITION | 10 | CHARLOTTE REGIONAL TPO | U-5112 | PRE-STI (TRANSITION) | BGDA, CMAQ, HSIP, L | 2021 | 676000 |  |  | 2024 | 4571000 |  |  | 5247000 | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | US 74 (ROOSEVELT BOULEVARD) | NCDOT | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO REDUCED CONFLICT INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5703 | [11 empty] | OTHER FUNDS PROVIDED BY THE CITY OF MONROE
UNION | US 74 (ROOSEVELT BLVD) | NCDOT | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO REDUCED CONFLICT INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5703A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
UNION | US 74 (ROOSEVELT BLVD) | NCDOT | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5703B | STATEWIDE MOBILITY | O, T | 2023 | 3457000 | 2023 | 325000 | 2026 | 1741000 |  |  | 5523000 | RIGHT-OF-WAY IN PROGRESS.
UNION | US 74 | NCDOT | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5723 | STATEWIDE MOBILITY | T |  |  |  |  | 2026 | 15000000 |  |  | 15000000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024
UNION | US 74 | NCDOT | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5764 | REGION E | T | 2025 | 24501000 | 2025 | 2700000 | 2028 | 43399000 |  |  | 70600000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | NCDOT | SR 1316 (REA ROAD EXTENSION) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5769
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | NCDOT | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5769A | REGION E | T | 2024 | 5701000 | 2024 | 3400000 | 2028 | 26402000 |  |  | 35503000
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | NCDOT | SR 1307 (BONDS GROVE CHURCH RD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5769AA | REGION E | HSIP, T | 2023 | 4000000 | 2024 | 1000000 | 2025 | 1225000 |  |  | 6225000
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | NCDOT | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5769B | REGION E | T | 2024 | 15500000 | 2024 | 2800000 | 2028 | 31400000 |  |  | 49700000
UNION | SR 1362 (CHESTNUT LANE CONNECTOR) | NCDOT | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5808 | DIVISION 10 | T | 2019 | 1615000 | 2019 | 1200000 | 2024 | 13501000 |  |  | 16316000 | RIGHT-OF-WAY IN PROGRESS
UNION | US 74 | NCDOT | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-5931 | STATEWIDE MOBILITY | T | 2025 | 1099000 | 2025 | 1000000 | 2028 | 4600000 |  |  | 6699000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764.
UNION | INDIAN TRAIL | INDIAN TRAIL | UNIONVILLE-INDIAN TRAIL ROAD AND SARDIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-5987 | DIVISION 10 | BGDA, CMAQ, L | 2020 | 25000 |  |  | 2020 | 3796000 |  |  | 3821000 | COMPLETE. $1.68M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES.
UNION | SR 1009 (CHARLOTTE AVENUE) | NCDOT | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6031 | DIVISION 10 | T | 2028 | 7700000 | 2028 | 4500000 | 2030 | 10101000 |  |  | 22301000
UNION | WESLEY CHAPEL | NCDOT | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6087 | DIVISION 10 | BGDA, CMAQ, L, S(M) |  |  |  |  | 2024 | 1880000 |  |  | 1880000 | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP.
UNION | MARVIN | NCDOT | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6088 | DIVISION 10 | BGDA, CMAQ, L, S(M) |  |  |  |  | 2023 | 1943000 |  |  | 1943000 | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP.
UNION | WEDDINGTON | NCDOT | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6090 | DIVISION 10 | CMAQ, L, S(M) | 2020 | 261000 |  |  | 2022 | 2443000 | 2020 | 391000 | 3095000 | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | STALLINGS | NCDOT | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6091 | DIVISION 10 | CMAQ, L, O, S(M) | 2020 | 450000 |  |  | 2022 | 2425000 | 2020 | 375000 | 3250000 | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT.
UNION | SR 1009 (OLD MONROE ROAD) | NCDOT | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6169 | NOT FUNDED | BGANY | NOT FUNDED | 3000000 | NOT FUNDED | 2800000 | NOT FUNDED | 26100000 |  |  | 31900000
UNION | SR 1004 (LAWYERS ROAD) | NCDOT | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-6170 | DIVISION 10 | BGANY | 2027 | 3000000 | 2027 | 1400000 | 2029 | 8800000 |  |  | 13200000
UNION | NC 84 | NCDOT | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6246 | EXEMPT | BGDA, L, S(M) | 2024 | 350000 |  |  | 2025 | 2080000 | 2022 | 200000 | 2630000 | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS.
UNION | NC 84 | NCDOT | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6247 | EXEMPT | BGDA, L, S(M) | 2024 | 270000 |  |  | 2026 | 2555000 | 2021 | 363000 | 3188000 | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
UNION | NC 75 | NCDOT | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | U-6248 | EXEMPT | L, T(DA) | 2024 | 1598000 |  |  | 2025 | 3543000 | 2021 | 200000 | 5341000 | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
UNION | VARIOUS | NCDOT | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN STATEWIDE CATEGORY. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | W-5210SW | STATEWIDE MOBILITY
UNION | SR 1005 (LANDSFORD ROAD) | NCDOT | SR 1937 (OLD PAGELAND MARSHVILLE ROAD). INSTALL AN ALL WAY STOP. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | W-5710AD | DIVISION 10 | HSIP |  |  |  |  | 2024 | 30000 |  |  | 30000
UNION | NC 200 (LANCASTER HIGHWAY) | NCDOT | SR 1137 (POTTER ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | W-5710AH | REGION E | HSIP |  |  |  |  | 2024 | 2200000 |  |  | 2200000
UNION | SR 1009 (OLD CHARLOTTE HIGHWAY) | NCDOT | WILLIAMS ROAD IN MONROE. CONSTRUCT SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | W-5710AN | DIVISION 10 | HSIP |  |  |  |  | 2024 | 570000 |  |  | 570000
UNION | UNION COUNTY | NCDOT | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | W-5710Y | DIVISION 10 | BGANY, HSIP, S(M) |  |  |  |  | 2021 | 2581000 |  |  | 2581000 | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP.
UNION | UNION COUNTY | NCDOT | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | W-5710Z | REGION E | BGANY, BGDA, HSIP, L, S(M) | 2020 | 35000 |  |  | 2022 | 2571000 | 2020 | 195000 | 2801000 | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP.
UNION | UNION COUNTY | UNION COUNTY | 5307 FUNDS TO REH/REN EQUIPMENT FFY20-21 (20-SU-089) | PUBLIC TRANSIT | CAPITAL (NON-STI) | 10 | CHARLOTTE REGIONAL TPO | TA-6149 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 17000 | 17000 | ADD FUNDING TO FY20
UNION | UNION COUNTY | UNION COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 10 | ROCKY RIVER RPO | TK-6169 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 732000 | 732000 | FUNDS AUTHORIZED IN PROGRESS
UNION | INDIAN TRAIL | INDIAN TRAIL | INSTALL TYPE TWO ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSINGS PATH PARK. | PUBLIC TRANSIT | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | TL-0030 | DIVISION 10 | CRPDA, L |  |  |  |  | 2023 | 585000 |  |  | 585000
UNION | UNION COUNTY TRANSPORTATION | UNION COUNTY TRANSPORTATION | LOW EMISSION ALTERNATIVE FUEL CONVERSION (MOTOR POOL FACILITY). | PUBLIC TRANSIT | LOCALLY SELECTED | 10 | CHARLOTTE REGIONAL TPO | TL-0031 | DIVISION 10 | CRPDA, L |  |  |  |  | 2024 | 200000 |  |  | 200000
UNION | UNION COUNTY | UNION COUNTY | 5307 OPERATIONS FOR FFY20-21 (20-LU-089) | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 10 | CHARLOTTE REGIONAL TPO | TO-6156 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1566000 | 1566000 | ADDING FUNDS FOR FFY20-21
UNION | CSX SF LINE | CSXT RR | MILEPOST 311.8 TO MILEPOST 316.9. 10,000 FEET SIDING EXTENSION AT STOUTS IN UNION COUNTY. | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5704 | REGION E | O, T |  |  |  |  | 2019 | 4000000 |  |  | 4000000 | COMPLETE - OTHER FUNDING PROVIDED BY CSX CORPORATION
UNION | CSX SF LINE | NCDOT | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5744 | STATEWIDE MOBILITY | DP, O, T | 2025 | 5851000 | 2025 | 826000 | 2027 | 9126000 |  |  | 15803000 | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX.
UNION | CSX SG LINE | NCDOT | CONSTRUCT RAIL SIDING AND GRADE SEPARATION IN VICINITY OF SR 1300 (HELMS ROAD) AND CLOSE AT-GRADE CROSSINGS AT SR 1300 (HELMS ROAD) AND SR 1432 (TORY PATH). | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5748 | REGION E | [10 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS; OTHER FUNDING PROVIDED BY CSX.
UNION | CSX SG LINE | CSXT RR | CONSTRUCT RAIL SIDING IN WAXHAW | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5748A | REGION E | T |  |  |  |  | 2022 | 5894000 |  |  | 5894000 | UNDER CONSTRUCTION.
UNION | CSX SG LINE | NCDOT | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). | RAIL | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | P-5748B | REGION E | DP, O, T | 2023 | 5000000 | 2023 | 378000 | 2024 | 18177000 |  |  | 23555000 | RIGHT-OF-WAY IN PROGRESS.
UNION | SR 3522 (WEDDINGTON ROAD) | NCDOT | CSX CROSSING 631587H NEAR MONROE. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 10 | CHARLOTTE REGIONAL TPO | RX-2010A | DIVISION 10 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
UNION, ANSON, MECKLENBURG | NC 218 | NCDOT | US 74 IN ANSON COUNTY TO US 601 IN UNION COUNTY, AND FROM MILL GROVE ROAD IN UNION COUNTY TO I-485 IN MECKLENBURG COUNTY. INSTALL MILLED RUMBLE STRIPS. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | HS-2010C | REGION E | HSIP |  |  |  |  | 2022 | 616000 |  |  | 616000 | UNDER CONSTRUCTION.
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | SR 3448-SR 3474 (TRADE STREET) TO SR 1377 (WESLEY CHAPEL-STOUTS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4714 | [11 empty] | OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL.
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4714AC | DIVISION 10 | BGANY, BGDA, S(M), T, T(DA) | 2019 | 11780000 | 2019 | 2200000 | 2025 | 20439000 |  |  | 34419000 | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS.
UNION, MECKLENBURG | SR 3174 / 1501 (IDLEWILD ROAD) | NCDOT | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4913
UNION, MECKLENBURG | SR 3174 / SR 1501 (IDLEWILD ROAD) | NCDOT | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN TO SIX LANES. | HIGHWAY | STI (PRIORITIZATION) | 10 | CHARLOTTE REGIONAL TPO | U-4913B | NOT FUNDED | T | NOT FUNDED | 14886000 | NOT FUNDED | 636000 | NOT FUNDED | 21500000 |  |  | 37022000
UNION, MECKLENBURG | VARIOUS | NCDOT | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN DIVISION CATEGORY. | HIGHWAY | SAFETY | 10 | CHARLOTTE REGIONAL TPO | W-5210DIV | DIVISION 10
VANCE | SR 1165 (BECKFORD DRIVE) | NCDOT | HARRISON STREET TO NORTH PARK DRIVE IN HENDERSON. WIDEN TO THREE LANES WITH CURB AND GUTTER, STORM DRAINAGE, AND SIDEWALKS. | HIGHWAY | TRANSITION | 5 | KERR-TAR RPO | U-4916 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF HENDERSON
VANCE | SR 1162 (DABNEY DRIVE) | NCDOT | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | HIGHWAY | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | U-5890 | DIVISION 5 | T | 2026 | 41300000 | 2026 | 7300000 | 2028 | 16801000 |  |  | 65401000
VANCE | SR 1001 (WARRENTON ROAD) | NCDOT | SR 1001 (WARRENTON ROAD) AT SR 1507 (BROOKSTON ROAD). SAFETY IMPROVEMENTS. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO | W-5705G | DIVISION 5 | HSIP |  |  |  |  | 2024 | 503000 |  |  | 503000
VANCE | US 1 | NCDOT | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO | W-5805G | STATEWIDE MOBILITY | HSIP | 2023 | 45000 |  |  | 2023 | 955000 |  |  | 1000000
VANCE | KERR AREA TRANSPORTATION AUTHORITY | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | KERR-TAR RPO | TA-6711 | REGION C | FEDT, L, T | [6 empty] | 2020 | 56000 | 56000
VANCE | CSX S-LINE | NCDOT | BERT WINSTON ROAD AND CEDAR CREEK ROAD GRADE SEPERATION AND FRANKLINTON ROADWAY IMPROVEMENTS. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753BF | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | SOUTH KITRELL ROADWAY IMPROVEMENTS. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753BG | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | NORTH KITRELL ROADWAY IMPROVEMENTS INLCUDING MCCLANAHAN GRADE SEPERATION AND PETER GILL ROAD. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753BH | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | FRANKLINTON TO RIDGEWAY - S-LINE RAIL IMPROVEMENTS. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753CA | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | BEAR POND ROAD GRADE SEPERATION. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753CD | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | JP TAYLOR ROAD GRADE SEPERATION AND SOUTH HENDERSON ROADWAY IMPROVEMENTS. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753CE | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | ALEXANDER AVENUE GRADE SEPERATION AND DABNEY DRIVE ROADWAY IMPROVEMENTS. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753CF | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | ANDREWS GRADE SEPARATION AND DOWNTOWN ROADWAY IMPROVEMENTS. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753CG | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | WARRENTON ROAD IMPROVEMENTS AND GREYSTONE GRADE SEPERATION. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753CH | STATEWIDE MOBILITY
VANCE | CSX S-LINE | NCDOT | BROOKSTONE ROAD GRADE SEPERATION AND CARROLL STREET GRADE SEPARATION. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753CI | STATEWIDE MOBILITY
VANCE, WARREN | I-85 | NCDOT | SOUTH OF US 158 IN VANCE COUNTY TO NORTH OF SR 1237 (MANSON DREWRY ROAD) IN WARREN COUNTY | HIGHWAY | TRANSITION | 5 | KERR-TAR RPO | I-0914BA | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
VANCE, WARREN | CSX S-LINE | NCDOT | FRANKLINTON TO RIDGEWAY. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753C | STATEWIDE MOBILITY
WAKE | RALEIGH DURHAM INTERNATIONAL AIRPORT (RDU) | RALEIGH DURHAM INTERNATIONAL AIRPORT (RDU) | RECONSTRUCT RUNWAY 5L-23R. | AVIATION | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | AV-5700 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 101000000 |  |  | 101000000
WAKE | VARIOUS | FUQUAY-VARINA | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0022 | DIVISION 5 | BGDA, L | 2023 | 95000 | 2023 | 95000 | 2023 | 1180000 | 2022 | 164000 | 1534000
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | HOLLY SPRINGS | FLINT POINT LANE TO MIDDLECREST WAY IN HOLLY SPRINGS. ENHANCE PEDESTRIAN SAFETY. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0023 | DIVISION 5 | BGDA, L |  |  |  |  | 2022 | 1115000 |  |  | 1115000 | UNDER CONSTRUCTION
WAKE | SR 3112 (NW CARY PARKWAY) | CARY | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0024 | DIVISION 5 | BGDA, L | 2022 | 40000 | 2022 | 163000 | 2023 | 4911000 | 2022 | 960000 | 6074000 | UNDER CONSTRUCTION
WAKE | SR 2000 (WAKE FOREST ROAD) | RALEIGH | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0025 | DIVISION 5 | BGDA, L | 2023 | 200000 |  |  | 2023 | 1339000 | 2022 | 150000 | 1689000
WAKE | LITTLE DRIVE | RALEIGH | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0026 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 1063000 | 2022 | 219000 | 1282000
WAKE | CRABTREE CREEK GREENWAY | RALEIGH | LASSITER MILL ROAD TO HERTFORD STREET IN RALEIGH. CONSTRUCT GREENWAY TRAIL. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0027 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 1689000 |  |  | 1689000
WAKE | CRABTREE CREEK GREENWAY | CARY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0036 | EXEMPT | CMAQ, L |  |  |  |  | 2024 | 1402000 | 2024 | 248000 | 1650000
WAKE | CRABTREE CREEK GREENWAY CONNECTOR | CARY | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0037 | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 2826000 |  |  | 2826000
WAKE | EAST JONES STREET | FUQUAY-VARINA | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0038 | EXEMPT | CMAQ, L | 2022 | 65000 | 2022 | 75000 | 2023 | 353000 | 2022 | 72000 | 565000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | CARY | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0039 | EXEMPT | CMAQ, L | 2023 | 167000 |  |  | 2024 | 1144000 | 2022 | 50000 | 1361000
WAKE | VARIOUS | APEX | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0047 | DIVISION 5 | L, TADA | 2023 | 221000 |  |  | 2023 | 1524000 |  |  | 1745000
WAKE | SR 1616 / NON-SYSTEM (OLD APEX ROAD) | CARY | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0048 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 2000000 |  |  | 2000000
WAKE | SR 2768 (SOUTHEAST JUDD PARKWAY) | FUQUAY-VARINA | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0054 | DIVISION 5 | BGDA, L | 2023 | 50000 |  |  | 2024 | 615000 | 2023 | 60000 | 725000
WAKE | US 401 (SOUTH SAUNDERS STREET) | RALEIGH | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0089 | EXEMPT | CMAQ, L |  |  |  |  | 2024 | 1095000 |  |  | 1095000
WAKE | HIGGINS GREENWAY | CARY | SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0091 | EXEMPT | CMAQ, L |  |  |  |  | 2024 | 2451000 |  |  | 2451000
WAKE | ALSTON RIDGE GREENWAY | FUQUAY-VARINA | ALSTON RIDGE GREENWAY TO BASS LAKE GREENWAY IN FUQUAY-VARINA. COMPLETE A GAP OF GREENWAY TRAIL. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0092 | EXEMPT | CMAQ, L |  |  |  |  | 2024 | 1548000 |  |  | 1548000
WAKE | UTLEY CREEK GREENWAY WEST | HOLLY SPRINGS | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0093 | EXEMPT | CMAQ, L |  |  |  |  | 2024 | 2750000 |  |  | 2750000
WAKE | SAUNDERS STREET | APEX | SAUNDERS STREET AT WEST CHATHAM STREET TO HINTON STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0095 | DIVISION 5 | BGDA, L |  |  |  |  | 2024 | 1344000 |  |  | 1344000
WAKE | SR 1012 (WESTERN BOULEVARD) | NCDOT | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | BIKE/PED | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | EB-5718 | DIVISION 5 | L, TAANY |  |  |  |  | 2028 | 4000000 |  |  | 4000000 | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166
WAKE | SR 3015 (AIRPORT BOULEVARD) | MORRISVILLE | MCCRIMMON PARKWAY TO FACTORY SHOPPES ROAD IN MORRISVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | EB-5814 | DIVISION 5 | L, TAANY |  |  |  |  | 2022 | 800000 |  |  | 800000 | UNDER CONSTRUCTION
WAKE | SR 1637 (CHURCH STREET) | MORRISVILLE | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | BIKE/PED | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | EB-5838 | DIVISION 5 | L, TAANY | 2023 | 250000 |  |  | 2024 | 1450000 | 2022 | 300000 | 2000000
WAKE | BLACK CREEK GREENWAY | CARY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | EB-5894 | DIVISION 5 | CMAQ, L, TAANY |  |  |  |  | 2023 | 9500000 |  |  | 9500000
WAKE | NC 55 (EAST WILLIAMS STREET) | HOLLY SPRINGS | SR 1301 (SUNSET LAKE ROAD) TO NC 55 IN HOLLY SPRINGS. CONSTRUCT SIDEWALK. | BIKE/PED | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | EB-5895 | DIVISION 5 | L, TAANY |  |  |  |  | 2021 | 500000 |  |  | 500000 | UNDER CONSTRUCTION
WAKE | SR 1306 (LAURA DUNCAN ROAD) | APEX | APEX COMMUNITY PARK AND NORTH SALEM STREET IN APEX. IMPROVE SAFETY OF PEDESTRIAN CROSSING. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | EB-6019 | DIVISION 5 | BGDA, L |  |  |  |  | 2021 | 544000 |  |  | 544000 | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION.
WAKE | BEAVER CREEK GREENWAY EXTENSION | APEX | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | EB-6021 | DIVISION 5 | L, TADA |  |  |  |  | 2023 | 6565000 |  |  | 6565000
WAKE | (SR 1307) WEST CHATHAM STREET | APEX | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | EB-6046 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 953000 |  |  | 953000
WAKE | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | WENDELL | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | EB-6048 | DIVISION 5 | BGDA, L | 2023 | 75000 |  |  | 2023 | 384000 |  |  | 459000 | RIGHT OF WAY IN PROGRESS.
WAKE | AVENT FERRY ROAD | HOLLY SPRINGS | COTTEN LANE TO WEST BALLANTINE STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO STINSON AVENUE VIA PINE AVENUE IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | BIKE/PED | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | EB-6049 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 1250000 |  |  | 1250000
WAKE | NC 50 | NCDOT | REPLACE BRIDGE 910069 OVER US 70 IN GARNER. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-4654 | REGION C | BFP |  |  |  |  | 2023 | 9000000 |  |  | 9000000
WAKE | SR 1006 (OLD STAGE ROAD) | NCDOT | REPLACE BRIDGE 910277 OVER BLACK CREEK. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-4655 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
WAKE | US 70/US 401/NC 50 (CAPITAL BOULEVARD) | NCDOT | REPLACE BRIDGE 910227 OVER PEACE STREET AND BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH AND REVISE INTERCHANGE AT PEACE STREET. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5121 | REGION C | [10 empty] | UNDER CONSTRUCTION; PARTICIPATION BY CITY OF RALEIGH; INCLUDES B-5317
WAKE | SR 1321 (AVENT FERRY ROAD) | NCDOT | REPLACE BRIDGE 910318 OVER LAKE JOHNSON IN RALEIGH. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5130 | DIVISION 5 | BFP |  |  |  |  | 2029 | 3650000 |  |  | 3650000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1162 (APEX BARBECUE ROAD) | NCDOT | REPLACE BRIDGE 910362 OVER BEAVER CREEK IN APEX. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5161 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION
WAKE | SR 2703 (NEW BETHEL CHURCH ROAD) | NCDOT | REPLACE BRIDGE 910248 OVER MAHLER'S CREEK IN GARNER. | HIGHWAY | TRANSITION | 5 | CAPITAL AREA MPO | B-5237 | DIVISION 5 | T |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | BUILD NC BONDS: $2.0 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
WAKE | US 70 WESTBOUND / NC 50 NORTHBOUND | NCDOT | REPLACE BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5317 | REGION C | [10 empty] | SCOPE AND COST INCLUDED IN B-5121
WAKE | SR 2044 (LIGON MILL ROAD) | NCDOT | REPLACE BRIDGE 910126 OVER SMITHS CREEK IN WAKE FOREST. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5318 | DIVISION 5 | BFP |  |  |  |  | 2023 | 11000000 |  |  | 11000000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1630 (GREEN LEVEL CHURCH ROAD) | NCDOT | REPLACE BRIDGE 910061 OVER KIT CREEK IN CARY. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5673 | DIVISION 5 | HFB | 2023 | 290000 |  |  | 2025 | 5800000 |  |  | 6090000
WAKE | US 401 (CAPITAL BOULEVARD) | NCDOT | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5684 | REGION C | BFP | 2029 | 6300000 | 2029 | 380000 | 2030 | 11600000 |  |  | 18280000
WAKE | NC 231 | NCDOT | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5986 | REGION C | BFP, NHPB | 2027 | 164000 | 2027 | 202000 | 2028 | 2948000 |  |  | 3314000
WAKE | US 401 | NCDOT | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | B-5987 | REGION C | NHPB | 2023 | 640000 | 2023 | 640000 | 2024 | 16899000 |  |  | 18179000 | RIGHT OF WAY IN PROGRESS.
WAKE | SR 1632 (LOUIS STEPHENS DRIVE) | MORRISVILLE | GRAY MARBLE ROAD TO ADDENBROCK DRIVE IN MORRISVILLE, AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0049 | EXEMPT | CMAQ, L |  |  |  |  | 2026 | 550000 |  |  | 550000
WAKE | SR 1379 (PENNY ROAD) | NCDOT | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0051 | EXEMPT | CMAQ, S | 2023 | 50000 |  |  | 2024 | 350000 | 2023 | 50000 | 450000 | "S" REFERS TO SPOT SAFETY HIGHWAY FUNDS
WAKE | SR 6107 (NORTH MAIN STREET) | HOLLY SPRINGS | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | BL-0052 | EXEMPT | CMAQ, L | 2023 | 250000 |  |  | 2023 | 500000 | 2023 | 75000 | 825000
WAKE | CRABTREE CREEK GREENWAY | CARY | CONSTRUCT GREENWAY CONNECTING EXISTING GREENWAY IN CARY THROUGH MORRISVILLE, INCLUDING REPLACEMENT OF TRAIN TRESTLE. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | C-5168 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE
WAKE | MINGO CREEK GREENWAY | KNIGHTDALE | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE | HIGHWAY | OTHER | 5 | CAPITAL AREA MPO | C-5604HA | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 2200000 |  |  | 2200000 | UNDER CONSTRUCTION
WAKE | HIGGINS GREENWAY | CARY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 | HIGHWAY | OTHER | 5 | CAPITAL AREA MPO | C-5604ID | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 1000000 |  |  | 1000000
WAKE | SR 1179 (BRIDGE STREET) | NCDOT | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | HIGHWAY | BRIDGES | 5 | CAPITAL AREA MPO | HB-0029 | DIVISION 5 | BGOFF | 2025 | 100000 | 2025 | 100000 | 2026 | 2000000 |  |  | 2200000
WAKE | NEW ROUTE; SR 1152 (HOLLY SPRINGS - NEW HILL ROAD) | NCDOT | NEW ROUTE INTERSECTING GREEN OAKS PARKWAY BETWEEN THOMAS MILL ROAD AND NC 55, SR 1153 INTERSECTION WITH BENNET KNOLL PARKWAY, AND SR 1152 INTERSECTION WITH SR 1153 IN HOLLY SPRINGS. CONSTRUCT ACCESS ROAD AND INTERSESCTION IMPROVEMENTS. | HIGHWAY | ECONOMIC DEVELOPMENT | 5 | CAPITAL AREA MPO | HE-0002 | DIVISION 5 | T | 2023 | 10000 |  |  | 2024 | 9690000 |  |  | 9700000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FUJIFILM DIOSYNTH BIOTECHNOLOGIES.
WAKE | VARIOUS | NCDOT | INTERCHANGE IMPROVEMENTS AT US 1 / SR 1127 (NEW HILL-HOLLEMANN ROAD), INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) / SR 1149 (FRIENDSHIP ROAD) AND SR 1149 (FRIENDSHIP ROAD) / SR 1152 (OLD HOLLY SPRINGS-NEW HILL ROAD). | HIGHWAY | ECONOMIC DEVELOPMENT | 5 | CAPITAL AREA MPO | HE-0010 | DIVISION 5 | T | 2024 | 200000 |  |  | 2024 | 9300000 | 2023 | 500000 | 10000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN.
WAKE | US 401 | NCDOT | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0006 | EXEMPT | NHPBA | 2023 | 2600000 | 2023 | 509000 | 2025 | 26900000 |  |  | 30009000
WAKE | NC 55 | NCDOT | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0007 | EXEMPT | NHPBA | 2024 | 9100000 | 2024 | 3600000 | 2025 | 23300000 |  |  | 36000000
WAKE | NC 50 (BENSON ROAD) | NCDOT | SR 2812 (TIMBER DRIVE) INTERSECTION IN GARNER. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008C | EXEMPT | BA | 2022 | 100000 |  |  | 2024 | 525000 |  |  | 625000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | NCDOT | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008D | EXEMPT | BA | 2023 | 500000 | 2023 | 210000 | 2025 | 2500000 |  |  | 3210000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1375 (LAKE WHEELER ROAD) | NCDOT | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008G | EXEMPT | BGBA, BGDA | 2023 | 790000 | 2023 | 30000 | 2024 | 2300000 |  |  | 3120000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | NCDOT | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008H | EXEMPT | BA | 2022 | 251000 | 2022 | 60000 | 2024 | 1750000 |  |  | 2061000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1010 (TEN-TEN ROAD) | NCDOT | SR 1386 (BELLS LAKE ROAD) , SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008L | EXEMPT | BA | 2023 | 300000 | 2023 | 225000 | 2025 | 2400000 |  |  | 2925000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NC 42 | NCDOT | SR 2735 (JOHNSON ROAD) INTERSECTION.INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008O | EXEMPT | BA | 2023 | 175000 | 2023 | 125000 | 2025 | 1300000 |  |  | 1600000
WAKE | SR 1010 (TEN-TEN ROAD) | NCDOT | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008P | EXEMPT | BA | 2023 | 250000 | 2023 | 175000 | 2025 | 1750000 |  |  | 2175000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1390 (OPTIMIST FARM ROAD) | NCDOT | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008Q | EXEMPT | BA | 2023 | 300000 | 2023 | 225000 | 2025 | 2400000 |  |  | 2925000
WAKE | SR 1379 (PENNY ROAD) | NCDOT | SR 1382 (OLDE SOUTH ROAD) INTERSECTION IN RALIEGH. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0008S | EXEMPT | BA | 2023 | 175000 | 2023 | 125000 | 2025 | 1100000 |  |  | 1400000
WAKE | SR 1301 (SUNSET LAKE ROAD) | FUQUAY-VARINA | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0027 | DIVISION 5 | BGDA, L | 2023 | 385000 | 2023 | 575000 | 2023 | 578000 | 2022 | 62000 | 1600000 | RIGHT-OF-WAY IN PROGRESS
WAKE | US 401 | FUQUAY-VARINA | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0028 | EXEMPT | BGDA, L |  |  |  |  | 2023 | 1252000 | 2022 | 134000 | 1386000 | UNDER CONSTRUCTION
WAKE | NC 55 | HOLLY SPRINGS | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0029 | EXEMPT | BGDA, L | 2023 | 102000 |  |  | 2023 | 914000 |  |  | 1016000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SOUTH MAIN STREET | HOLLY SPRINGS | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0030 | DIVISION 5 | BGDA, L | 2023 | 451000 |  |  | 2023 | 749000 |  |  | 1200000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1007 (POOLE ROAD) | NCDOT | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0031 | DIVISION 5 | BGDA, S | 2022 | 340000 | 2022 | 150000 | 2024 | 1700000 |  |  | 2190000 | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS
WAKE | LAKE BOONE TRAIL | RALEIGH | I-440 TO RIDGE ROAD IN RALEIGH. UPGRADE ROADWAY TO COMPLETE STREET. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0032 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 1264000 |  |  | 1264000
WAKE | (SR 3126) AIRPORT BOULEVARD | NCDOT | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0033 | DIVISION 5 | BGDA, L | 2022 | 600000 |  |  | 2024 | 6474000 |  |  | 7074000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 2768 (JUDD PARKWAY) | FUQUAY-VARINA | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0041 | EXEMPT | CMAQ, S, S(M) | 2022 | 63000 |  |  | 2023 | 745000 | 2022 | 86000 | 894000 | S(M) and S represent SPOT Mobility Funds of $400k. RIGHT-OF-WAY IN PROGRESS
WAKE | (JUDD PARKWAY) SR 1110 / SR 5056 | FUQUAY-VARINA | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0042 | EXEMPT | CMAQ, L | 2023 | 140000 | 2023 | 260000 | 2023 | 1274000 | 2022 | 253000 | 1927000 | RIGHT-OF-WAY IN PROGRESS
WAKE | (SIX FORKS ROAD) SR 1005 | NCDOT | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0043 | EXEMPT | CMAQ, S | 2024 | 275000 |  |  | 2025 | 1040000 | 2022 | 190000 | 1505000 | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS
WAKE | SR 1349 (DILLARD DRIVE) | NCDOT | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0050 | DIVISION 5 | BGDA, S | 2023 | 174000 |  |  | 2024 | 1098000 |  |  | 1272000 | "S" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1319 (JONES FRANKLIN ROAD) | NCDOT | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0051 | DIVISION 5 | BGDA, S | 2023 | 80000 |  |  | 2024 | 400000 | 2023 | 110000 | 590000
WAKE | BLUE RIDGE ROAD | RALEIGH | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0052 | DIVISION 5 | BGDA, S |  |  |  |  | 2023 | 7997000 |  |  | 7997000
WAKE | SR 1005 (SIX FORKS ROAD) | RALEIGH | ROWAN STREET TO SR 1827 (LYNN ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPERATED BIKEWAYS, RPOTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0119 | DIVISION 5 | BGDA, L |  |  |  |  | 2024 | 28000000 |  |  | 28000000
WAKE | NC 50 | CREEDMOOR | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | HL-0121 | DIVISION 5 | BGDA, L | 2024 | 103000 |  |  | 2024 | 777000 | 2024 | 266000 | 1146000
WAKE | SHELLEY ROAD | NCDOT | REPLACE BRIDGE NUMBER 378 OVER MINE CREEK FROM SHADOWBROOK DRIVE TO FOREST LAWN COURT. | HIGHWAY | MUNICIPAL BRIDGE | 5 | CAPITAL AREA MPO | HM-0002 | DIVISION 5 | BFPOFF |  |  | 2024 | 250000 | 2024 | 2500000 |  |  | 2750000
WAKE | CHESWICK DRIVE | NCDOT | REPLACE BRIDGE NUMBER 627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | HIGHWAY | MUNICIPAL BRIDGE | 5 | CAPITAL AREA MPO | HM-0003 | DIVISION 5 | BFPOFF | 2024 | 250000 | 2025 | 250000 | 2025 | 1250000 | 2024 | 500000 | 2250000
WAKE | VARIOUS | NCDOT | NCDOT MULTI-MODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. | HIGHWAY | OTHER | 5 | CAPITAL AREA MPO | HO-0001 | EXEMPT | DP, S |  |  |  |  | 2022 | 227000 | 2021 | 311000 | 538000 | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT
WAKE | NCSU CAMPUS | NCDOT | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. | HIGHWAY | OTHER | 5 | CAPITAL AREA MPO | HO-0001AA | EXEMPT | DP, S |  |  |  |  | 2023 | 2981000 | 2021 | 369000 | 3350000 | UNDER CONSTRUCTION
WAKE | NCSU CAMPUS | NCDOT | FIBER OPTIC CABLE INSTALLATION. | HIGHWAY | OTHER | 5 | CAPITAL AREA MPO | HO-0001AB | EXEMPT | DP, S |  |  |  |  | 2023 | 168000 | 2022 | 150000 | 318000
WAKE | NCSU CAMPUS | NCDOT | ECO DRIVING APPLICATION | HIGHWAY | OTHER | 5 | CAPITAL AREA MPO | HO-0001AC | EXEMPT | DP, S |  |  |  |  | 2024 | 704000 | 2023 | 74000 | 778000 | PROJECT DELETED
WAKE | NCSU CAMPUS | NCDOT | SYSTEMS ENGINEERING, GRANT ADMINISTRATION | HIGHWAY | OTHER | 5 | CAPITAL AREA MPO | HO-0001B | EXEMPT | DP, S | [6 empty] | 2021 | 200000 | 200000
WAKE | NCSU CAMPUS | NCDOT | BEFORE & AFTER STUDY, EXPANSION FEASIBILITY STUDY | HIGHWAY | OTHER | 5 | CAPITAL AREA MPO | HO-0001C | EXEMPT | DP, S | [6 empty] | 2021 | 310000 | 310000
WAKE | VARIOUS | NCDOT | DOWNTOWN RALEIGH BUSINESS DISTRICT. TRAFFIC SIGNAL REVISIONS AT VARIOUS LOCATIONS. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | HS-2005F | DIVISION 5 | HSIP |  |  |  |  | 2023 | 200000 |  |  | 200000 | UNDER CONSTRUCTION
WAKE | SR 2215 (BUFFALOE ROAD) | NCDOT | SR 2214 (SOUTHHALL ROAD)/BRINTONS COTTAGE STREET AND VALLEY STREAM DRIVE INTERSECTIONS IN RALEIGH. TRAFFIC SIGNALS REVISIONS, CURB RAMPS, AND PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | HS-2005G | DIVISION 5 | HSIP |  |  |  |  | 2023 | 147000 |  |  | 147000
WAKE | SR 1645(LUMLEY ROAD) | NCDOT | I-540 WESTBOUND RAMP/ARCO CORPORATE DRIVE IN RALEIGH. WIDENING, TURN LANE CONSTRUCTION, TRAFFIC SIGNAL UPGRADE. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | HS-2005I | DIVISION 5 | HSIP |  |  |  |  | 2024 | 180000 |  |  | 180000
WAKE | SR 2516 (HODGE ROAD) | NCDOT | THE MINGO CREEK TRAIL CROSSING. RELOCATE CROSSWALK. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | HS-2005J | DIVISION 5 | HSIP |  |  | 2024 | 20000 | 2024 | 155000 |  |  | 175000
WAKE | US 401 | NCDOT | SR 2108/SR 2036 (NEW HOPE ROAD) AND US 401 AT CALVARY DRIVE. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | HS-2005K | REGION C | HSIP |  |  |  |  | 2023 | 115000 |  |  | 115000
WAKE | SR 1142 (HUMIE OLIVE ROAD) | NCDOT | SR 1142 (HUMIE OLIVE ROAD) AT BLAZING TRAIL DRIVE/DRIVEWAY ACCESS TO APEX FRIENDSHIP HIGH AND ELEMENTARY SCHOOLS. INSTALL TRAFFIC AND PEDESTRIAN SIGNALS. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | HS-2005Q | DIVISION 5 | HSIP |  |  |  |  | 2024 | 130000 |  |  | 130000
WAKE | SR 3120 (MORRISVILLE PARKWAY) | NCDOT | SR 3120 (MORRISVILLE PARKWAY) AT SR 3043 (FERSON ROAD) / GREEN HOPE SCHOOL ROAD. IMPROVE PEDESTRIAN CROSSING. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | HS-2005R | DIVISION 5 | HSIP |  |  |  |  | 2024 | 50000 |  |  | 50000
WAKE | I-40 | NCDOT | SR 1728 (WADE AVENUE) TO I-440 / US 1 / US 64. WIDEN TO SIX LANES. | HIGHWAY | PRE-STI (HISTORIC) | 5 | CAPITAL AREA MPO | I-4744 | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 4635000 |  |  | 4635000 | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020
WAKE | I-40 | NCDOT | I-440 / US 64 (EXIT 301) TO JOHNSTON COUNTY LINE. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5111SW | STATEWIDE MOBILITY | NHP | 2019 | 15826000 |  |  | 2018 | 108398000 |  |  | 124224000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
WAKE | I-40; SR 1728 (WADE AVENUE) | NCDOT | EAST OF I-540 TO WADE AVENUE (EXIT 289) INCLUDING RAMPS, AND SR 1728 (WADE AVENUE) FROM I-40 TO SR 3009 (EDWARDS MILL ROAD). MILL AND RESURFACE ROADWAY, SHOULDERS AND RAMPS. | HIGHWAY | PRE-STI (HISTORIC) | 5 | CAPITAL AREA MPO | I-5112 | PRE-STI (TRANSITION) | BGANY, NHP |  |  |  |  | 2009 | 637000 |  |  | 637000 | PROJECT COMPLETE - GARVEE BOND FUNDING $5.8 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020
WAKE | I-40 | NCDOT | SR 1002 (AVIATION PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 1002 TO SR 3015 (AIRPORT BOULEVARD). | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5506 | STATEWIDE MOBILITY | [10 empty] | PROJECT COMPLETE.
WAKE | I-40 | NCDOT | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5700 | STATEWIDE MOBILITY | NHP, S(M) |  |  |  |  | 2020 | 51733000 |  |  | 51733000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034
WAKE | I-40 / US 64 | NCDOT | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5701 | STATEWIDE MOBILITY | NHP | 2027 | 0 | 2027 | 1100000 | 2027 | 67700000 |  |  | 68800000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703
WAKE | I-40 | NCDOT | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5703 | STATEWIDE MOBILITY | NHP | 2027 | 29600000 | 2027 | 3600000 | 2027 | 119100000 |  |  | 152300000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701
WAKE | I-440 / US 1 | NCDOT | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5708 | STATEWIDE MOBILITY | NHP | 2019 | 1736000 |  |  | 2026 | 9100000 |  |  | 10836000 | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033
WAKE | I-440 / US 1 | NCDOT | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5870 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 193101000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 213701000 |  |  | 411802000
WAKE | I-40 | NCDOT | NC 54 IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5873 | REGION C | [10 empty] | UNDER CONSTRUCTION
WAKE | I-40 | NCDOT | SR 1728 (WADE AVENUE) TO I-440 / US 1 IN RALEIGH. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO | I-5943 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 18419000 |  |  | 18419000 | UNDER CONSTRUCTION
WAKE | I-87 / US 64 / US 264 | NCDOT | I-440 IN RALEIGH TO SR 1003 (ROLESVILLE ROAD). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO | I-5944 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2029 | 28600000 |  |  | 28600000
WAKE | I-540 | NCDOT | TRIANGLE TOWNE CENTER BOULEVARD IN RALEIGH TO I-495 / US 64 / US 264 IN KNIGHTDALE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO | I-5945 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2029 | 27900000 |  |  | 27900000
WAKE | I-40 | NCDOT | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5966 | STATEWIDE MOBILITY | NHP | 2028 | 700000 | 2028 | 138000 | 2031 | 47701000 |  |  | 48539000
WAKE | I-540 | NCDOT | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5968 | STATEWIDE MOBILITY | NHP | 2028 | 3200000 | 2028 | 10000 | 2030 | 20502000 |  |  | 23712000
WAKE | I-440 / US 1 | NCDOT | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-5970 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48399000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 89899000 |  |  | 141598000
WAKE | I-440 / US 1 | NCDOT | SR 1728 (WADE AVENUE) TO SR 2000 (WAKE FOREST ROAD) IN RALEIGH. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO | I-5997 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2024 | 23100000 |  |  | 23100000
WAKE | I-540 | NCDOT | US 70 (GLENWOOD AVENUE) TO EAST OF TRIANGLE TOWN BOULEVARD IN RALEIGH. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO | I-5999 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2024 | 12000000 |  |  | 12000000 | COORDINATE WITH I-5998 AND I-6000;
WAKE | I-87 / US 64 / US 264 | NCDOT | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-6005 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 53699000 |  |  | 56499000
WAKE | I-87 / US 64 / US 264 | NCDOT | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | I-6007 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4601000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16199000 |  |  | 22100000
WAKE | NEW ROUTE (FUTURE NC 540) | NCDOT | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), NC 55 (SOUTH) TO EAST OF US 401 SOUTH. FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-2721 | STATEWIDE MOBILITY | [10 empty] | COORDINATE WITH U-5746; NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT
WAKE | NC 540 | NCDOT | NC 55 BYPASS TO EAST OF SR 1152 (HOLLY SPRINGS ROAD). CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-2721A | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 79500000 |  |  | 79500000 | UNDER CONSTRUCTION
WAKE | NC 540 | NCDOT | EAST OF SR 1152 (HOLLY SPRINGS ROAD) TO EAST OF US 401. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-2721B | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 63000000 |  |  | 63000000 | UNDER CONSTRUCTION
WAKE | US 401 | NCDOT | SR 2044 (LIGON MILL ROAD) TO NORTH OF SR 2225 (LOUISBURY ROAD) | HIGHWAY | PRE-STI (HISTORIC) | 5 | CAPITAL AREA MPO | R-2814A | [11 empty] | COMPLETE
WAKE | US 401 | NCDOT | ROLESVILLE BYPASS, NORTH OF SR 2225 (LOUISBURY ROAD) TO NC 96 ON NEW LOCATION | HIGHWAY | PRE-STI (HISTORIC) | 5 | CAPITAL AREA MPO | R-2814B | PRE-STI (TRANSITION) | BGANY | 2009 | 1727000 |  |  | 2011 | 7083000 |  |  | 8810000 | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022
WAKE | NEW ROUTE (FUTURE NC 540) | NCDOT | EASTERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), I-40 TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-2829 | STATEWIDE MOBILITY | [10 empty] | THE STIP ADDRESSES INFLATION BY DECREASING REVENUE, THEREFORE THE $350M SHOWN REPRESENTS THE $400M REQUIRED IN FY26. BOND R(T) FUNDING REPRESENTS THE $100M LOAN FROM NCDOT TO NC TURNPIKE AUTHORITY AND WILL BE REPAID AT FINANCIAL CLOSE.
WAKE | NEW ROUTE (FUTURE NC 540) | NCDOT | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-2829A | STATEWIDE MOBILITY | BOND R, BONDRT, NHP, S(M) | 2023 | 66809000 | 2023 | 8544000 | 2023 | 368065000 |  |  | 443418000 | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040
WAKE | NEW ROUTE (FUTURE NC 540) | NCDOT | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-2829B | STATEWIDE MOBILITY | BOND R, BONDRT, NHP, S(M) | 2023 | 68806000 | 2023 | 5500000 | 2023 | 458567000 |  |  | 532873000 | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040
WAKE | NC 55 | NCDOT | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | R-5705C | NOT FUNDED | T | NOT FUNDED | 8170000 | NOT FUNDED | 1386000 | NOT FUNDED | 17900000 |  |  | 27456000
WAKE | I-440/US-1 | NCDOT | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-2719 | STATEWIDE MOBILITY | NHP | 2019 | 34749000 |  |  | 2019 | 158558000 |  |  | 193307000 | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT OF WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033
WAKE | US 70 | NCDOT | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-2823 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 37100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 84202000 |  |  | 122502000
WAKE | NC 55 (WILLIAMS STREET) | NCDOT | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD) IN APEX. WIDEN TO A MULTI-LANE CURB AND GUTTER FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-2901 | [11 empty] | PROJECTS U-2901AA AND AB COMPLETE
WAKE | NC 55 (WILLIAMS STREET) | NCDOT | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-2901B | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3650000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20002000 |  |  | 34652000
WAKE | NC 55 (WILLIAMS STREET) | NCDOT | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-2901BA | REGION C | T | 2027 | 1000000 | 2027 | 250000 | 2029 | 17000000 |  |  | 18250000
WAKE | NC 54 (HILLSBOROUGH STREET) | NCDOT | SR 1664 / SR 3074 (BLUE RIDGE ROAD) IN VICINITY OF NC RAILROAD (CSX CORPORATION AND NORFOLK SOUTHERN) IN RALEIGH. CONSTRUCT GRADE SEPARATIONS AND ACCESS ROAD BETWEEN NC 54 AND SR 1664 / SR 3074. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-4437 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT - LET WITH U-2719; INCLUDES $19.9 MILLION FEDERAL TIGER GRANT
WAKE | US 64 | NCDOT | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5301 | STATEWIDE MOBILITY | T | 2027 | 100558000 | 2027 | 4012000 | 2030 | 134598000 |  |  | 239168000
WAKE | US 401 | NCDOT | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5302 | REGION C | T | 2019 | 9931000 |  |  | 2024 | 22962000 | 2019 | 1801000 | 34694000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE)
WAKE | US 1 | NCDOT | I-540 IN RALEIGH TO SR 1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. UPGRADE ROADWAY TO CONTROLLED ACCESS FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5307
WAKE | US 1 | NCDOT | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5307A | STATEWIDE MOBILITY | T | 2026 | 94301000 | 2026 | 12200000 | 2026 | 184700000 |  |  | 291201000 | DESIGN-BUILD PROJECT
WAKE | US 1 | NCDOT | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5307B | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 80403000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 92400000 |  |  | 179503000 | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE)
WAKE | US 1 | NCDOT | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5307C | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28199000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 108799000 |  |  | 142098000
WAKE | US 1 | NCDOT | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5307D | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83999000 |  |  | 141199000
WAKE | MORRISVILLE PARKWAY EXTENSION | CARY | SR 1600 / SR 1625 (GREEN LEVEL CHURCH ROAD) TO EAST OF NC 55 IN CARY. MULTI-LANE FACILITY ON NEW LOCATION, INCLUDING INTERCHANGE AT NC 540 (TRIANGLE EXPRESSWAY / WESTERN WAKE FREEWAY). | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5315 | [11 empty] | PART C CONSTRUCTION BY TOWN OF CARY
WAKE | MORRISVILLE PARKWAY EXTENSION | CARY | WEST OF HIGHCROFT DRIVE TO EAST OF MILLS PARK DRIVE IN CARY. CONSTRUCT 2-LANE FACILITY ON 4-LANE RIGHT OF WAY. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5315A | DIVISION 5 | [10 empty] | PROJECT COMPLETE.
WAKE | MORRISVILLE PARKWAY EXTENSION | CARY | NC 540 (TRIANGLE EXPRESSWAY / WESTERN WAKE FREEWAY). CONSTRUCT INTERCHANGE. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5315B | DIVISION 5 | [10 empty] | PROJECT COMPLETE.
WAKE | MORRISVILLE PARKWAY EXTENSION | NCDOT | SR 1600 / SR 1625 (GREEN LEVEL CHURCH ROAD) TO EAST OF NC 55 IN CARY. WIDEN TO 4 LANES WITH LANDSCAPED MEDIAN. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5315C | NOT FUNDED | L |  |  |  |  | NOT FUNDED | 7900000 |  |  | 7900000
WAKE | NORTH JUDD PARKWAY | NCDOT | NC 55 (NORTH BROAD STREET) TO NC 42 (WEST ACADEMY STREET) IN FUQUAY-VARINA, WAKE COUNTY. MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5317 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION BY TOWN OF FUQUAY-VARINA
WAKE | US 64 BUSINESS (WENDELL BOULEVARD) | NCDOT | SR 1003 (ROLESVILLE ROAD-EAGLE ROCK ROAD) IN WENDELL. CONNECTIVITY AND ACCESS IMPROVEMENTS AND SAFETY ENHANCEMENTS. | HIGHWAY | PRE-STI (HISTORIC) | 5 | CAPITAL AREA MPO | U-5323 | REGION C | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY TOWN OF WENDELL - IN PROGRESS
WAKE | SR 1650 (REEDY CREEK ROAD) | CARY | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5501 | DIVISION 5 | BGDA, L |  |  |  |  | 2020 | 7692000 |  |  | 7692000 | UNDER CONSTRUCTION BY TOWN OF CARY
WAKE | SR 1650 (REEDY CREEK ROAD) | CARY | SR 1652 (HARRISION AVENUE) TO SOUTH OF WATTS POND LANE IN CARY. WIDEN ROADWAY TO THREE LANES INSTALL ROUNDABOUTS AND PEDESTRIAN ENHANCEMENTS | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5501A | DIVISION 5
WAKE | SR 1930 (STADIUM DRIVE) SR 1933 (WEST NORTH AVENUE | WAKE FOREST | SR 1930 (STADIUM DRIVE), US 1 TO SR 1954 (NORTH WINGATE STREET) IN WAKE FOREST. COMPLETE STREETS IMPROVEMENTS TO INCLUDE: WIDEN TO THREE-LANE CURB AND GUTTER SECTION, CONSTRUCT SIDEWALK, MULTI-USE PATH, BICYCLE LANES, AND PEDESTRIAN / TRANSIT AMENITIES. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5515 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION BY TOWN OF WAKE FOREST
WAKE | WEST STREET | RALEIGH | CABARRUS STREET TO MARTIN STREET IN RALEIGH. EXTEND WEST STREET ON NEW LOCATION, WITH GRADE SEPARATION AT NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN "H" LINE. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5521 | DIVISION 5 | BGDA, L | 2024 | 2387000 | [6 empty] | 2387000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY CITY OF RALEIGH - IN PROGRESS
WAKE | SR 1115 (AVENT FERRY ROAD) | HOLLY SPRINGS | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5529 | DIVISION 5 | BGDA, L |  |  |  |  | 2020 | 1830000 |  |  | 1830000 | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS
WAKE | SR 1521 (LAKE PINE DRIVE) | APEX | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTI-USE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5537 | DIVISION 5 | BGDA, L |  |  |  |  | 2021 | 585000 |  |  | 585000 | UNDER CONSTRUCTION BY TOWN OF APEX
WAKE | SR 3014 (MORRISVILLE- CARPENTER ROAD) | MORRISVILLE | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5618 | DIVISION 5 | BGDA, L, S |  |  |  |  | 2020 | 7463000 |  |  | 7463000 | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION
WAKE | US 70 / NC 50 | NCDOT | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5744 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 138000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13998000 |  |  | 28536000
WAKE | US 401 | NCDOT | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5746 | REGION C | T | 2022 | 2938000 | 2022 | 610000 | 2024 | 5699000 |  |  | 9247000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NC 54; SR 1635 (MCCRIMMON PARKWAY) | NCDOT | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET); NC 54 AT SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. WIDEN SR 1635 AND CONVERT NC 54 AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5747 |  | T | [6 empty] | 2019 | 3001000 | 3001000 | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
WAKE | SR 1635 (MCCRIMMON PARKWAY) | NCDOT | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5747A | DIVISION 5 | T | 2021 | 4000000 | 2021 | 500000 | 2025 | 19600000 |  |  | 24100000 | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966
WAKE | NC 54 | NCDOT | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5747B | REGION C | T | 2019 | 72000 | 2024 | 620000 | 2025 | 22100000 |  |  | 22792000 | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
WAKE | US 401 | NCDOT | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5748 | REGION C | T | 2019 | 6840000 | 2021 | 212000 | 2024 | 22500000 | 2019 | 1921000 | 31473000 | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS
WAKE | NC 54 | NCDOT | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5750 | REGION C | T | 2019 | 3468000 | 2022 | 1900000 | 2025 | 22070000 | 2019 | 1620000 | 29058000 | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $10 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS
WAKE | US 401 | NCDOT | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5751 | REGION C | T | 2028 | 39151000 | 2028 | 2620000 | 2031 | 68300000 |  |  | 110071000
WAKE | SR 1002 (AVIATION PARKWAY) | NCDOT | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULT-ILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5811 | DIVISION 5 | T | 2026 | 8420000 | 2026 | 556000 | 2028 | 31401000 |  |  | 40377000
WAKE | SR 1010 (TEN-TEN ROAD) | NCDOT | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5825 | DIVISION 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 63900000 |  |  | 95400000 | COORDINATE WITH U-6066
WAKE | SR 2000 (FALLS OF NEUSE ROAD) | NCDOT | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5826 | DIVISION 5 | T |  |  |  |  | 2023 | 13501000 |  |  | 13501000 | UNDER CONSTRUCTION
WAKE | SR 1632 (LOUIS STEPHENS DRIVE) | NCDOT | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5827 | DIVISION 5 | T | 2020 | 1340000 |  |  | 2020 | 7699000 | 2019 | 1231000 | 10270000 | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
WAKE | MCCRIMMON PARKWAY | NCDOT | SR 3015 (AIRPORT BOULEVARD) TO SR 1002 (AVIATION PARKWAY) IN MORRISVILLE. WIDEN TO A FOUR LANE DIVIDED FACILITY, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5828 | DIVISION 5 | T |  |  |  |  | 2019 | 3097000 |  |  | 3097000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
WAKE | SR 1115 (AVENT FERRY ROAD) | HOLLY SPRINGS | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5889 | DIVISION 5 | T | 2026 | 1200000 | 2026 | 500000 | 2028 | 7300000 |  |  | 9000000
WAKE | NC 50 (CREEDMOOR ROAD) | NCDOT | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5891 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56401000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 66001000 |  |  | 124102000
WAKE | APEX PEAKWAY | APEX | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-5928 | DIVISION 5 | BGANY, BGDA, L |  |  |  |  | 2023 | 25000000 |  |  | 25000000
WAKE | SR 1728 (WADE AVENUE) | NCDOT | I-40 TO I-440 IN RALEIGH. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5936 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74499000 |  |  | 76699000
WAKE | NEW ROUTE | NCDOT | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5966 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2398000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 93701000 |  |  | 108999000 | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT
WAKE | VARIOUS | NCDOT | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-5967 | REGION C | BGANY, T |  |  | 2028 | 33000 | 2029 | 953000 |  |  | 986000
WAKE | VARIOUS | NCDOT | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6022 | REGION C | BGANY |  |  | 2022 | 451000 | 2023 | 2744000 |  |  | 3195000 | UNDER CONSTRUCTION
WAKE | VARIOUS | NCDOT | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6023 | DIVISION 5 | BGANY |  |  | 2022 | 250000 | 2023 | 2743000 |  |  | 2993000 | UNDER CONSTRUCTION
WAKE | VARIOUS | NCDOT | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6026 | DIVISION 5 | BGANY |  |  | 2022 | 450000 | 2023 | 1350000 |  |  | 1800000 | UNDER CONSTRUCTION. FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION
WAKE | US 1 | NCDOT | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6066 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 32400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40799000 |  |  | 74799000 | COORDINATE WITH U-5825
WAKE | SR 2542 (ROCK QUARRY ROAD) | RALEIGH | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6093 | DIVISION 5 | BGDA, L | 2021 | 1891000 |  |  | 2022 | 11062000 |  |  | 12953000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | HOLLY SPRINGS | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6094 | DIVISION 5 | BGDA, L | 2020 | 1480000 |  |  | 2023 | 1521000 |  |  | 3001000 | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS
WAKE | SR 2763 (OLD HONEYCUTT ROAD) SR 1301 (PURFOY ROAD) | FUQUAY-VARINA | INTERSECTION OF OLD HONEYCUTT ROAD (SR 2763) AND PURFOY ROAD (SR 1301) IN FUQUAY-VARINA. INTERSECTION IMPROVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6096 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION
WAKE | SR 5220 (JONES SAUSAGE ROAD) | NCDOT | SR 1004 (EAST GARNER ROAD) TO I-40 IN GARNER. WIDEN ROADWAY FROM SOUTH OF SR 2585 (WILMINGTON ROAD) TO I-40, INCLUDING ACCESS POINT IMPROVEMENTS, AND CONSTRUCT IMPROVEMENTS AT SR 1004 INTERSECTION AND I-40 INTERCHANGE. | HIGHWAY | ECONOMIC DEVELOPMENT | 5 | CAPITAL AREA MPO | U-6099 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMAZON
WAKE | US 401 | NCDOT | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6112 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24099000 |  |  | 82099000 | COORDINATE WITH R-2721 AND U-5746
WAKE | US 401 | NCDOT | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6116 | NOT FUNDED | T | NOT FUNDED | 2200000 | NOT FUNDED | 1400000 | NOT FUNDED | 4500000 |  |  | 8100000
WAKE | VARIOUS | NCDOT | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6117 | DIVISION 5 | BGANY | 2027 | 100000 | 2027 | 300000 | 2028 | 3800000 |  |  | 4200000
WAKE | VARIOUS | NCDOT | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6119 | DIVISION 5 | BGANY | 2027 | 100000 | 2027 | 200000 | 2028 | 4300000 |  |  | 4600000
WAKE | SR 1664 (DURALEIGH ROAD) | NCDOT | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6193 | NOT FUNDED | T | NOT FUNDED | 8500000 | NOT FUNDED | 770000 | NOT FUNDED | 12400000 |  |  | 21670000
WAKE | VARIOUS | NCDOT | GARNER CITYWIDE SIGNAL SYSTEM | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6194 | DIVISION 5 | BGANY | 2027 | 100000 | 2027 | 360000 | 2028 | 3200000 |  |  | 3660000
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | NCDOT | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | U-6217 | DIVISION 5 | T | 2028 | 13401000 | 2028 | 1142000 | 2031 | 27100000 |  |  | 41643000
WAKE | NC 98 | WAKE FOREST | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6222 | EXEMPT | BGDA, S |  |  |  |  | 2021 | 1050000 | 2020 | 150000 | 1200000 | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION
WAKE | SR 2700 (WHITE OAK RD) | GARNER | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6225 | DIVISION 5 | BGDA, L | 2021 | 75000 |  |  | 2023 | 2080000 |  |  | 2155000 | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS.
WAKE | SR 1624 (CARPENTER FIRE STATION ROAD) | CARY | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6227 | DIVISION 5 | BGDA, L | 2021 | 5629000 |  |  | 2023 | 8100000 |  |  | 13729000 | RIGHT OF WAY IN PROGRESS.
WAKE | US 401 BUSINESS (SOUTH MAIN STREET) SR 2051 ROAD); | ROLESVILLE | SR 2051 (BURLINGTON MILLS ROAD), EAST OF ROLESVILLE MIDDLE SCHOOL TO US 401 BUSINESS (SOUTH MAIN STREET) IN ROLESVILLE. REALIGN ROADWAY AND CONSTRUCT NEW INTERSECTION WITH SOUTH MAIN STREET. US 401 BUSINESS (SOUTH MAIN STREET), SR 2051 (BURLINGTON MILLS ROAD) TO NORTH OF SR 1003 (EAST YOUNG STREET) / SR 1945 (WEST YOUNG STREET) IN ROLESVILLE. CONSTRUCT SIDEWALK EXTENSIONS AND COMPLETE STREET IMRPOVEMENTS. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6241 | DIVISION 5 | BGDA, L |  |  |  |  | 2022 | 20452000 |  |  | 20452000 | UNDER CONSTRUCTION
WAKE | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | RALEIGH | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6242 | DIVISION 5 | BGDA, L | 2023 | 1700000 | 2023 | 1100000 | 2023 | 11148000 |  |  | 13948000 | RIGHT-OF-WAY IN PROGRESS.
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | HOLLY SPRINGS | FLINT POINT LANE TO SR 1301 (SUNSET LAKE ROAD) IN HOLLY SPRINGS. WIDEN TO A FOUR-LANE MEDIAN-DIVIDED FACILITY AND CONSTRUCT SIDEWALK. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6243 | DIVISION 5 | BGDA, L |  |  |  |  | 2022 | 18000000 |  |  | 18000000 | UNDER CONSTRUCTION
WAKE | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | WENDELL | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | HIGHWAY | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | U-6244 | EXEMPT | BGDA, L | 2022 | 110000 |  |  | 2023 | 423000 |  |  | 533000 | RIGHT-OF-WAY IN PROGRESS.
WAKE | VARIOUS | NCDOT | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS - REGIONAL IMPACT CATEGORY | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | W-5205REG | REGION C
WAKE | US 501 BUSINESS (ROXBORO STREET) | NCDOT | US 501 BUSINESS (ROXBORO STREET) AT SR 1443 (HORTON ROAD) AND SR 1641 (DENFIELD STREET) | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | W-5705AI | REGION C | HSIP |  |  |  |  | 2024 | 1320000 |  |  | 1320000
WAKE | NC 42 | NCDOT | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | W-5805A | REGION C | HSIP | 2023 | 235000 |  |  | 2024 | 725000 |  |  | 960000
WAKE | NC 98 BUSINESS | NCDOT | US 1, CLOVERLEAF DRIVE, AND RETAIL DRIVE / HAMPTON WAY IN WAKE FOREST. REVISE TRAFFIC SIGNALS. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | W-5805B | REGION C | [10 empty] | PROJECT DELETED; WORK TO BE ACCOMPLISHED UNDER U-6023.
WAKE | SR 1820 (LEAD MINE ROAD) | NCDOT | SR 1827 (LYNN ROAD) INTERSECTION IN RALEIGH. CONSTRUCT PEDESTRIAN REFUGE ISLANDS, AND REVISE CURB RAMPS, CROSSWALKS, AND OTHER PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | W-5805C | DIVISION 5 | HSIP |  |  |  |  | 2022 | 292000 |  |  | 292000 | UNDER CONSTRUCTION
WAKE | NC 42 | NCDOT | BRIDGE 910023 OVER MIDDLE CREEK. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | W-5805D | REGION C | HSIP |  |  |  |  | 2022 | 184000 |  |  | 184000 | UNDER CONSTRUCTION
WAKE | NC 98 | NCDOT | SR 2057 / SR 4465 (MOORES POND ROAD) | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | W-5805E | REGION C | HSIP | 2023 | 100000 |  |  | 2024 | 1230000 |  |  | 1330000
WAKE | SR 1004 (GARNER ROAD); TIMBER DRIVE EAST | NCDOT | SR 2539 (YEARGAN ROAD), SR 2564 (CREECH ROAD), AND SHENSTONE BOULEVARD INTERSECTIONS IN GARNER. UPGRADE TRAFFIC SIGNALS | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO | W-5805H | DIVISION 5 | HSIP |  |  |  |  | 2021 | 75000 |  |  | 75000 | UNDER CONSTRUCTION
WAKE | TRIANGLE TRANSIT AUTHORITY | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TA-4818A | PUBLIC TRANSIT | 5307, 5339 | [6 empty] | 2021 | 962000 | 962000
WAKE | GORALEIGH | GORALEIGH | REPLACEMENT BUS AND BUS FACILITIES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TA-4903 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 16417000 | 16417000
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TA-4903A | PUBLIC TRANSIT | 5307, CMAQ, L, S | [6 empty] | 2020 | 1126000 | 1126000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH PARK AND RIDE AT POOLE ROAD. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TA-5116 | PUBLIC TRANSIT | 5307 |  |  |  |  | 2021 | 455000 |  |  | 455000
WAKE | TRIANGLE TRANSIT AUTHORITY | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TA-5123A | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 3242000 | 3242000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | BUS REPLACEMENT | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TA-5140 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 4500000 | 4500000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GO RALEIGH | GO RALEIGH | SIX EXPANSION BUSES FOR ADDING ROUTE EXPANSION SERVICE. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TA-5186 | DIVISION 5 | [10 empty] | ACQUISITION IN PROGRESS BY GO RALEIGH
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | ADA EXPANSION BUS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TA-5202 | PUBLIC TRANSIT | 5307, 5339, L | [6 empty] | 2020 | 1184000 | 1184000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | GORALEIGH CAPITAL PROJECTS (PASSENGER AMENITIES, PEDESTRIAN CONNECTIONS, FACILITY MAINTENANCE, UPGRADE AND UPKEEPS ETC) | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TC-0015 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 10922000 | 10922000
WAKE | GOTRIANGLE | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TC-0016 | PUBLIC TRANSIT | BGDA, L | 2022 | 12000 |  |  | 2022 | 550000 | 2022 | 110000 | 672000
WAKE | GOTRIANGLE | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TC-0017 | PUBLIC TRANSIT | BGDA, L | 2022 | 14000 |  |  | 2022 | 330000 | 2022 | 130000 | 474000
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | US 64 BUSINESS (NEW HOPE ROAD) IN RALEIGH. CONSTRUCT TRANSFER FACILITY. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | TD-4912 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION BY GO RALEIGH
WAKE | GOCARY | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5264 | PUBLIC TRANSIT | L, T |  |  |  |  | 2023 | 20700000 |  |  | 20700000
WAKE | CARY TRANSIT / C-TRAN | CARY TRANSIT / C-TRAN | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | TD-5264B | DIVISION 5 | FEDT, L, T |  |  |  |  | 2020 | 7000000 |  |  | 7000000
WAKE | GO TRIANGLE | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | TD-5269 | DIVISION 5 | DP, O, T |  |  |  |  | 2020 | 53160000 |  |  | 53160000 | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | SOUTH WILMINGTON STREET AT PECAN ROAD IN RALEIGH. CONSTRUCT OFF-STREET TRANSFER FACILITY. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | TD-5272 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION BY GO RALEIGH
WAKE | GO TRIANGLE | GO TRIANGLE | EXPAND EXISTING GARAGE FACILITY IN MORRISVILLE. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5285 | REGION C | [10 empty] | IN PROGRESS
WAKE | GO TRIANGLE | GO TRIANGLE | PARK AND RIDE LOT AT SR 1774 (DISTRICT DRIVE). ADD SPACES, IMPROVE LIGHTING AND CONSTRUCT SHELTERS. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5287 | REGION C | [10 empty] | IN PROGRESS
WAKE | GO RALEIGH | GO RALEIGH | INTERSECTION OF SR 2298 (EDENTON STREET) AND NORTH SALISBURY STREET IN RALEIGH. CONSTRUCT BUS STOP SHELTER. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5293 | REGION C | [10 empty] | UNDER CONSTRUCTION BY GO TRIANGLE
WAKE | GORALEIGH | GORALEIGH | BUS STOP IMPROVEMENTS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5304 | PUBLIC TRANSIT | L | [6 empty] | 2022 | 3273000 | 3273000
WAKE | CARY TRANSIT/C-TRAN | CARY TRANSIT/C-TRAN | DOWNTOWN CARY MULTI-MODAL FACILITY. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5305 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 44200000 |  |  | 44200000
WAKE | VARIOUS | GO RALEIGH | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | TD-5307 | DIVISION 5 | L, O, T | 2027 | 1500000 |  |  | 2028 | 6658000 |  |  | 8158000
WAKE | GORALEIGH | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5308 | PUBLIC TRANSIT | L | 2022 | 2750000 |  |  | 2023 | 13800000 | 2022 | 4000000 | 20550000
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SITES IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE PE | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TD-5309 | DIVISION 5 | BGDA, L | [6 empty] | 2020 | 752000 | 752000
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOPS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE ROW | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TD-5309A | DIVISION 5 | BGDA, L | 2020 | 250000 | [6 empty] | 250000
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SIGHTS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE CON | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TD-5309B | DIVISION 5 | BGDA, L |  |  |  |  | 2020 | 1500000 |  |  | 1500000
WAKE | GOTRIANGLE | GOTRIANGLE | EXISTING PARK AND RIDE IMPROVEMENTS | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5314 | PUBLIC TRANSIT | L | [6 empty] | 2022 | 1105000 | 1105000
WAKE | GOTRIANGLE | GOTRIANGLE | BUILD NEW PARK AND RIDE AT HILLSBOROUGH ST AND I-440 IN RALEIGH. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5315 | PUBLIC TRANSIT | L |  |  |  |  | 2023 | 5200000 | 2022 | 2220000 | 7420000
WAKE | GOTRIANGLE | GOTRIANGLE | BUILD NEW PARK AND RIDE AT CREEDMOOR AND I-540 OR AT FALLS OF NEUSE AND I-540 IN RALEIGH. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5316 | PUBLIC TRANSIT | L |  |  |  |  | 2024 | 1500000 | 2023 | 1100000 | 2600000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH CONSTRUCTION OF PARK AND RIDE IN ROLESVILLE. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5317 | PUBLIC TRANSIT | L |  |  |  |  | 2021 | 55000 |  |  | 55000
WAKE | GORALEIGH | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5318 | PUBLIC TRANSIT | L | 2024 | 2249000 |  |  | 2025 | 2989000 | 2024 | 547000 | 5785000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT CRABTREE VALLEY MALL | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5319 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 324000 |  |  | 324000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT TRIANGLE TOWNE CENTER | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TD-5320 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 324000 |  |  | 324000
WAKE | AUTHORITY TRIANGLE TRANSIT | AUTHORITY TRIANGLE TRANSIT | FIXED GUIDEWAY - COMMUTER RAIL SERVICE- DURHAM/RALEIGH | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TE-4903B | PUBLIC TRANSIT | FED |  |  |  |  | 2020 | 222000 |  |  | 222000
WAKE | GORALEIGH | GORALEIGH | FIXED ROUTE PREVENTATIVE MAINTENANCE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5 | CAPITAL AREA MPO | TG-0013 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 9600000 | 9600000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH CAPITAL PROJECTS. | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5 | CAPITAL AREA MPO | TG-0015 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 4401000 | 4401000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH ADA PARATRANSIT SERVICE. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TG-4729B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 5000000 | 5000000
WAKE | GORALEIGH | GORALEIGH | ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TG-4792B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 10000000 | 10000000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | CARY TRANSIT/C-TRAN | PREVENTIVE MAINTENANCE, BUS FACILITIES, SUPPORT EQUIPMENT, AND SOFTWARE | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5 | CAPITAL AREA MPO | TG-4806 | PUBLIC TRANSIT | 5307, 5339, L | [6 empty] | 2020 | 615000 | 615000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TG-4935A | PUBLIC TRANSIT | 5307, 5339, L | [6 empty] | 2020 | 34275000 | 34275000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | CAPITAL COST OF CONTRACTING | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5 | CAPITAL AREA MPO | TG-6791 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 5000000 | 5000000
WAKE | GOTRIANGLE | GOTRIANGLE | PURCHASE AND INSTALL SIGNAGE AT DESIGNATED LOCATIONS ALONG I-540 AND I-40 FOR BUS ON SHOULDER SYSTEM. (BOSS) UTILIZE EASTBOUND SHOULDER OF I-540 BETWEEN NC-147 AND CAPITAL BLVD AND EASTBOUND ON I-40 BETWEEN WADE AVENUE AND S SAUNDERS STREET. | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TG-6814 | EXEMPT | BGDA, L | [6 empty] | 2021 | 454000 | 454000
WAKE | GORALEIGH | GORALEIGH | DESIGN, PURCHASE, AND INSTALL NEW AMENITIES AT 13 BUS STOP LOCATIONS ALONG ROUTES IN WAKE COUNTY,UPGRADES INCLUDE SHELTERS, BENCH, PAD, OR SOME COMBINATIONS | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TG-6815 | DIVISION 5 | BGDA, L | [6 empty] | 2021 | 907000 | 907000
WAKE | GORALEIGH | GORALEIGH | DEVELOPED ENHANCED TRANSFER POINTS THROUGHOUT GO RALEIGH SYSTEM IN LOCATION WITH HIGH RIDERSHIP (75 + BOARDINGS PER DAY) | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TG-6816 | DIVISION 5 | BGDA, L | [6 empty] | 2021 | 1185000 | 1185000
WAKE | WAKE COORDINATED TRANSPORTATION SERVICE | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TK-6170 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1580000 | 1580000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GO RALEIGH | GO RALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT WESTERN CORRIDOR (DOWNTOWN RALEIGH TO DOWNTOWN CARY). | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TL-0006 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 45168000 | 2022 | 1500000 | 46668000
WAKE | GORALEIGH | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN ON BUS RAPID TRANSIT IN WAKE TRANSIT PLAN NORTHERN CORRIDOR. | PUBLIC TRANSIT | PLANNING | 5 | CAPITAL AREA MPO | TL-0007 | PUBLIC TRANSIT | L | [6 empty] | 2020 | 5540000 | 5540000
WAKE | GOTRIANGLE | GOTRIANGLE | EARLY PROJECT DEVELOPMENT ACTIVITIES FOR COMMUTER RAIL FROM GARNER TO WESTERN DURHAM | PUBLIC TRANSIT | PLANNING | 5 | CAPITAL AREA MPO | TL-0008 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 9200000 | 9200000
WAKE | GOTRIANGLE | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TL-0011 | PUBLIC TRANSIT | BGDA, L | 2022 | 18000 |  |  | 2022 | 252000 | 2022 | 64000 | 334000
WAKE | GORALEIGH | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT SOUTHERN CORRIDOR ( DOWNTOWN RALEIGH TO DOWNTOWN GARNER) | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TL-0013 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 27777000 | 2022 | 1500000 | 29277000
WAKE | GOCARY | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TL-0019 | EXEMPT | CMAQ, L | 2022 | 167000 |  |  | 2022 | 1144000 | 2022 | 51000 | 1362000
WAKE | GORALEIGH | GORALEIGH | BUILD PARK AND RIDE FACILITY AT GORMAN STREET AT I-40 IN RALEIGH | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TL-0023 | PUBLIC TRANSIT | L |  |  |  |  | 2027 | 1614000 | 2025 | 1432000 | 3046000
WAKE | GOAPEX | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 | PUBLIC TRANSIT | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TM-0026 | DIVISION 5 | BGDA, L | [6 empty] | 2021 | 610000 | 610000
WAKE | GOTRIANGLE | GOTRIANGLE | OPERATING ASSISTANCE FOR TOWN OF MORRISVILLE NODE BASED SMART SHUTTLE. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TM-0035 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 3621000 | 3621000
WAKE | GORALEIGH | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TM-0039 | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2022 | 2000000 |  |  | 2000000
WAKE | WAKE COORDINATED TRANSIT SERVICE | WAKE COORDINATED TRANSIT SERVICE | WAKE COORDINATED TRANSIT SERVICES OPERATING ASSISTANCE. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TN-6116 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 4070000 | 4070000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 5 | CAPITAL AREA MPO | TO-0002 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 1368000 | 1368000
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 5 | CAPITAL AREA MPO | TO-5128 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2021 | 152980000 | 152980000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 5 | CAPITAL AREA MPO | TO-5129 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2021 | 19401000 | 19401000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | TRIANGLE TRANSIT AUTHORITY | TRIANGLE TRANSIT AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 5 | CAPITAL AREA MPO | TO-5131 | PUBLIC TRANSIT | L, SMAP | [6 empty] | 2021 | 37855000 | 37855000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | TO-6166A | REGION C | L, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21993000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6114000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 115649000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | 145256000
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, CARY TO RALEIGH. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | TO-6166B | REGION C | L |  |  |  |  | 2022 | 45168000 | 2022 | 1500000 | 46668000
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, RALEIGH TO GARNER. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | TO-6166C | REGION C | L |  |  |  |  | 2022 | 27777000 | 2022 | 1500000 | 29277000
WAKE | GORALEIGH | GORALEIGH | TOWN OF WAKE FOREST REVERSE CIRCULATOR OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 5 | CAPITAL AREA MPO | TO-6168 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 2283000 | 2283000
WAKE | TRIANGLE TRANSIT AUTHORITY | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | PUBLIC TRANSIT | PLANNING | 5 | CAPITAL AREA MPO | TP-4732B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 2952000 | 2952000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | PLANNING | 5 | CAPITAL AREA MPO | TP-5100A | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 1872000 | 1872000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | PLANNING ASSISTANCE - 5307 | PUBLIC TRANSIT | PLANNING | 5 | CAPITAL AREA MPO | TP-5100B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 3826000 | 3826000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE | PUBLIC TRANSIT | PLANNING | 5 | CAPITAL AREA MPO | TP-5112 | PUBLIC TRANSIT | 5307, 5311, L, S | [6 empty] | 2020 | 1836000 | 1836000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GO RALEIGH | GO RALEIGH | CONSTRUCT BUS RAPID TRANSIT ON NEW BERN CORRIDOR. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TP-5160 | PUBLIC TRANSIT
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT NEW BERN CORRIDOR | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TP-5160A | DIVISION 5 | 5309, ARP, FUZ, L | 2021 | 3086000 |  |  | 2021 | 68507000 | 2020 | 20841000 | 92434000
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT NEW BERN CORRIDOR, BETTERMENT FUNDING | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TP-5160B | DIVISION 5 | L |  |  |  |  | 2023 | 814000 |  |  | 814000
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | 5310 OPERATING | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TQ-6953 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2021 | 1200000 | 1200000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | 5310 ADMIN. | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TQ-7006 | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 65000 | 65000
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | 5310 ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 5 | CAPITAL AREA MPO | TQ9037 | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 65000 | 65000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | 5310 CAPITAL AND ADMIN | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TQ-9037 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2021 | 938000 | 938000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO | TS-5104 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 542000 | 542000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GOTRIANGLE | GOTRIANGLE | GOTRIANGLE WAKE COUNTY BUS PLAN UPDATE. | PUBLIC TRANSIT | PLANNING | 5 | CAPITAL AREA MPO | TU-0006 | PUBLIC TRANSIT | CMAQ, L | [6 empty] | 2021 | 740000 | 740000
WAKE | GORALEIGH | GORALEIGH | MAJOR INVESTMENT STUDY/ALTERNATIVES ANALYSIS FOR BUS RAPID TRANSIT EXTENSION TO RESEARCH TRIANGLE PARK AND CLAYTON. | PUBLIC TRANSIT | PLANNING | 5 | CAPITAL AREA MPO | TU-0007 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 430000 | 430000
WAKE | PIEDMONT CORRIDOR | NCDOT | CAPITAL YARD PHASE 1 IMPROVEMENTS - EXTEND TRACKS 1 AND 2, MAJOR WORK TRACK 3 | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-2918H | [11 empty] | IN PROGRESS
WAKE | VARIOUS | NSR RR | BOYLAN CROSSOVER IN RALEIGH. | RAIL | TRANSITION | 5 | CAPITAL AREA MPO | P-5005D | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAKE | NCRR | NCDOT | RALEIGH UNION STATION PROJECT - PHASE I. CONSTRUCT RALEIGH TRAIN STATION AND ASSOCIATED RAIL TRACK AND SIDING IMPROVEMENTS TO INCREASE PASSENGER AND FREIGHT CAPACITY. | RAIL | PRE-STI (HISTORIC) | 5 | CAPITAL AREA MPO | P-5500 | PRE-STI (TRANSITION) | [10 empty] | DP FUNDS - FEDERAL TIGER GRANT; O FUNDS - STATE LEGISLATIVE ALLOCATION FOR RAIL; PROJECT INCLUDES IN-KIND PROPERTY CONTRIBUTION BY TRIANGLE TRANSIT (CONTINGENT ON TT BOARD OF TRUSTEES APPROVAL) - 4 PARCELS TOTALING 3.5 ACRES WITH TAX VALUE OF $2.9 MILLION
WAKE | NCRR | NCDOT | CSXT S-LINE, TRACK AND SIGNAL IMPROVEMENTS - BOYLAN WYE CROSSOVER | RAIL | TRANSITION | 5 | CAPITAL AREA MPO | P-5500A | [11 empty] | DELETED - WORK TO BE ACCOMPLISHED UNDER P-5005D.
WAKE | NCRR | NCDOT | STATION SITE WORK | RAIL | PRE-STI (HISTORIC) | 5 | CAPITAL AREA MPO | P-5500B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAKE | NCRR | NCDOT | TRACK IMPROVEMENTS | RAIL | PRE-STI (HISTORIC) | 5 | CAPITAL AREA MPO | P-5500C | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAKE | CSX S LINE | NCDOT | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5707 | REGION C | T |  |  |  |  | 2024 | 32100000 |  |  | 32100000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NORFOLK SOUTHERN H LINE | CARY | CONSTRUCT GRADE SEPARATION AT HARRISON AVENUE CROSSING (734755X) IN CARY. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5708 | REGION C | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16600000 |  |  | 22600000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD
WAKE | CSX | NCDOT | CROSSING 630607N AT NEW HOPE CHURCH ROAD IN RALEIGH. CONSTRUCT GRADE SEPARATION. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5715 | REGION C | DP, T |  |  |  |  | 2024 | 19001000 |  |  | 19001000 | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD
WAKE | CSX | NCDOT | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5718 | REGION C | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29344000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3344000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 23798000 |  |  | 56486000 | "O"FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734
WAKE | CSX | NCDOT | CROSSING 630601X AT SR 2006 (DURANT ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5720 | REGION C | T |  |  |  |  | 2024 | 18200000 |  |  | 18200000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | NCDOT | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5734 | STATEWIDE MOBILITY | O, T | 2027 | 21000000 |  |  | 2029 | 16700000 |  |  | 37700000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718
WAKE | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | NCDOT | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5736 | STATEWIDE MOBILITY | O, T | 2028 | 200000 |  |  | 2029 | 3000000 |  |  | 3200000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
WAKE | CSX S LINE | NCDOT | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5737 | STATEWIDE MOBILITY | DP, T | 2022 | 6111000 | 2022 | 1220000 | 2025 | 22200000 |  |  | 29531000 | RIGHT OF WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | NCDOT | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5738 | NOT FUNDED | O, T | NOT FUNDED | 1800000 |  |  | NOT FUNDED | 11498000 |  |  | 13298000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
WAKE | CSX S LINE | NCDOT | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | RAIL | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO | P-5739 | NOT FUNDED | O, T | NOT FUNDED | 2200000 |  |  | NOT FUNDED | 14401000 |  |  | 16601000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION
WAKE | CSX S-LINE, CSX SA-LINE. | NCDOT | RALEIGH TO NC 98. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753A | STATEWIDE MOBILITY
WAKE | CSX S-LINE | NCDOT | RALEIGH UNION STATION TO NC 98 - S-LINE RAIL IMPROVEMENTS. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753AA | STATEWIDE MOBILITY
WAKE | CSX S-LINE | NCDOT | HARGETT STREET, MORGAN STREET AND CAPITAL BOULEVARD ROADWAY IMPROVEMENTS AND PEDESTRIAN OVERPASS AT JONES STREET. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753AE | STATEWIDE MOBILITY
WAKE | CSX S-LINE | NCDOT | WHITAKER MILL ROAD ROADWAY IMPROVEMENTS. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753AF | STATEWIDE MOBILITY
WAKE | CSX S-LINE | NCDOT | HIGHWOODS BOULEVARD GRADE SEPERATION. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753AG | STATEWIDE MOBILITY
WAKE | CSX S-LINE | NCDOT | GRESHAM LAKE AND LIGON MILL GRADE SEPERATIONS AND ROADWAY IMPROVEMENTS AT SEAWELL AND FRIENDSHIP CHAPEL ROAD. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753AH | STATEWIDE MOBILITY
WAKE | GORALEIGH | GORALEIGH | RALEIGH UNION STATION BUS FACILITY INTER-CITY/COMMUTER RAIL PARK AND RIDE | RAIL | LOCALLY SELECTED | 5 | CAPITAL AREA MPO | TL-0020 | PUBLIC TRANSIT | CMAQ, L |  |  |  |  | 2022 | 5625000 |  |  | 5625000
WAKE | FAYETTEVILLE STREET (SR 2513) | NCDOT | FAYETTEVILLE STREET AND THE CAROLINA COASTAL RAILWAY TRACKS CROSSING CLOSURE IN KNIGHTDALE. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 5 | CAPITAL AREA MPO | Y-4805F | DIVISION 5 | RR |  |  |  |  | 2025 | 1600000 |  |  | 1600000
WAKE, DURHAM | I-40 | NCDOT | EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | I-5995 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2026 | 32400000 |  |  | 32400000 | Combined with I-5996.
WAKE, DURHAM | I-540 | NCDOT | I-40 IN DURHAM TO US 70 IN RALEIGH. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | I-5998 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 14999000 |  |  | 14999000 | COORDINATE WITH I-5999 AND I-6000
WAKE, DURHAM | I-540 | NCDOT | I-40 IN DURHAM TO US 1 IN RALEIGH. BRIDGE PRESERVATION / REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | I-6000 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2027 | 7600000 |  |  | 7600000 | COORDINATE WITH I-5998 AND I-5999
WAKE, DURHAM | US 70 (GLENWOOD AVENUE) | NCDOT | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | HIGHWAY | STI (PRIORITIZATION) | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-5518 | STATEWIDE MOBILITY | NHP | 2026 | 153208000 | 2026 | 15714000 | 2026 | 168498000 |  |  | 337420000 | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT
WAKE, DURHAM | VARIOUS | NCDOT | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS - DIVISION NEEDS CATEGORY | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5205DIV | DIVISION 5
WAKE, DURHAM | GOTRIANGLE TRANSIT | GOTRIANGLE TRANSIT | PURCHASE EXPANSION VEHICLES FOR DRX ROUTE. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6668 | REGION C | [10 empty] | IN ACQUISITION
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | TRIANGLE J COUNCIL OF GOVERNMENTS (COG) | TRIANGLE J COUNCIL OF GOVERNMENTS (COG). TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN TRIANGLE OZONE NON-ATTAINMENT AREA. | HIGHWAY | OTHER | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | C-4924 | EXEMPT
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | NCDOT | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) | HIGHWAY | OTHER | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | C-4924A | EXEMPT | [10 empty] | IN PROGRESS
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | NCDOT | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) | HIGHWAY | OTHER | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | C-4924B | EXEMPT | CMAQ, L | [6 empty] | 2022 | 714000 | 714000 | IN PROGRESS
WAKE, DURHAM, ORANGE | AUTHORITY TRIANGLE TRANSIT | AUTHORITY TRIANGLE TRANSIT | FIXED GUIDEWAY - LIGHT RAIL SERVICE- CARY/RALEIGH | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5, 7 | CAPITAL AREA MPO | TE-4903A | PUBLIC TRANSIT | FED |  |  |  |  | 2020 | 1500000000 |  |  | 1500000000
WAKE, DURHAM, ORANGE | AUTHORITY TRIANGLE TRANSIT | AUTHORITY TRIANGLE TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4821B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 7876000 | 7876000 | FUNDS AUTHORIZED IN PROGRESS
WAKE, FRANKLIN | I-87 / FUTURE I-87 / US 64 / US 264 | NCDOT | SR 1003 (ROLESVILLE ROAD) TO NASH COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 5 | CAPITAL AREA MPO, KERR-TAR RPO | I-6001 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2025 | 30000000 |  |  | 30000000
WAKE, FRANKLIN | CSX S-LINE | NCDOT | NC 98 TO FRANKLINTON - S-LINE RAIL IMPROVEMENTS. | RAIL | OTHER | 5 | CAPITAL AREA MPO | P-5753BA | STATEWIDE MOBILITY
WAKE, FRANKLIN, VANCE | CSX S-LINE | NCDOT | NC 98 TO FRANKLINTON. | RAIL | OTHER | 5 | CAPITAL AREA MPO, KERR-TAR RPO | P-5753B | STATEWIDE MOBILITY
WAKE, FRANKLIN, WARREN | VARIOUS | NCDOT | INSTALL LONG-LIFE PAVEMENT MARKINGS | HIGHWAY | SAFETY | 5 | CAPITAL AREA MPO, KERR-TAR RPO | W-5805F | DIVISION 5 | HSIP |  |  |  |  | 2021 | 2553000 |  |  | 2553000 | UNDER CONSTRUCTION
WAKE, HARNETT | NC 55 | NCDOT | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 5, 6 | CAPITAL AREA MPO | R-5705B | REGION C | T | 2021 | 25171000 | 2021 | 1300000 | 2023 | 70722000 |  |  | 97193000 | UNDER CONSTRUCTION.
WAKE, IREDELL, MECKLENBURG, ROWAN, CLEVELAND, UNION, CABARRUS, GASTON, JOHNSTON, DURHAM, LINCOLN, FRANKLIN, ORANGE, CHATHAM, GRANVILLE, HARNETT | STATEWIDE TRAFFIC OPERATIONS | NCDOT | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT IN THE TRIANGLE AND METROLINA AREAS. | HIGHWAY | OTHER | 4, 5, 6, 7, 8, 9, 10, 12 | CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO, GASTON-CLEVELAND-LINCOLN MPO, CABARRUS-ROWAN MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HO-0010A | STATEWIDE MOBILITY | CRPANY, S(M) | [6 empty] | 2023 | 4000000 | 4000000
WAKE, JOHNSTON | I-40 | NCDOT | I-440 / US 64 (EXIT 301) TO NC 42 (EXIT 312). ADD 2 GENERAL-PURPOSE LANES IN EACH DIRECTION. | HIGHWAY | STI (PRIORITIZATION) | 4, 5 | CAPITAL AREA MPO | I-5111 | [11 empty] | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK 2019-2033.
WAKE, JOHNSTON | NEW ROUTE (FUTURE NC 540) | NCDOT | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), EAST OF US 401 TO I-40. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 4, 5 | CAPITAL AREA MPO | R-2828 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 135750000 |  |  | 135750000 | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT.
WAKE, JOHNSTON | I-40; I-87; I-440; US 1 / US 64 | NCDOT | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | HIGHWAY | STI (PRIORITIZATION) | 4, 5 | CAPITAL AREA MPO | U-6101 | NOT FUNDED | NHP | NOT FUNDED | 1000000 | NOT FUNDED | 500000 | NOT FUNDED | 138201000 |  |  | 139701000
WAKE, JOHNSTON | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 4, 5 | CAPITAL AREA MPO | TO-6166 | REGION A, C
WAKE, JOHNSTON, FRANKLIN, GRANVILLE | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | HIGHWAY | OTHER | 4, 5 | CAPITAL AREA MPO | C-5604 | EXEMPT | BGDA, CMAQ, L | 2020 | 1188000 |  |  | 2020 | 23622000 | 2020 | 4081000 | 28891000 | IN PROGRESS
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | PEDESTRIAN, BICYCLE, AND TRANSIT PROJECTS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO). | BIKE/PED | OTHER | 4, 5, 6 | CAPITAL AREA MPO | EL-5100 | DIVISION 4, 5, 6
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. | BIKE/PED | LOCALLY SELECTED | 4, 5, 6 | CAPITAL AREA MPO | U-5530 | DIVISION 4, 5, 6 | BGDA, L, TADA |  |  |  |  | 2020 | 3500000 |  |  | 3500000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | INTERSECTION IMPROVEMENTS AT MULTIPLE LOCATIONS WITHIN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) BOUNDARY. | HIGHWAY | LOCALLY SELECTED | 4, 5, 6 | CAPITAL AREA MPO | HL-0008 | EXEMPT | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 4, 5, 6 | CAPITAL AREA MPO | HL-0105 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 12588000 |  |  | 12588000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | LOCALLY SELECTED | 4, 5, 6 | CAPITAL AREA MPO | U-4735 | DIVISION 4, 5, 6 | BGDA |  |  |  |  | 2028 | 77938000 |  |  | 77938000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. | HIGHWAY | LOCALLY SELECTED | 4, 5, 6 | CAPITAL AREA MPO | U-4850 | DIVISION 4, 5, 6 | BGDA, L | [6 empty] | 2022 | 19000000 | 19000000 | FORMERLY U-9999B - IN PROGRESS
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. | HIGHWAY | LOCALLY SELECTED | 4, 5, 6 | CAPITAL AREA MPO | U-5118 | DIVISION 4, 5, 6 | BGDA, L |  |  |  |  | 2020 | 3750000 |  |  | 3750000 | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS.
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | LOCALLY SELECTED | 4, 5, 6 | CAPITAL AREA MPO | U-6218 | DIVISION 4, 5, 6 | TADA |  |  |  |  | 2022 | 21180000 |  |  | 21180000
WAKE, LEE, VANCE | CSX S-LINE | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. | PUBLIC TRANSIT | PLANNING | 5, 8 | CAPITAL AREA MPO, KERR-TAR RPO, TRIANGLE AREA RPO | TU-0004 | PUBLIC TRANSIT | FED, L, S | [6 empty] | 2021 | 1505000 | 1505000 | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS
WAKE, ORANGE | GOTRIANGLE TRANSIT | GOTRIANGLE TRANSIT | PURCHASE EXPANSION VEHICLES FOR CRX ROUTE. | PUBLIC TRANSIT | CAPITAL (NON-STI) | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6669 | REGION C, D | [10 empty] | IN ACQUISITION
WARREN | NC 903 | NCDOT | NC 903 CAUSEWAY ON EATONS FERRY BRIDGE OVER LAKE GASTON. UPGRADE GUARDRAIL. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO | HS-2005B | REGION C | HSIP |  |  |  |  | 2021 | 130000 |  |  | 130000 | UNDER CONSTRUCTION
WARREN | US 1 / US 158 | NCDOT | US 1 / US 158 AT SR 1237 (MASON DREWRY ROAD). INTERSECTION REALIGNMENT. | HIGHWAY | SAFETY | 5 | KERR-TAR RPO | HS-2005O | STATEWIDE MOBILITY | HSIP |  |  | 2024 | 80000 | 2024 | 335000 |  |  | 415000
WARREN | I-85 | NCDOT | NORTH OF SR 1237 (MANSON DREWRY ROAD) TO VIRGINIA STATE LINE | HIGHWAY | TRANSITION | 5 | KERR-TAR RPO | I-0914BB | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WARREN | CSX S-LINE | NCDOT | MANSON AXTELL ROAD GRADE SEPERATION. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753CJ | STATEWIDE MOBILITY
WARREN | CSX S-LINE | NCDOT | RIDGEWAY TO PASCHALL | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753D | STATEWIDE MOBILITY
WARREN | CSX S-LINE | NCDOT | RIDGEWAY TO THE VA STATE LINE - S-LINE RAIL IMPROVEMENTS. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753DA | STATEWIDE MOBILITY
WARREN | CSX S-LINE | NCDOT | SOUL CITY BOULEVARD ROADWAY IMPROVEMENTS INCLUDING DREWRY GRADE SEPERATION. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753DC | STATEWIDE MOBILITY
WARREN | CSX S-LINE | NCDOT | NORLINA ROADWAY IMPROVEMENTS. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753DD | STATEWIDE MOBILITY
WARREN | CSX S-LINE | NCDOT | WISE ROADWAY IMPROVEMENTS INLUDING FELTS ROAD. | RAIL | OTHER | 5 | KERR-TAR RPO | P-5753DE | STATEWIDE MOBILITY
WARREN, VANCE | I-85 | NCDOT | US 158 (MILE POST 213.5) IN VANCE COUNTY TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION AND SIGN UPGRADES. | HIGHWAY | PRE-STI (HISTORIC) | 5 | KERR-TAR RPO | I-0914 | PRE-STI (TRANSITION)
WARREN, VANCE | I-85 | NCDOT | REFURBISH SIGNS AND SIGNPOSTS | HIGHWAY | PRE-STI (HISTORIC) | 5 | KERR-TAR RPO | I-0914A | [11 empty] | COMPLETE
WARREN, VANCE | I-85 | NCDOT | ITS DEPLOYMENT FOR PARTS BA AND BB | HIGHWAY | PRE-STI (HISTORIC) | 5 | KERR-TAR RPO | I-0914BC | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WASHINGTON | NC 32 | NCDOT | PRESERVATION OF BRIDGE 930015 ON NC 32 OVER ALBEMARLE SOUND. | HIGHWAY | BRIDGES | 1 | ALBEMARLE RPO | HB-0016 | REGION A | BFP |  |  |  |  | 2027 | 50000000 |  |  | 50000000
WASHINGTON | SR 1126 (ROPER NEWLAND ROAD) | NCDOT | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5936 | DIVISION 1 | T | 2026 | 200000 | 2026 | 200000 | 2028 | 18700000 |  |  | 19100000
WASHINGTON | SR 1106 (MORATTOCK ROAD) | NCDOT | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 1 | ALBEMARLE RPO | R-5937 | DIVISION 1 | T | 2028 | 400000 | 2028 | 200000 | 2032 | 12300000 |  |  | 12900000
WASHINGTON | WASHINGTON COUNTY | WASHINGTON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 1 | ALBEMARLE RPO | TK-6171 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 356000 | 356000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA | US 221 | BLOWING ROCK | MAIN STREET IN BLOWING ROCK TO MOSES H CONE MEMORIAL PARK AND BASS LAKE. CONSTRUCT SIDEWALK. | BIKE/PED | LOCALLY SELECTED | 11 | HIGH COUNTRY RPO | EB-5798 | EXEMPT | [10 empty] | UNDER CONSTRUCTION. PROJECT TO BE ADMINISTERED BY THE TOWN OF BLOWING ROCK
WATAUGA | TOWN OF BLOWING ROCK | BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). | BIKE/PED | LOCALLY SELECTED | 11 | HIGH COUNTRY RPO | EB-5924 | EXEMPT | FLAP, L, S(M) | 2023 | 90000 |  |  | 2024 | 2014000 |  |  | 2104000 | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF S(M) IS CONTINGENCY FUNDS ON WBS 44607
WATAUGA | US 421 (KING STREET) MULTI-USE PATH | BOONE | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | EB-5983 | DIVISION 11 | L, TA5200 | 2024 | 20000 |  |  | 2025 | 1865000 | 2023 | 300000 | 2185000
WATAUGA | HUNTING HILLS LANE | BOONE | REPLACE BRIDGE NO. 940346 OVER SOUTH FORK OF NEW RIVER IN BOONE. | HIGHWAY | MUNICIPAL BRIDGE | 11 | HIGH COUNTRY RPO | B-5979 | DIVISION 11 | BGOFF, L |  |  |  |  | 2022 | 1500000 |  |  | 1500000 | RIGHT-OF-WAY IN PROGRESS.
WATAUGA | SR 1594 | NCDOT | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0062 | DIVISION 11 | DP, HFB | 2024 | 140000 |  |  | 2025 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
WATAUGA | US 221 / US 321 | NCDOT | DEERFIELD ROAD TO BOONE MALL. INSTALL PEDESTRIAN COUNTDOWN HEADS AND FLASHING YELLOW ARROWS AT VARIOUS INTERSECTIONS. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO | HS-2011B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 116000 |  |  | 116000 | UNDER CONSTRUCTION.
WATAUGA | NC 105 | NCDOT | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2566B | REGION F | NHP, T | 2022 | 14365000 | 2022 | 13700000 | 2025 | 87600000 |  |  | 115665000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $4M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
WATAUGA | NC 105 | NCDOT | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2566BA | DIVISION 11 | T |  |  | 2019 | 2850000 | 2022 | 23680000 |  |  | 26530000 | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
WATAUGA | NC 105 | NCDOT | SR 1658 (OLD SHULLS MILL ROAD) INTERSECTION. REALIGN SR 1658 (OLD SHULLS MILL ROAD). | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2566BB | REGION F | T |  |  |  |  | 2023 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION.
WATAUGA | US 421/US 321 | NCDOT | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2615 | REGION F | T | 2027 | 40900000 | 2027 | 1500000 | 2030 | 50199000 |  |  | 92599000
WATAUGA | SR 1522 (DEERFIELD ROAD) | NCDOT | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5830 | DIVISION 11 | T | 2024 | 5800000 | 2024 | 1200000 | 2025 | 6200000 |  |  | 13200000
WATAUGA | US 421 | NCDOT | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5872 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 |  |  | 8300000
WATAUGA | US 321 | NCDOT | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5874 | NOT FUNDED | NHP | NOT FUNDED | 5700000 | NOT FUNDED | 1000000 | NOT FUNDED | 7799000 |  |  | 14499000
WATAUGA | US 421 | NCDOT | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5903 | NOT FUNDED | T | NOT FUNDED | 30600000 | NOT FUNDED | 1500000 | NOT FUNDED | 54902000 |  |  | 87002000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NCDOT | US 421/321 WEST OF BOONE TO US 421 EAST OF BOONE. CONSTRUCT FREEWAY ON NEW LOCATION SOUTH OF BOONE. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5915 | DIVISION 11
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NCDOT | US 321/421 WEST OF BOONE TO NC 105 | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5915A | NOT FUNDED | NHP | NOT FUNDED | 81700000 | NOT FUNDED | 400000 | NOT FUNDED | 165600000 |  |  | 247700000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NCDOT | NC 105 TO US 221/321 SOUTH OF BOONE | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5915B | DIVISION 11 | NHP | 2028 | 84800000 | 2028 | 600000 | 2031 | 246600000 |  |  | 332000000 | BUILD NC BOND FUNDING: $6.2M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE)
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NCDOT | US 221/321 TO US 221/421 EAST OF BOONE | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5915C | NOT FUNDED | NHP | NOT FUNDED | 133800000 | NOT FUNDED | 400000 | NOT FUNDED | 384600000 |  |  | 518800000
WATAUGA | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | NCDOT | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | U-5810 | DIVISION 11 | T | 2022 | 13400000 | 2022 | 1500000 | 2024 | 22300000 |  |  | 37200000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
WATAUGA | APPALCART | APPALCART | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11 | HIGH COUNTRY RPO | TK-6107 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1872000 | 1872000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA | APPALCART | APPALCART | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 11 | HIGH COUNTRY RPO | TO-6101 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 9544000 | 9544000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA | APPALCART | APPALCART | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 11 | HIGH COUNTRY RPO | TO-6104 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 2632000 | 2632000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA, AVERY | NC 105 | NCDOT | US 221 TO SR 1107 (NC 105 BYPASS) IN BOONE. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-2566
WAYNE | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | EXTEND RUNWAY TO 5500 FEET. | AVIATION | STI (PRIORITIZATION) | 4 | EASTERN CAROLINA RPO | AV-5811 | DIVISION 4 | T |  |  |  |  | 2027 | 1000000 |  |  | 1000000
WAYNE | WAYNE EXECUTIVE JETPORT (GWW) | WAYNE EXECUTIVE JETPORT (GWW) | EXTEND RUNWAY. | AVIATION | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | AV-5843 | DIVISION 4 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7700000 |  |  | 7700000
WAYNE | STONEY CREEK GREENWAY | Goldsboro | US 70 BYPASS TO SR 1560 (ROYALL AVENUE). CONSTRUCT 10 FOOT WIDE ASPHALT GREENWAY. | BIKE/PED | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | EB-5707 | DIVISION 4 | L, SRTS |  |  |  |  | 2022 | 391000 |  |  | 391000 | UNDER CONSTRUCTION.
WAYNE | GOLDSBORO | Goldsboro | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | BIKE/PED | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | EB-5850 | DIVISION 4 | L, TA5200 |  |  |  |  | 2025 | 127000 | 2024 | 19000 | 146000
WAYNE | SR 1958 (BENNETTS BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 950117 OVER NE CAPE FEAR RIVER. | HIGHWAY | BRIDGES | 4 | EASTERN CAROLINA RPO | B-4844 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS.
WAYNE | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GOLDSBORO PLANNING ORGANIZATION. | HIGHWAY | LOCALLY SELECTED | 4 | GOLDSBORO URBAN AREA MPO | HL-0097 | EXEMPT | CRPDA, L |  |  |  |  | 2023 | 867000 |  |  | 867000
WAYNE | SR 1537 (AIRPORT ROAD) | NCDOT | INSTALL ALL WAY STOP AT SR 1537 (AIRPORT ROAD) AND SR 1545 (MT. CARMEL CHURCH ROAD). | HIGHWAY | SAFETY | 4 | GOLDSBORO URBAN AREA MPO | HS-2004C | DIVISION 4 | HSIP |  |  |  |  | 2022 | 66000 |  |  | 66000 | UNDER CONSTRUCTION.
WAYNE | SR 1002 (PIKEVILLE-PRINCETON ROAD) | NCDOT | INSTALL ALL WAY STOP WITH ISLAND AT SR 1002 (PIKEVILLE-PRINCETON ROAD) AND SR 1320 (HINNANT ROAD). | HIGHWAY | SAFETY | 4 | EASTERN CAROLINA RPO | HS-2004D | DIVISION 4 | HSIP |  |  |  |  | 2022 | 65000 |  |  | 65000 | UNDER CONSTRUCTION.
WAYNE | NC 111 | NCDOT | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT NC 111 AND SR 1754 (ZION CHURCH ROAD). | HIGHWAY | SAFETY | 4 | EASTERN CAROLINA RPO | HS-2004E | REGION A | HSIP |  |  |  |  | 2022 | 152000 |  |  | 152000 | UNDER CONSTRUCTION.
WAYNE | SR 1744 (INDIAN SPRINGS ROAD) | NCDOT | INSTALL ALL WAY STOP AT SR 1744 (INDIAN SPRINGS ROAD) AND SR 1941 (NORTHEAST CHURCH ROAD). | HIGHWAY | SAFETY | 4 | EASTERN CAROLINA RPO | HS-2004I | DIVISION 4 | HSIP |  |  |  |  | 2022 | 65000 |  |  | 65000 | UNDER CONSTRUCTION.
WAYNE | I-795 | NCDOT | WILSON COUNTY LINE TO SR 2075 (ASH STREET). UPGRADE GUARDRAIL, SHOULDER AND MEDIAN REPAIRS. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO | I-6047 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 6893000 |  |  | 6893000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034.
WAYNE | US 117 (FUTURE I-795) | NCDOT | US 70 TO DUPLIN COUNTY LINE. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO | I-6048 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2021 | 7892000 |  |  | 7892000 | UNDER CONSTRUCTION.
WAYNE | US 117 BUS/US 117 (N. WILLIAMS STREET) | NCDOT | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-2714 | REGION A | L, T | 2020 | 3510000 |  |  | 2020 | 24187000 | 2020 | 4290000 | 31987000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
WAYNE | US 117 (FUTURE I-795) | NCDOT | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | U-3125C | REGION A | NHP | 2026 | 100000 | 2026 | 138000 | 2028 | 13300000 |  |  | 13538000
WAYNE | US 117 (FUTURE I-795) | NCDOT | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-3125D | REGION A | NHP | 2027 | 13530000 | 2027 | 2172000 | 2029 | 59400000 |  |  | 75102000
WAYNE | US 117 (FUTURE I-795) | NCDOT | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-3125E | NOT FUNDED | NHP | NOT FUNDED | 35788000 | NOT FUNDED | 1513000 | NOT FUNDED | 135500000 |  |  | 172801000
WAYNE | US 117 (FUTURE I-795) | NCDOT | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-3125F | NOT FUNDED | NHP | NOT FUNDED | 20760000 | NOT FUNDED | 4729000 | NOT FUNDED | 62700000 |  |  | 88189000
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | SR 1560 (ROYAL AVENUE) TO NORTH OF SR 1572 (SAULSTON ROAD) IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-3609
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | SR 1560 (ROYAL AVENUE) TO SR 1003 (NEW HOPE ROAD). | HIGHWAY | TRANSITION | 4 | GOLDSBORO URBAN AREA MPO | U-3609A | PRE-STI (TRANSITION) | [10 empty] | COMPLETED.
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | WIDEN TO FOUR LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 WITH INTERSECTION IMPROVEMENT AT SR 1572 (SAULSTON ROAD). | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-3609B | REGION A | T | 2020 | 23339000 | 2020 | 3750000 | 2025 | 29670000 | 2020 | 2400000 | 59159000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE).
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | REALIGNMENT OF HOOD SWAMP ROAD. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-3609BA | REGION A | T |  |  |  |  | 2022 | 1780000 |  |  | 1780000 | UNDER CONSTRUCTION.
WAYNE | US 70 BUSINESS (EAST ASH STREET) | NCDOT | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-4407 | REGION A | T | 2026 | 3979000 | 2026 | 2090000 | 2028 | 17500000 |  |  | 23569000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | SR 1003 (NEW HOPE ROAD) TO US 70 IN GOLDSBORO. WIDEN TO FOUR LANES. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-4753 | DIVISION 4 | T | 2019 | 4180000 |  |  | 2025 | 8260000 |  |  | 12440000 | RIGHT-OF-WAY IN PROGRESS.
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | REALIGNMENT OF SR 1709 (CENTRAL HEIGHTS ROAD) AT BERKELEY BOULEVARD IN GOLDSBORO. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-5724 | REGION A | T |  |  |  |  | 2023 | 19839000 |  |  | 19839000 | UNDER CONSTRUCTION.
WAYNE | US 117 | NCDOT | SR 1120 (O'BERRY ROAD) IN GOLDSBORO. CONSTRUCT INTERCHANGE. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-5796 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION.
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | LOCKHAVEN DRIVE TO COUNTRY DAY ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-5994 | DIVISION 4 | T |  |  |  |  | 2023 | 450000 |  |  | 450000 | UNDER CONSTRUCTION.
WAYNE | US 70 | NCDOT | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-6110 | REGION A | NHP | 2025 | 200000 | 2025 | 2200000 | 2027 | 4100000 |  |  | 6500000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-6204 | DIVISION 4 | BG50200 | 2025 | 3500000 | 2025 | 2400000 | 2028 | 11400000 |  |  | 17300000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-6205 | DIVISION 4 | T | 2027 | 1900000 | 2027 | 1000000 | 2029 | 20300000 |  |  | 23200000
WAYNE | SR 1713 (MILLER'S CHAPEL ROAD) | NCDOT | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-6206 | DIVISION 4 | T | 2027 | 2500000 | 2027 | 900000 | 2029 | 5600000 |  |  | 9000000
WAYNE | NC 581 (BILL LANE BOULEVARD) | NCDOT | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 4 | GOLDSBORO URBAN AREA MPO | U-6207 | DIVISION 4 | T | 2027 | 1700000 | 2027 | 400000 | 2029 | 5001000 |  |  | 7101000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | SR 1622 (WOODSIDE DRIVE) TO SR 1752 (SAULSTON-PATETOWN ROAD). SAFETY IMPROVEMENTS INCLUDING WIDENING, SHOULDERS, SUPERELEVATION REVISIONS, OVERLAYING PAVEMENT MARKINGS AND SIGNING. | HIGHWAY | TRANSITION | 4 | EASTERN CAROLINA RPO | W-5500 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAYNE | SR 1927 (GENOA ROAD) | NCDOT | SR 1927 (GENOA ROAD) AT CRESCENT DRIVE. INTERSECTION IMPROVEMENTS. | HIGHWAY | SAFETY | 4 | GOLDSBORO URBAN AREA MPO | W-5704K | DIVISION 4 | HSIP |  |  |  |  | 2024 | 274000 |  |  | 274000 | UNDER CONSTRUCTION.
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 4 | GOLDSBORO URBAN AREA MPO | TG-4752A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | GOLDSBORO URBAN AREA MPO | TG-4752B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1004000 | 1004000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | GOLDSBORO URBAN AREA MPO | TG-4752C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 700000 | 700000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | ROUTINE CAPITAL AND PREVENTIVE MAINTENANCE | 4 | GOLDSBORO URBAN AREA MPO | TG-6146 | PUBLIC TRANSIT | 5311 | [6 empty] | 2020 | 176000 | 176000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | GOLDSBORO URBAN AREA MPO | TK-5179 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1224000 | 1224000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 4 | GOLDSBORO URBAN AREA MPO | TO-4719 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 3360000 | 3360000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 4 | GOLDSBORO URBAN AREA MPO | TO-6107 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 168000 | 168000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 4 | GOLDSBORO URBAN AREA MPO | TP-5116 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 124000 | 124000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | CAPITAL (NON-STI) | 4 | GOLDSBORO URBAN AREA MPO | TS-5129 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 20000 | 20000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | BAIN STREET | NCDOT | NORFOLK SOUTHERN CROSSING 722874X IN GOLDSBORO. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | GOLDSBORO URBAN AREA MPO | RX-2004F | DIVISION 4 | RR |  |  |  |  | 2024 | 417000 |  |  | 417000
WAYNE | JEFFERSON STREET | NCDOT | NORFOLK SOUTHERN CROSSING 722868U IN GOLDSBORO. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | GOLDSBORO URBAN AREA MPO | RX-2004M | DIVISION 4 | RR |  |  |  |  | 2027 | 411000 |  |  | 411000
WAYNE, DUPLIN | US 117 (FUTURE I-795) | NCDOT | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | HIGHWAY | STI (PRIORITIZATION) | 3, 4 | EASTERN CAROLINA RPO | U-3125B | NOT FUNDED | NHP | NOT FUNDED | 25266000 | NOT FUNDED | 10475000 | NOT FUNDED | 73300000 |  |  | 109041000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
WAYNE, DUPLIN, SAMPSON | US 117 (FUTURE I-795) | NCDOT | I-40 TO I-795. UPGRADE ROADWAY TO INTERSTATE STANDARDS, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 3, 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO, MID-CAROLINA RPO | U-3125
WAYNE, EDGECOMBE, WILSON | NC 111 | NCDOT | NC 111 FROM WAYNE/DUPLIN COUNTY LINE TO SR 1727 (DOLLARD TOWN ROAD). NC 111 FROM US 70 BYPASS OVERPASS TO NC 222. NC 111/NC 222 FROM FREMONT LIMITS TO SR 1513 (RED HILL ROAD). NC 111/NC 222 FROM STANTONSBURG LIMITS TO SARATOGA LIMITS. NC 111 FROM NC 222 IN WILSON COUNTY TO SR 1344 (SARA LEE ROAD) IN EDGECOMBE COUNTY. NC 111 FROM PRINCEVILLE TO EDGECOMBE/MARTIN COUNTY LINE. INSTALL RUMBLE STRIPS WITH SIX-INCH PAVEMENT MARKINGS. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO | HS-2004V | REGION A | HSIP |  |  |  |  | 2023 | 2161000 |  |  | 2161000 | UNDER CONSTRUCTION.
WAYNE, GREENE | US 13 | NCDOT | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 2, 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | R-5853 | DIVISION 2, 4 | T | 2025 | 2488000 | 2025 | 3040000 | 2027 | 8800000 |  |  | 14328000
WAYNE, JOHNSTON | US 70 | NCDOT | US 70 BYPASS TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO | R-5829
WAYNE, JOHNSTON | US 70 | NCDOT | US 70 BYPASS TO WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | STI (PRIORITIZATION) | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, UPPER COASTAL PLAIN RPO | R-5829A | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40072000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7908000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 101599000 |  |  | 149579000
WILKES | WILKES COUNTY AIRPORT (UKF) | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. | AVIATION | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | AV-5894 | DIVISION 11 | T | 2024 | 600000 |  |  | 2024 | 12300000 |  |  | 12900000
WILKES | SR 1313 | NCDOT | REPLACE BRIDGE 960075 OVER FISH DAM CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | B-4977 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 700000 |  |  | 700000 | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT
WILKES | SR 2418 | NCDOT | REPLACE BRIDGE 960004 OVER LITTLE HUNTING CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | BR-0108 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 1200000 |  |  | 1200000 | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT
WILKES | SR 1745 (SHUMATE MOUNTAIN ROAD) | NCDOT | REPLACE BRIDGE 960166 ON SR 1745 OVER WEST PRONG ROARING RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | BR-0124 | HIGHWAY FUND | DP, HFB | 2020 | 40000 |  |  | 2021 | 2900000 |  |  | 2940000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 1002 (TRAPHILL ROAD) | NCDOT | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | BR-0125 | HIGHWAY FUND | DP, HFB | 2020 | 280000 |  |  | 2021 | 2650000 |  |  | 2930000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 1749 (AUSTIN TRAPHILL ROAD) | NCDOT | REPLACE BRIDGE 960667 ON SR 1749 OVER SPARKS CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | BR-0126 | HIGHWAY FUND | DP, HFB | 2020 | 80000 |  |  | 2021 | 1550000 |  |  | 1630000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 2516 | NCDOT | REPLACE BRIDGE 960733 OVER CUB CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | BR-0208 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 600000 |  |  | 600000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.154
WILKES | SR 1148 | NCDOT | REPLACE BRIDGE 960419 OVER NAKED CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | BR-0209 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 650000 |  |  | 650000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.153
WILKES | ROAD) SR 1185 (CURTIS BRIDGE | NCDOT | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0020 | DIVISION 11 | DP, HFB | 2025 | 1120000 |  |  | 2027 | 6400000 |  |  | 7520000
WILKES | SR 1559 | NCDOT | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0063 | DIVISION 11 | DP, HFB | 2024 | 140000 |  |  | 2025 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | SR 1567 | NCDOT | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0064 | DIVISION 11 | DP, HFB | 2024 | 112000 |  |  | 2025 | 640000 |  |  | 752000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | SR 1170 | NCDOT | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0065 | DIVISION 11 | DP, HFB | 2026 | 126000 |  |  | 2027 | 720000 |  |  | 846000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | SR 1355 | NCDOT | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0066 | DIVISION 11 | DP, HFB | 2024 | 140000 |  |  | 2025 | 800000 |  |  | 940000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | US 421 BUSINESS | NCDOT | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | HIGHWAY | BRIDGES | 11 | HIGH COUNTRY RPO | HB-0069 | REGION F | DP, HFB | 2025 | 1680000 |  |  | 2027 | 9600000 |  |  | 11280000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | NEW ROUTE | NCDOT | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-0616 | NOT FUNDED | T | NOT FUNDED | 18200000 | NOT FUNDED | 1100000 | NOT FUNDED | 132201000 |  |  | 151501000
WILKES | NC 268 | NCDOT | NC 18 TO SR 1966 (AIRPORT ROAD). CONSTRUCT SIDEWALK FROM NC 18 TO SHAVER STREET. WIDEN TO FIVE-LANES FROM SHAVER STREET TO FAIRPLAINS ROAD. WIDEN TO FOUR-LANES DIVIDED FROM FAIRPLAINS ROAD TO SR 1966 (AIRPORT ROAD). | HIGHWAY | TRANSITION | 11 | HIGH COUNTRY RPO | R-2603 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WILKES | NC 115 | NCDOT | US 421 TO 2ND STREET. WIDEN ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5759 | DIVISION 11 | T | 2022 | 12615000 | 2022 | 900000 | 2024 | 27300000 | 2020 | 1365000 | 42180000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE);
WILKES | SR 1001 (OAKWOODS ROAD) | NCDOT | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5772 | DIVISION 11 | T | 2025 | 3000000 | 2025 | 1500000 | 2027 | 10448000 |  |  | 14948000
WILKES | NC 268 | NCDOT | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | R-5906 | DIVISION 11 | BGLT5, T | 2028 | 40885000 | 2028 | 600000 | 2031 | 52299000 |  |  | 93784000 | BUILD NC BOND FUNDING: $17M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE)
WILKES | US 421 | NCDOT | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO REDUCED CONFLICT INTERSECTIONS AND ADD SERVICE ROADS. | HIGHWAY | STI (PRIORITIZATION) | 11 | HIGH COUNTRY RPO | U-5312 | REGION F | NHP |  |  |  |  | 2023 | 31700000 |  |  | 31700000 | UNDER CONSTRUCTION.
WILKES | NC 268 | NCDOT | NC 268 EAST OF NORTH WILKESBORO. WIDEN MULTIPLE SECTIONS, IMPROVE SHOULDERS, AND INSTALL GUARDRAIL, RUMBLE STRIPS, AND PAVEMENT MARKINGS. | HIGHWAY | TRANSITION | 11 | HIGH COUNTRY RPO | W-5503 | REGION F | [10 empty] | PART COMPLETE
WILKES | NC 268 | NCDOT | SR 1966 (AIRPORT ROAD) TO SR 2026 (AUSTIN TRAPHILL ROAD). INSTALL GUARDRAIL AND PAVEMENT MARKINGS. | HIGHWAY | SAFETY | 11 | HIGH COUNTRY RPO | W-5503A | REGION F | HSIP |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION.
WILKES | WILKES TRANSPORTATION AUTHORITY | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 11 | HIGH COUNTRY RPO | TK-6172 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 912000 | 912000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | WILSON | WILSON | HOMINY CREEK GREENWAY AND TRAIL NETWORK PLAN. | BIKE/PED | LOCALLY SELECTED | 4 | UPPER COASTAL PLAIN RPO | BL-0069 | EXEMPT | DP | [6 empty] | 2023 | 950000 | 950000 | DP FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT.
WILSON | US 117 | NCDOT | REPLACE BRIDGE 970047 OVER SEABOARD COAST LINE RAILROAD. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-5666 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 4469000 |  |  | 4469000 | UNDER CONSTRUCTION.
WILSON | SR 1339 (SHARPE SHORE ROAD) | NCDOT | REPLACE BRIDGE 970092 OVER TOWN SWAMP. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-5998 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
WILSON | SR 1400 (ROCK QUARRY ROAD) | NCDOT | REPLACE BRIDGE 970096 OVER TRIBUTARY OF TOWN CREEK. | HIGHWAY | BRIDGES | 4 | UPPER COASTAL PLAIN RPO | B-6000 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
WILSON | US 264 | NCDOT | US 264 FROM I-795 TO TOISNOT SWAMP. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | HI-0006 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 10075000 |  |  | 10075000 | UNDER CONSTRUCTION.
WILSON | US 264 | NCDOT | US 264 FROM TOISNOT SWAMP TO THE GREENE COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | HI-0007 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 11015000 |  |  | 11015000 | UNDER CONSTRUCTION.
WILSON | US 264 | NCDOT | US 264 FROM THE WILSON COUNTY LINE TO I-95. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | HI-0014 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 6000000 |  |  | 6000000
WILSON | SR 1356 (RALEIGH ROAD PARKWAY) | NCDOT | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | HIGHWAY | LOCALLY SELECTED | 4 | UPPER COASTAL PLAIN RPO | HL-0034 | EXEMPT | BA |  |  | 2022 | 75000 | 2023 | 2407000 | 2021 | 45000 | 2527000 | UNDER CONSTRUCTION.
WILSON | SR 1103 (WIGGINS MILL ROAD) | NCDOT | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT SR 1103 (WIGGINS MILL ROAD) AND SR 1169 (RADFORD ROAD). | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | HS-2004F | DIVISION 4 | HSIP |  |  |  |  | 2022 | 30000 |  |  | 30000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004G AND HS-2004H.
WILSON | SR 1320 (AIRPORT BOULEVARD) | NCDOT | SR 1320 (AIRPORT BOULEVARD) AT CHELSEA DRIVE AND SR 1320 (AIRPORT BOULEVARD) AT JETSTREAM DRIVE IN WILSON. INSTALL TRAFFIC SIGNALS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | HS-2004O | DIVISION 4 | HSIP |  |  |  |  | 2023 | 241000 |  |  | 241000 | UNDER CONSTRUCTION.
WILSON | I-95 | NCDOT | JOHNSTON COUNTY LINE (MILE MARKER 108.2) TO NORTH OF SR 1116 (GOVERNOR HUNT ROAD) (MILE MARKER 114.5). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | I-5936 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2021 | 3303000 |  |  | 3303000 | UNDER CONSTRUCTION.
WILSON | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | NCDOT | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | U-5794 | NOT FUNDED | T | NOT FUNDED | 1000000 | NOT FUNDED | 946000 | NOT FUNDED | 9199000 |  |  | 11145000
WILSON | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | NCDOT | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | U-5941 | REGION A | BG5T50 | 2026 | 12100000 | 2026 | 3900000 | 2028 | 11000000 |  |  | 27000000
WILSON | WILSON | NCDOT | WILSON CITY SIGNAL SYSTEM. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | U-5945 | DIVISION 4 | BG5200 |  |  | 2024 | 700000 | 2025 | 6600000 |  |  | 7300000
WILSON | NC 58 (NASH STREET NW) | NCDOT | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 4 | UPPER COASTAL PLAIN RPO | U-6111 | REGION A | T | 2027 | 700000 | 2027 | 400000 | 2029 | 5400000 |  |  | 6500000
WILSON | US 301 | NCDOT | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | HIGHWAY | SAFETY | 4 | UPPER COASTAL PLAIN RPO | W-5804A | REGION A | HSIP | 2021 | 100000 |  |  | 2022 | 2334000 |  |  | 2434000 | UNDER CONSTRUCTION.
WILSON | CITY OF WILSON | CITY OF WILSON | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | TK-5178 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1304000 | 1304000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | WILSON COUNTY | WILSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 4 | UPPER COASTAL PLAIN RPO | TK-6173 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 344000 | 344000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | CITY OF WILSON | CITY OF WILSON | OPERATING ASSISTANCE | PUBLIC TRANSIT | MISCELLANEOUS/OTHER | 4 | UPPER COASTAL PLAIN RPO | TO-4779 | PUBLIC TRANSIT | 5311, L, SMAP | [6 empty] | 2020 | 4464000 | 4464000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | SR 1163 (GOLDSBORO STREET) | NCDOT | AT-GRADE CROSSING IMPROVEMENTS AT CSX (CROSSING 629 847Y) IN WILSON. | RAIL | RAIL-HIGHWAY GRADE CROSSING CLOSURE | 4 | UPPER COASTAL PLAIN RPO | RC-2004A | DIVISION 4 | RR | 2024 | 50000 | 2025 | 50000 | 2025 | 1200000 |  |  | 1300000
WILSON | SR 1163 (GOLDSBORO STREET / HERRING AVENUE) | NCDOT | CSX CROSSING 629847Y IN WILSON. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004A | DIVISION 4 | RR |  |  |  |  | 2024 | 800000 |  |  | 800000
WILSON | SR 1100 (CHICOPEE ROAD) | NCDOT | CSX CROSSING 629847Y IN WILSON. INSTALL ACTIVE WARNING DEVICES. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004B | DIVISION 4 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
WILSON | SR 1329 (VAN SLYKE ROAD) | NCDOT | CSX CROSSING 629843W IN WILSON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004E | DIVISION 4 | RR |  |  |  |  | 2024 | 417000 |  |  | 417000
WILSON | GREEN STREET | NCDOT | CSX CROSSING 629849M IN WILSON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | RAIL-HIGHWAY GRADE CROSSING IMPROVEMENT | 4 | UPPER COASTAL PLAIN RPO | RX-2004I | DIVISION 4 | RR |  |  |  |  | 2025 | 417000 |  |  | 417000
YADKIN | US 21 BUS | NCDOT | REPLACE BRIDGE 980059 OVER JONESVILLE CREEK. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | B-4979 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT.
YADKIN | US 421 NORTHBOUND | NCDOT | REPLACE STRUCTURE 980105 OVER YADKIN RIVER OVERFLOW. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | B-5389 | HIGHWAY FUND | HFB | [9 empty] | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT.
YADKIN | NC 67 | NCDOT | REPLACE BRIDGE 980035 OVER YADKIN RIVER. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | B-5825 | REGION F | T |  |  |  |  | 2021 | 11465000 |  |  | 11465000 | UNDER CONSTRUCTION.
YADKIN | US 21 BUSINESS | NCDOT | REPLACE BRIDGE 980029 OVER I-77. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | B-5833 | REGION F | BFP | 2021 | 1600000 |  |  | 2024 | 4599000 |  |  | 6199000 | RIGHT-OF-WAY IN PROGRESS.
YADKIN | SR 1512 | NCDOT | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | BR-0109 | HIGHWAY FUND | HFB | 2022 | 3000 | 2022 | 5000 | 2023 | 788000 |  |  | 796000 | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT
YADKIN | SR 1325 (MOUNTAIN VIEW CHURCH ROAD) | NCDOT | REPLACE BRIDGE 980189 ON SR 1325 OVER SOUTH DEEP CREEK. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | BR-0127 | HIGHWAY FUND | DP, HFB | 2020 | 45000 |  |  | 2021 | 850000 |  |  | 895000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
YADKIN | SR 1152 | NCDOT | REPLACE BRIDGE 980020 OVER SOUTH DEEP CREEK. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | BR-0200 | HIGHWAY FUND | HFB |  |  |  |  | 2019 | 850000 |  |  | 850000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENT HFB PROJECT NUMBER 17BP.11.R.183.
YADKIN | SR 1119 | NCDOT | REPLACE BRIDGE 980028 OVER NORTH LITTLE HUNTING CREEK. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | BR-0205 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.130
YADKIN | I-77 | NCDOT | SOUTH OF SR 1125 (ASHBURY CHURCH ROAD-MILEPOST 71) TO US 21 IN YADKIN COUNTY (EXIT 79) | HIGHWAY | PRE-STI (HISTORIC) | 11 | NORTHWEST PIEDMONT RPO | I-2808A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
YADKIN | I-77 | NCDOT | MILEMARKER 71.8 TO MILEMARKER 75.8. PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 11 | NORTHWEST PIEDMONT RPO | I-5864 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 6285000 |  |  | 6285000 | COMBINE WITH I-5865 FOR LETTING.
YADKIN | I-77 | NCDOT | MILEMARKER 75.8 TO US 21 (EXIT 79). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 11 | NORTHWEST PIEDMONT RPO | I-5865 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 2990000 |  |  | 2990000 | COMBINE WITH I-5864 FOR LETTING.
YADKIN | SR 1605 (OLD US 421) | NCDOT | SR 1146 (SHACKTOWN ROAD) TO SR 1711 (SPEER BRIDGE ROAD). CONSTRUCT NEW ROADWAY TO REALIGN SR 1605 WITH SR 1711 AND CONSTRUCT A ROUNDABOUT AT THE INTERSECTION WITH SR 1146. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5730 | DIVISION 11 | T |  |  |  |  | 2022 | 3216000 |  |  | 3216000 | UNDER CONSTRUCTION.
YADKIN | US 601 | NCDOT | US 601 (CAROLINA AVENUE) AND NC 67 (MAIN STREET). UPGRADE INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5831 | DIVISION 11 | T |  |  | 2023 | 650000 | 2024 | 3900000 |  |  | 4550000 | RIGHT-OF-WAY IN PROGRESS
YADKIN | US 601 (SOUTH STATE STREET) | NCDOT | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5894 | NOT FUNDED | NHP | NOT FUNDED | 750000 | NOT FUNDED | 100000 | NOT FUNDED | 4500000 |  |  | 5350000 | COORDINATE WITH U-5809.
YADKIN | US 601 | NCDOT | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5896 | NOT FUNDED | T | NOT FUNDED | 2000000 | NOT FUNDED | 300000 | NOT FUNDED | 2100000 |  |  | 4400000
YADKIN | SR 1314 (EAST MAIN STREET) | NCDOT | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5909 | DIVISION 11 | BGLT5 | 2026 | 1900000 | 2026 | 5800000 | 2028 | 4300000 |  |  | 12000000
YADKIN | SR 1605 (OLD US 421) | NCDOT | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5912 | DIVISION 11 | T | 2023 | 600000 | 2023 | 100000 | 2024 | 1200000 |  |  | 1900000 | RIGHT-OF-WAY IN PROGRESS.
YADKIN | NC 67 | NCDOT | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5914 | DIVISION 11 | BGLT5, T | 2026 | 9000000 | 2026 | 1000000 | 2028 | 47130000 |  |  | 57130000 | BUILD NC BONDS: $25.2M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE)
YADKIN | US 601 (STATE STREET) | NCDOT | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | U-5809 | DIVISION 11 | T |  |  | 2023 | 800000 | 2024 | 11401000 |  |  | 12201000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894.
YADKIN | VARIOUS | NCDOT | DIVISION 11 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN REGIONAL CATEGORY. | HIGHWAY | SAFETY | 11 | NORTHWEST PIEDMONT RPO | W-5211REG | REGION F
YADKIN, SURRY | I-77 | NCDOT | SOUTH OF SR 1125 (MILE MARKER 71) IN YADKIN COUNTY TO US 21 BYPASS (MILE MARKER 83.5) IN SURRY COUNTY (EXIT 83). PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 11 | NORTHWEST PIEDMONT RPO | I-2808 | [11 empty] | SECTION A - GARVEE BOND FUNDING $35 MILLION; PAYBACK FY 2007 - FY 2018. SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
YADKIN, SURRY | I-77 | NCDOT | US 21 IN YADKIN COUNTY (EXIT 79) TO US 21 BYPASS (EXIT 83) IN SURRY COUNTY | HIGHWAY | INTERSTATE MAINTENANCE | 11 | NORTHWEST PIEDMONT RPO | I-2808B | [11 empty] | SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
YADKIN, SURRY | I-77 | NCDOT | US 21 IN YADKIN COUNTY (EXIT 79) TO MILEMARKER 83.4 IN SURRY COUNTY . PAVEMENT REHABILITATION. | HIGHWAY | INTERSTATE MAINTENANCE | 11 | NORTHWEST PIEDMONT RPO | I-5912 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
YADKIN, SURRY | NC 67, US 21 BUS | NCDOT | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | HIGHWAY | BRIDGES | 11 | NORTHWEST PIEDMONT RPO | R-5913
YADKIN, SURRY | NC 67, US 21 BUSINESS | NCDOT | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | HIGHWAY | STI (PRIORITIZATION) | 11 | NORTHWEST PIEDMONT RPO | R-5913A | DIVISION 11 | BG5200 | 2023 | 1100000 | 2023 | 220000 | 2025 | 3300000 |  |  | 4620000
YANCEY | US 19W | NCDOT | SR 1454 TO SR 1382 NEAR BURNSVILLE. INSTALL GUARDRAIL. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO | HS-2013J | REGION G | HSIP |  |  |  |  | 2024 | 1230000 |  |  | 1230000
YANCEY | NC 197 | NCDOT | NC 197 FROM SR 1338 TO THE MITCHELL COUNTY LINE, NEAR GREEN MOUNTAIN. INSTALL SHOULDER GUARDRAIL. | HIGHWAY | SAFETY | 13 | HIGH COUNTRY RPO | W-5813H | REGION G | HSIP |  |  |  |  | 2022 | 474000 |  |  | 474000 | COMPLETE
YANCEY | AUTHORITY YANCEY COUNTY TRANSPORTATION | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. | PUBLIC TRANSIT | STI (PRIORITIZATION) | 13 | HIGH COUNTRY RPO | TA-6723 | DIVISION 13 | L, T |  |  |  |  | 2024 | 2389000 | 2023 | 111000 | 2500000 | LOCAL FUNDING PROVIDED BY YANCEY COUNTY
YANCEY | YANCEY COUNTY TRANSPORTATION AUTHORITY | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | OPERATIONS AND MAINTENANCE | 13 | HIGH COUNTRY RPO | TK-6175 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 580000 | 580000 | FUNDS AUTHORIZED IN PROGRESS

## 2024-2033 STIP Funding Details
2024-2033 STATE TRANSPORTATION IMPROVEMENT PROGRAM | [12 empty] | DRAFT 2024-2033 STIP WINDOW
PROJECT ID | MODE | ROUTE/CITY | DESCRIPTION | DIVISION(S) | MPOs/RPOs | COMMENT | CATEGORY FUNDED | FUNDING COMMENT | FUND SOURCE | ACTIVITY | TOTAL FUNDED (MAY INCLUDE PREVIOUSLY AUTHORIZED FUNDS) | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | AFTER 2033
A-0009 | HIGHWAY | US 19, US 74, US 129, NC 28, NC 143 | CORRIDOR "K", ANDREWS TO NC 28 EAST OF ALMOND. UPGRADE ROADWAY TO INCLUDE EXISTING FACILITIES AND NEW LOCATION. | 14 | Southwestern RPO | [5 empty] | 84907000
A-0009A | HIGHWAY | FUTURE US 74 | US 19 BUSINESS IN ANDREWS TO US 129 | 14 | Southwestern RPO |  | NOT FUNDED |  | NHP | UTILITIES | 925000 | [11 empty] | 925000
A-0009A | HIGHWAY | FUTURE US 74 | US 19 BUSINESS IN ANDREWS TO US 129 | 14 | Southwestern RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 366000000 | [11 empty] | 366000000
A-0009A | HIGHWAY | FUTURE US 74 | US 19 BUSINESS IN ANDREWS TO US 129 | 14 | Southwestern RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 14300000 | [11 empty] | 14300000
A-0009CA | HIGHWAY | US 129, NC 143 | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | UTILITIES | 2030000
A-0009CA | HIGHWAY | US 129, NC 143 | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | CONSTRUCTION | 54624000 | FY 2023: 22226000; FY 2024: 18868000; FY 2025: 12984000
A-0009CA | HIGHWAY | US 129, NC 143 | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | RIGHT-OF-WAY | 1900000
A-0009CB | HIGHWAY | NC 143 | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | RIGHT-OF-WAY | 3300000
A-0009CB | HIGHWAY | NC 143 | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | UTILITIES | 1300000
A-0009CB | HIGHWAY | NC 143 | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | CONSTRUCTION | 133871000 | FY 2023: 40050000; FY 2024: 42485000; FY 2025: 30799000; FY 2026: 19198000
A-0009CC | HIGHWAY | NC 143, NC 28 | NC 143 FROM NORTH OF APPALACHIAN TRAIL TO NC 28; NC 28 FROM NC 143 TO WEST OF SR 1228 (STECOAH ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | RIGHT-OF-WAY | 2300000
A-0009CC | HIGHWAY | NC 143, NC 28 | NC 143 FROM NORTH OF APPALACHIAN TRAIL TO NC 28; NC 28 FROM NC 143 TO WEST OF SR 1228 (STECOAH ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | CONSTRUCTION | 77500000 | FY 2023: 18980000; FY 2024: 23432000; FY 2025: 18413000; FY 2026: 13053000; FY 2027: 3622000
A-0009CC | HIGHWAY | NC 143, NC 28 | NC 143 FROM NORTH OF APPALACHIAN TRAIL TO NC 28; NC 28 FROM NC 143 TO WEST OF SR 1228 (STECOAH ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHS | UTILITIES | 550000
A-0009CD | HIGHWAY | NC 28 | WEST OF SR 1228 (STECOAH ROAD) TO EAST OF SR 1235 (GUNTERS GAP ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | ADHS | CONSTRUCTION | 35100000 | [11 empty] | 35100000
A-0010 | HIGHWAY | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) IN ASHEVILLE TO TENNESSEE STATE LINE AT SAMS GAP. MULTI-LANE FREEWAY, PART ON NEW LOCATION. | 13 | French Broad River MPO, Land-of-Sky RPO | COORDINATE WITH B-4442, B-4443, B-4444. |  |  |  |  | 303926000
A-0010AA | HIGHWAY | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) TO US 25/70 | 13 | French Broad River MPO |  | REGION G |  | T | RIGHT-OF-WAY | 42700000 | FY 2028: 7007000; FY 2029: 10511000; FY 2030: 10511000; FY 2031: 6131000; FY 2032: 8540000
A-0010AA | HIGHWAY | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) TO US 25/70 | 13 | French Broad River MPO |  | REGION G |  | T | UTILITIES | 1000000 | FY 2028: 500000; FY 2029: 500000
A-0010AA | HIGHWAY | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) TO US 25/70 | 13 | French Broad River MPO |  | REGION G |  | T | CONSTRUCTION | 279800000 | FY 2031: 33107000; FY 2032: 69012000; FY 2033: 65188000 | 112493000
A-0010AB | HIGHWAY | I-26 (US 19/US 23) | US 25/70 TO SR 2207 (N BUNCOMBE SCHOOL ROAD) | 13 | French Broad River MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 72000000 | [11 empty] | 72000000
A-0010AB | HIGHWAY | I-26 (US 19/US 23) | US 25/70 TO SR 2207 (N BUNCOMBE SCHOOL ROAD) | 13 | French Broad River MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5600000 | [11 empty] | 5600000
A-0010AC | HIGHWAY | I-26 (US 19/US 23) | SR 2207 (N BUNCOMBE SCHOOL ROAD) TO SOUTH OF SR 2148 (STOCKTON ROAD) | 13 | French Broad River MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 700000 | [11 empty] | 700000
A-0010AC | HIGHWAY | I-26 (US 19/US 23) | SR 2207 (N BUNCOMBE SCHOOL ROAD) TO SOUTH OF SR 2148 (STOCKTON ROAD) | 13 | French Broad River MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 27000000 | [11 empty] | 27000000
A-0011 | HIGHWAY | US 64/NC 69 | NC 69, GEORGIA STATE LINE TO US 64. WIDEN TO FOUR LANES DIVIDED. US 64, NC 69 TO EAST OF NC 175. WIDEN TO MULTI-LANES. | 14 | Southwestern RPO | APD FUNDS ARE 100% FEDERAL |  |  |  |  | 47732000
A-0011C | HIGHWAY | NC 69 | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). WIDEN TO FOUR-LANES | 14 | Southwestern RPO | UNDER CONSTRUCTION | EXEMPT |  | ADHS | CONSTRUCTION | 52600000
A-0011D | HIGHWAY | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. | 14 | Southwestern RPO |  | NOT FUNDED |  | ADHS | CONSTRUCTION | 52800000 | [11 empty] | 52800000
A-0011D | HIGHWAY | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. | 14 | Southwestern RPO |  | NOT FUNDED |  | ADHS | RIGHT-OF-WAY | 20845000 | [11 empty] | 20845000
A-0011D | HIGHWAY | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. | 14 | Southwestern RPO |  | NOT FUNDED |  | ADHS | UTILITIES | 378000 | [11 empty] | 378000
AO-0001 | AVIATION | ASHEVILLE REGIONAL AIRPORT | MODERNIZE AIRPORT TERMINAL BUILDING. | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "S" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | EXEMPT |  | S | CONSTRUCTION | 14250000 | FY 2023: 4750000; FY 2024: 4750000
AO-0001 | AVIATION | ASHEVILLE REGIONAL AIRPORT | MODERNIZE AIRPORT TERMINAL BUILDING. | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "S" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | EXEMPT |  | L | CONSTRUCTION | 136674000 | FY 2023: 65250000
AO-0001 | AVIATION | ASHEVILLE REGIONAL AIRPORT | MODERNIZE AIRPORT TERMINAL BUILDING. | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "S" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | EXEMPT |  | FED | CONSTRUCTION | 2884000
AV-5700 | AVIATION | RALEIGH DURHAM INTERNATIONAL AIRPORT (RDU) | RECONSTRUCT RUNWAY 5L-23R. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 99500000 | FY 2023: 99500000
AV-5700 | AVIATION | RALEIGH DURHAM INTERNATIONAL AIRPORT (RDU) | RECONSTRUCT RUNWAY 5L-23R. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
AV-5701 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L EXTENSION PROGRAM | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 19500000 | FY 2023: 19500000
AV-5701 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L EXTENSION PROGRAM | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
AV-5704 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | UPGRADE AIRFIELD LIGHTING VAULT. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 500000
AV-5707 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY G. | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 15400000 | FY 2023: 15400000
AV-5707 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY G. | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
AV-5708 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY OVER FUTURE I-73 EAST OF SR 2085 (BRYAN BOULEVARD). | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | STATEWIDE MOBILITY |  |  |  | 525000
AV-5708 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY OVER FUTURE I-73 EAST OF SR 2085 (BRYAN BOULEVARD). | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000
AV-5711 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. | 7 | Greensboro Urban Area MPO | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 7500000 | FY 2026: 7500000
AV-5711 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. | 7 | Greensboro Urban Area MPO | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2026: 500000; FY 2027: 500000; FY 2028: 500000
AV-5715 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2024: 500000; FY 2025: 500000; FY 2026: 500000
AV-5715 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 9500000 | FY 2024: 9500000
AV-5718 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | HIGH SPEED TAXIWAY TO RUNWAY 5R-23L. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
AV-5718 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | HIGH SPEED TAXIWAY TO RUNWAY 5R-23L. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 2500000 | FY 2023: 2500000
AV-5730 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | EXTEND RUNWAY 6-24 PHASE 1. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | NOT FUNDED |  | O | CONSTRUCTION | 4500000 | [11 empty] | 4500000
AV-5730 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | EXTEND RUNWAY 6-24 PHASE 1. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | NOT FUNDED |  | T | CONSTRUCTION | 500000 | [11 empty] | 500000
AV-5731 | AVIATION | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) | 10 | Cabarrus-Rowan MPO |  | REGION E |  | O | CONSTRUCTION | 7617000 | FY 2025: 7617000
AV-5731 | AVIATION | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) | 10 | Cabarrus-Rowan MPO |  | REGION E |  | T | CONSTRUCTION | 300000 | FY 2025: 300000
AV-5733 | AVIATION | ALBERT J. ELLIS AIRPORT (OAJ) | DESIGN AND CONSTRUCT RUNWAY 23 HOLDING APRON. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | T | CONSTRUCTION | 300000
AV-5733 | AVIATION | ALBERT J. ELLIS AIRPORT (OAJ) | DESIGN AND CONSTRUCT RUNWAY 23 HOLDING APRON. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | O | CONSTRUCTION | 450000
AV-5734 | AVIATION | FAYETTEVILLE REGIONAL AIRPORT (FAY) | REPLACE PERIMETER FENCING AND ROAD. | 6 | Fayetteville Area MPO |  | REGION C |  | O | CONSTRUCTION | 3140000 | FY 2024: 3140000
AV-5734 | AVIATION | FAYETTEVILLE REGIONAL AIRPORT (FAY) | REPLACE PERIMETER FENCING AND ROAD. | 6 | Fayetteville Area MPO |  | REGION C |  | T | CONSTRUCTION | 300000 | FY 2024: 300000
AV-5735 | AVIATION | ASHEVILLE REGIONAL AIRPORT (AVL) | AIRFIELD IMPROVEMENTS PROGRAM - RUNWAY CONSTRUCTION | 13 | French Broad River MPO | UNDER CONSTRUCTION | REGION G |  |  |  | 300000
AV-5736 | AVIATION | SILER CITY MUNICIPAL AIRPORT (SCR) | ACQUIRE NAVIGATION EASEMENTS IN RUNWAY 4 AND RUNWAY 22 APPROACHES, AND REMOVE OBSTRUCTIONS IN EASEMENTS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | RIGHT-OF-WAY | 365000 | FY 2024: 365000
AV-5737 | AVIATION | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN THE RUNWAY 24 APPROACH. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  |  |  | 163000
AV-5737 | AVIATION | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN THE RUNWAY 24 APPROACH. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 120000 | FY 2027: 120000
AV-5737 | AVIATION | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN THE RUNWAY 24 APPROACH. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 1080000 | FY 2027: 1080000
AV-5738 | AVIATION | SMITH REYNOLDS AIRPORT (INT) | ACQUIRE LAND AND CLEAR TERRAIN OBSTRUCTIONS EAST OF RUNWAY 15-33 TO DRAIN AND GRADE MATERIAL IN PLACE. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS BY AIRPORT | DIVISION 9 |  |  |  | 363000
AV-5738 | AVIATION | SMITH REYNOLDS AIRPORT (INT) | ACQUIRE LAND AND CLEAR TERRAIN OBSTRUCTIONS EAST OF RUNWAY 15-33 TO DRAIN AND GRADE MATERIAL IN PLACE. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS BY AIRPORT | DIVISION 9 |  | T | CONSTRUCTION | 2450000 | FY 2031: 1225000; FY 2032: 1225000
AV-5739 | AVIATION | CAPE FEAR REGIONAL (SUT) | APPROACH CLEARING AT RUNWAY 5 AND RUNWAY 23. | 3 | Cape Fear RPO | COMPLETED. | DIVISION 3 |  |  |  | 1116000
AV-5741 | AVIATION | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | O | CONSTRUCTION | 384000 | FY 2025: 384000
AV-5741 | AVIATION | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | CONSTRUCTION | 3460000 | FY 2025: 1538000; FY 2026: 1922000
AV-5742 | AVIATION | ODELL WILLIAMSON MUNICIPAL AIRPORT (60J) | RUNWAY PROTECTION ZONE 2 - RUNWAY 24 LAND ACQUISITION AND OBSTRUCTION REMOVAL. | 3 | Grand Strand Area Transportation Study | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  |  |  | 674000
AV-5743 | AVIATION | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | 2 | Mid-East RPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 1635000 | FY 2028: 1635000
AV-5743 | AVIATION | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | 2 | Mid-East RPO |  | DIVISION 2 |  |  |  | 300000
AV-5743 | AVIATION | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | 2 | Mid-East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 3648000 | FY 2029: 1824000; FY 2030: 1824000
AV-5744 | AVIATION | HENDERSON FIELD (ACZ) | EXTEND RUNWAY TO 5500 FEET. | 3 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | T | RIGHT-OF-WAY | 1978000
AV-5744 | AVIATION | HENDERSON FIELD (ACZ) | EXTEND RUNWAY TO 5500 FEET. | 3 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | T | CONSTRUCTION | 13105000 | FY 2024: 3000000; FY 2025: 3000000; FY 2026: 3552000; FY 2027: 3553000
AV-5745 | AVIATION | JOHNSTON COUNTY AIRPORT (JNX) | LAND ACQUISITION & CLEARING PROJECT. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 335000 | FY 2023: 335000
AV-5746 | AVIATION | MICHAEL J. SMITH FIELD (MRH) | FULL PARALLEL TAXIWAY 8-26. | 2 | Down East RPO | COMPLETE | DIVISION 2 |  |  |  | 2621000
AV-5747 | AVIATION | LUMBERTON REGIONAL AIRPORT (LBT) | PARTIAL PARALLEL TAXIWAY RUNWAY 5. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | CONSTRUCTION | 2600000
AV-5748 | AVIATION | COLUMBUS COUNTY AIRPORT (CPC) | APRON EXPANSION. | 6 | Cape Fear RPO |  | DIVISION 6 |  | T | CONSTRUCTION | 1808000 | FY 2024: 1808000
AV-5752 | AVIATION | HICKORY REGIONAL AIRPORT (HKY) | LAND ACQUISITION AND OBSTRUCTION REMOVAL. | 12 | Greater Hickory MPO |  | DIVISION 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 600000
AV-5753 | AVIATION | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | OBSTRUCTION REMOVAL IN RUNWAY 5 APPROACH. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 295000 | FY 2025: 295000
AV-5755 | AVIATION | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LAND ACQUISITION FOR RUNWAY 5 APPROACH. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 176000 | FY 2024: 176000
AV-5761 | AVIATION | RICHMOND COUNTY AIRPORT (RCZ) | CLEAR OBSTRUCTIONS IN RUNWAY 14 APPROACH. | 8 | Lumber River RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 570000 | FY 2026: 570000
AV-5762 | AVIATION | RALEIGH EXECUTIVE SANFORD - LEE COUNTY AIRPORT (TT | CONSTRUCT CORPORATE AREA APRON PHASE I. | 8 | Triangle Area RPO | UNDER CONSTRUCTION; INCLUDES $1.5 M IN ECONOMIC DEVELOPMENT FUNDING | DIVISION 8 |  |  |  | 3996000
AV-5763 | AVIATION | RICHMOND COUNTY AIRPORT (RCZ) | EXTEND RUNWAY 14-32 TO 5500 FEET. | 8 | Lumber River RPO |  | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5065000
AV-5778 | AVIATION | TRI-COUNTY AIRPORT (ASJ) | RUNWAY EXTENSION. | 1 | Peanut Belt RPO |  | DIVISION 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1700000
AV-5788 | AVIATION | MARTIN COUNTY AIRPORT (MCZ) | CONSTRUCT TAXILANES AND APRON. | 1 | Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | T | CONSTRUCTION | 950000 | FY 2023: 950000
AV-5795 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | EXPAND THE GENERAL AVIATION APRON. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 500000
AV-5795 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | EXPAND THE GENERAL AVIATION APRON. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 800000
AV-5796 | AVIATION | INTERNATIONAL (ILM) WILMINGTON | INCREASE WIDTH OF ALL TAXIWAYS. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | NOT FUNDED |  | O | CONSTRUCTION | 3300000 | [11 empty] | 3300000
AV-5796 | AVIATION | INTERNATIONAL (ILM) WILMINGTON | INCREASE WIDTH OF ALL TAXIWAYS. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | NOT FUNDED |  | T | CONSTRUCTION | 500000 | [11 empty] | 500000
AV-5798 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | TAXIWAY IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 5100000 | FY 2028: 5100000
AV-5798 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | TAXIWAY IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 500000 | FY 2028: 500000
AV-5799 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | WIDEN NORTH-SOUTH TAXIWAY SYSTEM. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | NOT FUNDED |  | O | CONSTRUCTION | 6000000 | [11 empty] | 6000000
AV-5799 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | WIDEN NORTH-SOUTH TAXIWAY SYSTEM. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | NOT FUNDED |  | T | CONSTRUCTION | 500000 | [11 empty] | 500000
AV-5800 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY J EXTENSION, TAXIWAY D TO TAXIWAY J2. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
AV-5800 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY J EXTENSION, TAXIWAY D TO TAXIWAY J2. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 5500000 | FY 2023: 5500000
AV-5801 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | EXPANSION OF AIR CARRIER APRON. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 500000
AV-5801 | AVIATION | WILMINGTON INTERNATIONAL (ILM) | EXPANSION OF AIR CARRIER APRON. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM. | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 3440000
AV-5802 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT NORTHWEST APRON TO INCREASE CAPACITY FOR FUTURE EXPANSION. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 9500000 | FY 2023: 9500000
AV-5802 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT NORTHWEST APRON TO INCREASE CAPACITY FOR FUTURE EXPANSION. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
AV-5803 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 26500000 | FY 2024: 26500000
AV-5803 | AVIATION | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1500000 | FY 2024: 500000; FY 2025: 500000; FY 2026: 500000
AV-5804 | AVIATION | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR ROADWAY RELOCATION, RPZ AND RUNWAY EXTENSION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | REGION B |  | T | RIGHT-OF-WAY | 300000 | FY 2023: 300000
AV-5804 | AVIATION | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR ROADWAY RELOCATION, RPZ AND RUNWAY EXTENSION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | REGION B |  | O | RIGHT-OF-WAY | 397000 | FY 2023: 397000
AV-5805 | AVIATION | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR RUNWAY EXTENSION AND ROADWAY RELOCATION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | REGION B |  | O | RIGHT-OF-WAY | 61000 | FY 2023: 61000
AV-5805 | AVIATION | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR RUNWAY EXTENSION AND ROADWAY RELOCATION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | REGION B |  | T | RIGHT-OF-WAY | 300000 | FY 2023: 300000
AV-5806 | AVIATION | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. | 3 | Jacksonville Urban Area MPO | OTHER FUNDS ARE AIRPORT FUNDS | REGION B |  | O | CONSTRUCTION | 12580000 | FY 2025: 12580000
AV-5806 | AVIATION | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. | 3 | Jacksonville Urban Area MPO | OTHER FUNDS ARE AIRPORT FUNDS | REGION B |  | T | CONSTRUCTION | 300000 | FY 2025: 300000
AV-5811 | AVIATION | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | EXTEND RUNWAY TO 5500 FEET. | 4 | Eastern Carolina RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 1000000 | FY 2027: 1000000
AV-5812 | AVIATION | HYDE COUNTY AIRPORT (7W6) | EXTEND RUNWAY TO 5000 FEET. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  |  |  | 200000
AV-5812 | AVIATION | HYDE COUNTY AIRPORT (7W6) | EXTEND RUNWAY TO 5000 FEET. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | T | CONSTRUCTION | 1800000 | FY 2023: 1800000
AV-5814 | AVIATION | CHARLOTTE-MONROE EXECUTIVE AIRPORT (EQY) | RELOCATE AND WIDEN THE EXISTING PARALLEL TAXIWAY SECTION BETWEEN THE EXISTING RAMP AND THE RUNWAY 5 TAXIWAY EXTENSION. | 10 | Charlotte Regional TPO |  | DIVISION 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 8800000
AV-5815 | AVIATION | HENDERSON FIELD (ACZ) | APRON EXPANSION. | 3 | Cape Fear RPO |  | DIVISION 3 |  | T | CONSTRUCTION | 6100000 | FY 2024: 6100000
AV-5816 | AVIATION | SILER CITY MUNICIPAL AIRPORT (SCR) | EXTEND RUNWAY 22 AND PARALLEL TAXIWAY BY 500 FT, INCLUDING RELOCATION OF AIRPORT ROAD | 8 | Triangle Area RPO |  | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2000000
AV-5816 | AVIATION | SILER CITY MUNICIPAL AIRPORT (SCR) | EXTEND RUNWAY 22 AND PARALLEL TAXIWAY BY 500 FT, INCLUDING RELOCATION OF AIRPORT ROAD | 8 | Triangle Area RPO |  | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 80000
AV-5816 | AVIATION | SILER CITY MUNICIPAL AIRPORT (SCR) | EXTEND RUNWAY 22 AND PARALLEL TAXIWAY BY 500 FT, INCLUDING RELOCATION OF AIRPORT ROAD | 8 | Triangle Area RPO |  | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5700000
AV-5817 | AVIATION | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBB LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. | 10 | Rocky River RPO |  | DIVISION 10 |  | T | CONSTRUCTION | 2500000 | FY 2027: 2500000
AV-5817 | AVIATION | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBB LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. | 10 | Rocky River RPO |  | DIVISION 10 |  | T | RIGHT-OF-WAY | 4400000 | FY 2025: 2200000; FY 2026: 2200000
AV-5818 | AVIATION | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). | 5 | Kerr-Tar RPO |  | DIVISION 5 |  | T | CONSTRUCTION | 15160000 | FY 2028: 5054000; FY 2029: 5053000; FY 2030: 5053000
AV-5818 | AVIATION | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). | 5 | Kerr-Tar RPO |  | DIVISION 5 |  |  |  | 1123000
AV-5819 | AVIATION | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | RIGHT-OF-WAY | 3100000 | FY 2026: 3100000
AV-5819 | AVIATION | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | CONSTRUCTION | 22700000 | FY 2028: 8567000; FY 2029: 7567000; FY 2030: 6566000
AV-5822 | AVIATION | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | CONSTRUCT TAXI LANE AND PREPARATION FOR ADDITIONAL T-HANGARS. | 4 | Peanut Belt RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 1100000 | FY 2024: 1100000
AV-5823 | AVIATION | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | REHABILITATE RUNWAY. | 3 | Mid-Carolina RPO |  | DIVISION 3 |  | T | CONSTRUCTION | 2200000 | FY 2025: 2200000
AV-5826 | AVIATION | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. | 6 | Mid-Carolina RPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 7200000
AV-5831 | AVIATION | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE AND STRENGTHEN RUNWAY TO ACCOMMODATE LARGER PRIVATE AIRCRAFT. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. TO BE LET WITH AV-5900. | DIVISION 9 |  |  |  | 600000
AV-5831 | AVIATION | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE AND STRENGTHEN RUNWAY TO ACCOMMODATE LARGER PRIVATE AIRCRAFT. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. TO BE LET WITH AV-5900. | DIVISION 9 |  | T | CONSTRUCTION | 14551000 | FY 2023: 6051000
AV-5832 | AVIATION | AIRPORT (INT) SMITH REYNOLDS | CONSTRUCT NEW TAXILANE. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 4551000
AV-5832 | AVIATION | AIRPORT (INT) SMITH REYNOLDS | CONSTRUCT NEW TAXILANE. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | CONSTRUCTION | 15700000 | FY 2025: 9850000; FY 2026: 5850000
AV-5833 | AVIATION | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. | 4 | Peanut Belt RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 2300000 | FY 2026: 2300000
AV-5843 | AVIATION | WAYNE EXECUTIVE JETPORT (GWW) | EXTEND RUNWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 7700000
AV-5845 | AVIATION | ROCKY MOUNT WILSON AIRPORT (RWI) | CONSTRUCT TAXIWAY AND T HANGARS. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 694000
AV-5845 | AVIATION | ROCKY MOUNT WILSON AIRPORT (RWI) | CONSTRUCT TAXIWAY AND T HANGARS. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | T | CONSTRUCTION | 3050000
AV-5848 | AVIATION | ASHE COUNTY AIRPORT (GEV) | CONSTRUCT APRON EXPANSONS. | 11 | High Country RPO | UNDER CONSTRUCTION. | DIVISION 11 |  | T | CONSTRUCTION | 2700000
AV-5850 | AVIATION | MACON COUNTY AIRPORT | EXTEND RUNWAY. | 14 | Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 166000
AV-5850 | AVIATION | MACON COUNTY AIRPORT | EXTEND RUNWAY. | 14 | Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4834000
AV-5851 | AVIATION | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | CONSTRUCT 100 FT PAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | T | CONSTRUCTION | 2080000 | FY 2027: 2080000
AV-5852 | AVIATION | (SIF) ROCKINGHAM COUNTY AIRPORT | EXTEND RUNWAY TO 5500 FT. | 7 | Piedmont Triad RPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2600000
AV-5852 | AVIATION | (SIF) ROCKINGHAM COUNTY AIRPORT | EXTEND RUNWAY TO 5500 FT. | 7 | Piedmont Triad RPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 200000
AV-5853 | AVIATION | RICHMOND COUNTY AIRPORT (RCZ) | CONSTRUCT EAST RAMP EXPANSION. | 8 | Lumber River RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 2000000 | FY 2024: 1600000; FY 2025: 400000
AV-5854 | AVIATION | LAURINBURG- MAXTON AIRPORT (MEB) | CONSTRUCT 1500 FT RUNWAY EXTENSION. | 8 | Lumber River RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 6390000 | FY 2033: 3095000 | 3295000
AV-5855 | AVIATION | MOORE COUNTY AIRPORT (SOP) | CONSTRUCT HANGAR TAXIWAYS AND INTERNAL AIRFIELD SERVICE ROAD. | 8 | Triangle Area RPO | UNDER CONSTRUCTION | DIVISION 8 |  |  |  | 300000
AV-5855 | AVIATION | MOORE COUNTY AIRPORT (SOP) | CONSTRUCT HANGAR TAXIWAYS AND INTERNAL AIRFIELD SERVICE ROAD. | 8 | Triangle Area RPO | UNDER CONSTRUCTION | DIVISION 8 |  | T | CONSTRUCTION | 2900000
AV-5858 | AVIATION | REGIONAL AIRPORT (HBI) ASHEBORO | CONSTRUCT TAXILANE EXTENSION, EXTEND ACCESS ROAD, AND CONSTRUCT NEW ACCESS ROAD. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 5500000 | FY 2031: 3500000; FY 2032: 2000000
AV-5859 | AVIATION | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | CONSTRUCT GENERAL AVIATION APRON AND AIRCRAFT STORAGE HANGARS. | 11 | Northwest Piedmont RPO | COMPLETE. | DIVISION 11 |  | T | CONSTRUCTION | 4000000
AV-5859 | AVIATION | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | CONSTRUCT GENERAL AVIATION APRON AND AIRCRAFT STORAGE HANGARS. | 11 | Northwest Piedmont RPO | COMPLETE. | DIVISION 11 |  |  |  | 2180000
AV-5878 | AVIATION | TRI-COUNTY AIRPORT (ASJ) | CONSTRUCT ACCESS ROAD TO T-HANGARS. | 1 | Peanut Belt RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 2200000 | [11 empty] | 2200000
AV-5879 | AVIATION | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 607000000 | FY 2024: 607000000
AV-5879 | AVIATION | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 500000 | FY 2024: 500000
AV-5881 | AVIATION | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND WEST RAMP NEAR CONCOURSE A - PHASE II. | 10 | Charlotte Regional TPO | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 39600000
AV-5881 | AVIATION | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND WEST RAMP NEAR CONCOURSE A - PHASE II. | 10 | Charlotte Regional TPO | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 500000
AV-5882 | AVIATION | ASHEVILLE REGIONAL AIRPORT (AVL) | EXPAND TERMINAL APRON TO THE SOUTH. | 13 | French Broad River MPO | COMPLETE. | STATEWIDE MOBILITY |  |  |  | 50000
AV-5882 | AVIATION | ASHEVILLE REGIONAL AIRPORT (AVL) | EXPAND TERMINAL APRON TO THE SOUTH. | 13 | French Broad River MPO | COMPLETE. | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 6500000
AV-5882 | AVIATION | ASHEVILLE REGIONAL AIRPORT (AVL) | EXPAND TERMINAL APRON TO THE SOUTH. | 13 | French Broad River MPO | COMPLETE. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 195000
AV-5885 | AVIATION | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 7000000 | FY 2024: 7000000
AV-5885 | AVIATION | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 500000 | FY 2024: 500000
AV-5886 | AVIATION | WILIMINGTON INTERNATION (ILM) | TAXIWAY J IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | NOT FUNDED |  | O | CONSTRUCTION | 5100000 | [11 empty] | 5100000
AV-5886 | AVIATION | WILIMINGTON INTERNATION (ILM) | TAXIWAY J IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | NOT FUNDED |  | T | CONSTRUCTION | 500000 | [11 empty] | 500000
AV-5889 | AVIATION | CONCORD REGIONAL AIRPORT (JQF) | EXTEND RUNWAY SAFETY AREA. | 10 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 300000 | [11 empty] | 300000
AV-5890 | AVIATION | CONCORD REGIONAL AIRPORT (JQF) | REHABILITATE APRON AND TAXIWAY PAVEMENT. | 10 | Cabarrus-Rowan MPO | COMPLETE. | REGION E |  | T | CONSTRUCTION | 300000
AV-5891 | AVIATION | COASTAL CAROLINA REGIONAL AIRPORT (EWN) | RUNWAY EXTENSION. | 2 | New Bern Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 300000 | [11 empty] | 300000
AV-5892 | AVIATION | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. | 10 | Cabarrus-Rowan MPO | OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT | REGION E |  | O | CONSTRUCTION | 1870000 | FY 2023: 1870000
AV-5892 | AVIATION | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. | 10 | Cabarrus-Rowan MPO | OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT | REGION E |  | T | CONSTRUCTION | 300000 | FY 2023: 300000
AV-5893 | AVIATION | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | REGION E |  | O | CONSTRUCTION | 202000000 | FY 2025: 202000000
AV-5893 | AVIATION | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | REGION E |  | T | CONSTRUCTION | 500000 | FY 2025: 500000
AV-5894 | AVIATION | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. | 11 | High Country RPO |  | DIVISION 11 |  | T | RIGHT-OF-WAY | 600000 | FY 2024: 600000
AV-5894 | AVIATION | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. | 11 | High Country RPO |  | DIVISION 11 |  | T | CONSTRUCTION | 12300000 | FY 2026: 1000000; FY 2027: 2200000; FY 2028: 4800000; FY 2029: 2300000; FY 2030: 2000000
AV-5896 | AVIATION | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 5610000 | FY 2026: 1700000; FY 2027: 3910000
AV-5896 | AVIATION | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | T | CONSTRUCTION | 3725000 | FY 2027: 3725000
AV-5897 | AVIATION | TARBORO EDGECOMBE AIRPORT (ETC) | RUNWAY EXTENSION. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4500000
AV-5898 | AVIATION | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | CONSTRUCT T-HANGAR TAXILANES FOR ADDITION OF T-HANGARS. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | CONSTRUCTION | 770000 | FY 2025: 770000
AV-5899 | AVIATION | RALEIGH EXECUTIVE JETPORT (TTA) | RUNWAY 21 AND RUNWAY 3 BYPASS TAXIWAY. CONSTRUCT AIRPLANE RUN-UP LANE AT EACH END OF TAXIWAY. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 1700000 | FY 2024: 1700000
AV-5901 | AVIATION | LUMBERTON REGIONAL AIRPORT (LBT) | RUNWAY 13-31. CONSTRUCT TAXIWAYS. | 6 | Lumber River RPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4500000
B-2500 | HIGHWAY | NC 12 | REPLACE BRIDGE 270011 (HERBERT C. BONNER BRIDGE) OVER OREGON INLET AND NC 12 IMPROVEMENTS. | 1 | Albemarle RPO |  | PRE-STI (TRANSITION) |  |  |  | 513209000
B-3159 | HIGHWAY | NC 8 | REPLACE BRIDGE 280027 OVER US 29 / US 64 / US 70 / I-85 BUSINESS IN LEXINGTON. | 9 | High Point Urban Area MPO | COMPLETE | REGION D |  |  |  | 25161000
B-3186 | HIGHWAY | US 23/US 74 | REPLACE BRIDGE 430155, AND BRIDGE 430158 OVER RICHLAND CREEK. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH B-5898. | STATEWIDE MOBILITY |  |  |  | 100000
B-3186 | HIGHWAY | US 23/US 74 | REPLACE BRIDGE 430155, AND BRIDGE 430158 OVER RICHLAND CREEK. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH B-5898. | STATEWIDE MOBILITY |  | NHPB | RIGHT-OF-WAY | 800000
B-3186 | HIGHWAY | US 23/US 74 | REPLACE BRIDGE 430155, AND BRIDGE 430158 OVER RICHLAND CREEK. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH B-5898. | STATEWIDE MOBILITY |  | NHPB | CONSTRUCTION | 6100000 | FY 2024: 3325000; FY 2025: 2775000
B-4069 | HIGHWAY | SR 1326 | REPLACE BRIDGE 159 OVER HANGING DOG CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  |  |  | 297000
B-4069 | HIGHWAY | SR 1326 | REPLACE BRIDGE 159 OVER HANGING DOG CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 1800000 | FY 2027: 1800000
B-4069 | HIGHWAY | SR 1326 | REPLACE BRIDGE 159 OVER HANGING DOG CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 295000 | FY 2024: 295000
B-4182 | HIGHWAY | SR 1503 (LAUREL VALLEY) | REPLACE BRIDGE 560246 OVER LAUREL CREEK. | 13 | French Broad River MPO, Land-of-Sky RPO | CONSTRUCTION FUNDED WITH STATE LEGISLATIVE BRIDGE PROGRAM FUNDS (17BP.13.R.105) | DIVISION 13 |  |  |  | 327000
B-4410A | HIGHWAY | SR 1627 (PINKSTON ROAD) | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | T | RIGHT-OF-WAY | 25000
B-4410A | HIGHWAY | SR 1627 (PINKSTON ROAD) | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | T | CONSTRUCTION | 288000 | FY 2023: 288000
B-4410A | HIGHWAY | SR 1627 (PINKSTON ROAD) | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 72000 | FY 2023: 72000
B-4439 | HIGHWAY | SR 1342 (MAKATOKA ROAD NORTHWEST) | REPLACE BRIDGE 090100 OVER MUDDY BRANCH. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 1250000 | FY 2023: 694000
B-4439 | HIGHWAY | SR 1342 (MAKATOKA ROAD NORTHWEST) | REPLACE BRIDGE 090100 OVER MUDDY BRANCH. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | RIGHT-OF-WAY | 550000
B-4439 | HIGHWAY | SR 1342 (MAKATOKA ROAD NORTHWEST) | REPLACE BRIDGE 090100 OVER MUDDY BRANCH. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 179000
B-4442 | HIGHWAY | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100370, AND BRIDGE 100373 OVER REEMS CREEK. | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 22000
B-4442 | HIGHWAY | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100370, AND BRIDGE 100373 OVER REEMS CREEK. | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPB | RIGHT-OF-WAY | 400000
B-4442 | HIGHWAY | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100370, AND BRIDGE 100373 OVER REEMS CREEK. | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPB | CONSTRUCTION | 29996000 | FY 2023: 10545000; FY 2024: 11216000; FY 2025: 7935000
B-4443 | HIGHWAY | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | 13 | French Broad River MPO | COORDINATE WITH A-0010A | STATEWIDE MOBILITY |  |  |  | 181000
B-4443 | HIGHWAY | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | 13 | French Broad River MPO | COORDINATE WITH A-0010A | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 720000 | FY 2025: 720000
B-4443 | HIGHWAY | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | 13 | French Broad River MPO | COORDINATE WITH A-0010A | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 15000000 | FY 2029: 5790000; FY 2030: 7391000; FY 2031: 1819000
B-4444 | HIGHWAY | US 19/23/25/70 | REHABILITATE DECK ON BRIDGE 100353 OVER SR 1882. | 13 | French Broad River MPO | COORDINATE WITH A-0010A | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 1000000 | FY 2026: 1000000
B-4450 | HIGHWAY | US 321 | REPLACE BRIDGE 130367 OVER CATAWBA RIVER. | 11 | Greater Hickory MPO | TO BE CONSTRUCTED WITH U-4700 |  |  |  |  | 17000
B-4461 | HIGHWAY | SR 1916 (CORINTH ROAD) | REPLACE BRIDGE 180010 OVER SHADDOX CREEK. | 8 | Triangle Area RPO | COMPLETE | HIGHWAY FUND |  |  |  | 2365000
B-4484 | HIGHWAY | ROAD) SR 1470 (MAPLE CYPRESS | REPLACE BRIDGE 240138 AND 240139 OVER NEUSE RIVER. | 2 | Down East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  | T | CONSTRUCTION | 18700000
B-4490 | HIGHWAY | NC 24/NC 210 | REPLACE BRIDGE 250116 OVER CSX RAILROAD, NORFOLK SOUTHERN RAILROAD, AND HILLSBORO STREET. | 6 | Fayetteville Area MPO | COMPLETED. | STATEWIDE MOBILITY |  |  |  | 44910000
B-4491 | HIGHWAY | NC 59 | REPLACE BRIDGE 250022 OVER I-95 BUSINESS/US 301. | 6 | Fayetteville Area MPO | COMPLETED. | REGION C |  |  |  | 22545000
B-4491 | HIGHWAY | NC 59 | REPLACE BRIDGE 250022 OVER I-95 BUSINESS/US 301. | 6 | Fayetteville Area MPO | COMPLETED. | REGION C |  | NHPB | CONSTRUCTION | 3533000
B-4562 | HIGHWAY | SR 2143 (BEULAHTOWN ROAD) | REPLACE BRIDGE 500216 OVER LITTLE BUFFALO CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. | DIVISION 4 |  |  |  | 3416000
B-4566 | HIGHWAY | NC 903 | REPLACE BRIDGE 530045 OVER NEUSE RIVER. | 2 | Eastern Carolina RPO |  | REGION B |  | BFP | CONSTRUCTION | 6500000 | FY 2028: 3250000; FY 2029: 3250000
B-4593 | HIGHWAY | NC 55 | REPLACE BRIDGE 680038 OVER TRENT CREEK. | 2 | Down East RPO | UNDER CONSTRUCTION. | REGION B |  | NHPB | CONSTRUCTION | 5837000 | FY 2023: 1637000
B-4605 | HIGHWAY | SR 1777 (BLACK JACK / GRIMESLAND ROAD) | REPLACE BRIDGE 730005 OVER CHICOD CREEK. | 2 | Mid-East RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1100000
B-4607 | HIGHWAY | SR 1923 (GARDENVILLE ROAD) | REPLACE BRIDGE 730043 OVER SWIFT CREEK. | 2 | Down East RPO, Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  | BGOFF | RIGHT-OF-WAY | 260000
B-4607 | HIGHWAY | SR 1923 (GARDENVILLE ROAD) | REPLACE BRIDGE 730043 OVER SWIFT CREEK. | 2 | Down East RPO, Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  |  |  | 105000
B-4607 | HIGHWAY | SR 1923 (GARDENVILLE ROAD) | REPLACE BRIDGE 730043 OVER SWIFT CREEK. | 2 | Down East RPO, Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  | BGOFF | CONSTRUCTION | 1775000 | FY 2023: 1095000
B-4635 | HIGHWAY | US 13 | REPLACE BRIDGE 810009 OVER SOUTH RIVER OVERFLOW. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 2250000
B-4636 | HIGHWAY | NC 24 | REPLACE BRIDGE 810056 OVER SIX RUNS CREEK. | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  |  |  | 135000
B-4636 | HIGHWAY | NC 24 | REPLACE BRIDGE 810056 OVER SIX RUNS CREEK. | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 5900000 | FY 2029: 2950000; FY 2030: 2950000
B-4636 | HIGHWAY | NC 24 | REPLACE BRIDGE 810056 OVER SIX RUNS CREEK. | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | HFB | RIGHT-OF-WAY | 390000
B-4654 | HIGHWAY | NC 50 | REPLACE BRIDGE 910069 OVER US 70 IN GARNER. | 5 | Capital Area MPO |  | REGION C |  | BFP | CONSTRUCTION | 9000000 | FY 2023: 900000; FY 2024: 8100000
B-4655 | HIGHWAY | SR 1006 (OLD STAGE ROAD) | REPLACE BRIDGE 910277 OVER BLACK CREEK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | HIGHWAY FUND |  |  |  | 1498000
B-4722 | HIGHWAY | US 70 | REPLACE BRIDGE 150033 OVER NORTH RIVER AND REPAIRS TO EXISTING STRUCTURE TO SERVE AS DETOUR. | 2 | Down East RPO |  | REGION B |  |  |  | 17337000
B-4786 | HIGHWAY | US 13 | REPLACE BRIDGE 730038 OVER TAR RIVER IN GREENVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | NHPB | CONSTRUCTION | 8200000 | FY 2023: 5054000; FY 2024: 1801000
B-4803 | HIGHWAY | SR 1925 (WORSHAM MILL ROAD) | REPLACE BRIDGE 780097 OVER WOLF ISLAND CREEK. | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 2358000
B-4844 | HIGHWAY | SR 1958 (BENNETTS BRIDGE ROAD) | REPLACE BRIDGE 950117 OVER NE CAPE FEAR RIVER. | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1200000
B-4844 | HIGHWAY | SR 1958 (BENNETTS BRIDGE ROAD) | REPLACE BRIDGE 950117 OVER NE CAPE FEAR RIVER. | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | HIGHWAY FUND |  |  |  | 507000
B-4863 | HIGHWAY | SR 1335 (ISLAND ROAD) | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | DIVISION 2 |  |  |  | 7788000
B-4863 | HIGHWAY | SR 1335 (ISLAND ROAD) | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | DIVISION 2 |  | DP | CONSTRUCTION | 1000000
B-4863 | HIGHWAY | SR 1335 (ISLAND ROAD) | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | DIVISION 2 |  | T | BUILD NC CON | 21240000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 4248000
B-4863 | HIGHWAY | SR 1335 (ISLAND ROAD) | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | DIVISION 2 |  | T | CONSTRUCTION | 51495000 | FY 2023: 18955000; FY 2024: 22097000; FY 2025: 5998000
B-4931 | HIGHWAY | US 258 | REPLACE BRIDGE 320022 OVER TOWN CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 2129000
B-4933 | HIGHWAY | NC 33 | REPLACE BRIDGE 320080 OVER TAR RIVER. REPLACE BRIDGE 320049 OVER TAR RIVER OVERFLOW. | 4 | Upper Coastal Plain RPO |  | REGION A |  | BFP | CONSTRUCTION | 11700000 | FY 2027: 4563000; FY 2028: 5733000; FY 2029: 1404000
B-4933 | HIGHWAY | NC 33 | REPLACE BRIDGE 320080 OVER TAR RIVER. REPLACE BRIDGE 320049 OVER TAR RIVER OVERFLOW. | 4 | Upper Coastal Plain RPO |  | REGION A |  | BFP | RIGHT-OF-WAY | 860000 | FY 2025: 60000; FY 2026: 800000
B-4933 | HIGHWAY | NC 33 | REPLACE BRIDGE 320080 OVER TAR RIVER. REPLACE BRIDGE 320049 OVER TAR RIVER OVERFLOW. | 4 | Upper Coastal Plain RPO |  | REGION A |  |  |  | 1285000
B-4937 | HIGHWAY | I-95 | REPLACE BRIDGE 500118 AND 500119 OVER CSX RAILROAD. | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 9600000 | FY 2029: 2400000; FY 2030: 4800000; FY 2031: 2400000
B-4958 | HIGHWAY | SR 2128 (BUNCH ROAD) | REPLACE BRIDGE 400106 OVER REEDY FORK CREEK IN OAK RIDGE. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 1240000
B-4960 | HIGHWAY | SR 3058 (JUDGE ADAMS ROAD) | REPLACE BRIDGE 400214 OVER LITTLE ALAMANCE CREEK. | 7 | Burlington-Graham MPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 3514000
B-4964 | HIGHWAY | SR 2600 (MIZPAH CHURCH ROAD) | REPLACE BRIDGE 780085 OVER SOUTHERN RAILROAD. | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 2843000
B-4967 | HIGHWAY | SR 1203 (TURNPIKE ROAD) | REPLACE BRIDGE 460008 OVER LUMBER RIVER. | 8 | Lumber River RPO | UNDER CONSTRUCTION | DIVISION 8 |  |  |  | 2303000
B-4977 | HIGHWAY | SR 1313 | REPLACE BRIDGE 960075 OVER FISH DAM CREEK. | 11 | High Country RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | HIGHWAY FUND |  | HFB | CONSTRUCTION | 700000
B-4979 | HIGHWAY | US 21 BUS | REPLACE BRIDGE 980059 OVER JONESVILLE CREEK. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1600000
B-5003 | HIGHWAY | COMMONWEALTH AVENUE | REPLACE BRIDGE 820081 OVER LEITH CREEK WITH CULVERT IN LAURINBURG. | 8 | Lumber River RPO | UNDER CONSTRUCTION BY CITY OF LAURINBURG - MUNICIPAL BRIDGE | PRE-STI (TRANSITION) |  |  |  | 653000
B-5007 | HIGHWAY | WEST FIRST STREET | REPLACE BRIDGE 330296 OVER NORFOLK SOUTHERN RAILWAY IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 604000
B-5007 | HIGHWAY | WEST FIRST STREET | REPLACE BRIDGE 330296 OVER NORFOLK SOUTHERN RAILWAY IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BFPOFF | RIGHT-OF-WAY | 70000 | FY 2027: 70000
B-5007 | HIGHWAY | WEST FIRST STREET | REPLACE BRIDGE 330296 OVER NORFOLK SOUTHERN RAILWAY IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BFPOFF | CONSTRUCTION | 700000 | FY 2028: 700000
B-5119 | HIGHWAY | I-40 / BUSINESS 85 (WESTBOUND) | REPLACE BRIDGE 400291 AND BRIDGE 400349 OVER US 29 / US 70 / US 220 IN GREENSBORO. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 8293000
B-5121 | HIGHWAY | US 70/US 401/NC 50 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910227 OVER PEACE STREET AND BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH AND REVISE INTERCHANGE AT PEACE STREET. | 5 | Capital Area MPO | UNDER CONSTRUCTION; PARTICIPATION BY CITY OF RALEIGH; INCLUDES B-5317 | REGION C |  |  |  | 87843000
B-5123 | HIGHWAY | US 29 | REPLACE BRIDGE 120014 AND 120019 OVER ROCKY RIVER AND ACCESS ROAD. | 10 | Cabarrus-Rowan MPO | COMPLETE | REGION E |  |  |  | 10000000
B-5130 | HIGHWAY | SR 1321 (AVENT FERRY ROAD) | REPLACE BRIDGE 910318 OVER LAKE JOHNSON IN RALEIGH. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  |  |  | 489000
B-5130 | HIGHWAY | SR 1321 (AVENT FERRY ROAD) | REPLACE BRIDGE 910318 OVER LAKE JOHNSON IN RALEIGH. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BFP | CONSTRUCTION | 3650000 | FY 2029: 2072000; FY 2030: 1578000
B-5136 | HIGHWAY | US 29/US 601 | REPLACE BRIDGE 120066 AND BRIDGE 120069 OVER SOUTHERN RAILROAD. | 10 | Cabarrus-Rowan MPO | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | REGION E |  |  |  | 16557000
B-5136 | HIGHWAY | US 29/US 601 | REPLACE BRIDGE 120066 AND BRIDGE 120069 OVER SOUTHERN RAILROAD. | 10 | Cabarrus-Rowan MPO | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | REGION E |  | T | BUILD NC CON | 2790000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 372000
B-5160 | HIGHWAY | SR 1986 (MT. VERNON ROAD) | REPLACE BRIDGE 790050 OVER NAILS BRANCH. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 755000
B-5161 | HIGHWAY | SR 1162 (APEX BARBECUE ROAD) | REPLACE BRIDGE 910362 OVER BEAVER CREEK IN APEX. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  |  |  | 4056000
B-5196 | HIGHWAY | MONTREAT (TEXAS ROAD) | REPLACE BRIDGE 100528 OVER FLAT CREEK. | 13 | French Broad River MPO | MUNICIPAL BRIDGE | DIVISION 13 |  |  |  | 869000
B-5210 | HIGHWAY | SR 1600 (EAST RIVER ROAD) | REPLACE BRIDGE 340076 OVER SYCAMORE CREEK. | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION - BRIDGE PURCHASE ORDER CONTRACT (BPOC) | DIVISION 5 |  |  |  | 600000
B-5237 | HIGHWAY | SR 2703 (NEW BETHEL CHURCH ROAD) | REPLACE BRIDGE 910248 OVER MAHLER'S CREEK IN GARNER. | 5 | Capital Area MPO | BUILD NC BONDS: $2.0 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 5 |  | T | BUILD NC CON | 2000000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 271000
B-5237 | HIGHWAY | SR 2703 (NEW BETHEL CHURCH ROAD) | REPLACE BRIDGE 910248 OVER MAHLER'S CREEK IN GARNER. | 5 | Capital Area MPO | BUILD NC BONDS: $2.0 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 5 |  |  |  | 4024000
B-5310 | HIGHWAY | SR 1817 (BRADSHAW ROAD) | REPLACE BRIDGE 810188 OVER WARD SWAMP. | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  |  |  | 226000
B-5310 | HIGHWAY | SR 1817 (BRADSHAW ROAD) | REPLACE BRIDGE 810188 OVER WARD SWAMP. | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 1500000 | FY 2024: 1140000; FY 2025: 360000
B-5310 | HIGHWAY | SR 1817 (BRADSHAW ROAD) | REPLACE BRIDGE 810188 OVER WARD SWAMP. | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | BGOFF | RIGHT-OF-WAY | 100000 | FY 2023: 100000
B-5318 | HIGHWAY | SR 2044 (LIGON MILL ROAD) | REPLACE BRIDGE 910126 OVER SMITHS CREEK IN WAKE FOREST. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BFP | CONSTRUCTION | 11000000 | FY 2023: 2880000; FY 2024: 6029000; FY 2025: 2091000
B-5320 | HIGHWAY | SR 1139 (ENON ROAD) | REPLACE BRIDGE 380096 OVER TAR RIVER. | 5 | Kerr-Tar RPO | PROJECT COMPLETE | DIVISION 5 |  |  |  | 3725000
B-5323 | HIGHWAY | SR 1442 (DAVE WINSTON ROAD) | REPLACE BRIDGE 380143 OVER JOHNSON CREEK. | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | DIVISION 5 |  | BFPOFF | CONSTRUCTION | 3700000 | FY 2023: 3700000
B-5344 | HIGHWAY | SR 2821 (HARVEST ROAD) | REPLACE BRIDGE 400161 OVER SOUTH BUFFALO CREEK. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 1195000
B-5347 | HIGHWAY | SR 1212 (POND ROAD) | REPLACE BRIDGE 000170 OVER PRONG OF ALAMANCE CREEK IN ALAMANCE. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | HIGHWAY FUND |  |  |  | 1560000
B-5348 | HIGHWAY | SR 1005 (OLD GREENSBORO ROAD) | REPLACE BRIDGE 670085 OVER PHIL'S CREEK. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | HIGHWAY FUND |  |  |  | 1345000
B-5352 | HIGHWAY | US 220 (NORTHBOUND) | REPLACE BRIDGE 780131 OVER NORFOLK SOUTHERN RAILROAD. | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 2390000
B-5356 | HIGHWAY | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | REPLACE BRIDGE 400299 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965 | STATEWIDE MOBILITY |  |  |  | 280000
B-5356 | HIGHWAY | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | REPLACE BRIDGE 400299 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965 | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 11700000 | FY 2028: 6431000; FY 2029: 4421000; FY 2030: 848000
B-5360 | HIGHWAY | SR 2481 (LOW BRIDGE ROAD) | REPLACE BRIDGE 750374 OVER SANDY CREEK. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - LET WITH B-5546; PRIOR YEARS COST INCLUDES B-5546 CONSTRUCTION | HIGHWAY FUND |  |  |  | 2568000
B-5365 | HIGHWAY | US 29; NC 152 | REPLACE BRIDGE 790021 AND BRIDGE 790034 OVER NORFOLK SOUTHERN RAILROAD AND US 29 IN CHINA GROVE. | 9 | Cabarrus-Rowan MPO | INCLUDED IN I-3802 |  |  |  |  | 150000
B-5375 | HIGHWAY | SR 1132 (MIAMI CHURCH ROAD) | REPLACE BRIDGE 120137 OVER DUTCH BUFFALO CREEK. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGOFF | CONSTRUCTION | 1573000 | FY 2023: 1557000
B-5375 | HIGHWAY | SR 1132 (MIAMI CHURCH ROAD) | REPLACE BRIDGE 120137 OVER DUTCH BUFFALO CREEK. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | DIVISION 10 |  |  |  | 360000
B-5376 | HIGHWAY | SR 1681 (OLD CAMDEN ROAD) | REPLACE BRIDGE 890021 OVER STEWART'S CREEK. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  |  |  | 200000
B-5376 | HIGHWAY | SR 1681 (OLD CAMDEN ROAD) | REPLACE BRIDGE 890021 OVER STEWART'S CREEK. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGOFF | CONSTRUCTION | 2100000 | FY 2028: 1589000; FY 2029: 511000
B-5376 | HIGHWAY | SR 1681 (OLD CAMDEN ROAD) | REPLACE BRIDGE 890021 OVER STEWART'S CREEK. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGOFF | RIGHT-OF-WAY | 210000 | FY 2023: 210000
B-5378 | HIGHWAY | MICHAEL BAKER ROAD | REPLACE BRIDGE 590210 OVER BRIAR CREEK IN CHARLOTTE. | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE - MUNICIPAL BRIDGE. UNDER CONSTRUCTION | DIVISION 10 |  |  |  | 1835000
B-5389 | HIGHWAY | US 421 NORTHBOUND | REPLACE STRUCTURE 980105 OVER YADKIN RIVER OVERFLOW. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 7800000
B-5403 | HIGHWAY | SR 1532 (ISLAND COVE ROAD) | REPLACE BRIDGE 870196 OVER CRAB CREEK. | 14 | Land-of-Sky RPO | COMPLETE | DIVISION 14 |  |  |  | 1233000
B-5503 | HIGHWAY | SR 1142 (PRISON CAMP ROAD) | REPLACE BRIDGE 570053 OVER COLLIE SWAMP. | 1 | Mid-East RPO | COMPLETED. | DIVISION 1 |  |  |  | 2195000
B-5507 | HIGHWAY | NC 32 | REPLACE BRIDGE 200024 OVER WARWICK CREEK, BRIDGE 200020 OVER DILLARD CREEK, AND BRIDGE 200021 OVER SAND RUN. | 1 | Albemarle RPO | COMPLETED. | HIGHWAY FUND |  |  |  | 6307000
B-5534 | HIGHWAY | NC 11/NC 111 | BRIDGE 300082 OVER BURNT COAT CREEK. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 2675000
B-5542 | HIGHWAY | CLAREMOUNT | PRESERVATION OF BUNKER HILL COVERED BRIDGE. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. OTHER FUNDS NATIONAL HISTORIC BRIDGE PROGRAM FUNDS. | DIVISION 12 |  |  |  | 290000
B-5542 | HIGHWAY | CLAREMOUNT | PRESERVATION OF BUNKER HILL COVERED BRIDGE. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. OTHER FUNDS NATIONAL HISTORIC BRIDGE PROGRAM FUNDS. | DIVISION 12 |  | O | CONSTRUCTION | 296000
B-5546 | HIGHWAY | SR 2481 (LOW BRIDGE ROAD) | REPLACE BRIDGE 750307 OVER MOUNT PLEASANT CREEK. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - LET WITH B-5360; CONSTRUCTION COST IS INCLUDED IN THAT PROJECT | HIGHWAY FUND |  |  |  | 123000
B-5550 | HIGHWAY | BREVARD | REPLACE BRIDGE 870102 ON RAILROAD AVENUE OVER KINGS CREEK. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF BREVARD | DIVISION 14 |  |  |  | 416000
B-5550 | HIGHWAY | BREVARD | REPLACE BRIDGE 870102 ON RAILROAD AVENUE OVER KINGS CREEK. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF BREVARD | DIVISION 14 |  | BFPOFF | CONSTRUCTION | 1400000 | FY 2023: 1400000
B-5553 | HIGHWAY | BALLINGER ROAD | REPLACE BRIDGE 400098 OVER A TRIBUTARY OF HORSEPEN CREEK IN GREENSBORO. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION BY CITY OF GREENSBORO; MUNICIPAL BRIDGE PROJECT | DIVISION 7 |  |  |  | 3203000
B-5606 | HIGHWAY | SR 1338 (WYNNE FORK ROAD) | REPLACE BRIDGE 710011 OVER RACOON CREEK. | 1 | Albemarle RPO | COMPLETED. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | DIVISION 1 |  |  |  | 1622000
B-5606 | HIGHWAY | SR 1338 (WYNNE FORK ROAD) | REPLACE BRIDGE 710011 OVER RACOON CREEK. | 1 | Albemarle RPO | COMPLETED. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | DIVISION 1 |  | T | BUILD NC CON | 1545000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 206000
B-5610 | HIGHWAY | NC 12 | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | NHPB | CONSTRUCTION | 1403000 | FY 2023: 14000; FY 2024: 1179000; FY 2025: 210000
B-5610 | HIGHWAY | NC 12 | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  |  |  | 100000
B-5610 | HIGHWAY | NC 12 | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | NHPB | RIGHT-OF-WAY | 320000
B-5610 | HIGHWAY | NC 12 | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | NHPB | UTILITIES | 440000
B-5612 | HIGHWAY | NC 222 | REPLACE BRIDGE 730024 OVER TAR RIVER. | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  | T | RIGHT-OF-WAY | 950000
B-5612 | HIGHWAY | NC 222 | REPLACE BRIDGE 730024 OVER TAR RIVER. | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  | T | CONSTRUCTION | 14000000 | FY 2028: 6300000; FY 2029: 6440000; FY 2030: 1260000
B-5612 | HIGHWAY | NC 222 | REPLACE BRIDGE 730024 OVER TAR RIVER. | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  |  |  | 1120000
B-5614 | HIGHWAY | SR 1112 (MOUTH OF THE CREEK ROAD) | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  |  |  | 100000
B-5614 | HIGHWAY | SR 1112 (MOUTH OF THE CREEK ROAD) | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | BGOFF | RIGHT-OF-WAY | 319000
B-5614 | HIGHWAY | SR 1112 (MOUTH OF THE CREEK ROAD) | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | BGOFF | UTILITIES | 108000
B-5614 | HIGHWAY | SR 1112 (MOUTH OF THE CREEK ROAD) | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | BGOFF | CONSTRUCTION | 9801000 | FY 2023: 1935000; FY 2024: 5580000; FY 2025: 2286000
B-5619 | HIGHWAY | SR 1389 (HARDY BRIDGE ROAD) | REPLACE BRIDGE 530052 OVER NEUSE RIVER AND 530152 OVER NEUSE RIVER OVERFLOW. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 2 |  | BGOFF | RIGHT-OF-WAY | 500000
B-5619 | HIGHWAY | SR 1389 (HARDY BRIDGE ROAD) | REPLACE BRIDGE 530052 OVER NEUSE RIVER AND 530152 OVER NEUSE RIVER OVERFLOW. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 2 |  | BGOFF | CONSTRUCTION | 9170000 | FY 2023: 3057000
B-5621 | HIGHWAY | SR 1904 (PINE RIDGE ROAD) | REPLACE BRIDGE 810248 OVER SIX RUNS CREEK. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 100000
B-5621 | HIGHWAY | SR 1904 (PINE RIDGE ROAD) | REPLACE BRIDGE 810248 OVER SIX RUNS CREEK. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 2500000 | FY 2023: 509000
B-5621 | HIGHWAY | SR 1904 (PINE RIDGE ROAD) | REPLACE BRIDGE 810248 OVER SIX RUNS CREEK. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | RIGHT-OF-WAY | 154000
B-5629 | HIGHWAY | SR 1515 (OLD MILL CREEK ROAD SE) | REPLACE BRIDGE 090040 OVER MILL CREEK. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 200000
B-5629 | HIGHWAY | SR 1515 (OLD MILL CREEK ROAD SE) | REPLACE BRIDGE 090040 OVER MILL CREEK. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 2450000 | FY 2023: 2450000
B-5629 | HIGHWAY | SR 1515 (OLD MILL CREEK ROAD SE) | REPLACE BRIDGE 090040 OVER MILL CREEK. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | RIGHT-OF-WAY | 115000
B-5631 | HIGHWAY | SR 1620 (TIMOTHY ROAD) | REPLACE BRIDGE 810169 OVER BIG JUNIPER RUN. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 285000
B-5631 | HIGHWAY | SR 1620 (TIMOTHY ROAD) | REPLACE BRIDGE 810169 OVER BIG JUNIPER RUN. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 1320000 | FY 2023: 1307000
B-5632 | HIGHWAY | SR 1828 (CYPRESS CREEK ROAD) | REPLACE BRIDGE 300187 OVER BLACK SWAMP. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 1900000 | FY 2023: 301000; FY 2024: 1599000
B-5632 | HIGHWAY | SR 1828 (CYPRESS CREEK ROAD) | REPLACE BRIDGE 300187 OVER BLACK SWAMP. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | RIGHT-OF-WAY | 190000 | FY 2023: 190000
B-5632 | HIGHWAY | SR 1828 (CYPRESS CREEK ROAD) | REPLACE BRIDGE 300187 OVER BLACK SWAMP. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 213000
B-5639 | HIGHWAY | NC 11 | BRIDGE 300036 OVER MAXWELL CREEK. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 3422000
B-5639 | HIGHWAY | NC 11 | BRIDGE 300036 OVER MAXWELL CREEK. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | RIGHT-OF-WAY | 56000
B-5641 | HIGHWAY | SR 1946 (NORTHEAST ROAD) | REPLACE BRIDGE 300201 OVER ISLAND CREEK. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 1669000 | FY 2023: 914000
B-5641 | HIGHWAY | SR 1946 (NORTHEAST ROAD) | REPLACE BRIDGE 300201 OVER ISLAND CREEK. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 405000
B-5647 | HIGHWAY | SR 1135 (PROVIDENCE CHURCH ROAD) | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 1500000 | FY 2024: 1140000; FY 2025: 360000
B-5647 | HIGHWAY | SR 1135 (PROVIDENCE CHURCH ROAD) | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | BGOFF | UTILITIES | 25000 | FY 2023: 25000
B-5647 | HIGHWAY | SR 1135 (PROVIDENCE CHURCH ROAD) | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  |  |  | 100000
B-5647 | HIGHWAY | SR 1135 (PROVIDENCE CHURCH ROAD) | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | BGOFF | RIGHT-OF-WAY | 60000 | FY 2023: 60000
B-5651 | HIGHWAY | SR 1706 (KORNEGAY TOWN ROAD) | REPLACE BRIDGE 810214 OVER KILL SWAMP. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 1084000
B-5655 | HIGHWAY | NC 111 / NC 122 | REPLACE BRIDGE 320011 OVER TOWN CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1950000
B-5660 | HIGHWAY | SR 1100 (BELLS BRIDGE ROAD) | REPLACE BRIDGE 410065 AND 410066 OVER DEEP CREEK. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 4113000
B-5662 | HIGHWAY | NC 561 | REPLACE BRIDGE 410093 OVER CONOCONNARA SWAMP. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 2581000
B-5664 | HIGHWAY | SR 1555 (BARBOUR MILL ROAD) | REPLACE BRIDGE 500145 OVER SWIFT CREEK. | 4 | Capital Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 4946000
B-5665 | HIGHWAY | SR 1309 (SPRUILLS BRIDGE ROAD) | REPLACE BRIDGE 410138 OVER LITTLE FISHING CREEK. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. DIVISION PURCHASE ORDER CONTRACT. | HIGHWAY FUND |  |  |  | 2060000
B-5666 | HIGHWAY | US 117 | REPLACE BRIDGE 970047 OVER SEABOARD COAST LINE RAILROAD. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 4469000
B-5671 | HIGHWAY | NC 97 | REPLACE BRIDGE 320087 OVER SWIFT CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 2279000
B-5673 | HIGHWAY | SR 1630 (GREEN LEVEL CHURCH ROAD) | REPLACE BRIDGE 910061 OVER KIT CREEK IN CARY. | 5 | Capital Area MPO |  | DIVISION 5 |  |  |  | 194000
B-5673 | HIGHWAY | SR 1630 (GREEN LEVEL CHURCH ROAD) | REPLACE BRIDGE 910061 OVER KIT CREEK IN CARY. | 5 | Capital Area MPO |  | DIVISION 5 |  | HFB | RIGHT-OF-WAY | 290000 | FY 2023: 290000
B-5673 | HIGHWAY | SR 1630 (GREEN LEVEL CHURCH ROAD) | REPLACE BRIDGE 910061 OVER KIT CREEK IN CARY. | 5 | Capital Area MPO |  | DIVISION 5 |  | HFB | CONSTRUCTION | 5800000 | FY 2025: 5800000
B-5674 | HIGHWAY | US 15 / US 501 NORTHBOUND | REPLACE BRIDGE 310080 OVER SR 1308 (CORNWALLIS ROAD) IN DURHAM. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  |  |  | 100000
B-5674 | HIGHWAY | US 15 / US 501 NORTHBOUND | REPLACE BRIDGE 310080 OVER SR 1308 (CORNWALLIS ROAD) IN DURHAM. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | BFP | RIGHT-OF-WAY | 700000 | FY 2027: 700000
B-5674 | HIGHWAY | US 15 / US 501 NORTHBOUND | REPLACE BRIDGE 310080 OVER SR 1308 (CORNWALLIS ROAD) IN DURHAM. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | BFP | CONSTRUCTION | 5450000 | FY 2028: 4617000; FY 2029: 833000
B-5684 | HIGHWAY | US 401 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | 5 | Capital Area MPO |  | REGION C |  |  |  | 100000
B-5684 | HIGHWAY | US 401 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | 5 | Capital Area MPO |  | REGION C |  | BFP | RIGHT-OF-WAY | 6300000 | FY 2029: 3150000; FY 2030: 3150000
B-5684 | HIGHWAY | US 401 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | 5 | Capital Area MPO |  | REGION C |  | BFP | UTILITIES | 380000 | FY 2029: 380000
B-5684 | HIGHWAY | US 401 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | 5 | Capital Area MPO |  | REGION C |  | BFP | CONSTRUCTION | 11600000 | FY 2030: 1180000; FY 2031: 7034000; FY 2032: 3386000
B-5693 | HIGHWAY | SR 1924 (CURRIE ROAD) | REPLACE BRIDGE 770059 OVER BIG MARSH SWAMP. | 6 | Lumber River RPO | COMPLETED. | DIVISION 6 |  |  |  | 1462000
B-5708 | HIGHWAY | NC 24 | REPLACE BRIDGE 250144 OVER SOUTH RIVER. | 6 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 5000000 | FY 2027: 1300000; FY 2028: 3700000
B-5708 | HIGHWAY | NC 24 | REPLACE BRIDGE 250144 OVER SOUTH RIVER. | 6 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  | T | UTILITIES | 56000 | FY 2026: 56000
B-5708 | HIGHWAY | NC 24 | REPLACE BRIDGE 250144 OVER SOUTH RIVER. | 6 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  |  |  | 100000
B-5708 | HIGHWAY | NC 24 | REPLACE BRIDGE 250144 OVER SOUTH RIVER. | 6 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 464000 | FY 2026: 464000
B-5713 | HIGHWAY | WILLOW ROAD | REPLACE BRIDGE 400352 OVER I-40 / BUSINESS 85 IN GREENSBORO. | 7 | Greensboro Urban Area MPO | "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | DIVISION 7 |  |  |  | 100000
B-5713 | HIGHWAY | WILLOW ROAD | REPLACE BRIDGE 400352 OVER I-40 / BUSINESS 85 IN GREENSBORO. | 7 | Greensboro Urban Area MPO | "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | DIVISION 7 |  | BFP | RIGHT-OF-WAY | 1000000 | FY 2029: 1000000
B-5713 | HIGHWAY | WILLOW ROAD | REPLACE BRIDGE 400352 OVER I-40 / BUSINESS 85 IN GREENSBORO. | 7 | Greensboro Urban Area MPO | "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | DIVISION 7 |  | BFP | CONSTRUCTION | 8000000 | FY 2030: 5322000; FY 2031: 2678000
B-5715 | HIGHWAY | SR 2351 (WITTY ROAD) | REPLACE BRIDGE 780017 OVER HAW RIVER. | 7 | Greensboro Urban Area MPO, Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 1283000
B-5716 | HIGHWAY | SR 1138 (LINDSEY BRIDGE ROAD) | REPLACE BRIDGE 780140 OVER DAN RIVER | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 950000
B-5716 | HIGHWAY | SR 1138 (LINDSEY BRIDGE ROAD) | REPLACE BRIDGE 780140 OVER DAN RIVER | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGOFF | RIGHT-OF-WAY | 610000 | FY 2023: 610000
B-5716 | HIGHWAY | SR 1138 (LINDSEY BRIDGE ROAD) | REPLACE BRIDGE 780140 OVER DAN RIVER | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGOFF | CONSTRUCTION | 6101000 | FY 2024: 741000; FY 2025: 4277000; FY 2026: 1083000
B-5717 | HIGHWAY | SR 4240 (GATE CITY BOULEVARD) | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | DIVISION 7 |  | BFP | CONSTRUCTION | 8957000 | FY 2023: 6272000; FY 2024: 1595000
B-5717 | HIGHWAY | SR 4240 (GATE CITY BOULEVARD) | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | DIVISION 7 |  | S | RIGHT-OF-WAY | 710000
B-5717 | HIGHWAY | SR 4240 (GATE CITY BOULEVARD) | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | DIVISION 7 |  | S | UTILITIES | 165000
B-5718 | HIGHWAY | PATTON AVENUE | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | DIVISION 7 |  | BFP | UTILITIES | 74000 | FY 2027: 74000
B-5718 | HIGHWAY | PATTON AVENUE | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | DIVISION 7 |  | BFP | CONSTRUCTION | 3350000 | FY 2028: 2725000; FY 2029: 625000
B-5718 | HIGHWAY | PATTON AVENUE | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | DIVISION 7 |  |  |  | 202000
B-5718 | HIGHWAY | PATTON AVENUE | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | DIVISION 7 |  | BFP | RIGHT-OF-WAY | 218000 | FY 2027: 218000
B-5721 | HIGHWAY | SR 2177 (DAN VALLEY ROAD) | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 200000
B-5721 | HIGHWAY | SR 2177 (DAN VALLEY ROAD) | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 7 |  | BGLT5 | RIGHT-OF-WAY | 188000
B-5721 | HIGHWAY | SR 2177 (DAN VALLEY ROAD) | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 7 |  | BGLT5 | UTILITIES | 336000
B-5721 | HIGHWAY | SR 2177 (DAN VALLEY ROAD) | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 7 |  | BGLT5 | CONSTRUCTION | 3800000 | FY 2023: 1380000; FY 2024: 2265000; FY 2025: 155000
B-5722 | HIGHWAY | SR 1169 (ISLAND DRIVE) | REPLACE BRIDGE 780277 OVER BEAVER CREEK | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | BGOFF | RIGHT-OF-WAY | 200000 | FY 2023: 200000
B-5722 | HIGHWAY | SR 1169 (ISLAND DRIVE) | REPLACE BRIDGE 780277 OVER BEAVER CREEK | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2024: 752000; FY 2025: 1248000
B-5722 | HIGHWAY | SR 1169 (ISLAND DRIVE) | REPLACE BRIDGE 780277 OVER BEAVER CREEK | 7 | Piedmont Triad RPO |  | DIVISION 7 |  |  |  | 575000
B-5723 | HIGHWAY | SR 1158 (JACKSON LAKE ROAD) | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | BGOFF | UTILITIES | 570000 | FY 2030: 570000
B-5723 | HIGHWAY | SR 1158 (JACKSON LAKE ROAD) | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | BGOFF | CONSTRUCTION | 2100000 | FY 2031: 2100000
B-5723 | HIGHWAY | SR 1158 (JACKSON LAKE ROAD) | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | BGOFF | RIGHT-OF-WAY | 30000 | FY 2030: 30000
B-5725 | HIGHWAY | SR 1710 (GRIERS CHURCH ROAD) | REPLACE BRIDGE 160007 OVER HYCO CREEK. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | BGOFF | RIGHT-OF-WAY | 30000 | FY 2030: 30000
B-5725 | HIGHWAY | SR 1710 (GRIERS CHURCH ROAD) | REPLACE BRIDGE 160007 OVER HYCO CREEK. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | BGOFF | CONSTRUCTION | 1700000 | FY 2031: 850000; FY 2032: 850000
B-5739 | HIGHWAY | SR 2621 (FOUSHEE ROAD) | REPLACE BRIDGE 750170 OVER REED CREEK. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 8 |  |  |  | 1127000
B-5755 | HIGHWAY | SR 1406 (ROCKFISH ROAD) | REPLACE BRIDGE 460057 OVER PUPPY CREEK. | 8 | Fayetteville Area MPO | UNDER CONSTRUCTION | DIVISION 8 |  |  |  | 1056000
B-5763 | HIGHWAY | SR 2407 (STARMOUNT ROAD) | REPLACE BRIDGE 750129 OVER BRANCH OF SANDY CREEK. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION | DIVISION 8 |  |  |  | 625000
B-5769 | HIGHWAY | SR 2539 (PEACH ORCHARD ROAD) | REPLACE BRIDGE 790200 OVER TOWN CREEK. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 1225000
B-5770 | HIGHWAY | SALISBURY RIDGE ROAD | REPLACE BRIDGE 330243 OVER NC 150 IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 366000
B-5770 | HIGHWAY | SALISBURY RIDGE ROAD | REPLACE BRIDGE 330243 OVER NC 150 IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGOFF | CONSTRUCTION | 5501000 | FY 2023: 3311000; FY 2024: 654000
B-5772 | HIGHWAY | SR 1724 (HURLEY SCHOOL ROAD) | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  | BGOFF | CONSTRUCTION | 1950000 | FY 2023: 1649000
B-5772 | HIGHWAY | SR 1724 (HURLEY SCHOOL ROAD) | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 100000
B-5772 | HIGHWAY | SR 1724 (HURLEY SCHOOL ROAD) | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  | BGOFF | RIGHT-OF-WAY | 77000
B-5772 | HIGHWAY | SR 1724 (HURLEY SCHOOL ROAD) | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  | BGOFF | UTILITIES | 31000
B-5778 | HIGHWAY | NC 801 | REPLACE BRIDGE 790061 OVER FOURTH CREEK. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | HIGHWAY FUND |  |  |  | 3570000
B-5779 | HIGHWAY | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | 9 | High Point Urban Area MPO |  | REGION D |  | BFP | RIGHT-OF-WAY | 130000 | FY 2028: 130000
B-5779 | HIGHWAY | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | 9 | High Point Urban Area MPO |  | REGION D |  | BFP | UTILITIES | 290000 | FY 2028: 290000
B-5779 | HIGHWAY | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | 9 | High Point Urban Area MPO |  | REGION D |  | BFP | CONSTRUCTION | 7700000 | FY 2029: 2320000; FY 2030: 4732000; FY 2031: 648000
B-5779 | HIGHWAY | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | 9 | High Point Urban Area MPO |  | REGION D |  |  |  | 100000
B-5780 | HIGHWAY | NC 47 | REPLACE BRIDGE 280017 OVER SWEARING CREEK. | 9 | High Point Urban Area MPO | COMPLETE | HIGHWAY FUND |  |  |  | 2025000
B-5783 | HIGHWAY | US 29 / US 70 / BUSINESS 85 | REPLACE BRIDGE 280164 AND BRIDGE 280168 OVER NORFOLK SOUTHERN RAILROAD. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | REGION D |  |  |  | 100000
B-5783 | HIGHWAY | US 29 / US 70 / BUSINESS 85 | REPLACE BRIDGE 280164 AND BRIDGE 280168 OVER NORFOLK SOUTHERN RAILROAD. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | REGION D |  | BFP | CONSTRUCTION | 5778000 | FY 2023: 1155000; FY 2024: 3788000; FY 2025: 835000
B-5806 | HIGHWAY | SR 2111 (BELK MILL ROAD) | REPLACE BRIDGE 890129 OVER LANES CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  |  |  | 368000
B-5806 | HIGHWAY | SR 2111 (BELK MILL ROAD) | REPLACE BRIDGE 890129 OVER LANES CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGOFF | CONSTRUCTION | 1242000 | FY 2023: 1230000
B-5808 | HIGHWAY | US 29 US 601 | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | REGION E |  | BFP | CONSTRUCTION | 10100000 | FY 2023: 3180000; FY 2024: 6130000; FY 2025: 790000
B-5808 | HIGHWAY | US 29 US 601 | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | REGION E |  | NHPB | RIGHT-OF-WAY | 255000
B-5808 | HIGHWAY | US 29 US 601 | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | REGION E |  | NHPB | UTILITIES | 1156000
B-5808 | HIGHWAY | US 29 US 601 | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | REGION E |  |  |  | 100000
B-5809 | HIGHWAY | SR 1142 (CITY POND ROAD) | REPLACE BRIDGE 030075 OVER NORTH FORK JONES CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  |  |  | 250000
B-5809 | HIGHWAY | SR 1142 (CITY POND ROAD) | REPLACE BRIDGE 030075 OVER NORTH FORK JONES CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGOFF | CONSTRUCTION | 1180000 | FY 2023: 1168000
B-5809 | HIGHWAY | SR 1142 (CITY POND ROAD) | REPLACE BRIDGE 030075 OVER NORTH FORK JONES CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGOFF | RIGHT-OF-WAY | 105000
B-5811 | HIGHWAY | SR 1434 (ROGERS ROAD) | REPLACE BRIDGE 830042 OVER BIG BEAR CREEK. | 10 | Rocky River RPO |  | DIVISION 10 |  |  |  | 237000
B-5811 | HIGHWAY | SR 1434 (ROGERS ROAD) | REPLACE BRIDGE 830042 OVER BIG BEAR CREEK. | 10 | Rocky River RPO |  | DIVISION 10 |  | BGOFF | CONSTRUCTION | 600000 | FY 2030: 600000
B-5811 | HIGHWAY | SR 1434 (ROGERS ROAD) | REPLACE BRIDGE 830042 OVER BIG BEAR CREEK. | 10 | Rocky River RPO |  | DIVISION 10 |  | BGOFF | RIGHT-OF-WAY | 15000 | FY 2025: 15000
B-5817 | HIGHWAY | SR 1634 (GRASSY ISLAND ROAD) | REPLACE BRIDGE 030007 OVER BROWN CREEK. NC FLAP DOT 1634(1). | 10 | Rocky River RPO | STATE MATCHING FUNDS FROM DIVISION 10 17BP FUNDS. COMPLETED. | EXEMPT |  |  |  | 2150000
B-5825 | HIGHWAY | NC 67 | REPLACE BRIDGE 980035 OVER YADKIN RIVER. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | REGION F |  |  |  | 933000
B-5825 | HIGHWAY | NC 67 | REPLACE BRIDGE 980035 OVER YADKIN RIVER. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | REGION F |  | T | CONSTRUCTION | 11465000 | FY 2023: 3794000; FY 2024: 675000
B-5831 | HIGHWAY | I-77 NORTHBOUND | REPLACE BRIDGE 850006 OVER NC 268, NORFOLK SOUTHERN RAILROAD, AND THE YADKIN RIVER. | 11 | Northwest Piedmont RPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 15300000 | FY 2031: 5333000; FY 2032: 7123000; FY 2033: 2844000
B-5831 | HIGHWAY | I-77 NORTHBOUND | REPLACE BRIDGE 850006 OVER NC 268, NORFOLK SOUTHERN RAILROAD, AND THE YADKIN RIVER. | 11 | Northwest Piedmont RPO |  | STATEWIDE MOBILITY |  |  |  | 100000
B-5831 | HIGHWAY | I-77 NORTHBOUND | REPLACE BRIDGE 850006 OVER NC 268, NORFOLK SOUTHERN RAILROAD, AND THE YADKIN RIVER. | 11 | Northwest Piedmont RPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 260000 | FY 2024: 260000
B-5832 | HIGHWAY | SR 2080 (QUAKER CHURCH ROAD) | REPLACE BRIDGE 850152 OVER ARARAT RIVER. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BGOFF | RIGHT-OF-WAY | 200000 | FY 2024: 200000
B-5832 | HIGHWAY | SR 2080 (QUAKER CHURCH ROAD) | REPLACE BRIDGE 850152 OVER ARARAT RIVER. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BGOFF | CONSTRUCTION | 3600000 | FY 2030: 1823000; FY 2031: 1777000
B-5832 | HIGHWAY | SR 2080 (QUAKER CHURCH ROAD) | REPLACE BRIDGE 850152 OVER ARARAT RIVER. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  |  |  | 100000
B-5833 | HIGHWAY | US 21 BUSINESS | REPLACE BRIDGE 980029 OVER I-77. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  |  |  | 100000
B-5833 | HIGHWAY | US 21 BUSINESS | REPLACE BRIDGE 980029 OVER I-77. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  | BFP | CONSTRUCTION | 4599000 | FY 2024: 1347000; FY 2025: 2143000; FY 2026: 1109000
B-5833 | HIGHWAY | US 21 BUSINESS | REPLACE BRIDGE 980029 OVER I-77. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  | BFP | RIGHT-OF-WAY | 1600000
B-5835 | HIGHWAY | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | 11 | High Country RPO |  | DIVISION 11 |  | BGOFF | UTILITIES | 300000 | FY 2025: 300000
B-5835 | HIGHWAY | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | 11 | High Country RPO |  | DIVISION 11 |  | BGOFF | CONSTRUCTION | 1291000 | FY 2026: 1291000
B-5835 | HIGHWAY | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | 11 | High Country RPO |  | DIVISION 11 |  | BGOFF | RIGHT-OF-WAY | 150000 | FY 2025: 150000
B-5835 | HIGHWAY | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | 11 | High Country RPO |  | DIVISION 11 |  |  |  | 100000
B-5835 | HIGHWAY | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | 11 | High Country RPO |  | DIVISION 11 |  | BGOFF | CONSTRUCTION | 709000 | FY 2027: 709000
B-5843 | HIGHWAY | SR 2402 (HOOVER ROAD) | REPLACE BRIDGE 480020 OVER I-L CREEK. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGOFF | CONSTRUCTION | 668000 | FY 2031: 668000
B-5843 | HIGHWAY | SR 2402 (HOOVER ROAD) | REPLACE BRIDGE 480020 OVER I-L CREEK. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  |  |  | 226000
B-5843 | HIGHWAY | SR 2402 (HOOVER ROAD) | REPLACE BRIDGE 480020 OVER I-L CREEK. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGOFF | RIGHT-OF-WAY | 67000 | FY 2023: 67000
B-5843 | HIGHWAY | SR 2402 (HOOVER ROAD) | REPLACE BRIDGE 480020 OVER I-L CREEK. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGOFF | CONSTRUCTION | 7000 | FY 2030: 7000
B-5846 | HIGHWAY | SR 1892 (JENNINGS ROAD) | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | BGOFF | CONSTRUCTION | 3300000 | FY 2023: 1039000; FY 2024: 2261000
B-5846 | HIGHWAY | SR 1892 (JENNINGS ROAD) | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | BGOFF | UTILITIES | 325000
B-5846 | HIGHWAY | SR 1892 (JENNINGS ROAD) | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  |  |  | 100000
B-5846 | HIGHWAY | SR 1892 (JENNINGS ROAD) | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | BGOFF | RIGHT-OF-WAY | 85000
B-5847 | HIGHWAY | SR 1709 (ROCK BARN ROAD) | REPLACE BRIDGE 170173 OVER I-40. | 12 | Greater Hickory MPO |  | DIVISION 12 |  |  |  | 100000
B-5847 | HIGHWAY | SR 1709 (ROCK BARN ROAD) | REPLACE BRIDGE 170173 OVER I-40. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BFP | CONSTRUCTION | 10300000 | FY 2030: 2190000; FY 2031: 6894000; FY 2032: 1216000
B-5847 | HIGHWAY | SR 1709 (ROCK BARN ROAD) | REPLACE BRIDGE 170173 OVER I-40. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BFP | RIGHT-OF-WAY | 1400000 | FY 2023: 93000; FY 2024: 1027000; FY 2025: 140000; FY 2026: 140000
B-5869 | HIGHWAY | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | REGION G |  | BFP | UTILITIES | 270000
B-5869 | HIGHWAY | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | REGION G |  | BFP | CONSTRUCTION | 19200000 | FY 2023: 5912000; FY 2024: 8243000; FY 2025: 5045000
B-5869 | HIGHWAY | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | REGION G |  | BFP | RIGHT-OF-WAY | 640000
B-5869 | HIGHWAY | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | REGION G |  |  |  | 471000
B-5869 | HIGHWAY | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | REGION G |  | BGDA | RIGHT-OF-WAY | 2560000
B-5871 | HIGHWAY | SR 1306 (BILLS CREEK ROAD) | REPLACE BRIDGE 800628 OVER LAKE LURE DAM AND BROAD RIVER. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  |  |  | 200000
B-5871 | HIGHWAY | SR 1306 (BILLS CREEK ROAD) | REPLACE BRIDGE 800628 OVER LAKE LURE DAM AND BROAD RIVER. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | BGOFF | CONSTRUCTION | 5000000 | FY 2027: 618000; FY 2028: 2108000; FY 2029: 1656000; FY 2030: 618000
B-5871 | HIGHWAY | SR 1306 (BILLS CREEK ROAD) | REPLACE BRIDGE 800628 OVER LAKE LURE DAM AND BROAD RIVER. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 250000 | FY 2023: 250000
B-5876 | HIGHWAY | US 74 | REPLACE BRIDGE 800083 AND BRIDGE 800084 OVER SECOND BROAD RIVER. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 9798000 | FY 2025: 3513000; FY 2026: 4675000; FY 2027: 1610000
B-5876 | HIGHWAY | US 74 | REPLACE BRIDGE 800083 AND BRIDGE 800084 OVER SECOND BROAD RIVER. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  |  |  | 740000
B-5898 | HIGHWAY | US 23/ US 74 | REPLACE BRIDGE 430168 OVER US 19 AND US 23. | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-3186. | STATEWIDE MOBILITY |  | NHPB | CONSTRUCTION | 3100000 | FY 2024: 2227000; FY 2025: 873000
B-5898 | HIGHWAY | US 23/ US 74 | REPLACE BRIDGE 430168 OVER US 19 AND US 23. | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-3186. | STATEWIDE MOBILITY |  |  |  | 100000
B-5898 | HIGHWAY | US 23/ US 74 | REPLACE BRIDGE 430168 OVER US 19 AND US 23. | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-3186. | STATEWIDE MOBILITY |  | NHPB | RIGHT-OF-WAY | 150000
B-5920 | HIGHWAY | SR 1216 (STEEL BRIDGE ROAD) | REPLACE BRIDGE 430246 OVER WEST FORK PIGEON CREEK. | 14 | French Broad River MPO |  | DIVISION 14 |  |  |  | 100000
B-5920 | HIGHWAY | SR 1216 (STEEL BRIDGE ROAD) | REPLACE BRIDGE 430246 OVER WEST FORK PIGEON CREEK. | 14 | French Broad River MPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 640000 | FY 2024: 526000; FY 2025: 114000
B-5920 | HIGHWAY | SR 1216 (STEEL BRIDGE ROAD) | REPLACE BRIDGE 430246 OVER WEST FORK PIGEON CREEK. | 14 | French Broad River MPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 30000 | FY 2023: 30000
B-5921 | HIGHWAY | SR 1120 (CEDAR CREEK ROAD) | REPLACE BRIDGE 490008 CEDAR CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  |  |  | 100000
B-5921 | HIGHWAY | SR 1120 (CEDAR CREEK ROAD) | REPLACE BRIDGE 490008 CEDAR CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 400000 | FY 2024: 400000
B-5921 | HIGHWAY | SR 1120 (CEDAR CREEK ROAD) | REPLACE BRIDGE 490008 CEDAR CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 20000 | FY 2023: 20000
B-5925 | HIGHWAY | SR 1548 (OLD HIGHWAY 64) | REPLACE BRIDGE 223 OVER HIWASSEE RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  |  |  | 344000
B-5925 | HIGHWAY | SR 1548 (OLD HIGHWAY 64) | REPLACE BRIDGE 223 OVER HIWASSEE RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BFP | CONSTRUCTION | 2600000 | FY 2024: 2600000
B-5925 | HIGHWAY | SR 1548 (OLD HIGHWAY 64) | REPLACE BRIDGE 223 OVER HIWASSEE RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BFP | RIGHT-OF-WAY | 260000 | FY 2023: 260000
B-5929 | HIGHWAY | TRACY GROVE ROAD | REPLACE BRIDGE 440350 OVER DEVILS FORK CREEK. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE | DIVISION 14 |  | L | CONSTRUCTION | 230000 | FY 2023: 230000
B-5929 | HIGHWAY | TRACY GROVE ROAD | REPLACE BRIDGE 440350 OVER DEVILS FORK CREEK. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE | DIVISION 14 |  |  |  | 205000
B-5929 | HIGHWAY | TRACY GROVE ROAD | REPLACE BRIDGE 440350 OVER DEVILS FORK CREEK. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE | DIVISION 14 |  | BGOFF | CONSTRUCTION | 920000 | FY 2023: 920000
B-5930 | HIGHWAY | SARDIS LANE | REPLACE BRIDGE 590433 OVER MCALPINE CREEK. | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE | DIVISION 10 |  | L | CONSTRUCTION | 400000
B-5930 | HIGHWAY | SARDIS LANE | REPLACE BRIDGE 590433 OVER MCALPINE CREEK. | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE | DIVISION 10 |  | BGOFF | CONSTRUCTION | 1600000
B-5930 | HIGHWAY | SARDIS LANE | REPLACE BRIDGE 590433 OVER MCALPINE CREEK. | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE | DIVISION 10 |  |  |  | 300000
B-5931 | HIGHWAY | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | DIVISION 10 |  |  |  | 1137000
B-5931 | HIGHWAY | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | DIVISION 10 |  | BGOFF | CONSTRUCTION | 2200000 | FY 2023: 2200000
B-5931 | HIGHWAY | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | DIVISION 10 |  | L | CONSTRUCTION | 550000 | FY 2023: 550000
B-5937 | HIGHWAY | US 158 | REHABILITATE BRIDGE 260016 OVER CURRITUCK SOUND. | 1 | Albemarle RPO | COMPLETED. | STATEWIDE MOBILITY |  |  |  | 30100000
B-5938 | HIGHWAY | SR 1182 (ATLANTIC BEACH CAUSEWAY) | REHABILITATE BRIDGE 150068 OVER BOGUE SOUND. | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE) | DIVISION 2 |  | T | CONSTRUCTION | 1000000 | FY 2023: 1000000
B-5938 | HIGHWAY | SR 1182 (ATLANTIC BEACH CAUSEWAY) | REHABILITATE BRIDGE 150068 OVER BOGUE SOUND. | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE) | DIVISION 2 |  |  |  | 5592000
B-5938 | HIGHWAY | SR 1182 (ATLANTIC BEACH CAUSEWAY) | REHABILITATE BRIDGE 150068 OVER BOGUE SOUND. | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE) | DIVISION 2 |  | T | BUILD NC CON | 6195000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000
B-5939 | HIGHWAY | NC 58 | REHABILITATE BRIDGE 150006 OVER BOGUE SOUND. | 2 | Down East RPO | UNDER CONSTRUCTION | REGION B |  |  |  | 4560000
B-5944 | HIGHWAY | SR 1509 (QUEENS CREEK ROAD) | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | BFP | CONSTRUCTION | 10099000 | FY 2030: 1816000; FY 2031: 5804000; FY 2032: 2479000
B-5944 | HIGHWAY | SR 1509 (QUEENS CREEK ROAD) | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | BFP | RIGHT-OF-WAY | 500000 | FY 2028: 500000
B-5944 | HIGHWAY | SR 1509 (QUEENS CREEK ROAD) | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  |  |  | 500000
B-5945 | HIGHWAY | NC 87 | REPLACE BRIDGE 080014 OVER HAMMOND CREEK. | 6 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 700000 | FY 2027: 700000
B-5945 | HIGHWAY | NC 87 | REPLACE BRIDGE 080014 OVER HAMMOND CREEK. | 6 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  |  |  | 10000
B-5945 | HIGHWAY | NC 87 | REPLACE BRIDGE 080014 OVER HAMMOND CREEK. | 6 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 7200000 | FY 2028: 1584000; FY 2029: 4680000; FY 2030: 936000
B-5947 | HIGHWAY | NC 581 | REPLACE BRIDGE 630091 OVER TAR RIVER. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | NHPB | CONSTRUCTION | 6400000 | FY 2023: 64000; FY 2024: 4897000; FY 2025: 1439000
B-5947 | HIGHWAY | NC 581 | REPLACE BRIDGE 630091 OVER TAR RIVER. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | NHPB | UTILITIES | 123000 | FY 2023: 38000
B-5947 | HIGHWAY | NC 581 | REPLACE BRIDGE 630091 OVER TAR RIVER. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  |  |  | 10000
B-5947 | HIGHWAY | NC 581 | REPLACE BRIDGE 630091 OVER TAR RIVER. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | NHPB | RIGHT-OF-WAY | 400000
B-5949 | HIGHWAY | NC 200 | REPLACE BRIDGE 890053 OVER STEWARTS CREEK. | 10 | Charlotte Regional TPO |  | REGION E |  |  |  | 10000
B-5949 | HIGHWAY | NC 200 | REPLACE BRIDGE 890053 OVER STEWARTS CREEK. | 10 | Charlotte Regional TPO |  | REGION E |  | BFP | CONSTRUCTION | 2500000 | FY 2027: 924000; FY 2028: 1576000
B-5949 | HIGHWAY | NC 200 | REPLACE BRIDGE 890053 OVER STEWARTS CREEK. | 10 | Charlotte Regional TPO |  | REGION E |  | BFP | RIGHT-OF-WAY | 120000 | FY 2024: 120000
B-5950 | HIGHWAY | NC 67 (WESTBOUND) (SILAS CREEK PARKWAY) | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | REGION D |  |  |  | 10000
B-5950 | HIGHWAY | NC 67 (WESTBOUND) (SILAS CREEK PARKWAY) | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | BFP | RIGHT-OF-WAY | 750000 | FY 2026: 750000
B-5950 | HIGHWAY | NC 67 (WESTBOUND) (SILAS CREEK PARKWAY) | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | BFP | UTILITIES | 1000 | FY 2026: 1000
B-5950 | HIGHWAY | NC 67 (WESTBOUND) (SILAS CREEK PARKWAY) | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | BFP | CONSTRUCTION | 7501000 | FY 2027: 1881000; FY 2028: 4863000; FY 2029: 757000
B-5952 | HIGHWAY | NC 97 | REPLACE BRIDGE 320051 OVER TAR RIVER. | 4 | Rocky Mount Urban Area MPO |  | REGION A |  |  |  | 10000
B-5952 | HIGHWAY | NC 97 | REPLACE BRIDGE 320051 OVER TAR RIVER. | 4 | Rocky Mount Urban Area MPO |  | REGION A |  | BFP | RIGHT-OF-WAY | 100000 | FY 2028: 100000
B-5952 | HIGHWAY | NC 97 | REPLACE BRIDGE 320051 OVER TAR RIVER. | 4 | Rocky Mount Urban Area MPO |  | REGION A |  | BFP | UTILITIES | 703000 | FY 2028: 703000
B-5952 | HIGHWAY | NC 97 | REPLACE BRIDGE 320051 OVER TAR RIVER. | 4 | Rocky Mount Urban Area MPO |  | REGION A |  | BFP | CONSTRUCTION | 6900000 | FY 2030: 1805000; FY 2031: 4155000; FY 2032: 940000
B-5961 | HIGHWAY | SR 1421 (MARYS GROVE ROAD) | REPLACE BRIDGE 350097 OVER UN-NAMED TRIBUTARY OF MUDDY FORK CREEK. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | DIVISION 12 |  |  |  | 600000
B-5961 | HIGHWAY | SR 1421 (MARYS GROVE ROAD) | REPLACE BRIDGE 350097 OVER UN-NAMED TRIBUTARY OF MUDDY FORK CREEK. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | BGOFF | RIGHT-OF-WAY | 67000
B-5961 | HIGHWAY | SR 1421 (MARYS GROVE ROAD) | REPLACE BRIDGE 350097 OVER UN-NAMED TRIBUTARY OF MUDDY FORK CREEK. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | BGOFF | CONSTRUCTION | 705000 | FY 2023: 698000
B-5971 | HIGHWAY | SR 1149 (ELK SPUR STREET) | REPLACE BRIDGE 850387 OVER ELKIN CREEK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  |  |  | 10000
B-5971 | HIGHWAY | SR 1149 (ELK SPUR STREET) | REPLACE BRIDGE 850387 OVER ELKIN CREEK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BGOFF | CONSTRUCTION | 6400000 | FY 2027: 64000; FY 2028: 4262000; FY 2029: 2074000
B-5971 | HIGHWAY | SR 1149 (ELK SPUR STREET) | REPLACE BRIDGE 850387 OVER ELKIN CREEK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BGOFF | RIGHT-OF-WAY | 300000 | FY 2026: 300000
B-5976 | HIGHWAY | SR 1400 (CUMNOCK ROAD) | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | 8 | Triangle Area RPO |  | DIVISION 8 |  | BGOFF | CONSTRUCTION | 6200000 | FY 2031: 3100000; FY 2032: 3100000
B-5976 | HIGHWAY | SR 1400 (CUMNOCK ROAD) | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | 8 | Triangle Area RPO |  | DIVISION 8 |  |  |  | 413000
B-5976 | HIGHWAY | SR 1400 (CUMNOCK ROAD) | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | 8 | Triangle Area RPO |  | DIVISION 8 |  | BGOFF | RIGHT-OF-WAY | 600000 | FY 2030: 600000
B-5979 | HIGHWAY | HUNTING HILLS LANE | REPLACE BRIDGE NO. 940346 OVER SOUTH FORK OF NEW RIVER IN BOONE. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  | L | CONSTRUCTION | 300000
B-5979 | HIGHWAY | HUNTING HILLS LANE | REPLACE BRIDGE NO. 940346 OVER SOUTH FORK OF NEW RIVER IN BOONE. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  |  |  | 260000
B-5979 | HIGHWAY | HUNTING HILLS LANE | REPLACE BRIDGE NO. 940346 OVER SOUTH FORK OF NEW RIVER IN BOONE. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  | BGOFF | CONSTRUCTION | 1200000
B-5980 | HIGHWAY | SR 1522 (HALIFAX ROAD) | REPLACE BRIDGE 630203 OVER I-95. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | STATEWIDE MOBILITY |  |  |  | 1613000
B-5980 | HIGHWAY | SR 1522 (HALIFAX ROAD) | REPLACE BRIDGE 630203 OVER I-95. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | STATEWIDE MOBILITY |  | NHPB | RIGHT-OF-WAY | 2100000
B-5980 | HIGHWAY | SR 1522 (HALIFAX ROAD) | REPLACE BRIDGE 630203 OVER I-95. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | STATEWIDE MOBILITY |  | NHPB | CONSTRUCTION | 16564000 | FY 2023: 5498000; FY 2024: 1025000
B-5981 | HIGHWAY | US 117 NBL | REPLACE BRIDGE 300016 OVER CSX RAILROAD. BRIDGE PRESERVATION OF BRIDGE 300017 OVER CSX. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 7100000 | FY 2023: 631000; FY 2024: 4778000; FY 2025: 1691000
B-5981 | HIGHWAY | US 117 NBL | REPLACE BRIDGE 300016 OVER CSX RAILROAD. BRIDGE PRESERVATION OF BRIDGE 300017 OVER CSX. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGLT5 | RIGHT-OF-WAY | 443000
B-5981 | HIGHWAY | US 117 NBL | REPLACE BRIDGE 300016 OVER CSX RAILROAD. BRIDGE PRESERVATION OF BRIDGE 300017 OVER CSX. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 110000
B-5985 | HIGHWAY | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770125 AND 770175 OVER LUMBER RIVER. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  |  |  | 110000
B-5985 | HIGHWAY | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770125 AND 770175 OVER LUMBER RIVER. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | NHPB | RIGHT-OF-WAY | 395000
B-5985 | HIGHWAY | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770125 AND 770175 OVER LUMBER RIVER. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | NHPB | UTILITIES | 485000
B-5985A | HIGHWAY | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770125 OVER LUMBER RIVER. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | BFP | CONSTRUCTION | 8500000 | FY 2023: 2295000; FY 2024: 3825000; FY 2025: 2380000
B-5985B | HIGHWAY | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770175 OVER LUMBER RIVER. | 6 | Lumber River RPO |  | REGION C |  | BFP | CONSTRUCTION | 8175000 | FY 2024: 2207000; FY 2025: 3679000; FY 2026: 2289000
B-5986 | HIGHWAY | NC 231 | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | 5 | Capital Area MPO |  | REGION C |  | BFP | CONSTRUCTION | 2948000 | FY 2028: 775000; FY 2029: 2002000; FY 2030: 171000
B-5986 | HIGHWAY | NC 231 | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | 5 | Capital Area MPO |  | REGION C |  | NHPB | RIGHT-OF-WAY | 164000 | FY 2027: 164000
B-5986 | HIGHWAY | NC 231 | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | 5 | Capital Area MPO |  | REGION C |  |  |  | 110000
B-5986 | HIGHWAY | NC 231 | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | 5 | Capital Area MPO |  | REGION C |  | NHPB | UTILITIES | 202000 | FY 2027: 202000
B-5987 | HIGHWAY | US 401 | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | REGION C |  |  |  | 110000
B-5987 | HIGHWAY | US 401 | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | REGION C |  | NHPB | RIGHT-OF-WAY | 640000 | FY 2023: 640000
B-5987 | HIGHWAY | US 401 | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | REGION C |  | NHPB | UTILITIES | 640000 | FY 2023: 640000
B-5987 | HIGHWAY | US 401 | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | REGION C |  | NHPB | CONSTRUCTION | 16899000 | FY 2024: 2585000; FY 2025: 7629000; FY 2026: 5121000; FY 2027: 1564000
B-5988 | HIGHWAY | WADESBORO | REPLACE BRIDGE 030316 ON BURNS STREET OVER LAMPLEY CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY TOWN OF WADESBORO. | DIVISION 10 |  | L | RIGHT-OF-WAY | 34000
B-5988 | HIGHWAY | WADESBORO | REPLACE BRIDGE 030316 ON BURNS STREET OVER LAMPLEY CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY TOWN OF WADESBORO. | DIVISION 10 |  | L | CONSTRUCTION | 242000
B-5988 | HIGHWAY | WADESBORO | REPLACE BRIDGE 030316 ON BURNS STREET OVER LAMPLEY CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY TOWN OF WADESBORO. | DIVISION 10 |  | BGOFF | RIGHT-OF-WAY | 135000
B-5988 | HIGHWAY | WADESBORO | REPLACE BRIDGE 030316 ON BURNS STREET OVER LAMPLEY CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY TOWN OF WADESBORO. | DIVISION 10 |  |  |  | 176000
B-5988 | HIGHWAY | WADESBORO | REPLACE BRIDGE 030316 ON BURNS STREET OVER LAMPLEY CREEK. | 10 | Rocky River RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY TOWN OF WADESBORO. | DIVISION 10 |  | BGOFF | CONSTRUCTION | 969000
B-5989 | HIGHWAY | SR 1395 | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 13 |  |  |  | 110000
B-5989 | HIGHWAY | SR 1395 | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 13000
B-5989 | HIGHWAY | SR 1395 | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | UTILITIES | 130000 | FY 2023: 130000
B-5989 | HIGHWAY | SR 1395 | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | CONSTRUCTION | 4600000 | FY 2023: 2576000; FY 2024: 2024000
B-5990 | HIGHWAY | SR 1138 WESTBOUND | REPLACE BRIDGE 590001 OVER SUGAR CREEK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  |  |  | 110000
B-5990 | HIGHWAY | SR 1138 WESTBOUND | REPLACE BRIDGE 590001 OVER SUGAR CREEK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BFP | CONSTRUCTION | 4000000 | FY 2026: 2588000; FY 2027: 1412000
B-5990 | HIGHWAY | SR 1138 WESTBOUND | REPLACE BRIDGE 590001 OVER SUGAR CREEK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BFP | RIGHT-OF-WAY | 174000 | FY 2024: 174000
B-5990 | HIGHWAY | SR 1138 WESTBOUND | REPLACE BRIDGE 590001 OVER SUGAR CREEK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BFP | UTILITIES | 174000 | FY 2024: 174000
B-5994 | HIGHWAY | SR 1142 (WEYERHAEUSER ROAD) | REPLACE BRIDGE 510032 OVER TUCKAHOE SWAMP. | 2 | Down East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  |  |  | 1468000
B-5995 | HIGHWAY | SR 1302 (JANIERO ROAD) | REPLACE BRIDGE 680057 OVER DAWSON CREEK. | 2 | Down East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  | BGOFF | RIGHT-OF-WAY | 600000
B-5995 | HIGHWAY | SR 1302 (JANIERO ROAD) | REPLACE BRIDGE 680057 OVER DAWSON CREEK. | 2 | Down East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  |  |  | 200000
B-5995 | HIGHWAY | SR 1302 (JANIERO ROAD) | REPLACE BRIDGE 680057 OVER DAWSON CREEK. | 2 | Down East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  | BGOFF | CONSTRUCTION | 3850000 | FY 2023: 827000; FY 2024: 2800000; FY 2025: 223000
B-5996 | HIGHWAY | SR 1300 (ASH-LITTLE RIVER ROAD NORTHWEST) | REPLACE BRIDGE 090126 OVER CAWCAW SWAMP. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | RIGHT-OF-WAY | 100000
B-5996 | HIGHWAY | SR 1300 (ASH-LITTLE RIVER ROAD NORTHWEST) | REPLACE BRIDGE 090126 OVER CAWCAW SWAMP. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 200000
B-5996 | HIGHWAY | SR 1300 (ASH-LITTLE RIVER ROAD NORTHWEST) | REPLACE BRIDGE 090126 OVER CAWCAW SWAMP. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2023: 1687000
B-5997 | HIGHWAY | SR 1399 (ZACK'S MILL ROAD) | REPLACE BRIDGE 500277 OVER POLECAT BRANCH. | 4 | Capital Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 935000
B-5998 | HIGHWAY | SR 1339 (SHARPE SHORE ROAD) | REPLACE BRIDGE 970092 OVER TOWN SWAMP. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION | DIVISION 4 |  |  |  | 778000
B-6000 | HIGHWAY | SR 1400 (ROCK QUARRY ROAD) | REPLACE BRIDGE 970096 OVER TRIBUTARY OF TOWN CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION | DIVISION 4 |  |  |  | 873000
B-6001 | HIGHWAY | SR 1153 (MILL CREEK ROAD) | REPLACE BRIDGE 500068 OVER JUNIPER SWAMP. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 280000
B-6001 | HIGHWAY | SR 1153 (MILL CREEK ROAD) | REPLACE BRIDGE 500068 OVER JUNIPER SWAMP. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | DIVISION 4 |  | BGOFF | CONSTRUCTION | 1015000
B-6002 | HIGHWAY | SR 1126 (FAITH BAPTIST CHURCH ROAD) | REPLACE BRIDGE 320064 OVER TOWN CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1200000
B-6003 | HIGHWAY | SR 1609 (BAPTIST CHURCH ROAD) | REPLACE BRIDGE 340078 OVER TAR RIVER | 5 | Capital Area MPO |  | DIVISION 5 |  |  |  | 200000
B-6003 | HIGHWAY | SR 1609 (BAPTIST CHURCH ROAD) | REPLACE BRIDGE 340078 OVER TAR RIVER | 5 | Capital Area MPO |  | DIVISION 5 |  | BGOFF | RIGHT-OF-WAY | 440000 | FY 2030: 440000
B-6003 | HIGHWAY | SR 1609 (BAPTIST CHURCH ROAD) | REPLACE BRIDGE 340078 OVER TAR RIVER | 5 | Capital Area MPO |  | DIVISION 5 |  | BGOFF | CONSTRUCTION | 4400000 | FY 2031: 2278000; FY 2032: 2122000
B-6004 | HIGHWAY | SR 1534 (OVER LYON ROAD) | REPLACE BRIDGE 080197 OVER KELLY CANAL. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  |  |  | 1300000
B-6005 | HIGHWAY | SR 1210 (HOOVER ROAD) | REPLACE BRIDGE 420234 OVER BARBEQUE SWAMP. | 6 | Mid-Carolina RPO | COMPLETED. | DIVISION 6 |  |  |  | 1465000
B-6006 | HIGHWAY | SR 1159 (OLD TRAM ROAD) | REPLACE BRIDGE 230313 OVER BOOGY BRANCH. | 6 | Cape Fear RPO | COMPLETED. | DIVISION 6 |  |  |  | 1438000
B-6007 | HIGHWAY | SR 2269 (BLOOMINGDALE ROAD) | REPLACE BRIDGE 770108 OVER INDIAN SWAMP. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | DIVISION 6 |  |  |  | 3786000
B-6008 | HIGHWAY | SR 1536 (JAMES PORTER ROAD) | REPLACE BRIDGE 080198 OVER KELLY CANAL. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  |  |  | 1190000
B-6009 | HIGHWAY | SR 2030 (HOLLOW BRIDGE ROAD) | REPLACE BRIDGE 250044 OVER SANDY CREEK AND BRIDGE 250043 OVER SANDY CREEK OVERFLOW. | 6 | Mid-Carolina RPO | COMPLETED. | DIVISION 6 |  |  |  | 2741000
B-6010 | HIGHWAY | SR 1183 (UPPER SHUT-IN ROAD) | REPLACE BRIDGE 560302 OVER SHUT IN CREEK. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION | DIVISION 13 |  |  |  | 825000
B-6011 | HIGHWAY | SR 1430 (HARLAND ROAD) | REPLACE BRIDGE 110145 OVER BRISTOL CREEK. | 13 | Greater Hickory MPO | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION. | DIVISION 13 |  |  |  | 265000
B-6011 | HIGHWAY | SR 1430 (HARLAND ROAD) | REPLACE BRIDGE 110145 OVER BRISTOL CREEK. | 13 | Greater Hickory MPO | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | CONSTRUCTION | 725000 | FY 2023: 44000
B-6011 | HIGHWAY | SR 1430 (HARLAND ROAD) | REPLACE BRIDGE 110145 OVER BRISTOL CREEK. | 13 | Greater Hickory MPO | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 65000
B-6012 | HIGHWAY | SR 1341 (FOSTER CREEK ROAD) | REPLACE BRIDGE 560073 OVER FOSTER CREEK. | 13 | French Broad River MPO | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | DIVISION 13 |  | T | BUILD NC CON | 4440000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 592000
B-6012 | HIGHWAY | SR 1341 (FOSTER CREEK ROAD) | REPLACE BRIDGE 560073 OVER FOSTER CREEK. | 13 | French Broad River MPO | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | DIVISION 13 |  | T | CONSTRUCTION | 388000
B-6012 | HIGHWAY | SR 1341 (FOSTER CREEK ROAD) | REPLACE BRIDGE 560073 OVER FOSTER CREEK. | 13 | French Broad River MPO | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | DIVISION 13 |  |  |  | 908000
B-6013 | HIGHWAY | SR 1106 (LYNN GAP ROAD) | REPLACE BRIDGE 600207 OVER GRASSY CREEK. | 13 | High Country RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016 | DIVISION 13 |  | BGOFF | CONSTRUCTION | 800000 | FY 2023: 86000
B-6013 | HIGHWAY | SR 1106 (LYNN GAP ROAD) | REPLACE BRIDGE 600207 OVER GRASSY CREEK. | 13 | High Country RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016 | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 40000
B-6013 | HIGHWAY | SR 1106 (LYNN GAP ROAD) | REPLACE BRIDGE 600207 OVER GRASSY CREEK. | 13 | High Country RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016 | DIVISION 13 |  |  |  | 200000
B-6014 | HIGHWAY | SR 1781 (POLLY SPOUT ROAD) | REPLACE BRIDGE 580312 OVER SECOND BROAD RIVER. | 13 | Foothills RPO | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION. | DIVISION 13 |  |  |  | 200000
B-6014 | HIGHWAY | SR 1781 (POLLY SPOUT ROAD) | REPLACE BRIDGE 580312 OVER SECOND BROAD RIVER. | 13 | Foothills RPO | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | CONSTRUCTION | 4831000 | FY 2023: 711000
B-6014 | HIGHWAY | SR 1781 (POLLY SPOUT ROAD) | REPLACE BRIDGE 580312 OVER SECOND BROAD RIVER. | 13 | Foothills RPO | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 100000
B-6015 | HIGHWAY | SR 1913 (SUGAR LOAF ROAD) | REPLACE BRIDGE 110237 OVER ROCK CREEK. | 13 | Greater Hickory MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION. | DIVISION 13 |  |  |  | 200000
B-6015 | HIGHWAY | SR 1913 (SUGAR LOAF ROAD) | REPLACE BRIDGE 110237 OVER ROCK CREEK. | 13 | Greater Hickory MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 100000
B-6015 | HIGHWAY | SR 1913 (SUGAR LOAF ROAD) | REPLACE BRIDGE 110237 OVER ROCK CREEK. | 13 | Greater Hickory MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | CONSTRUCTION | 819000
B-6016 | HIGHWAY | SR 2027 (MARTINS CREEK ROAD) | REPLACE BRIDGE 100142 OVER MARTIN CREEK. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014 | DIVISION 13 |  |  |  | 200000
B-6016 | HIGHWAY | SR 2027 (MARTINS CREEK ROAD) | REPLACE BRIDGE 100142 OVER MARTIN CREEK. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014 | DIVISION 13 |  | BGOFF | CONSTRUCTION | 700000
B-6016 | HIGHWAY | SR 2027 (MARTINS CREEK ROAD) | REPLACE BRIDGE 100142 OVER MARTIN CREEK. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014 | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 50000
B-6017 | HIGHWAY | SR 1151 (BALTIMORE BRANCH ROAD) | REPLACE BRIDGE 560222 OVER BACK BRANCH. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION | DIVISION 13 |  |  |  | 820000
B-6018 | HIGHWAY | SR 1296 (BROOKS BRANCH ROAD) | REPLACE BRIDGE 100536 OVER NEWFOUND CREEK. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | CONSTRUCTION | 872000
B-6018 | HIGHWAY | SR 1296 (BROOKS BRANCH ROAD) | REPLACE BRIDGE 100536 OVER NEWFOUND CREEK. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION. | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 55000
B-6018 | HIGHWAY | SR 1296 (BROOKS BRANCH ROAD) | REPLACE BRIDGE 100536 OVER NEWFOUND CREEK. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION. | DIVISION 13 |  |  |  | 200000
B-6019 | HIGHWAY | SR 1127 (ROBERTS BRANCH ROAD) | REPLACE BRIDGE 560311 OVER ROBERTS BRANCH. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION | DIVISION 13 |  |  |  | 950000
B-6025 | HIGHWAY | SR 1114 (SHOPE ROAD) | REPLACE BRIDGE 550244 OVER NORTH FORK COWEETA CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  |  |  | 255000
B-6025 | HIGHWAY | SR 1114 (SHOPE ROAD) | REPLACE BRIDGE 550244 OVER NORTH FORK COWEETA CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | BGOFF | CONSTRUCTION | 550000 | FY 2023: 6000; FY 2024: 544000
B-6025 | HIGHWAY | SR 1114 (SHOPE ROAD) | REPLACE BRIDGE 550244 OVER NORTH FORK COWEETA CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 15000 | FY 2023: 15000
B-6026 | HIGHWAY | SR 1500 (WATAUGA ROAD) | REPLACE BRIDGE 550214 OVER WATAUGA CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 50000 | FY 2024: 50000
B-6026 | HIGHWAY | SR 1500 (WATAUGA ROAD) | REPLACE BRIDGE 550214 OVER WATAUGA CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  |  |  | 200000
B-6026 | HIGHWAY | SR 1500 (WATAUGA ROAD) | REPLACE BRIDGE 550214 OVER WATAUGA CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 500000 | FY 2028: 442000; FY 2029: 58000
B-6028 | HIGHWAY | SR 1528 (LITTLE ELLIJAY ROAD) | REPLACE BRIDGE 550150 OVER ELLIJAY CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  |  |  | 250000
B-6028 | HIGHWAY | SR 1528 (LITTLE ELLIJAY ROAD) | REPLACE BRIDGE 550150 OVER ELLIJAY CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | BGOFF | CONSTRUCTION | 1800000 | FY 2023: 770000
B-6029 | HIGHWAY | SR 1001 (ELLIJAY ROAD) | REPLACE BRIDGE 550009 OVER NORTH PRONG ELLIJAY CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  |  |  | 200000
B-6029 | HIGHWAY | SR 1001 (ELLIJAY ROAD) | REPLACE BRIDGE 550009 OVER NORTH PRONG ELLIJAY CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | BGOFF | CONSTRUCTION | 700000 | FY 2023: 7000; FY 2024: 693000
B-6029 | HIGHWAY | SR 1001 (ELLIJAY ROAD) | REPLACE BRIDGE 550009 OVER NORTH PRONG ELLIJAY CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 70000 | FY 2023: 70000
B-6030 | HIGHWAY | SR 1351 (MATLOCK CREEK ROAD) | REPLACE BRIDGE 550220 OVER MATLOCK CREEK. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 14 |  |  |  | 262000
B-6030 | HIGHWAY | SR 1351 (MATLOCK CREEK ROAD) | REPLACE BRIDGE 550220 OVER MATLOCK CREEK. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 14 |  | BGOFF | CONSTRUCTION | 625000 | FY 2029: 514000; FY 2030: 111000
B-6031 | HIGHWAY | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490069 OVER SAVANNAH CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  |  |  | 200000
B-6031 | HIGHWAY | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490069 OVER SAVANNAH CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 800000 | FY 2025: 609000; FY 2026: 191000
B-6031 | HIGHWAY | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490069 OVER SAVANNAH CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 80000 | FY 2024: 80000
B-6032 | HIGHWAY | SR 1397 (THOMAS VALLEY ROAD) | REPLACE BRIDGE 490144 OVER NATIONS CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. 80 2019 BGOFF R 0 | DIVISION 14 |  |  |  | 200000
B-6032 | HIGHWAY | SR 1397 (THOMAS VALLEY ROAD) | REPLACE BRIDGE 490144 OVER NATIONS CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. 80 2019 BGOFF R 0 | DIVISION 14 |  | BGOFF | CONSTRUCTION | 983000 | FY 2023: 564000
B-6032 | HIGHWAY | SR 1397 (THOMAS VALLEY ROAD) | REPLACE BRIDGE 490144 OVER NATIONS CREEK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. 80 2019 BGOFF R 0 | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 50000
B-6033 | HIGHWAY | SR 1445 (LEE BUMGARNER ROAD) | REPLACE BRIDGE 490129 OVER SCOTT CREEK. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 14 |  |  |  | 320000
B-6033 | HIGHWAY | SR 1445 (LEE BUMGARNER ROAD) | REPLACE BRIDGE 490129 OVER SCOTT CREEK. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 14 |  | BGOFF | CONSTRUCTION | 1200000 | FY 2029: 911000; FY 2030: 289000
B-6034 | HIGHWAY | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490065 OVER SAVANNAH CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  |  |  | 200000
B-6034 | HIGHWAY | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490065 OVER SAVANNAH CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 800000 | FY 2027: 658000; FY 2028: 142000
B-6034 | HIGHWAY | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490065 OVER SAVANNAH CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 80000 | FY 2024: 80000
B-6035 | HIGHWAY | SR 1738 (HOOPER CEMETERY ROAD) | REPLACE BRIDGE 490203 OVER CANEY FORK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  |  |  | 200000
B-6035 | HIGHWAY | SR 1738 (HOOPER CEMETERY ROAD) | REPLACE BRIDGE 490203 OVER CANEY FORK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | BGOFF | CONSTRUCTION | 1415000 | FY 2023: 855000
B-6035 | HIGHWAY | SR 1738 (HOOPER CEMETERY ROAD) | REPLACE BRIDGE 490203 OVER CANEY FORK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 70000
B-6036 | HIGHWAY | SR 1737 (CANEY FORK ROAD) | REPLACE BRIDGE 490081 OVER JOHNS CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 70000 | FY 2023: 70000
B-6036 | HIGHWAY | SR 1737 (CANEY FORK ROAD) | REPLACE BRIDGE 490081 OVER JOHNS CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  |  |  | 200000
B-6036 | HIGHWAY | SR 1737 (CANEY FORK ROAD) | REPLACE BRIDGE 490081 OVER JOHNS CREEK. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 700000 | FY 2027: 576000; FY 2028: 124000
B-6037 | HIGHWAY | NC 86 | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILROAD. | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  | BFP | CONSTRUCTION | 2500000 | FY 2025: 1852000; FY 2026: 648000
B-6037 | HIGHWAY | NC 86 | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILROAD. | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  |  |  | 100000
B-6037 | HIGHWAY | NC 86 | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILROAD. | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  | BFP | RIGHT-OF-WAY | 250000 | FY 2024: 250000
B-6038 | HIGHWAY | NC 14 / NC 87 | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | 7 | Piedmont Triad RPO |  | REGION D |  | NHPB | UTILITIES | 163000 | FY 2027: 163000
B-6038 | HIGHWAY | NC 14 / NC 87 | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | 7 | Piedmont Triad RPO |  | REGION D |  |  |  | 100000
B-6038 | HIGHWAY | NC 14 / NC 87 | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | 7 | Piedmont Triad RPO |  | REGION D |  | BFP | CONSTRUCTION | 3900000 | FY 2028: 39000; FY 2029: 3206000; FY 2030: 655000
B-6038 | HIGHWAY | NC 14 / NC 87 | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | 7 | Piedmont Triad RPO |  | REGION D |  | NHPB | RIGHT-OF-WAY | 390000 | FY 2027: 390000
B-6041 | HIGHWAY | I-40 | REPLACE BRIDGE 170177 AND 170178 OVER LYLE CREEK. | 12 | Greater Hickory MPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 860000 | FY 2025: 860000
B-6041 | HIGHWAY | I-40 | REPLACE BRIDGE 170177 AND 170178 OVER LYLE CREEK. | 12 | Greater Hickory MPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 13500000 | FY 2030: 5563000; FY 2031: 6452000; FY 2032: 1485000
B-6041 | HIGHWAY | I-40 | REPLACE BRIDGE 170177 AND 170178 OVER LYLE CREEK. | 12 | Greater Hickory MPO |  | STATEWIDE MOBILITY |  |  |  | 100000
B-6044 | HIGHWAY | I-95 | REPLACE BRIDGE 500082 AND 500085 OVER BLACK CREEK AND BRIDGE 500100 AND 500101 OVER NEUSE RIVER. | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY |  |  |  | 100000
B-6044 | HIGHWAY | I-95 | REPLACE BRIDGE 500082 AND 500085 OVER BLACK CREEK AND BRIDGE 500100 AND 500101 OVER NEUSE RIVER. | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 28800000 | FY 2029: 10042000; FY 2030: 10716000; FY 2031: 7037000; FY 2032: 1005000
B-6044 | HIGHWAY | I-95 | REPLACE BRIDGE 500082 AND 500085 OVER BLACK CREEK AND BRIDGE 500100 AND 500101 OVER NEUSE RIVER. | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 90000 | FY 2027: 90000
B-6046 | HIGHWAY | SR 1917 (BETHLEHEM CHURCH ROAD) | REPLACE BRIDGE 830102 OVER LONG CREEK. | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  |  |  | 100000
B-6046 | HIGHWAY | SR 1917 (BETHLEHEM CHURCH ROAD) | REPLACE BRIDGE 830102 OVER LONG CREEK. | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGOFF | CONSTRUCTION | 1700000 | FY 2024: 291000; FY 2025: 1409000
B-6046 | HIGHWAY | SR 1917 (BETHLEHEM CHURCH ROAD) | REPLACE BRIDGE 830102 OVER LONG CREEK. | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGOFF | RIGHT-OF-WAY | 145000
B-6047 | HIGHWAY | SR 2125 (HARRIS HENRIETTA ROAD) | REPLACE BRIDGE 800145 OVER FLOYDS CREEK. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  |  |  | 100000
B-6047 | HIGHWAY | SR 2125 (HARRIS HENRIETTA ROAD) | REPLACE BRIDGE 800145 OVER FLOYDS CREEK. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | BGOFF | CONSTRUCTION | 2100000 | FY 2024: 1551000; FY 2025: 549000
B-6047 | HIGHWAY | SR 2125 (HARRIS HENRIETTA ROAD) | REPLACE BRIDGE 800145 OVER FLOYDS CREEK. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | BGOFF | RIGHT-OF-WAY | 210000 | FY 2023: 210000
B-6048 | HIGHWAY | SR 1812 (DIGGS ROAD) | REPLACE BRIDGE 030039 OVER JONES CREEK. | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  |  |  | 100000
B-6048 | HIGHWAY | SR 1812 (DIGGS ROAD) | REPLACE BRIDGE 030039 OVER JONES CREEK. | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGOFF | CONSTRUCTION | 1900000 | FY 2027: 819000; FY 2028: 1081000
B-6048 | HIGHWAY | SR 1812 (DIGGS ROAD) | REPLACE BRIDGE 030039 OVER JONES CREEK. | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGOFF | RIGHT-OF-WAY | 190000 | FY 2023: 190000
B-6049 | HIGHWAY | SR 1206 (WRIGHT BRIDGE ROAD) | REPLACE BRIDGE 810072 OVER GREAT COHARIE CREEK. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 100000
B-6049 | HIGHWAY | SR 1206 (WRIGHT BRIDGE ROAD) | REPLACE BRIDGE 810072 OVER GREAT COHARIE CREEK. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | CONSTRUCTION | 3400000 | FY 2023: 34000; FY 2024: 2677000; FY 2025: 689000
B-6049 | HIGHWAY | SR 1206 (WRIGHT BRIDGE ROAD) | REPLACE BRIDGE 810072 OVER GREAT COHARIE CREEK. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGOFF | RIGHT-OF-WAY | 340000 | FY 2023: 340000
B-6050 | HIGHWAY | SR 2137 (PITTMAN ROAD) SR 2130 (E MAIN STREET) SR | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 210000
B-6050 | HIGHWAY | SR 2137 (PITTMAN ROAD) SR 2130 (E MAIN STREET) SR | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BFP | CONSTRUCTION | 15000000 | FY 2027: 5301000; FY 2028: 6681000; FY 2029: 3018000
B-6050 | HIGHWAY | SR 2137 (PITTMAN ROAD) SR 2130 (E MAIN STREET) SR | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BFP | RIGHT-OF-WAY | 1500000 | FY 2025: 43000; FY 2026: 514000; FY 2027: 514000; FY 2028: 129000; FY 2029: 300000
B-6051 | HIGHWAY | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | REGION F |  | HIB | CONSTRUCTION | 36168000 | FY 2024: 4765000; FY 2025: 12705000; FY 2026: 10469000; FY 2027: 7213000; FY 2028: 1016000
B-6051 | HIGHWAY | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | REGION F |  | BFP | CONSTRUCTION | 4731000 | FY 2024: 623000; FY 2025: 1662000; FY 2026: 1369000; FY 2027: 944000; FY 2028: 133000
B-6051 | HIGHWAY | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | REGION F |  | HIB | RIGHT-OF-WAY | 4000000 | FY 2023: 4000000
B-6053 | HIGHWAY | PROVIDENCE ROAD | REPLACE BRIDGE 690034 OVER KNOBBS CREEK TRIBUTARY IN ELIZABETH CITY. | 1 | Albemarle RPO | COMPLETED. MUNICIPAL BRIDGE. | DIVISION 1 |  | L | CONSTRUCTION | 345000
B-6053 | HIGHWAY | PROVIDENCE ROAD | REPLACE BRIDGE 690034 OVER KNOBBS CREEK TRIBUTARY IN ELIZABETH CITY. | 1 | Albemarle RPO | COMPLETED. MUNICIPAL BRIDGE. | DIVISION 1 |  | L | UTILITIES | 27000
B-6053 | HIGHWAY | PROVIDENCE ROAD | REPLACE BRIDGE 690034 OVER KNOBBS CREEK TRIBUTARY IN ELIZABETH CITY. | 1 | Albemarle RPO | COMPLETED. MUNICIPAL BRIDGE. | DIVISION 1 |  | BGOFF | CONSTRUCTION | 1380000
B-6053 | HIGHWAY | PROVIDENCE ROAD | REPLACE BRIDGE 690034 OVER KNOBBS CREEK TRIBUTARY IN ELIZABETH CITY. | 1 | Albemarle RPO | COMPLETED. MUNICIPAL BRIDGE. | DIVISION 1 |  |  |  | 350000
B-6053 | HIGHWAY | PROVIDENCE ROAD | REPLACE BRIDGE 690034 OVER KNOBBS CREEK TRIBUTARY IN ELIZABETH CITY. | 1 | Albemarle RPO | COMPLETED. MUNICIPAL BRIDGE. | DIVISION 1 |  | BGOFF | UTILITIES | 108000
B-6054A | HIGHWAY | I-40 | REPLACE BRIDGE 430057 OVER US FOREST SERVICE ROAD/COLD SPRINGS CREEK AT HARMON'S DEN. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | ENGINEERING | 500000
B-6054A | HIGHWAY | I-40 | REPLACE BRIDGE 430057 OVER US FOREST SERVICE ROAD/COLD SPRINGS CREEK AT HARMON'S DEN. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 21788000 | FY 2023: 9681000; FY 2024: 1801000
B-6054B | HIGHWAY | I-40 | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 25000000 | FY 2023: 6417000; FY 2024: 13579000; FY 2025: 5004000
B-6054B | HIGHWAY | I-40 | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | ENGINEERING | 500000
B-6054B | HIGHWAY | I-40 | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | UTILITIES | 5000
B-6054C | HIGHWAY | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | ENGINEERING | 2500000
B-6054C | HIGHWAY | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 47000
B-6054C | HIGHWAY | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | UTILITIES | 5000
B-6054C | HIGHWAY | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 79725000 | FY 2023: 45199000; FY 2024: 17945000; FY 2025: 15784000
B-6054D | HIGHWAY | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 14 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 500000
B-6054D | HIGHWAY | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 14 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 5000 | FY 2024: 5000
B-6054D | HIGHWAY | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 14 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  | T | UTILITIES | 5000 | FY 2024: 5000
B-6054D | HIGHWAY | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 14 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 62100000 | FY 2024: 19474000; FY 2025: 32429000; FY 2026: 10197000
B-6054E | HIGHWAY | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 31100000 | FY 2023: 7656000; FY 2024: 13316000; FY 2025: 6335000; FY 2026: 3793000
B-6054E | HIGHWAY | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | ENGINEERING | 2000000
B-6054E | HIGHWAY | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 50000 | FY 2023: 50000
B-6054E | HIGHWAY | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | UTILITIES | 5000 | FY 2023: 5000
B-8888 | HIGHWAY | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | BGOFF | CONSTRUCTION | 0 | FY 2023: 0
B-8888DIV | HIGHWAY | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | BFP | CONSTRUCTION | 0 | FY 2023: 0
B-8888REG | HIGHWAY | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | REGION SW |  | BFP | CONSTRUCTION | 0 | FY 2023: 0
B-8888SW | HIGHWAY | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 0 | FY 2023: 0
B-9999 | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 257354000
B-9999DIV | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | BG | IMPLEMENTATION | 7200000
B-9999REG | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM. | 99 | STATEWIDE PROJECT |  | REGION SW |  | BG | IMPLEMENTATION | 7200000
B-9999SW | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | BG | IMPLEMENTATION | 9600000
BF-0001 | BIKE/PED | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | EXEMPT |  | FLAP | ENGINEERING | 8000
BF-0001 | BIKE/PED | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | EXEMPT |  | FLAP | CONSTRUCTION | 152000 | FY 2023: 150000
BF-0001 | BIKE/PED | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | EXEMPT |  | S(M) | ENGINEERING | 2000
BF-0001 | BIKE/PED | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | EXEMPT |  | S(M) | CONSTRUCTION | 38000 | FY 2023: 38000
BF-0002 | BIKE/PED | ECUSTA TRAIL | TRANSYLVANIA COUNTY LINE TO LAMB CREEK. CONSTRUCT GREENWAY. | 14 | Land-of-Sky RPO | FLAP PROJECT NC 61. PE AWARDED $1.0M. | EXEMPT |  | FLAP | ENGINEERING | 1000000 | FY 2023: 1000000
BK-5100 | HIGHWAY | VARIOUS | ESTABLISH BRIDGE MANAGEMENT SYSTEM. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 2500000
BK-5101 | HIGHWAY | VARIOUS | DECK PRESERVATION AT 15 SELECTED LOCATIONS. | 99 | STATEWIDE PROJECT | UNDER CONSTRUCTION | DIVISION SW |  |  |  | 12337000
BK-5102 | HIGHWAY | VARIOUS | BRIDGE PAINTING AT 19 SELECTED LOCATIONS. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 10918000
BL-0001 | BIKE/PED | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  | BGANY | CONSTRUCTION | 272000 | FY 2023: 272000
BL-0001 | BIKE/PED | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  | BGDA | ENGINEERING | 64000
BL-0001 | BIKE/PED | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2023: 80000
BL-0001 | BIKE/PED | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  | L | ENGINEERING | 16000
BL-0001 | BIKE/PED | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  | L | RIGHT-OF-WAY | 20000 | FY 2023: 20000
BL-0001 | BIKE/PED | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  | L | CONSTRUCTION | 68000 | FY 2023: 68000
BL-0002 | BIKE/PED | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11 |  | BGANY | CONSTRUCTION | 352000 | FY 2024: 101000; FY 2025: 251000
BL-0002 | BIKE/PED | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11 |  | BGDA | ENGINEERING | 64000
BL-0002 | BIKE/PED | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11 |  | BGDA | RIGHT-OF-WAY | 19000 | FY 2024: 19000
BL-0002 | BIKE/PED | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11 |  | L | ENGINEERING | 16000
BL-0002 | BIKE/PED | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11 |  | L | RIGHT-OF-WAY | 5000 | FY 2024: 5000
BL-0002 | BIKE/PED | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11 |  | L | CONSTRUCTION | 88000 | FY 2024: 25000; FY 2025: 63000
BL-0003 | BIKE/PED | DAVIDSON | WEST BRANCH NATURE PRESERVE. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | ENGINEERING | 121000 | FY 2023: 121000
BL-0003 | BIKE/PED | DAVIDSON | WEST BRANCH NATURE PRESERVE. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 30000 | FY 2023: 30000
BL-0005 | BIKE/PED | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 13 | French Broad River MPO | COMPLETE. "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. HF FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | DIVISION 13 |  | BGDA | CONSTRUCTION | 749000 | FY 2023: 585000
BL-0005 | BIKE/PED | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 13 | French Broad River MPO | COMPLETE. "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. HF FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | DIVISION 13 |  | HF | CONSTRUCTION | 142000 | FY 2023: 93000
BL-0005 | BIKE/PED | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 13 | French Broad River MPO | COMPLETE. "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. HF FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | DIVISION 13 |  | HSIP | CONSTRUCTION | 45000 | FY 2023: 29000
BL-0005 | BIKE/PED | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 13 | French Broad River MPO | COMPLETE. "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. HF FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | DIVISION 13 |  | S(M) | ENGINEERING | 1000
BL-0005 | BIKE/PED | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 13 | French Broad River MPO | COMPLETE. "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. HF FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | DIVISION 13 |  | S(M) | CONSTRUCTION | 188000 | FY 2023: 147000
BL-0005 | BIKE/PED | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 13 | French Broad River MPO | COMPLETE. "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. HF FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | DIVISION 13 |  | BGDA | ENGINEERING | 3000
BL-0006 | BIKE/PED | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | ENGINEERING | 60000 | FY 2026: 60000
BL-0006 | BIKE/PED | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | CONSTRUCTION | 600000 | FY 2026: 600000
BL-0006 | BIKE/PED | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). | 13 | French Broad River MPO |  | DIVISION 13 |  | L | ENGINEERING | 15000 | FY 2026: 15000
BL-0006 | BIKE/PED | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 150000 | FY 2026: 150000
BL-0007 | BIKE/PED | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021 | DIVISION 14 |  | L | CONSTRUCTION | 1118000 | FY 2023: 1118000
BL-0007 | BIKE/PED | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021 | DIVISION 14 |  | L | CONSTRUCTION | 40000 | FY 2023: 40000
BL-0007 | BIKE/PED | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021 | DIVISION 14 |  | TADA | CONSTRUCTION | 160000 | FY 2023: 160000
BL-0007 | BIKE/PED | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021 | DIVISION 14 |  | L | CONSTRUCTION | 579000 | FY 2023: 579000
BL-0007 | BIKE/PED | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021 | DIVISION 14 |  | BGDA | CONSTRUCTION | 2318000 | FY 2023: 2318000
BL-0007 | BIKE/PED | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021 | DIVISION 14 |  | BGDA | ENGINEERING | 836000 | FY 2023: 290000
BL-0007 | BIKE/PED | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021 | DIVISION 14 |  | BGANY | CONSTRUCTION | 4470000 | FY 2023: 4470000
BL-0007 | BIKE/PED | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021 | DIVISION 14 |  | L | ENGINEERING | 210000 | FY 2023: 73000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | BGDA | CONSTRUCTION | 487000 | FY 2024: 487000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | L | CONSTRUCTION | 449000 | FY 2024: 449000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | L | CONSTRUCTION | 122000 | FY 2024: 122000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | L | CONSTRUCTION | 20000 | FY 2024: 20000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | L | ENGINEERING | 121000 | FY 2023: 121000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | BGDA | CONSTRUCTION | 1796000 | FY 2024: 1796000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | BGDA | ENGINEERING | 484000 | FY 2023: 484000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | BGDA | ENGINEERING | 638000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | BGANY | CONSTRUCTION | 78000 | FY 2024: 78000
BL-0008 | BIKE/PED | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP | DIVISION 14 |  | L | ENGINEERING | 160000
BL-0009 | BIKE/PED | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 493000 | FY 2025: 493000
BL-0009 | BIKE/PED | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | CONSTRUCTION | 147000 | FY 2027: 147000
BL-0009 | BIKE/PED | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 124000 | FY 2025: 124000
BL-0009 | BIKE/PED | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | ENGINEERING | 28000 | FY 2024: 28000
BL-0009 | BIKE/PED | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | ENGINEERING | 110000 | FY 2024: 110000
BL-0009 | BIKE/PED | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | CONSTRUCTION | 585000 | FY 2027: 585000
BL-0010 | BIKE/PED | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1300000 | FY 2026: 1300000
BL-0010 | BIKE/PED | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 188000 | FY 2023: 188000
BL-0010 | BIKE/PED | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 258000 | FY 2024: 258000
BL-0010 | BIKE/PED | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 188000 | FY 2023: 188000
BL-0010 | BIKE/PED | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 1300000 | FY 2026: 1300000
BL-0010 | BIKE/PED | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 258000 | FY 2024: 258000
BL-0011 | BIKE/PED | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 268000 | FY 2024: 268000
BL-0011 | BIKE/PED | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 13000 | FY 2023: 13000
BL-0011 | BIKE/PED | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 67000 | FY 2024: 67000
BL-0011 | BIKE/PED | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | ENGINEERING | 50000 | FY 2023: 50000
BL-0012 | BIKE/PED | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 98000 | FY 2023: 98000
BL-0012 | BIKE/PED | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 146000 | FY 2023: 146000
BL-0012 | BIKE/PED | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 63000 | FY 2024: 63000
BL-0012 | BIKE/PED | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 94000 | FY 2024: 94000
BL-0012 | BIKE/PED | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 524000 | FY 2025: 524000
BL-0012 | BIKE/PED | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 785000 | FY 2025: 785000
BL-0013 | BIKE/PED | MOORE AVENUE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | CONSTRUCTION | 1200000 | FY 2025: 1200000
BL-0013 | BIKE/PED | MOORE AVENUE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | CONSTRUCTION | 800000 | FY 2025: 800000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | CONSTRUCTION | 375000 | FY 2024: 375000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | CONSTRUCTION | 76000 | FY 2025: 76000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | RIGHT-OF-WAY | 3000 | FY 2024: 3000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | RIGHT-OF-WAY | 26000 | FY 2023: 26000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | ENGINEERING | 21000 | FY 2023: 21000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | ENGINEERING | 51000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 11000 | FY 2024: 11000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 105000 | FY 2023: 105000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | ENGINEERING | 83000 | FY 2023: 83000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | ENGINEERING | 206000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGANY | CONSTRUCTION | 1501000 | FY 2024: 1501000
BL-0014 | BIKE/PED | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | CONSTRUCTION | 305000 | FY 2025: 305000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 633000 | FY 2026: 633000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 35000 | FY 2027: 35000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 158000 | FY 2026: 158000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 2000 | FY 2026: 2000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 18000 | FY 2025: 18000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 108000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 138000 | FY 2027: 138000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 7000 | FY 2026: 7000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 72000 | FY 2025: 72000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | ENGINEERING | 38000 | FY 2025: 38000
BL-0015 | BIKE/PED | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 9000 | FY 2025: 9000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 28000 | FY 2026: 28000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 66000 | FY 2025: 66000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 1000 | FY 2025: 1000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 14000 | FY 2024: 14000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 2000 | FY 2024: 2000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 6000 | FY 2025: 6000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 58000 | FY 2024: 58000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | ENGINEERING | 8000 | FY 2024: 8000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 45000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 264000 | FY 2025: 264000
BL-0016 | BIKE/PED | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 7000 | FY 2026: 7000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 4000 | FY 2025: 4000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 126000 | FY 2025: 126000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 1000 | FY 2025: 1000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 9000 | FY 2024: 9000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 12000 | FY 2024: 12000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 17000 | FY 2023: 17000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 504000 | FY 2025: 504000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 44000 | FY 2026: 44000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 36000 | FY 2024: 36000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | ENGINEERING | 48000 | FY 2024: 48000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | ENGINEERING | 69000 | FY 2023: 69000
BL-0017 | BIKE/PED | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 177000 | FY 2026: 177000
BL-0018 | BIKE/PED | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | ENGINEERING | 41000 | FY 2023: 41000
BL-0018 | BIKE/PED | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | CONSTRUCTION | 465000 | FY 2024: 465000
BL-0018 | BIKE/PED | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | RIGHT-OF-WAY | 103000 | FY 2023: 103000
BL-0018 | BIKE/PED | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | ENGINEERING | 164000 | FY 2023: 164000
BL-0018 | BIKE/PED | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGANY | CONSTRUCTION | 1861000 | FY 2024: 1861000
BL-0018 | BIKE/PED | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 410000 | FY 2023: 410000
BL-0019 | BIKE/PED | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO | DP REPRESENT RAISE GRANT FUNDS | DIVISION 9 |  | L | RIGHT-OF-WAY | 20000 | FY 2025: 20000
BL-0019 | BIKE/PED | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO | DP REPRESENT RAISE GRANT FUNDS | DIVISION 9 |  | L | CONSTRUCTION | 1500000 | FY 2025: 1500000
BL-0019 | BIKE/PED | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO | DP REPRESENT RAISE GRANT FUNDS | DIVISION 9 |  | L | ENGINEERING | 200000 | FY 2024: 200000
BL-0019 | BIKE/PED | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO | DP REPRESENT RAISE GRANT FUNDS | DIVISION 9 |  | DP | CONSTRUCTION | 6000000 | FY 2025: 6000000
BL-0019 | BIKE/PED | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO | DP REPRESENT RAISE GRANT FUNDS | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2025: 80000
BL-0019 | BIKE/PED | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO | DP REPRESENT RAISE GRANT FUNDS | DIVISION 9 |  | BGDA | ENGINEERING | 800000 | FY 2024: 800000
BL-0020 | BIKE/PED | DEPOT STREET | US 311 (MAIN STREET) TO SR 1992 (SULLIVANTOWN ROAD) IN WALKERTOWN. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 96000 | FY 2023: 96000
BL-0020 | BIKE/PED | DEPOT STREET | US 311 (MAIN STREET) TO SR 1992 (SULLIVANTOWN ROAD) IN WALKERTOWN. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 383000 | FY 2023: 383000
BL-0021 | BIKE/PED | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION TRANSPORTATION ALTERNATIVES PROGRAM. | 3 | Grand Strand Area Transportation Study |  | DIVISION 3 |  | TADA | CONSTRUCTION | 1215000 | 303000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 432000
BL-0022 | BIKE/PED | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | ENGINEERING | 33000
BL-0022 | BIKE/PED | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 236000 | FY 2023: 2000; FY 2024: 234000
BL-0022 | BIKE/PED | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | UTILITIES | 19000 | FY 2023: 19000
BL-0022 | BIKE/PED | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 19000 | FY 2023: 19000
BL-0022 | BIKE/PED | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | UTILITIES | 76000 | FY 2023: 76000
BL-0022 | BIKE/PED | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 131000
BL-0022 | BIKE/PED | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 76000 | FY 2023: 76000
BL-0022 | BIKE/PED | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 944000 | FY 2023: 10000; FY 2024: 934000
BL-0023 | BIKE/PED | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO MIDDLECREST WAY IN HOLLY SPRINGS. ENHANCE PEDESTRIAN SAFETY. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGDA | CONSTRUCTION | 558000
BL-0023 | BIKE/PED | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO MIDDLECREST WAY IN HOLLY SPRINGS. ENHANCE PEDESTRIAN SAFETY. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | CONSTRUCTION | 557000
BL-0024 | BIKE/PED | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 20000
BL-0024 | BIKE/PED | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | UTILITIES | 81000
BL-0024 | BIKE/PED | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | RIGHT-OF-WAY | 20000
BL-0024 | BIKE/PED | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | ENGINEERING | 528000
BL-0024 | BIKE/PED | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGDA | UTILITIES | 82000
BL-0024 | BIKE/PED | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | CONSTRUCTION | 2701000 | FY 2023: 1342000; FY 2024: 1359000
BL-0024 | BIKE/PED | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGDA | ENGINEERING | 432000
BL-0024 | BIKE/PED | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGDA | CONSTRUCTION | 2210000 | FY 2023: 1098000; FY 2024: 1112000
BL-0025 | BIKE/PED | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | ENGINEERING | 30000
BL-0025 | BIKE/PED | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 40000 | FY 2023: 40000
BL-0025 | BIKE/PED | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 268000 | FY 2023: 3000; FY 2024: 265000
BL-0025 | BIKE/PED | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 1071000 | FY 2023: 11000; FY 2024: 1060000
BL-0025 | BIKE/PED | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 120000
BL-0025 | BIKE/PED | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 160000 | FY 2023: 160000
BL-0026 | BIKE/PED | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 153000
BL-0026 | BIKE/PED | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 744000 | FY 2023: 7000; FY 2024: 737000
BL-0026 | BIKE/PED | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | ENGINEERING | 66000
BL-0026 | BIKE/PED | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 319000 | FY 2023: 3000; FY 2024: 316000
BL-0027 | BIKE/PED | CRABTREE CREEK GREENWAY | LASSITER MILL ROAD TO HERTFORD STREET IN RALEIGH. CONSTRUCT GREENWAY TRAIL. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 1182000 | FY 2023: 12000; FY 2024: 1170000
BL-0027 | BIKE/PED | CRABTREE CREEK GREENWAY | LASSITER MILL ROAD TO HERTFORD STREET IN RALEIGH. CONSTRUCT GREENWAY TRAIL. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 507000 | FY 2023: 5000; FY 2024: 502000
BL-0028 | BIKE/PED | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | CMAQ | CONSTRUCTION | 375000 | FY 2023: 4000; FY 2024: 371000
BL-0028 | BIKE/PED | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | STBG | CONSTRUCTION | 354000 | FY 2023: 4000; FY 2024: 350000
BL-0028 | BIKE/PED | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | STBG | ENGINEERING | 75000
BL-0028 | BIKE/PED | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | ENGINEERING | 31000
BL-0028 | BIKE/PED | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | CMAQ | ENGINEERING | 48000
BL-0028 | BIKE/PED | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 182000 | FY 2023: 2000; FY 2024: 180000
BL-0030 | BIKE/PED | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 14000
BL-0030 | BIKE/PED | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 91000
BL-0030 | BIKE/PED | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | BGDACV | ENGINEERING | 15000
BL-0030 | BIKE/PED | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | BGDACV | CONSTRUCTION | 52000
BL-0030 | BIKE/PED | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | ENGINEERING | 7000
BL-0030 | BIKE/PED | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 19000
BL-0031 | BIKE/PED | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STPEHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 97000 | FY 2023: 1000; FY 2024: 96000
BL-0031 | BIKE/PED | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STPEHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | ENGINEERING | 20000
BL-0031 | BIKE/PED | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STPEHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | STBG | CONSTRUCTION | 243000 | FY 2023: 2000; FY 2024: 241000
BL-0031 | BIKE/PED | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STPEHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | STBG | ENGINEERING | 40000
BL-0032 | BIKE/PED | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | L | ENGINEERING | 20000
BL-0032 | BIKE/PED | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | L | RIGHT-OF-WAY | 2000 | FY 2023: 2000
BL-0032 | BIKE/PED | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | L | CONSTRUCTION | 68000 | FY 2023: 1000; FY 2024: 67000
BL-0032 | BIKE/PED | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | CMAQ | RIGHT-OF-WAY | 8000 | FY 2023: 8000
BL-0032 | BIKE/PED | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | CMAQ | ENGINEERING | 80000
BL-0032 | BIKE/PED | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | CMAQ | CONSTRUCTION | 272000 | FY 2023: 3000; FY 2024: 269000
BL-0033 | BIKE/PED | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 10000 | FY 2024: 10000
BL-0033 | BIKE/PED | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | CONSTRUCTION | 290000 | FY 2025: 200000; FY 2026: 90000
BL-0033 | BIKE/PED | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | ENGINEERING | 38000 | FY 2023: 38000
BL-0033 | BIKE/PED | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1159000 | FY 2025: 801000; FY 2026: 358000
BL-0033 | BIKE/PED | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 40000 | FY 2024: 40000
BL-0033 | BIKE/PED | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 150000 | FY 2023: 150000
BL-0034 | BIKE/PED | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) | WEST OF KELSEY SCOTT PARK GREENWAY TO END OF SALISBURY MALL GREENWAY/CAROLINA THREAD TRAIL. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 72000 | FY 2024: 72000
BL-0034 | BIKE/PED | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) | WEST OF KELSEY SCOTT PARK GREENWAY TO END OF SALISBURY MALL GREENWAY/CAROLINA THREAD TRAIL. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 483000 | FY 2025: 139000; FY 2026: 344000
BL-0034 | BIKE/PED | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) | WEST OF KELSEY SCOTT PARK GREENWAY TO END OF SALISBURY MALL GREENWAY/CAROLINA THREAD TRAIL. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | ENGINEERING | 30000
BL-0034 | BIKE/PED | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) | WEST OF KELSEY SCOTT PARK GREENWAY TO END OF SALISBURY MALL GREENWAY/CAROLINA THREAD TRAIL. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 18000 | FY 2024: 18000
BL-0034 | BIKE/PED | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) | WEST OF KELSEY SCOTT PARK GREENWAY TO END OF SALISBURY MALL GREENWAY/CAROLINA THREAD TRAIL. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | CONSTRUCTION | 121000 | FY 2025: 35000; FY 2026: 86000
BL-0034 | BIKE/PED | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) | WEST OF KELSEY SCOTT PARK GREENWAY TO END OF SALISBURY MALL GREENWAY/CAROLINA THREAD TRAIL. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 121000
BL-0035 | BIKE/PED | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 32000
BL-0035 | BIKE/PED | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 8 | Triangle Area RPO |  | EXEMPT |  | L | CONSTRUCTION | 32000 | FY 2023: 32000
BL-0035 | BIKE/PED | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 8 | Triangle Area RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 2000
BL-0035 | BIKE/PED | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 8000
BL-0035 | BIKE/PED | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 128000 | FY 2023: 128000
BL-0035 | BIKE/PED | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 8 | Triangle Area RPO |  | EXEMPT |  | L | ENGINEERING | 8000
BL-0036 | BIKE/PED | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 198000 | FY 2024: 198000
BL-0036 | BIKE/PED | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1122000 | FY 2024: 1019000; FY 2025: 103000
BL-0036 | BIKE/PED | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 5 | Capital Area MPO |  | EXEMPT |  | L | ENGINEERING | 50000 | FY 2024: 50000
BL-0036 | BIKE/PED | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 280000 | FY 2024: 254000; FY 2025: 26000
BL-0037 | BIKE/PED | CRABTREE CREEK GREENWAY CONNECTOR | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 2261000 | FY 2023: 23000; FY 2024: 1892000; FY 2025: 346000
BL-0037 | BIKE/PED | CRABTREE CREEK GREENWAY CONNECTOR | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 565000 | FY 2023: 6000; FY 2024: 473000; FY 2025: 86000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | ENGINEERING | 14000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 70000 | FY 2024: 70000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 1000 | FY 2023: 1000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 13000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 3000 | FY 2023: 3000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | UTILITIES | 60000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 52000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 58000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | UTILITIES | 15000
BL-0038 | BIKE/PED | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 279000 | FY 2024: 279000
BL-0039 | BIKE/PED | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 858000 | FY 2024: 712000; FY 2025: 146000
BL-0039 | BIKE/PED | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 286000 | FY 2024: 237000; FY 2025: 49000
BL-0039 | BIKE/PED | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | L | ENGINEERING | 12000
BL-0039 | BIKE/PED | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 125000 | FY 2023: 125000
BL-0039 | BIKE/PED | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 38000
BL-0039 | BIKE/PED | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 42000 | FY 2023: 42000
BL-0040 | BIKE/PED | VARIOUS | MIDDLE SOUND LOOP CONNECTOR CONSTRUCTION AND PORTERS NECK WALMART CONNECTOR. CONSTRUCT MULTI-USE PATH. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGDA | CONSTRUCTION | 554000 | FY 2023: 554000
BL-0040 | BIKE/PED | VARIOUS | MIDDLE SOUND LOOP CONNECTOR CONSTRUCTION AND PORTERS NECK WALMART CONNECTOR. CONSTRUCT MULTI-USE PATH. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | CONSTRUCTION | 138000 | FY 2023: 138000
BL-0041 | BIKE/PED | LATHAM PARK GREENWAY LAKE DANIEL GREENWAY; | LAKE DANIEL GREENWAY, FRIENDLY AVENUE TO JOSEPHINE BOYD STREET, AND LATHAM PARK GREENWAY AT TENNIS COURTS NEAR WENDOVER AVENUE IN GREENSBORO. REPAIR SURFACES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDACV | CONSTRUCTION | 500000 | FY 2023: 500000
BL-0042 | BIKE/PED | VANCE ARLINGTON GREENWAY | NORTH OF FLORIDA STREET TO BRAGG STREET IN GREENSBORO. CONSTRUCT GREENWAY AND SIDEPATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDACV | CONSTRUCTION | 1200000 | FY 2023: 12000; FY 2024: 1188000
BL-0043 | BIKE/PED | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | CONSTRUCTION | 105000 | FY 2024: 105000
BL-0043 | BIKE/PED | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | ENGINEERING | 23000
BL-0043 | BIKE/PED | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 419000 | FY 2024: 419000
BL-0043 | BIKE/PED | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 92000
BL-0044 | BIKE/PED | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO | “S” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | DIVISION 7 |  | BGDA | CONSTRUCTION | 978000 | FY 2023: 822000; FY 2024: 156000
BL-0044 | BIKE/PED | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO | “S” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | DIVISION 7 |  | L | CONSTRUCTION | 193000 | FY 2023: 162000; FY 2024: 31000
BL-0044 | BIKE/PED | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO | “S” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | DIVISION 7 |  | S | ENGINEERING | 175000
BL-0044 | BIKE/PED | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO | “S” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | DIVISION 7 |  | S | CONSTRUCTION | 140000 | FY 2023: 118000; FY 2024: 22000
BL-0045 | BIKE/PED | WILMINGTON | WILMINGTON RAIL TRAIL. CONSTRUCT MULTI-USE PATH FROM 3RD STREET IN DOWNTOWN WILMINGTON TO THE LOVE GROVE BRIDGE MULTI-USE PATH FACILITY. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDACV | ENGINEERING | 680000
BL-0046 | BIKE/PED | SR 1116 (OCEAN BOULEVARD) | INSTALL BIKE LANES ALONG SR 1116 (OCEAN BOULEVARD) FROM JUST WEST OF SHELL DRIVE TO DUNESCAPE DRIVE IN HOLDEN BEACH. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  | BGDA | CONSTRUCTION | 913000
BL-0046 | BIKE/PED | SR 1116 (OCEAN BOULEVARD) | INSTALL BIKE LANES ALONG SR 1116 (OCEAN BOULEVARD) FROM JUST WEST OF SHELL DRIVE TO DUNESCAPE DRIVE IN HOLDEN BEACH. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  | L | CONSTRUCTION | 700000
BL-0047 | BIKE/PED | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 44000 | FY 2023: 44000
BL-0047 | BIKE/PED | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 305000 | FY 2023: 305000
BL-0047 | BIKE/PED | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. | 5 | Capital Area MPO |  | DIVISION 5 |  | TADA | RIGHT-OF-WAY | 177000 | FY 2023: 177000
BL-0047 | BIKE/PED | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. | 5 | Capital Area MPO |  | DIVISION 5 |  | TADA | CONSTRUCTION | 1219000 | FY 2023: 1219000
BL-0048 | BIKE/PED | SR 1616 / NON-SYSTEM (OLD APEX ROAD) | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 800000 | FY 2023: 8000; FY 2024: 792000
BL-0048 | BIKE/PED | SR 1616 / NON-SYSTEM (OLD APEX ROAD) | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 1200000 | FY 2023: 12000; FY 2024: 1188000
BL-0049 | HIGHWAY | SR 1632 (LOUIS STEPHENS DRIVE) | GRAY MARBLE ROAD TO ADDENBROCK DRIVE IN MORRISVILLE, AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 385000 | FY 2026: 4000; FY 2027: 381000
BL-0049 | HIGHWAY | SR 1632 (LOUIS STEPHENS DRIVE) | GRAY MARBLE ROAD TO ADDENBROCK DRIVE IN MORRISVILLE, AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 165000 | FY 2026: 2000; FY 2027: 163000
BL-0050 | HIGHWAY | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 140000 | FY 2023: 140000
BL-0050 | HIGHWAY | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | CMAQ | CONSTRUCTION | 315000 | FY 2024: 315000
BL-0050 | HIGHWAY | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | RIGHT-OF-WAY | 60000 | FY 2023: 60000
BL-0050 | HIGHWAY | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | CONSTRUCTION | 135000 | FY 2024: 135000
BL-0051 | HIGHWAY | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO | "S" REFERS TO SPOT SAFETY HIGHWAY FUNDS | EXEMPT |  | CMAQ | ENGINEERING | 39000 | FY 2023: 39000
BL-0051 | HIGHWAY | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO | "S" REFERS TO SPOT SAFETY HIGHWAY FUNDS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 39000 | FY 2023: 39000
BL-0051 | HIGHWAY | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO | "S" REFERS TO SPOT SAFETY HIGHWAY FUNDS | EXEMPT |  | CMAQ | CONSTRUCTION | 273000 | FY 2024: 273000
BL-0051 | HIGHWAY | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO | "S" REFERS TO SPOT SAFETY HIGHWAY FUNDS | EXEMPT |  | S | ENGINEERING | 11000 | FY 2023: 11000
BL-0051 | HIGHWAY | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO | "S" REFERS TO SPOT SAFETY HIGHWAY FUNDS | EXEMPT |  | S | RIGHT-OF-WAY | 11000 | FY 2023: 11000
BL-0051 | HIGHWAY | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO | "S" REFERS TO SPOT SAFETY HIGHWAY FUNDS | EXEMPT |  | S | CONSTRUCTION | 77000 | FY 2024: 77000
BL-0052 | HIGHWAY | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | EXEMPT |  | L | ENGINEERING | 15000 | FY 2023: 15000
BL-0052 | HIGHWAY | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 50000 | FY 2023: 50000
BL-0052 | HIGHWAY | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 100000 | FY 2023: 100000
BL-0052 | HIGHWAY | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 400000 | FY 2023: 400000
BL-0052 | HIGHWAY | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 200000 | FY 2023: 200000
BL-0052 | HIGHWAY | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 60000 | FY 2023: 60000
BL-0053 | HIGHWAY | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 24000 | FY 2023: 24000
BL-0053 | HIGHWAY | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 600000 | FY 2023: 600000
BL-0053 | HIGHWAY | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | EXEMPT |  | L | ENGINEERING | 120000 | FY 2023: 120000
BL-0053 | HIGHWAY | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 2400000 | FY 2023: 2400000
BL-0053 | HIGHWAY | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 96000 | FY 2023: 96000
BL-0053 | HIGHWAY | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 480000 | FY 2023: 480000
BL-0054 | BIKE/PED | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 40000 | FY 2023: 40000
BL-0054 | BIKE/PED | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 492000 | FY 2024: 492000
BL-0054 | BIKE/PED | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | ENGINEERING | 12000 | FY 2023: 12000
BL-0054 | BIKE/PED | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 10000 | FY 2023: 10000
BL-0054 | BIKE/PED | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 123000 | FY 2024: 123000
BL-0054 | BIKE/PED | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 48000 | FY 2023: 48000
BL-0055 | BIKE/PED | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | CONSTRUCTION | 1561000 | FY 2026: 1561000
BL-0055 | BIKE/PED | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | ENGINEERING | 91000 | FY 2025: 91000
BL-0055 | BIKE/PED | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | ENGINEERING | 272000 | FY 2025: 272000
BL-0055 | BIKE/PED | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | CONSTRUCTION | 520000 | FY 2026: 520000
BL-0056 | BIKE/PED | SR 2162 (WHITE OAK ROAD) MAPLE AVENUE McNEELY AVEN | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | CONSTRUCTION | 493000 | FY 2026: 493000
BL-0056 | BIKE/PED | SR 2162 (WHITE OAK ROAD) MAPLE AVENUE McNEELY AVEN | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | ENGINEERING | 422000 | FY 2024: 422000
BL-0056 | BIKE/PED | SR 2162 (WHITE OAK ROAD) MAPLE AVENUE McNEELY AVEN | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 78000 | FY 2025: 78000
BL-0056 | BIKE/PED | SR 2162 (WHITE OAK ROAD) MAPLE AVENUE McNEELY AVEN | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | CONSTRUCTION | 1479000 | FY 2026: 1479000
BL-0056 | BIKE/PED | SR 2162 (WHITE OAK ROAD) MAPLE AVENUE McNEELY AVEN | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | ENGINEERING | 141000 | FY 2024: 141000
BL-0056 | BIKE/PED | SR 2162 (WHITE OAK ROAD) MAPLE AVENUE McNEELY AVEN | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 26000 | FY 2025: 26000
BL-0057 | BIKE/PED | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | L | CONSTRUCTION | 1218000 | FY 2025: 1218000
BL-0057 | BIKE/PED | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | BGDA | CONSTRUCTION | 389000 | FY 2025: 389000
BL-0057 | BIKE/PED | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 4483000 | FY 2025: 4483000
BL-0058 | BIKE/PED | RAIL TRAIL PEDESTRIAN BRIDGE | SR 3815 (EAST MOREHEAD STREET) TO BROOKLYN VILLAGE LIGHT RAIL STATION. CONSTRUCT RAIL TRAIL PEDESTRIAN BRIDGE OVER I-277 (BELK FREEWAY). | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 1903000 | FY 2023: 1903000
BL-0058 | BIKE/PED | RAIL TRAIL PEDESTRIAN BRIDGE | SR 3815 (EAST MOREHEAD STREET) TO BROOKLYN VILLAGE LIGHT RAIL STATION. CONSTRUCT RAIL TRAIL PEDESTRIAN BRIDGE OVER I-277 (BELK FREEWAY). | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 4440000 | FY 2023: 4440000
BL-0059 | BIKE/PED | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | L | CONSTRUCTION | 52000 | FY 2024: 31000; FY 2025: 21000
BL-0059 | BIKE/PED | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | BGDACV | ENGINEERING | 57000 | FY 2023: 57000
BL-0059 | BIKE/PED | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | BGDACV | RIGHT-OF-WAY | 53000 | FY 2023: 53000
BL-0059 | BIKE/PED | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | BGDACV | CONSTRUCTION | 250000 | FY 2024: 147000; FY 2025: 103000
BL-0060 | BIKE/PED | CLARKE CREEK GREENWAY | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | CONSTRUCTION | 387000 | FY 2025: 4000; FY 2026: 339000; FY 2027: 44000
BL-0060 | BIKE/PED | CLARKE CREEK GREENWAY | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1551000 | FY 2025: 16000; FY 2026: 1359000; FY 2027: 176000
BL-0061 | HIGHWAY | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 5 | Kerr-Tar RPO |  | EXEMPT |  | L | CONSTRUCTION | 90000 | FY 2024: 1000; FY 2025: 89000
BL-0061 | HIGHWAY | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 5 | Kerr-Tar RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 104000 | FY 2023: 104000
BL-0061 | HIGHWAY | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 5 | Kerr-Tar RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 52000 | FY 2024: 52000
BL-0061 | HIGHWAY | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 5 | Kerr-Tar RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 360000 | FY 2024: 4000; FY 2025: 356000
BL-0061 | HIGHWAY | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 5 | Kerr-Tar RPO |  | EXEMPT |  | L | ENGINEERING | 26000 | FY 2023: 26000
BL-0061 | HIGHWAY | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 5 | Kerr-Tar RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 13000 | FY 2024: 13000
BL-0062 | HIGHWAY | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 8 | Triangle Area RPO |  | EXEMPT |  | L | CONSTRUCTION | 28000 | FY 2024: 28000
BL-0062 | HIGHWAY | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 8 | Triangle Area RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 1000 | FY 2024: 1000
BL-0062 | HIGHWAY | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 8 | Triangle Area RPO |  | EXEMPT |  | L | ENGINEERING | 12000 | FY 2023: 12000
BL-0062 | HIGHWAY | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 113000 | FY 2024: 113000
BL-0062 | HIGHWAY | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 47000 | FY 2023: 47000
BL-0062 | HIGHWAY | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 4000 | FY 2024: 4000
BL-0063 | HIGHWAY | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 114000 | FY 2023: 114000
BL-0063 | HIGHWAY | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | ENGINEERING | 72000 | FY 2023: 72000
BL-0063 | HIGHWAY | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 287000 | FY 2023: 287000
BL-0063 | HIGHWAY | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 457000 | FY 2023: 457000
BL-0063 | HIGHWAY | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 220000 | FY 2024: 2000; FY 2025: 218000
BL-0063 | HIGHWAY | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | CONSTRUCTION | 55000 | FY 2024: 1000; FY 2025: 54000
BL-0064 | HIGHWAY | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10' MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | L | CONSTRUCTION | 249000 | FY 2024: 249000
BL-0064 | HIGHWAY | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10' MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 107000 | FY 2023: 107000
BL-0064 | HIGHWAY | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10' MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 41000 | FY 2023: 41000
BL-0064 | HIGHWAY | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10' MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 468000 | FY 2024: 468000
BL-0064 | HIGHWAY | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10' MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | L | ENGINEERING | 27000 | FY 2023: 27000
BL-0064 | HIGHWAY | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10' MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 10000 | FY 2023: 10000
BL-0065 | BIKE/PED | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | L | RIGHT-OF-WAY | 56000 | FY 2024: 56000
BL-0065 | BIKE/PED | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | L | ENGINEERING | 61000 | FY 2023: 61000
BL-0065 | BIKE/PED | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGDA | CONSTRUCTION | 1264000 | FY 2025: 1264000
BL-0065 | BIKE/PED | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGDA | ENGINEERING | 245000 | FY 2023: 245000
BL-0065 | BIKE/PED | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | L | CONSTRUCTION | 317000 | FY 2025: 317000
BL-0065 | BIKE/PED | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGDA | RIGHT-OF-WAY | 225000 | FY 2024: 225000
BL-0066 | BIKE/PED | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 4000 | FY 2025: 4000
BL-0066 | BIKE/PED | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | TADA | RIGHT-OF-WAY | 250000 | FY 2024: 250000
BL-0066 | BIKE/PED | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | TADA | CONSTRUCTION | 1785000 | FY 2025: 1785000
BL-0066 | BIKE/PED | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | TADA | ENGINEERING | 350000 | FY 2023: 350000
BL-0066 | BIKE/PED | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 63000 | FY 2024: 63000
BL-0066 | BIKE/PED | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGDA | CONSTRUCTION | 15000 | FY 2025: 15000
BL-0066 | BIKE/PED | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | ENGINEERING | 87000 | FY 2023: 87000
BL-0066 | BIKE/PED | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 446000 | FY 2025: 446000
BL-0067 | BIKE/PED | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGDA | ENGINEERING | 150000 | FY 2023: 150000
BL-0067 | BIKE/PED | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 250000 | FY 2024: 250000
BL-0067 | BIKE/PED | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGDA | CONSTRUCTION | 1200000 | FY 2025: 1200000
BL-0067 | BIKE/PED | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | ENGINEERING | 37000 | FY 2023: 37000
BL-0067 | BIKE/PED | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 63000 | FY 2024: 63000
BL-0067 | BIKE/PED | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 300000 | FY 2025: 300000
BL-0068 | BIKE/PED | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | ENGINEERING | 81000 | FY 2023: 81000
BL-0068 | BIKE/PED | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 100000 | FY 2025: 100000
BL-0068 | BIKE/PED | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 400000 | FY 2025: 400000
BL-0068 | BIKE/PED | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGDA | ENGINEERING | 324000 | FY 2023: 324000
BL-0068 | BIKE/PED | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 170000 | FY 2027: 170000
BL-0068 | BIKE/PED | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGDA | CONSTRUCTION | 680000 | FY 2027: 680000
BL-0069 | BIKE/PED | WILSON | HOMINY CREEK GREENWAY AND TRAIL NETWORK PLAN. | 4 | Upper Coastal Plain RPO | DP FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT. | EXEMPT |  | DP | ENGINEERING | 950000 | FY 2023: 950000
BL-0070 | BIKE/PED | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 8 | Durham-Chapel Hill-Carrboro MPO | "S" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | DIVISION 8 |  | L | CONSTRUCTION | 17000 | FY 2023: 17000
BL-0070 | BIKE/PED | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 8 | Durham-Chapel Hill-Carrboro MPO | "S" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | DIVISION 8 |  | S | CONSTRUCTION | 18000 | FY 2023: 18000
BL-0070 | BIKE/PED | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 8 | Durham-Chapel Hill-Carrboro MPO | "S" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | DIVISION 8 |  | BGDACV | ENGINEERING | 5000 | FY 2023: 5000
BL-0070 | BIKE/PED | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 8 | Durham-Chapel Hill-Carrboro MPO | "S" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | DIVISION 8 |  | BGDA | CONSTRUCTION | 140000 | FY 2023: 140000
BL-0071 | BIKE/PED | HIGH POINT | SUNSET DRIVE FROM HARVELL PARK AND GOLDSTON PARK. CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "S" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | EXEMPT |  | DP | RIGHT-OF-WAY | 2000000 | FY 2023: 2000000
BL-0071 | BIKE/PED | HIGH POINT | SUNSET DRIVE FROM HARVELL PARK AND GOLDSTON PARK. CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "S" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | EXEMPT |  | DP | ENGINEERING | 5000000 | FY 2023: 5000000
BL-0071A | BIKE/PED | SOUTHWEST HERITAGE GREENWAY | CONSTRUCT GREENWAY ON NEW LOCATION CONNECTING HARVELL PARK AND GOLDSTON PARK. | 7 | High Point Urban Area MPO |  | EXEMPT |  | DP | CONSTRUCTION | 6626000 | FY 2024: 6626000
BL-0071A | BIKE/PED | SOUTHWEST HERITAGE GREENWAY | CONSTRUCT GREENWAY ON NEW LOCATION CONNECTING HARVELL PARK AND GOLDSTON PARK. | 7 | High Point Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 1000000 | FY 2024: 1000000
BL-0071A | BIKE/PED | SOUTHWEST HERITAGE GREENWAY | CONSTRUCT GREENWAY ON NEW LOCATION CONNECTING HARVELL PARK AND GOLDSTON PARK. | 7 | High Point Urban Area MPO |  | EXEMPT |  | S | CONSTRUCTION | 200000 | FY 2024: 200000
BL-0071B | BIKE/PED | ELM STREET | CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS FROM SUNSET DRIVE TO COMMERCE AVENUE. | 7 | High Point Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 6188000 | FY 2024: 6188000
BL-0071B | BIKE/PED | ELM STREET | CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS FROM SUNSET DRIVE TO COMMERCE AVENUE. | 7 | High Point Urban Area MPO |  | EXEMPT |  | O | CONSTRUCTION | 1500000 | FY 2024: 1500000
BL-0071B | BIKE/PED | ELM STREET | CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS FROM SUNSET DRIVE TO COMMERCE AVENUE. | 7 | High Point Urban Area MPO |  | EXEMPT |  | DP | CONSTRUCTION | 6176000 | FY 2024: 6176000
BL-0072 | BIKE/PED | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | ENGINEERING | 258000 | FY 2023: 258000
BL-0072 | BIKE/PED | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 92000 | FY 2024: 92000
BL-0072 | BIKE/PED | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 460000 | FY 2025: 460000
BL-0072 | BIKE/PED | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 64000 | FY 2023: 64000
BL-0072 | BIKE/PED | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 23000 | FY 2024: 23000
BL-0072 | BIKE/PED | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 115000 | FY 2025: 115000
BL-0073 | BIKE/PED | SR 1308 (GUM BRANCH ROAD) | CONSTRUCT 1000 FEET OF SIDEWALK FROM INTERSECTION OF NC 53 (WESTERN BOULEVARD) AND GUM BRANCH ROAD TO THE CITY OF JACKSONVILLE LIMITS. CONSTRUCT 1600 FEET OF SIDEWALK FROM ONSVILLE DRIVE TO ONSVILLE DRIVE. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | CRPDA | ENGINEERING | 256000 | FY 2024: 256000
BL-0073 | BIKE/PED | SR 1308 (GUM BRANCH ROAD) | CONSTRUCT 1000 FEET OF SIDEWALK FROM INTERSECTION OF NC 53 (WESTERN BOULEVARD) AND GUM BRANCH ROAD TO THE CITY OF JACKSONVILLE LIMITS. CONSTRUCT 1600 FEET OF SIDEWALK FROM ONSVILLE DRIVE TO ONSVILLE DRIVE. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | L | ENGINEERING | 64000 | FY 2024: 64000
BL-0074 | BIKE/PED | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 110000 | FY 2025: 110000
BL-0074 | BIKE/PED | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | ENGINEERING | 209000 | FY 2023: 209000
BL-0074 | BIKE/PED | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | RIGHT-OF-WAY | 20000 | FY 2024: 20000
BL-0074 | BIKE/PED | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 438000 | FY 2025: 438000
BL-0074 | BIKE/PED | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | ENGINEERING | 53000 | FY 2023: 53000
BL-0074 | BIKE/PED | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | RIGHT-OF-WAY | 4000 | FY 2024: 4000
BL-0075 | BIKE/PED | WRIGHTSVILLE BEACH | INSTALLATION OF ON-STREET BICYCLE LANES AND PEDESTRIAN CROSSWALKS ALONG US 76 (CAUSEWAY DRIVE) AND US 74 (WEST SALISBURY STREET) IN WRIGHTSVILLE BEACH. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 269000 | FY 2024: 269000
BL-0075 | BIKE/PED | WRIGHTSVILLE BEACH | INSTALLATION OF ON-STREET BICYCLE LANES AND PEDESTRIAN CROSSWALKS ALONG US 76 (CAUSEWAY DRIVE) AND US 74 (WEST SALISBURY STREET) IN WRIGHTSVILLE BEACH. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 68000 | FY 2024: 68000
BL-0076 | BIKE/PED | RICEVILLE ROAD | US 70 TO NORTH OF THE VA HOSPITAL DRIVEWAY. IMPROVE SIDEWALKS. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 208000 | FY 2023: 208000
BL-0076 | BIKE/PED | RICEVILLE ROAD | US 70 TO NORTH OF THE VA HOSPITAL DRIVEWAY. IMPROVE SIDEWALKS. | 13 | French Broad River MPO |  | DIVISION 13 |  | TADA | CONSTRUCTION | 830000 | FY 2023: 830000
BL-0077 | BIKE/PED | SWANNANOA GREENWAY | BLEACHERY ROAD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | CONSTRUCTION | 2500000 | FY 2028: 2500000
BL-0077 | BIKE/PED | SWANNANOA GREENWAY | BLEACHERY ROAD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 625000 | FY 2028: 625000
BL-0078 | BIKE/PED | ECUSTA TRAIL | US 64 TO TRANSYLVANIA COUNTY LINE. CONSTRUCT GREENWAY. | 14 | French Broad River MPO |  | DIVISION 14 |  | BGDA | CONSTRUCTION | 10467000 | FY 2027: 10467000
BL-0078 | BIKE/PED | ECUSTA TRAIL | US 64 TO TRANSYLVANIA COUNTY LINE. CONSTRUCT GREENWAY. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | CONSTRUCTION | 2616000 | FY 2027: 2616000
BL-0079 | BIKE/PED | TEXAS ROAD | REPLACE EXISTING HIGHWAY BRIDGE WITH PEDESTRIAN BRIDGE. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | CONSTRUCTION | 153000 | FY 2024: 153000
BL-0079 | BIKE/PED | TEXAS ROAD | REPLACE EXISTING HIGHWAY BRIDGE WITH PEDESTRIAN BRIDGE. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 38000 | FY 2024: 38000
BL-0080 | BIKE/PED | HUNTERSVILLE | INSTALL GREENWAY CULVERT UNDER US 21. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 650000 | FY 2025: 650000
BL-0080 | BIKE/PED | HUNTERSVILLE | INSTALL GREENWAY CULVERT UNDER US 21. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 2600000 | FY 2025: 2600000
BL-0081 | BIKE/PED | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. INSTALL SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. INSTALL SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 347000 | FY 2024: 347000
BL-0081 | BIKE/PED | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. INSTALL SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. INSTALL SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 106000 | FY 2026: 106000
BL-0081 | BIKE/PED | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. INSTALL SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. INSTALL SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 865000 | FY 2027: 865000
BL-0081 | BIKE/PED | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. INSTALL SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. INSTALL SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 216000 | FY 2027: 216000
BL-0081 | BIKE/PED | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. INSTALL SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. INSTALL SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 27000 | FY 2026: 27000
BL-0081 | BIKE/PED | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. INSTALL SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. INSTALL SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 87000 | FY 2024: 87000
BL-0082 | BIKE/PED | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. INSTALL SHARED USE PATH. | 12 | Charlotte Regional TPO |  | REGION F |  | TADA | CONSTRUCTION | 1914000 | FY 2029: 1914000
BL-0082 | BIKE/PED | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. INSTALL SHARED USE PATH. | 12 | Charlotte Regional TPO |  | REGION F |  | L | RIGHT-OF-WAY | 350000 | FY 2027: 350000
BL-0082 | BIKE/PED | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. INSTALL SHARED USE PATH. | 12 | Charlotte Regional TPO |  | REGION F |  | L | CONSTRUCTION | 1915000 | FY 2029: 1915000
BL-0082 | BIKE/PED | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. INSTALL SHARED USE PATH. | 12 | Charlotte Regional TPO |  | REGION F |  | TADA | ENGINEERING | 172000 | FY 2025: 172000
BL-0082 | BIKE/PED | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. INSTALL SHARED USE PATH. | 12 | Charlotte Regional TPO |  | REGION F |  | TADA | RIGHT-OF-WAY | 350000 | FY 2027: 350000
BL-0082 | BIKE/PED | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. INSTALL SHARED USE PATH. | 12 | Charlotte Regional TPO |  | REGION F |  | L | ENGINEERING | 172000 | FY 2025: 172000
BL-0083 | BIKE/PED | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. INSTALL SIDEWALK. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 2048000 | FY 2026: 2048000
BL-0083 | BIKE/PED | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. INSTALL SIDEWALK. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 377000 | FY 2025: 377000
BL-0083 | BIKE/PED | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. INSTALL SIDEWALK. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 309000 | FY 2025: 309000
BL-0083 | BIKE/PED | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. INSTALL SIDEWALK. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1676000 | FY 2026: 1676000
BL-0084 | BIKE/PED | ALBEMARLE ROAD AND WILORA LAKE ROAD | REDMAN ROAD TO CENTRAL AVENUE. INSTALL SIDEWALK. ALBEMARKLE ROAD TO 100 FEET NORTH OF BARR DRIVE. INSTALL SIDEWALK. INSTALL PEDESTRIAN IMPROVEMENTS AT VARIOUS INTERSECTIONS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1436000 | FY 2026: 1436000
BL-0084 | BIKE/PED | ALBEMARLE ROAD AND WILORA LAKE ROAD | REDMAN ROAD TO CENTRAL AVENUE. INSTALL SIDEWALK. ALBEMARKLE ROAD TO 100 FEET NORTH OF BARR DRIVE. INSTALL SIDEWALK. INSTALL PEDESTRIAN IMPROVEMENTS AT VARIOUS INTERSECTIONS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 1756000 | FY 2026: 1756000
BL-0085 | BIKE/PED | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 240000 | FY 2027: 240000
BL-0085 | BIKE/PED | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 361000 | FY 2027: 361000
BL-0085 | BIKE/PED | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 1537000 | FY 2029: 1537000
BL-0085 | BIKE/PED | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 132000 | FY 2025: 132000
BL-0085 | BIKE/PED | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 198000 | FY 2025: 198000
BL-0085 | BIKE/PED | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1024000 | FY 2029: 1024000
BL-0086 | BIKE/PED | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | TADA | ENGINEERING | 230000 | FY 2024: 230000
BL-0086 | BIKE/PED | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 1250000 | FY 2025: 1250000
BL-0086 | BIKE/PED | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 138000 | FY 2024: 138000
BL-0086 | BIKE/PED | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | CONSTRUCTION | 313000 | FY 2025: 313000
BL-0086 | BIKE/PED | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | UTILITIES | 11000 | FY 2024: 11000
BL-0086 | BIKE/PED | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 34000 | FY 2024: 34000
BL-0086 | BIKE/PED | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | ENGINEERING | 57000 | FY 2024: 57000
BL-0086 | BIKE/PED | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | TADA | UTILITIES | 45000 | FY 2024: 45000
BL-0087 | BIKE/PED | VARIOUS CONCORD | ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. GLENN STREET NORTHWEST FROM ELM AVENUE NORTHWEST TO ACADEMY AVENUE NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | CONSTRUCTION | 325000 | FY 2024: 325000
BL-0087 | BIKE/PED | VARIOUS CONCORD | ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. GLENN STREET NORTHWEST FROM ELM AVENUE NORTHWEST TO ACADEMY AVENUE NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. INSTALL SIDEWALKS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 1300000 | FY 2024: 1300000
BL-0088 | BIKE/PED | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | L | UTILITIES | 2000 | FY 2024: 2000
BL-0088 | BIKE/PED | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | TADA | CONSTRUCTION | 304000 | FY 2025: 304000
BL-0088 | BIKE/PED | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | TADA | UTILITIES | 8000 | FY 2024: 8000
BL-0088 | BIKE/PED | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | TADA | RIGHT-OF-WAY | 72000 | FY 2024: 72000
BL-0088 | BIKE/PED | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | L | CONSTRUCTION | 76000 | FY 2025: 76000
BL-0088 | BIKE/PED | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | L | RIGHT-OF-WAY | 18000 | FY 2024: 18000
BL-0088 | BIKE/PED | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | L | ENGINEERING | 14000 | FY 2024: 14000
BL-0088 | BIKE/PED | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. INSTALL SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | TADA | ENGINEERING | 56000 | FY 2024: 56000
BL-0089 | BIKE/PED | US 401 (SOUTH SAUNDERS STREET) | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 657000 | FY 2024: 657000
BL-0089 | BIKE/PED | US 401 (SOUTH SAUNDERS STREET) | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 438000 | FY 2024: 438000
BL-0090 | BIKE/PED | EAST MCLVER STREET, SOUTH WILMA STREET | EAST MCLVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | RIGHT-OF-WAY | 40000 | FY 2024: 40000
BL-0090 | BIKE/PED | EAST MCLVER STREET, SOUTH WILMA STREET | EAST MCLVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | CONSTRUCTION | 180000 | FY 2024: 180000
BL-0090 | BIKE/PED | EAST MCLVER STREET, SOUTH WILMA STREET | EAST MCLVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | RIGHT-OF-WAY | 10000 | FY 2024: 10000
BL-0090 | BIKE/PED | EAST MCLVER STREET, SOUTH WILMA STREET | EAST MCLVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | CONSTRUCTION | 718000 | FY 2024: 718000
BL-0090 | BIKE/PED | EAST MCLVER STREET, SOUTH WILMA STREET | EAST MCLVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | ENGINEERING | 120000 | FY 2024: 120000
BL-0090 | BIKE/PED | EAST MCLVER STREET, SOUTH WILMA STREET | EAST MCLVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | ENGINEERING | 30000 | FY 2024: 30000
BL-0091 | BIKE/PED | HIGGINS GREENWAY | SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1936000 | FY 2024: 1936000
BL-0091 | BIKE/PED | HIGGINS GREENWAY | SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 515000 | FY 2024: 515000
BL-0092 | BIKE/PED | ALSTON RIDGE GREENWAY | ALSTON RIDGE GREENWAY TO BASS LAKE GREENWAY IN FUQUAY-VARINA. COMPLETE A GAP OF GREENWAY TRAIL. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 619000 | FY 2024: 619000
BL-0092 | BIKE/PED | ALSTON RIDGE GREENWAY | ALSTON RIDGE GREENWAY TO BASS LAKE GREENWAY IN FUQUAY-VARINA. COMPLETE A GAP OF GREENWAY TRAIL. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 929000 | FY 2024: 929000
BL-0093 | BIKE/PED | UTLEY CREEK GREENWAY WEST | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 830000 | FY 2024: 830000
BL-0093 | BIKE/PED | UTLEY CREEK GREENWAY WEST | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1920000 | FY 2024: 1920000
BL-0094 | BIKE/PED | NC 210 | CONSTRUCT A MULTI-USE PATH FROM HARNETT CENTRAL ROAD TO NORTH HARNETT PRIMARY SCHOOL ROAD. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | CONSTRUCTION | 146000 | FY 2024: 146000
BL-0094 | BIKE/PED | NC 210 | CONSTRUCT A MULTI-USE PATH FROM HARNETT CENTRAL ROAD TO NORTH HARNETT PRIMARY SCHOOL ROAD. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | ENGINEERING | 29000 | FY 2024: 29000
BL-0094 | BIKE/PED | NC 210 | CONSTRUCT A MULTI-USE PATH FROM HARNETT CENTRAL ROAD TO NORTH HARNETT PRIMARY SCHOOL ROAD. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | RIGHT-OF-WAY | 7000 | FY 2024: 7000
BL-0094 | BIKE/PED | NC 210 | CONSTRUCT A MULTI-USE PATH FROM HARNETT CENTRAL ROAD TO NORTH HARNETT PRIMARY SCHOOL ROAD. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | CONSTRUCTION | 404000 | FY 2024: 404000
BL-0094 | BIKE/PED | NC 210 | CONSTRUCT A MULTI-USE PATH FROM HARNETT CENTRAL ROAD TO NORTH HARNETT PRIMARY SCHOOL ROAD. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | ENGINEERING | 11000 | FY 2024: 11000
BL-0094 | BIKE/PED | NC 210 | CONSTRUCT A MULTI-USE PATH FROM HARNETT CENTRAL ROAD TO NORTH HARNETT PRIMARY SCHOOL ROAD. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | RIGHT-OF-WAY | 3000 | FY 2024: 3000
BL-0095 | BIKE/PED | SAUNDERS STREET | SAUNDERS STREET AT WEST CHATHAM STREET TO HINTON STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 1075000 | FY 2024: 1075000
BL-0095 | BIKE/PED | SAUNDERS STREET | SAUNDERS STREET AT WEST CHATHAM STREET TO HINTON STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 269000 | FY 2024: 269000
BL-0096 | BIKE/PED | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 1537000 | FY 2028: 1537000
BL-0096 | BIKE/PED | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 132000 | FY 2024: 132000
BL-0096 | BIKE/PED | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 240000 | FY 2026: 240000
BL-0096 | BIKE/PED | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1024000 | FY 2028: 1024000
BL-0096 | BIKE/PED | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 198000 | FY 2024: 198000
BL-0096 | BIKE/PED | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). INSTALL SHARED USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 361000 | FY 2026: 361000
BO-2401 | BIKE/PED | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | DIVISION 1 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2401 | BIKE/PED | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | DIVISION 1 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2402 | BIKE/PED | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | DIVISION 2 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2402 | BIKE/PED | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | DIVISION 2 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2403 | BIKE/PED | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | DIVISION 3 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2403 | BIKE/PED | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | DIVISION 3 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2404 | BIKE/PED | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2404 | BIKE/PED | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | DIVISION 4 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2405 | BIKE/PED | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2405 | BIKE/PED | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2406 | BIKE/PED | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | DIVISION 6 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2406 | BIKE/PED | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | DIVISION 6 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2407 | BIKE/PED | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO |  | DIVISION 7 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2407 | BIKE/PED | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO |  | DIVISION 7 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2408 | BIKE/PED | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 8 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2408 | BIKE/PED | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 8 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2409 | BIKE/PED | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | DIVISION 9 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2409 | BIKE/PED | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | DIVISION 9 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2410 | BIKE/PED | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO |  | DIVISION 10 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2410 | BIKE/PED | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO |  | DIVISION 10 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2411 | BIKE/PED | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO |  | DIVISION 11 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2411 | BIKE/PED | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO |  | DIVISION 11 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2412 | BIKE/PED | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO |  | DIVISION 12 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2412 | BIKE/PED | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO |  | DIVISION 12 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2413 | BIKE/PED | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO |  | DIVISION 13 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2413 | BIKE/PED | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO |  | DIVISION 13 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2414 | BIKE/PED | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO |  | DIVISION 14 |  | S | CONSTRUCTION | 1000000 | FY 2024: 200000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
BO-2414 | BIKE/PED | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO |  | DIVISION 14 |  | TA | CONSTRUCTION | 4000000 | FY 2024: 800000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
BO-2415 | BIKE/PED | MORGAN CREEK GREENWAY | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | BGDA | CONSTRUCTION | 647000 | FY 2024: 647000
BO-2415 | BIKE/PED | MORGAN CREEK GREENWAY | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 550000 | FY 2023: 550000
BO-2415 | BIKE/PED | MORGAN CREEK GREENWAY | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 550000 | FY 2024: 550000
BO-2415 | BIKE/PED | MORGAN CREEK GREENWAY | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | TADA | RIGHT-OF-WAY | 623000 | FY 2023: 623000
BP-5500 | HIGHWAY | VARIOUS | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | 99 | STATEWIDE PROJECT | [5 empty] | 32648000
BR-0012 | HIGHWAY | US 74 | REPLACE BRIDGES 220048 AND 220049 OVER SANDY RUN. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045 | HIGHWAY FUND |  | HFB | RIGHT-OF-WAY | 42000
BR-0012 | HIGHWAY | US 74 | REPLACE BRIDGES 220048 AND 220049 OVER SANDY RUN. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 10300000 | FY 2024: 103000; FY 2025: 5710000; FY 2026: 3358000; FY 2027: 1129000
BR-0025 | HIGHWAY | SR 1639 (MEACHAM RD) | REPLACE BRIDGE 480118 OVER I-40. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BFP | CONSTRUCTION | 5500000 | FY 2029: 2750000; FY 2030: 2750000
BR-0035 | HIGHWAY | NC 22 | REPLACE BRIDGE 620062 OVER NICKS CREEK IN CARTHAGE. | 8 | Triangle Area RPO | PROJECT WILL BE COMPLETED UNDER THE STATE BRIDGE PROGRAM. PROJECT TO NO LONGER UTILIZE BUILD NC BONDS. UNDER CONSTRUCTION | REGION E |  | NHPB | CONSTRUCTION | 4100000 | FY 2023: 1009000
BR-0036 | HIGHWAY | NC 33 | REPLACE BRIDGE 630041 OVER I-95. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 4700000
BR-0039 | HIGHWAY | SR 1510 | REPLACE BRIDGE 630224 OVER I-95. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 5200000
BR-0107 | HIGHWAY | SR 1577 | REPLACE BRIDGE 480131 OVER UT TO SNOW CREEK. | 12 | Charlotte Regional TPO | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 800000
BR-0108 | HIGHWAY | SR 2418 | REPLACE BRIDGE 960004 OVER LITTLE HUNTING CREEK. | 11 | High Country RPO | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1200000
BR-0109 | HIGHWAY | SR 1512 | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | HIGHWAY FUND |  | HFB | RIGHT-OF-WAY | 3000
BR-0109 | HIGHWAY | SR 1512 | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | HIGHWAY FUND |  | HFB | UTILITIES | 5000
BR-0109 | HIGHWAY | SR 1512 | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | HIGHWAY FUND |  | HFB | CONSTRUCTION | 788000 | FY 2023: 788000
BR-0111 | HIGHWAY | SR 1404 (SEVEN BRIDGES ROAD) | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  | DP | UTILITIES | 56000
BR-0111 | HIGHWAY | SR 1404 (SEVEN BRIDGES ROAD) | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  | DP | CONSTRUCTION | 5450000
BR-0111 | HIGHWAY | SR 1404 (SEVEN BRIDGES ROAD) | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  | DP | RIGHT-OF-WAY | 420000
BR-0111 | HIGHWAY | SR 1404 (SEVEN BRIDGES ROAD) | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  |  |  | 100000
BR-0112 | HIGHWAY | SR 1616 (SHARP POINT ROAD) | REPLACE BRIDGE 320035 OVER OTTER CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  | DP | CONSTRUCTION | 1112000
BR-0112 | HIGHWAY | SR 1616 (SHARP POINT ROAD) | REPLACE BRIDGE 320035 OVER OTTER CREEK. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  |  |  | 230000
BR-0113 | HIGHWAY | SR 1601 (SLEDGE ROAD) | REPLACE BRIDGE 410115 OVER ROCKY SWAMP. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  |  |  | 100000
BR-0113 | HIGHWAY | SR 1601 (SLEDGE ROAD) | REPLACE BRIDGE 410115 OVER ROCKY SWAMP. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  | DP | CONSTRUCTION | 796000
BR-0113 | HIGHWAY | SR 1601 (SLEDGE ROAD) | REPLACE BRIDGE 410115 OVER ROCKY SWAMP. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 4 |  | HFB | RIGHT-OF-WAY | 130000
BR-0114 | HIGHWAY | SR 1601 (BRANTON ROAD) | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | DIVISION 12 |  | HFB | CONSTRUCTION | 850000
BR-0114 | HIGHWAY | SR 1601 (BRANTON ROAD) | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | DIVISION 12 |  | HFB | RIGHT-OF-WAY | 150000
BR-0114 | HIGHWAY | SR 1601 (BRANTON ROAD) | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | DIVISION 12 |  | DP | CONSTRUCTION | 300000
BR-0114 | HIGHWAY | SR 1601 (BRANTON ROAD) | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | DIVISION 12 |  |  |  | 250000
BR-0115 | HIGHWAY | SR 1595 (COOLBROOK ROAD) | REPLACE BRIDGE 480166 ON SR 1595 OVER ROCKY CREEK. | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | DIVISION 12 |  | DP | CONSTRUCTION | 1600000
BR-0115 | HIGHWAY | SR 1595 (COOLBROOK ROAD) | REPLACE BRIDGE 480166 ON SR 1595 OVER ROCKY CREEK. | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | DIVISION 12 |  | HFB | RIGHT-OF-WAY | 170000
BR-0115 | HIGHWAY | SR 1595 (COOLBROOK ROAD) | REPLACE BRIDGE 480166 ON SR 1595 OVER ROCKY CREEK. | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | DIVISION 12 |  |  |  | 270000
BR-0116 | HIGHWAY | SR 1403 (COOPER ROAD) | REPLACE BRIDGE 630080 OVER GIDEON SWAMP. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  |  |  | 100000
BR-0116 | HIGHWAY | SR 1403 (COOPER ROAD) | REPLACE BRIDGE 630080 OVER GIDEON SWAMP. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1000000
BR-0121 | HIGHWAY | SR 1804 (HOUSES MILL ROAD) | REPLACE BRIDGE 810178 OVER SEVENMILE SWAMP. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 3 |  |  |  | 250000
BR-0121 | HIGHWAY | SR 1804 (HOUSES MILL ROAD) | REPLACE BRIDGE 810178 OVER SEVENMILE SWAMP. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 3 |  | DP | CONSTRUCTION | 1400000
BR-0122 | HIGHWAY | SR 1703 (OLD GOLDSBORO ROAD) | REPLACE BRIDGE 810348 OVER BEAVERDAM CREEK. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 3 |  | DP | CONSTRUCTION | 727000
BR-0122 | HIGHWAY | SR 1703 (OLD GOLDSBORO ROAD) | REPLACE BRIDGE 810348 OVER BEAVERDAM CREEK. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | DIVISION 3 |  |  |  | 150000
BR-0124 | HIGHWAY | SR 1745 (SHUMATE MOUNTAIN ROAD) | REPLACE BRIDGE 960166 ON SR 1745 OVER WEST PRONG ROARING RIVER. | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  |  |  | 100000
BR-0124 | HIGHWAY | SR 1745 (SHUMATE MOUNTAIN ROAD) | REPLACE BRIDGE 960166 ON SR 1745 OVER WEST PRONG ROARING RIVER. | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | DP | CONSTRUCTION | 2900000
BR-0124 | HIGHWAY | SR 1745 (SHUMATE MOUNTAIN ROAD) | REPLACE BRIDGE 960166 ON SR 1745 OVER WEST PRONG ROARING RIVER. | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | HFB | RIGHT-OF-WAY | 40000
BR-0125 | HIGHWAY | SR 1002 (TRAPHILL ROAD) | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | HFB | RIGHT-OF-WAY | 280000
BR-0125 | HIGHWAY | SR 1002 (TRAPHILL ROAD) | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | DP | CONSTRUCTION | 2350000
BR-0125 | HIGHWAY | SR 1002 (TRAPHILL ROAD) | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  |  |  | 380000
BR-0125 | HIGHWAY | SR 1002 (TRAPHILL ROAD) | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | HFB | CONSTRUCTION | 300000
BR-0126 | HIGHWAY | SR 1749 (AUSTIN TRAPHILL ROAD) | REPLACE BRIDGE 960667 ON SR 1749 OVER SPARKS CREEK. | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  |  |  | 100000
BR-0126 | HIGHWAY | SR 1749 (AUSTIN TRAPHILL ROAD) | REPLACE BRIDGE 960667 ON SR 1749 OVER SPARKS CREEK. | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | DP | CONSTRUCTION | 1550000
BR-0126 | HIGHWAY | SR 1749 (AUSTIN TRAPHILL ROAD) | REPLACE BRIDGE 960667 ON SR 1749 OVER SPARKS CREEK. | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | HFB | RIGHT-OF-WAY | 80000
BR-0127 | HIGHWAY | SR 1325 (MOUNTAIN VIEW CHURCH ROAD) | REPLACE BRIDGE 980189 ON SR 1325 OVER SOUTH DEEP CREEK. | 11 | Northwest Piedmont RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | DP | CONSTRUCTION | 850000
BR-0127 | HIGHWAY | SR 1325 (MOUNTAIN VIEW CHURCH ROAD) | REPLACE BRIDGE 980189 ON SR 1325 OVER SOUTH DEEP CREEK. | 11 | Northwest Piedmont RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | HFB | RIGHT-OF-WAY | 45000
BR-0130 | HIGHWAY | I-40 | REPLACE BRIDGES 110114 AND 110120 OVER SILVER CREEK. | 13 | Greater Hickory MPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 11800000 | FY 2030: 5900000; FY 2031: 5900000
BR-0200 | HIGHWAY | SR 1152 | REPLACE BRIDGE 980020 OVER SOUTH DEEP CREEK. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENT HFB PROJECT NUMBER 17BP.11.R.183. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 850000
BR-0201 | HIGHWAY | SR 1348 | REPLACE BRIDGE 10291 OVER DUCK CREEK. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.88 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1050000
BR-0202 | HIGHWAY | SR 1892 | REPLACE BRIDGE 480212 OVER PATTERSON CREEK. | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.49 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1250000
BR-0203 | HIGHWAY | SR 1896 | REPLACE BRIDGE 480214 OVER PATTERSON CREEK | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.50 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1000000
BR-0204 | HIGHWAY | SR 1892 | REPLACE BRIDGE 480219 OVER OLIN CREEK. | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.51 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 900000
BR-0205 | HIGHWAY | SR 1119 | REPLACE BRIDGE 980028 OVER NORTH LITTLE HUNTING CREEK. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.130 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 2000000
BR-0206 | HIGHWAY | SR 1422 | REPLACE BRIDGE 20035 OVER GLADE CREEK. | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.157 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 750000
BR-0207 | HIGHWAY | SR 1433 | REPLACE BRIDGE 20133 OVER LITTLE RIVER. | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.159 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 500000
BR-0208 | HIGHWAY | SR 2516 | REPLACE BRIDGE 960733 OVER CUB CREEK. | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.154 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 600000
BR-0209 | HIGHWAY | SR 1148 | REPLACE BRIDGE 960419 OVER NAKED CREEK. | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.153 | HIGHWAY FUND |  | HFB | CONSTRUCTION | 650000
BR-0210 | HIGHWAY | SR 2081 | REPLACE BRIDGE 850153 OVER HOGAN CREEK. | 11 | Northwest Piedmont RPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  | DP | CONSTRUCTION | 875000
BR-0210 | HIGHWAY | SR 2081 | REPLACE BRIDGE 850153 OVER HOGAN CREEK. | 11 | Northwest Piedmont RPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING | HIGHWAY FUND |  |  |  | 50000
BR-0241 | HIGHWAY | SR 1243 (LEGGETT ROAD) | REPLACE BRIDGE 320054 OVER TAR RIVER. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 4.R.101 PROJECT. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 3600000
BR-0243 | HIGHWAY | SR 1162 (BAY ROAD) | REPLACE BRIDGE 300045 OVER ISLAND CREEK. | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.83 PROJECT. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1700000
C-3600 | HIGHWAY | VARIOUS | DEPARTMENT OF MOTOR VEHICLES (DMV), VEHICLE EMISSION COMPLIANCE SYSTEM. UPGRADE NORTH CAROLINA'S MOTOR VEHICLE EMISSIONS INSPECTION AND MAINTENANCE (I/M) PROGRAM. | 99 | STATEWIDE PROJECT | IN PROGRESS BY DEPARTMENT OF MOTOR VEHICLES | EXEMPT |  |  |  | 6702000
C-4902 | HIGHWAY | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY SOLAR CENTER CLEAN TRANSPORTATION PROGRAM. DEVELOP AND ADMINISTER A SEVEN YEAR CLEAN FUEL-ADVANCED TECHNOLOGY REBATE PROGRAM IN ALL CMAQ ELIGIBLE COUNTIES TO REDUCE EMISSIONS. | 99 | STATEWIDE PROJECT | IN PROGRESS BY NORTH CAROLINA STATE UNIVERSITY | EXEMPT |  |  |  | 4694000
C-4908 | HIGHWAY | VARIOUS | CONSTRUCT SIDEWALKS AT SELECTED LOCATIONS IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  |  |  | 1376000
C-4924 | HIGHWAY | TRIANGLE J COUNCIL OF GOVERNMENTS | TRIANGLE J COUNCIL OF GOVERNMENTS (COG). TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN TRIANGLE OZONE NON-ATTAINMENT AREA. | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  |  |  | 8400000
C-4924B | HIGHWAY | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | CMAQ | IMPLEMENTATION | 571000
C-4924B | HIGHWAY | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | L | IMPLEMENTATION | 143000
C-4928 | HIGHWAY | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | DIVISION 5 |  | CMAQ | CONSTRUCTION | 2331000 | FY 2023: 2331000
C-4928 | HIGHWAY | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 612000
C-4928 | HIGHWAY | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | DIVISION 5 |  | BGDA | CONSTRUCTION | 120000 | FY 2023: 120000
C-4928 | HIGHWAY | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | DIVISION 5 |  | L | CONSTRUCTION | 4920000 | FY 2023: 4920000
C-4928 | HIGHWAY | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | DIVISION 5 |  | BGANY | RIGHT-OF-WAY | 2146000
C-4928 | HIGHWAY | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | DIVISION 5 |  |  |  | 994000
C-4928 | HIGHWAY | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 302000
C-4934 | HIGHWAY | NC 279 (NEW HOPE ROAD) | NC 279 (NEW HOPE ROAD), BURTONWOOD DRIVE TO SR 2466 (GARRISON BOULEVARD) IN GASTONIA. ADD TURN LANE. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | EXEMPT |  |  |  | 3917000
C-4936 | HIGHWAY | VARIOUS | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PART). IMPLEMENT A REGIONAL AIR QUALITY AWARENESS PROGRAM. | 7, 8, 9 | Greensboro Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Urban Area MPO | IN PROGRESS BY PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | EXEMPT |  |  |  | 714000
C-5160 | HIGHWAY | NEWSOME ROAD | CITY OF SALISBURY - CONSTRUCT BIKE LANES. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION BY CITY OF SALISBURY | EXEMPT |  |  |  | 2119000
C-5161 | HIGHWAY | KANNAPOLIS | IRISH BUFFALO CREEK GREENWAY IN KANNAPOLIS. CONSTRUCT GREENWAY. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | EXEMPT |  |  |  | 2167000
C-5166 | BIKE/PED | NC 56 | GREENWAY IN CREEDMOOR. CONSTRUCT BIKE-PEDESTRIAN TRAIL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CREEDMOOR; LET WITH EB-5513 | EXEMPT |  |  |  | 4991000
C-5168 | HIGHWAY | CRABTREE CREEK GREENWAY | CONSTRUCT GREENWAY CONNECTING EXISTING GREENWAY IN CARY THROUGH MORRISVILLE, INCLUDING REPLACEMENT OF TRAIN TRESTLE. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE | EXEMPT |  |  |  | 4247000
C-5179 | HIGHWAY | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | EXEMPT |  | BGDA | CONSTRUCTION | 631000
C-5179 | HIGHWAY | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | EXEMPT |  | BGDACV | CONSTRUCTION | 429000
C-5179 | HIGHWAY | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | EXEMPT |  | CMAQ | CONSTRUCTION | 3072000
C-5179 | HIGHWAY | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | EXEMPT |  | L | CONSTRUCTION | 926000
C-5179 | HIGHWAY | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | EXEMPT |  |  |  | 1149000
C-5181 | HIGHWAY | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | BGDA | CONSTRUCTION | 205000 | FY 2023: 205000
C-5181 | HIGHWAY | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | CONSTRUCTION | 131000 | FY 2023: 131000
C-5181 | HIGHWAY | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | CONSTRUCTION | 51000 | FY 2023: 51000
C-5181 | HIGHWAY | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | IMPLEMENTATION | 2000
C-5181 | HIGHWAY | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  |  |  | 100000
C-5181 | HIGHWAY | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 523000 | FY 2023: 523000
C-5181 | HIGHWAY | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 10000
C-5183 | HIGHWAY | VARIOUS | CONSTRUCT SIDEWALKS IN DURHAM. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  |  |  | 109000
C-5183B | HIGHWAY | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS ST. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | EXEMPT |  | BGDA | CONSTRUCTION | 433000 | FY 2023: 433000
C-5183B | HIGHWAY | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS ST. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | EXEMPT |  | CMAQ | CONSTRUCTION | 644000 | FY 2023: 644000
C-5183B | HIGHWAY | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS ST. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | EXEMPT |  | L | CONSTRUCTION | 269000 | FY 2023: 269000
C-5184 | HIGHWAY | RIVERWALK TRAIL | RIVERWALK TRAIL, PHASE III IN HILLSBOROUGH. CONSTRUCT A PAVED OFF-ROAD TAIL ALONG ENO RIVER CONNECTING RIVER PARK, GOLD PARK AND THE OCCONEECHEE MOUNTAIN STATE NATURAL AREA, AND CONSTRUCT SIDEWALK TO PROVIDE PEDESTRIAN AND BICYCLE CONNECTIONS TO THE GREE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF HILLSBOROUGH | EXEMPT |  |  |  | 610000
C-5195 | HIGHWAY | CLAREMONT | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN CLAREMONT. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION | EXEMPT |  |  |  | 395000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | L | ENGINEERING | 100000 | FY 2023: 100000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | L | CONSTRUCTION | 500000 | FY 2025: 500000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | L | RIGHT-OF-WAY | 492000 | FY 2023: 492000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | CMAQ | CONSTRUCTION | 2000000 | FY 2025: 2000000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | BGANY | CONSTRUCTION | 1990000 | FY 2025: 1990000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | BGANY | ENGINEERING | 400000 | FY 2023: 400000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  |  |  | 8000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | L | CONSTRUCTION | 498000 | FY 2025: 498000
C-5196 | HIGHWAY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | CMAQ | RIGHT-OF-WAY | 2364000 | FY 2023: 2364000
C-5200 | HIGHWAY | MOORESVILLE | NC 115 AND NC 150 IN MOORESVILLE. CONSTRUCT SOUTHBOUND NC 115 RIGHT TURN LANE AT NC 150 AND WESTBOUND NC 150 SHARED THROUGH-RIGHT LANE AT NC 115. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | EXEMPT |  |  |  | 1283000
C-5200 | HIGHWAY | MOORESVILLE | NC 115 AND NC 150 IN MOORESVILLE. CONSTRUCT SOUTHBOUND NC 115 RIGHT TURN LANE AT NC 150 AND WESTBOUND NC 150 SHARED THROUGH-RIGHT LANE AT NC 115. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | EXEMPT |  | BGDA | CONSTRUCTION | 1211000
C-5200 | HIGHWAY | MOORESVILLE | NC 115 AND NC 150 IN MOORESVILLE. CONSTRUCT SOUTHBOUND NC 115 RIGHT TURN LANE AT NC 150 AND WESTBOUND NC 150 SHARED THROUGH-RIGHT LANE AT NC 115. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | EXEMPT |  | L | CONSTRUCTION | 303000
C-5225 | HIGHWAY | CHARLOTTE | TOBY CREEK GREENWAY (PHASE II). CONNECT UNCC TO NEARBY RETAIL AND RESIDENTIAL DEVELOPMENT. | 10 | Charlotte Regional TPO | [5 empty] | 3093000
C-5505 | HIGHWAY | BELMONT | RAIL TRAIL, WOODLAWN AVENUE TO BELMONT ABBEY COLLEGE AND DOWNTOWN. CONVERT ABANDONED NCDOT RAILROAD LINE TO A PEDESTRIAN TRAIL. | 12 | Gaston-Cleveland-Lincoln MPO | IN PROGRESS | EXEMPT |  |  |  | 1900000
C-5529 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | EXEMPT |  | BGDA | ENGINEERING | 207000 | FY 2023: 207000
C-5529 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | EXEMPT |  | BGDA | CONSTRUCTION | 846000 | FY 2023: 846000
C-5529 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | EXEMPT |  | L | ENGINEERING | 52000 | FY 2023: 52000
C-5529 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | EXEMPT |  | L | CONSTRUCTION | 282000 | FY 2023: 282000
C-5529 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | EXEMPT |  |  |  | 1677000
C-5531 | HIGHWAY | MOORESVILLE | KISTLER FARM-BRIARCLIFF-BELLINGHAM-WHITE OAK SIDEWALK NETWORK IN MOORESVILLE. CONSTRUCT SIDEWALKS IN VARIOUS LOCATIONS. | 12 | Charlotte Regional TPO | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | EXEMPT |  | L | CONSTRUCTION | 160000
C-5531 | HIGHWAY | MOORESVILLE | KISTLER FARM-BRIARCLIFF-BELLINGHAM-WHITE OAK SIDEWALK NETWORK IN MOORESVILLE. CONSTRUCT SIDEWALKS IN VARIOUS LOCATIONS. | 12 | Charlotte Regional TPO | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | EXEMPT |  |  |  | 3552000
C-5531 | HIGHWAY | MOORESVILLE | KISTLER FARM-BRIARCLIFF-BELLINGHAM-WHITE OAK SIDEWALK NETWORK IN MOORESVILLE. CONSTRUCT SIDEWALKS IN VARIOUS LOCATIONS. | 12 | Charlotte Regional TPO | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | EXEMPT |  | BGDA | CONSTRUCTION | 641000
C-5534 | HIGHWAY | CHARLOTTE | SR 4979 (BALLANTYNE COMMONS PARKWAY-MCKEE ROAD) AND NC 16 (PROVIDENCE ROAD) IN CHARLOTTE. CONSTRUCT AN ADDITIONAL LEFT TURN LANE ON SR 4979 AND A SECOND LEFT TURN LANE ON SOUTHBOUND NC 16. | 10 | Charlotte Regional TPO | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES. | EXEMPT |  | BGDA | CONSTRUCTION | 640000
C-5534 | HIGHWAY | CHARLOTTE | SR 4979 (BALLANTYNE COMMONS PARKWAY-MCKEE ROAD) AND NC 16 (PROVIDENCE ROAD) IN CHARLOTTE. CONSTRUCT AN ADDITIONAL LEFT TURN LANE ON SR 4979 AND A SECOND LEFT TURN LANE ON SOUTHBOUND NC 16. | 10 | Charlotte Regional TPO | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES. | EXEMPT |  |  |  | 1113000
C-5536 | HIGHWAY | CHARLOTTE | MECKLENBURG COUNTY AIR QUALITY -GRADE (GRANTS TO REPLACE AGING DIESEL ENGINES). REPLACE, REPOWER OR RETROFIT AGING DIESEL VEHICLES AND EQUIPMENT. | 10 | Charlotte Regional TPO | COMPLETE. | EXEMPT |  |  |  | 979000
C-5536 | HIGHWAY | CHARLOTTE | MECKLENBURG COUNTY AIR QUALITY -GRADE (GRANTS TO REPLACE AGING DIESEL ENGINES). REPLACE, REPOWER OR RETROFIT AGING DIESEL VEHICLES AND EQUIPMENT. | 10 | Charlotte Regional TPO | COMPLETE. | EXEMPT |  | CMAQ | CONSTRUCTION | 139000
C-5538 | HIGHWAY | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  |  |  | 530000
C-5538 | HIGHWAY | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1797000
C-5538 | HIGHWAY | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1053000
C-5538 | HIGHWAY | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 563000
C-5538 | HIGHWAY | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 263000
C-5546 | HIGHWAY | ROCKY MOUNT | BENVENUE ROAD (NC 43/NC 48) AT JEFFREYS ROAD. INTERSECTION IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | EXEMPT |  |  |  | 16000
C-5546 | HIGHWAY | ROCKY MOUNT | BENVENUE ROAD (NC 43/NC 48) AT JEFFREYS ROAD. INTERSECTION IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 130000 | FY 2023: 130000
C-5549 | HIGHWAY | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 688000 | FY 2023: 688000
C-5549 | HIGHWAY | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | EXEMPT |  |  |  | 172000
C-5555 | HIGHWAY | VARIOUS | SIDEWALK PROJECTS AT SELECTED LOCATIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF GREENSBORO | EXEMPT |  |  |  | 1029000
C-5555E | HIGHWAY | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BGDA | CONSTRUCTION | 722000
C-5555E | HIGHWAY | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 200000
C-5555E | HIGHWAY | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 181000
C-5555E | HIGHWAY | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 50000
C-5558 | HIGHWAY | VARIOUS | CITY OF HIGH POINT SIGNAL SYSTEM EXPANSION AND UPGRADE. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | EXEMPT |  |  |  | 10232000
C-5559 | HIGHWAY | VARIOUS | TRANSIT OPERATIONS SUPPORT FOR CITY OF LEXINGTON CIRCULATOR ROUTE AND THOMASVILLE / LEXINGTON CONNECTOR ROUTE. | 9 | High Point Urban Area MPO | IMPLEMENTATION BY DAVIDSON COUNTY - IN PROGRESS | EXEMPT |  |  |  | 180000
C-5600 | HIGHWAY | VARIOUS | STATEWIDE CMAQ PROJECTS TO IMPROVE AIR QUALITY WITHIN NONATTAINMENT AND MAINTENANCE AREAS. | 99 | STATEWIDE PROJECT |  | EXEMPT |  |  |  | 41540000
C-5600E | HIGHWAY | I-85 | GUILDFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 312000 | FY 2023: 312000
C-5600E | HIGHWAY | I-85 | GUILDFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | S(M) | CONSTRUCTION | 330000 | FY 2023: 330000
C-5600E | HIGHWAY | I-85 | GUILDFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1249000 | FY 2023: 1249000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | L | ENGINEERING | 3000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | L | IMPLEMENTATION | 3000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | L | OPERATIONS | 3000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 3000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 15000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | CMAQ | OPERATIONS | 15000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 78000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 15000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 15000
C-5602 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | 7 | Burlington-Graham MPO |  | EXEMPT |  | L | CONSTRUCTION | 21000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | L | ENGINEERING | 63000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 246000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | L | IMPLEMENTATION | 63000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | L | OPERATIONS | 63000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 369000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 63000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | CMAQ | OPERATIONS | 246000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  |  |  | 1590000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 246000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 1479000
C-5603 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | EXEMPT |  | CMAQ | IMPLEMENTATION | 246000
C-5603D | HIGHWAY | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 295000 | FY 2023: 295000
C-5603D | HIGHWAY | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | CONSTRUCTION | 74000 | FY 2023: 74000
C-5603D | HIGHWAY | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | ENGINEERING | 7000
C-5603D | HIGHWAY | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 8000
C-5603D | HIGHWAY | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 28000
C-5603D | HIGHWAY | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 2000
C-5603F | HIGHWAY | SR 1643 (BETHPAGE ROAD) | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS | 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 208000
C-5603F | HIGHWAY | SR 1643 (BETHPAGE ROAD) | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS | 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | ENGINEERING | 52000
C-5603H | HIGHWAY | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 514000 | FY 2023: 514000
C-5603H | HIGHWAY | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | CONSTRUCTION | 129000 | FY 2023: 129000
C-5603H | HIGHWAY | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | ENGINEERING | 11000
C-5603H | HIGHWAY | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 44000
C-5603H | HIGHWAY | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 12000
C-5603H | HIGHWAY | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 50000
C-5603I | HIGHWAY | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | RIGHT-OF-WAY | 50000 | FY 2023: 50000
C-5603I | HIGHWAY | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | CONSTRUCTION | 229000 | FY 2024: 229000
C-5603I | HIGHWAY | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | ENGINEERING | 100000
C-5603I | HIGHWAY | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | CMAQ | CONSTRUCTION | 916000 | FY 2024: 916000
C-5603I | HIGHWAY | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 200000 | FY 2023: 200000
C-5603I | HIGHWAY | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | CMAQ | ENGINEERING | 400000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  |  |  | 18097000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | L | OPERATIONS | 103000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | L | IMPLEMENTATION | 237000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | L | OPERATIONS | 237000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 4725000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 237000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | L | ENGINEERING | 237000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | OPERATIONS | 951000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 18897000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 951000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | IMPLEMENTATION | 951000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | BGDA | OPERATIONS | 414000
C-5604 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | 4, 5 | Capital Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 951000
C-5604HA | HIGHWAY | MINGO CREEK GREENWAY | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | L | CONSTRUCTION | 440000 | FY 2023: 440000
C-5604HA | HIGHWAY | MINGO CREEK GREENWAY | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 298000
C-5604HA | HIGHWAY | MINGO CREEK GREENWAY | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | CMAQ | CONSTRUCTION | 1760000 | FY 2023: 1760000
C-5604HA | HIGHWAY | MINGO CREEK GREENWAY | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | L | RIGHT-OF-WAY | 74000
C-5604ID | HIGHWAY | HIGGINS GREENWAY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 200000 | FY 2023: 200000
C-5604ID | HIGHWAY | HIGGINS GREENWAY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 | 5 | Capital Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 380000
C-5604ID | HIGHWAY | HIGGINS GREENWAY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 1520000
C-5604ID | HIGHWAY | HIGGINS GREENWAY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 800000 | FY 2023: 800000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | L | ENGINEERING | 90000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | L | IMPLEMENTATION | 232000 | FY 2023: 142000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | L | OPERATIONS | 90000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 121000 | FY 2023: 121000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 357000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 1098000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 90000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | CMAQ | IMPLEMENTATION | 925000 | FY 2023: 568000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 484000 | FY 2023: 484000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | CMAQ | OPERATIONS | 357000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 357000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  |  |  | 2845000
C-5605 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 4392000
C-5605H | HIGHWAY | VARIOUS | INSTALL SIGNS & KIOSKS | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 484000 | FY 2023: 484000
C-5605H | HIGHWAY | VARIOUS | INSTALL SIGNS & KIOSKS | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | CONSTRUCTION | 121000 | FY 2023: 121000
C-5606B | HIGHWAY | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | EXEMPT |  | CMAQ | ENGINEERING | 101000
C-5606B | HIGHWAY | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | EXEMPT |  | L | CONSTRUCTION | 106000 | FY 2024: 106000
C-5606B | HIGHWAY | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | EXEMPT |  | L | RIGHT-OF-WAY | 1000 | FY 2023: 1000
C-5606B | HIGHWAY | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 4000 | FY 2023: 4000
C-5606B | HIGHWAY | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | EXEMPT |  | L | ENGINEERING | 25000
C-5606B | HIGHWAY | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | EXEMPT |  | CMAQ | CONSTRUCTION | 423000 | FY 2024: 423000
C-5606D | HIGHWAY | US 321 BUSINESS, NC 275/279 | CONSTRUCT SIDEWALKS ALONG PORTIONS OF US 321 BUSINESS AND NC 275/279 NEAR GASTON COLLEGE, INCLUDING A CROSSWALK ACROSS NC 275/279. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 314000 | FY 2023: 314000
C-5606D | HIGHWAY | US 321 BUSINESS, NC 275/279 | CONSTRUCT SIDEWALKS ALONG PORTIONS OF US 321 BUSINESS AND NC 275/279 NEAR GASTON COLLEGE, INCLUDING A CROSSWALK ACROSS NC 275/279. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 79000 | FY 2023: 79000
C-5606E | HIGHWAY | NEW ROUTE | TECHNOLOGY PARK TO GASTON COLLEGE. CONSTRUCT GREENWAY. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 470000 | FY 2023: 470000
C-5606E | HIGHWAY | NEW ROUTE | TECHNOLOGY PARK TO GASTON COLLEGE. CONSTRUCT GREENWAY. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 118000 | FY 2023: 118000
C-5606I | HIGHWAY | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 125000 | FY 2023: 125000
C-5606I | HIGHWAY | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 31000 | FY 2023: 31000
C-5606I | HIGHWAY | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | EXEMPT |  | S | CONSTRUCTION | 250000 | FY 2023: 250000
C-5606J | HIGHWAY | NEW ROUTE | CONSTRUCT POSTON PARK SIDEWALK CONNECTOR. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 149000 | FY 2023: 149000
C-5606J | HIGHWAY | NEW ROUTE | CONSTRUCT POSTON PARK SIDEWALK CONNECTOR. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | CONSTRUCTION | 37000 | FY 2023: 37000
C-5606K | HIGHWAY | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 12000 | FY 2023: 12000
C-5606K | HIGHWAY | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | CONSTRUCTION | 316000 | FY 2024: 316000
C-5606K | HIGHWAY | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 3000 | FY 2023: 3000
C-5606K | HIGHWAY | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1265000 | FY 2024: 1265000
C-5606K | HIGHWAY | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 103000 | FY 2023: 103000
C-5606K | HIGHWAY | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | ENGINEERING | 26000 | FY 2023: 26000
C-5606M | HIGHWAY | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 382000 | FY 2023: 382000
C-5606M | HIGHWAY | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 15000 | FY 2024: 15000
C-5606M | HIGHWAY | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1091000 | FY 2025: 1091000
C-5606M | HIGHWAY | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | ENGINEERING | 95000 | FY 2023: 95000
C-5606M | HIGHWAY | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 4000 | FY 2024: 4000
C-5606M | HIGHWAY | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | CONSTRUCTION | 273000 | FY 2025: 273000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 72000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 288000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | L | OPERATIONS | 72000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | L | IMPLEMENTATION | 72000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 432000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 288000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | CMAQ | OPERATIONS | 288000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 288000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1722000
C-5607 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | L | ENGINEERING | 72000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | CMAQ | OPERATIONS | 41000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | L | OPERATIONS | 10000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 61000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 10000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | CMAQ | IMPLEMENTATION | 41000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | L | IMPLEMENTATION | 10000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 242000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 41000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 41000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  |  |  | 1023000
C-5608 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | 12 | Greater Hickory MPO | IN PROGRESS | EXEMPT |  | L | ENGINEERING | 10000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | L | ENGINEERING | 48000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | L | IMPLEMENTATION | 48000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | L | OPERATIONS | 48000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 291000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 48000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | IMPLEMENTATION | 195000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | OPERATIONS | 195000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 1164000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 195000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  |  |  | 105000
C-5609 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | 7, 9 | High Point Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 195000
C-5609F | HIGHWAY | VARIOUS | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. | 7 | High Point Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 110000 | FY 2023: 110000
C-5609F | HIGHWAY | VARIOUS | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. | 7 | High Point Urban Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 32000 | FY 2023: 32000
C-5609F | HIGHWAY | VARIOUS | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. | 7 | High Point Urban Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 440000 | FY 2023: 440000
C-5609F | HIGHWAY | VARIOUS | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. | 7 | High Point Urban Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 8000 | FY 2023: 8000
C-5609L | HIGHWAY | VARIOUS | SIDEWALK IMPROVEMENTS. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 372000 | FY 2023: 372000
C-5609L | HIGHWAY | VARIOUS | SIDEWALK IMPROVEMENTS. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 19000
C-5609L | HIGHWAY | VARIOUS | SIDEWALK IMPROVEMENTS. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 1488000 | FY 2023: 1488000
C-5609L | HIGHWAY | VARIOUS | SIDEWALK IMPROVEMENTS. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 76000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | L | ENGINEERING | 21000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | L | IMPLEMENTATION | 21000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | L | OPERATIONS | 21000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 21000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | CMAQ | IMPLEMENTATION | 84000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | CMAQ | OPERATIONS | 84000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 495000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 84000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 84000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  |  |  | 254000
C-5610 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | 5 | Kerr-Tar RPO | IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 123000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  |  |  | 162000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | L | ENGINEERING | 1000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | L | OPERATIONS | 1000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | L | IMPLEMENTATION | 1000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | L | CONSTRUCTION | 4000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 1000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 3000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | CMAQ | OPERATIONS | 3000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 15000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 3000
C-5612 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | 14 | Land-of-Sky RPO, Southwestern RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 3000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | CMAQ | OPERATIONS | 414000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | L | OPERATIONS | 104000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | L | CONSTRUCTION | 622000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | L | RIGHT-OF-WAY | 104000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | L | IMPLEMENTATION | 104000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | CMAQ | CONSTRUCTION | 2486000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 414000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | CMAQ | ENGINEERING | 414000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  |  |  | 6304000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | L | ENGINEERING | 104000
C-5613 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | EXEMPT |  | CMAQ | IMPLEMENTATION | 414000
C-5613BD | HIGHWAY | SR 1138 (ARROWOOD ROAD) | NC 49 (SOUTH TRYON) TO SOUTH BOULEVARD. ITS UPGRADES. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 3000
C-5613BD | HIGHWAY | SR 1138 (ARROWOOD ROAD) | NC 49 (SOUTH TRYON) TO SOUTH BOULEVARD. ITS UPGRADES. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 482000 | FY 2023: 482000
C-5613BD | HIGHWAY | SR 1138 (ARROWOOD ROAD) | NC 49 (SOUTH TRYON) TO SOUTH BOULEVARD. ITS UPGRADES. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 1000
C-5613BD | HIGHWAY | SR 1138 (ARROWOOD ROAD) | NC 49 (SOUTH TRYON) TO SOUTH BOULEVARD. ITS UPGRADES. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 128000 | FY 2023: 128000
C-5613BE | HIGHWAY | SR 2467 (MALLARD CREEK ROAD) | NC 24 (HARRIS BOULEVARD) TO GOVERNOR HUNT ROAD. ITS AND TRAFFIC MANAGEMENT UPGRADES. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 158000 | FY 2023: 158000
C-5613BE | HIGHWAY | SR 2467 (MALLARD CREEK ROAD) | NC 24 (HARRIS BOULEVARD) TO GOVERNOR HUNT ROAD. ITS AND TRAFFIC MANAGEMENT UPGRADES. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 42000 | FY 2023: 42000
C-5613J | HIGHWAY | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | RIGHT-OF-WAY | 25000
C-5613J | HIGHWAY | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | CONSTRUCTION | 405000 | FY 2024: 286000; FY 2025: 119000
C-5613J | HIGHWAY | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | CMAQ | CONSTRUCTION | 822000 | FY 2024: 580000; FY 2025: 242000
C-5613J | HIGHWAY | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 50000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | L | ENGINEERING | 3000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | L | IMPLEMENTATION | 3000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | L | OPERATIONS | 3000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 9000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 3000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 9000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | CMAQ | OPERATIONS | 9000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 45000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 9000
C-5614 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | 9 | Northwest Piedmont RPO |  | EXEMPT |  | L | CONSTRUCTION | 12000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 92000 | FY 2023: 23000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | L | OPERATIONS | 24000 | FY 2023: 6000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 182000 | FY 2023: 80000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | L | IMPLEMENTATION | 24000 | FY 2023: 6000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | L | ENGINEERING | 24000 | FY 2023: 6000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 728000 | FY 2023: 320000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 92000 | FY 2023: 23000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 92000 | FY 2023: 23000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 24000 | FY 2023: 6000
C-5616 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | CMAQ | OPERATIONS | 92000 | FY 2023: 23000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | CMAQ | OPERATIONS | 5000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | L | OPERATIONS | 1000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | L | CONSTRUCTION | 8000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 1000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 5000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | L | IMPLEMENTATION | 1000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 30000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 5000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 5000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  |  |  | 127000
C-5617 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | 10 | Rocky River RPO |  | EXEMPT |  | L | ENGINEERING | 1000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | L | ENGINEERING | 9000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | L | OPERATIONS | 9000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | L | IMPLEMENTATION | 9000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | L | CONSTRUCTION | 51000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 9000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 36000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | OPERATIONS | 36000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 204000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 36000
C-5618 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | 7, 8 | Triangle Area RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 36000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | L | ENGINEERING | 85000 | FY 2023: 17000; FY 2024: 17000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | L | IMPLEMENTATION | 85000 | FY 2023: 17000; FY 2024: 17000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | L | OPERATIONS | 85000 | FY 2023: 17000; FY 2024: 17000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  |  |  | 40000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | L | CONSTRUCTION | 500000 | FY 2023: 100000; FY 2024: 100000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 85000 | FY 2023: 17000; FY 2024: 17000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | CMAQ | OPERATIONS | 335000 | FY 2023: 67000; FY 2024: 67000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1995000 | FY 2023: 399000; FY 2024: 399000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 335000 | FY 2023: 67000; FY 2024: 67000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 335000 | FY 2023: 67000; FY 2024: 67000
C-5619 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | 4 | Upper Coastal Plain RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 335000 | FY 2023: 67000; FY 2024: 67000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | L | OPERATIONS | 75000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | L | IMPLEMENTATION | 75000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 1065000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 75000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | L | ENGINEERING | 75000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | OPERATIONS | 291000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 4266000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 291000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  |  |  | 2221000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 291000
C-5620 | HIGHWAY | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | EXEMPT |  | CMAQ | IMPLEMENTATION | 291000
C-5621 | HIGHWAY | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | ENGINEERING | 669000
C-5621 | HIGHWAY | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | S(M) | CONSTRUCTION | 1870000 | FY 2023: 204000; FY 2024: 1246000; FY 2025: 420000
C-5621 | HIGHWAY | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  |  |  | 5004000
C-5621 | HIGHWAY | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 1308000
C-5621 | HIGHWAY | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | BA | RIGHT-OF-WAY | 785000
C-5621 | HIGHWAY | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | BA | ENGINEERING | 333000
C-5621 | HIGHWAY | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | CONSTRUCTION | 7474000 | FY 2023: 816000; FY 2024: 4980000; FY 2025: 1678000
C-5622 | HIGHWAY | GASTON COUNTY | HIGHLAND BRANCH GREENWAY, PHASE I. CONSTRUCT GREENWAY | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | EXEMPT |  |  |  | 420000
C-5622 | HIGHWAY | GASTON COUNTY | HIGHLAND BRANCH GREENWAY, PHASE I. CONSTRUCT GREENWAY | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | EXEMPT |  | L | CONSTRUCTION | 53000
C-5624 | HIGHWAY | CONOVER | CONSTRUCT 1ST STREET/US 70 BIKE AND PEDESTRIAN IMPROVEMENTS. | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  |  |  | 393000
C-5624 | HIGHWAY | CONOVER | CONSTRUCT 1ST STREET/US 70 BIKE AND PEDESTRIAN IMPROVEMENTS. | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | BGANY | CONSTRUCTION | 2123000 | FY 2024: 2123000
C-5624 | HIGHWAY | CONOVER | CONSTRUCT 1ST STREET/US 70 BIKE AND PEDESTRIAN IMPROVEMENTS. | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | L | CONSTRUCTION | 531000 | FY 2024: 531000
C-5650 | HIGHWAY | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | CMAQ | CONSTRUCTION | 1000000 | FY 2024: 1000000
C-5650 | HIGHWAY | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | BGDACV | CONSTRUCTION | 206000 | FY 2024: 206000
C-5650 | HIGHWAY | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 888000 | FY 2024: 888000
C-5650 | HIGHWAY | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | BGANY | CONSTRUCTION | 530000 | FY 2024: 530000
C-5650 | HIGHWAY | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  |  |  | 270000
C-5650 | HIGHWAY | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2023: 100000
C-5650 | HIGHWAY | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 25000 | FY 2023: 25000
C-5700 | HIGHWAY | OAKDALE ROAD | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | 7 | High Point Urban Area MPO |  | EXEMPT |  |  |  | 40000
C-5700 | HIGHWAY | OAKDALE ROAD | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | 7 | High Point Urban Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 136000 | FY 2024: 136000
C-5700 | HIGHWAY | OAKDALE ROAD | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | 7 | High Point Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 34000 | FY 2024: 34000
C-5701 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | BA | CONSTRUCTION | 650000
C-5701 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | L | CONSTRUCTION | 39000
C-5701 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | L | CONSTRUCTION | 478000
C-5701 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | L | RIGHT-OF-WAY | 68000
C-5701 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | CONSTRUCTION | 1912000
C-5701 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | BGDA | CONSTRUCTION | 157000
C-5701 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  |  |  | 2761000
C-5701 | HIGHWAY | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 256000
C-5702 | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM, INCLUDING EMISSIONS-REDUCING SUB-AWARDS, IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  |  |  | 2994000
C-5702D | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 1210000
C-5702D | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  | L | IMPLEMENTATION | 349000 | FY 2023: 349000
C-5702D | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 1396000 | FY 2023: 1396000
C-5702D | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  | L | IMPLEMENTATION | 303000
C-5702E | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 1222000
C-5702E | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 3245000 | FY 2023: 3245000
C-5702E | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  | L | IMPLEMENTATION | 306000
C-5702E | HIGHWAY | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | 99 | STATEWIDE PROJECT |  | EXEMPT |  | L | IMPLEMENTATION | 811000 | FY 2023: 811000
C-5703 | HIGHWAY | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | REGION F |  | CMAQ | RIGHT-OF-WAY | 600000
C-5703 | HIGHWAY | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | REGION F |  | S(M) | CONSTRUCTION | 1963000 | FY 2023: 1242000; FY 2024: 701000
C-5703 | HIGHWAY | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | REGION F |  | S(M) | RIGHT-OF-WAY | 139000
C-5703 | HIGHWAY | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | REGION F |  | L | CONSTRUCTION | 319000 | FY 2023: 202000; FY 2024: 114000
C-5703 | HIGHWAY | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | REGION F |  | CMAQ | CONSTRUCTION | 9081000 | FY 2023: 5747000; FY 2024: 3243000
C-5703 | HIGHWAY | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | REGION F |  |  |  | 2120000
C-5703 | HIGHWAY | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | REGION F |  | L | RIGHT-OF-WAY | 11000
C-5704 | HIGHWAY | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 41000 | FY 2024: 41000
C-5704 | HIGHWAY | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 10000 | FY 2024: 10000
C-5704 | HIGHWAY | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | CONSTRUCTION | 332000 | FY 2024: 332000
C-5704 | HIGHWAY | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  |  |  | 100000
C-5704 | HIGHWAY | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | ENGINEERING | 20000
C-5704 | HIGHWAY | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 78000
C-5704 | HIGHWAY | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 321000 | FY 2024: 321000
C-5705 | HIGHWAY | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | L | ENGINEERING | 8000 | FY 2023: 8000
C-5705 | HIGHWAY | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 20000 | FY 2024: 20000
C-5705 | HIGHWAY | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 314000 | FY 2025: 314000
C-5705 | HIGHWAY | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 80000 | FY 2024: 80000
C-5705 | HIGHWAY | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 32000 | FY 2023: 32000
C-5705 | HIGHWAY | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 78000 | FY 2025: 78000
E-4018 | BIKE/PED | VARIOUS | NATIONAL RECREATIONAL TRAILS. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 1845000
E-4018 | BIKE/PED | VARIOUS | NATIONAL RECREATIONAL TRAILS. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  | TA | CONSTRUCTION | 19200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 2400000
EB-3314 | BIKE/PED | VARIOUS | STATEWIDE PEDESTRIAN FACILITIES PROGRAM. | 99 | STATEWIDE PROJECT | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 6476000
EB-4020 | BIKE/PED | BRUSHY FORK GREENWAY | WATERWORKS ROAD TO REYNOLDS PARK ROAD IN WINSTON-SALEM. PAVED MULTI-USE TRAIL. | 9 | Winston-Salem Urban Area MPO |  | PRE-STI (TRANSITION) |  |  |  | 1473000
EB-4020C | BIKE/PED | BRUSHY FORK GREENWAY | LOWERY STREET TO REYNOLDS PARK ROAD | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 432000 | FY 2023: 432000
EB-4020C | BIKE/PED | BRUSHY FORK GREENWAY | LOWERY STREET TO REYNOLDS PARK ROAD | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | PRE-STI (TRANSITION) |  | BGANY | CONSTRUCTION | 1726000 | FY 2023: 1726000
EB-4539 | BIKE/PED | FAYETTEVILLE | CAPE FEAR RIVER GREENWAY, CLARK PARK SOUTH TO THE CAPE FEAR BOTANICAL GARDENS. CONSTRUCT SECOND PHASE OF AN OFF-ROAD MULTI-USE TRAIL. | 6 | Fayetteville Area MPO |  | PRE-STI (TRANSITION) |  |  |  | 2600000
EB-4539BC | BIKE/PED | FAYETTEVILLE | NORTH OF CSX RAIL LINE TO SOUTH OF CSX RAIL LINE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 190000
EB-4539BC | BIKE/PED | FAYETTEVILLE | NORTH OF CSX RAIL LINE TO SOUTH OF CSX RAIL LINE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | TAANY | CONSTRUCTION | 761000
EB-4707 | HIGHWAY | SR 2220 (OLD CHAPEL HILL ROAD) SR 1838 (OLD DURHAM | US 15 / US 501 IN ORANGE COUNTY TO SR 1116 (GARRETT ROAD) IN DURHAM COUNTY. BICYCLE, PEDESTRIAN, AND TRANSIT IMPROVEMENTS; AND CONSTRUCTION OF ROUNDABOUT. | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | PRE-STI (TRANSITION) |  |  |  | 13348000
EB-5513 | BIKE/PED | US 15 | SR 1110 IWEST HILLSBORO STREET) TO NC 56 IN CREEDMOOR. CONSTRUCT SIDEWALK / PATH. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY CITY OF CREEDMOOR; LET WITH C-5166A AND C-5166B | PRE-STI (TRANSITION) |  |  |  | 875000
EB-5514 | BIKE/PED | NC 751 / SR 1183 / SR 2220 / NON-SYSTEM (UNIVERSIT | SR 1116 (GARRETT ROAD) TO SR 1158 (CORNWALLIS ROAD) IN DURHAM. ADD BICYCLE LANES AND PEDESTRIAN IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY CITY OF DURHAM | PRE-STI (TRANSITION) |  |  |  | 2413000
EB-5517 | BIKE/PED | NEW PEDESTRIAN BRIDGE AND APPROACHES | EXISTING SIDEWALK TO PIEDMONT ENVIRONMENTAL CENTER ENTRANCE IN HIGH POINT AND JAMESTOWN. CONSTRUCT PEDESTRIAN BRIDGE OVER EAST FORK OF DEEP RIVER. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN | PRE-STI (TRANSITION) |  |  |  | 1200000
EB-5518 | BIKE/PED | LATHAM PARK GREENWAY | BATTLEGROUND AVENUE TO MENDENHALL STREET IN GREENSBORO. REMOVE THROUGH LANE ON HILL STREET AND CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION BY CITY OF GREENSBORO | PRE-STI (TRANSITION) |  |  |  | 562000
EB-5519 | BIKE/PED | SR 4121 (EAST MAIN STREET) | EXISTING SIDEWALK NEAR JAMESTOWN MUNICIPAL BUILDING TO YORKLEIGH LANE NEAR GUILFORD TECHNICAL COMMUNITY COLLEGE JAMESTOWN CAMPUS/RAGSDALE HIGH SCHOOL COMPLEX IN JAMESTOWN. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN | PRE-STI (TRANSITION) |  |  |  | 1062000
EB-5521 | BIKE/PED | NC 134 (NORTH MAIN STREET); SR 1005 (SOUTH MAIN ST | SR 1323 (OKEEWEMEE ROAD) TO BARNHILL STREET IN TROY. CONSTRUCT SIDEWALKS. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION BY TOWN OF TROY | PRE-STI (TRANSITION) |  |  |  | 715000
EB-5531 | BIKE/PED | BESSEMER CITY | PHASE I: 12TH STREET, CHADWICK COURT TO KAISER ROAD. PHASE II: YELLOW JACKET LANE/BESS TOWN ROAD, 12TH STREET TO 14TH STREET (NC 274). CONSTRUCT SIDEWALKS. | 12 | Gaston-Cleveland-Lincoln MPO |  | PRE-STI (TRANSITION) |  | BGANY | CONSTRUCTION | 300000
EB-5533 | BIKE/PED | GASTONIA | POSTON PARK TO SOUTH FORK RIVER GREENWAY. CONSTRUCT TRAIL. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 875000
EB-5539 | BIKE/PED | GREENVILLE | SOUTH TAR RIVER GREENWAY. PHASE 3: PITT STREET TO NASH STREET. CONSTRUCT GREENWAY USING EXISTING SIDEWALKS, ROADS AND ON NEW LOCATION ALONG THE RIVER. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  |  |  | 2984000
EB-5540 | BIKE/PED | LITTLE CROSS CREEK GREENWAY EXTENSION | FILTER PLANT DRIVE TO ROWAN STREET BRIDGE IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TAANY | CONSTRUCTION | 600000 | FY 2023: 600000
EB-5540 | BIKE/PED | LITTLE CROSS CREEK GREENWAY EXTENSION | FILTER PLANT DRIVE TO ROWAN STREET BRIDGE IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  |  |  | 75000
EB-5540 | BIKE/PED | LITTLE CROSS CREEK GREENWAY EXTENSION | FILTER PLANT DRIVE TO ROWAN STREET BRIDGE IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | CONSTRUCTION | 150000 | FY 2023: 150000
EB-5541 | BIKE/PED | BIG CROSS CREEK GREENWAY | LITTLE CROSS CREEK TO SMITH LAKE IN FORT BRAGG. CONSTRUCT MULTI-USE TRAIL. | 6 | Fayetteville Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY USING STBGDA FUNDS | NOT FUNDED |  |  |  | 720000
EB-5547 | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM EXISTING FLAT CREEK GREENWAY TRAILHEAD NORTH OF US 70 TO THE OAKS TRAIL. | 13 | French Broad River MPO | $3.234M IN BGANY USED AS PART OF MULTIPLE FUND SWAPS. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.991M. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.915M. | DIVISION 13 |  |  |  | 866000
EB-5547A | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 312000 | FY 2024: 312000
EB-5547A | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | ENGINEERING | 232000 | FY 2023: 232000
EB-5547A | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 32000 | FY 2023: 32000
EB-5547A | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | CONSTRUCTION | 1247000 | FY 2024: 1247000
EB-5547A | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | ENGINEERING | 58000 | FY 2023: 58000
EB-5547A | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 8000 | FY 2023: 8000
EB-5547B | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 310000 | FY 2024: 310000
EB-5547B | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 4000 | FY 2023: 4000
EB-5547B | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | ENGINEERING | 37000
EB-5547B | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | CONSTRUCTION | 1241000 | FY 2024: 1241000
EB-5547B | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | ENGINEERING | 147000
EB-5547B | BIKE/PED | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 16000 | FY 2023: 16000
EB-5600 | BIKE/PED | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | DIVISION 3 |  | BGANY | RIGHT-OF-WAY | 24000 | FY 2024: 24000
EB-5600 | BIKE/PED | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | DIVISION 3 |  | L | RIGHT-OF-WAY | 6000 | FY 2024: 6000
EB-5600 | BIKE/PED | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | DIVISION 3 |  | L | CONSTRUCTION | 148000 | FY 2024: 148000
EB-5600 | BIKE/PED | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | DIVISION 3 |  | BGANY | ENGINEERING | 120000
EB-5600 | BIKE/PED | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | DIVISION 3 |  | BGANY | CONSTRUCTION | 590000 | FY 2024: 590000
EB-5600 | BIKE/PED | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | DIVISION 3 |  | L | ENGINEERING | 30000
EB-5619 | BIKE/PED | GRANTS CREEK GREENWAY | KELSEY SCOTT PARK TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT MULTI-USE PATH. | 9 | Cabarrus-Rowan MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SALISBURY | DIVISION 9 |  |  |  | 702000
EB-5619B | BIKE/PED | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO WILTSHIRE VILLAGE. CONSTRUCT MULTIUSE PATH. | 9 | Cabarrus-Rowan MPO | RIGHT OF WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 288000 | FY 2023: 288000
EB-5619B | BIKE/PED | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO WILTSHIRE VILLAGE. CONSTRUCT MULTIUSE PATH. | 9 | Cabarrus-Rowan MPO | RIGHT OF WAY IN PROGRESS | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 660000
EB-5619B | BIKE/PED | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO WILTSHIRE VILLAGE. CONSTRUCT MULTIUSE PATH. | 9 | Cabarrus-Rowan MPO | RIGHT OF WAY IN PROGRESS | DIVISION 9 |  | BGDA | CONSTRUCTION | 1151000 | FY 2023: 1151000
EB-5619B | BIKE/PED | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO WILTSHIRE VILLAGE. CONSTRUCT MULTIUSE PATH. | 9 | Cabarrus-Rowan MPO | RIGHT OF WAY IN PROGRESS | DIVISION 9 |  | L | RIGHT-OF-WAY | 165000
EB-5619C | BIKE/PED | GRANTS CREEK GREENWAY | WILTSHIRE VILLAGE TO KELSEY SCOTT PARK. CONSTRUCT MULTIUSE PATH. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 470000 | FY 2024: 470000
EB-5619C | BIKE/PED | GRANTS CREEK GREENWAY | WILTSHIRE VILLAGE TO KELSEY SCOTT PARK. CONSTRUCT MULTIUSE PATH. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | ENGINEERING | 74000 | FY 2023: 74000
EB-5619C | BIKE/PED | GRANTS CREEK GREENWAY | WILTSHIRE VILLAGE TO KELSEY SCOTT PARK. CONSTRUCT MULTIUSE PATH. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BGDA | ENGINEERING | 294000 | FY 2023: 294000
EB-5619C | BIKE/PED | GRANTS CREEK GREENWAY | WILTSHIRE VILLAGE TO KELSEY SCOTT PARK. CONSTRUCT MULTIUSE PATH. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 1882000 | FY 2024: 1882000
EB-5701 | BIKE/PED | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 196000
EB-5701 | BIKE/PED | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | CONSTRUCTION | 1226000 | FY 2024: 1226000
EB-5701 | BIKE/PED | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | UTILITIES | 60000 | FY 2023: 60000
EB-5701 | BIKE/PED | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | RIGHT-OF-WAY | 176000 | FY 2023: 176000
EB-5701 | BIKE/PED | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 44000 | FY 2023: 44000
EB-5701 | BIKE/PED | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | UTILITIES | 15000 | FY 2023: 15000
EB-5701 | BIKE/PED | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 307000 | FY 2024: 307000
EB-5703 | BIKE/PED | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  |  |  | 717000
EB-5703 | BIKE/PED | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 30000
EB-5703 | BIKE/PED | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | CONSTRUCTION | 260000 | FY 2023: 260000
EB-5703 | BIKE/PED | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 120000
EB-5703 | BIKE/PED | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | TAANY | CONSTRUCTION | 1040000 | FY 2023: 1040000
EB-5704 | BIKE/PED | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  |  |  | 268000
EB-5704 | BIKE/PED | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 34000
EB-5704 | BIKE/PED | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | CONSTRUCTION | 116000 | FY 2023: 116000
EB-5704 | BIKE/PED | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 135000
EB-5704 | BIKE/PED | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | TAANY | CONSTRUCTION | 464000 | FY 2023: 464000
EB-5707 | BIKE/PED | STONEY CREEK GREENWAY | US 70 BYPASS TO SR 1560 (ROYALL AVENUE). CONSTRUCT 10 FOOT WIDE ASPHALT GREENWAY. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | L | CONSTRUCTION | 23000
EB-5707 | BIKE/PED | STONEY CREEK GREENWAY | US 70 BYPASS TO SR 1560 (ROYALL AVENUE). CONSTRUCT 10 FOOT WIDE ASPHALT GREENWAY. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | SRTS | CONSTRUCTION | 368000 | FY 2023: 180000
EB-5707 | BIKE/PED | STONEY CREEK GREENWAY | US 70 BYPASS TO SR 1560 (ROYALL AVENUE). CONSTRUCT 10 FOOT WIDE ASPHALT GREENWAY. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 15000
EB-5708 | BIKE/PED | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 35000
EB-5708 | BIKE/PED | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | CONSTRUCTION | 19000 | FY 2023: 19000
EB-5708 | BIKE/PED | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | SRTS | CONSTRUCTION | 215000 | FY 2023: 215000
EB-5708 | BIKE/PED | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 142000
EB-5708 | BIKE/PED | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | TAANY | CONSTRUCTION | 196000 | FY 2023: 196000
EB-5708 | BIKE/PED | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  |  |  | 276000
EB-5711 | BIKE/PED | US 64 BUSINESS (SUNSET AVENUE) | SR 1836 (MAY DRIVE) TO US 301 BUSINESS, NORTH BOUND (CHURCH STREET). INSTALL PEDESTRIAN SIGNALS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  |  |  | 25000
EB-5711 | BIKE/PED | US 64 BUSINESS (SUNSET AVENUE) | SR 1836 (MAY DRIVE) TO US 301 BUSINESS, NORTH BOUND (CHURCH STREET). INSTALL PEDESTRIAN SIGNALS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 116000 | FY 2023: 116000
EB-5711 | BIKE/PED | US 64 BUSINESS (SUNSET AVENUE) | SR 1836 (MAY DRIVE) TO US 301 BUSINESS, NORTH BOUND (CHURCH STREET). INSTALL PEDESTRIAN SIGNALS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA5200 | CONSTRUCTION | 464000 | FY 2023: 464000
EB-5715 | BIKE/PED | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | DIVISION 5 |  | TAANY | CONSTRUCTION | 2144000 | FY 2023: 2144000
EB-5715 | BIKE/PED | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | DIVISION 5 |  |  |  | 437000
EB-5715 | BIKE/PED | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | DIVISION 5 |  | L | RIGHT-OF-WAY | 59000
EB-5715 | BIKE/PED | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | DIVISION 5 |  | L | CONSTRUCTION | 536000 | FY 2023: 536000
EB-5715 | BIKE/PED | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 237000
EB-5716 | BIKE/PED | HOLDEN ROAD; EAST LINDSAY STREET | HOLDEN ROAD, SOUTH OF MEADOWVIEW ROAD TO SPRING GARDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK ON WEST SIDE. EAST LINDSAY STREET, MURROW BOULEVARD TO BESSEMER AVENUE IN GREENSBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 530000
EB-5718 | BIKE/PED | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | DIVISION 5 |  | TAANY | CONSTRUCTION | 3200000 | FY 2028: 1462000; FY 2029: 1738000
EB-5718 | BIKE/PED | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | DIVISION 5 |  | L | CONSTRUCTION | 800000 | FY 2028: 366000; FY 2029: 434000
EB-5720 | BIKE/PED | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | DIVISION 5 |  |  |  | 870000
EB-5720 | BIKE/PED | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | DIVISION 5 |  | HP | CONSTRUCTION | 2320000 | FY 2024: 2320000
EB-5720 | BIKE/PED | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | DIVISION 5 |  | L | RIGHT-OF-WAY | 11000 | FY 2024: 11000
EB-5720 | BIKE/PED | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | DIVISION 5 |  | L | CONSTRUCTION | 908000 | FY 2024: 908000
EB-5720 | BIKE/PED | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 3000 | FY 2024: 3000
EB-5720 | BIKE/PED | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | DIVISION 5 |  | TAANY | CONSTRUCTION | 2792000 | FY 2024: 2792000
EB-5721 | BIKE/PED | ORANGE COUNTY BICYCLE ROUTE 1 | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  |  |  | 120000
EB-5721 | BIKE/PED | ORANGE COUNTY BICYCLE ROUTE 1 | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 314000 | FY 2023: 314000
EB-5721 | BIKE/PED | ORANGE COUNTY BICYCLE ROUTE 1 | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | TADA | CONSTRUCTION | 1257000 | FY 2023: 1257000
EB-5722 | BIKE/PED | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGDA | CONSTRUCTION | 1252000 | FY 2023: 1252000
EB-5722 | BIKE/PED | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | TAANY | CONSTRUCTION | 1978000 | FY 2023: 1978000
EB-5722 | BIKE/PED | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 314000 | FY 2023: 314000
EB-5722 | BIKE/PED | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 728000
EB-5722 | BIKE/PED | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 415000
EB-5722 | BIKE/PED | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 494000 | FY 2023: 494000
EB-5722 | BIKE/PED | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | RIGHT-OF-WAY | 182000
EB-5723 | BIKE/PED | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). CONSTRUCT A MULTI-USE PATH. SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 1020000 | FY 2023: 1020000
EB-5723 | BIKE/PED | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). CONSTRUCT A MULTI-USE PATH. SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | TAANY | RIGHT-OF-WAY | 100000 | FY 2023: 100000
EB-5723 | BIKE/PED | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). CONSTRUCT A MULTI-USE PATH. SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 25000 | FY 2023: 25000
EB-5723 | BIKE/PED | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). CONSTRUCT A MULTI-USE PATH. SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 2042000 | FY 2023: 2042000
EB-5723 | BIKE/PED | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). CONSTRUCT A MULTI-USE PATH. SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  |  |  | 953000
EB-5723 | BIKE/PED | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). CONSTRUCT A MULTI-USE PATH. SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | TAANY | CONSTRUCTION | 868000 | FY 2023: 868000
EB-5729 | BIKE/PED | NC 97 (ATLANTIC AVENUE) | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 240000
EB-5729 | BIKE/PED | NC 97 (ATLANTIC AVENUE) | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 1480000
EB-5729 | BIKE/PED | NC 97 (ATLANTIC AVENUE) | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TA5200 | ENGINEERING | 960000
EB-5729 | BIKE/PED | NC 97 (ATLANTIC AVENUE) | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TA5200 | CONSTRUCTION | 5920000
EB-5732 | BIKE/PED | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1200000 | FY 2026: 574000; FY 2027: 580000; FY 2028: 46000
EB-5732 | BIKE/PED | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | TAANY | RIGHT-OF-WAY | 80000 | FY 2025: 80000
EB-5732 | BIKE/PED | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  |  |  | 720000
EB-5732 | BIKE/PED | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | TAANY | CONSTRUCTION | 4800000 | FY 2026: 2295000; FY 2027: 2321000; FY 2028: 184000
EB-5732 | BIKE/PED | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 20000 | FY 2025: 20000
EB-5734 | BIKE/PED | SR 2103 (EAST RALEIGH STREET) | SOUTH 7TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 8 | Triangle Area RPO |  | DIVISION 8 |  |  |  | 39000
EB-5734 | BIKE/PED | SR 2103 (EAST RALEIGH STREET) | SOUTH 7TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 149000 | FY 2023: 149000
EB-5734 | BIKE/PED | SR 2103 (EAST RALEIGH STREET) | SOUTH 7TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 595000 | FY 2023: 595000
EB-5741 | BIKE/PED | US 1 / US 15 / US 501 (SANDHILLS BOULEVARD) | MAPLE AVENUE IN ABERDEEN. CONSTRUCT MID-BLOCK CROSSWALK, MEDIAN REFUGE ISLAND, AND INSTALL PEDESTRIAN SIGNAL. | 8 | Triangle Area RPO |  | DIVISION 8 |  |  |  | 8000
EB-5741 | BIKE/PED | US 1 / US 15 / US 501 (SANDHILLS BOULEVARD) | MAPLE AVENUE IN ABERDEEN. CONSTRUCT MID-BLOCK CROSSWALK, MEDIAN REFUGE ISLAND, AND INSTALL PEDESTRIAN SIGNAL. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 56000 | FY 2023: 56000
EB-5741 | BIKE/PED | US 1 / US 15 / US 501 (SANDHILLS BOULEVARD) | MAPLE AVENUE IN ABERDEEN. CONSTRUCT MID-BLOCK CROSSWALK, MEDIAN REFUGE ISLAND, AND INSTALL PEDESTRIAN SIGNAL. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 224000 | FY 2023: 224000
EB-5742 | BIKE/PED | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 8 | Triangle Area RPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | DIVISION 8 |  | L | ENGINEERING | 15000
EB-5742 | BIKE/PED | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 8 | Triangle Area RPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | DIVISION 8 |  | L | CONSTRUCTION | 202000 | FY 2024: 202000
EB-5742 | BIKE/PED | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 8 | Triangle Area RPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | DIVISION 8 |  | TA5200 | ENGINEERING | 62000
EB-5742 | BIKE/PED | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 8 | Triangle Area RPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | DIVISION 8 |  | TA5200 | CONSTRUCTION | 809000 | FY 2024: 809000
EB-5743 | BIKE/PED | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | ENGINEERING | 64000 | FY 2023: 64000
EB-5743 | BIKE/PED | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | CONSTRUCTION | 1028000 | FY 2025: 1028000
EB-5743 | BIKE/PED | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 257000 | FY 2025: 257000
EB-5743 | BIKE/PED | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 321000
EB-5743 | BIKE/PED | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | ENGINEERING | 257000 | FY 2023: 257000
EB-5744 | BIKE/PED | SR 1950 (WEST ACADEMY STREET) | SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN. CONSTRUCT SIDEWALK ON NORTH SIDE. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  |  |  | 69000
EB-5744 | BIKE/PED | SR 1950 (WEST ACADEMY STREET) | SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN. CONSTRUCT SIDEWALK ON NORTH SIDE. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 160000 | FY 2023: 160000
EB-5744 | BIKE/PED | SR 1950 (WEST ACADEMY STREET) | SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN. CONSTRUCT SIDEWALK ON NORTH SIDE. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 640000 | FY 2023: 640000
EB-5745 | BIKE/PED | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 308000
EB-5745 | BIKE/PED | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | ENGINEERING | 62000 | FY 2023: 62000
EB-5745 | BIKE/PED | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 27000 | FY 2024: 27000
EB-5745 | BIKE/PED | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 246000 | FY 2025: 220000; FY 2026: 26000
EB-5745 | BIKE/PED | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | ENGINEERING | 246000 | FY 2023: 246000
EB-5745 | BIKE/PED | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | RIGHT-OF-WAY | 108000 | FY 2024: 108000
EB-5745 | BIKE/PED | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | CONSTRUCTION | 984000 | FY 2025: 881000; FY 2026: 103000
EB-5748 | BIKE/PED | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | ENGINEERING | 81000
EB-5748 | BIKE/PED | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | CONSTRUCTION | 324000 | FY 2027: 324000
EB-5748 | BIKE/PED | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | ENGINEERING | 20000
EB-5748 | BIKE/PED | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 101000
EB-5748 | BIKE/PED | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 81000 | FY 2027: 81000
EB-5750 | BIKE/PED | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | TAANY | CONSTRUCTION | 7680000
EB-5750 | BIKE/PED | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 12 | Greater Hickory MPO |  | DIVISION 12 |  |  |  | 4000
EB-5750 | BIKE/PED | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGANY | CONSTRUCTION | 3600000
EB-5750 | BIKE/PED | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 1920000
EB-5750 | BIKE/PED | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 900000
EB-5753 | BIKE/PED | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (E COURT ST). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | CONSTRUCTION | 250000 | FY 2024: 250000
EB-5753 | BIKE/PED | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (E COURT ST). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | RIGHT-OF-WAY | 80000 | FY 2023: 80000
EB-5753 | BIKE/PED | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (E COURT ST). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | ENGINEERING | 20000
EB-5753 | BIKE/PED | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (E COURT ST). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 13 | Foothills RPO |  | DIVISION 13 |  | L | CONSTRUCTION | 62000 | FY 2024: 62000
EB-5753 | BIKE/PED | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (E COURT ST). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 13 | Foothills RPO |  | DIVISION 13 |  | L | ENGINEERING | 5000
EB-5753 | BIKE/PED | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (E COURT ST). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 13 | Foothills RPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 20000 | FY 2023: 20000
EB-5756 | BIKE/PED | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | L | CONSTRUCTION | 59000 | FY 2023: 18000; FY 2024: 41000
EB-5756 | BIKE/PED | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | TA5200 | ENGINEERING | 14000
EB-5756 | BIKE/PED | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  |  |  | 69000
EB-5756 | BIKE/PED | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | L | ENGINEERING | 4000
EB-5756 | BIKE/PED | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | TA5200 | CONSTRUCTION | 235000 | FY 2023: 70000; FY 2024: 165000
EB-5761 | BIKE/PED | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | ENGINEERING | 40000 | FY 2023: 40000
EB-5761 | BIKE/PED | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | RIGHT-OF-WAY | 50000 | FY 2024: 50000
EB-5761 | BIKE/PED | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 500000 | FY 2025: 500000
EB-5761 | BIKE/PED | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA5200 | ENGINEERING | 160000 | FY 2023: 160000
EB-5761 | BIKE/PED | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA5200 | CONSTRUCTION | 2000000 | FY 2025: 2000000
EB-5763 | BIKE/PED | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | ENGINEERING | 40000
EB-5763 | BIKE/PED | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA5200 | CONSTRUCTION | 1200000 | FY 2025: 1200000
EB-5763 | BIKE/PED | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA5200 | RIGHT-OF-WAY | 240000 | FY 2024: 240000
EB-5763 | BIKE/PED | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA5200 | ENGINEERING | 160000
EB-5763 | BIKE/PED | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | RIGHT-OF-WAY | 60000 | FY 2024: 60000
EB-5763 | BIKE/PED | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 300000 | FY 2025: 300000
EB-5768 | BIKE/PED | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | ENGINEERING | 70000 | FY 2023: 70000
EB-5768 | BIKE/PED | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | RIGHT-OF-WAY | 48000 | FY 2024: 48000
EB-5768 | BIKE/PED | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | CONSTRUCTION | 1008000 | FY 2024: 1008000
EB-5768 | BIKE/PED | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | ENGINEERING | 280000 | FY 2023: 280000
EB-5768 | BIKE/PED | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 315000
EB-5768 | BIKE/PED | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 252000 | FY 2024: 252000
EB-5768 | BIKE/PED | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 12000 | FY 2024: 12000
EB-5774 | BIKE/PED | NC 251 (RIVERSIDE DRIVE) MULTI-USE PATH | US 19/23/70 (EXIT 25) TO US 25. CONSTRUCT MULTI-USE PATH VIA BEAVERDAM CREEK. | 13 | French Broad River MPO | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION | DIVISION 13 |  |  |  | 580000
EB-5774 | BIKE/PED | NC 251 (RIVERSIDE DRIVE) MULTI-USE PATH | US 19/23/70 (EXIT 25) TO US 25. CONSTRUCT MULTI-USE PATH VIA BEAVERDAM CREEK. | 13 | French Broad River MPO | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION | DIVISION 13 |  | BGDA | ENGINEERING | 1600000
EB-5774 | BIKE/PED | NC 251 (RIVERSIDE DRIVE) MULTI-USE PATH | US 19/23/70 (EXIT 25) TO US 25. CONSTRUCT MULTI-USE PATH VIA BEAVERDAM CREEK. | 13 | French Broad River MPO | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION | DIVISION 13 |  | L | ENGINEERING | 400000
EB-5774A | BIKE/PED | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | CRPDA | RIGHT-OF-WAY | 1911000 | FY 2023: 1911000
EB-5774A | BIKE/PED | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | TADA | RIGHT-OF-WAY | 1495000 | FY 2023: 1495000
EB-5774A | BIKE/PED | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 1202000 | FY 2025: 1202000
EB-5774A | BIKE/PED | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 375000 | FY 2023: 375000
EB-5774A | BIKE/PED | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | CONSTRUCTION | 4808000 | FY 2025: 4808000
EB-5774A | BIKE/PED | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 478000 | FY 2023: 478000
EB-5774B | BIKE/PED | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 500000 | FY 2026: 500000
EB-5774B | BIKE/PED | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | CONSTRUCTION | 760000 | FY 2026: 760000
EB-5774B | BIKE/PED | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | TADA | RIGHT-OF-WAY | 310000 | FY 2025: 310000
EB-5774B | BIKE/PED | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 190000 | FY 2026: 190000
EB-5774B | BIKE/PED | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 44000 | FY 2025: 44000
EB-5774B | BIKE/PED | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | RIGHT-OF-WAY | 176000 | FY 2025: 176000
EB-5774B | BIKE/PED | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | CONSTRUCTION | 2000000 | FY 2026: 2000000
EB-5774B | BIKE/PED | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 78000 | FY 2025: 78000
EB-5777 | BIKE/PED | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY; CONSTRUCT GREENWAY FROM SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | RIGHT-OF-WAY | 768000
EB-5777 | BIKE/PED | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY; CONSTRUCT GREENWAY FROM SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1632000 | FY 2024: 1632000
EB-5777 | BIKE/PED | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY; CONSTRUCT GREENWAY FROM SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 192000
EB-5777 | BIKE/PED | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY; CONSTRUCT GREENWAY FROM SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 408000 | FY 2024: 408000
EB-5781 | BIKE/PED | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | BGDA | CONSTRUCTION | 411000
EB-5781 | BIKE/PED | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 2116000
EB-5781 | BIKE/PED | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 529000
EB-5781 | BIKE/PED | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 103000
EB-5782 | BIKE/PED | GREENWAY MCALPINE CREEK | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | $3.926M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | TAANY | CONSTRUCTION | 1848000 | FY 2023: 1848000
EB-5782 | BIKE/PED | GREENWAY MCALPINE CREEK | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | $3.926M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 2102000 | FY 2023: 2102000
EB-5782 | BIKE/PED | GREENWAY MCALPINE CREEK | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | $3.926M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 3926000 | FY 2023: 3926000
EB-5783 | BIKE/PED | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | BGANY | RIGHT-OF-WAY | 30000
EB-5783 | BIKE/PED | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | BGDA | ENGINEERING | 185000
EB-5783 | BIKE/PED | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 238000
EB-5783 | BIKE/PED | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | BGDA | CONSTRUCTION | 1221000 | FY 2024: 1221000
EB-5783 | BIKE/PED | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | L | ENGINEERING | 46000
EB-5783 | BIKE/PED | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 67000
EB-5783 | BIKE/PED | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 305000 | FY 2024: 305000
EB-5783 | BIKE/PED | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  |  |  | 150000
EB-5785 | BIKE/PED | HUNTERSVILLE | UPPER MCDOWELL CREEK GREENWAY, CHILGROVE LANE TO NC 73. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 4271000 | FY 2023: 4271000
EB-5785 | BIKE/PED | HUNTERSVILLE | UPPER MCDOWELL CREEK GREENWAY, CHILGROVE LANE TO NC 73. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | L | CONSTRUCTION | 1068000 | FY 2023: 1068000
EB-5787 | BIKE/PED | MOORESVILLE | BELLINGHAM PARK GREENWAY EXTENSION TO JOHNSON DAIRY ROAD. CONSTRUCT GREENWAY. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 12 |  | BGDA | CONSTRUCTION | 3555000 | FY 2023: 3555000
EB-5787 | BIKE/PED | MOORESVILLE | BELLINGHAM PARK GREENWAY EXTENSION TO JOHNSON DAIRY ROAD. CONSTRUCT GREENWAY. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 12 |  | L | CONSTRUCTION | 889000 | FY 2023: 889000
EB-5788 | BIKE/PED | STATESVILLE | SHELTON AVENUE MULTI-USE PATH, GARNER BAGNAL BOULEVARD TO AMITY HILL ROAD. CONSTRUCT GREENWAY. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 201000 | FY 2023: 201000
EB-5788 | BIKE/PED | STATESVILLE | SHELTON AVENUE MULTI-USE PATH, GARNER BAGNAL BOULEVARD TO AMITY HILL ROAD. CONSTRUCT GREENWAY. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 12 |  | L | RIGHT-OF-WAY | 50000 | FY 2023: 50000
EB-5788 | BIKE/PED | STATESVILLE | SHELTON AVENUE MULTI-USE PATH, GARNER BAGNAL BOULEVARD TO AMITY HILL ROAD. CONSTRUCT GREENWAY. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 12 |  |  |  | 240000
EB-5790 | BIKE/PED | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919 | DIVISION 13 |  | BGDA | CONSTRUCTION | 840000 | FY 2023: 840000
EB-5790 | BIKE/PED | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919 | DIVISION 13 |  | L | CONSTRUCTION | 210000 | FY 2023: 210000
EB-5790 | BIKE/PED | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919 | DIVISION 13 |  | L | CONSTRUCTION | 89000 | FY 2023: 89000
EB-5790 | BIKE/PED | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919 | DIVISION 13 |  | TAANY | CONSTRUCTION | 357000 | FY 2023: 357000
EB-5790 | BIKE/PED | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919 | DIVISION 13 |  |  |  | 96000
EB-5798 | BIKE/PED | US 221 | MAIN STREET IN BLOWING ROCK TO MOSES H CONE MEMORIAL PARK AND BASS LAKE. CONSTRUCT SIDEWALK. | 11 | High Country RPO | UNDER CONSTRUCTION. PROJECT TO BE ADMINISTERED BY THE TOWN OF BLOWING ROCK | EXEMPT |  |  |  | 1201000
EB-5806 | BIKE/PED | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | DIVISION 11 |  | BGANY | CONSTRUCTION | 414000 | FY 2023: 414000
EB-5806 | BIKE/PED | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | DIVISION 11 |  | TADA | CONSTRUCTION | 125000 | FY 2023: 125000
EB-5806 | BIKE/PED | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | DIVISION 11 |  | TADA | RIGHT-OF-WAY | 96000
EB-5806 | BIKE/PED | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | DIVISION 11 |  | L | CONSTRUCTION | 169000 | FY 2023: 169000
EB-5806 | BIKE/PED | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | DIVISION 11 |  | L | CONSTRUCTION | 31000 | FY 2023: 31000
EB-5806 | BIKE/PED | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | DIVISION 11 |  | BGDACV | CONSTRUCTION | 261000 | FY 2023: 261000
EB-5806 | BIKE/PED | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | DIVISION 11 |  | L | RIGHT-OF-WAY | 24000
EB-5807 | BIKE/PED | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 13 |  | L | CONSTRUCTION | 250000
EB-5807 | BIKE/PED | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 13 |  | L | CONSTRUCTION | 74000
EB-5807 | BIKE/PED | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 13 |  | BGANY | CONSTRUCTION | 1000000
EB-5807 | BIKE/PED | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 13 |  |  |  | 63000
EB-5807 | BIKE/PED | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 13 |  | BGDA | CONSTRUCTION | 295000
EB-5808 | BIKE/PED | HICKORY | UPGRADE CURRENT PEDESTRIAN SIGNALS AND INSTALL NEW PEDESTRIAN SIGNALS. | 11, 12, 13 | Greater Hickory MPO | $322K IN STBG-DA FUNDS SWITCHED WITH $322K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11, 12, 13 |  |  |  | 72000
EB-5808 | BIKE/PED | HICKORY | UPGRADE CURRENT PEDESTRIAN SIGNALS AND INSTALL NEW PEDESTRIAN SIGNALS. | 11, 12, 13 | Greater Hickory MPO | $322K IN STBG-DA FUNDS SWITCHED WITH $322K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11, 12, 13 |  | BGANY | CONSTRUCTION | 322000 | FY 2023: 322000
EB-5808 | BIKE/PED | HICKORY | UPGRADE CURRENT PEDESTRIAN SIGNALS AND INSTALL NEW PEDESTRIAN SIGNALS. | 11, 12, 13 | Greater Hickory MPO | $322K IN STBG-DA FUNDS SWITCHED WITH $322K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 11, 12, 13 |  | L | CONSTRUCTION | 80000 | FY 2023: 80000
EB-5810 | BIKE/PED | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGDA | CONSTRUCTION | 5000 | FY 2024: 5000
EB-5810 | BIKE/PED | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | TAANY | CONSTRUCTION | 176000 | FY 2024: 176000
EB-5810 | BIKE/PED | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 44000 | FY 2024: 44000
EB-5810 | BIKE/PED | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 60000
EB-5810 | BIKE/PED | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 1000 | FY 2024: 1000
EB-5812 | BIKE/PED | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 150000
EB-5812 | BIKE/PED | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 30000
EB-5812 | BIKE/PED | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 300000 | FY 2026: 300000
EB-5812 | BIKE/PED | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | ENGINEERING | 120000
EB-5812 | BIKE/PED | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | CONSTRUCTION | 1200000 | FY 2026: 1200000
EB-5814 | BIKE/PED | SR 3015 (AIRPORT BOULEVARD) | MCCRIMMON PARKWAY TO FACTORY SHOPPES ROAD IN MORRISVILLE. CONSTRUCT SIDEWALK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  |  |  | 65000
EB-5814 | BIKE/PED | SR 3015 (AIRPORT BOULEVARD) | MCCRIMMON PARKWAY TO FACTORY SHOPPES ROAD IN MORRISVILLE. CONSTRUCT SIDEWALK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | TAANY | CONSTRUCTION | 640000
EB-5814 | BIKE/PED | SR 3015 (AIRPORT BOULEVARD) | MCCRIMMON PARKWAY TO FACTORY SHOPPES ROAD IN MORRISVILLE. CONSTRUCT SIDEWALK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | CONSTRUCTION | 160000
EB-5817 | BIKE/PED | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | COMPLETE. | DIVISION 10 |  |  |  | 450000
EB-5817 | BIKE/PED | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | COMPLETE. | DIVISION 10 |  | BGDA | CONSTRUCTION | 1026000
EB-5817 | BIKE/PED | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | COMPLETE. | DIVISION 10 |  | L | CONSTRUCTION | 1200000
EB-5817 | BIKE/PED | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | COMPLETE. | DIVISION 10 |  | L | CONSTRUCTION | 256000
EB-5817 | BIKE/PED | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO | COMPLETE. | DIVISION 10 |  | TADA | CONSTRUCTION | 1400000
EB-5818 | BIKE/PED | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 12 |  | BGDA | CONSTRUCTION | 1200000 | FY 2023: 1200000
EB-5818 | BIKE/PED | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 12 |  | L | CONSTRUCTION | 470000 | FY 2023: 470000
EB-5818 | BIKE/PED | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 12 |  |  |  | 450000
EB-5819 | BIKE/PED | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGDA | CONSTRUCTION | 383000 | FY 2023: 383000
EB-5819 | BIKE/PED | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | CONSTRUCTION | 383000 | FY 2023: 383000
EB-5819 | BIKE/PED | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  |  |  | 206000
EB-5820 | BIKE/PED | CHARLOTTE | CHARLOTTE BICYCLE EXPANSION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | DIVISION 10 |  |  |  | 675000
EB-5821 | BIKE/PED | REEMS CREEK GREENWAY | CONSTRUCT MULTI-USE PATH ALONG REEMS CREEK CORRIDOR FROM WESTERN EDGE OF TOWN OF WEAVERVILLE TO KARPEN SOCCER FIELDS | 13 | French Broad River MPO | IN PROGRESS | DIVISION 13 |  |  |  | 600000
EB-5822 | BIKE/PED | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | 13 | French Broad River MPO |  | DIVISION 13 |  | TAANY | ENGINEERING | 480000
EB-5822 | BIKE/PED | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | 13 | French Broad River MPO |  | DIVISION 13 |  | TAANY | RIGHT-OF-WAY | 103000 | FY 2023: 103000
EB-5822 | BIKE/PED | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | 13 | French Broad River MPO |  | DIVISION 13 |  | TAANY | CONSTRUCTION | 2200000 | FY 2025: 2200000
EB-5822 | BIKE/PED | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | 13 | French Broad River MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 26000 | FY 2023: 26000
EB-5822 | BIKE/PED | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | CONSTRUCTION | 1000000 | FY 2025: 1000000
EB-5822 | BIKE/PED | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | 13 | French Broad River MPO |  | DIVISION 13 |  | L | ENGINEERING | 120000
EB-5822 | BIKE/PED | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 800000 | FY 2025: 800000
EB-5823 | BIKE/PED | BENT CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY CREEK RIVER PARK TO WESTERN NC FARMERS MARKET. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | ENGINEERING | 320000 | FY 2029: 320000
EB-5823 | BIKE/PED | BENT CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY CREEK RIVER PARK TO WESTERN NC FARMERS MARKET. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | ENGINEERING | 80000 | FY 2029: 80000
EB-5824 | BIKE/PED | HOMINY CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | DIVISION 13 |  | BGANY | ENGINEERING | 528000
EB-5824 | BIKE/PED | HOMINY CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | DIVISION 13 |  | BGANY | CONSTRUCTION | 2789000 | FY 2023: 2789000
EB-5824 | BIKE/PED | HOMINY CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | DIVISION 13 |  | BGDA | ENGINEERING | 520000
EB-5824 | BIKE/PED | HOMINY CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | DIVISION 13 |  | BGDA | CONSTRUCTION | 37000 | FY 2023: 37000
EB-5824 | BIKE/PED | HOMINY CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | DIVISION 13 |  | L | ENGINEERING | 130000
EB-5824 | BIKE/PED | HOMINY CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | DIVISION 13 |  | L | ENGINEERING | 132000
EB-5824 | BIKE/PED | HOMINY CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | DIVISION 13 |  | L | CONSTRUCTION | 1018000 | FY 2023: 1018000
EB-5827 | BIKE/PED | FONTA FLORA TRAIL | FONTA FLORA STATE TRAIL, INTERSECTION OF LAUREL RIDGE COURT AND NORTH POWERHOUSE ROAD TO THE PROPOSED HARRIS WHISNANT TRAILHEAD AT THE INTERSECTION OF HARRY WHISNANT ROAD AND COBB ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN FACILITY. | 13 | Greater Hickory MPO | $410K IN STBG-DA FUNDS SWITCHED WITH $410K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 410000 | FY 2023: 410000
EB-5827 | BIKE/PED | FONTA FLORA TRAIL | FONTA FLORA STATE TRAIL, INTERSECTION OF LAUREL RIDGE COURT AND NORTH POWERHOUSE ROAD TO THE PROPOSED HARRIS WHISNANT TRAILHEAD AT THE INTERSECTION OF HARRY WHISNANT ROAD AND COBB ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN FACILITY. | 13 | Greater Hickory MPO | $410K IN STBG-DA FUNDS SWITCHED WITH $410K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  | L | RIGHT-OF-WAY | 216000 | FY 2023: 216000
EB-5827 | BIKE/PED | FONTA FLORA TRAIL | FONTA FLORA STATE TRAIL, INTERSECTION OF LAUREL RIDGE COURT AND NORTH POWERHOUSE ROAD TO THE PROPOSED HARRIS WHISNANT TRAILHEAD AT THE INTERSECTION OF HARRY WHISNANT ROAD AND COBB ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN FACILITY. | 13 | Greater Hickory MPO | $410K IN STBG-DA FUNDS SWITCHED WITH $410K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 13 |  |  |  | 544000
EB-5828 | BIKE/PED | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 25000 | FY 2023: 25000
EB-5828 | BIKE/PED | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | L | RIGHT-OF-WAY | 6000 | FY 2023: 6000
EB-5828 | BIKE/PED | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | L | CONSTRUCTION | 108000 | FY 2024: 108000
EB-5828 | BIKE/PED | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. | 12 | Greater Hickory MPO | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | BGANY | CONSTRUCTION | 433000 | FY 2024: 433000
EB-5829 | BIKE/PED | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  |  |  | 141000
EB-5829 | BIKE/PED | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | CONSTRUCTION | 281000
EB-5829 | BIKE/PED | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | CONSTRUCTION | 444000 | FY 2023: 444000
EB-5829 | BIKE/PED | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | TADA | CONSTRUCTION | 1331000
EB-5829 | BIKE/PED | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | TADA | CONSTRUCTION | 843000 | FY 2023: 843000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | L | ENGINEERING | 105000 | FY 2023: 105000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | L | CONSTRUCTION | 313000 | FY 2025: 313000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | L | CONSTRUCTION | 1888000 | FY 2025: 19000; FY 2026: 973000; FY 2027: 759000; FY 2028: 137000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | TADA | ENGINEERING | 300000 | FY 2023: 300000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | L | ENGINEERING | 75000 | FY 2023: 75000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | BGDA | RIGHT-OF-WAY | 240000 | FY 2024: 240000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | BGDA | ENGINEERING | 420000 | FY 2023: 420000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | BGANY | CONSTRUCTION | 7552000 | FY 2025: 76000; FY 2026: 3893000; FY 2027: 3037000; FY 2028: 546000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | BGDA | CONSTRUCTION | 1247000 | FY 2025: 1247000
EB-5831 | BIKE/PED | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 13 |  | L | RIGHT-OF-WAY | 60000 | FY 2024: 60000
EB-5832 | BIKE/PED | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  |  |  | 364000
EB-5832 | BIKE/PED | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGDA | CONSTRUCTION | 800000
EB-5832 | BIKE/PED | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | CONSTRUCTION | 136000
EB-5832 | BIKE/PED | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | CONSTRUCTION | 200000
EB-5832 | BIKE/PED | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | TAANY | CONSTRUCTION | 542000
EB-5834 | BIKE/PED | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TAANY | ENGINEERING | 84000 | FY 2023: 84000
EB-5834 | BIKE/PED | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 163000 | FY 2025: 163000
EB-5834 | BIKE/PED | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 118000 | FY 2026: 118000
EB-5834 | BIKE/PED | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | BGDACV | CONSTRUCTION | 704000 | FY 2026: 704000
EB-5834 | BIKE/PED | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | ENGINEERING | 24000 | FY 2023: 24000
EB-5834 | BIKE/PED | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TAANY | CONSTRUCTION | 471000 | FY 2026: 471000
EB-5834 | BIKE/PED | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 41000 | FY 2025: 41000
EB-5835 | BIKE/PED | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TAANY | ENGINEERING | 84000 | FY 2023: 84000
EB-5835 | BIKE/PED | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 40000 | FY 2027: 40000
EB-5835 | BIKE/PED | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 239000 | FY 2028: 239000
EB-5835 | BIKE/PED | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 10000 | FY 2027: 10000
EB-5835 | BIKE/PED | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | ENGINEERING | 21000 | FY 2023: 21000
EB-5835 | BIKE/PED | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TAANY | CONSTRUCTION | 957000 | FY 2028: 957000
EB-5837 | BIKE/PED | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  |  |  | 567000
EB-5837 | BIKE/PED | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 3000 | FY 2023: 3000
EB-5837 | BIKE/PED | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 1120000 | FY 2024: 374000; FY 2025: 373000; FY 2026: 373000
EB-5837 | BIKE/PED | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 14000 | FY 2023: 14000
EB-5837 | BIKE/PED | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TAANY | CONSTRUCTION | 4480000 | FY 2024: 1494000; FY 2025: 1493000; FY 2026: 1493000
EB-5838 | BIKE/PED | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | TAANY | RIGHT-OF-WAY | 200000 | FY 2023: 200000
EB-5838 | BIKE/PED | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | TAANY | ENGINEERING | 240000
EB-5838 | BIKE/PED | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | TAANY | CONSTRUCTION | 1160000 | FY 2024: 1160000
EB-5838 | BIKE/PED | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 50000 | FY 2023: 50000
EB-5838 | BIKE/PED | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | ENGINEERING | 60000
EB-5838 | BIKE/PED | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 290000 | FY 2024: 290000
EB-5840 | BIKE/PED | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT | DIVISION 9 |  | BGDA | CONSTRUCTION | 477000 | FY 2023: 477000
EB-5840 | BIKE/PED | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT | DIVISION 9 |  | L | CONSTRUCTION | 400000 | FY 2023: 400000
EB-5840 | BIKE/PED | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT | DIVISION 9 |  | L | CONSTRUCTION | 346000 | FY 2023: 346000
EB-5840 | BIKE/PED | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT | DIVISION 9 |  | TAANY | CONSTRUCTION | 1600000 | FY 2023: 1600000
EB-5840 | BIKE/PED | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT | DIVISION 9 |  | TADA | CONSTRUCTION | 907000 | FY 2023: 907000
EB-5841 | BIKE/PED | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 10 | Rocky River RPO |  | DIVISION 10 |  | L | ENGINEERING | 10000 | FY 2024: 10000
EB-5841 | BIKE/PED | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 10 | Rocky River RPO |  | DIVISION 10 |  | TA5200 | CONSTRUCTION | 200000 | FY 2026: 200000
EB-5841 | BIKE/PED | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 10 | Rocky River RPO |  | DIVISION 10 |  | TA5200 | RIGHT-OF-WAY | 200000 | FY 2025: 200000
EB-5841 | BIKE/PED | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 10 | Rocky River RPO |  | DIVISION 10 |  | TA5200 | ENGINEERING | 40000 | FY 2024: 40000
EB-5841 | BIKE/PED | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 10 | Rocky River RPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 50000 | FY 2025: 50000
EB-5841 | BIKE/PED | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 10 | Rocky River RPO |  | DIVISION 10 |  | L | CONSTRUCTION | 50000 | FY 2026: 50000
EB-5843 | BIKE/PED | EAST 10TH STREET | MARSHALL STREET TO PARKE AVENUE IN ROANOKE RAPIDS. CONSTRUCT SIDEWALK ON BOTH SIDES OF ROAD. | 4 | Peanut Belt RPO |  | DIVISION 4 |  | L | CONSTRUCTION | 40000 | FY 2025: 40000
EB-5843 | BIKE/PED | EAST 10TH STREET | MARSHALL STREET TO PARKE AVENUE IN ROANOKE RAPIDS. CONSTRUCT SIDEWALK ON BOTH SIDES OF ROAD. | 4 | Peanut Belt RPO |  | DIVISION 4 |  | TA5200 | CONSTRUCTION | 160000 | FY 2025: 160000
EB-5844 | BIKE/PED | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | L | CONSTRUCTION | 33000 | FY 2024: 33000
EB-5844 | BIKE/PED | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | TAANY | RIGHT-OF-WAY | 320000 | FY 2023: 320000
EB-5844 | BIKE/PED | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | TAANY | CONSTRUCTION | 936000 | FY 2024: 936000
EB-5844 | BIKE/PED | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | L | CONSTRUCTION | 234000 | FY 2024: 234000
EB-5844 | BIKE/PED | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | L | RIGHT-OF-WAY | 80000 | FY 2023: 80000
EB-5844 | BIKE/PED | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  |  |  | 664000
EB-5844 | BIKE/PED | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 131000 | FY 2024: 131000
EB-5845 | BIKE/PED | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | L | ENGINEERING | 38000
EB-5845 | BIKE/PED | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | L | RIGHT-OF-WAY | 32000 | FY 2023: 32000
EB-5845 | BIKE/PED | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | L | CONSTRUCTION | 86000 | FY 2024: 86000
EB-5845 | BIKE/PED | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | TA5200 | ENGINEERING | 154000
EB-5845 | BIKE/PED | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | TA5200 | RIGHT-OF-WAY | 129000 | FY 2023: 129000
EB-5845 | BIKE/PED | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | TA5200 | CONSTRUCTION | 344000 | FY 2024: 344000
EB-5848 | BIKE/PED | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | 1 | Albemarle RPO |  | DIVISION 1 |  | L | CONSTRUCTION | 256000 | FY 2025: 256000
EB-5848 | BIKE/PED | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | 1 | Albemarle RPO |  | DIVISION 1 |  | TALT5 | CONSTRUCTION | 1024000 | FY 2025: 1024000
EB-5850 | BIKE/PED | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | L | ENGINEERING | 4000 | FY 2024: 4000
EB-5850 | BIKE/PED | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | TA5200 | CONSTRUCTION | 101000 | FY 2025: 101000
EB-5850 | BIKE/PED | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | TA5200 | ENGINEERING | 15000 | FY 2024: 15000
EB-5850 | BIKE/PED | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 26000 | FY 2025: 26000
EB-5857 | BIKE/PED | STANFIELD | NC 200, NORTH LOVE CHAPEL TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | ENGINEERING | 19000
EB-5857 | BIKE/PED | STANFIELD | NC 200, NORTH LOVE CHAPEL TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | RIGHT-OF-WAY | 58000
EB-5857 | BIKE/PED | STANFIELD | NC 200, NORTH LOVE CHAPEL TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | CONSTRUCTION | 148000 | FY 2023: 1000; FY 2024: 147000
EB-5857 | BIKE/PED | STANFIELD | NC 200, NORTH LOVE CHAPEL TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | TALT5 | ENGINEERING | 76000
EB-5857 | BIKE/PED | STANFIELD | NC 200, NORTH LOVE CHAPEL TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | TALT5 | RIGHT-OF-WAY | 232000
EB-5857 | BIKE/PED | STANFIELD | NC 200, NORTH LOVE CHAPEL TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | TALT5 | CONSTRUCTION | 592000 | FY 2023: 6000; FY 2024: 586000
EB-5858 | BIKE/PED | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | TA5200 | UTILITIES | 112000
EB-5858 | BIKE/PED | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | TA5200 | CONSTRUCTION | 960000
EB-5858 | BIKE/PED | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | TA5200 | RIGHT-OF-WAY | 16000
EB-5858 | BIKE/PED | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | TA5200 | ENGINEERING | 656000
EB-5858 | BIKE/PED | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | L | UTILITIES | 28000
EB-5858 | BIKE/PED | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | L | RIGHT-OF-WAY | 4000
EB-5858 | BIKE/PED | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | L | ENGINEERING | 164000
EB-5858 | BIKE/PED | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | L | CONSTRUCTION | 240000
EB-5859 | BIKE/PED | HAZELWOOD AVENUE (PLOTT CREEK ROAD) | HAZELWOOD AVENUE (PLOTT CREEK ROAD), RICHLAND CREEK BRIDGE TO WILL HYATT ROAD. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 14 | French Broad River MPO | UNDER CONSTRUCTION | DIVISION 14 |  |  |  | 183000
EB-5860 | BIKE/PED | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | CONSTRUCTION | 260000 | FY 2026: 260000
EB-5860 | BIKE/PED | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 14 | French Broad River MPO |  | DIVISION 14 |  | TAANY | CONSTRUCTION | 1040000 | FY 2026: 1040000
EB-5860 | BIKE/PED | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 14 | French Broad River MPO |  | DIVISION 14 |  | TAANY | UTILITIES | 28000 | FY 2025: 28000
EB-5860 | BIKE/PED | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 14 | French Broad River MPO |  | DIVISION 14 |  | TAANY | ENGINEERING | 96000 | FY 2024: 96000
EB-5860 | BIKE/PED | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | UTILITIES | 7000 | FY 2025: 7000
EB-5860 | BIKE/PED | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | RIGHT-OF-WAY | 9000 | FY 2025: 9000
EB-5860 | BIKE/PED | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | ENGINEERING | 24000 | FY 2024: 24000
EB-5860 | BIKE/PED | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 14 | French Broad River MPO |  | DIVISION 14 |  | TAANY | RIGHT-OF-WAY | 36000 | FY 2025: 36000
EB-5861 | BIKE/PED | THIRD STREET GREENWAY | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | ENGINEERING | 37000 | FY 2023: 37000
EB-5861 | BIKE/PED | THIRD STREET GREENWAY | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 857000 | FY 2024: 857000
EB-5861 | BIKE/PED | THIRD STREET GREENWAY | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | TAANY | ENGINEERING | 148000 | FY 2023: 148000
EB-5861 | BIKE/PED | THIRD STREET GREENWAY | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | TAANY | CONSTRUCTION | 3430000 | FY 2024: 3430000
EB-5862 | BIKE/PED | INDUSTRIAL PARK AVENUE | RANDOLPH COMMUNITY COLLEGE ENTRANCE TO CONTINUING EDUCATION AND INDUSTRIAL CENTER IN ASHEBORO. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 29000
EB-5862 | BIKE/PED | INDUSTRIAL PARK AVENUE | RANDOLPH COMMUNITY COLLEGE ENTRANCE TO CONTINUING EDUCATION AND INDUSTRIAL CENTER IN ASHEBORO. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 118000
EB-5862 | BIKE/PED | INDUSTRIAL PARK AVENUE | RANDOLPH COMMUNITY COLLEGE ENTRANCE TO CONTINUING EDUCATION AND INDUSTRIAL CENTER IN ASHEBORO. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  |  |  | 20000
EB-5863 | BIKE/PED | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 30000 | FY 2023: 30000
EB-5863 | BIKE/PED | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 294000 | FY 2024: 294000
EB-5863 | BIKE/PED | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 236000
EB-5863 | BIKE/PED | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 120000 | FY 2023: 120000
EB-5863 | BIKE/PED | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 1175000 | FY 2024: 1175000
EB-5863 | BIKE/PED | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | ENGINEERING | 59000
EB-5864 | BIKE/PED | KNOLL ROAD | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | ENGINEERING | 38000 | FY 2023: 38000
EB-5864 | BIKE/PED | KNOLL ROAD | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 380000 | FY 2024: 380000
EB-5864 | BIKE/PED | KNOLL ROAD | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 152000 | FY 2023: 152000
EB-5864 | BIKE/PED | KNOLL ROAD | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 1520000 | FY 2024: 1520000
EB-5865 | BIKE/PED | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 186000 | FY 2024: 186000
EB-5865 | BIKE/PED | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 744000 | FY 2024: 744000
EB-5865 | BIKE/PED | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | UTILITIES | 72000 | FY 2023: 72000
EB-5865 | BIKE/PED | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 61000
EB-5865 | BIKE/PED | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 20000 | FY 2023: 20000
EB-5865 | BIKE/PED | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | ENGINEERING | 15000
EB-5865 | BIKE/PED | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 80000 | FY 2023: 80000
EB-5865 | BIKE/PED | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | UTILITIES | 18000 | FY 2023: 18000
EB-5867 | BIKE/PED | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 203000 | FY 2024: 203000
EB-5867 | BIKE/PED | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 812000 | FY 2024: 812000
EB-5867 | BIKE/PED | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | UTILITIES | 72000 | FY 2023: 72000
EB-5867 | BIKE/PED | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 119000
EB-5867 | BIKE/PED | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | UTILITIES | 18000 | FY 2023: 18000
EB-5867 | BIKE/PED | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 17000 | FY 2023: 17000
EB-5867 | BIKE/PED | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | ENGINEERING | 30000
EB-5867 | BIKE/PED | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 85000 | FY 2023: 85000
EB-5868 | BIKE/PED | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 89000 | FY 2024: 89000
EB-5868 | BIKE/PED | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | UTILITIES | 80000 | FY 2024: 80000
EB-5868 | BIKE/PED | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 884000 | FY 2025: 884000
EB-5868 | BIKE/PED | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 93000 | FY 2023: 93000
EB-5868 | BIKE/PED | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 221000 | FY 2025: 221000
EB-5868 | BIKE/PED | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | ENGINEERING | 23000 | FY 2023: 23000
EB-5868 | BIKE/PED | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 22000 | FY 2024: 22000
EB-5868 | BIKE/PED | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | UTILITIES | 20000 | FY 2024: 20000
EB-5869 | BIKE/PED | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 24000 | FY 2023: 24000
EB-5869 | BIKE/PED | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 8 |  | TA5200 | CONSTRUCTION | 240000 | FY 2024: 240000
EB-5869 | BIKE/PED | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 8 |  | L | CONSTRUCTION | 60000 | FY 2024: 60000
EB-5869 | BIKE/PED | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 8 |  | L | RIGHT-OF-WAY | 6000 | FY 2023: 6000
EB-5869 | BIKE/PED | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 8 |  |  |  | 34000
EB-5870 | BIKE/PED | SR 1579 (SOUTH MAIN STREET) | SR 1531 (MANSFIELD DRIVE) TO END OF EXISTING SIDEWALK IN BROADWAY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 17000 | FY 2023: 17000
EB-5870 | BIKE/PED | SR 1579 (SOUTH MAIN STREET) | SR 1531 (MANSFIELD DRIVE) TO END OF EXISTING SIDEWALK IN BROADWAY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TALT5 | CONSTRUCTION | 69000 | FY 2023: 69000
EB-5870 | BIKE/PED | SR 1579 (SOUTH MAIN STREET) | SR 1531 (MANSFIELD DRIVE) TO END OF EXISTING SIDEWALK IN BROADWAY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  |  |  | 10000
EB-5872 | BIKE/PED | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE, AND PROVIDE PEDESTRIAN ACCOMMODATIONS AT US 15 / US 401 / US 501 INTERSECTION AND ACROSS US 74. | 8 | Lumber River RPO | PROJECT LENGTH REFLECTS PARTS A ONLY- PART B IS NON-STI PROJECT; EB 5872C PROJECT BREAK DELETED WORK TO BE ACCOMPLISHED UNDER EB-5872A. | DIVISION 8 |  |  |  | 87000
EB-5872A | BIKE/PED | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 348000 | FY 2024: 348000
EB-5872A | BIKE/PED | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 33000 | FY 2024: 33000
EB-5872A | BIKE/PED | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 88000 | FY 2024: 88000
EB-5872A | BIKE/PED | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 133000 | FY 2024: 133000
EB-5873 | BIKE/PED | SR 1278 (SOUTH COLLEGE DRIVE) | SR 1300 (EAST GREEN DRIVE) TO SR 1113 (EAST KIVETT DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | TA5200 | CONSTRUCTION | 288000 | FY 2023: 288000
EB-5873 | BIKE/PED | SR 1278 (SOUTH COLLEGE DRIVE) | SR 1300 (EAST GREEN DRIVE) TO SR 1113 (EAST KIVETT DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 72000 | FY 2023: 72000
EB-5874 | BIKE/PED | NC 68 (EASTCHESTER DRIVE) | JOHNSON STREET TO SR 1278 (NORTH COLLEGE DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 126000 | FY 2023: 126000
EB-5874 | BIKE/PED | NC 68 (EASTCHESTER DRIVE) | JOHNSON STREET TO SR 1278 (NORTH COLLEGE DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | TA50200 | CONSTRUCTION | 504000 | FY 2023: 504000
EB-5876 | BIKE/PED | HOLDEN ROAD | SR 4121 (WEST GATE CITY BOULEVARD) TO NORTH OF SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION BY CITY OF GREENSBORO | DIVISION 7 |  |  |  | 393000
EB-5877 | BIKE/PED | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWLAKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 20000
EB-5877 | BIKE/PED | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWLAKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TAANY | CONSTRUCTION | 240000 | FY 2023: 240000
EB-5877 | BIKE/PED | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWLAKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 60000 | FY 2023: 60000
EB-5877 | BIKE/PED | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWLAKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | RIGHT-OF-WAY | 5000
EB-5877 | BIKE/PED | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWLAKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 86000
EB-5878 | BIKE/PED | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | RIGHT-OF-WAY | 35000
EB-5878 | BIKE/PED | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 52000 | FY 2023: 52000
EB-5878 | BIKE/PED | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 140000
EB-5878 | BIKE/PED | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TAANY | CONSTRUCTION | 207000 | FY 2023: 207000
EB-5878 | BIKE/PED | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 18000
EB-5879 | BIKE/PED | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | TA5200 | ENGINEERING | 13000
EB-5879 | BIKE/PED | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | TA5200 | CONSTRUCTION | 53000 | FY 2024: 53000
EB-5879 | BIKE/PED | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | TA5200 | RIGHT-OF-WAY | 22000 | FY 2024: 22000
EB-5879 | BIKE/PED | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 6000 | FY 2024: 6000
EB-5879 | BIKE/PED | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | L | ENGINEERING | 3000
EB-5879 | BIKE/PED | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  |  |  | 16000
EB-5879 | BIKE/PED | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 13000 | FY 2024: 13000
EB-5880 | BIKE/PED | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | ENGINEERING | 18000 | FY 2023: 18000
EB-5880 | BIKE/PED | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 6000 | FY 2024: 6000
EB-5880 | BIKE/PED | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 88000 | FY 2025: 88000
EB-5880 | BIKE/PED | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | TAANY | ENGINEERING | 71000 | FY 2023: 71000
EB-5880 | BIKE/PED | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 25000 | FY 2024: 25000
EB-5880 | BIKE/PED | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 353000 | FY 2025: 353000
EB-5883 | BIKE/PED | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 2249000 | FY 2024: 2249000
EB-5883 | BIKE/PED | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  |  |  | 381000
EB-5883 | BIKE/PED | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 59000 | FY 2023: 59000
EB-5883 | BIKE/PED | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 562000 | FY 2024: 562000
EB-5883 | BIKE/PED | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 237000 | FY 2023: 237000
EB-5885 | BIKE/PED | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 24000 | FY 2023: 24000
EB-5885 | BIKE/PED | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | TA5200 | CONSTRUCTION | 96000 | FY 2023: 96000
EB-5886A | BIKE/PED | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | L | ENGINEERING | 34000
EB-5886A | BIKE/PED | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | L | RIGHT-OF-WAY | 9000 | FY 2024: 9000
EB-5886A | BIKE/PED | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | L | CONSTRUCTION | 170000 | FY 2026: 2000; FY 2027: 168000
EB-5886A | BIKE/PED | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | TAANY | ENGINEERING | 136000
EB-5886A | BIKE/PED | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 37000 | FY 2024: 37000
EB-5886A | BIKE/PED | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | TAANY | CONSTRUCTION | 678000 | FY 2026: 7000; FY 2027: 671000
EB-5886B | BIKE/PED | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | L | ENGINEERING | 107000
EB-5886B | BIKE/PED | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | L | RIGHT-OF-WAY | 173000 | FY 2023: 173000
EB-5886B | BIKE/PED | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | L | CONSTRUCTION | 621000 | FY 2025: 6000; FY 2026: 542000; FY 2027: 73000
EB-5886B | BIKE/PED | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | TAANY | ENGINEERING | 427000
EB-5886B | BIKE/PED | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 691000 | FY 2023: 691000
EB-5886B | BIKE/PED | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | DIVISION 7 |  | TAANY | CONSTRUCTION | 2483000 | FY 2025: 25000; FY 2026: 2165000; FY 2027: 293000
EB-5888 | BIKE/PED | SR 1747 (EAST STADIUM DRIVE) | SR 1962 (NORTH PIERCE STREET) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | TA5200 | CONSTRUCTION | 354000 | FY 2023: 201000; FY 2024: 153000
EB-5888 | BIKE/PED | SR 1747 (EAST STADIUM DRIVE) | SR 1962 (NORTH PIERCE STREET) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  |  |  | 124000
EB-5888 | BIKE/PED | SR 1747 (EAST STADIUM DRIVE) | SR 1962 (NORTH PIERCE STREET) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | L | CONSTRUCTION | 89000 | FY 2023: 51000; FY 2024: 38000
EB-5889 | BIKE/PED | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 100000 | FY 2023: 100000
EB-5889 | BIKE/PED | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | TA5200 | CONSTRUCTION | 400000 | FY 2023: 400000
EB-5890 | BIKE/PED | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | ENGINEERING | 9000 | FY 2023: 9000
EB-5890 | BIKE/PED | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 3000 | FY 2024: 3000
EB-5890 | BIKE/PED | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 46000 | FY 2025: 46000
EB-5890 | BIKE/PED | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | TAANY | ENGINEERING | 37000 | FY 2023: 37000
EB-5890 | BIKE/PED | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 13000 | FY 2024: 13000
EB-5890 | BIKE/PED | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 184000 | FY 2025: 184000
EB-5891 | BIKE/PED | US 220 BUSINESS | EAST JACKSON STREET IN MAYODAN TO MAYO RIVER STATE PARK. CONSTRUCT MULTI-USE PATH. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  |  |  | 130000
EB-5891 | BIKE/PED | US 220 BUSINESS | EAST JACKSON STREET IN MAYODAN TO MAYO RIVER STATE PARK. CONSTRUCT MULTI-USE PATH. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | L | CONSTRUCTION | 130000 | FY 2024: 130000
EB-5891 | BIKE/PED | US 220 BUSINESS | EAST JACKSON STREET IN MAYODAN TO MAYO RIVER STATE PARK. CONSTRUCT MULTI-USE PATH. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | TALT5 | CONSTRUCTION | 522000 | FY 2024: 522000
EB-5894 | BIKE/PED | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | DIVISION 5 |  | CMAQ | CONSTRUCTION | 985000 | FY 2023: 985000
EB-5894 | BIKE/PED | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | DIVISION 5 |  | TAANY | CONSTRUCTION | 6615000 | FY 2023: 6615000
EB-5894 | BIKE/PED | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | DIVISION 5 |  |  |  | 10000
EB-5894 | BIKE/PED | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 246000 | FY 2023: 246000
EB-5894 | BIKE/PED | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 1654000 | FY 2023: 1654000
EB-5895 | BIKE/PED | NC 55 (EAST WILLIAMS STREET) | SR 1301 (SUNSET LAKE ROAD) TO NC 55 IN HOLLY SPRINGS. CONSTRUCT SIDEWALK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  |  |  | 100000
EB-5895 | BIKE/PED | NC 55 (EAST WILLIAMS STREET) | SR 1301 (SUNSET LAKE ROAD) TO NC 55 IN HOLLY SPRINGS. CONSTRUCT SIDEWALK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | CONSTRUCTION | 100000
EB-5895 | BIKE/PED | NC 55 (EAST WILLIAMS STREET) | SR 1301 (SUNSET LAKE ROAD) TO NC 55 IN HOLLY SPRINGS. CONSTRUCT SIDEWALK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | TAANY | CONSTRUCTION | 400000
EB-5898 | BIKE/PED | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 5000 | FY 2024: 5000
EB-5898 | BIKE/PED | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 206000 | FY 2024: 206000
EB-5898 | BIKE/PED | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 52000 | FY 2024: 52000
EB-5898 | BIKE/PED | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  |  |  | 50000
EB-5898 | BIKE/PED | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 20000 | FY 2024: 20000
EB-5899 | BIKE/PED | NC 731 (EAST ALLENTON STREET) | EXISTING SIDEWALK ON NC 731 TO STANBECK PARK IN MT. GILEAD. CONSTRUCT SIDEWALK. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  |  |  | 14000
EB-5899 | BIKE/PED | NC 731 (EAST ALLENTON STREET) | EXISTING SIDEWALK ON NC 731 TO STANBECK PARK IN MT. GILEAD. CONSTRUCT SIDEWALK. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 55000 | FY 2023: 55000
EB-5899 | BIKE/PED | NC 731 (EAST ALLENTON STREET) | EXISTING SIDEWALK ON NC 731 TO STANBECK PARK IN MT. GILEAD. CONSTRUCT SIDEWALK. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | TALT5 | CONSTRUCTION | 222000 | FY 2023: 222000
EB-5900 | BIKE/PED | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 780000 | FY 2024: 780000
EB-5900 | BIKE/PED | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 312000 | FY 2023: 312000
EB-5900 | BIKE/PED | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 78000 | FY 2023: 78000
EB-5900 | BIKE/PED | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 3120000 | FY 2024: 3120000
EB-5902 | BIKE/PED | CONCORD | DOWNTOWN PEDESTRIAN SIGNAL UPGRADES. | 10 | Cabarrus-Rowan MPO | COMPLETE. | DIVISION 10 |  | L | CONSTRUCTION | 62000
EB-5902 | BIKE/PED | CONCORD | DOWNTOWN PEDESTRIAN SIGNAL UPGRADES. | 10 | Cabarrus-Rowan MPO | COMPLETE. | DIVISION 10 |  | TADA | CONSTRUCTION | 250000
EB-5903 | BIKE/PED | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. | 10 | Cabarrus-Rowan MPO | COMPLETE. | DIVISION 10 |  | L | CONSTRUCTION | 93000
EB-5903 | BIKE/PED | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. | 10 | Cabarrus-Rowan MPO | COMPLETE. | DIVISION 10 |  | TADA | CONSTRUCTION | 320000
EB-5903 | BIKE/PED | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. | 10 | Cabarrus-Rowan MPO | COMPLETE. | DIVISION 10 |  | L | CONSTRUCTION | 80000
EB-5903 | BIKE/PED | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. | 10 | Cabarrus-Rowan MPO | COMPLETE. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 373000
EB-5903 | BIKE/PED | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. | 10 | Cabarrus-Rowan MPO | COMPLETE. | DIVISION 10 |  |  |  | 10000
EB-5904 | BIKE/PED | DURHAM BELTLINE TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | DIVISION 5 |  | BGDA | CONSTRUCTION | 1863000 | FY 2023: 1863000
EB-5904 | BIKE/PED | DURHAM BELTLINE TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | DIVISION 5 |  | DP | CONSTRUCTION | 9000000 | FY 2023: 9000000
EB-5904 | BIKE/PED | DURHAM BELTLINE TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | DIVISION 5 |  | L | CONSTRUCTION | 6016000 | FY 2023: 6016000
EB-5904 | BIKE/PED | DURHAM BELTLINE TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | DIVISION 5 |  | TAANY | CONSTRUCTION | 120000 | FY 2023: 120000
EB-5904 | BIKE/PED | DURHAM BELTLINE TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | DIVISION 5 |  | TADA | CONSTRUCTION | 410000 | FY 2023: 410000
EB-5904 | BIKE/PED | DURHAM BELTLINE TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | DIVISION 5 |  |  |  | 14031000
EB-5905 | BIKE/PED | US 64 BUSINESS (THOMAS STREET) | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | BG5200 | CONSTRUCTION | 96000 | FY 2027: 96000
EB-5905 | BIKE/PED | US 64 BUSINESS (THOMAS STREET) | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 24000 | FY 2027: 24000
EB-5907 | BIKE/PED | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | RIGHT-OF-WAY | 2000 | FY 2024: 2000
EB-5907 | BIKE/PED | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | CONSTRUCTION | 168000 | FY 2026: 168000
EB-5907 | BIKE/PED | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TAANY | ENGINEERING | 67000 | FY 2023: 67000
EB-5907 | BIKE/PED | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TAANY | RIGHT-OF-WAY | 8000 | FY 2024: 8000
EB-5907 | BIKE/PED | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TAANY | CONSTRUCTION | 674000 | FY 2026: 674000
EB-5907 | BIKE/PED | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | ENGINEERING | 17000 | FY 2023: 17000
EB-5911 | BIKE/PED | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | DIVISION 12 |  |  |  | 1272000
EB-5911 | BIKE/PED | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | DIVISION 12 |  | TAANY | CONSTRUCTION | 6498000 | FY 2023: 6498000
EB-5911 | BIKE/PED | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | DIVISION 12 |  | TAANY | RIGHT-OF-WAY | 964000
EB-5911 | BIKE/PED | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | DIVISION 12 |  | L | RIGHT-OF-WAY | 241000
EB-5911 | BIKE/PED | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | DIVISION 12 |  | L | CONSTRUCTION | 1625000 | FY 2023: 1625000
EB-5912 | BIKE/PED | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TAANY | ENGINEERING | 349000 | FY 2023: 349000
EB-5912 | BIKE/PED | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | ENGINEERING | 87000 | FY 2023: 87000
EB-5912 | BIKE/PED | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TAANY | CONSTRUCTION | 1396000 | FY 2027: 1396000
EB-5912 | BIKE/PED | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TAANY | RIGHT-OF-WAY | 582000 | FY 2025: 582000
EB-5912 | BIKE/PED | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 145000 | FY 2025: 145000
EB-5912 | BIKE/PED | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 288000
EB-5912 | BIKE/PED | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 349000 | FY 2027: 349000
EB-5913 | BIKE/PED | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | ENGINEERING | 33000 | FY 2023: 33000
EB-5913 | BIKE/PED | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 71000 | FY 2025: 71000
EB-5913 | BIKE/PED | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TAANY | ENGINEERING | 131000 | FY 2023: 131000
EB-5913 | BIKE/PED | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TAANY | CONSTRUCTION | 283000 | FY 2025: 283000
EB-5915 | BIKE/PED | THERMAL BELT RAIL TRAIL | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | 13 | Foothills RPO | UNDER CONSTRUCTION. | DIVISION 13 |  | L | CONSTRUCTION | 91000
EB-5915 | BIKE/PED | THERMAL BELT RAIL TRAIL | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | 13 | Foothills RPO | UNDER CONSTRUCTION. | DIVISION 13 |  | TA5200 | CONSTRUCTION | 364000
EB-5916 | BIKE/PED | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | RIGHT-OF-WAY | 60000 | FY 2023: 60000
EB-5916 | BIKE/PED | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | CONSTRUCTION | 2450000 | FY 2024: 2450000
EB-5916 | BIKE/PED | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | ENGINEERING | 288000
EB-5916 | BIKE/PED | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | ENGINEERING | 160000
EB-5916 | BIKE/PED | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | 13 | Foothills RPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 15000 | FY 2023: 15000
EB-5916 | BIKE/PED | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | 13 | Foothills RPO |  | DIVISION 13 |  | L | ENGINEERING | 40000
EB-5916 | BIKE/PED | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | 13 | Foothills RPO |  | DIVISION 13 |  | L | ENGINEERING | 72000
EB-5916 | BIKE/PED | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | 13 | Foothills RPO |  | DIVISION 13 |  | L | CONSTRUCTION | 613000 | FY 2024: 613000
EB-5918 | BIKE/PED | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | 13 | Land-of-Sky RPO |  | DIVISION 13 |  | L | CONSTRUCTION | 30000 | FY 2024: 30000
EB-5918 | BIKE/PED | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | 13 | Land-of-Sky RPO |  | DIVISION 13 |  | TALT5 | ENGINEERING | 36000 | FY 2023: 36000
EB-5918 | BIKE/PED | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | 13 | Land-of-Sky RPO |  | DIVISION 13 |  | TALT5 | CONSTRUCTION | 120000 | FY 2024: 120000
EB-5918 | BIKE/PED | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | 13 | Land-of-Sky RPO |  | DIVISION 13 |  | L | ENGINEERING | 9000 | FY 2023: 9000
EB-5920 | BIKE/PED | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 10000
EB-5920 | BIKE/PED | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | CONSTRUCTION | 468000 | FY 2025: 468000
EB-5920 | BIKE/PED | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | UTILITIES | 68000 | FY 2024: 68000
EB-5920 | BIKE/PED | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | RIGHT-OF-WAY | 64000 | FY 2024: 64000
EB-5920 | BIKE/PED | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | ENGINEERING | 40000
EB-5920 | BIKE/PED | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 117000 | FY 2025: 117000
EB-5920 | BIKE/PED | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 16000 | FY 2024: 16000
EB-5920 | BIKE/PED | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | UTILITIES | 17000 | FY 2024: 17000
EB-5921 | BIKE/PED | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | DIVISION 9 |  | TAANY | ENGINEERING | 360000 | FY 2027: 360000
EB-5921 | BIKE/PED | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | DIVISION 9 |  | L | CONSTRUCTION | 420000 | FY 2031: 420000
EB-5921 | BIKE/PED | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | DIVISION 9 |  | TAANY | CONSTRUCTION | 1680000 | FY 2031: 1680000
EB-5921 | BIKE/PED | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | DIVISION 9 |  | L | ENGINEERING | 90000 | FY 2027: 90000
EB-5921 | BIKE/PED | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | DIVISION 9 |  | L | RIGHT-OF-WAY | 126000 | FY 2028: 126000
EB-5921 | BIKE/PED | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | DIVISION 9 |  | TAANY | RIGHT-OF-WAY | 504000 | FY 2028: 504000
EB-5922 | BIKE/PED | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 27000 | FY 2025: 27000
EB-5922 | BIKE/PED | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | TA5200 | CONSTRUCTION | 108000 | FY 2025: 108000
EB-5923 | BIKE/PED | SR 1432 (SKYLAND DRIVE) | SR 1429 (CHIPPER CURVE ROAD) TO US 23 BUSINESS. CONSTRUCT SIDEWALK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | TALT5 | CONSTRUCTION | 768000 | FY 2023: 768000
EB-5923 | BIKE/PED | SR 1432 (SKYLAND DRIVE) | SR 1429 (CHIPPER CURVE ROAD) TO US 23 BUSINESS. CONSTRUCT SIDEWALK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  |  |  | 110000
EB-5923 | BIKE/PED | SR 1432 (SKYLAND DRIVE) | SR 1429 (CHIPPER CURVE ROAD) TO US 23 BUSINESS. CONSTRUCT SIDEWALK. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | L | CONSTRUCTION | 192000 | FY 2023: 192000
EB-5924 | BIKE/PED | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF S(M) IS CONTINGENCY FUNDS ON WBS 44607 | EXEMPT |  | S(M) | CONSTRUCTION | 145000 | FY 2024: 145000
EB-5924 | BIKE/PED | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF S(M) IS CONTINGENCY FUNDS ON WBS 44607 | EXEMPT |  | L | CONSTRUCTION | 245000 | FY 2024: 245000
EB-5924 | BIKE/PED | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF S(M) IS CONTINGENCY FUNDS ON WBS 44607 | EXEMPT |  | L | RIGHT-OF-WAY | 17000 | FY 2023: 17000
EB-5924 | BIKE/PED | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF S(M) IS CONTINGENCY FUNDS ON WBS 44607 | EXEMPT |  | FLAP | CONSTRUCTION | 1624000 | FY 2024: 1624000
EB-5924 | BIKE/PED | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF S(M) IS CONTINGENCY FUNDS ON WBS 44607 | EXEMPT |  |  |  | 118000
EB-5924 | BIKE/PED | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF S(M) IS CONTINGENCY FUNDS ON WBS 44607 | EXEMPT |  | FLAP | RIGHT-OF-WAY | 73000 | FY 2023: 73000
EB-5926 | BIKE/PED | US 19 (SOCO ROAD) | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 14 | French Broad River MPO | UNDER CONSTRUCTION. $1.44M IN BGANY USED AS PART OF FUND SWAP; $80K ADDED AS ADMINISTRATIVE MODIFICATION. | DIVISION 14 |  | L | CONSTRUCTION | 380000 | FY 2023: 69000
EB-5926 | BIKE/PED | US 19 (SOCO ROAD) | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 14 | French Broad River MPO | UNDER CONSTRUCTION. $1.44M IN BGANY USED AS PART OF FUND SWAP; $80K ADDED AS ADMINISTRATIVE MODIFICATION. | DIVISION 14 |  | BGANY | CONSTRUCTION | 1520000 | FY 2023: 278000
EB-5926 | BIKE/PED | US 19 (SOCO ROAD) | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 14 | French Broad River MPO | UNDER CONSTRUCTION. $1.44M IN BGANY USED AS PART OF FUND SWAP; $80K ADDED AS ADMINISTRATIVE MODIFICATION. | DIVISION 14 |  |  |  | 175000
EB-5929 | BIKE/PED | CHARLOTTE | BELK GREENWAY CONNECTOR PHASE ONE. EAST STONEWALL STREET AT SOUTH DAVIDSON STREET TO SOUTH KINGS DRIVE. | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | RIGHT-OF-WAY | 69000
EB-5929 | BIKE/PED | CHARLOTTE | BELK GREENWAY CONNECTOR PHASE ONE. EAST STONEWALL STREET AT SOUTH DAVIDSON STREET TO SOUTH KINGS DRIVE. | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1090000 | FY 2025: 1090000
EB-5929 | BIKE/PED | CHARLOTTE | BELK GREENWAY CONNECTOR PHASE ONE. EAST STONEWALL STREET AT SOUTH DAVIDSON STREET TO SOUTH KINGS DRIVE. | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 30000
EB-5929 | BIKE/PED | CHARLOTTE | BELK GREENWAY CONNECTOR PHASE ONE. EAST STONEWALL STREET AT SOUTH DAVIDSON STREET TO SOUTH KINGS DRIVE. | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 467000 | FY 2025: 467000
EB-5929 | BIKE/PED | CHARLOTTE | BELK GREENWAY CONNECTOR PHASE ONE. EAST STONEWALL STREET AT SOUTH DAVIDSON STREET TO SOUTH KINGS DRIVE. | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  |  |  | 557000
EB-5930 | BIKE/PED | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | ENGINEERING | 109000
EB-5930 | BIKE/PED | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | TADA | CONSTRUCTION | 1055000 | FY 2023: 1055000
EB-5930 | BIKE/PED | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | TADA | RIGHT-OF-WAY | 129000
EB-5930 | BIKE/PED | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | TADA | ENGINEERING | 203000
EB-5930 | BIKE/PED | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 70000
EB-5930 | BIKE/PED | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  |  |  | 170000
EB-5930 | BIKE/PED | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | CONSTRUCTION | 568000 | FY 2023: 568000
EB-5931 | BIKE/PED | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | BGDA | ENGINEERING | 313000
EB-5931 | BIKE/PED | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | L | CONSTRUCTION | 723000 | FY 2023: 723000
EB-5931 | BIKE/PED | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | L | CONSTRUCTION | 1180000 | FY 2023: 1180000
EB-5931 | BIKE/PED | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | L | RIGHT-OF-WAY | 52000 | FY 2023: 52000
EB-5931 | BIKE/PED | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 208000 | FY 2023: 208000
EB-5931 | BIKE/PED | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 4719000 | FY 2023: 4719000
EB-5931 | BIKE/PED | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | DIVISION 10 |  | L | ENGINEERING | 78000
EB-5932 | BIKE/PED | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | TADA | ENGINEERING | 97000
EB-5932 | BIKE/PED | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | TADA | RIGHT-OF-WAY | 174000
EB-5932 | BIKE/PED | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | CONSTRUCTION | 250000 | FY 2023: 250000
EB-5932 | BIKE/PED | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | RIGHT-OF-WAY | 43000
EB-5932 | BIKE/PED | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | ENGINEERING | 25000
EB-5932 | BIKE/PED | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  |  |  | 80000
EB-5932 | BIKE/PED | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | TADA | CONSTRUCTION | 1000000 | FY 2023: 1000000
EB-5933 | BIKE/PED | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  |  |  | 220000
EB-5933 | BIKE/PED | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 702000 | FY 2024: 702000
EB-5933 | BIKE/PED | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 176000 | FY 2024: 176000
EB-5935 | BIKE/PED | CLAREMONT | CONSTRUCT SIDEWALK ALONG CENTENNIAL BOULEVARD FROM NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II). | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | L | CONSTRUCTION | 120000 | FY 2024: 120000
EB-5935 | BIKE/PED | CLAREMONT | CONSTRUCT SIDEWALK ALONG CENTENNIAL BOULEVARD FROM NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II). | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | BGANY | CONSTRUCTION | 480000 | FY 2024: 480000
EB-5937 | BIKE/PED | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | DIVISION 12 |  | TADA | RIGHT-OF-WAY | 180000
EB-5937 | BIKE/PED | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | DIVISION 12 |  | L | CONSTRUCTION | 355000 | FY 2023: 355000
EB-5937 | BIKE/PED | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | DIVISION 12 |  | L | RIGHT-OF-WAY | 45000
EB-5937 | BIKE/PED | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | DIVISION 12 |  |  |  | 400000
EB-5937 | BIKE/PED | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | DIVISION 12 |  | BGANY | CONSTRUCTION | 1420000 | FY 2023: 1420000
EB-5938 | BIKE/PED | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  |  |  | 640000
EB-5938 | BIKE/PED | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | BGANY | CONSTRUCTION | 2400000 | FY 2023: 2400000
EB-5938 | BIKE/PED | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | L | RIGHT-OF-WAY | 21000
EB-5938 | BIKE/PED | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | L | CONSTRUCTION | 619000 | FY 2023: 619000
EB-5938 | BIKE/PED | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | TADA | RIGHT-OF-WAY | 84000
EB-5938 | BIKE/PED | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | TADA | CONSTRUCTION | 76000 | FY 2023: 76000
EB-5939 | BIKE/PED | HICKORY | RIVERWALK. CONSTRUCT MULTI-USE PATH FROM OLD LENOIR ROAD AT CITY OWNED PROPERTY TO END OF PROPOSED ROSALES BRIDGE. | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 13 |  |  |  | 2500000
EB-5939 | BIKE/PED | HICKORY | RIVERWALK. CONSTRUCT MULTI-USE PATH FROM OLD LENOIR ROAD AT CITY OWNED PROPERTY TO END OF PROPOSED ROSALES BRIDGE. | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | BGDA | CONSTRUCTION | 5200000 | FY 2023: 5200000
EB-5939 | BIKE/PED | HICKORY | RIVERWALK. CONSTRUCT MULTI-USE PATH FROM OLD LENOIR ROAD AT CITY OWNED PROPERTY TO END OF PROPOSED ROSALES BRIDGE. | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | L | CONSTRUCTION | 1300000 | FY 2023: 1300000
EB-5944 | BIKE/PED | ASHEVILLE | JOHNSTON BOULEVARD, PATTON AVENUE TO IONA CIRCLE. CONSTRUCT SIDEWALKS. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGDA | CONSTRUCTION | 1880000 | FY 2023: 1880000
EB-5944 | BIKE/PED | ASHEVILLE | JOHNSTON BOULEVARD, PATTON AVENUE TO IONA CIRCLE. CONSTRUCT SIDEWALKS. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 470000 | FY 2023: 470000
EB-5945 | BIKE/PED | TOWN OF CANTON | CHAMPION DRIVE, NORTH CANTON ROAD TO THICKETY ROAD. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  |  |  | 238000
EB-5945 | BIKE/PED | TOWN OF CANTON | CHAMPION DRIVE, NORTH CANTON ROAD TO THICKETY ROAD. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | BGDA | RIGHT-OF-WAY | 307000 | FY 2023: 307000
EB-5945 | BIKE/PED | TOWN OF CANTON | CHAMPION DRIVE, NORTH CANTON ROAD TO THICKETY ROAD. CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | L | RIGHT-OF-WAY | 77000 | FY 2023: 77000
EB-5946 | BIKE/PED | TOWN OF MILLS RIVER | NC 280, FRENCH BROAD RIVER TO HAYWOOD ROAD (NC 191). CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | ENGINEERING | 75000 | FY 2026: 75000
EB-5946 | BIKE/PED | TOWN OF MILLS RIVER | NC 280, FRENCH BROAD RIVER TO HAYWOOD ROAD (NC 191). CONSTRUCT MULTI-USE PATH. | 14 | French Broad River MPO |  | DIVISION 14 |  | TADA | ENGINEERING | 300000 | FY 2026: 300000
EB-5947 | BIKE/PED | ASHEVILLE | NEW HAW CREEK ROAD, BEVERLY ROAD TO BELL ROAD. CONSTRUCT SIDEWALKS. | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | DIVISION 13 |  | BGANY | CONSTRUCTION | 1900000 | FY 2023: 1900000
EB-5947 | BIKE/PED | ASHEVILLE | NEW HAW CREEK ROAD, BEVERLY ROAD TO BELL ROAD. CONSTRUCT SIDEWALKS. | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | DIVISION 13 |  | L | CONSTRUCTION | 475000 | FY 2023: 475000
EB-5948 | BIKE/PED | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | BGDA | CONSTRUCTION | 572000 | FY 2023: 572000
EB-5948 | BIKE/PED | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | L | CONSTRUCTION | 228000 | FY 2023: 228000
EB-5948 | BIKE/PED | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | TADA | CONSTRUCTION | 340000 | FY 2023: 340000
EB-5949 | HIGHWAY | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | DIVISION 10 |  | O | CONSTRUCTION | 1141000
EB-5949 | HIGHWAY | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | DIVISION 10 |  | O | CONSTRUCTION | 1435000
EB-5949 | HIGHWAY | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | DIVISION 10 |  | L | CONSTRUCTION | 294000
EB-5949 | HIGHWAY | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | DIVISION 10 |  | BGDA | CONSTRUCTION | 1175000
EB-5949 | HIGHWAY | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | DIVISION 10 |  | L | CONSTRUCTION | 359000
EB-5950 | HIGHWAY | WAXHAW | NC 16 TO SUNSET HILL ROAD. KENSINGTON DRIVE CORRIDOR IMPROVEMENT PROJECT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGDA | CONSTRUCTION | 2749000 | FY 2024: 2749000
EB-5950 | HIGHWAY | WAXHAW | NC 16 TO SUNSET HILL ROAD. KENSINGTON DRIVE CORRIDOR IMPROVEMENT PROJECT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | L | RIGHT-OF-WAY | 170000
EB-5950 | HIGHWAY | WAXHAW | NC 16 TO SUNSET HILL ROAD. KENSINGTON DRIVE CORRIDOR IMPROVEMENT PROJECT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | L | CONSTRUCTION | 1069000 | FY 2024: 1069000
EB-5950 | HIGHWAY | WAXHAW | NC 16 TO SUNSET HILL ROAD. KENSINGTON DRIVE CORRIDOR IMPROVEMENT PROJECT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 421000
EB-5952 | BIKE/PED | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 99000
EB-5952 | BIKE/PED | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 148000 | FY 2023: 148000
EB-5952 | BIKE/PED | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | RIGHT-OF-WAY | 50000
EB-5952 | BIKE/PED | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 198000
EB-5952 | BIKE/PED | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGDA | CONSTRUCTION | 593000 | FY 2023: 593000
EB-5953 | BIKE/PED | SR 4000 (UNIVERSITY PARKWAY) | SR-1686 (SHATTALON DRIVE) TO ROBIN WOOD LANE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM | DIVISION 9 |  |  |  | 95000
EB-5953 | BIKE/PED | SR 4000 (UNIVERSITY PARKWAY) | SR-1686 (SHATTALON DRIVE) TO ROBIN WOOD LANE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM | DIVISION 9 |  | BGDA | CONSTRUCTION | 508000 | FY 2024: 508000
EB-5953 | BIKE/PED | SR 4000 (UNIVERSITY PARKWAY) | SR-1686 (SHATTALON DRIVE) TO ROBIN WOOD LANE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM | DIVISION 9 |  | L | CONSTRUCTION | 127000 | FY 2024: 127000
EB-5954 | BIKE/PED | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | RIGHT-OF-WAY | 8000 | FY 2023: 8000
EB-5954 | BIKE/PED | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 324000 | FY 2023: 324000
EB-5954 | BIKE/PED | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 34000 | FY 2023: 34000
EB-5954 | BIKE/PED | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 226000
EB-5954 | BIKE/PED | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | CONSTRUCTION | 1296000 | FY 2023: 1296000
EB-5955 | BIKE/PED | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 70000
EB-5955 | BIKE/PED | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 53000
EB-5955 | BIKE/PED | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | CONSTRUCTION | 376000 | FY 2024: 376000
EB-5955 | BIKE/PED | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | RIGHT-OF-WAY | 13000
EB-5955 | BIKE/PED | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 94000 | FY 2024: 94000
EB-5956 | BIKE/PED | SR 1992 (SULLIVANTOWN ROAD) | US 311 AT HARLEY DRIVE TO WALKERTOWN HIGH/MIDDLE SCHOOL IN WALKERTOWN. INSTALL BICYCLE AND PEDESTRIAN FACILITIES AND CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 70000
EB-5956 | BIKE/PED | SR 1992 (SULLIVANTOWN ROAD) | US 311 AT HARLEY DRIVE TO WALKERTOWN HIGH/MIDDLE SCHOOL IN WALKERTOWN. INSTALL BICYCLE AND PEDESTRIAN FACILITIES AND CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 448000 | FY 2023: 448000
EB-5956 | BIKE/PED | SR 1992 (SULLIVANTOWN ROAD) | US 311 AT HARLEY DRIVE TO WALKERTOWN HIGH/MIDDLE SCHOOL IN WALKERTOWN. INSTALL BICYCLE AND PEDESTRIAN FACILITIES AND CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 112000 | FY 2023: 112000
EB-5957 | BIKE/PED | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | RIGHT-OF-WAY | 7000
EB-5957 | BIKE/PED | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 46000 | FY 2023: 46000
EB-5957 | BIKE/PED | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 36000
EB-5957 | BIKE/PED | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 29000
EB-5957 | BIKE/PED | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGDA | CONSTRUCTION | 186000 | FY 2023: 186000
EB-5958 | BIKE/PED | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | DIVISION 9 |  | BGDA | CONSTRUCTION | 1502000
EB-5958 | BIKE/PED | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | DIVISION 9 |  | L | CONSTRUCTION | 364000
EB-5958 | BIKE/PED | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | DIVISION 9 |  | L | CONSTRUCTION | 375000
EB-5958 | BIKE/PED | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | DIVISION 9 |  | BGANY | CONSTRUCTION | 1452000
EB-5959 | BIKE/PED | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  |  |  | 110000
EB-5959 | BIKE/PED | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 129000 | FY 2025: 129000
EB-5959 | BIKE/PED | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 50000 | FY 2025: 50000
EB-5959 | BIKE/PED | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | L | ENGINEERING | 22000
EB-5959 | BIKE/PED | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | BGDA | CONSTRUCTION | 516000 | FY 2025: 516000
EB-5959 | BIKE/PED | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | BGANY | CONSTRUCTION | 202000 | FY 2025: 202000
EB-5959 | BIKE/PED | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | BGDA | ENGINEERING | 88000
EB-5960 | BIKE/PED | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | BGDA | CONSTRUCTION | 2373000 | FY 2023: 2373000
EB-5960 | BIKE/PED | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | L | ENGINEERING | 25000
EB-5960 | BIKE/PED | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 33000 | FY 2023: 33000
EB-5960 | BIKE/PED | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  |  |  | 125000
EB-5960 | BIKE/PED | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | BGANY | ENGINEERING | 100000
EB-5960 | BIKE/PED | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 593000 | FY 2023: 593000
EB-5960 | BIKE/PED | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS | DIVISION 9 |  | BGANY | CONSTRUCTION | 130000 | FY 2023: 130000
EB-5961 | BIKE/PED | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | L | ENGINEERING | 13000
EB-5961 | BIKE/PED | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | L | RIGHT-OF-WAY | 11000 | FY 2023: 11000
EB-5961 | BIKE/PED | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | L | CONSTRUCTION | 35000 | FY 2024: 35000
EB-5961 | BIKE/PED | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | TA5200 | ENGINEERING | 50000
EB-5961 | BIKE/PED | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | TA5200 | RIGHT-OF-WAY | 42000 | FY 2023: 42000
EB-5961 | BIKE/PED | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | TA5200 | CONSTRUCTION | 140000 | FY 2024: 140000
EB-5963 | BIKE/PED | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 14 | French Broad River MPO |  | DIVISION 14 |  | TAANY | RIGHT-OF-WAY | 640000 | FY 2025: 640000
EB-5963 | BIKE/PED | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 14 | French Broad River MPO |  | DIVISION 14 |  | TAANY | UTILITIES | 76000 | FY 2025: 76000
EB-5963 | BIKE/PED | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 14 | French Broad River MPO |  | DIVISION 14 |  | TAANY | ENGINEERING | 126000 | FY 2024: 126000
EB-5963 | BIKE/PED | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | CONSTRUCTION | 180000 | FY 2026: 180000
EB-5963 | BIKE/PED | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | RIGHT-OF-WAY | 160000 | FY 2025: 160000
EB-5963 | BIKE/PED | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | ENGINEERING | 31000 | FY 2024: 31000
EB-5963 | BIKE/PED | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 14 | French Broad River MPO |  | DIVISION 14 |  | TAANY | CONSTRUCTION | 720000 | FY 2026: 720000
EB-5963 | BIKE/PED | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 14 | French Broad River MPO |  | DIVISION 14 |  | L | UTILITIES | 19000 | FY 2025: 19000
EB-5964 | BIKE/PED | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 14 | Southwestern RPO |  | DIVISION 14 |  | TA5200 | RIGHT-OF-WAY | 16000 | FY 2023: 16000
EB-5964 | BIKE/PED | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 14 | Southwestern RPO |  | DIVISION 14 |  | TA5200 | CONSTRUCTION | 520000 | FY 2024: 520000
EB-5964 | BIKE/PED | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 14 | Southwestern RPO |  | DIVISION 14 |  | TA5200 | ENGINEERING | 16000
EB-5964 | BIKE/PED | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 14 | Southwestern RPO |  | DIVISION 14 |  | L | CONSTRUCTION | 130000 | FY 2024: 130000
EB-5964 | BIKE/PED | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 14 | Southwestern RPO |  | DIVISION 14 |  | L | RIGHT-OF-WAY | 4000 | FY 2023: 4000
EB-5964 | BIKE/PED | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 14 | Southwestern RPO |  | DIVISION 14 |  | L | ENGINEERING | 4000
EB-5965 | BIKE/PED | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 50000 | FY 2026: 50000
EB-5965 | BIKE/PED | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 449000 | FY 2027: 449000
EB-5965 | BIKE/PED | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO |  | DIVISION 13 |  | TAANY | ENGINEERING | 568000 | FY 2024: 568000
EB-5965 | BIKE/PED | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO |  | DIVISION 13 |  | TAANY | RIGHT-OF-WAY | 200000 | FY 2026: 200000
EB-5965 | BIKE/PED | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO |  | DIVISION 13 |  | TAANY | CONSTRUCTION | 1796000 | FY 2027: 1796000
EB-5965 | BIKE/PED | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | ENGINEERING | 142000 | FY 2024: 142000
EB-5966 | BIKE/PED | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | ENGINEERING | 120000 | FY 2024: 120000
EB-5966 | BIKE/PED | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 13 | Foothills RPO |  | DIVISION 13 |  | L | CONSTRUCTION | 150000 | FY 2026: 150000
EB-5966 | BIKE/PED | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | CONSTRUCTION | 600000 | FY 2026: 600000
EB-5966 | BIKE/PED | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 13 | Foothills RPO |  | DIVISION 13 |  | L | ENGINEERING | 30000 | FY 2024: 30000
EB-5966 | BIKE/PED | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 13 | Foothills RPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 60000 | FY 2025: 60000
EB-5966 | BIKE/PED | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 13 | Foothills RPO |  | DIVISION 13 |  | TA5200 | RIGHT-OF-WAY | 240000 | FY 2025: 240000
EB-5969 | BIKE/PED | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 371000 | FY 2023: 371000
EB-5969 | BIKE/PED | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 692000 | FY 2025: 692000
EB-5969 | BIKE/PED | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TAANY | CONSTRUCTION | 860000 | FY 2027: 860000
EB-5969 | BIKE/PED | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 19000 | FY 2027: 19000
EB-5969 | BIKE/PED | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 215000 | FY 2027: 215000
EB-5969 | BIKE/PED | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 173000 | FY 2025: 173000
EB-5969 | BIKE/PED | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 93000 | FY 2023: 93000
EB-5969 | BIKE/PED | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 77000 | FY 2027: 77000
EB-5970 | BIKE/PED | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1391000 | FY 2028: 139000; FY 2029: 1252000
EB-5970 | BIKE/PED | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TAANY | CONSTRUCTION | 3246000 | FY 2028: 325000; FY 2029: 2921000
EB-5971 | BIKE/PED | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 58000 | FY 2025: 58000
EB-5971 | BIKE/PED | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TAANY | CONSTRUCTION | 232000 | FY 2025: 232000
EB-5972 | BIKE/PED | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 10 | Rocky River RPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 26000 | FY 2026: 26000
EB-5972 | BIKE/PED | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 10 | Rocky River RPO |  | DIVISION 10 |  | TA5200 | CONSTRUCTION | 360000 | FY 2027: 360000
EB-5972 | BIKE/PED | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 10 | Rocky River RPO |  | DIVISION 10 |  | TA5200 | RIGHT-OF-WAY | 104000 | FY 2026: 104000
EB-5972 | BIKE/PED | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 10 | Rocky River RPO |  | DIVISION 10 |  | L | ENGINEERING | 2000 | FY 2024: 2000
EB-5972 | BIKE/PED | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 10 | Rocky River RPO |  | DIVISION 10 |  | L | CONSTRUCTION | 90000 | FY 2027: 90000
EB-5972 | BIKE/PED | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 10 | Rocky River RPO |  | DIVISION 10 |  | TA5200 | ENGINEERING | 8000 | FY 2024: 8000
EB-5973 | BIKE/PED | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 10 | Rocky River RPO |  | DIVISION 10 |  | L | ENGINEERING | 3000 | FY 2024: 3000
EB-5973 | BIKE/PED | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 10 | Rocky River RPO |  | DIVISION 10 |  | L | CONSTRUCTION | 24000 | FY 2025: 24000
EB-5973 | BIKE/PED | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 10 | Rocky River RPO |  | DIVISION 10 |  | TA5200 | ENGINEERING | 9000 | FY 2024: 9000
EB-5973 | BIKE/PED | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 10 | Rocky River RPO |  | DIVISION 10 |  | TA5200 | CONSTRUCTION | 96000 | FY 2025: 96000
EB-5974 | BIKE/PED | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | 10 | Rocky River RPO |  | NOT FUNDED |  | L | ENGINEERING | 6000 | [11 empty] | 6000
EB-5974 | BIKE/PED | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | 10 | Rocky River RPO |  | NOT FUNDED |  | TA5200 | CONSTRUCTION | 160000 | [11 empty] | 160000
EB-5974 | BIKE/PED | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | 10 | Rocky River RPO |  | NOT FUNDED |  | TA5200 | RIGHT-OF-WAY | 24000 | [11 empty] | 24000
EB-5974 | BIKE/PED | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | 10 | Rocky River RPO |  | NOT FUNDED |  | TA5200 | ENGINEERING | 24000 | [11 empty] | 24000
EB-5974 | BIKE/PED | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | 10 | Rocky River RPO |  | NOT FUNDED |  | L | RIGHT-OF-WAY | 6000 | [11 empty] | 6000
EB-5974 | BIKE/PED | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | 10 | Rocky River RPO |  | NOT FUNDED |  | L | CONSTRUCTION | 40000 | [11 empty] | 40000
EB-5975 | BIKE/PED | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 516000
EB-5975 | BIKE/PED | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | CONSTRUCTION | 1652000 | FY 2025: 1652000
EB-5975 | BIKE/PED | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | ENGINEERING | 413000 | FY 2023: 413000
EB-5975 | BIKE/PED | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 413000 | FY 2025: 413000
EB-5975 | BIKE/PED | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | ENGINEERING | 103000 | FY 2023: 103000
EB-5976 | BIKE/PED | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 350000
EB-5976 | BIKE/PED | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | ENGINEERING | 70000 | FY 2023: 70000
EB-5976 | BIKE/PED | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 280000 | FY 2025: 280000
EB-5976 | BIKE/PED | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | ENGINEERING | 280000 | FY 2023: 280000
EB-5976 | BIKE/PED | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TA5200 | CONSTRUCTION | 1120000 | FY 2025: 1120000
EB-5977 | BIKE/PED | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  |  |  | 348000
EB-5977 | BIKE/PED | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 86000
EB-5977 | BIKE/PED | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | BGDACV | CONSTRUCTION | 1168000 | FY 2023: 1168000
EB-5977 | BIKE/PED | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | L | RIGHT-OF-WAY | 22000
EB-5977 | BIKE/PED | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | L | CONSTRUCTION | 292000 | FY 2023: 292000
EB-5978 | BIKE/PED | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 13 | Greater Hickory MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 580000 | FY 2024: 580000
EB-5978 | BIKE/PED | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 13 | Greater Hickory MPO |  | DIVISION 13 |  | TAANY | RIGHT-OF-WAY | 80000
EB-5978 | BIKE/PED | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 13 | Greater Hickory MPO |  | DIVISION 13 |  |  |  | 312000
EB-5978 | BIKE/PED | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 13 | Greater Hickory MPO |  | DIVISION 13 |  | L | RIGHT-OF-WAY | 20000
EB-5978 | BIKE/PED | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 13 | Greater Hickory MPO |  | DIVISION 13 |  | TAANY | CONSTRUCTION | 2320000 | FY 2024: 2320000
EB-5979 | BIKE/PED | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 1 | Mid-East RPO |  | DIVISION 1 |  | L | ENGINEERING | 2000 | FY 2025: 2000
EB-5979 | BIKE/PED | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 1 | Mid-East RPO |  | DIVISION 1 |  | L | CONSTRUCTION | 18000 | FY 2027: 18000
EB-5979 | BIKE/PED | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 1 | Mid-East RPO |  | DIVISION 1 |  | TA5200 | ENGINEERING | 8000 | FY 2025: 8000
EB-5979 | BIKE/PED | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 1 | Mid-East RPO |  | DIVISION 1 |  | TA5200 | CONSTRUCTION | 72000 | FY 2027: 72000
EB-5980 | BIKE/PED | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | L | ENGINEERING | 7000 | [11 empty] | 7000
EB-5980 | BIKE/PED | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | TA5200 | RIGHT-OF-WAY | 40000 | [11 empty] | 40000
EB-5980 | BIKE/PED | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | TA5200 | ENGINEERING | 27000 | [11 empty] | 27000
EB-5980 | BIKE/PED | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | L | RIGHT-OF-WAY | 10000 | [11 empty] | 10000
EB-5980 | BIKE/PED | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | TA5200 | CONSTRUCTION | 630000 | [11 empty] | 630000
EB-5980 | BIKE/PED | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | L | CONSTRUCTION | 157000 | [11 empty] | 157000
EB-5981 | BIKE/PED | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | TA5200 | ENGINEERING | 66000 | [11 empty] | 66000
EB-5981 | BIKE/PED | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | TA5200 | RIGHT-OF-WAY | 32000 | [11 empty] | 32000
EB-5981 | BIKE/PED | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | TA5200 | CONSTRUCTION | 1635000 | [11 empty] | 1635000
EB-5981 | BIKE/PED | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | L | ENGINEERING | 17000 | [11 empty] | 17000
EB-5981 | BIKE/PED | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | L | RIGHT-OF-WAY | 8000 | [11 empty] | 8000
EB-5981 | BIKE/PED | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | L | CONSTRUCTION | 409000 | [11 empty] | 409000
EB-5982 | BIKE/PED | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 3 | Cape Fear RPO |  | DIVISION 3 |  | L | ENGINEERING | 6000 | FY 2023: 6000
EB-5982 | BIKE/PED | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 3 | Cape Fear RPO |  | DIVISION 3 |  | L | RIGHT-OF-WAY | 10000 | FY 2024: 10000
EB-5982 | BIKE/PED | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 3 | Cape Fear RPO |  | DIVISION 3 |  | L | CONSTRUCTION | 35000 | FY 2025: 35000
EB-5982 | BIKE/PED | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 3 | Cape Fear RPO |  | DIVISION 3 |  | TA5200 | ENGINEERING | 24000 | FY 2023: 24000
EB-5982 | BIKE/PED | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 3 | Cape Fear RPO |  | DIVISION 3 |  | TA5200 | RIGHT-OF-WAY | 40000 | FY 2024: 40000
EB-5982 | BIKE/PED | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 3 | Cape Fear RPO |  | DIVISION 3 |  | TA5200 | CONSTRUCTION | 140000 | FY 2025: 140000
EB-5983 | BIKE/PED | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 11 | High Country RPO |  | DIVISION 11 |  | TA5200 | ENGINEERING | 240000 | FY 2023: 240000
EB-5983 | BIKE/PED | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 11 | High Country RPO |  | DIVISION 11 |  | TA5200 | RIGHT-OF-WAY | 16000 | FY 2024: 16000
EB-5983 | BIKE/PED | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 11 | High Country RPO |  | DIVISION 11 |  | L | ENGINEERING | 60000 | FY 2023: 60000
EB-5983 | BIKE/PED | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 11 | High Country RPO |  | DIVISION 11 |  | L | RIGHT-OF-WAY | 4000 | FY 2024: 4000
EB-5983 | BIKE/PED | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 11 | High Country RPO |  | DIVISION 11 |  | L | CONSTRUCTION | 373000 | FY 2025: 373000
EB-5983 | BIKE/PED | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 11 | High Country RPO |  | DIVISION 11 |  | TA5200 | CONSTRUCTION | 1492000 | FY 2025: 1492000
EB-5984 | BIKE/PED | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA5200 | CONSTRUCTION | 2160000 | FY 2028: 2160000
EB-5984 | BIKE/PED | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | ENGINEERING | 60000 | FY 2026: 60000
EB-5984 | BIKE/PED | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 540000 | FY 2028: 540000
EB-5984 | BIKE/PED | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | TA5200 | ENGINEERING | 240000 | FY 2026: 240000
EB-5985 | BIKE/PED | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 377000 | FY 2023: 377000
EB-5985 | BIKE/PED | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 62000 | FY 2023: 62000
EB-5985 | BIKE/PED | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | ENGINEERING | 120000
EB-5985 | BIKE/PED | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 94000 | FY 2023: 94000
EB-5985 | BIKE/PED | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | ENGINEERING | 30000
EB-5985 | BIKE/PED | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 16000 | FY 2023: 16000
EB-5986 | BIKE/PED | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 56000 | FY 2023: 56000
EB-5986 | BIKE/PED | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | ENGINEERING | 40000 | FY 2023: 40000
EB-5986 | BIKE/PED | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 960000 | FY 2024: 960000
EB-5986 | BIKE/PED | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 14000 | FY 2023: 14000
EB-5986 | BIKE/PED | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | ENGINEERING | 10000 | FY 2023: 10000
EB-5986 | BIKE/PED | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 240000 | FY 2024: 240000
EB-5987 | BIKE/PED | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 9000 | FY 2024: 9000
EB-5987 | BIKE/PED | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 792000 | FY 2025: 792000
EB-5987 | BIKE/PED | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | ENGINEERING | 79000
EB-5987 | BIKE/PED | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 198000 | FY 2025: 198000
EB-5987 | BIKE/PED | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 2000 | FY 2024: 2000
EB-5987 | BIKE/PED | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | ENGINEERING | 20000
EB-5988 | BIKE/PED | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | TA5200 | CONSTRUCTION | 218000 | FY 2026: 218000
EB-5988 | BIKE/PED | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 1000 | FY 2025: 1000
EB-5988 | BIKE/PED | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 54000 | FY 2026: 54000
EB-5988 | BIKE/PED | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | TA5200 | ENGINEERING | 24000 | FY 2024: 24000
EB-5988 | BIKE/PED | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | TA5200 | RIGHT-OF-WAY | 4000 | FY 2025: 4000
EB-5988 | BIKE/PED | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | L | ENGINEERING | 6000 | FY 2024: 6000
EB-5989 | BIKE/PED | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | TA5200 | ENGINEERING | 96000 | FY 2024: 96000
EB-5989 | BIKE/PED | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | TA5200 | RIGHT-OF-WAY | 40000 | FY 2025: 40000
EB-5989 | BIKE/PED | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | TA5200 | CONSTRUCTION | 960000 | FY 2026: 960000
EB-5989 | BIKE/PED | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 240000 | FY 2026: 240000
EB-5989 | BIKE/PED | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | L | ENGINEERING | 24000 | FY 2024: 24000
EB-5989 | BIKE/PED | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 7 | High Point Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 10000 | FY 2025: 10000
EB-5990 | BIKE/PED | HIGH POINT RAILROAD ESPLANADE | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 160000
EB-5990 | BIKE/PED | HIGH POINT RAILROAD ESPLANADE | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 1600000
EB-5990 | BIKE/PED | HIGH POINT RAILROAD ESPLANADE | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TA5200 | ENGINEERING | 640000
EB-5990 | BIKE/PED | HIGH POINT RAILROAD ESPLANADE | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TA5200 | CONSTRUCTION | 6400000
EB-5992 | BIKE/PED | SPRING GARDEN STREET | MERRITT DRIVE TO EXISTING SIDEWALK WEST OF HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 7000
EB-5992 | BIKE/PED | SPRING GARDEN STREET | MERRITT DRIVE TO EXISTING SIDEWALK WEST OF HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 63000
EB-5992 | BIKE/PED | SPRING GARDEN STREET | MERRITT DRIVE TO EXISTING SIDEWALK WEST OF HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | ENGINEERING | 28000
EB-5992 | BIKE/PED | SPRING GARDEN STREET | MERRITT DRIVE TO EXISTING SIDEWALK WEST OF HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | CONSTRUCTION | 252000
EB-5994 | BIKE/PED | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTI-USE PATH ON NORTH SIDE OF NC 54. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | ENGINEERING | 190000
EB-5994 | BIKE/PED | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTI-USE PATH ON NORTH SIDE OF NC 54. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | RIGHT-OF-WAY | 34000
EB-5994 | BIKE/PED | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTI-USE PATH ON NORTH SIDE OF NC 54. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 9000
EB-5994 | BIKE/PED | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTI-USE PATH ON NORTH SIDE OF NC 54. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 48000
EB-5994 | BIKE/PED | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTI-USE PATH ON NORTH SIDE OF NC 54. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | CONSTRUCTION | 950000
EB-5994 | BIKE/PED | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTI-USE PATH ON NORTH SIDE OF NC 54. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 238000
EB-5995 | BIKE/PED | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 10000 | FY 2023: 10000
EB-5995 | BIKE/PED | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 76000 | FY 2025: 76000
EB-5995 | BIKE/PED | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 38000 | FY 2023: 38000
EB-5995 | BIKE/PED | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 305000 | FY 2025: 305000
EB-5996 | BIKE/PED | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 20000 | FY 2024: 20000
EB-5996 | BIKE/PED | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 166000 | FY 2025: 166000
EB-5996 | BIKE/PED | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 80000 | FY 2024: 80000
EB-5996 | BIKE/PED | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 664000 | FY 2025: 664000
EB-5997 | BIKE/PED | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 58000 | FY 2025: 58000
EB-5997 | BIKE/PED | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 230000 | FY 2025: 230000
EB-5997 | BIKE/PED | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | ENGINEERING | 56000 | FY 2023: 56000
EB-5997 | BIKE/PED | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 9000 | FY 2024: 9000
EB-5997 | BIKE/PED | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | ENGINEERING | 14000 | FY 2023: 14000
EB-5997 | BIKE/PED | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 36000 | FY 2024: 36000
EB-5998 | BIKE/PED | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | DIVISION 7 |  | L | ENGINEERING | 41000 | FY 2023: 41000
EB-5998 | BIKE/PED | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | DIVISION 7 |  | L | CONSTRUCTION | 700000 | FY 2026: 700000
EB-5998 | BIKE/PED | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | DIVISION 7 |  | TAANY | ENGINEERING | 163000 | FY 2023: 163000
EB-5998 | BIKE/PED | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | DIVISION 7 |  | TAANY | CONSTRUCTION | 2800000 | FY 2026: 2800000
EB-5999 | BIKE/PED | JOHNSON STREET | PARRIS AVENUE TO SR 1896 (EAST HARTLEY DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 29000
EB-5999 | BIKE/PED | JOHNSON STREET | PARRIS AVENUE TO SR 1896 (EAST HARTLEY DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TA5200 | CONSTRUCTION | 116000
EB-6000 | BIKE/PED | SR 1536 (PENNY ROAD) | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTI-USE PATH. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 300000
EB-6000 | BIKE/PED | SR 1536 (PENNY ROAD) | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTI-USE PATH. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TA5200 | ENGINEERING | 120000
EB-6000 | BIKE/PED | SR 1536 (PENNY ROAD) | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTI-USE PATH. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TA5200 | CONSTRUCTION | 1200000
EB-6000 | BIKE/PED | SR 1536 (PENNY ROAD) | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTI-USE PATH. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 30000
EB-6001 | BIKE/PED | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO | COORDINATE WITH U-5815 | DIVISION 8 |  | L | CONSTRUCTION | 68000 | FY 2025: 68000
EB-6001 | BIKE/PED | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO | COORDINATE WITH U-5815 | DIVISION 8 |  | TA5200 | CONSTRUCTION | 272000 | FY 2025: 272000
EB-6001 | BIKE/PED | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO | COORDINATE WITH U-5815 | DIVISION 8 |  | TA5200 | ENGINEERING | 21000 | FY 2023: 21000
EB-6001 | BIKE/PED | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO | COORDINATE WITH U-5815 | DIVISION 8 |  | L | ENGINEERING | 5000 | FY 2023: 5000
EB-6001 | BIKE/PED | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO | COORDINATE WITH U-5815 | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 27000 | FY 2024: 27000
EB-6001 | BIKE/PED | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO | COORDINATE WITH U-5815 | DIVISION 8 |  | L | RIGHT-OF-WAY | 7000 | FY 2024: 7000
EB-6002 | BIKE/PED | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | ENGINEERING | 38000 | FY 2023: 38000
EB-6002 | BIKE/PED | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 280000 | FY 2025: 280000
EB-6002 | BIKE/PED | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 153000 | FY 2023: 153000
EB-6002 | BIKE/PED | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 1120000 | FY 2025: 1120000
EB-6003 | BIKE/PED | MCIVER STREET | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO |  | NOT FUNDED |  | L | ENGINEERING | 26000 | [11 empty] | 26000
EB-6003 | BIKE/PED | MCIVER STREET | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO |  | NOT FUNDED |  | L | CONSTRUCTION | 173000 | [11 empty] | 173000
EB-6003 | BIKE/PED | MCIVER STREET | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO |  | NOT FUNDED |  | TA5200 | ENGINEERING | 102000 | [11 empty] | 102000
EB-6003 | BIKE/PED | MCIVER STREET | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | 8 | Triangle Area RPO |  | NOT FUNDED |  | TA5200 | CONSTRUCTION | 691000 | [11 empty] | 691000
EB-6004 | BIKE/PED | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 26000 | FY 2024: 26000
EB-6004 | BIKE/PED | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 104000 | FY 2024: 104000
EB-6005 | BIKE/PED | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | 8 | Triangle Area RPO |  | NOT FUNDED |  | TA5200 | ENGINEERING | 23000 | [11 empty] | 23000
EB-6005 | BIKE/PED | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | 8 | Triangle Area RPO |  | NOT FUNDED |  | TA5200 | CONSTRUCTION | 147000 | [11 empty] | 147000
EB-6005 | BIKE/PED | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | 8 | Triangle Area RPO |  | NOT FUNDED |  | L | ENGINEERING | 6000 | [11 empty] | 6000
EB-6005 | BIKE/PED | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | 8 | Triangle Area RPO |  | NOT FUNDED |  | L | CONSTRUCTION | 37000 | [11 empty] | 37000
EB-6006 | BIKE/PED | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 680000 | FY 2026: 680000
EB-6006 | BIKE/PED | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 9000 | FY 2024: 9000
EB-6006 | BIKE/PED | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 170000 | FY 2026: 170000
EB-6006 | BIKE/PED | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 90000
EB-6006 | BIKE/PED | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 36000 | FY 2024: 36000
EB-6006 | BIKE/PED | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | DIVISION 8 |  | L | ENGINEERING | 23000
EB-6007 | BIKE/PED | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | NOT FUNDED |  | TA5200 | CONSTRUCTION | 736000 | [11 empty] | 736000
EB-6007 | BIKE/PED | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | NOT FUNDED |  | TA5200 | RIGHT-OF-WAY | 56000 | [11 empty] | 56000
EB-6007 | BIKE/PED | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | NOT FUNDED |  | TA5200 | ENGINEERING | 102000 | [11 empty] | 102000
EB-6007 | BIKE/PED | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | NOT FUNDED |  | L | CONSTRUCTION | 184000 | [11 empty] | 184000
EB-6007 | BIKE/PED | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | NOT FUNDED |  | L | ENGINEERING | 25000 | [11 empty] | 25000
EB-6007 | BIKE/PED | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | 8 | Triangle Area RPO |  | NOT FUNDED |  | L | RIGHT-OF-WAY | 14000 | [11 empty] | 14000
EB-6008 | BIKE/PED | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | ENGINEERING | 271000
EB-6008 | BIKE/PED | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 689000 | FY 2025: 689000
EB-6008 | BIKE/PED | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | CONSTRUCTION | 1804000 | FY 2025: 1804000
EB-6008 | BIKE/PED | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | CMAQ | RIGHT-OF-WAY | 238000 | FY 2024: 238000
EB-6008 | BIKE/PED | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 68000
EB-6008 | BIKE/PED | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TAANY | RIGHT-OF-WAY | 88000 | FY 2024: 88000
EB-6008 | BIKE/PED | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | CMAQ | CONSTRUCTION | 951000 | FY 2025: 951000
EB-6008 | BIKE/PED | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 82000 | FY 2024: 82000
EB-6009 | BIKE/PED | SR 2526 (SUMMIT AVENUE) | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 131000
EB-6009 | BIKE/PED | SR 2526 (SUMMIT AVENUE) | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 744000
EB-6009 | BIKE/PED | SR 2526 (SUMMIT AVENUE) | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | ENGINEERING | 525000
EB-6009 | BIKE/PED | SR 2526 (SUMMIT AVENUE) | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | CONSTRUCTION | 2975000
EB-6010 | BIKE/PED | US 70 (WEST WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) TO GIBSON PARK ENTRANCE IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO | COORDINATE WITH U-6121 | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 44000
EB-6010 | BIKE/PED | US 70 (WEST WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) TO GIBSON PARK ENTRANCE IN HIGH POINT. CONSTRUCT SIDEWALK. | 7 | High Point Urban Area MPO | COORDINATE WITH U-6121 | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TA5200 | CONSTRUCTION | 176000
EB-6011 | BIKE/PED | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | TA5200 | RIGHT-OF-WAY | 8000 | [11 empty] | 8000
EB-6011 | BIKE/PED | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | TA5200 | CONSTRUCTION | 84000 | [11 empty] | 84000
EB-6011 | BIKE/PED | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | TA5200 | ENGINEERING | 14000 | [11 empty] | 14000
EB-6011 | BIKE/PED | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | L | ENGINEERING | 4000 | [11 empty] | 4000
EB-6011 | BIKE/PED | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | L | RIGHT-OF-WAY | 2000 | [11 empty] | 2000
EB-6011 | BIKE/PED | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | L | CONSTRUCTION | 21000 | [11 empty] | 21000
EB-6012 | BIKE/PED | DOWNTOWN GREENWAY | CHANEY AVENUE TO WARDOLA DRIVE IN JACKSONVILLE. CONSTRUCT MULTI-USE PATH. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | CONSTRUCTION | 273000
EB-6012 | BIKE/PED | DOWNTOWN GREENWAY | CHANEY AVENUE TO WARDOLA DRIVE IN JACKSONVILLE. CONSTRUCT MULTI-USE PATH. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | TA5200 | CONSTRUCTION | 1094000
EB-6013 | BIKE/PED | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 6 | Lumber River RPO |  | DIVISION 6 |  | TA5200 | ENGINEERING | 136000 | FY 2027: 136000
EB-6013 | BIKE/PED | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 6 | Lumber River RPO |  | DIVISION 6 |  | TA5200 | RIGHT-OF-WAY | 134000 | FY 2028: 134000
EB-6013 | BIKE/PED | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 6 | Lumber River RPO |  | DIVISION 6 |  | L | CONSTRUCTION | 170000 | FY 2029: 170000
EB-6013 | BIKE/PED | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 6 | Lumber River RPO |  | DIVISION 6 |  | L | RIGHT-OF-WAY | 34000 | FY 2028: 34000
EB-6013 | BIKE/PED | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 6 | Lumber River RPO |  | DIVISION 6 |  | L | ENGINEERING | 34000 | FY 2027: 34000
EB-6013 | BIKE/PED | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 6 | Lumber River RPO |  | DIVISION 6 |  | TA5200 | CONSTRUCTION | 678000 | FY 2029: 678000
EB-6014 | BIKE/PED | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | L | RIGHT-OF-WAY | 7000
EB-6014 | BIKE/PED | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | L | CONSTRUCTION | 113000
EB-6014 | BIKE/PED | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | TALT5 | RIGHT-OF-WAY | 28000
EB-6014 | BIKE/PED | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | TALT5 | CONSTRUCTION | 452000
EB-6015A | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 53000
EB-6015A | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 528000 | FY 2024: 528000
EB-6015A | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 132000 | FY 2024: 132000
EB-6015A | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 15000 | FY 2023: 15000
EB-6015A | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | L | ENGINEERING | 13000
EB-6015A | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 61000 | FY 2023: 61000
EB-6015B | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 42000 | FY 2024: 42000
EB-6015B | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 368000 | FY 2025: 368000
EB-6015B | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 44000 | FY 2023: 44000
EB-6015B | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 92000 | FY 2025: 92000
EB-6015B | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 10000 | FY 2024: 10000
EB-6015B | BIKE/PED | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 8 | Lumber River RPO |  | DIVISION 8 |  | L | ENGINEERING | 11000 | FY 2023: 11000
EB-6016 | BIKE/PED | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | L | RIGHT-OF-WAY | 2000 | FY 2027: 2000
EB-6016 | BIKE/PED | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 248000 | FY 2028: 248000
EB-6016 | BIKE/PED | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | TAANY | ENGINEERING | 206000 | FY 2026: 206000
EB-6016 | BIKE/PED | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | TAANY | RIGHT-OF-WAY | 8000 | FY 2027: 8000
EB-6016 | BIKE/PED | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | TAANY | CONSTRUCTION | 994000 | FY 2028: 994000
EB-6016 | BIKE/PED | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | L | ENGINEERING | 52000 | FY 2026: 52000
EB-6017 | BIKE/PED | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | L | ENGINEERING | 17000 | FY 2026: 17000
EB-6017 | BIKE/PED | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | TAANY | CONSTRUCTION | 318000 | FY 2028: 318000
EB-6017 | BIKE/PED | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | TAANY | ENGINEERING | 66000 | FY 2026: 66000
EB-6017 | BIKE/PED | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 4 | Capital Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 96000 | FY 2028: 96000
EB-6018 | BIKE/PED | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | RIGHT-OF-WAY | 58000 | FY 2024: 58000
EB-6018 | BIKE/PED | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | UTILITIES | 44000 | FY 2024: 44000
EB-6018 | BIKE/PED | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | ENGINEERING | 22000 | FY 2023: 22000
EB-6018 | BIKE/PED | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | CONSTRUCTION | 144000 | FY 2025: 144000
EB-6018 | BIKE/PED | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | UTILITIES | 11000 | FY 2024: 11000
EB-6018 | BIKE/PED | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | RIGHT-OF-WAY | 14000 | FY 2024: 14000
EB-6018 | BIKE/PED | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | L | ENGINEERING | 6000 | FY 2023: 6000
EB-6018 | BIKE/PED | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 8 | Lumber River RPO |  | DIVISION 8 |  | TA5200 | CONSTRUCTION | 576000 | FY 2025: 576000
EB-6019 | BIKE/PED | SR 1306 (LAURA DUNCAN ROAD) | APEX COMMUNITY PARK AND NORTH SALEM STREET IN APEX. IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION. | DIVISION 5 |  |  |  | 9000
EB-6019 | BIKE/PED | SR 1306 (LAURA DUNCAN ROAD) | APEX COMMUNITY PARK AND NORTH SALEM STREET IN APEX. IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION. | DIVISION 5 |  | BGDA | CONSTRUCTION | 381000
EB-6019 | BIKE/PED | SR 1306 (LAURA DUNCAN ROAD) | APEX COMMUNITY PARK AND NORTH SALEM STREET IN APEX. IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION. | DIVISION 5 |  | L | CONSTRUCTION | 163000
EB-6020 | BIKE/PED | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | ENGINEERING | 140000
EB-6020 | BIKE/PED | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | CONSTRUCTION | 291000 | FY 2024: 291000
EB-6020 | BIKE/PED | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | RIGHT-OF-WAY | 30000 | FY 2024: 30000
EB-6020 | BIKE/PED | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | RIGHT-OF-WAY | 120000 | FY 2024: 120000
EB-6020 | BIKE/PED | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 6 | Capital Area MPO |  | DIVISION 6 |  | BGDA | CONSTRUCTION | 1166000 | FY 2024: 1166000
EB-6020 | BIKE/PED | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 6 | Capital Area MPO |  | DIVISION 6 |  | L | ENGINEERING | 35000
EB-6021 | BIKE/PED | BEAVER CREEK GREENWAY EXTENSION | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 5512000 | FY 2023: 5512000
EB-6021 | BIKE/PED | BEAVER CREEK GREENWAY EXTENSION | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | 5 | Capital Area MPO |  | DIVISION 5 |  | TADA | CONSTRUCTION | 1053000 | FY 2023: 1053000
EB-6025 | BIKE/PED | RICE HOPE MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGDA | ENGINEERING | 24000
EB-6025 | BIKE/PED | RICE HOPE MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGDA | CONSTRUCTION | 134000 | FY 2023: 134000
EB-6025 | BIKE/PED | RICE HOPE MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | ENGINEERING | 6000
EB-6025 | BIKE/PED | RICE HOPE MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | CONSTRUCTION | 33000 | FY 2023: 33000
EB-6026 | BIKE/PED | BELVILLE ELEMENTARY MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | ENGINEERING | 6000
EB-6026 | BIKE/PED | BELVILLE ELEMENTARY MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | CONSTRUCTION | 24000 | FY 2023: 24000
EB-6026 | BIKE/PED | BELVILLE ELEMENTARY MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | TADA | ENGINEERING | 24000
EB-6026 | BIKE/PED | BELVILLE ELEMENTARY MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | TADA | CONSTRUCTION | 94000 | FY 2023: 94000
EB-6027 | BIKE/PED | SR 1403 (MIDDLE SOUND LOOP) | CONSTRUCT MULTI-USE PATH SOUTH OF MARKET STREET FROM RED CEDAR ROAD TO EXISTING TRAIL AT CORNER OF MARKET STREET AND MIDDLE SOUND LOOP ROAD. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | CONSTRUCTION | 1000000 | FY 2023: 1000000
EB-6027 | BIKE/PED | SR 1403 (MIDDLE SOUND LOOP) | CONSTRUCT MULTI-USE PATH SOUTH OF MARKET STREET FROM RED CEDAR ROAD TO EXISTING TRAIL AT CORNER OF MARKET STREET AND MIDDLE SOUND LOOP ROAD. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | RIGHT-OF-WAY | 500000
EB-6027 | BIKE/PED | SR 1403 (MIDDLE SOUND LOOP) | CONSTRUCT MULTI-USE PATH SOUTH OF MARKET STREET FROM RED CEDAR ROAD TO EXISTING TRAIL AT CORNER OF MARKET STREET AND MIDDLE SOUND LOOP ROAD. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 305000
EB-6028 | BIKE/PED | WILMINGTON | CONSTRUCT SIGNALIZED PEDESTRIAN CROSSING AT US 17 BUSINESS (MARKET STREET) AND 21ST STREET. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 33000 | FY 2023: 33000
EB-6028 | BIKE/PED | WILMINGTON | CONSTRUCT SIGNALIZED PEDESTRIAN CROSSING AT US 17 BUSINESS (MARKET STREET) AND 21ST STREET. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | TADA | CONSTRUCTION | 131000 | FY 2023: 131000
EB-6028 | BIKE/PED | WILMINGTON | CONSTRUCT SIGNALIZED PEDESTRIAN CROSSING AT US 17 BUSINESS (MARKET STREET) AND 21ST STREET. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  |  |  | 75000
EB-6030 | BIKE/PED | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | ENGINEERING | 15000
EB-6030 | BIKE/PED | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | RIGHT-OF-WAY | 15000 | FY 2023: 15000
EB-6030 | BIKE/PED | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | CONSTRUCTION | 90000 | FY 2024: 90000
EB-6030 | BIKE/PED | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TADA | ENGINEERING | 60000
EB-6030 | BIKE/PED | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TADA | RIGHT-OF-WAY | 60000 | FY 2023: 60000
EB-6030 | BIKE/PED | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TADA | CONSTRUCTION | 360000 | FY 2024: 360000
EB-6031 | BIKE/PED | US 401 (RAMSEY STREET) | CONSTRUCT SIDEWALK FROM SUMMERCHASE DRIVE TO SR 1611 (ANDREWS ROAD). | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | L | CONSTRUCTION | 17000
EB-6031 | BIKE/PED | US 401 (RAMSEY STREET) | CONSTRUCT SIDEWALK FROM SUMMERCHASE DRIVE TO SR 1611 (ANDREWS ROAD). | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | TADA | CONSTRUCTION | 68000
EB-6032 | BIKE/PED | NC 59 (HOPE MILLS ROAD) | CONSTRUCT SIDEWALK FROM FAYETTEVILLE CITY LIMITS TO SUMAC CIRCLE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | TADA | CONSTRUCTION | 300000
EB-6032 | BIKE/PED | NC 59 (HOPE MILLS ROAD) | CONSTRUCT SIDEWALK FROM FAYETTEVILLE CITY LIMITS TO SUMAC CIRCLE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  |  |  | 23000
EB-6032 | BIKE/PED | NC 59 (HOPE MILLS ROAD) | CONSTRUCT SIDEWALK FROM FAYETTEVILLE CITY LIMITS TO SUMAC CIRCLE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | L | CONSTRUCTION | 75000
EB-6033 | BIKE/PED | VARIOUS | SAFE ROUTES TO SCHOOL EDUCATION. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 2833000
EB-6034 | BIKE/PED | SR 1144 (FIRST STREET) | CONSTRUCTION OF BIKE LANES ON BOTH SIDES OF FIRST STREET FROM EAST OF WEST FIRST STREET EXTENSION TO EAST OF GREENSBORO STREET IN OCEAN ISLE BEACH. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  | L | CONSTRUCTION | 414000
EB-6034 | BIKE/PED | SR 1144 (FIRST STREET) | CONSTRUCTION OF BIKE LANES ON BOTH SIDES OF FIRST STREET FROM EAST OF WEST FIRST STREET EXTENSION TO EAST OF GREENSBORO STREET IN OCEAN ISLE BEACH. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  | BGDA | CONSTRUCTION | 622000
EB-6036 | BIKE/PED | CHARLOTTE | HORNETS NEST PARK ACCESS IMPROVEMENTS INCLUDING SIDEWALKS, A MULTI-USE PATH, AND A TRAFFIC SIGNAL WITH LEFT TURN LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 1500000 | FY 2023: 1500000
EB-6036 | BIKE/PED | CHARLOTTE | HORNETS NEST PARK ACCESS IMPROVEMENTS INCLUDING SIDEWALKS, A MULTI-USE PATH, AND A TRAFFIC SIGNAL WITH LEFT TURN LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 375000 | FY 2023: 375000
EB-6037A | BIKE/PED | SHELBY RAIL TRAIL | SOUTH DEKALB STREET TO WEST GROVER STREET IN SHELBY. CONSTRUCT MULTIUSE PATH. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CONSTRUCTION | 1040000 | FY 2024: 10000; FY 2025: 750000; FY 2026: 280000
EB-6037A | BIKE/PED | SHELBY RAIL TRAIL | SOUTH DEKALB STREET TO WEST GROVER STREET IN SHELBY. CONSTRUCT MULTIUSE PATH. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | TAANY | CONSTRUCTION | 4160000 | FY 2024: 42000; FY 2025: 2998000; FY 2026: 1120000
EB-6037B | BIKE/PED | ECUSTA TRAIL | BREVARD BIKE PATH IN BREVARD TO KANUGA ROAD IN HENDERSONVILLE. CONSTRUCT MULTIUSE PATH. | 14 | French Broad River MPO, Land-of-Sky RPO | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE. | DIVISION 14 |  | L | RIGHT-OF-WAY | 1600000
EB-6037B | BIKE/PED | ECUSTA TRAIL | BREVARD BIKE PATH IN BREVARD TO KANUGA ROAD IN HENDERSONVILLE. CONSTRUCT MULTIUSE PATH. | 14 | French Broad River MPO, Land-of-Sky RPO | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE. | DIVISION 14 |  | TAANY | RIGHT-OF-WAY | 6400000
EB-6037C | BIKE/PED | A&Y GREENWAY | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGANY | CONSTRUCTION | 2749000 | FY 2023: 2749000
EB-6037C | BIKE/PED | A&Y GREENWAY | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 1787000 | FY 2023: 1787000
EB-6037C | BIKE/PED | A&Y GREENWAY | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TAANY | CONSTRUCTION | 4400000 | FY 2023: 4400000
EB-6038 | BIKE/PED | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | EXEMPT |  | DP | CONSTRUCTION | 15092000 | FY 2023: 4779000; FY 2024: 4779000
EB-6038 | BIKE/PED | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | EXEMPT |  | L | CONSTRUCTION | 4124000 | FY 2023: 1306000; FY 2024: 1306000
EB-6038 | BIKE/PED | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | EXEMPT |  | L | ENGINEERING | 288000
EB-6038 | BIKE/PED | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | EXEMPT |  | DP | ENGINEERING | 1764000
EB-6038 | BIKE/PED | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | EXEMPT |  | DP | RIGHT-OF-WAY | 403000
EB-6038 | BIKE/PED | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | EXEMPT |  | L | RIGHT-OF-WAY | 259000
EB-6039 | BIKE/PED | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | ENGINEERING | 59000
EB-6039 | BIKE/PED | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 398000 | FY 2024: 398000
EB-6039 | BIKE/PED | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | ENGINEERING | 15000
EB-6039 | BIKE/PED | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 100000 | FY 2024: 100000
EB-6040 | BIKE/PED | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | ENGINEERING | 53000
EB-6040 | BIKE/PED | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 317000 | FY 2023: 317000
EB-6040 | BIKE/PED | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 1270000 | FY 2023: 1270000
EB-6040 | BIKE/PED | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | ENGINEERING | 13000
EB-6041 | BIKE/PED | SPRING LAKE | CONSTRUCT GREENWAY TRAIL NEAR THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | L | CONSTRUCTION | 439000
EB-6041 | BIKE/PED | SPRING LAKE | CONSTRUCT GREENWAY TRAIL NEAR THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | TADA | CONSTRUCTION | 106000
EB-6042 | BIKE/PED | GREENVILLE | CONSTRUCT MULTI-USE PATH AT VARIOUS LOCATIONS INCLUDING ALONG THE TAR RIVER, MOYE BOULEVARD, THE NORFOLK SOUTHERN RAIL CORRIDOR, AND TOWN CREEK IN GREENVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | EXEMPT |  | L | CONSTRUCTION | 2559000
EB-6042 | BIKE/PED | GREENVILLE | CONSTRUCT MULTI-USE PATH AT VARIOUS LOCATIONS INCLUDING ALONG THE TAR RIVER, MOYE BOULEVARD, THE NORFOLK SOUTHERN RAIL CORRIDOR, AND TOWN CREEK IN GREENVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | EXEMPT |  |  |  | 3327000
EB-6042 | BIKE/PED | GREENVILLE | CONSTRUCT MULTI-USE PATH AT VARIOUS LOCATIONS INCLUDING ALONG THE TAR RIVER, MOYE BOULEVARD, THE NORFOLK SOUTHERN RAIL CORRIDOR, AND TOWN CREEK IN GREENVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | EXEMPT |  | DP | CONSTRUCTION | 4510000
EB-6046 | BIKE/PED | (SR 1307) WEST CHATHAM STREET | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 381000 | FY 2023: 381000
EB-6046 | BIKE/PED | (SR 1307) WEST CHATHAM STREET | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 572000 | FY 2023: 572000
EB-6048 | BIKE/PED | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 60000 | FY 2023: 60000
EB-6048 | BIKE/PED | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 5 |  | BGDA | CONSTRUCTION | 307000 | FY 2023: 307000
EB-6048 | BIKE/PED | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 5 |  | L | RIGHT-OF-WAY | 15000 | FY 2023: 15000
EB-6048 | BIKE/PED | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 5 |  | L | CONSTRUCTION | 77000 | FY 2023: 77000
EB-6049 | BIKE/PED | AVENT FERRY ROAD | COTTEN LANE TO WEST BALLANTINE STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO STINSON AVENUE VIA PINE AVENUE IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 250000 | FY 2023: 250000
EB-6049 | BIKE/PED | AVENT FERRY ROAD | COTTEN LANE TO WEST BALLANTINE STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO STINSON AVENUE VIA PINE AVENUE IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 1000000 | FY 2023: 1000000
EB-6050 | BIKE/PED | NC 24 (W.T. HARRIS BOULEVARD) | PLAZA ROAD TO GRIER ROAD. CONSTRUCT SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 1151000 | FY 2025: 1151000
EB-6050 | BIKE/PED | NC 24 (W.T. HARRIS BOULEVARD) | PLAZA ROAD TO GRIER ROAD. CONSTRUCT SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 72000 | FY 2023: 72000
EB-6050 | BIKE/PED | NC 24 (W.T. HARRIS BOULEVARD) | PLAZA ROAD TO GRIER ROAD. CONSTRUCT SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 6000 | FY 2023: 6000
EB-6050 | BIKE/PED | NC 24 (W.T. HARRIS BOULEVARD) | PLAZA ROAD TO GRIER ROAD. CONSTRUCT SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 767000 | FY 2025: 767000
EB-6050 | BIKE/PED | NC 24 (W.T. HARRIS BOULEVARD) | PLAZA ROAD TO GRIER ROAD. CONSTRUCT SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 4000 | FY 2023: 4000
EB-6050 | BIKE/PED | NC 24 (W.T. HARRIS BOULEVARD) | PLAZA ROAD TO GRIER ROAD. CONSTRUCT SIDEWALK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 48000 | FY 2023: 48000
EB-6051 | BIKE/PED | LAWYERS ROAD, WILGROVE-MINT HILL ROAD, WILSON GROV | EXTEND EXISTING SIDEWALKS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 188000
EB-6051 | BIKE/PED | LAWYERS ROAD, WILGROVE-MINT HILL ROAD, WILSON GROV | EXTEND EXISTING SIDEWALKS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 1287000 | FY 2024: 1287000
EB-6051 | BIKE/PED | LAWYERS ROAD, WILGROVE-MINT HILL ROAD, WILSON GROV | EXTEND EXISTING SIDEWALKS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 30000 | FY 2023: 30000
EB-6051 | BIKE/PED | LAWYERS ROAD, WILGROVE-MINT HILL ROAD, WILSON GROV | EXTEND EXISTING SIDEWALKS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 188000
EB-6051 | BIKE/PED | LAWYERS ROAD, WILGROVE-MINT HILL ROAD, WILSON GROV | EXTEND EXISTING SIDEWALKS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 30000 | FY 2023: 30000
EB-6051 | BIKE/PED | LAWYERS ROAD, WILGROVE-MINT HILL ROAD, WILSON GROV | EXTEND EXISTING SIDEWALKS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1287000 | FY 2024: 1287000
EB-6052 | BIKE/PED | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 4000 | FY 2023: 4000
EB-6052 | BIKE/PED | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 160000 | FY 2023: 160000
EB-6052 | BIKE/PED | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 501000 | FY 2025: 501000
EB-6052 | BIKE/PED | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | ENGINEERING | 6000 | FY 2023: 6000
EB-6052 | BIKE/PED | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | RIGHT-OF-WAY | 240000 | FY 2023: 240000
EB-6052 | BIKE/PED | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | TADA | CONSTRUCTION | 751000 | FY 2025: 751000
EL-4828 | BIKE/PED | MORGAN CREEK GREENWAY | WESTERN SECTION, SR 1919 (SMITH LEVEL ROAD) TO UNIVERSITY LAKE IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY TOWN OF CARRBORO | PRE-STI (TRANSITION) |  |  |  | 253000
EL-4828A | BIKE/PED | MORGAN CREEK GREENWAY (CARRBORO) | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | PRE-STI (TRANSITION) |  | TADA | CONSTRUCTION | 730000 | FY 2023: 730000
EL-4828A | BIKE/PED | MORGAN CREEK GREENWAY (CARRBORO) | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | PRE-STI (TRANSITION) |  | BGDA | CONSTRUCTION | 524000 | FY 2023: 524000
EL-4828A | BIKE/PED | MORGAN CREEK GREENWAY (CARRBORO) | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 131000 | FY 2023: 131000
EL-4828A | BIKE/PED | MORGAN CREEK GREENWAY (CARRBORO) | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 183000 | FY 2023: 183000
EL-5100 | BIKE/PED | VARIOUS | PEDESTRIAN, BICYCLE, AND TRANSIT PROJECTS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO). | 4, 5, 6 | Capital Area MPO |  | DIVISION 4, 5, 6 |  |  |  | 22332000
EL-5101 | BIKE/PED | VARIOUS | PEDESTRIAN AND BICYCLE PROJECTS IN THE GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO). | 7 | Greensboro Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS - IN PROGRESS | DIVISION 7 |  |  |  | 32374000
EL-5101DR | BIKE/PED | MURROW BLVD | MURROW BOULEVARD BRIDGE OVER CHURCH STREET. REPAIR BRIDGE DECK AND COMPLETE GREENWAY ACROSS STRUCTURE. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  | BGDA | CONSTRUCTION | 1440000 | FY 2023: 1440000
EL-5101DR | BIKE/PED | MURROW BLVD | MURROW BOULEVARD BRIDGE OVER CHURCH STREET. REPAIR BRIDGE DECK AND COMPLETE GREENWAY ACROSS STRUCTURE. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  | L | CONSTRUCTION | 360000 | FY 2023: 360000
ER-2971 | BIKE/PED | VARIOUS | SIDEWALK PROGRAM IN ALL FOURTEEN HIGHWAY DIVISIONS. | 99 | STATEWIDE PROJECT | IN PROGRESS - $182,000 IN STPDA FUNDS ALLOCATED TO ER-2971E | PRE-STI (TRANSITION) |  |  |  | 25408000
ER-5600 | HIGHWAY | VARIOUS | VEGETATION MANAGEMENT - CLEAR ZONE IMPROVEMENT AND MANAGEMENT STATEWIDE. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 3264000
ER-5600 | HIGHWAY | VARIOUS | VEGETATION MANAGEMENT - CLEAR ZONE IMPROVEMENT AND MANAGEMENT STATEWIDE. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  | STPE | CONSTRUCTION | 4000000 | FY 2023: 2000000
F-5003 | FERRY | NC 45 | SWAN QUARTER VISITORS CENTER. REPLACEMENT. | 1 | Albemarle RPO | COMPLETED. | PRE-STI (TRANSITION) |  |  |  | 2771000
F-5700 | FERRY | NC 12 | CONSTRUCT RIVER CLASS FERRY. | 1 | Albemarle RPO | COMPLETE | DIVISION 1 |  |  |  | 13313000
F-5702 | FERRY | NC 12 | HATTERAS FERRY DOCK IN DARE COUNTY TO OCRACOKE FERRY DOCKS IN HYDE COUNTY. CONSTRUCT TWO PASSENGER FERRIES TO BE USED ALONG NEW ROUTE. IMPLEMENT TRANSIT SYSTEM TO AID PASSENGERS ON OCRACOKE ISLAND. | 1 | Albemarle RPO | OTHER FUNDS ARE FROM STATE APPROPRIATION 7355. | DIVISION 1 |  |  |  | 6700000
F-5703 | FERRY | VARIOUS | REPLACEMENT VESSEL (SUPPORT FLEET) FOR TUGS AND BARGES | 1, 2, 3 | Jacksonville Urban Area MPO, Albemarle RPO, Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RPO |  | DIVISION 1, 2, 3 |  |  |  | 6250000
F-5703A | FERRY | VARIOUS | Z-DRIVE TOWING AND PUSHING TUG | 1, 2, 3 | Albemarle RPO, Cape Fear RPO, Down East RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RP | COMPLETED. | DIVISION 1, 2, 3 |  | T | CONSTRUCTION | 3250000
F-5703B | FERRY | VARIOUS | TWO SUPPORT/ANCHOR TUGS, ONE SUPPORT TUG, THREE BARGES | 1, 2, 3 | Albemarle RPO, Cape Fear RPO, Down East RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RP | COMPLETED. | DIVISION 1, 2, 3 |  | T | CONSTRUCTION | 2100000
F-5704 | FERRY | NC 12 | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY | 1, 2 | Albemarle RPO, Down East RPO |  | DIVISION 1, 2 |  | T | CONSTRUCTION | 25600000 | FY 2025: 12800000; FY 2026: 12800000
F-5705 | FERRY | SOUTHPORT-FORT FISHER | SOUTHPORT-FORT FISHER FERRY. CONSTRUCT RIVER CLASS FERRY. | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 14000000 | [11 empty] | 14000000
F-5706 | FERRY | HATTERAS - SOUTH DOCK | CONSTRUCT PASSENGER FERRY. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 6500000 | [11 empty] | 6500000
F-5707 | FERRY | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | REGION B |  | T | CONSTRUCTION | 5000000 | FY 2025: 2500000; FY 2026: 2500000
FF-0001 | FERRY | NC 12 | HATTERAS AND OCRACOKE ISLAND FERRY RAMP AND DOCK IMPROVEMENTS. | 1 | Albemarle RPO | FLAP PROJECT NC 62. AWARDED $3.5M. | EXEMPT |  | FLAP | CONSTRUCTION | 2430000 | FY 2026: 2430000
FF-0001 | FERRY | NC 12 | HATTERAS AND OCRACOKE ISLAND FERRY RAMP AND DOCK IMPROVEMENTS. | 1 | Albemarle RPO | FLAP PROJECT NC 62. AWARDED $3.5M. | EXEMPT |  | FLAP | ENGINEERING | 1070000 | FY 2023: 1070000
HA-0001 | HIGHWAY | NEW ROUTE | CONSTRUCT ACCESS ROAD INTO BURKE COUNTY INDUSTRIAL PARK. | 13 | Greater Hickory MPO | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000 | EXEMPT |  | ADHSL | ENGINEERING | 287000
HA-0001 | HIGHWAY | NEW ROUTE | CONSTRUCT ACCESS ROAD INTO BURKE COUNTY INDUSTRIAL PARK. | 13 | Greater Hickory MPO | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000 | EXEMPT |  | ADHSL | CONSTRUCTION | 1613000 | FY 2023: 1231000; FY 2024: 382000
HA-0002 | HIGHWAY | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | EXEMPT |  | ADHSL | CONSTRUCTION | 686000 | FY 2023: 550000; FY 2024: 136000
HA-0002 | HIGHWAY | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | EXEMPT |  | ADHSL | ENGINEERING | 200000
HA-0002 | HIGHWAY | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | EXEMPT |  | ADHSL | RIGHT-OF-WAY | 10000
HA-0003 | HIGHWAY | SR 1970 (COMMERCIAL BLVD) | CONSTRUCT ROADWAY EXTENSION TO INDUSTRIAL PARK. | 14 | French Broad River MPO | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000 | EXEMPT |  | ADHSL | RIGHT-OF-WAY | 70000
HA-0003 | HIGHWAY | SR 1970 (COMMERCIAL BLVD) | CONSTRUCT ROADWAY EXTENSION TO INDUSTRIAL PARK. | 14 | French Broad River MPO | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000 | EXEMPT |  | ADHSL | CONSTRUCTION | 1830000
HA-0004 | HIGHWAY | US 441 | SR 1515 (HYATT ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND RIGHT-IN/RIGHT-OUT AT INGLES DEVELOPMENT SITE. | 14 | Southwestern RPO | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,500,000. UNDER CONSTRUCTION. | EXEMPT |  |  |  | 300000
HA-0004 | HIGHWAY | US 441 | SR 1515 (HYATT ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND RIGHT-IN/RIGHT-OUT AT INGLES DEVELOPMENT SITE. | 14 | Southwestern RPO | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,500,000. UNDER CONSTRUCTION. | EXEMPT |  | ADHSL | CONSTRUCTION | 1500000 | FY 2023: 454000
HA-0005 | HIGHWAY | NEW ROUTE | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | EXEMPT |  | ADHSL | ENGINEERING | 15000
HA-0005 | HIGHWAY | NEW ROUTE | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | EXEMPT |  | ADHSL | RIGHT-OF-WAY | 15000 | FY 2023: 15000
HA-0005 | HIGHWAY | NEW ROUTE | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | EXEMPT |  | ADHSL | CONSTRUCTION | 900000 | FY 2023: 10000; FY 2024: 890000
HA-0006 | HIGHWAY | NORTHWEST DRIVE, AEV LANE | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AMERICAN EMERGENCY VEHICLES LANE FROM NORTHWEST DRIVE TO AMERICAN EMERGENCY VEHICLES FACILITY. WIDEN PAVEMENT AND INSTALL SIGNAL AT NC 88 AND NORTHWEST DRIVE. | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | EXEMPT |  | ADHSL | ENGINEERING | 47000 | FY 2023: 47000
HA-0006 | HIGHWAY | NORTHWEST DRIVE, AEV LANE | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AMERICAN EMERGENCY VEHICLES LANE FROM NORTHWEST DRIVE TO AMERICAN EMERGENCY VEHICLES FACILITY. WIDEN PAVEMENT AND INSTALL SIGNAL AT NC 88 AND NORTHWEST DRIVE. | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | EXEMPT |  | ADHSL | CONSTRUCTION | 643000 | FY 2025: 643000
HA-0006 | HIGHWAY | NORTHWEST DRIVE, AEV LANE | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AMERICAN EMERGENCY VEHICLES LANE FROM NORTHWEST DRIVE TO AMERICAN EMERGENCY VEHICLES FACILITY. WIDEN PAVEMENT AND INSTALL SIGNAL AT NC 88 AND NORTHWEST DRIVE. | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | EXEMPT |  | ADHSL | RIGHT-OF-WAY | 60000 | FY 2024: 60000
HB-0001 | HIGHWAY | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. | STATEWIDE MOBILITY |  | HFB | CONSTRUCTION | 52400000 | FY 2024: 9956000; FY 2025: 12576000; FY 2026: 11528000; FY 2027: 9956000; FY 2028: 8384000
HB-0001 | HIGHWAY | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 6300000 | FY 2024: 0; FY 2025: 0; FY 2026: 2299000; FY 2027: 2172000; FY 2028: 1829000
HB-0001 | HIGHWAY | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. | STATEWIDE MOBILITY |  | HFB | UTILITIES | 500000 | FY 2023: 500000
HB-0001 | HIGHWAY | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. | STATEWIDE MOBILITY |  | HFB | RIGHT-OF-WAY | 500000 | FY 2023: 500000
HB-0001 | HIGHWAY | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 94100000 | FY 2024: 39824000; FY 2025: 50304000; FY 2026: 3972000
HB-0001 | HIGHWAY | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 109200000 | FY 2024: 0; FY 2025: 0; FY 2026: 39841000; FY 2027: 37652000; FY 2028: 31707000
HB-0001 | HIGHWAY | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. | STATEWIDE MOBILITY |  |  |  | 5100000
HB-0001A | HIGHWAY | US 64 | BROADBAND AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 5300000 | FY 2026: 5300000
HB-0001A | HIGHWAY | US 64 | BROADBAND AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 5300000 | FY 2026: 5300000
HB-0001A | HIGHWAY | US 64 | BROADBAND AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 15900000 | FY 2026: 15900000
HB-0002 | HIGHWAY | I-40 | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 17500000 | FY 2024: 8750000; FY 2025: 8750000
HB-0002 | HIGHWAY | I-40 | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 2000000 | FY 2023: 1600000; FY 2024: 200000; FY 2025: 200000
HB-0003 | HIGHWAY | I-40 | REPLACE BRIDGE 430239 OVER SR 1550 (INCINERATOR ROAD). | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 1000000 | FY 2023: 200000; FY 2024: 600000; FY 2025: 100000; FY 2026: 100000
HB-0003 | HIGHWAY | I-40 | REPLACE BRIDGE 430239 OVER SR 1550 (INCINERATOR ROAD). | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 17100000 | FY 2024: 8550000; FY 2025: 8550000
HB-0004 | HIGHWAY | I-40 | REPLACE BRIDGE 430243 OVER NC 215 (CHAMPION DRIVE). | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 1000000 | FY 2023: 800000; FY 2024: 100000; FY 2025: 100000
HB-0004 | HIGHWAY | I-40 | REPLACE BRIDGE 430243 OVER NC 215 (CHAMPION DRIVE). | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 7300000 | FY 2023: 3650000; FY 2024: 3650000
HB-0005 | HIGHWAY | I-40 | REPLACE BRIDGES 430205 AND 430208 OVER SR 1364 (COLEMAN MOUNTAIN ROAD). | 14 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 9400000 | FY 2030: 4700000; FY 2031: 4700000
HB-0005 | HIGHWAY | I-40 | REPLACE BRIDGES 430205 AND 430208 OVER SR 1364 (COLEMAN MOUNTAIN ROAD). | 14 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 2000000 | FY 2024: 436000; FY 2025: 582000; FY 2026: 582000; FY 2028: 200000; FY 2029: 200000
HB-0006 | HIGHWAY | US 74 | REPLACE BRIDGE 430126 OVER I-40. | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 9000000 | FY 2030: 4500000; FY 2031: 4500000
HB-0006 | HIGHWAY | US 74 | REPLACE BRIDGE 430126 OVER I-40. | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 1000000 | FY 2024: 218000; FY 2025: 291000; FY 2026: 291000; FY 2028: 100000; FY 2029: 100000
HB-0007 | HIGHWAY | CHURCH ROAD) SR 1529 (MOUNT OLIVE | REPLACE BRIDGE 770299 AND 770300 OVER SADDLE TREE SWAMP. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | BGOFF | UTILITIES | 170000 | FY 2023: 170000
HB-0007 | HIGHWAY | CHURCH ROAD) SR 1529 (MOUNT OLIVE | REPLACE BRIDGE 770299 AND 770300 OVER SADDLE TREE SWAMP. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | BGOFF | CONSTRUCTION | 1700000 | FY 2024: 1700000
HB-0007 | HIGHWAY | CHURCH ROAD) SR 1529 (MOUNT OLIVE | REPLACE BRIDGE 770299 AND 770300 OVER SADDLE TREE SWAMP. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | BGOFF | RIGHT-OF-WAY | 170000 | FY 2023: 170000
HB-0008 | HIGHWAY | CHURCH ROAD) SR 1214 (MOUNT PISGAH | REPLACE BRIDGE 420034 OVER UPPER LITTLE RIVER. | 6 | Mid-Carolina RPO |  | DIVISION 6 |  | BGOFF | RIGHT-OF-WAY | 330000 | FY 2027: 330000
HB-0008 | HIGHWAY | CHURCH ROAD) SR 1214 (MOUNT PISGAH | REPLACE BRIDGE 420034 OVER UPPER LITTLE RIVER. | 6 | Mid-Carolina RPO |  | DIVISION 6 |  | BGOFF | CONSTRUCTION | 1900000 | FY 2028: 1216000; FY 2029: 684000
HB-0009 | HIGHWAY | ROAD) SR 1800 (BLACKSMITH | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | 6 | Cape Fear RPO |  | DIVISION 6 |  | BGOFF | RIGHT-OF-WAY | 140000 | FY 2029: 140000
HB-0009 | HIGHWAY | ROAD) SR 1800 (BLACKSMITH | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | 6 | Cape Fear RPO |  | DIVISION 6 |  | BGOFF | UTILITIES | 110000 | FY 2029: 110000
HB-0009 | HIGHWAY | ROAD) SR 1800 (BLACKSMITH | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | 6 | Cape Fear RPO |  | DIVISION 6 |  | BGOFF | CONSTRUCTION | 1400000 | FY 2030: 1400000
HB-0010 | HIGHWAY | SR 1716 (JACKIE LEE ROAD) | REPLACE BRIDGE 250091 OVER WADE CANAL. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | BGOFF | RIGHT-OF-WAY | 120000 | FY 2029: 120000
HB-0010 | HIGHWAY | SR 1716 (JACKIE LEE ROAD) | REPLACE BRIDGE 250091 OVER WADE CANAL. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | BGOFF | CONSTRUCTION | 850000 | FY 2030: 850000
HB-0016 | HIGHWAY | NC 32 | PRESERVATION OF BRIDGE 930015 ON NC 32 OVER ALBEMARLE SOUND. | 1 | Albemarle RPO |  | REGION A |  | BFP | CONSTRUCTION | 50000000 | FY 2027: 7500000; FY 2028: 12500000; FY 2029: 12500000; FY 2030: 12500000; FY 2031: 5000000
HB-0017 | HIGHWAY | US 64 | PRESERVATION OF BRIDGE 270009 ON US 64 IN MANNS HARBOR. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | REGION A |  | BFP | CONSTRUCTION | 38823000 | FY 2023: 7323000; FY 2024: 11250000; FY 2025: 11250000
HB-0018 | HIGHWAY | I-40 | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 40600000 | FY 2026: 13533000; FY 2027: 13533000; FY 2028: 13534000
HB-0018 | HIGHWAY | I-40 | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | BFP | RIGHT-OF-WAY | 700000
HB-0018 | HIGHWAY | I-40 | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | BFP | UTILITIES | 700000
HB-0020 | HIGHWAY | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 11 | High Country RPO |  | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 897000 | FY 2025: 341000; FY 2026: 376000; FY 2027: 90000; FY 2028: 90000
HB-0020 | HIGHWAY | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 11 | High Country RPO |  | DIVISION 11 |  | HFB | CONSTRUCTION | 5120000 | FY 2027: 51000; FY 2028: 3071000; FY 2029: 1998000
HB-0020 | HIGHWAY | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 11 | High Country RPO |  | DIVISION 11 |  | DP | CONSTRUCTION | 1280000 | FY 2027: 13000; FY 2028: 768000; FY 2029: 499000
HB-0020 | HIGHWAY | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 11 | High Country RPO |  | DIVISION 11 |  | DP | RIGHT-OF-WAY | 223000 | FY 2025: 85000; FY 2026: 94000; FY 2027: 22000; FY 2028: 22000
HB-0021 | HIGHWAY | OXFORD ROAD | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | BGOFF | UTILITIES | 143000 | FY 2024: 143000
HB-0021 | HIGHWAY | OXFORD ROAD | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | BGOFF | CONSTRUCTION | 1668000 | FY 2024: 1152000; FY 2025: 516000
HB-0021 | HIGHWAY | OXFORD ROAD | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | BGOFF | RIGHT-OF-WAY | 50000 | FY 2023: 50000
HB-0022 | HIGHWAY | ROCK SPRINGS ROAD | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | BGOFF | RIGHT-OF-WAY | 100000 | FY 2029: 100000
HB-0022 | HIGHWAY | ROCK SPRINGS ROAD | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | BGOFF | UTILITIES | 126000 | FY 2029: 126000
HB-0022 | HIGHWAY | ROCK SPRINGS ROAD | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | BGOFF | CONSTRUCTION | 2277000 | FY 2030: 700000; FY 2031: 1577000
HB-0023 | HIGHWAY | SR 1876 (SONOMA ROAD) | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 80000 | FY 2023: 80000
HB-0023 | HIGHWAY | SR 1876 (SONOMA ROAD) | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | BGOFF | UTILITIES | 80000 | FY 2023: 80000
HB-0023 | HIGHWAY | SR 1876 (SONOMA ROAD) | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | BGOFF | CONSTRUCTION | 1600000 | FY 2024: 1600000
HB-0024 | HIGHWAY | US-401 | REPLACE BRIDGE 340056 OVER SANDY CREEK. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGOFF | RIGHT-OF-WAY | 100000 | FY 2027: 100000
HB-0024 | HIGHWAY | US-401 | REPLACE BRIDGE 340056 OVER SANDY CREEK. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGOFF | UTILITIES | 100000 | FY 2027: 100000
HB-0024 | HIGHWAY | US-401 | REPLACE BRIDGE 340056 OVER SANDY CREEK. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGOFF | CONSTRUCTION | 2846000 | FY 2028: 2846000
HB-0025 | HIGHWAY | SR 1004 (POORS FORD ROAD) | REPLACE BRIDGE 740087 OVER BROAD RIVER. | 14 | Foothills RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 5200000 | FY 2027: 5200000
HB-0025 | HIGHWAY | SR 1004 (POORS FORD ROAD) | REPLACE BRIDGE 740087 OVER BROAD RIVER. | 14 | Foothills RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 260000 | FY 2024: 260000
HB-0025 | HIGHWAY | SR 1004 (POORS FORD ROAD) | REPLACE BRIDGE 740087 OVER BROAD RIVER. | 14 | Foothills RPO |  | DIVISION 14 |  | BGOFF | UTILITIES | 260000 | FY 2024: 260000
HB-0026 | HIGHWAY | SR 1533 (EVERETT ROAD) | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | 14 | Land-of-Sky RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 4000000 | FY 2028: 4000000
HB-0026 | HIGHWAY | SR 1533 (EVERETT ROAD) | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | 14 | Land-of-Sky RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 200000 | FY 2024: 200000
HB-0026 | HIGHWAY | SR 1533 (EVERETT ROAD) | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | 14 | Land-of-Sky RPO |  | DIVISION 14 |  | BGOFF | UTILITIES | 200000 | FY 2024: 200000
HB-0027 | HIGHWAY | SR 1355 (PANTHER CREEK ROAD) | REPLACE BRIDGE 430206 OVER FINES CREEK. | 14 | Land-of-Sky RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 50000 | FY 2024: 50000
HB-0027 | HIGHWAY | SR 1355 (PANTHER CREEK ROAD) | REPLACE BRIDGE 430206 OVER FINES CREEK. | 14 | Land-of-Sky RPO |  | DIVISION 14 |  | BGOFF | UTILITIES | 50000 | FY 2024: 50000
HB-0027 | HIGHWAY | SR 1355 (PANTHER CREEK ROAD) | REPLACE BRIDGE 430206 OVER FINES CREEK. | 14 | Land-of-Sky RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 1000000 | FY 2027: 1000000
HB-0029 | HIGHWAY | SR 1179 (BRIDGE STREET) | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGOFF | UTILITIES | 100000 | FY 2025: 100000
HB-0029 | HIGHWAY | SR 1179 (BRIDGE STREET) | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2026: 2000000
HB-0029 | HIGHWAY | SR 1179 (BRIDGE STREET) | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGOFF | RIGHT-OF-WAY | 100000 | FY 2025: 100000
HB-0030 | HIGHWAY | SR 1679 (PEEKS CREEK ROAD) | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 100000 | FY 2025: 100000
HB-0030 | HIGHWAY | SR 1679 (PEEKS CREEK ROAD) | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | UTILITIES | 100000 | FY 2025: 100000
HB-0030 | HIGHWAY | SR 1679 (PEEKS CREEK ROAD) | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2026: 2000000
HB-0031 | HIGHWAY | THIRD STREET | REPLACE BRIDGE 330185 OVER US 52 / NC 8 IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | RIGHT-OF-WAY | 275000 | FY 2025: 275000
HB-0031 | HIGHWAY | THIRD STREET | REPLACE BRIDGE 330185 OVER US 52 / NC 8 IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | UTILITIES | 275000 | FY 2025: 275000
HB-0031 | HIGHWAY | THIRD STREET | REPLACE BRIDGE 330185 OVER US 52 / NC 8 IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | CONSTRUCTION | 5500000 | FY 2026: 5500000
HB-0032 | HIGHWAY | SR 1004 (HUDSON CHAPEL ROAD) | REPLACE BRIDGE 480081 CATAWBA RIVER. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGOFF | RIGHT-OF-WAY | 775000 | FY 2025: 775000
HB-0032 | HIGHWAY | SR 1004 (HUDSON CHAPEL ROAD) | REPLACE BRIDGE 480081 CATAWBA RIVER. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGOFF | UTILITIES | 775000 | FY 2025: 775000
HB-0032 | HIGHWAY | SR 1004 (HUDSON CHAPEL ROAD) | REPLACE BRIDGE 480081 CATAWBA RIVER. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGOFF | CONSTRUCTION | 15500000 | FY 2027: 7750000; FY 2028: 7750000
HB-0033 | HIGHWAY | POLO ROAD | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BFP | RIGHT-OF-WAY | 300000 | FY 2027: 300000
HB-0033 | HIGHWAY | POLO ROAD | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BFP | UTILITIES | 300000 | FY 2027: 300000
HB-0033 | HIGHWAY | POLO ROAD | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BFP | CONSTRUCTION | 6000000 | FY 2028: 6000000
HB-0034 | HIGHWAY | SR 1007 (PLANK ROAD) | REPLACE BRIDGE 180169 OVER DEEP RIVER. | 8 | Triangle Area RPO |  | DIVISION 8 |  | BGOFF | UTILITIES | 325000 | FY 2025: 325000
HB-0034 | HIGHWAY | SR 1007 (PLANK ROAD) | REPLACE BRIDGE 180169 OVER DEEP RIVER. | 8 | Triangle Area RPO |  | DIVISION 8 |  | BGOFF | CONSTRUCTION | 6500000 | FY 2026: 6500000
HB-0034 | HIGHWAY | SR 1007 (PLANK ROAD) | REPLACE BRIDGE 180169 OVER DEEP RIVER. | 8 | Triangle Area RPO |  | DIVISION 8 |  | BGOFF | RIGHT-OF-WAY | 325000 | FY 2025: 325000
HB-0035 | HIGHWAY | SR 1535 (PRICE ROAD) | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | BGOFF | UTILITIES | 180000 | FY 2025: 180000
HB-0035 | HIGHWAY | SR 1535 (PRICE ROAD) | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | BGOFF | CONSTRUCTION | 3600000 | FY 2026: 3600000
HB-0035 | HIGHWAY | SR 1535 (PRICE ROAD) | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | BGOFF | RIGHT-OF-WAY | 180000 | FY 2025: 180000
HB-0036 | HIGHWAY | SIXTEENTH STREET | REPLACE BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | RIGHT-OF-WAY | 210000 | FY 2026: 210000
HB-0036 | HIGHWAY | SIXTEENTH STREET | REPLACE BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | UTILITIES | 210000 | FY 2026: 210000
HB-0036 | HIGHWAY | SIXTEENTH STREET | REPLACE BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | CONSTRUCTION | 4200000 | FY 2027: 4200000
HB-0037 | HIGHWAY | SR 1679 (GOLD MINE ROAD) | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | RIGHT-OF-WAY | 50000 | FY 2026: 50000
HB-0037 | HIGHWAY | SR 1679 (GOLD MINE ROAD) | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | UTILITIES | 50000 | FY 2026: 50000
HB-0037 | HIGHWAY | SR 1679 (GOLD MINE ROAD) | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGOFF | CONSTRUCTION | 1000000 | FY 2027: 1000000
HB-0038 | HIGHWAY | SR 1745 (BEND OF THE RIVER ROAD) | REPLACE BRIDGE 630110 OVER TAR RIVER RESERVOIR. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | BGOFF | RIGHT-OF-WAY | 310000 | FY 2026: 310000
HB-0038 | HIGHWAY | SR 1745 (BEND OF THE RIVER ROAD) | REPLACE BRIDGE 630110 OVER TAR RIVER RESERVOIR. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | BGOFF | UTILITIES | 310000 | FY 2026: 310000
HB-0038 | HIGHWAY | SR 1745 (BEND OF THE RIVER ROAD) | REPLACE BRIDGE 630110 OVER TAR RIVER RESERVOIR. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | BGOFF | CONSTRUCTION | 6200000 | FY 2027: 6200000
HB-0043 | HIGHWAY | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 101000 | FY 2025: 101000
HB-0043 | HIGHWAY | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 576000 | FY 2026: 576000
HB-0043 | HIGHWAY | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 144000 | FY 2026: 144000
HB-0043 | HIGHWAY | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 25000 | FY 2025: 25000
HB-0044 | HIGHWAY | SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 240000 | FY 2028: 240000
HB-0044 | HIGHWAY | SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 168000 | FY 2027: 168000
HB-0044 | HIGHWAY | SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 960000 | FY 2028: 960000
HB-0044 | HIGHWAY | SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 42000 | FY 2027: 42000
HB-0045 | HIGHWAY | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2028: 160000
HB-0045 | HIGHWAY | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2027: 112000
HB-0045 | HIGHWAY | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2027: 28000
HB-0045 | HIGHWAY | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2028: 640000
HB-0046 | HIGHWAY | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 36000 | FY 2024: 36000
HB-0046 | HIGHWAY | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 208000 | FY 2025: 208000
HB-0046 | HIGHWAY | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 146000 | FY 2024: 146000
HB-0046 | HIGHWAY | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 832000 | FY 2025: 832000
HB-0047 | HIGHWAY | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 128000 | FY 2026: 128000
HB-0047 | HIGHWAY | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 90000 | FY 2025: 90000
HB-0047 | HIGHWAY | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 22000 | FY 2025: 22000
HB-0047 | HIGHWAY | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 512000 | FY 2026: 512000
HB-0048 | HIGHWAY | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2027: 28000
HB-0048 | HIGHWAY | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2028: 160000
HB-0048 | HIGHWAY | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2027: 112000
HB-0048 | HIGHWAY | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2028: 640000
HB-0049 | HIGHWAY | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 320000 | FY 2028: 320000
HB-0049 | HIGHWAY | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 224000 | FY 2027: 224000
HB-0049 | HIGHWAY | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 56000 | FY 2027: 56000
HB-0049 | HIGHWAY | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 1280000 | FY 2028: 1280000
HB-0050 | HIGHWAY | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 56000 | FY 2027: 56000
HB-0050 | HIGHWAY | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 320000 | FY 2028: 320000
HB-0050 | HIGHWAY | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 224000 | FY 2027: 224000
HB-0050 | HIGHWAY | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 1280000 | FY 2028: 1280000
HB-0051 | HIGHWAY | SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 168000 | FY 2025: 168000
HB-0051 | HIGHWAY | SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 960000 | FY 2026: 960000
HB-0051 | HIGHWAY | SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 240000 | FY 2026: 240000
HB-0051 | HIGHWAY | SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 42000 | FY 2025: 42000
HB-0052 | HIGHWAY | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 208000 | FY 2025: 208000
HB-0052 | HIGHWAY | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 146000 | FY 2024: 146000
HB-0052 | HIGHWAY | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 832000 | FY 2025: 832000
HB-0052 | HIGHWAY | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 36000 | FY 2024: 36000
HB-0053 | HIGHWAY | SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 144000 | FY 2028: 144000
HB-0053 | HIGHWAY | SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 101000 | FY 2027: 101000
HB-0053 | HIGHWAY | SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 25000 | FY 2027: 25000
HB-0053 | HIGHWAY | SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 576000 | FY 2028: 576000
HB-0054 | HIGHWAY | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 56000 | FY 2025: 56000
HB-0054 | HIGHWAY | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 320000 | FY 2026: 320000
HB-0054 | HIGHWAY | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 224000 | FY 2025: 224000
HB-0054 | HIGHWAY | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 1280000 | FY 2026: 1280000
HB-0055 | HIGHWAY | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2025: 160000
HB-0055 | HIGHWAY | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2024: 112000
HB-0055 | HIGHWAY | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2024: 28000
HB-0055 | HIGHWAY | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2025: 640000
HB-0056 | HIGHWAY | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2026: 28000
HB-0056 | HIGHWAY | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2027: 160000
HB-0056 | HIGHWAY | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2026: 112000
HB-0056 | HIGHWAY | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2027: 640000
HB-0057 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2024: 160000
HB-0057 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2023: 112000
HB-0057 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2023: 28000
HB-0057 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2024: 640000
HB-0058 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2023: 28000
HB-0058 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2024: 160000
HB-0058 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2023: 112000
HB-0058 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2024: 640000
HB-0059 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2024: 160000
HB-0059 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2023: 112000
HB-0059 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2023: 28000
HB-0059 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2024: 640000
HB-0060 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 36000 | FY 2023: 36000
HB-0060 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 208000 | FY 2024: 208000
HB-0060 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 146000 | FY 2023: 146000
HB-0060 | HIGHWAY | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 832000 | FY 2024: 832000
HB-0061 | HIGHWAY | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 128000 | FY 2027: 128000
HB-0061 | HIGHWAY | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 90000 | FY 2026: 90000
HB-0061 | HIGHWAY | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 22000 | FY 2026: 22000
HB-0061 | HIGHWAY | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 512000 | FY 2027: 512000
HB-0062 | HIGHWAY | SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2024: 28000
HB-0062 | HIGHWAY | SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2025: 160000
HB-0062 | HIGHWAY | SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2024: 112000
HB-0062 | HIGHWAY | SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2025: 640000
HB-0063 | HIGHWAY | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2025: 160000
HB-0063 | HIGHWAY | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2024: 112000
HB-0063 | HIGHWAY | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2024: 28000
HB-0063 | HIGHWAY | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2025: 640000
HB-0064 | HIGHWAY | SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 22000 | FY 2024: 22000
HB-0064 | HIGHWAY | SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 128000 | FY 2025: 128000
HB-0064 | HIGHWAY | SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 90000 | FY 2024: 90000
HB-0064 | HIGHWAY | SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 512000 | FY 2025: 512000
HB-0065 | HIGHWAY | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 25000 | FY 2026: 25000
HB-0065 | HIGHWAY | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 576000 | FY 2027: 576000
HB-0065 | HIGHWAY | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 144000 | FY 2027: 144000
HB-0065 | HIGHWAY | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 101000 | FY 2026: 101000
HB-0066 | HIGHWAY | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2024: 28000
HB-0066 | HIGHWAY | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2025: 160000
HB-0066 | HIGHWAY | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2024: 112000
HB-0066 | HIGHWAY | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2025: 640000
HB-0067 | HIGHWAY | SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2025: 160000
HB-0067 | HIGHWAY | SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2024: 112000
HB-0067 | HIGHWAY | SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2025: 640000
HB-0067 | HIGHWAY | SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2024: 28000
HB-0068 | HIGHWAY | SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | RIGHT-OF-WAY | 28000 | FY 2024: 28000
HB-0068 | HIGHWAY | SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | DP | CONSTRUCTION | 160000 | FY 2025: 160000
HB-0068 | HIGHWAY | SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | RIGHT-OF-WAY | 112000 | FY 2024: 112000
HB-0068 | HIGHWAY | SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | DIVISION 11 |  | HFB | CONSTRUCTION | 640000 | FY 2025: 640000
HB-0069 | HIGHWAY | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | REGION F |  | DP | CONSTRUCTION | 1920000 | FY 2027: 1920000
HB-0069 | HIGHWAY | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | REGION F |  | HFB | RIGHT-OF-WAY | 1344000 | FY 2025: 1344000
HB-0069 | HIGHWAY | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | REGION F |  | DP | RIGHT-OF-WAY | 336000 | FY 2025: 336000
HB-0069 | HIGHWAY | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | REGION F |  | HFB | CONSTRUCTION | 7680000 | FY 2027: 7680000
HB-8888 | HIGHWAY | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | BGOFF | CONSTRUCTION | 353413000 |  | 6844000 | 32732000 | 19395000 | 11028000 | 12892000 | 32990000 | 35922000 | 31434000 | 37990000 | 44062000 | 88124000
HB-8888DIV | HIGHWAY | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | BFP | CONSTRUCTION | 155544000 |  | 0 | 0 | 0 | 0 | 0 | 3140000 | 8012000 | 12549000 | 28274000 | 32711000 | 70858000
HB-8888REG | HIGHWAY | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | REGION SW |  | BFP | CONSTRUCTION | 155544000 |  | 0 | 0 | 0 | 0 | 0 | 3140000 | 8012000 | 12549000 | 28274000 | 32711000 | 70858000
HB-8888SW | HIGHWAY | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | BFP | CONSTRUCTION | 207391000 |  | 0 | 0 | 0 | 0 | 0 | 4186000 | 10683000 | 16732000 | 37699000 | 43615000 | 94476000
HB-9999ADIV | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 117000000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 15600000
HB-9999AREG | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 117000000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 15600000
HB-9999ASW | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 156000000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 20800000
HB-9999BDIV | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 9000000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 1200000
HB-9999CDIV | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 11700000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 1560000
HB-9999CREG | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 11700000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 1560000
HB-9999CSW | HIGHWAY | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 15600000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 2080000
HE-0001 | HIGHWAY | I-26 | CONSTRUCT NEW INTERCHANGE NEAR AND ACCESS ROAD NEAR MILEMARKER 35, CONNECTING TO FREDERICK LAW OLMSTEAD WAY EAST. | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. STATE FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY. | EXEMPT |  | ADHSL | CONSTRUCTION | 2500000 | FY 2024: 2500000
HE-0001 | HIGHWAY | I-26 | CONSTRUCT NEW INTERCHANGE NEAR AND ACCESS ROAD NEAR MILEMARKER 35, CONNECTING TO FREDERICK LAW OLMSTEAD WAY EAST. | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. STATE FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY. | EXEMPT |  | S | CONSTRUCTION | 30000000 | FY 2024: 30000000
HE-0002 | HIGHWAY | NEW ROUTE; SR 1152 (HOLLY SPRINGS - NEW HILL ROAD) | NEW ROUTE INTERSECTING GREEN OAKS PARKWAY BETWEEN THOMAS MILL ROAD AND NC 55, SR 1153 INTERSECTION WITH BENNET KNOLL PARKWAY, AND SR 1152 INTERSECTION WITH SR 1153 IN HOLLY SPRINGS. CONSTRUCT ACCESS ROAD AND INTERSESCTION IMPROVEMENTS. | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FUJIFILM DIOSYNTH BIOTECHNOLOGIES. | DIVISION 5 |  | T | RIGHT-OF-WAY | 10000 | FY 2023: 10000
HE-0002 | HIGHWAY | NEW ROUTE; SR 1152 (HOLLY SPRINGS - NEW HILL ROAD) | NEW ROUTE INTERSECTING GREEN OAKS PARKWAY BETWEEN THOMAS MILL ROAD AND NC 55, SR 1153 INTERSECTION WITH BENNET KNOLL PARKWAY, AND SR 1152 INTERSECTION WITH SR 1153 IN HOLLY SPRINGS. CONSTRUCT ACCESS ROAD AND INTERSESCTION IMPROVEMENTS. | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FUJIFILM DIOSYNTH BIOTECHNOLOGIES. | DIVISION 5 |  | T | CONSTRUCTION | 9690000 | FY 2024: 95000; FY 2025: 5105000; FY 2026: 4490000
HE-0003 | HIGHWAY | SR 1710 (GRACE DRIVE/ WATKINS DRIVE) AND SR 1737 | FROM US-158 TO NORTH OF SR 1734 (KENNAMETAL DRIVE). WIDEN TO FOUR LANES. REALIGN SR 1737 (POWER PLACE) AND US-158 INTERSECTION. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR ROSEBURG FOREST PRODUCTS. | DIVISION 4 |  | T | CONSTRUCTION | 2000000 | FY 2023: 250000
HE-0004 | HIGHWAY | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | DIVISION 8 |  | T | CONSTRUCTION | 10000000 | FY 2023: 5000000; FY 2024: 5000000
HE-0004 | HIGHWAY | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | DIVISION 8 |  | S | RIGHT-OF-WAY | 5000000
HE-0004 | HIGHWAY | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | DIVISION 8 |  | S | UTILITIES | 2000000
HE-0004 | HIGHWAY | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | DIVISION 8 |  | S | CONSTRUCTION | 27000000 | FY 2023: 27000000
HE-0004 | HIGHWAY | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | DIVISION 8 |  | S | MITIGATION | 1000000 | FY 2023: 1000000
HE-0005 | HIGHWAY | VARIOUS | CONSTUCT ROAD IMPROVEMENTS AND WETLANDS MITIGATION AT THE PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | EXEMPT |  | S | CONSTRUCTION | 30000000 | FY 2023: 8619000; FY 2024: 13416000; FY 2025: 6199000; FY 2026: 1766000
HE-0005 | HIGHWAY | VARIOUS | CONSTUCT ROAD IMPROVEMENTS AND WETLANDS MITIGATION AT THE PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | EXEMPT |  | S | UTILITIES | 500000
HE-0005 | HIGHWAY | VARIOUS | CONSTUCT ROAD IMPROVEMENTS AND WETLANDS MITIGATION AT THE PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | EXEMPT |  | S | RIGHT-OF-WAY | 1000000
HE-0006A | HIGHWAY | VARIOUS | CONSTRUCTION OF SITE DESIGN 1A. RESURFACING AND STRENGTHENING OF SURROUNDING ROADWAYS NEAR TRIANGLE INNOVATION POINT MEGASITE. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | HIGHWAY FUND |  | S | CONSTRUCTION | 7000000 | FY 2023: 7000000
HE-0006B | HIGHWAY | VARIOUS | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | HIGHWAY FUND |  | S | ENGINEERING | 3000000 | FY 2023: 3000000
HE-0006B | HIGHWAY | VARIOUS | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | HIGHWAY FUND |  | S | RIGHT-OF-WAY | 10000000 | FY 2023: 5000000; FY 2024: 5000000
HE-0006B | HIGHWAY | VARIOUS | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | HIGHWAY FUND |  | S | UTILITIES | 5000000 | FY 2023: 2500000; FY 2024: 2500000
HE-0006B | HIGHWAY | VARIOUS | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | HIGHWAY FUND |  | S | CONSTRUCTION | 175000000 | FY 2024: 100000000; FY 2025: 75000000
HE-0006C | HIGHWAY | VARIOUS | CONSTRUCTION OF SITE DESIGN 2A AND 2B. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | HIGHWAY FUND |  | S | CONSTRUCTION | 50000000 | FY 2025: 25000000; FY 2026: 25000000
HE-0007A | HIGHWAY | SR 1004 (OLD OXFORD ROAD) | FIRST AVE (MERCK DRIVEWAY). CONSTRUCT RIGHT TURN LANE. | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | DIVISION 5 |  | T | ENGINEERING | 25000 | FY 2023: 25000
HE-0007A | HIGHWAY | SR 1004 (OLD OXFORD ROAD) | FIRST AVE (MERCK DRIVEWAY). CONSTRUCT RIGHT TURN LANE. | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | DIVISION 5 |  | T | CONSTRUCTION | 165000 | FY 2023: 2000; FY 2024: 163000
HE-0007B | HIGHWAY | SR 1794 (TEKNIKA PARKWAY) | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | T | ENGINEERING | 90000 | FY 2023: 90000
HE-0007B | HIGHWAY | SR 1794 (TEKNIKA PARKWAY) | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | T | RIGHT-OF-WAY | 95000 | FY 2023: 95000
HE-0007B | HIGHWAY | SR 1794 (TEKNIKA PARKWAY) | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | T | CONSTRUCTION | 815000 | FY 2023: 8000; FY 2024: 807000
HE-0007C | HIGHWAY | SR 2635 (INTERNATIONAL DRIVE) | SR 1004 (OLD OXFORD RD) TO NEW LOCATION. CONSTRUCT NEW LANES. | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY | DIVISION 5 |  | T | ENGINEERING | 600000 | FY 2023: 300000; FY 2024: 300000
HE-0008 | HIGHWAY | US 64 | EXTEND LEFT TURN LANE AND CONSTRUCT RIGHT TURN LANE AT PROPOSED NEW ACCESS ROAD ACROSS FROM SR 2112 (DECKER ROAD) AND WIDEN RAIL CROSSING 836515Y. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR. | DIVISION 9 |  | T | ENGINEERING | 300000
HE-0008 | HIGHWAY | US 64 | EXTEND LEFT TURN LANE AND CONSTRUCT RIGHT TURN LANE AT PROPOSED NEW ACCESS ROAD ACROSS FROM SR 2112 (DECKER ROAD) AND WIDEN RAIL CROSSING 836515Y. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR. | DIVISION 9 |  | T | CONSTRUCTION | 1500000 | FY 2023: 15000; FY 2024: 1485000
HE-0009 | HIGHWAY | NC 152 | WIDEN PAVEMENT AND CONSTRUCT ROUNDABOUT AT THE INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. | 9 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | DIVISION 9 |  | T | CONSTRUCTION | 3900000 | FY 2024: 39000; FY 2025: 2894000; FY 2026: 967000
HE-0009 | HIGHWAY | NC 152 | WIDEN PAVEMENT AND CONSTRUCT ROUNDABOUT AT THE INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. | 9 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | DIVISION 9 |  | T | ENGINEERING | 600000
HE-0009A | HIGHWAY | NC 152 | NC 152, INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. INTERMEDIATE INTERSECTION IMPROVEMENTS. WIDEN PAVEMENT AND CONSTRUCT TURN LANES FOR PHASE I OF ROADWAY IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. CONSTRUCTION BY STATE FORCES. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | DIVISION 9 |  | T | CONSTRUCTION | 1000000 | FY 2023: 1000000
HE-0010 | HIGHWAY | VARIOUS | INTERCHANGE IMPROVEMENTS AT US 1 / SR 1127 (NEW HILL-HOLLEMANN ROAD), INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) / SR 1149 (FRIENDSHIP ROAD) AND SR 1149 (FRIENDSHIP ROAD) / SR 1152 (OLD HOLLY SPRINGS-NEW HILL ROAD). | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | DIVISION 5 |  | T | ENGINEERING | 500000 | FY 2023: 500000
HE-0010 | HIGHWAY | VARIOUS | INTERCHANGE IMPROVEMENTS AT US 1 / SR 1127 (NEW HILL-HOLLEMANN ROAD), INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) / SR 1149 (FRIENDSHIP ROAD) AND SR 1149 (FRIENDSHIP ROAD) / SR 1152 (OLD HOLLY SPRINGS-NEW HILL ROAD). | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | DIVISION 5 |  | T | RIGHT-OF-WAY | 200000 | FY 2024: 200000
HE-0010 | HIGHWAY | VARIOUS | INTERCHANGE IMPROVEMENTS AT US 1 / SR 1127 (NEW HILL-HOLLEMANN ROAD), INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) / SR 1149 (FRIENDSHIP ROAD) AND SR 1149 (FRIENDSHIP ROAD) / SR 1152 (OLD HOLLY SPRINGS-NEW HILL ROAD). | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | DIVISION 5 |  | T | CONSTRUCTION | 9300000 | FY 2024: 4600000; FY 2025: 4700000
HE-0011 | HIGHWAY | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | DIVISION 8 |  | T | ENGINEERING | 1000000 | FY 2023: 1000000
HE-0011 | HIGHWAY | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | DIVISION 8 |  | T | CONSTRUCTION | 8500000 | FY 2024: 4250000; FY 2025: 4250000
HE-0011 | HIGHWAY | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | DIVISION 8 |  | T | RIGHT-OF-WAY | 250000 | FY 2023: 250000
HE-0011 | HIGHWAY | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. | 8 | Triangle Area RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | DIVISION 8 |  | T | UTILITIES | 250000 | FY 2023: 250000
HE-0012 | HIGHWAY | FAYETTEVILLE | CONSTRUCT NEW ACCESS ROAD WITH IMPROVEMENTS AT INTERSECTION WITH SR 1838 (DUNN ROAD) IN FAYETTEVILLE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | DIVISION 6 |  | T | RIGHT-OF-WAY | 20000 | FY 2023: 20000
HE-0012 | HIGHWAY | FAYETTEVILLE | CONSTRUCT NEW ACCESS ROAD WITH IMPROVEMENTS AT INTERSECTION WITH SR 1838 (DUNN ROAD) IN FAYETTEVILLE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | DIVISION 6 |  | T | UTILITIES | 50000 | FY 2023: 50000
HE-0012 | HIGHWAY | FAYETTEVILLE | CONSTRUCT NEW ACCESS ROAD WITH IMPROVEMENTS AT INTERSECTION WITH SR 1838 (DUNN ROAD) IN FAYETTEVILLE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | DIVISION 6 |  | T | CONSTRUCTION | 1100000 | FY 2023: 1100000
HE-0013 | HIGHWAY | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. | DIVISION 8 |  | T | RIGHT-OF-WAY | 50000 | FY 2024: 50000
HE-0013 | HIGHWAY | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. | DIVISION 8 |  | T | UTILITIES | 250000 | FY 2024: 250000
HE-0013 | HIGHWAY | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. | DIVISION 8 |  | T | CONSTRUCTION | 1500000 | FY 2024: 1000000; FY 2025: 500000
HE-0013 | HIGHWAY | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. | DIVISION 8 |  | T | ENGINEERING | 500000 | FY 2023: 250000; FY 2024: 250000
HE-0013A | HIGHWAY | SCOTLAND COUNTY INDUSTRIAL PARK ACCESS ROAD | IMPROVE THE EXISTING ACCESS ROAD INTO THE SCOTLAND COUNTY INDUSTRIAL PARK. | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. | DIVISION 8 |  | T | CONSTRUCTION | 200000 | FY 2023: 200000
HE-0014 | HIGHWAY | SR 1104 OLD LINWOOD ROAD | CONSTRUCT NEW ACCESS ROAD NORTH OF SR 1254 (BROWN STREET) AND IMPROVEMENTS TO SR 1104 (OLD LINWOOD ROAD). | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | DIVISION 9 |  | T | ENGINEERING | 400000 | FY 2023: 400000
HE-0014 | HIGHWAY | SR 1104 OLD LINWOOD ROAD | CONSTRUCT NEW ACCESS ROAD NORTH OF SR 1254 (BROWN STREET) AND IMPROVEMENTS TO SR 1104 (OLD LINWOOD ROAD). | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | DIVISION 9 |  | T | UTILITIES | 10000 | FY 2024: 10000
HE-0014 | HIGHWAY | SR 1104 OLD LINWOOD ROAD | CONSTRUCT NEW ACCESS ROAD NORTH OF SR 1254 (BROWN STREET) AND IMPROVEMENTS TO SR 1104 (OLD LINWOOD ROAD). | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | DIVISION 9 |  | T | CONSTRUCTION | 8590000 | FY 2024: 4590000; FY 2025: 4000000
HE-0015 | HIGHWAY | NC 49 | PRINCE CIRCLE TO WEST OF GENERAL SERVICES DRIVE SW. CONVERT EXISTING FULL ACCESS CROSSOVER TO RCI WITH LEFTOVERS AND SIGNALIZED U-TURN LEFTOVERS. | 10 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841. | REGION E |  | O | CONSTRUCTION | 2091000 | FY 2023: 2091000
HE-0015 | HIGHWAY | NC 49 | PRINCE CIRCLE TO WEST OF GENERAL SERVICES DRIVE SW. CONVERT EXISTING FULL ACCESS CROSSOVER TO RCI WITH LEFTOVERS AND SIGNALIZED U-TURN LEFTOVERS. | 10 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841. | REGION E |  | T | CONSTRUCTION | 2000000 | FY 2023: 2000000
HF-0001 | HIGHWAY | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | EXEMPT |  | FLAP | ENGINEERING | 4000
HF-0001 | HIGHWAY | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | EXEMPT |  | S(M) | CONSTRUCTION | 47000 | FY 2023: 47000
HF-0001 | HIGHWAY | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | EXEMPT |  | FLAP | CONSTRUCTION | 188000 | FY 2023: 186000
HF-0001 | HIGHWAY | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | EXEMPT |  | S(M) | ENGINEERING | 1000
HF-0002 | HIGHWAY | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | S(M) | CONSTRUCTION | 46000 | FY 2023: 46000
HF-0002 | HIGHWAY | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | FLAP | ENGINEERING | 8000
HF-0002 | HIGHWAY | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | FLAP | CONSTRUCTION | 184000 | FY 2023: 184000
HF-0002 | HIGHWAY | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | S(M) | ENGINEERING | 2000
HF-0003 | HIGHWAY | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | S(M) | CONSTRUCTION | 315000 | FY 2024: 213000; FY 2025: 102000
HF-0003 | HIGHWAY | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | S(M) | ENGINEERING | 35000
HF-0003 | HIGHWAY | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | FLAP | ENGINEERING | 140000
HF-0003 | HIGHWAY | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | FLAP | CONSTRUCTION | 1260000 | FY 2024: 854000; FY 2025: 406000
HF-0004 | HIGHWAY | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | FLAP | ENGINEERING | 24000
HF-0004 | HIGHWAY | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | FLAP | CONSTRUCTION | 396000 | FY 2024: 396000
HF-0004 | HIGHWAY | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | S(M) | ENGINEERING | 6000
HF-0004 | HIGHWAY | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. STATE MATCH ARE HIGHWAY FUNDS. | EXEMPT |  | S(M) | CONSTRUCTION | 99000 | FY 2024: 99000
HF-0005 | HIGHWAY | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE #63 OVER BLAIR CREEK AND BRIDGE #88 OVER HYATT MILL CREEK. | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. STATE FUNDS ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | EXEMPT |  | FLAP | ENGINEERING | 240000
HF-0005 | HIGHWAY | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE #63 OVER BLAIR CREEK AND BRIDGE #88 OVER HYATT MILL CREEK. | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. STATE FUNDS ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | EXEMPT |  | FLAP | CONSTRUCTION | 960000 | FY 2024: 810000; FY 2025: 150000
HF-0005 | HIGHWAY | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE #63 OVER BLAIR CREEK AND BRIDGE #88 OVER HYATT MILL CREEK. | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. STATE FUNDS ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | EXEMPT |  | S(M) | ENGINEERING | 60000
HF-0005 | HIGHWAY | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE #63 OVER BLAIR CREEK AND BRIDGE #88 OVER HYATT MILL CREEK. | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. STATE FUNDS ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | EXEMPT |  | S(M) | CONSTRUCTION | 240000 | FY 2024: 202000; FY 2025: 38000
HF-0006 | HIGHWAY | US 64 | DRY FALLS RECREATION AREA. IMPROVE PARKING AREA, CONSTRUCT PEDESTRIAN BRIDGE, AND CONSTRUCT OBSERVATION PLATFORM. | 14 | Southwestern RPO | FLAP PROJECT NC 64. AWARDED $1.0M. | EXEMPT |  | FLAP | CONSTRUCTION | 500000 | FY 2026: 500000
HF-0006 | HIGHWAY | US 64 | DRY FALLS RECREATION AREA. IMPROVE PARKING AREA, CONSTRUCT PEDESTRIAN BRIDGE, AND CONSTRUCT OBSERVATION PLATFORM. | 14 | Southwestern RPO | FLAP PROJECT NC 64. AWARDED $1.0M. | EXEMPT |  | FLAP | ENGINEERING | 500000 | FY 2024: 500000
HF-0007 | HIGHWAY | SR 1286/ SR 1383 (TSALI ROAD) | NC 28 TO END OF MAINTENANCE. RESURFACE AND REPAIR CORRIDOR. | 14 | Southwestern RPO | FLAP PROJECT NC 65. AWARDED $1.2M. | EXEMPT |  | FLAP | ENGINEERING | 150000 | FY 2023: 150000
HF-0007 | HIGHWAY | SR 1286/ SR 1383 (TSALI ROAD) | NC 28 TO END OF MAINTENANCE. RESURFACE AND REPAIR CORRIDOR. | 14 | Southwestern RPO | FLAP PROJECT NC 65. AWARDED $1.2M. | EXEMPT |  | FLAP | CONSTRUCTION | 1050000 | FY 2025: 1050000
HF-0008 | HIGHWAY | NC 615 (MARSH CAUSEWAY) | HQ/ VC ENTRACE ROAD TO WEST OF KNOTTS ISLAND ROAD. IMPROVE CORRIDOR AT VARIOUS LOCATIONS. | 1 | Albemarle RPO | FLAP PROJECT NC 71. AWARDED $700K. | EXEMPT |  | FLAP | CONSTRUCTION | 700000 | FY 2025: 700000
HI-0001 | HIGHWAY | I-85 / US 15 | NORTH OF SR 1637 (REDWOOD ROAD) IN DURHAM COUNTY TO SOUTH OF US 15 / SR 1100 (GATE ONE ROAD) IN GRANVILLE COUNTY. PAVEMENT REHABILITATION. | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 50000
HI-0001 | HIGHWAY | I-85 / US 15 | NORTH OF SR 1637 (REDWOOD ROAD) IN DURHAM COUNTY TO SOUTH OF US 15 / SR 1100 (GATE ONE ROAD) IN GRANVILLE COUNTY. PAVEMENT REHABILITATION. | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 5665000 | FY 2023: 1238000
HI-0002 | HIGHWAY | I-85 | NC 109 IN THOMASVILLE TO SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. PAVEMENT REHABILITATION. | 8, 9 | High Point Urban Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 15392000 | FY 2023: 8127000; FY 2024: 4276000
HI-0003 | HIGHWAY | I-73 / US 220 | SR 1009 (OLD US HIGHWAY 311) TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO, High Point Urban Area MPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 5000000 | FY 2029: 1541000; FY 2030: 2951000; FY 2031: 508000
HI-0003 | HIGHWAY | I-73 / US 220 | SR 1009 (OLD US HIGHWAY 311) TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO, High Point Urban Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3120000 | FY 2029: 962000; FY 2030: 1841000; FY 2031: 317000
HI-0004 | HIGHWAY | I-74 | SR 1928 (CEDAR SQUARE ROAD) TO I-73 / US 220. PAVEMENT REHABILITATION. | 8 | High Point Urban Area MPO, Piedmont Triad RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3140000 | FY 2029: 1193000; FY 2030: 1707000; FY 2031: 240000
HI-0004 | HIGHWAY | I-74 | SR 1928 (CEDAR SQUARE ROAD) TO I-73 / US 220. PAVEMENT REHABILITATION. | 8 | High Point Urban Area MPO, Piedmont Triad RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 5000000 | FY 2029: 1900000; FY 2030: 2718000; FY 2031: 382000
HI-0005 | HIGHWAY | I-285 / US 52 / NC 8 | I-40 IN FORSYTH COUNTY TO SR 3010 (OLD US 52) IN DAVIDSON COUNTY. PAVEMENT REHABILITATION. | 9 | Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 10801000 | FY 2025: 3564000; FY 2026: 4110000; FY 2027: 2672000; FY 2028: 455000
HI-0005 | HIGHWAY | I-285 / US 52 / NC 8 | I-40 IN FORSYTH COUNTY TO SR 3010 (OLD US 52) IN DAVIDSON COUNTY. PAVEMENT REHABILITATION. | 9 | Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 16199000 | FY 2025: 5346000; FY 2026: 6164000; FY 2027: 4007000; FY 2028: 682000
HI-0006 | HIGHWAY | US 264 | US 264 FROM I-795 TO TOISNOT SWAMP. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 10075000 | FY 2023: 6975000
HI-0007 | HIGHWAY | US 264 | US 264 FROM TOISNOT SWAMP TO THE GREENE COUNTY LINE. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 11015000 | FY 2023: 7215000
HI-0008 | HIGHWAY | I-95 | I-95 FROM MILE MARKER 97 TO MILE MARKER 101. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 7229000 | FY 2023: 4505000; FY 2024: 596000
HI-0009 | HIGHWAY | I-40 | SR 1001 (SUGAR HILL ROAD)/MILE MARKER 81 TO NC 226/MILE MARKER 86. PAVEMENT REHABILITATION. | 13 | Foothills RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 12361000 | FY 2028: 124000; FY 2029: 8094000; FY 2030: 4143000
HI-0009 | HIGHWAY | I-40 | SR 1001 (SUGAR HILL ROAD)/MILE MARKER 81 TO NC 226/MILE MARKER 86. PAVEMENT REHABILITATION. | 13 | Foothills RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 2539000 | FY 2028: 25000; FY 2029: 1663000; FY 2030: 851000
HI-0010 | HIGHWAY | I-40 | MILE MARKER 67 TO MILE MARKER 73 (OLD FORT MOUNTAIN). CONSTRUCT SAFETY AND DRAINAGE IMPROVEMENTS, REHABILITATE PAVEMENT, AND RECONSTRUCT MEDIAN BARRIER. | 13 | Foothills RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 1000000 | FY 2023: 333000; FY 2024: 451000; FY 2025: 216000
HI-0010 | HIGHWAY | I-40 | MILE MARKER 67 TO MILE MARKER 73 (OLD FORT MOUNTAIN). CONSTRUCT SAFETY AND DRAINAGE IMPROVEMENTS, REHABILITATE PAVEMENT, AND RECONSTRUCT MEDIAN BARRIER. | 13 | Foothills RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 16500000 | FY 2023: 5491000; FY 2024: 7445000; FY 2025: 3564000
HI-0011 | HIGHWAY | I-40 | I-40 FROM THE JOHNSTON COUNTY LINE (MILE MARKER 340) TO THE DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | 3 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 9900000 | FY 2028: 2806000; FY 2029: 4435000; FY 2030: 2659000
HI-0011 | HIGHWAY | I-40 | I-40 FROM THE JOHNSTON COUNTY LINE (MILE MARKER 340) TO THE DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | 3 | Mid-Carolina RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 12500000 | FY 2028: 3543000; FY 2029: 5599000; FY 2030: 3358000
HI-0012 | HIGHWAY | I-40 | I-40 FROM THE SAMPSON COUNTY LINE (MILE MARKER 360) TO THE PENDER COUNTY LINE (MILE MARKER 388). PAVEMENT REHABILITATION. | 3 | Eastern Carolina RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 22400000 | FY 2028: 4842000; FY 2029: 9306000; FY 2030: 6437000; FY 2031: 1815000
HI-0012 | HIGHWAY | I-40 | I-40 FROM THE SAMPSON COUNTY LINE (MILE MARKER 360) TO THE PENDER COUNTY LINE (MILE MARKER 388). PAVEMENT REHABILITATION. | 3 | Eastern Carolina RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 8700000 | FY 2028: 1881000; FY 2029: 3614000; FY 2030: 2500000; FY 2031: 705000
HI-0013 | HIGHWAY | US 264 | US 264 FROM THE US 64 / US 264 SPLIT TO THE WILSON COUNTY LINE. PAVEMENT REHABILITATION. | 4, 5 | Upper Coastal Plain RPO, Capital Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 16500000 | FY 2027: 4552000; FY 2028: 7958000; FY 2029: 3990000
HI-0014 | HIGHWAY | US 264 | US 264 FROM THE WILSON COUNTY LINE TO I-95. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 6000000 | FY 2026: 2035000; FY 2027: 3347000; FY 2028: 618000
HI-0015 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM EAST OF NC 214 TO WEST OF SR 1824 (WATER TANK ROAD). PAVEMENT REHABILITATION. | 6 | Cape Fear RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 6695000 | FY 2024: 2611000; FY 2025: 3749000; FY 2026: 335000
HI-0015 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM EAST OF NC 214 TO WEST OF SR 1824 (WATER TANK ROAD). PAVEMENT REHABILITATION. | 6 | Cape Fear RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3605000 | FY 2024: 1406000; FY 2025: 2019000; FY 2026: 180000
HI-0016 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM EAST OF NC 41 TO THE COLUMBUS COUNTY LINE. PAVEMENT REHABILITATION. | 6 | Lumber River RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 2190000 | FY 2024: 197000; FY 2025: 1424000; FY 2026: 569000
HI-0016 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM EAST OF NC 41 TO THE COLUMBUS COUNTY LINE. PAVEMENT REHABILITATION. | 6 | Lumber River RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 7810000 | FY 2024: 703000; FY 2025: 5076000; FY 2026: 2031000
HI-0017 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM THE SCOTLAND COUNTY LINE TO I-74/US 74 BUSINESS. PAVEMENT REHABILITATION. | 6 | Lumber River RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 2500000 | FY 2024: 250000; FY 2025: 1850000; FY 2026: 400000
HI-0017 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM THE SCOTLAND COUNTY LINE TO I-74/US 74 BUSINESS. PAVEMENT REHABILITATION. | 6 | Lumber River RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 4300000 | FY 2024: 430000; FY 2025: 3182000; FY 2026: 688000
HI-0018 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM WEST OF US 701 BUSINESS TO WEST OF NC 214. PAVEMENT REHABILITATION. | 6 | Cape Fear RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 24200000 | FY 2025: 9680000; FY 2026: 12100000; FY 2027: 2420000
HI-0019 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM WEST OF SR 1585 (UNION VALLEY ROAD) TO WEST OF US 701 BUSINESS. PAVEMENT REHABILITATION. | 6 | Cape Fear RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 5000000 | FY 2029: 1966000; FY 2030: 3034000
HI-0019 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM WEST OF SR 1585 (UNION VALLEY ROAD) TO WEST OF US 701 BUSINESS. PAVEMENT REHABILITATION. | 6 | Cape Fear RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 400000 | FY 2029: 157000; FY 2030: 243000
HI-0020 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM THE ROBESON COUNTY LINE TO WEST OF SR 1585 (UNION VALLEY ROAD). PAVEMENT REHABILITATION. | 6 | Cape Fear RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 621000 | FY 2029: 190000; FY 2030: 304000; FY 2031: 127000
HI-0020 | HIGHWAY | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM THE ROBESON COUNTY LINE TO WEST OF SR 1585 (UNION VALLEY ROAD). PAVEMENT REHABILITATION. | 6 | Cape Fear RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 14381000 | FY 2029: 4399000; FY 2030: 7042000; FY 2031: 2940000
HI-0021 | HIGHWAY | I-95 | I-95 FROM THE ROBESON COUNTY LINE TO NC 53/210. PAVEMENT REHABILITATION. | 6 | Fayetteville Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 8000000 | FY 2029: 3053000; FY 2030: 4323000; FY 2031: 624000
HI-0022 | HIGHWAY | I-95 | I-95 FROM NC 53 TO I-95 BUSINESS / US 301. PAVEMENT REHABILITATION. | 6 | Fayetteville Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 5800000 | FY 2029: 2139000; FY 2030: 3661000
HI-0023 | HIGHWAY | I-885 | I-40 TO 0.4 MILES NORTH OF TW ALEXANDER DRIVE. PAVEMENT REHABILITATION. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3300000 | FY 2024: 3300000
HI-9999 | HIGHWAY | VARIOUS | INTERSTATE MAINTENANCE PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 760210000 | FY 2028: 0; FY 2029: 33989000; FY 2030: 44962000; FY 2031: 114263000; FY 2032: 141749000; FY 2033: 141749000 | 283498000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | L | CONSTRUCTION | 785000 | FY 2025: 785000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | L | CONSTRUCTION | 785000 | FY 2026: 785000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | L | RIGHT-OF-WAY | 908000 | FY 2023: 908000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | L | RIGHT-OF-WAY | 196000 | FY 2023: 196000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | L | ENGINEERING | 342000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | BGDA | CONSTRUCTION | 3140000 | FY 2025: 3140000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 784000 | FY 2023: 784000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | BGANY | ENGINEERING | 1368000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | BGANY | RIGHT-OF-WAY | 3632000 | FY 2023: 3632000
HL-0001 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | DIVISION 10 |  | BGDA | CONSTRUCTION | 3140000 | FY 2026: 3140000
HL-0002 | HIGHWAY | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | EXEMPT |  | L | CONSTRUCTION | 80000 | FY 2023: 80000
HL-0002 | HIGHWAY | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | EXEMPT |  | BGDA | RIGHT-OF-WAY | 80000
HL-0002 | HIGHWAY | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | EXEMPT |  | L | RIGHT-OF-WAY | 20000
HL-0002 | HIGHWAY | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | EXEMPT |  | BGANY | CONSTRUCTION | 320000 | FY 2023: 320000
HL-0003 | HIGHWAY | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | REGION G |  | S(M) | CONSTRUCTION | 2676000 | FY 2024: 2676000
HL-0003 | HIGHWAY | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | REGION G |  | S(M) | ENGINEERING | 24000 | FY 2023: 24000
HL-0003 | HIGHWAY | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | REGION G |  | S(M) | ENGINEERING | 36000
HL-0003 | HIGHWAY | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | REGION G |  | BGDA | CONSTRUCTION | 1968000 | FY 2024: 1968000
HL-0003 | HIGHWAY | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | REGION G |  | BGDA | ENGINEERING | 96000 | FY 2023: 96000
HL-0003 | HIGHWAY | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | REGION G |  | BGANY | CONSTRUCTION | 2899000 | FY 2024: 2899000
HL-0003 | HIGHWAY | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | REGION G |  | BGDA | ENGINEERING | 144000
HL-0004 | HIGHWAY | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | L | RIGHT-OF-WAY | 124000 | FY 2023: 124000
HL-0004 | HIGHWAY | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | L | ENGINEERING | 96000
HL-0004 | HIGHWAY | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | L | CONSTRUCTION | 960000 | FY 2024: 960000
HL-0004 | HIGHWAY | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | BGANY | RIGHT-OF-WAY | 80000 | FY 2023: 80000
HL-0004 | HIGHWAY | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | BGDA | ENGINEERING | 384000
HL-0004 | HIGHWAY | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | L | RIGHT-OF-WAY | 20000 | FY 2023: 20000
HL-0004 | HIGHWAY | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | BGANY | CONSTRUCTION | 3840000 | FY 2024: 3840000
HL-0004 | HIGHWAY | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 496000 | FY 2023: 496000
HL-0005 | HIGHWAY | VARIOUS | CITY OF SALISBURY SIGNAL SYSTEM UPGRADE. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 343000
HL-0005 | HIGHWAY | VARIOUS | CITY OF SALISBURY SIGNAL SYSTEM UPGRADE. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 86000
HL-0006 | HIGHWAY | US 401 | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | 5 | Capital Area MPO |  | EXEMPT |  | NHPBA | RIGHT-OF-WAY | 2600000 | FY 2023: 2133000; FY 2024: 267000; FY 2025: 100000; FY 2026: 100000
HL-0006 | HIGHWAY | US 401 | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | 5 | Capital Area MPO |  | EXEMPT |  | NHPBA | UTILITIES | 509000 | FY 2023: 509000
HL-0006 | HIGHWAY | US 401 | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | 5 | Capital Area MPO |  | EXEMPT |  | NHPBA | CONSTRUCTION | 26900000 | FY 2025: 10593000; FY 2026: 10647000; FY 2027: 5660000
HL-0007 | HIGHWAY | NC 55 | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | 5 | Capital Area MPO |  | EXEMPT |  | NHPBA | RIGHT-OF-WAY | 9100000 | FY 2024: 2427000; FY 2025: 4853000; FY 2026: 910000; FY 2027: 910000
HL-0007 | HIGHWAY | NC 55 | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | 5 | Capital Area MPO |  | EXEMPT |  | NHPBA | UTILITIES | 3600000 | FY 2024: 1800000; FY 2025: 1800000
HL-0007 | HIGHWAY | NC 55 | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | 5 | Capital Area MPO |  | EXEMPT |  | NHPBA | CONSTRUCTION | 23300000 | FY 2025: 5701000; FY 2026: 9851000; FY 2027: 6395000; FY 2028: 1353000
HL-0008C | HIGHWAY | NC 50 (BENSON ROAD) | SR 2812 (TIMBER DRIVE) INTERSECTION IN GARNER. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | RIGHT-OF-WAY | 100000
HL-0008C | HIGHWAY | NC 50 (BENSON ROAD) | SR 2812 (TIMBER DRIVE) INTERSECTION IN GARNER. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | CONSTRUCTION | 525000 | FY 2024: 525000
HL-0008D | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | UTILITIES | 210000 | FY 2023: 210000
HL-0008D | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | CONSTRUCTION | 2500000 | FY 2025: 25000; FY 2026: 2475000
HL-0008D | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | RIGHT-OF-WAY | 500000 | FY 2023: 500000
HL-0008G | HIGHWAY | SR 1375 (LAKE WHEELER ROAD) | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BGBA | RIGHT-OF-WAY | 790000 | FY 2023: 790000
HL-0008G | HIGHWAY | SR 1375 (LAKE WHEELER ROAD) | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BGBA | UTILITIES | 30000 | FY 2023: 30000
HL-0008G | HIGHWAY | SR 1375 (LAKE WHEELER ROAD) | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BGBA | CONSTRUCTION | 837000 | FY 2024: 837000
HL-0008G | HIGHWAY | SR 1375 (LAKE WHEELER ROAD) | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BGDA | CONSTRUCTION | 1463000 | FY 2025: 1463000
HL-0008H | HIGHWAY | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | RIGHT-OF-WAY | 251000
HL-0008H | HIGHWAY | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | UTILITIES | 60000
HL-0008H | HIGHWAY | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | CONSTRUCTION | 1750000 | FY 2024: 18000; FY 2025: 1732000
HL-0008L | HIGHWAY | SR 1010 (TEN-TEN ROAD) | SR 1386 (BELLS LAKE ROAD) , SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | RIGHT-OF-WAY | 300000 | FY 2023: 300000
HL-0008L | HIGHWAY | SR 1010 (TEN-TEN ROAD) | SR 1386 (BELLS LAKE ROAD) , SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | UTILITIES | 225000 | FY 2023: 225000
HL-0008L | HIGHWAY | SR 1010 (TEN-TEN ROAD) | SR 1386 (BELLS LAKE ROAD) , SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | CONSTRUCTION | 2400000 | FY 2025: 2066000; FY 2026: 334000
HL-0008O | HIGHWAY | NC 42 | SR 2735 (JOHNSON ROAD) INTERSECTION.INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | RIGHT-OF-WAY | 175000 | FY 2023: 175000
HL-0008O | HIGHWAY | NC 42 | SR 2735 (JOHNSON ROAD) INTERSECTION.INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | UTILITIES | 125000 | FY 2023: 125000
HL-0008O | HIGHWAY | NC 42 | SR 2735 (JOHNSON ROAD) INTERSECTION.INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | CONSTRUCTION | 1300000 | FY 2025: 1100000; FY 2026: 200000
HL-0008P | HIGHWAY | SR 1010 (TEN-TEN ROAD) | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | RIGHT-OF-WAY | 250000 | FY 2023: 250000
HL-0008P | HIGHWAY | SR 1010 (TEN-TEN ROAD) | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | UTILITIES | 175000 | FY 2023: 175000
HL-0008P | HIGHWAY | SR 1010 (TEN-TEN ROAD) | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BA | CONSTRUCTION | 1750000 | FY 2025: 1750000
HL-0008Q | HIGHWAY | SR 1390 (OPTIMIST FARM ROAD) | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | CONSTRUCTION | 2400000 | FY 2025: 2066000; FY 2026: 334000
HL-0008Q | HIGHWAY | SR 1390 (OPTIMIST FARM ROAD) | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | RIGHT-OF-WAY | 300000 | FY 2023: 300000
HL-0008Q | HIGHWAY | SR 1390 (OPTIMIST FARM ROAD) | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | UTILITIES | 225000 | FY 2023: 225000
HL-0008S | HIGHWAY | SR 1379 (PENNY ROAD) | SR 1382 (OLDE SOUTH ROAD) INTERSECTION IN RALIEGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | RIGHT-OF-WAY | 175000 | FY 2023: 175000
HL-0008S | HIGHWAY | SR 1379 (PENNY ROAD) | SR 1382 (OLDE SOUTH ROAD) INTERSECTION IN RALIEGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | UTILITIES | 125000 | FY 2023: 125000
HL-0008S | HIGHWAY | SR 1379 (PENNY ROAD) | SR 1382 (OLDE SOUTH ROAD) INTERSECTION IN RALIEGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO |  | EXEMPT |  | BA | CONSTRUCTION | 1100000 | FY 2025: 1100000
HL-0009 | HIGHWAY | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. S FUNDS REPRESENT STATE HIGHWAY FUNDS. | EXEMPT |  | DP | CONSTRUCTION | 3882000 | FY 2023: 1941000; FY 2024: 1941000
HL-0009 | HIGHWAY | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. S FUNDS REPRESENT STATE HIGHWAY FUNDS. | EXEMPT |  | L | CONSTRUCTION | 1178000 | FY 2023: 589000; FY 2024: 589000
HL-0009 | HIGHWAY | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. S FUNDS REPRESENT STATE HIGHWAY FUNDS. | EXEMPT |  | DP | UTILITIES | 930000
HL-0009 | HIGHWAY | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. S FUNDS REPRESENT STATE HIGHWAY FUNDS. | EXEMPT |  | DP | RIGHT-OF-WAY | 100000
HL-0009 | HIGHWAY | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. S FUNDS REPRESENT STATE HIGHWAY FUNDS. | EXEMPT |  | DP | ENGINEERING | 350000
HL-0009 | HIGHWAY | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. S FUNDS REPRESENT STATE HIGHWAY FUNDS. | EXEMPT |  | S | CONSTRUCTION | 250000 | FY 2023: 250000
HL-0012 | HIGHWAY | I-240 | US 70 (CHARLOTTE STREET) INTERSECTIONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS AND A RIGHT TURN LANE ON THE I-240 EASTBOUND OFF-RAMP. | 13 | French Broad River MPO | UNDER CONSTRUCTION. "S(M)" FUNDS REPRESENT SPOT MOBILITY AND HIGH IMPACT/LOW COST FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. PE AND ROW FUNDED UNDER SM-5713E (HIGHWAY FUNDS). | EXEMPT |  | BGDA | CONSTRUCTION | 668000 | FY 2023: 668000
HL-0012 | HIGHWAY | I-240 | US 70 (CHARLOTTE STREET) INTERSECTIONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS AND A RIGHT TURN LANE ON THE I-240 EASTBOUND OFF-RAMP. | 13 | French Broad River MPO | UNDER CONSTRUCTION. "S(M)" FUNDS REPRESENT SPOT MOBILITY AND HIGH IMPACT/LOW COST FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. PE AND ROW FUNDED UNDER SM-5713E (HIGHWAY FUNDS). | EXEMPT |  | S(M) | CONSTRUCTION | 1012000 | FY 2023: 1012000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGANY | ENGINEERING | 160000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | ENGINEERING | 19000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | CONSTRUCTION | 64000 | FY 2024: 64000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | CONSTRUCTION | 72000 | FY 2024: 72000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | RIGHT-OF-WAY | 24000 | FY 2023: 24000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | ENGINEERING | 4000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | ENGINEERING | 40000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGDA | CONSTRUCTION | 256000 | FY 2024: 256000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGDA | ENGINEERING | 16000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGANY | CONSTRUCTION | 288000 | FY 2024: 288000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGANY | ENGINEERING | 76000
HL-0013 | HIGHWAY | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 96000 | FY 2023: 96000
HL-0014 | HIGHWAY | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | ENGINEERING | 8000
HL-0014 | HIGHWAY | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | ENGINEERING | 7000
HL-0014 | HIGHWAY | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | RIGHT-OF-WAY | 5000 | FY 2023: 5000
HL-0014 | HIGHWAY | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGANY | CONSTRUCTION | 272000 | FY 2023: 272000
HL-0014 | HIGHWAY | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | L | CONSTRUCTION | 68000 | FY 2023: 68000
HL-0014 | HIGHWAY | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 20000 | FY 2023: 20000
HL-0014 | HIGHWAY | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGANY | ENGINEERING | 28000
HL-0014 | HIGHWAY | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | DIVISION 13 |  | BGDA | ENGINEERING | 32000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | BGDA | ENGINEERING | 356000 | FY 2023: 356000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | L | CONSTRUCTION | 636000 | FY 2025: 636000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | L | RIGHT-OF-WAY | 4000 | FY 2025: 4000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | L | RIGHT-OF-WAY | 52000 | FY 2024: 52000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | L | ENGINEERING | 89000 | FY 2023: 89000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | L | ENGINEERING | 75000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | BGDA | RIGHT-OF-WAY | 209000 | FY 2024: 209000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | BGDA | ENGINEERING | 301000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | BGANY | CONSTRUCTION | 2545000 | FY 2025: 2545000
HL-0015 | HIGHWAY | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | EXEMPT |  | BGDA | RIGHT-OF-WAY | 17000 | FY 2025: 17000
HL-0016 | HIGHWAY | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | BGDA | CONSTRUCTION | 412000 | FY 2024: 412000
HL-0016 | HIGHWAY | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 18000 | FY 2024: 18000
HL-0016 | HIGHWAY | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 103000 | FY 2024: 103000
HL-0016 | HIGHWAY | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | BGDA | RIGHT-OF-WAY | 72000 | FY 2024: 72000
HL-0023 | HIGHWAY | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | BA | RIGHT-OF-WAY | 1479000 | FY 2023: 1479000
HL-0023 | HIGHWAY | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | BA | CONSTRUCTION | 5195000 | FY 2025: 5195000
HL-0023 | HIGHWAY | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | O | RIGHT-OF-WAY | 78000 | FY 2023: 78000
HL-0023 | HIGHWAY | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | O | CONSTRUCTION | 274000 | FY 2025: 274000
HL-0024 | HIGHWAY | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN T FOR CON AS PART OF FUND SWAP 8-9-22. | EXEMPT |  | BA | UTILITIES | 800000 | FY 2023: 800000
HL-0024 | HIGHWAY | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN T FOR CON AS PART OF FUND SWAP 8-9-22. | EXEMPT |  | T | CONSTRUCTION | 5923000 | FY 2025: 59000; FY 2026: 4459000; FY 2027: 1405000
HL-0024 | HIGHWAY | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN T FOR CON AS PART OF FUND SWAP 8-9-22. | EXEMPT |  | BA | RIGHT-OF-WAY | 1500000 | FY 2023: 178000; FY 2024: 533000; FY 2025: 489000; FY 2026: 150000; FY 2027: 150000
HL-0024 | HIGHWAY | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN T FOR CON AS PART OF FUND SWAP 8-9-22. | EXEMPT |  | BA | ENGINEERING | 1211000
HL-0025 | HIGHWAY | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | BA | RIGHT-OF-WAY | 701000 | FY 2023: 201000; FY 2024: 500000
HL-0025 | HIGHWAY | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | BA | CONSTRUCTION | 5892000 | FY 2024: 59000; FY 2025: 4725000; FY 2026: 1108000
HL-0025 | HIGHWAY | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | BA | ENGINEERING | 1016000
HL-0026 | HIGHWAY | VARIOUS | FAYETTEVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | 6, 8 | Fayetteville Area MPO |  | DIVISION 6, 8 |  | BGDA | CONSTRUCTION | 88993000 | 2185000 | 1516000 | 0 | 0 | 0 | 3399000 | 5773000 | 5773000 | 5773000 | 5773000 | 5773000 | 51957000
HL-0027 | HIGHWAY | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | ENGINEERING | 12000
HL-0027 | HIGHWAY | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | CONSTRUCTION | 462000 | FY 2023: 5000; FY 2024: 457000
HL-0027 | HIGHWAY | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | CONSTRUCTION | 116000 | FY 2023: 1000; FY 2024: 115000
HL-0027 | HIGHWAY | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | UTILITIES | 115000 | FY 2023: 115000
HL-0027 | HIGHWAY | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | ENGINEERING | 50000
HL-0027 | HIGHWAY | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | UTILITIES | 460000 | FY 2023: 460000
HL-0027 | HIGHWAY | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 308000 | FY 2023: 308000
HL-0027 | HIGHWAY | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 77000 | FY 2023: 77000
HL-0028 | HIGHWAY | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | BGDA | ENGINEERING | 107000
HL-0028 | HIGHWAY | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | BGDA | CONSTRUCTION | 1002000 | FY 2023: 10000; FY 2024: 992000
HL-0028 | HIGHWAY | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | L | ENGINEERING | 27000
HL-0028 | HIGHWAY | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | L | CONSTRUCTION | 250000 | FY 2023: 2000; FY 2024: 248000
HL-0029 | HIGHWAY | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BGDA | RIGHT-OF-WAY | 51000 | FY 2023: 51000
HL-0029 | HIGHWAY | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 457000 | FY 2023: 330000; FY 2024: 127000
HL-0029 | HIGHWAY | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | BGDA | CONSTRUCTION | 457000 | FY 2023: 330000; FY 2024: 127000
HL-0029 | HIGHWAY | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 51000 | FY 2023: 51000
HL-0030 | HIGHWAY | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 293000 | FY 2023: 293000
HL-0030 | HIGHWAY | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | CONSTRUCTION | 487000 | FY 2023: 296000; FY 2024: 191000
HL-0030 | HIGHWAY | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 158000 | FY 2023: 158000
HL-0030 | HIGHWAY | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | CONSTRUCTION | 262000 | FY 2023: 159000; FY 2024: 103000
HL-0031 | HIGHWAY | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | S | RIGHT-OF-WAY | 68000
HL-0031 | HIGHWAY | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | S | CONSTRUCTION | 339000 | FY 2024: 3000; FY 2025: 336000
HL-0031 | HIGHWAY | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | S | UTILITIES | 30000
HL-0031 | HIGHWAY | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | CONSTRUCTION | 1361000 | FY 2024: 14000; FY 2025: 1347000
HL-0031 | HIGHWAY | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 272000
HL-0031 | HIGHWAY | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | UTILITIES | 120000
HL-0032 | HIGHWAY | LAKE BOONE TRAIL | I-440 TO RIDGE ROAD IN RALEIGH. UPGRADE ROADWAY TO COMPLETE STREET. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 1011000 | FY 2023: 530000; FY 2024: 481000
HL-0032 | HIGHWAY | LAKE BOONE TRAIL | I-440 TO RIDGE ROAD IN RALEIGH. UPGRADE ROADWAY TO COMPLETE STREET. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 253000 | FY 2023: 132000; FY 2024: 121000
HL-0033 | HIGHWAY | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 360000
HL-0033 | HIGHWAY | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | CONSTRUCTION | 3884000 | FY 2024: 39000; FY 2025: 3004000; FY 2026: 841000
HL-0033 | HIGHWAY | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 240000
HL-0033 | HIGHWAY | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | CONSTRUCTION | 2590000 | FY 2024: 26000; FY 2025: 2003000; FY 2026: 561000
HL-0034 | HIGHWAY | SR 1356 (RALEIGH ROAD PARKWAY) | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | EXEMPT |  | BA | ENGINEERING | 45000
HL-0034 | HIGHWAY | SR 1356 (RALEIGH ROAD PARKWAY) | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | EXEMPT |  | BA | UTILITIES | 75000
HL-0034 | HIGHWAY | SR 1356 (RALEIGH ROAD PARKWAY) | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | EXEMPT |  | BA | CONSTRUCTION | 2407000 | FY 2023: 2407000
HL-0036 | HIGHWAY | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW SIDEWALK ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TADA | CONSTRUCTION | 359000 | FY 2023: 4000; FY 2024: 355000
HL-0036 | HIGHWAY | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW SIDEWALK ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | ENGINEERING | 10000
HL-0036 | HIGHWAY | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW SIDEWALK ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | CONSTRUCTION | 90000 | FY 2023: 1000; FY 2024: 89000
HL-0036 | HIGHWAY | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW SIDEWALK ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | TADA | ENGINEERING | 40000
HL-0037 | HIGHWAY | VARIOUS | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING AND PAVEMENT RESTRIPING. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDACV | CONSTRUCTION | 975000 | FY 2023: 975000
HL-0038 | HIGHWAY | VARIOUS | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, PAVEMENT RESTRIPING AND MARKERS, AND SIGN REPLACEMENT. | 10 | Charlotte Regional TPO |  |  |  | BGDACV | ENGINEERING | 5000
HL-0038A | HIGHWAY | US 29/74 (WILKINSON BLVD) AND US 29 (N TRYON ST) | US 29/74 (WILKINSON BLVD) FROM GASTON COUNTY LINE TO FIELD RIDGE ROAD AND US 29 (NORTH TRYON STREET) FROM WEST SUGAR CREEK ROAD TO OLD CONCORD ROAD. RESURFACE ROADWAYS. | 10 | Charlotte Regional TPO | COMPLETE. | EXEMPT |  | BGDACV | CONSTRUCTION | 2596000 | FY 2023: 1393000
HL-0038B | HIGHWAY | VARIOUS | REPLACE PAVEMENT MARKINGS AND SNOW PLOWABLE MARKERS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | BGDACV | CONSTRUCTION | 2318000 | FY 2023: 2025000; FY 2024: 270000
HL-0038C | HIGHWAY | VARIOUS | REPLACE TRAFFIC SIGNAL LOOPS. | 10 | Charlotte Regional TPO | COMPLETE. | EXEMPT |  | BGDACV | CONSTRUCTION | 90000 | FY 2023: 89000
HL-0038D | HIGHWAY | I-485 | REPLACE OVERHEAD SIGNS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | BGDACV | CONSTRUCTION | 705000 | FY 2023: 92000
HL-0039A | HIGHWAY | NORTH CHARLOTTE AVENUE AND NEW TOWN ROAD | NORTH CHARLOTTE AVENUE FROM WALNUT STREET TO NC 200 AND NEW TOWN ROAD FROM CUTHBERTSON ROAD TO ENNIS ROAD. RESURFACE ROADWAYS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGDACV | CONSTRUCTION | 938000 | FY 2023: 928000
HL-0039B | HIGHWAY | VARIOUS | REPLACE PAVEMENT MARKINGS. | 10 | Charlotte Regional TPO | COMPLETE. | EXEMPT |  | BGDACV | CONSTRUCTION | 126000 | FY 2023: 125000
HL-0039C | HIGHWAY | VARIOUS | REPLACE TRAFFIC SIGNAL LOOPS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | BGDACV | CONSTRUCTION | 189000 | FY 2023: 189000
HL-0040 | HIGHWAY | WILMINGTON | CONSTRUCT A NEW NORTH GATE ON NORTH CAROLINA PORTS AUTHORITY PROPERTY. | 3 | Wilmington Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY. | DIVISION 3 |  | BGDA | ENGINEERING | 250000
HL-0040 | HIGHWAY | WILMINGTON | CONSTRUCT A NEW NORTH GATE ON NORTH CAROLINA PORTS AUTHORITY PROPERTY. | 3 | Wilmington Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY. | DIVISION 3 |  | L | ENGINEERING | 63000
HL-0041 | HIGHWAY | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 5 | Capital Area MPO | S(M) and S represent SPOT Mobility Funds of $400k. RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 50000
HL-0041 | HIGHWAY | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 5 | Capital Area MPO | S(M) and S represent SPOT Mobility Funds of $400k. RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | S(M) | CONSTRUCTION | 94000 | FY 2023: 94000
HL-0041 | HIGHWAY | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 5 | Capital Area MPO | S(M) and S represent SPOT Mobility Funds of $400k. RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | S(M) | RIGHT-OF-WAY | 13000
HL-0041 | HIGHWAY | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 5 | Capital Area MPO | S(M) and S represent SPOT Mobility Funds of $400k. RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | S(M) | ENGINEERING | 17000
HL-0041 | HIGHWAY | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 5 | Capital Area MPO | S(M) and S represent SPOT Mobility Funds of $400k. RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 375000 | FY 2023: 375000
HL-0041 | HIGHWAY | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 5 | Capital Area MPO | S(M) and S represent SPOT Mobility Funds of $400k. RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 69000
HL-0041 | HIGHWAY | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 5 | Capital Area MPO | S(M) and S represent SPOT Mobility Funds of $400k. RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | S | CONSTRUCTION | 276000 | FY 2023: 276000
HL-0042 | HIGHWAY | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | ENGINEERING | 202000
HL-0042 | HIGHWAY | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 112000 | FY 2023: 112000
HL-0042 | HIGHWAY | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | UTILITIES | 208000 | FY 2023: 208000
HL-0042 | HIGHWAY | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | CMAQ | CONSTRUCTION | 975000 | FY 2023: 12000; FY 2024: 963000
HL-0042 | HIGHWAY | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | ENGINEERING | 51000
HL-0042 | HIGHWAY | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | RIGHT-OF-WAY | 28000 | FY 2023: 28000
HL-0042 | HIGHWAY | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | UTILITIES | 52000 | FY 2023: 52000
HL-0042 | HIGHWAY | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | EXEMPT |  | L | CONSTRUCTION | 299000 | FY 2023: 3000; FY 2024: 296000
HL-0043 | HIGHWAY | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS | EXEMPT |  | S | ENGINEERING | 38000
HL-0043 | HIGHWAY | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS | EXEMPT |  | S | CONSTRUCTION | 208000 | FY 2025: 208000
HL-0043 | HIGHWAY | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS | EXEMPT |  | CMAQ | CONSTRUCTION | 832000 | FY 2025: 832000
HL-0043 | HIGHWAY | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 220000 | FY 2024: 220000
HL-0043 | HIGHWAY | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS | EXEMPT |  | CMAQ | ENGINEERING | 152000
HL-0043 | HIGHWAY | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS | EXEMPT |  | S | RIGHT-OF-WAY | 55000 | FY 2024: 55000
HL-0044 | HIGHWAY | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 5 | Kerr-Tar RPO |  | EXEMPT |  | L | CONSTRUCTION | 98000 | FY 2023: 1000; FY 2024: 97000
HL-0044 | HIGHWAY | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 5 | Kerr-Tar RPO |  | EXEMPT |  | CMAQ | ENGINEERING | 85000
HL-0044 | HIGHWAY | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 5 | Kerr-Tar RPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 30000 | FY 2023: 30000
HL-0044 | HIGHWAY | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 5 | Kerr-Tar RPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 370000 | FY 2023: 4000; FY 2024: 366000
HL-0044 | HIGHWAY | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 5 | Kerr-Tar RPO |  | EXEMPT |  | L | ENGINEERING | 17000
HL-0044 | HIGHWAY | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 5 | Kerr-Tar RPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 6000 | FY 2023: 6000
HL-0045 | HIGHWAY | EXCHANGE PARK LANE | SOUTH CHURTON STREET TO FARIBAULT LANE IN HILLSBOROGH. REPAIR BRIDGE 670241 OVER ENO RIVER. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 27000 | FY 2023: 0; FY 2024: 27000
HL-0045 | HIGHWAY | EXCHANGE PARK LANE | SOUTH CHURTON STREET TO FARIBAULT LANE IN HILLSBOROGH. REPAIR BRIDGE 670241 OVER ENO RIVER. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | BGDACV | CONSTRUCTION | 126000 | FY 2023: 1000; FY 2024: 125000
HL-0045 | HIGHWAY | EXCHANGE PARK LANE | SOUTH CHURTON STREET TO FARIBAULT LANE IN HILLSBOROGH. REPAIR BRIDGE 670241 OVER ENO RIVER. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | ENGINEERING | 20000
HL-0046 | HIGHWAY | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 712000 | FY 2023: 712000
HL-0046 | HIGHWAY | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDA | RIGHT-OF-WAY | 120000 | FY 2023: 120000
HL-0046 | HIGHWAY | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDA | CONSTRUCTION | 2848000 | FY 2023: 2848000
HL-0046 | HIGHWAY | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 30000 | FY 2023: 30000
HL-0047 | HIGHWAY | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 110000 | FY 2024: 110000
HL-0047 | HIGHWAY | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 14000 | FY 2023: 14000
HL-0047 | HIGHWAY | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDA | RIGHT-OF-WAY | 56000 | FY 2023: 56000
HL-0047 | HIGHWAY | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDA | CONSTRUCTION | 440000 | FY 2024: 440000
HL-0048 | HIGHWAY | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDA | RIGHT-OF-WAY | 8000 | FY 2023: 8000
HL-0048 | HIGHWAY | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDA | CONSTRUCTION | 800000 | FY 2024: 800000
HL-0048 | HIGHWAY | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDACV | ENGINEERING | 255000
HL-0048 | HIGHWAY | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 2000 | FY 2023: 2000
HL-0048 | HIGHWAY | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 200000 | FY 2024: 200000
HL-0049 | HIGHWAY | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BGDACV | ENGINEERING | 145000
HL-0049 | HIGHWAY | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BGDACV | RIGHT-OF-WAY | 11000 | FY 2023: 11000
HL-0049 | HIGHWAY | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BGDACV | CONSTRUCTION | 664000 | FY 2024: 664000
HL-0049 | HIGHWAY | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | ENGINEERING | 36000
HL-0049 | HIGHWAY | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 3000 | FY 2023: 3000
HL-0049 | HIGHWAY | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 166000 | FY 2024: 166000
HL-0050 | HIGHWAY | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 5 | Capital Area MPO | "S" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 110000 | FY 2023: 110000
HL-0050 | HIGHWAY | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 5 | Capital Area MPO | "S" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | S | CONSTRUCTION | 406000 | FY 2024: 406000
HL-0050 | HIGHWAY | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 5 | Capital Area MPO | "S" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | S | RIGHT-OF-WAY | 64000 | FY 2023: 64000
HL-0050 | HIGHWAY | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 5 | Capital Area MPO | "S" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | CONSTRUCTION | 692000 | FY 2024: 692000
HL-0051 | HIGHWAY | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 88000 | FY 2023: 88000
HL-0051 | HIGHWAY | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 64000 | FY 2023: 64000
HL-0051 | HIGHWAY | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 320000 | FY 2024: 320000
HL-0051 | HIGHWAY | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. | 5 | Capital Area MPO |  | DIVISION 5 |  | S | ENGINEERING | 22000 | FY 2023: 22000
HL-0051 | HIGHWAY | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. | 5 | Capital Area MPO |  | DIVISION 5 |  | S | RIGHT-OF-WAY | 16000 | FY 2023: 16000
HL-0051 | HIGHWAY | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. | 5 | Capital Area MPO |  | DIVISION 5 |  | S | CONSTRUCTION | 80000 | FY 2024: 80000
HL-0052 | HIGHWAY | BLUE RIDGE ROAD | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 6398000 | FY 2023: 64000; FY 2024: 3997000; FY 2025: 2337000
HL-0052 | HIGHWAY | BLUE RIDGE ROAD | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | S | CONSTRUCTION | 1599000 | FY 2023: 16000; FY 2024: 999000; FY 2025: 584000
HL-0053 | HIGHWAY | SR 2822 (ROBINSON CHURCH ROAD) | NC 24 TO PLOTT ROAD. WIDEN TO THREE LANES. | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 6227000 | FY 2025: 6227000
HL-0053 | HIGHWAY | SR 2822 (ROBINSON CHURCH ROAD) | NC 24 TO PLOTT ROAD. WIDEN TO THREE LANES. | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  | T(DA) | CONSTRUCTION | 6227000 | FY 2025: 6227000
HL-0055 | HIGHWAY | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 275000 | FY 2025: 275000
HL-0055 | HIGHWAY | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | T(DA) | CONSTRUCTION | 1098000 | FY 2025: 1098000
HL-0055 | HIGHWAY | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | T(DA) | ENGINEERING | 380000 | FY 2023: 380000
HL-0055 | HIGHWAY | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | L | ENGINEERING | 95000 | FY 2023: 95000
HL-0055 | HIGHWAY | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | T(DA) | RIGHT-OF-WAY | 466000 | FY 2024: 466000
HL-0055 | HIGHWAY | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 177000 | FY 2024: 177000
HL-0056 | HIGHWAY | NC 115 | SR 2427 (MCCORD ROAD) TO SAM FURR ROAD. IMPROVE CORRIDOR. | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | EXEMPT |  | T(DA) | RIGHT-OF-WAY | 1996000 | FY 2025: 499000; FY 2026: 998000; FY 2027: 499000
HL-0056 | HIGHWAY | NC 115 | SR 2427 (MCCORD ROAD) TO SAM FURR ROAD. IMPROVE CORRIDOR. | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | EXEMPT |  | T(DA) | CONSTRUCTION | 3457000 | FY 2027: 3457000
HL-0056 | HIGHWAY | NC 115 | SR 2427 (MCCORD ROAD) TO SAM FURR ROAD. IMPROVE CORRIDOR. | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | EXEMPT |  | T(DA) | ENGINEERING | 526000 | FY 2024: 526000
HL-0056 | HIGHWAY | NC 115 | SR 2427 (MCCORD ROAD) TO SAM FURR ROAD. IMPROVE CORRIDOR. | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | EXEMPT |  | L | CONSTRUCTION | 1481000 | FY 2027: 1481000
HL-0056 | HIGHWAY | NC 115 | SR 2427 (MCCORD ROAD) TO SAM FURR ROAD. IMPROVE CORRIDOR. | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | EXEMPT |  | L | RIGHT-OF-WAY | 856000 | FY 2025: 214000; FY 2026: 428000; FY 2027: 214000
HL-0056 | HIGHWAY | NC 115 | SR 2427 (MCCORD ROAD) TO SAM FURR ROAD. IMPROVE CORRIDOR. | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | EXEMPT |  | L | ENGINEERING | 225000 | FY 2024: 225000
HL-0057 | HIGHWAY | NC 24 WT HARRIS BOULEVARD | SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO I-85 NORTH RAMP. INSTALL OVERHEAD STREET LIGHTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 537000 | FY 2023: 537000
HL-0057 | HIGHWAY | NC 24 WT HARRIS BOULEVARD | SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO I-85 NORTH RAMP. INSTALL OVERHEAD STREET LIGHTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BA | CONSTRUCTION | 998000 | FY 2023: 998000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | BGDA | ENGINEERING | 25000 | FY 2023: 25000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | S | CONSTRUCTION | 300000 | FY 2023: 3000; FY 2024: 297000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | S | UTILITIES | 200000 | FY 2023: 200000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | S | ENGINEERING | 50000 | FY 2023: 50000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | S | RIGHT-OF-WAY | 200000 | FY 2023: 200000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | BGDA | CONSTRUCTION | 764000 | FY 2023: 8000; FY 2024: 756000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | BGDA | RIGHT-OF-WAY | 130000 | FY 2023: 130000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | BGDA | UTILITIES | 50000 | FY 2023: 50000
HL-0059 | HIGHWAY | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | "S" FUNDS REFLECT SPOT MOBILITY FUNDS | EXEMPT |  | CMAQ | CONSTRUCTION | 180000 | FY 2023: 2000; FY 2024: 178000
HL-0060 | HIGHWAY | HIGH POINT | HIGH POINT SIGNAL SYSTEM RETIMING STUDY | 7 | High Point Urban Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 1218000 | FY 2023: 1218000
HL-0060 | HIGHWAY | HIGH POINT | HIGH POINT SIGNAL SYSTEM RETIMING STUDY | 7 | High Point Urban Area MPO |  | EXEMPT |  | L | ENGINEERING | 305000 | FY 2023: 305000
HL-0061 | HIGHWAY | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO | ROW FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | ENGINEERING | 479000 | FY 2023: 479000
HL-0061 | HIGHWAY | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO | ROW FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | CONSTRUCTION | 77000 | FY 2025: 77000
HL-0061 | HIGHWAY | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO | ROW FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | RIGHT-OF-WAY | 460000 | FY 2024: 460000
HL-0061 | HIGHWAY | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO | ROW FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | CONSTRUCTION | 310000 | FY 2025: 310000
HL-0061 | HIGHWAY | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO | ROW FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 1840000 | FY 2024: 1840000
HL-0061 | HIGHWAY | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO | ROW FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | ENGINEERING | 120000 | FY 2023: 120000
HL-0062 | HIGHWAY | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. | EXEMPT |  | L | RIGHT-OF-WAY | 191000 | FY 2024: 191000
HL-0062 | HIGHWAY | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. | EXEMPT |  | BGDA | UTILITIES | 306000 | FY 2024: 306000
HL-0062 | HIGHWAY | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. | EXEMPT |  | L | CONSTRUCTION | 1289000 | FY 2025: 1289000
HL-0062 | HIGHWAY | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. | EXEMPT |  | L | UTILITIES | 76000 | FY 2024: 76000
HL-0062 | HIGHWAY | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. | EXEMPT |  | BGDA | CONSTRUCTION | 5156000 | FY 2025: 5156000
HL-0062 | HIGHWAY | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. | EXEMPT |  | BGDA | RIGHT-OF-WAY | 764000 | FY 2024: 764000
HL-0062 | HIGHWAY | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. | EXEMPT |  | BGDA | ENGINEERING | 1117000 | FY 2023: 1117000
HL-0062 | HIGHWAY | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. | EXEMPT |  | L | ENGINEERING | 279000 | FY 2023: 279000
HL-0063 | HIGHWAY | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | BGDA | ENGINEERING | 666000 | FY 2023: 666000
HL-0063 | HIGHWAY | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 886000 | FY 2024: 886000
HL-0063 | HIGHWAY | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | BGDA | UTILITIES | 8000 | FY 2024: 8000
HL-0063 | HIGHWAY | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 3325000 | FY 2025: 3325000
HL-0063 | HIGHWAY | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | ENGINEERING | 167000 | FY 2023: 167000
HL-0063 | HIGHWAY | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 222000 | FY 2024: 222000
HL-0063 | HIGHWAY | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | UTILITIES | 2000 | FY 2024: 2000
HL-0063 | HIGHWAY | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | CONSTRUCTION | 831000 | FY 2025: 831000
HL-0064 | HIGHWAY | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | UTILITIES | 652000 | FY 2024: 652000
HL-0064 | HIGHWAY | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 4817000 | FY 2024: 4817000
HL-0064 | HIGHWAY | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BGDA | UTILITIES | 2609000 | FY 2024: 2609000
HL-0064 | HIGHWAY | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 1204000 | FY 2024: 1204000
HL-0065 | HIGHWAY | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 13 | Foothills RPO | "DP" = RAISE GRANT; "O" = OTHER FEDERAL; S(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | DIVISION 13 |  | DP | ENGINEERING | 1140000 | FY 2023: 1140000
HL-0065 | HIGHWAY | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 13 | Foothills RPO | "DP" = RAISE GRANT; "O" = OTHER FEDERAL; S(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | DIVISION 13 |  | DP | RIGHT-OF-WAY | 1050000 | FY 2024: 1050000
HL-0065 | HIGHWAY | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 13 | Foothills RPO | "DP" = RAISE GRANT; "O" = OTHER FEDERAL; S(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | DIVISION 13 |  | DP | UTILITIES | 2110000 | FY 2024: 2110000
HL-0065 | HIGHWAY | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 13 | Foothills RPO | "DP" = RAISE GRANT; "O" = OTHER FEDERAL; S(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | DIVISION 13 |  | DP | CONSTRUCTION | 15740000 | FY 2025: 15740000
HL-0065 | HIGHWAY | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 13 | Foothills RPO | "DP" = RAISE GRANT; "O" = OTHER FEDERAL; S(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | DIVISION 13 |  | L | CONSTRUCTION | 1010000 | FY 2025: 1010000
HL-0065 | HIGHWAY | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 13 | Foothills RPO | "DP" = RAISE GRANT; "O" = OTHER FEDERAL; S(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | DIVISION 13 |  | O | CONSTRUCTION | 1000000 | FY 2025: 1000000
HL-0065 | HIGHWAY | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 13 | Foothills RPO | "DP" = RAISE GRANT; "O" = OTHER FEDERAL; S(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | DIVISION 13 |  | S(M) | CONSTRUCTION | 2360000 | FY 2025: 2360000
HL-0090 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. | 13, 14 | French Broad River MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 0 | FY 2023: 0; FY 2024: 0; FY 2025: 0; FY 2026: 0
HL-0090 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. | 13, 14 | French Broad River MPO |  | EXEMPT |  | L | CONSTRUCTION | 0 | FY 2023: 0; FY 2024: 0; FY 2025: 0; FY 2026: 0
HL-0091 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE BURLINGON PLANNING ORGANIZATION. | 7 | Burlington-Graham MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 1365000 | FY 2023: 543000; FY 2024: 274000; FY 2025: 274000; FY 2026: 274000
HL-0091 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE BURLINGON PLANNING ORGANIZATION. | 7 | Burlington-Graham MPO |  | EXEMPT |  | L | CONSTRUCTION | 343000 | FY 2023: 136000; FY 2024: 69000; FY 2025: 69000; FY 2026: 69000
HL-0092 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION. | 10, 12 | Charlotte Regional TPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 6258000 | FY 2023: 0; FY 2024: 864000; FY 2025: 2697000; FY 2026: 2697000
HL-0092 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION. | 10, 12 | Charlotte Regional TPO |  | EXEMPT |  | L | CONSTRUCTION | 1564000 | FY 2023: 0; FY 2024: 216000; FY 2025: 674000; FY 2026: 674000
HL-0093 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CABARRUS-ROWAN PLANNING ORGANIZATION. | 9, 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 2445000 | FY 2023: 972000; FY 2024: 491000; FY 2025: 491000; FY 2026: 491000
HL-0093 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CABARRUS-ROWAN PLANNING ORGANIZATION. | 9, 10 | Cabarrus-Rowan MPO |  | EXEMPT |  | L | CONSTRUCTION | 612000 | FY 2023: 243000; FY 2024: 123000; FY 2025: 123000; FY 2026: 123000
HL-0094 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE DURHAM PLANNING ORGANIZATION. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 3955000 | FY 2023: 1573000; FY 2024: 794000; FY 2025: 794000; FY 2026: 794000
HL-0094 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE DURHAM PLANNING ORGANIZATION. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | CONSTRUCTION | 990000 | FY 2023: 393000; FY 2024: 199000; FY 2025: 199000; FY 2026: 199000
HL-0095 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FAYETTEVILLE PLANNING ORGANIZATION. | 6, 8 | Fayetteville Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 3531000 | FY 2023: 1404000; FY 2024: 709000; FY 2025: 709000; FY 2026: 709000
HL-0095 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FAYETTEVILLE PLANNING ORGANIZATION. | 6, 8 | Fayetteville Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 882000 | FY 2023: 351000; FY 2024: 177000; FY 2025: 177000; FY 2026: 177000
HL-0096 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GASTON CLEVELAND LINCOLN PLANNING ORGANIZATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 1927000 | FY 2023: 766000; FY 2024: 387000; FY 2025: 387000; FY 2026: 387000
HL-0096 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GASTON CLEVELAND LINCOLN PLANNING ORGANIZATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | EXEMPT |  | L | CONSTRUCTION | 483000 | FY 2023: 192000; FY 2024: 97000; FY 2025: 97000; FY 2026: 97000
HL-0097 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GOLDSBORO PLANNING ORGANIZATION. | 4 | Goldsboro Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 174000 | FY 2023: 69000; FY 2024: 35000; FY 2025: 35000; FY 2026: 35000
HL-0097 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GOLDSBORO PLANNING ORGANIZATION. | 4 | Goldsboro Urban Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 693000 | FY 2023: 276000; FY 2024: 139000; FY 2025: 139000; FY 2026: 139000
HL-0098 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENSBORO PLANNING ORGANIZATION. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 3547000 | FY 2023: 1411000; FY 2024: 712000; FY 2025: 712000; FY 2026: 712000
HL-0098 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENSBORO PLANNING ORGANIZATION. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 887000 | FY 2023: 353000; FY 2024: 178000; FY 2025: 178000; FY 2026: 178000
HL-0099 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENVILLE PLANNING ORGANIZATION. | 2 | Greenville Urban Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 1340000 | FY 2023: 533000; FY 2024: 269000; FY 2025: 269000; FY 2026: 269000
HL-0099 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENVILLE PLANNING ORGANIZATION. | 2 | Greenville Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 334000 | FY 2023: 133000; FY 2024: 67000; FY 2025: 67000; FY 2026: 67000
HL-0100 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREATER HICKORY PLANNING ORGANIZATION. | 11, 12, 13 | Greater Hickory MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 2415000 | FY 2023: 960000; FY 2024: 485000; FY 2025: 485000; FY 2026: 485000
HL-0100 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREATER HICKORY PLANNING ORGANIZATION. | 11, 12, 13 | Greater Hickory MPO |  | EXEMPT |  | L | CONSTRUCTION | 603000 | FY 2023: 240000; FY 2024: 121000; FY 2025: 121000; FY 2026: 121000
HL-0101 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE HIGH POINT PLANNING ORGANIZATION. | 7, 8, 9 | High Point Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 473000 | FY 2023: 188000; FY 2024: 95000; FY 2025: 95000; FY 2026: 95000
HL-0101 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE HIGH POINT PLANNING ORGANIZATION. | 7, 8, 9 | High Point Urban Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 1893000 | FY 2023: 753000; FY 2024: 380000; FY 2025: 380000; FY 2026: 380000
HL-0102 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE JACKSONVILLE PLANNING ORGANIZATION. | 3 | Jacksonville Urban Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 1200000 | FY 2023: 477000; FY 2024: 241000; FY 2025: 241000; FY 2026: 241000
HL-0102 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE JACKSONVILLE PLANNING ORGANIZATION. | 3 | Jacksonville Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 299000 | FY 2023: 119000; FY 2024: 60000; FY 2025: 60000; FY 2026: 60000
HL-0103 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GRAND STRAND AREA TRANSPORTATION STUDY PLANNING ORGANIZATION. | 3 | Grand Strand Area Transportation Study |  | EXEMPT |  | CRPDA | CONSTRUCTION | 230000 | FY 2023: 92000; FY 2024: 46000; FY 2025: 46000; FY 2026: 46000
HL-0103 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GRAND STRAND AREA TRANSPORTATION STUDY PLANNING ORGANIZATION. | 3 | Grand Strand Area Transportation Study |  | EXEMPT |  | L | CONSTRUCTION | 59000 | FY 2023: 23000; FY 2024: 12000; FY 2025: 12000; FY 2026: 12000
HL-0104 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE NEW BERN PLANNING ORGANIZATION. | 2 | New Bern Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 633000 | FY 2023: 288000; FY 2024: 115000; FY 2025: 115000; FY 2026: 115000
HL-0104 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE NEW BERN PLANNING ORGANIZATION. | 2 | New Bern Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 159000 | FY 2023: 72000; FY 2024: 29000; FY 2025: 29000; FY 2026: 29000
HL-0105 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION. | 4, 5, 6 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 2519000 | FY 2023: 1001000; FY 2024: 506000; FY 2025: 506000; FY 2026: 506000
HL-0105 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION. | 4, 5, 6 | Capital Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 10069000 | FY 2023: 4003000; FY 2024: 2022000; FY 2025: 2022000; FY 2026: 2022000
HL-0106 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE ROCKY MOUNT PLANNING ORGANIZATION. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 777000 | FY 2023: 309000; FY 2024: 156000; FY 2025: 156000; FY 2026: 156000
HL-0106 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE ROCKY MOUNT PLANNING ORGANIZATION. | 4 | Rocky Mount Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 194000 | FY 2023: 77000; FY 2024: 39000; FY 2025: 39000; FY 2026: 39000
HL-0107 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WILMINGTON PLANNING ORGANIZATION. | 3 | Wilmington Urban Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 2501000 | FY 2023: 995000; FY 2024: 502000; FY 2025: 502000; FY 2026: 502000
HL-0107 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WILMINGTON PLANNING ORGANIZATION. | 3 | Wilmington Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 627000 | FY 2023: 249000; FY 2024: 126000; FY 2025: 126000; FY 2026: 126000
HL-0108 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WINSTON-SALEM PLANNING ORGANIZATION. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | CRPDA | CONSTRUCTION | 4448000 | FY 2023: 1769000; FY 2024: 893000; FY 2025: 893000; FY 2026: 893000
HL-0108 | HIGHWAY | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WINSTON-SALEM PLANNING ORGANIZATION. | 9 | Winston-Salem Urban Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 1111000 | FY 2023: 442000; FY 2024: 223000; FY 2025: 223000; FY 2026: 223000
HL-0109 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | RIGHT-OF-WAY | 49000 | FY 2024: 49000
HL-0109 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 532000 | FY 2025: 532000
HL-0109 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | ENGINEERING | 109000 | FY 2023: 109000
HL-0109 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | RIGHT-OF-WAY | 12000 | FY 2024: 12000
HL-0109 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 132000 | FY 2025: 132000
HL-0109 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | ENGINEERING | 380000 | FY 2023: 380000
HL-0110 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | DIVISION 3 |  | BGDA | ENGINEERING | 47000 | FY 2023: 47000
HL-0110 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | DIVISION 3 |  | HF | CONSTRUCTION | 55000 | FY 2025: 55000
HL-0110 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | DIVISION 3 |  | HF | RIGHT-OF-WAY | 59000 | FY 2024: 59000
HL-0110 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | DIVISION 3 |  | HF | ENGINEERING | 12000 | FY 2023: 12000
HL-0110 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | DIVISION 3 |  | BGDA | RIGHT-OF-WAY | 237000 | FY 2024: 237000
HL-0110 | HIGHWAY | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | DIVISION 3 |  | BGDA | CONSTRUCTION | 219000 | FY 2025: 219000
HL-0111 | HIGHWAY | BEATY STREET | MAIN STREET. INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | ENGINEERING | 215000 | FY 2025: 215000
HL-0111 | HIGHWAY | BEATY STREET | MAIN STREET. INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | CONSTRUCTION | 1097000 | FY 2029: 1097000
HL-0111 | HIGHWAY | BEATY STREET | MAIN STREET. INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 136000 | FY 2027: 136000
HL-0111 | HIGHWAY | BEATY STREET | MAIN STREET. INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 203000 | FY 2027: 203000
HL-0111 | HIGHWAY | BEATY STREET | MAIN STREET. INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1645000 | FY 2029: 1645000
HL-0111 | HIGHWAY | BEATY STREET | MAIN STREET. INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | ENGINEERING | 143000 | FY 2025: 143000
HL-0112 | HIGHWAY | DEARMON ROAD | BENFIELD ROAD TO BROWNE ROAD. COMPLETE STREET IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 5486000 | FY 2024: 5486000
HL-0112 | HIGHWAY | DEARMON ROAD | BENFIELD ROAD TO BROWNE ROAD. COMPLETE STREET IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 10189000 | FY 2024: 10189000
HL-0113 | HIGHWAY | LANCASTER HIGHWAY | PROVIDENCE ROAD W. INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1185000 | FY 2026: 1185000
HL-0113 | HIGHWAY | LANCASTER HIGHWAY | PROVIDENCE ROAD W. INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | CONSTRUCTION | 508000 | FY 2026: 508000
HL-0114 | HIGHWAY | LANGTREE ROAD | PIN OAK LANE TO MOUNT MOURNE LOOP. WIDEN ROADWAY. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | BGDA | ENGINEERING | 873000 | FY 2024: 873000
HL-0114 | HIGHWAY | LANGTREE ROAD | PIN OAK LANE TO MOUNT MOURNE LOOP. WIDEN ROADWAY. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | L | ENGINEERING | 218000 | FY 2024: 218000
HL-0115 | HIGHWAY | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMRPOVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | RIGHT-OF-WAY | 103000 | FY 2027: 103000
HL-0115 | HIGHWAY | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMRPOVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 620000 | FY 2029: 620000
HL-0115 | HIGHWAY | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMRPOVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | ENGINEERING | 92000 | FY 2025: 92000
HL-0115 | HIGHWAY | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMRPOVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 414000 | FY 2027: 414000
HL-0115 | HIGHWAY | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMRPOVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | ENGINEERING | 369000 | FY 2025: 369000
HL-0115 | HIGHWAY | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMRPOVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGDA | CONSTRUCTION | 2479000 | FY 2029: 2479000
HL-0116 | HIGHWAY | BONDS GROVE CHURCH ROAD | WAXAHW MARVIN ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 119000 | FY 2026: 119000
HL-0116 | HIGHWAY | BONDS GROVE CHURCH ROAD | WAXAHW MARVIN ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | ENGINEERING | 350000 | FY 2024: 350000
HL-0116 | HIGHWAY | BONDS GROVE CHURCH ROAD | WAXAHW MARVIN ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | CONSTRUCTION | 885000 | FY 2028: 885000
HL-0116 | HIGHWAY | BONDS GROVE CHURCH ROAD | WAXAHW MARVIN ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | ENGINEERING | 88000 | FY 2024: 88000
HL-0116 | HIGHWAY | BONDS GROVE CHURCH ROAD | WAXAHW MARVIN ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 3542000 | FY 2028: 3542000
HL-0116 | HIGHWAY | BONDS GROVE CHURCH ROAD | WAXAHW MARVIN ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 476000 | FY 2026: 476000
HL-0117 | HIGHWAY | NC 218 | LOVE MILL ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 216000 | FY 2024: 216000
HL-0117 | HIGHWAY | NC 218 | LOVE MILL ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 1644000 | FY 2026: 1644000
HL-0117 | HIGHWAY | NC 218 | LOVE MILL ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | ENGINEERING | 60000 | FY 2023: 60000
HL-0117 | HIGHWAY | NC 218 | LOVE MILL ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 92000 | FY 2024: 92000
HL-0117 | HIGHWAY | NC 218 | LOVE MILL ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | CONSTRUCTION | 705000 | FY 2026: 705000
HL-0117 | HIGHWAY | NC 218 | LOVE MILL ROAD. INSTALL ROUNDABOUT. | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | ENGINEERING | 140000 | FY 2023: 140000
HL-0118 | HIGHWAY | STUMPTOWN ROAD | NC 115. EXTEND ROADWAY APPROXIMATELY 800 FEET. | 10 | Charlotte Regional TPO |  | REGION E |  | L | ENGINEERING | 37000 | FY 2025: 37000
HL-0118 | HIGHWAY | STUMPTOWN ROAD | NC 115. EXTEND ROADWAY APPROXIMATELY 800 FEET. | 10 | Charlotte Regional TPO |  | REGION E |  | L | RIGHT-OF-WAY | 396000 | FY 2025: 396000
HL-0118 | HIGHWAY | STUMPTOWN ROAD | NC 115. EXTEND ROADWAY APPROXIMATELY 800 FEET. | 10 | Charlotte Regional TPO |  | REGION E |  | BGDA | RIGHT-OF-WAY | 1584000 | FY 2025: 1584000
HL-0118 | HIGHWAY | STUMPTOWN ROAD | NC 115. EXTEND ROADWAY APPROXIMATELY 800 FEET. | 10 | Charlotte Regional TPO |  | REGION E |  | BGDA | ENGINEERING | 148000 | FY 2025: 148000
HL-0118 | HIGHWAY | STUMPTOWN ROAD | NC 115. EXTEND ROADWAY APPROXIMATELY 800 FEET. | 10 | Charlotte Regional TPO |  | REGION E |  | L | CONSTRUCTION | 856000 | FY 2027: 856000
HL-0118 | HIGHWAY | STUMPTOWN ROAD | NC 115. EXTEND ROADWAY APPROXIMATELY 800 FEET. | 10 | Charlotte Regional TPO |  | REGION E |  | BGDA | CONSTRUCTION | 3424000 | FY 2027: 3424000
HL-0119 | HIGHWAY | SR 1005 (SIX FORKS ROAD) | ROWAN STREET TO SR 1827 (LYNN ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPERATED BIKEWAYS, RPOTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 14000000 | FY 2024: 14000000
HL-0119 | HIGHWAY | SR 1005 (SIX FORKS ROAD) | ROWAN STREET TO SR 1827 (LYNN ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPERATED BIKEWAYS, RPOTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 14000000 | FY 2024: 14000000
HL-0120 | HIGHWAY | US 15 | INTERSECTION OF US 15 AND SR 1129 (HESTER ROAD) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 258000 | FY 2024: 258000
HL-0120 | HIGHWAY | US 15 | INTERSECTION OF US 15 AND SR 1129 (HESTER ROAD) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 144000 | FY 2024: 144000
HL-0120 | HIGHWAY | US 15 | INTERSECTION OF US 15 AND SR 1129 (HESTER ROAD) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 1373000 | FY 2024: 1373000
HL-0120 | HIGHWAY | US 15 | INTERSECTION OF US 15 AND SR 1129 (HESTER ROAD) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | ENGINEERING | 64000 | FY 2024: 64000
HL-0120 | HIGHWAY | US 15 | INTERSECTION OF US 15 AND SR 1129 (HESTER ROAD) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 36000 | FY 2024: 36000
HL-0120 | HIGHWAY | US 15 | INTERSECTION OF US 15 AND SR 1129 (HESTER ROAD) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 343000 | FY 2024: 343000
HL-0121 | HIGHWAY | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 622000 | FY 2024: 622000
HL-0121 | HIGHWAY | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 155000 | FY 2024: 155000
HL-0121 | HIGHWAY | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | ENGINEERING | 53000 | FY 2024: 53000
HL-0121 | HIGHWAY | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 82000 | FY 2024: 82000
HL-0121 | HIGHWAY | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 213000 | FY 2024: 213000
HL-0121 | HIGHWAY | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 21000 | FY 2024: 21000
HM-0001 | HIGHWAY | EAST FISHER STREET | REPLACE BRIDGE 138 OVER NORFOLK SOUTHERN RAILROAD BETWEEN SOUTH LONG STREET AND SOUTH LEE STREET IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | BFPOFF | CONSTRUCTION | 2000000 | FY 2024: 2000000
HM-0002 | HIGHWAY | SHELLEY ROAD | REPLACE BRIDGE NUMBER 378 OVER MINE CREEK FROM SHADOWBROOK DRIVE TO FOREST LAWN COURT. | 5 | Capital Area MPO |  | DIVISION 5 |  | BFPOFF | CONSTRUCTION | 2500000 | FY 2024: 2500000
HM-0002 | HIGHWAY | SHELLEY ROAD | REPLACE BRIDGE NUMBER 378 OVER MINE CREEK FROM SHADOWBROOK DRIVE TO FOREST LAWN COURT. | 5 | Capital Area MPO |  | DIVISION 5 |  | BFPOFF | UTILITIES | 250000 | FY 2024: 250000
HM-0003 | HIGHWAY | CHESWICK DRIVE | REPLACE BRIDGE NUMBER 627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 5 | Capital Area MPO |  | DIVISION 5 |  | BFPOFF | ENGINEERING | 500000 | FY 2024: 500000
HM-0003 | HIGHWAY | CHESWICK DRIVE | REPLACE BRIDGE NUMBER 627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 5 | Capital Area MPO |  | DIVISION 5 |  | BFPOFF | RIGHT-OF-WAY | 250000 | FY 2024: 250000
HM-0003 | HIGHWAY | CHESWICK DRIVE | REPLACE BRIDGE NUMBER 627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 5 | Capital Area MPO |  | DIVISION 5 |  | BFPOFF | UTILITIES | 250000 | FY 2025: 250000
HM-0003 | HIGHWAY | CHESWICK DRIVE | REPLACE BRIDGE NUMBER 627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 5 | Capital Area MPO |  | DIVISION 5 |  | BFPOFF | CONSTRUCTION | 1250000 | FY 2025: 1250000
HO-0001 | HIGHWAY | VARIOUS | NCDOT MULTI-MODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT | EXEMPT |  | DP | ENGINEERING | 64000
HO-0001 | HIGHWAY | VARIOUS | NCDOT MULTI-MODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT | EXEMPT |  | S | ENGINEERING | 247000
HO-0001 | HIGHWAY | VARIOUS | NCDOT MULTI-MODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT | EXEMPT |  | S | CONSTRUCTION | 227000 | FY 2023: 87000; FY 2024: 94000
HO-0001AA | HIGHWAY | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | S | ENGINEERING | 183000 | FY 2023: 37000
HO-0001AA | HIGHWAY | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | S | CONSTRUCTION | 1490000 | FY 2023: 803000; FY 2024: 370000; FY 2025: 282000; FY 2026: 35000
HO-0001AA | HIGHWAY | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | DP | CONSTRUCTION | 1491000 | FY 2023: 804000; FY 2024: 370000; FY 2025: 282000; FY 2026: 35000
HO-0001AA | HIGHWAY | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. | 5 | Capital Area MPO | UNDER CONSTRUCTION | EXEMPT |  | DP | ENGINEERING | 186000 | FY 2023: 38000
HO-0001AB | HIGHWAY | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. | 5 | Capital Area MPO |  | EXEMPT |  | DP | CONSTRUCTION | 84000 | FY 2023: 84000
HO-0001AB | HIGHWAY | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. | 5 | Capital Area MPO |  | EXEMPT |  | S | ENGINEERING | 75000
HO-0001AB | HIGHWAY | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. | 5 | Capital Area MPO |  | EXEMPT |  | S | CONSTRUCTION | 84000 | FY 2023: 84000
HO-0001AB | HIGHWAY | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. | 5 | Capital Area MPO |  | EXEMPT |  | DP | ENGINEERING | 75000
HO-0001AC | HIGHWAY | NCSU CAMPUS | ECO DRIVING APPLICATION | 5 | Capital Area MPO | PROJECT DELETED | EXEMPT |  | DP | CONSTRUCTION | 352000 | FY 2024: 352000
HO-0001AC | HIGHWAY | NCSU CAMPUS | ECO DRIVING APPLICATION | 5 | Capital Area MPO | PROJECT DELETED | EXEMPT |  | S | ENGINEERING | 37000 | FY 2023: 37000
HO-0001AC | HIGHWAY | NCSU CAMPUS | ECO DRIVING APPLICATION | 5 | Capital Area MPO | PROJECT DELETED | EXEMPT |  | DP | ENGINEERING | 37000 | FY 2023: 37000
HO-0001AC | HIGHWAY | NCSU CAMPUS | ECO DRIVING APPLICATION | 5 | Capital Area MPO | PROJECT DELETED | EXEMPT |  | S | CONSTRUCTION | 352000 | FY 2024: 352000
HO-0001B | HIGHWAY | NCSU CAMPUS | SYSTEMS ENGINEERING, GRANT ADMINISTRATION | 5 | Capital Area MPO |  | EXEMPT |  | DP | ENGINEERING | 50000 | FY 2023: 5000; FY 2024: 5000
HO-0001B | HIGHWAY | NCSU CAMPUS | SYSTEMS ENGINEERING, GRANT ADMINISTRATION | 5 | Capital Area MPO |  | EXEMPT |  | S | ENGINEERING | 150000 | FY 2023: 5000; FY 2024: 5000
HO-0001C | HIGHWAY | NCSU CAMPUS | BEFORE & AFTER STUDY, EXPANSION FEASIBILITY STUDY | 5 | Capital Area MPO |  | EXEMPT |  | DP | ENGINEERING | 156000 | FY 2023: 88000; FY 2024: 25000
HO-0001C | HIGHWAY | NCSU CAMPUS | BEFORE & AFTER STUDY, EXPANSION FEASIBILITY STUDY | 5 | Capital Area MPO |  | EXEMPT |  | S | ENGINEERING | 154000 | FY 2023: 87000; FY 2024: 25000
HO-0002A | HIGHWAY | US 74 | I-40 IN ASHEVILLE TO I-77 AT I-485 (SOUTH) IN CHARLOTTE. INSTALL BROADBAND. | 10, 12, 13, 14 | Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002B, AND HO-0002C. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 18435000 | FY 2023: 4539000; FY 2024: 434000
HO-0002B | HIGHWAY | US 74 | EASTERN END OF MONROE BYPASS TO I-95 IN LUMBERTON. INSTALL BROADBAND AND ITS COMPONENTS INCLUDING CONNECTIONS TO SIGNAL SYSTEMS, DMS, AND CCTV. | 6, 8, 10 | Lumber River RPO, Rocky River RPO, Charlotte Regional TPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002C. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 14216000 | FY 2023: 3046000
HO-0002C | HIGHWAY | US 74 | I-95 IN LUMBERTON TO I-140 IN WILMINGTON. INSTALL BROADBAND. | 3, 6 | Cape Fear RPO, Lumber River RPO, Wilmington Urban Area MPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002B. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 10456000 | FY 2023: 1505000
HO-0002D | HIGHWAY | US 74 | EASTERN END OF MONROE BYPASS TO I-140 IN WILMINGTON. VULNERABILITY ASSESSMENTS, INSTALLATION OF FLOOD GAUGES, AND FLOOD MONITORING. | 3, 6, 8, 10 | Lumber River RPO, Cape Fear RPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 440000
HO-0002D | HIGHWAY | US 74 | EASTERN END OF MONROE BYPASS TO I-140 IN WILMINGTON. VULNERABILITY ASSESSMENTS, INSTALLATION OF FLOOD GAUGES, AND FLOOD MONITORING. | 3, 6, 8, 10 | Lumber River RPO, Cape Fear RPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | DP | ENGINEERING | 1760000
HO-0003 | HIGHWAY | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. | 14 | Land-of-Sky RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 100000
HO-0003 | HIGHWAY | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. | 14 | Land-of-Sky RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 100000 | FY 2023: 100000
HO-0003 | HIGHWAY | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. | 14 | Land-of-Sky RPO |  | EXEMPT |  | L | IMPLEMENTATION | 25000
HO-0003 | HIGHWAY | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. | 14 | Land-of-Sky RPO |  | EXEMPT |  | L | IMPLEMENTATION | 25000 | FY 2023: 25000
HO-0004 | HIGHWAY | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. | 14 | Southwestern RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 100000
HO-0004 | HIGHWAY | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. | 14 | Southwestern RPO |  | EXEMPT |  | L | IMPLEMENTATION | 25000 | FY 2023: 25000
HO-0004 | HIGHWAY | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. | 14 | Southwestern RPO |  | EXEMPT |  | CMAQ | IMPLEMENTATION | 100000 | FY 2023: 100000
HO-0004 | HIGHWAY | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. | 14 | Southwestern RPO |  | EXEMPT |  | L | IMPLEMENTATION | 25000
HO-0005 | HIGHWAY | VARIOUS | NCDOT TRAFFIC SYSTEMS OPERATIONS. INSTALL STATEWIDE ITS DEVICE OPERATIONS. | 4, 5, 7, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Winston-Salem Urban Area MPO, Greensboro Urban Area MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Rocky Mount Urban Area MP | UNDER CONSTRUCTION. | EXEMPT |  | CMAQ | CONSTRUCTION | 17284000 | FY 2023: 5828000; FY 2024: 6096000
HO-0005 | HIGHWAY | VARIOUS | NCDOT TRAFFIC SYSTEMS OPERATIONS. INSTALL STATEWIDE ITS DEVICE OPERATIONS. | 4, 5, 7, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Winston-Salem Urban Area MPO, Greensboro Urban Area MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Rocky Mount Urban Area MP | UNDER CONSTRUCTION. | EXEMPT |  | S(M) | CONSTRUCTION | 4321000 | FY 2023: 1457000; FY 2024: 1524000
HO-0009 | HIGHWAY | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount | "S" FUNDING REFLECTS PARTICIPATION BY DAQ | EXEMPT |  | S | IMPLEMENTATION | 282000
HO-0009 | HIGHWAY | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount | "S" FUNDING REFLECTS PARTICIPATION BY DAQ | EXEMPT |  | CMAQ | IMPLEMENTATION | 578000
HO-0009 | HIGHWAY | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount | "S" FUNDING REFLECTS PARTICIPATION BY DAQ | EXEMPT |  | CMAQ | IMPLEMENTATION | 595000 | FY 2023: 595000
HO-0009 | HIGHWAY | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount | "S" FUNDING REFLECTS PARTICIPATION BY DAQ | EXEMPT |  | L | IMPLEMENTATION | 149000 | FY 2023: 149000
HO-0010A | HIGHWAY | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT IN THE TRIANGLE AND METROLINA AREAS. | 4, 5, 6, 7, 8, 9, 10, 12 | Capital Area MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO, Cabarrus-Rowan MPO, Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | S(M) | IMPLEMENTATION | 800000 | FY 2023: 800000
HO-0010A | HIGHWAY | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT IN THE TRIANGLE AND METROLINA AREAS. | 4, 5, 6, 7, 8, 9, 10, 12 | Capital Area MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO, Cabarrus-Rowan MPO, Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | CRPANY | IMPLEMENTATION | 3200000 | FY 2023: 3200000
HO-0010B | HIGHWAY | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT ACROSS THE ENTIRE STATE. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | CRPANY | IMPLEMENTATION | 8000000 | FY 2024: 4000000; FY 2025: 4000000
HO-0010B | HIGHWAY | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT ACROSS THE ENTIRE STATE. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | S(M) | IMPLEMENTATION | 2000000 | FY 2024: 1000000; FY 2025: 1000000
HO-0011 | HIGHWAY | I-40 AND I-95 | I-40 FROM TENNESSEE STATE LINE TO MM 20 AND I-95 FROM EXIT 13 TO SOUTH OF PROPOSED I-295. IMPLEMENT SYSTEM TO PROVIDE REAL TIME ALERTS IN VEHICLES WHEN DRIVERS ENCOUNTER A ROAD ANOMALY REQUIRING THEM TO TAKE DRIVING ACTION. | 6, 14 | Land-of-Sky RPO, Lumber River RPO | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH. | STATEWIDE MOBILITY |  | DP | IMPLEMENTATION | 1534000 | FY 2024: 1534000
HO-0011 | HIGHWAY | I-40 AND I-95 | I-40 FROM TENNESSEE STATE LINE TO MM 20 AND I-95 FROM EXIT 13 TO SOUTH OF PROPOSED I-295. IMPLEMENT SYSTEM TO PROVIDE REAL TIME ALERTS IN VEHICLES WHEN DRIVERS ENCOUNTER A ROAD ANOMALY REQUIRING THEM TO TAKE DRIVING ACTION. | 6, 14 | Land-of-Sky RPO, Lumber River RPO | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH. | STATEWIDE MOBILITY |  | O | IMPLEMENTATION | 438000 | FY 2024: 438000
HS-2001A | HIGHWAY | US 158 | CONSTRUCT ROUNDABOUT AT US 158 AND SR 1147 (INDIANTOWN ROAD). | 1 | Albemarle RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 45000 | FY 2023: 45000
HS-2001B | HIGHWAY | US 13, US 17, NC 171 | UPGRADE CURVE WARNING SIGNS AT VARIOUS LOCATIONS. | 1 | Mid-East RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 35000 | FY 2023: 35000
HS-2001C | HIGHWAY | SR 1354 (MILLPOND ROAD) | SR 1354 (MILLPOND ROAD) BETWEEN US 158 AND SR 1001 (TURNPIKE ROAD). UPGRADE PAVEMENT MARKINGS. | 1 | Albemarle RPO |  | DIVISION 1 |  | HSIP | CONSTRUCTION | 40000 | FY 2024: 40000
HS-2001D | HIGHWAY | VARIOUS | UPGRADE WARNING SIGNS AT CURVES AT VARIOUS LOCATIONS. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | HSIP | CONSTRUCTION | 41000 | FY 2023: 41000
HS-2001E | HIGHWAY | VARIOUS | UPGRADE WARNING SIGNS AT CURVES AT VARIOUS LOCATIONS. | 1 | Peanut Belt RPO, Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | HSIP | CONSTRUCTION | 12000 | FY 2023: 12000
HS-2001F | HIGHWAY | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | T | UTILITIES | 534000 | FY 2023: 534000
HS-2001F | HIGHWAY | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | T | CONSTRUCTION | 1600000 | FY 2024: 16000; FY 2025: 1584000
HS-2001F | HIGHWAY | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | T | RIGHT-OF-WAY | 1534000 | FY 2023: 1534000
HS-2001F | HIGHWAY | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | HSIP | UTILITIES | 266000 | FY 2023: 266000
HS-2001F | HIGHWAY | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | HSIP | RIGHT-OF-WAY | 766000 | FY 2023: 766000
HS-2001F | HIGHWAY | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | HSIP | CONSTRUCTION | 800000 | FY 2024: 8000; FY 2025: 792000
HS-2002A | HIGHWAY | SR 1703 (14TH STREET) | INSTALL CROSSWALK, WHEELCHAIR RAMPS, SIDEWALK, AND FENCING ALONG SR 1703 (14TH STREET) FROM HASKETT WAY AND BERKLEY ROAD. REMOVE TWO EXISTING OBSOLETE CROSSWALKS. | 2 | Greenville Urban Area MPO | COMPLETED. | DIVISION 2 |  | HSIP | CONSTRUCTION | 50000
HS-2002B | HIGHWAY | NC 24 | NC 24 BETWEEN SR 1259 (TAYLOR NOTION ROAD) AND US 70. INSTALL PAVEMENT MARKINGS AND RUMBLE STRIPES ON TWO-WAY LEFT TURN LANE. | 2 | Down East RPO | COMPLETED. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 640000
HS-2002C | HIGHWAY | US 70 | INSTALL RESTRICTED CROSSING INTERSECTIONS AT US 70 AND SR 1324 (KENNEDY HOME ROAD) / SR 1519 (EASON ROAD) AND AT ADJACENT CROSSOVER TO THE WEST. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | UTILITIES | 20000
HS-2002C | HIGHWAY | US 70 | INSTALL RESTRICTED CROSSING INTERSECTIONS AT US 70 AND SR 1324 (KENNEDY HOME ROAD) / SR 1519 (EASON ROAD) AND AT ADJACENT CROSSOVER TO THE WEST. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 250000
HS-2002D | HIGHWAY | US 264 | CONSTRUCT REDUCED CONFLICT INTERSECTION AT US 264 AND SR 1410 (VOA ROAD). | 2 | Mid-East RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 889000 | FY 2023: 100000
HS-2002D | HIGHWAY | US 264 | CONSTRUCT REDUCED CONFLICT INTERSECTION AT US 264 AND SR 1410 (VOA ROAD). | 2 | Mid-East RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 15000
HS-2002E | HIGHWAY | US 264 ALTERNATE | US 264 ALTERNATE (GREENVILLE BOULEVARD) AT SR 1534 (OLD PACTOLUS ROAD). CONSTRUCT RESTRICTED-CROSSING INTERSECTION. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 732000 | FY 2023: 732000
HS-2002F | HIGHWAY | SR 1001 / SR 1256 (MAIN STREET) | SR 1001 / SR 1256 (MAIN STREET) AT SR 1005 (SUNSET BOULEVARD). INSTALL ALL WAY STOP, REVISE OVERHEAD FLASHER, AND INSTALL CHANNELIZATION. | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | HSIP | CONSTRUCTION | 58000 | FY 2023: 58000
HS-2002F | HIGHWAY | SR 1001 / SR 1256 (MAIN STREET) | SR 1001 / SR 1256 (MAIN STREET) AT SR 1005 (SUNSET BOULEVARD). INSTALL ALL WAY STOP, REVISE OVERHEAD FLASHER, AND INSTALL CHANNELIZATION. | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | HSIP | RIGHT-OF-WAY | 15000
HS-2002G | HIGHWAY | NC 58 (SALTER PATH ROAD) | NC 58 (SALTER PATH ROAD) AT THE OCEAN CLUB ENTRANCE JUST WEST OF TRADEWINDS DRIVE. INSTALL CROSSWALK WITH RAPID FLASHING BEACONS. | 2 | Down East RPO | COMPLETED. | REGION B |  | HSIP | CONSTRUCTION | 25000
HS-2002H | HIGHWAY | NC 58 (WEST FORT MACON ROAD) | NC 58 (WEST FORT MACON ROAD) AT ATLANTIC STATION SHOPPING CENTER / ATLANTIC BEACH TOWN PARK. INSTALL PEDESTRIAN HEADS FOR EXISTING SIGNAL AND WHEEL CHAIR RAMP REVISIONS. | 2 | Down East RPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 12000 | FY 2023: 12000
HS-2002I | HIGHWAY | NC 58 | NC 58 JUST WEST OF CEDAR LANE. INSTALL CROSSWALKS, CONCRETE MONOLITHIC PEDESTRIAN REFUGE ISLAND, SIDEWALKS, AND RECTANGULAR RAPID-FLASHING BEACONS. | 2 | Down East RPO |  | REGION B |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2024: 5000
HS-2002I | HIGHWAY | NC 58 | NC 58 JUST WEST OF CEDAR LANE. INSTALL CROSSWALKS, CONCRETE MONOLITHIC PEDESTRIAN REFUGE ISLAND, SIDEWALKS, AND RECTANGULAR RAPID-FLASHING BEACONS. | 2 | Down East RPO |  | REGION B |  | HSIP | CONSTRUCTION | 77000 | FY 2025: 77000
HS-2002J | HIGHWAY | NC 33 | NC 33 FROM US 13/NC 11 (MEMORIAL DRIVE) TO DAUGHTRIDGE DRIVE IN GREENVILLE. INSTALL MEDIAN ISLAND AND REVISE PAVEMENT MARKINGS. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 120000 | FY 2023: 73000; FY 2024: 47000
HS-2002K | HIGHWAY | NC 11 | NC 11 AT SR 1716 (HARVEY ROUSE ROAD), NC 11 AT NC 118/SR 1091 (GRIFTON-HUGO ROAD), AND NC 11 AT SR 1714 (CREEK ROAD). CONVERT MEDIAN OPENINGS TO REDUCED CONFLICT INTERSECTIONS. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | UTILITIES | 80000 | FY 2023: 80000
HS-2002K | HIGHWAY | NC 11 | NC 11 AT SR 1716 (HARVEY ROUSE ROAD), NC 11 AT NC 118/SR 1091 (GRIFTON-HUGO ROAD), AND NC 11 AT SR 1714 (CREEK ROAD). CONVERT MEDIAN OPENINGS TO REDUCED CONFLICT INTERSECTIONS. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 846000 | FY 2023: 297000; FY 2024: 549000
HS-2002L | HIGHWAY | US 264 ALTERNATE | US 264 ALTERNATE/NC 43 (GREENVILLE BOULEVARD) AT NC 11/NC 43/NC 903 (MEMORIAL DRIVE) AND NC 11/NC 903 (MEMORIAL DRIVE) AT MALL DRIVE IN GREENVILLE. REVISE AND CONSTRUCT TURN LANES. | 2 | Greenville Urban Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 430000 | FY 2024: 430000
HS-2002M | HIGHWAY | SR 1598 (10TH STREET) | SR 1598 (10TH STREET) AT COLLEGE HILL DRIVE AND SR 1598 (10TH STREET) AT ELM STREET IN GREENVILLE. UPGRADE TRAFFIC SIGNALS. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 2 |  | HSIP | CONSTRUCTION | 55000 | FY 2023: 33000; FY 2024: 22000
HS-2002N | HIGHWAY | US 258 | US 258 AT SR 1342 (WILL BAKER ROAD / CENTRAL AVENUE). INSTALL FLASHER AND UPGRADE TRAFFIC SIGNAL. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 62000 | FY 2023: 38000; FY 2024: 24000
HS-2002O | HIGHWAY | US 17 BUSINESS (MARTIN LUTHER KING JR. BOULEVARD) | US 17 BUSINESS (MARTIN LUTHER KING JR. BOULEVARD) AT TRENT CREEK ROAD. INSTALL FLASHER. | 2 | New Bern Area MPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 25000 | FY 2023: 11000; FY 2024: 14000
HS-2002P | HIGHWAY | US 258 | US 258 AT SR 1120 (NOBLES MILL ROAD) AND US 258 AT SR 1908 (BILL STROUD ROAD). CONSTRUCT TURN LANES. | 2 | Eastern Carolina RPO | UTILITY RELOCATION IN PROGRESS. | REGION B |  | HSIP | UTILITIES | 150000 | FY 2024: 150000
HS-2002P | HIGHWAY | US 258 | US 258 AT SR 1120 (NOBLES MILL ROAD) AND US 258 AT SR 1908 (BILL STROUD ROAD). CONSTRUCT TURN LANES. | 2 | Eastern Carolina RPO | UTILITY RELOCATION IN PROGRESS. | REGION B |  | HSIP | CONSTRUCTION | 661000 | FY 2024: 661000
HS-2002Q | HIGHWAY | US 258 | US 258 BETWEEN NC 24 IN RICHLANDS AND US 70 IN KINSTON. INSTALL RUMBLES STRIPES. | 2, 3 | Eastern Carolina RPO, Jacksonville Urban Area MPO, Down East RPO |  | REGION B |  | HSIP | CONSTRUCTION | 585000 | FY 2025: 357000; FY 2026: 228000
HS-2002R | HIGHWAY | SR 1702 (EVANS STREET) | SR 1702 (EVANS STREET) AT HOWELL STREET IN GREENVILLE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 2 |  | HSIP | UTILITIES | 65000 | FY 2023: 65000
HS-2002R | HIGHWAY | SR 1702 (EVANS STREET) | SR 1702 (EVANS STREET) AT HOWELL STREET IN GREENVILLE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 2 |  | HSIP | CONSTRUCTION | 400000 | FY 2023: 400000
HS-2002S | HIGHWAY | NC 43 | NC 43 BETWEEN NC 118 IN CRAVEN COUNTY AND SR 1730 (HERMAN GARRIS ROAD) IN PITT COUNTY, NC 43 BETWEEN SR 1205 (ROCK SPRING ROAD) AND THE SOUTHERN LIMITS OF FALKLAND, AND NC 43 BETWEEN THE NORTHERN LIMITS OF FALKLAND IN PITT COUNTY AND NC 42 IN EDGECOMBE COUNTY. INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Down East RPO, Upper Coastal Plain RPO |  | REGION A, B |  | HSIP | CONSTRUCTION | 760000 | FY 2024: 760000
HS-2002T | HIGHWAY | US 264 | US 264 BETWEEN THE WILSON COUNTY LINE AND SR 1128 (DAVENPORT FARM ROAD) / SR 1206 (BELL ARTHUR ROAD) IN PITT COUNTY. INSTALL RUMBLE STRIPES. | 2 | Mid-East RPO, Eastern Carolina RPO, Greenville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 378000 | FY 2023: 378000
HS-2002U | HIGHWAY | SR 1310 (LENNOXVILLE ROAD) | SR 1310 (LENNOXVILLE ROAD) AT CARTERET AVENUE IN BEAUFORT. INSTALL CROSSWALK SIGNALIZATION. | 2 | Down East RPO | UNDER CONSTRUCTION. | DIVISION 2 |  | HSIP | CONSTRUCTION | 25000 | FY 2023: 25000
HS-2002V | HIGHWAY | NC 55 (NEUSE BOULEVARD) | AT SR 1215 (SIMMONS STREET) IN NEW BERN. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 2 | New Bern Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 18000 | FY 2024: 18000
HS-2002W | HIGHWAY | NC 55 (NEUSE BOULEVARD) | AT SR 1309 / SR 1402 (GLENBURNIE ROAD) IN NEW BERN. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 2 | New Bern Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 18000 | FY 2024: 18000
HS-2002X | HIGHWAY | SR 1725 (COUNTY HOME ROAD) | AT EXISTING CROSSWALK JUST SOUTH OF DISTRICT PARK DRIVE IN GREENVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 2 |  | HSIP | CONSTRUCTION | 35000 | FY 2023: 35000
HS-2003A | HIGHWAY | SR 1217 (17TH STREET) | INSTALL NEAR SIDE SIGNAL HEADS ON PEDESTAL ON BOTH SIDES OF SR 1217 (17TH STREET) AT DOCK STREET IN WILMINGTON. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | HSIP | CONSTRUCTION | 34000 | FY 2023: 34000
HS-2003B | HIGHWAY | VARIOUS | INSTALL PAVEMENT MARKINGS ALONG VARIOUS ROUTES. | 3 | Eastern Carolina RPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | HSIP | CONSTRUCTION | 3432000
HS-2003C | HIGHWAY | SR 1535 (LIDDELL ROAD) | SR 1535 (LIDDELL ROAD) AND SR 1534 (DRUMMERSVILLE ROAD). INSTALL ALL WAY STOP. | 3 | Eastern Carolina RPO |  | DIVISION 3 |  | HSIP | CONSTRUCTION | 31000 | FY 2024: 31000
HS-2003D | HIGHWAY | US 17 | US 17 AND SR 1130 (MOUNT PISGAH ROAD) / SR 1344 (SELLERS ROAD). INSTALL SIGNALIZED LEFTOVER. | 3 | Grand Strand Area Transportation Study |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 269000 | FY 2025: 269000
HS-2003E | HIGHWAY | US 117 (SYCAMORE STREET) | US 117 (SYCAMORE STREET) AND SR 1102 (CHARITY ROAD) IN ROSE HILL. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 3 | Eastern Carolina RPO |  | REGION B |  | HSIP | CONSTRUCTION | 97000 | FY 2025: 97000
HS-2003F | HIGHWAY | US 17 | US 17 AND NC 210 WEST OF SNEADS FERRY. REVISE TRAFFIC SIGNAL AND INSTALL BE PREPARED TO STOP SIGNS. | 3 | Cape Fear RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 194000 | FY 2026: 194000
HS-2003G | HIGHWAY | NC 130 | NC 130 AND SR 1120 (SABBATH HOME ROAD) / SR 1239 (OCEAN VIEW AVENUE) IN HOLDEN BEACH. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 3 | Grand Strand Area Transportation Study |  | REGION B |  | HSIP | CONSTRUCTION | 84000 | FY 2026: 84000
HS-2003H | HIGHWAY | US 117 / NC 132 (COLLEGE ROAD) | US 117 / NC 132 (COLLEGE ROAD) AT LAKE AVENUE-HUGH MCRAE PARK IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 66000 | FY 2025: 66000
HS-2003I | HIGHWAY | NC 403 | NC 403 AT SR 1306 (BEAUTANCUS ROAD). INSTALL ALL WAY STOP, STOP AHEAD WARNING SIGNS, BRIGHTSIDES, STOP BARS, CONCRETE ISLAND, AND REFRESH PAVEMENT MARKINGS. REMOVE ACTUATED CURVE WARNING FLASHER. | 3 | Eastern Carolina RPO |  | REGION B |  | HSIP | CONSTRUCTION | 154000 | FY 2024: 154000
HS-2003J | HIGHWAY | US 17 (OLEANDER DRIVE) | US 17 (OLEANDER DRIVE) AT 42ND STREET IN WILMINGTON. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 59000 | FY 2025: 59000
HS-2003K | HIGHWAY | US 74 WESTBOUND ON-RAMP | US 74 WESTBOUND ON-RAMP AND SR 1627 (3RD STREET / MARTIN LUTHER KING JUNIOR BOULEVARD) IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 16000 | FY 2025: 16000
HS-2003L | HIGHWAY | US 17-76 (OLEANDER DRIVE) | US 17-76 (OLEANDER DRIVE) AND SR 1421 (GREENVILLE LOOP ROAD) / GREENVILLE AVENUE IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 3 | Wilmington Urban Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 84000 | FY 2025: 84000
HS-2003M | HIGHWAY | US 117 (NORWOOD STREET) | US 117 (NORWOOD STREET) AND SR 1173 (SOUTHERLAND STREET) IN WALLACE. REVISE TRAFFIC SIGNAL. | 3 | Eastern Carolina RPO |  | REGION B |  | HSIP | CONSTRUCTION | 44000 | FY 2025: 44000
HS-2003N | HIGHWAY | NC 24 BUSINESS (ROUTELEDGE ROAD) | NC 24 BUSINESS (ROUTELEDGE ROAD) AND NC 24 / NC 903 (SOUTH KENANSVILLE BYPASS). REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 3 | Eastern Carolina RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 252000 | FY 2025: 252000
HS-2003O | HIGHWAY | US 74/76 | US 74/76 AT SR 1714 (ENTERPRISE DRIVE) AND US 74/76 AT SR 1494 (WOOD TREATMENT ROAD). INSTALL TRAFFIC SIGNALS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 533000 | FY 2026: 533000
HS-2003P | HIGHWAY | US 117 (SHIPYARD BOULEVARD) | US 117 (SHIPYARD BOULEVARD) AT CONVERSE ROAD / LONGSTREET DRIVE IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND ADD PEDESTRIAN ACCOMMODATIONS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 271000 | FY 2026: 271000
HS-2003Q | HIGHWAY | US 17 (DAWSON STREET) | US 17 (DAWSON STREET) AT US 421 (3RD STREET) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL, UPGRADE PAVEMENT MARKINGS, AND ADD PEDESTRIAN ACCOMMODATIONS. | 3 | Wilmington Urban Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 184000 | FY 2026: 184000
HS-2003R | HIGHWAY | US 421 | US 421 AT SR 1573 (DOW ROAD) IN CAROLINA BEACH. UPGRADE TRAFFIC SIGNAL. | 3 | Wilmington Urban Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 23000 | FY 2026: 23000
HS-2003S | HIGHWAY | US 17 BUSINESS (MARKET STREET) | US 17 BUSINESS (MARKET STREET) AND SR 1272 (NEW CENTRE DRIVE). INSTALL CROSSWALKS. | 3 | Wilmington Urban Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 114000 | FY 2026: 114000
HS-2003T | HIGHWAY | US 17 BUSINESS (MARKET STREET) | US 17 BUSINESS (MARKET STREET) AT SR 2219 (GREEN MEADOWS DRIVE) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 32000 | FY 2026: 32000
HS-2003U | HIGHWAY | SR 2048 (GORDON ROAD) | SR 2048 (GORDON ROAD) JUST WEST OF I-40. INSTALL SIX INCH PAVEMENT MARKINGS. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | HSIP | CONSTRUCTION | 37000 | FY 2023: 37000
HS-2003V | HIGHWAY | US 17/76 (OLEANDER DRIVE) | US 17/76 (OLEANDER DRIVE) AT SR 1209 (INDEPENDENCE BOULEVARD) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 23000 | FY 2026: 23000
HS-2003W | HIGHWAY | US 17 | US 17 AT SR 1136 (RED BUG ROAD) AND US 17 AT SR 1345 (ROYAL OAK ROAD). INSTALL A REDUCED CONFLICT INTERSECTION. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 1900000 | FY 2023: 1900000
HS-2003X | HIGHWAY | NC 24 | AT SR 1514 (PHILLIPS LOOP ROAD) IN SWANSBORO. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNALS AND ADVANCE FLASHERS. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 202000 | FY 2026: 202000
HS-2003Y | HIGHWAY | US 117 / NC 132 (COLLEGE ROAD) | AT SR 2313 (WILSHIRE BOULEVARD) IN WILMINGTON. INSTALL PEDESTRIAN COUNTDOWN HEADS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 63000 | FY 2026: 63000
HS-2003Z | HIGHWAY | US 17/76 (WOOSTER STREET) | AT SR 1217 (17TH STREET) IN WILMINGTON. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN COUNTDOWN HEADS. | 3 | Wilmington Urban Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 114000 | FY 2026: 114000
HS-2004B | HIGHWAY | NC 97 | INSTALL LEFT TURN LANE AT NC 97 AND SR 1603 (OLD CARRIAGE ROAD). | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 205000
HS-2004B | HIGHWAY | NC 97 | INSTALL LEFT TURN LANE AT NC 97 AND SR 1603 (OLD CARRIAGE ROAD). | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | RIGHT-OF-WAY | 86000
HS-2004C | HIGHWAY | SR 1537 (AIRPORT ROAD) | INSTALL ALL WAY STOP AT SR 1537 (AIRPORT ROAD) AND SR 1545 (MT. CARMEL CHURCH ROAD). | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | HSIP | CONSTRUCTION | 66000
HS-2004D | HIGHWAY | SR 1002 (PIKEVILLE-PRINCETON ROAD) | INSTALL ALL WAY STOP WITH ISLAND AT SR 1002 (PIKEVILLE-PRINCETON ROAD) AND SR 1320 (HINNANT ROAD). | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 4 |  | HSIP | CONSTRUCTION | 65000
HS-2004E | HIGHWAY | NC 111 | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT NC 111 AND SR 1754 (ZION CHURCH ROAD). | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 152000
HS-2004F | HIGHWAY | SR 1103 (WIGGINS MILL ROAD) | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT SR 1103 (WIGGINS MILL ROAD) AND SR 1169 (RADFORD ROAD). | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004G AND HS-2004H. | DIVISION 4 |  | HSIP | CONSTRUCTION | 30000
HS-2004G | HIGHWAY | NC 48 | INSTALL ALL WAY STOP AND REVISE EXISTING OVERHEAD AND SHOULDER-MOUNTED FLASHERS AT NC 48 AND NC 903. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004H. | REGION A |  | HSIP | CONSTRUCTION | 50000
HS-2004H | HIGHWAY | SR 1001 (OLD BAILEY HIGHWAY) | INSTALL ALL WAY STOP AT SR 1001 (OLD BAILEY HIGHWAY) AND SR 1717 (MACEDONIA ROAD / SANDY CROSS ROAD). | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004G. | DIVISION 4 |  | HSIP | CONSTRUCTION | 25000
HS-2004I | HIGHWAY | SR 1744 (INDIAN SPRINGS ROAD) | INSTALL ALL WAY STOP AT SR 1744 (INDIAN SPRINGS ROAD) AND SR 1941 (NORTHEAST CHURCH ROAD). | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | DIVISION 4 |  | HSIP | CONSTRUCTION | 65000
HS-2004J | HIGHWAY | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS. | 4 | Peanut Belt RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | DIVISION 4 |  | HSIP | CONSTRUCTION | 5246000 | FY 2023: 2249000
HS-2004L | HIGHWAY | NC 242 | CURVE IMPROVEMENTS BETWEEN 0.08 MILES AND 0.31 MILES NORTH OF SR 1116 (GODWIN LAKE ROAD). | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 555000 | FY 2023: 6000; FY 2024: 549000
HS-2004L | HIGHWAY | NC 242 | CURVE IMPROVEMENTS BETWEEN 0.08 MILES AND 0.31 MILES NORTH OF SR 1116 (GODWIN LAKE ROAD). | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | RIGHT-OF-WAY | 272000 | FY 2023: 272000
HS-2004M | HIGHWAY | NC 48 | INSTALL MINI ROUNDABOUTS ALONG NC 48 (GOLDROCK ROAD) AT WATERLOO DRIVE / ROUNDTREE DRIVE AND AT GREYSON ROAD / CUNNINGHAM DRIVE. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 1210000 | FY 2023: 12000; FY 2024: 1198000
HS-2004N | HIGHWAY | SR 1700 (OAK LEVEL ROAD) | SR 1700 (OAK LEVEL ROAD) AT SR 1603 (OLD CARRIAGE ROAD). REVISE TRAFFIC SIGNAL. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | HSIP | CONSTRUCTION | 29000 | FY 2023: 29000
HS-2004O | HIGHWAY | SR 1320 (AIRPORT BOULEVARD) | SR 1320 (AIRPORT BOULEVARD) AT CHELSEA DRIVE AND SR 1320 (AIRPORT BOULEVARD) AT JETSTREAM DRIVE IN WILSON. INSTALL TRAFFIC SIGNALS. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | DIVISION 4 |  | HSIP | CONSTRUCTION | 241000 | FY 2023: 241000
HS-2004P | HIGHWAY | US 301 (BRIGHTLEAF BOULEVARD) | US 301 (BRIGHTLEAF BOULEVARD) AT NORTH STREET IN SMITHFIELD. INSTALL / UPGRADE HIGH VISIBILITY CROSSWALKS, AUDIBLE COUNTDOWN PEDESTRIAN SIGNAL HEADS, PEDESTRIAN IMPROVEMENTS, TRAFFIC SIGNAL, AND TRAFFIC SIGNAL SYSTEM. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 70000 | FY 2023: 70000
HS-2004Q | HIGHWAY | US 64 | US 64 AT BRIDGES 630019 AND 630020 OVER TAR RIVER. PAVEMENT IMPROVEMENTS. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 521000 | FY 2023: 521000
HS-2004R | HIGHWAY | US 258 | US 258 BETWEEN THE PITT COUNTY LINE AND US 64 IN EDGECOMBE COUNTY AND BETWEEN PRINCEVILLE AND SR 1102 (MULLIN ROAD) IN HALIFAX COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS, SNOWPLOWABLE PAVEMENT MARKERS, AND RUMBLE STRIPES. | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 780000 | FY 2023: 780000
HS-2004S | HIGHWAY | SR 1902 (GLEN LAUREL ROAD) | SR 1902 (GLEN LAUREL ROAD) AT SR 1903 (VINSON ROAD). TRAFFIC SIGNAL INSTALLATION. | 4 | Capital Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | HSIP | CONSTRUCTION | 96000 | FY 2023: 96000
HS-2004T | HIGHWAY | US 158 | US 158 FROM EASTERN LITTLETON TOWN LIMITS AND 0.15 MILES WEST OF SR 1432 (EVERETTS SCHOOL ROAD). INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 230000 | FY 2023: 230000
HS-2004U | HIGHWAY | NC 58 | NC 58 FROM NORTHERN STATONSBURG TOWN LIMITS TO 0.3 MILES NORTH OF SR 1622 (EVANSDALE ROAD) IN WILSON COUNTY. NC 58 FROM SOUTH OF SR 1314 (THOMPSON CHAPEL CHURCH ROAD) IN WILSON COUNTY TO SOUTHERN NASHVILLE TOWN LIMIT IN NASH COUNTY. NC 58 FROM SOUTH OF SR 1004 (TAYLORS STORE ROAD) TO SOUTHERN CASTALIA TOWN LIMIT IN NASH COUNTY. INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 301000 | FY 2023: 301000
HS-2004V | HIGHWAY | NC 111 | NC 111 FROM WAYNE/DUPLIN COUNTY LINE TO SR 1727 (DOLLARD TOWN ROAD). NC 111 FROM US 70 BYPASS OVERPASS TO NC 222. NC 111/NC 222 FROM FREMONT LIMITS TO SR 1513 (RED HILL ROAD). NC 111/NC 222 FROM STANTONSBURG LIMITS TO SARATOGA LIMITS. NC 111 FROM NC 222 IN WILSON COUNTY TO SR 1344 (SARA LEE ROAD) IN EDGECOMBE COUNTY. NC 111 FROM PRINCEVILLE TO EDGECOMBE/MARTIN COUNTY LINE. INSTALL RUMBLE STRIPS WITH SIX-INCH PAVEMENT MARKINGS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 2161000 | FY 2023: 2161000
HS-2004W | HIGHWAY | US 70 | US 70 AT US 70A/SR 2532 (WEST EDWARDS STREET) AND US 70 AT SR 2314 (PONDFIELD ROAD). INSTALL REDUCED CONFLICT INTERSECTION WITH WESTBOUND U-TURN AT SR 2314 (PONDFIELD ROAD). | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 800000 | FY 2024: 800000
HS-2004X | HIGHWAY | NC 43 | NC 43 FROM 0.5 MILES NORTH OF SR 1425 (CASTALIA ROAD) IN NASH COUNTY TO NC 561 IN HALIFAX COUNTY. INSTALL RUMBLE STRIPS. | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 361000 | FY 2023: 361000
HS-2005 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | [5 empty] | 22000
HS-2005A | HIGHWAY | SR 1602 (MAIN STREET) | SR 1207 (SPRING STREET) INTERSECTION IN OXFORD. CONSTRUCT MINI-ROUNDABOUT. | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | DIVISION 5 |  | HSIP | CONSTRUCTION | 100000
HS-2005B | HIGHWAY | NC 903 | NC 903 CAUSEWAY ON EATONS FERRY BRIDGE OVER LAKE GASTON. UPGRADE GUARDRAIL. | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | REGION C |  | HSIP | CONSTRUCTION | 130000
HS-2005C | HIGHWAY | NC 54 | NC 55 IN DURHAM. INSTALL CONCRETE PEDESTRIAN REFUGE ISLANDS IN ALL QUADRANTS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | HSIP | CONSTRUCTION | 75000 | FY 2023: 75000
HS-2005D | HIGHWAY | SR 1303 (PICKETT ROAD) | SR 1116 (GARRETT ROAD)/(LUNA LANE) INTERSECTION IN DURHAM. INSTALL TRAFFIC SIGNAL. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2023: 2000
HS-2005D | HIGHWAY | SR 1303 (PICKETT ROAD) | SR 1116 (GARRETT ROAD)/(LUNA LANE) INTERSECTION IN DURHAM. INSTALL TRAFFIC SIGNAL. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 100000 | FY 2023: 100000
HS-2005E | HIGHWAY | US 15 / US 501 BUSINESS | NC 751 (ACADEMY ROAD) INTERCHANGE IN DURHAM. INSTALL GUARDRAIL. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | HSIP | CONSTRUCTION | 175000 | FY 2023: 175000
HS-2005F | HIGHWAY | VARIOUS | DOWNTOWN RALEIGH BUSINESS DISTRICT. TRAFFIC SIGNAL REVISIONS AT VARIOUS LOCATIONS. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | HSIP | CONSTRUCTION | 200000 | FY 2023: 200000
HS-2005G | HIGHWAY | SR 2215 (BUFFALOE ROAD) | SR 2214 (SOUTHHALL ROAD)/BRINTONS COTTAGE STREET AND VALLEY STREAM DRIVE INTERSECTIONS IN RALEIGH. TRAFFIC SIGNALS REVISIONS, CURB RAMPS, AND PAVEMENT MARKINGS. | 5 | Capital Area MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 147000 | FY 2023: 147000
HS-2005H | HIGHWAY | SR 1973 (PAGE ROAD) | CHURCHILL HALL/ARBY'S/MCDONALD DRIVEWAY. INSTALL DIRECTIONAL CROSSOVER. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 20000 | FY 2023: 20000
HS-2005I | HIGHWAY | SR 1645(LUMLEY ROAD) | I-540 WESTBOUND RAMP/ARCO CORPORATE DRIVE IN RALEIGH. WIDENING, TURN LANE CONSTRUCTION, TRAFFIC SIGNAL UPGRADE. | 5 | Capital Area MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 180000 | FY 2024: 180000
HS-2005J | HIGHWAY | SR 2516 (HODGE ROAD) | THE MINGO CREEK TRAIL CROSSING. RELOCATE CROSSWALK. | 5 | Capital Area MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 155000 | FY 2024: 101000; FY 2025: 54000
HS-2005J | HIGHWAY | SR 2516 (HODGE ROAD) | THE MINGO CREEK TRAIL CROSSING. RELOCATE CROSSWALK. | 5 | Capital Area MPO |  | DIVISION 5 |  | HSIP | UTILITIES | 20000 | FY 2024: 20000
HS-2005K | HIGHWAY | US 401 | SR 2108/SR 2036 (NEW HOPE ROAD) AND US 401 AT CALVARY DRIVE. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 5 | Capital Area MPO |  | REGION C |  | HSIP | CONSTRUCTION | 115000 | FY 2023: 75000; FY 2024: 40000
HS-2005L | HIGHWAY | SR 1327 (GREGSON STREET) | SR 1327 (GREGSON STREET) AT KNOX STREET. INSTALL TRAFFIC SIGNAL. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 110000 | FY 2023: 110000
HS-2005M | HIGHWAY | NC 55 (ALSTON AVENUE) | NC 98 AT SR 1670 (GEER STREET). REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNAL HEADS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | HSIP | CONSTRUCTION | 62000 | FY 2023: 62000
HS-2005N | HIGHWAY | NC 98 | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 500000 | FY 2024: 500000
HS-2005N | HIGHWAY | NC 98 | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | HSIP | CONSTRUCTION | 285000 | FY 2025: 197000; FY 2026: 88000
HS-2005N | HIGHWAY | NC 98 | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | L | CONSTRUCTION | 500000 | FY 2025: 345000; FY 2026: 155000
HS-2005N | HIGHWAY | NC 98 | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | T | CONSTRUCTION | 1000000 | FY 2025: 690000; FY 2026: 310000
HS-2005O | HIGHWAY | US 1 / US 158 | US 1 / US 158 AT SR 1237 (MASON DREWRY ROAD). INTERSECTION REALIGNMENT. | 5 | Kerr-Tar RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 335000 | FY 2024: 335000
HS-2005O | HIGHWAY | US 1 / US 158 | US 1 / US 158 AT SR 1237 (MASON DREWRY ROAD). INTERSECTION REALIGNMENT. | 5 | Kerr-Tar RPO |  | STATEWIDE MOBILITY |  | HSIP | UTILITIES | 80000 | FY 2024: 80000
HS-2005P | HIGHWAY | US 501 | US 501 AT NC 57 (HILLSBOROUGH ROAD). INSTALL TRAFFIC SIGNAL. | 5 | Kerr-Tar RPO |  | REGION C |  | HSIP | CONSTRUCTION | 260000 | FY 2024: 260000
HS-2005Q | HIGHWAY | SR 1142 (HUMIE OLIVE ROAD) | SR 1142 (HUMIE OLIVE ROAD) AT BLAZING TRAIL DRIVE/DRIVEWAY ACCESS TO APEX FRIENDSHIP HIGH AND ELEMENTARY SCHOOLS. INSTALL TRAFFIC AND PEDESTRIAN SIGNALS. | 5 | Capital Area MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 130000 | FY 2024: 130000
HS-2005R | HIGHWAY | SR 3120 (MORRISVILLE PARKWAY) | SR 3120 (MORRISVILLE PARKWAY) AT SR 3043 (FERSON ROAD) / GREEN HOPE SCHOOL ROAD. IMPROVE PEDESTRIAN CROSSING. | 5 | Capital Area MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 50000 | FY 2024: 50000
HS-2006A | HIGHWAY | SR 1415 (YADKIN ROAD) | SR 1415 (YADKIN ROAD) AT US 401 (SKIBO ROAD), AT SR 1437 (SANTE FE DRIVE), AND AT SOUTHWICK DRIVE. ADD SIGNALIZED PEDESTRIAN CROSSINGS TO ALL THREE INTERSECTIONS AND UPGRADE SIGNAL AT SOUTHWICK DRIVE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 455000 | FY 2023: 455000
HS-2006B | HIGHWAY | SR 1006 (PERSON STREET) | SR 1006 (PERSON STREET) FROM US 301 / I-95 BUSINESS (EASTERN BOULEVARD) TO JUST EAST OF WATER STREET. CONVERT SECTION FROM FOUR LANES TO THREE LANES WITH INTERSECTION IMPROVEMENTS AT BROAD STREET AND EASTERN BOULEVARD IN FAYETTEVILLE. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 651000 | FY 2023: 644000
HS-2006C | HIGHWAY | NC 53 (CEDAR CREEK ROAD) | NC 53 (CEDAR CREEK ROAD) FROM JUST NORTH OF PLYMOUTH STREET TO JUST SOUTH OF TROY DRIVE. INSTALL MEDIAN WITH SOUTHBOUND U-TURN AND BULB-OUT, SIDEWALK, AND RECTANGULAR RAPID FLASHING BEACON PEDESTRIAN CROSSING WITH REFUGE IN FAYETTEVILLE. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | HSIP | CONSTRUCTION | 1142000 | FY 2024: 1142000
HS-2006C | HIGHWAY | NC 53 (CEDAR CREEK ROAD) | NC 53 (CEDAR CREEK ROAD) FROM JUST NORTH OF PLYMOUTH STREET TO JUST SOUTH OF TROY DRIVE. INSTALL MEDIAN WITH SOUTHBOUND U-TURN AND BULB-OUT, SIDEWALK, AND RECTANGULAR RAPID FLASHING BEACON PEDESTRIAN CROSSING WITH REFUGE IN FAYETTEVILLE. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | HSIP | RIGHT-OF-WAY | 15000 | FY 2023: 15000
HS-2006D | HIGHWAY | SR 1935 (HOWELL ROAD) | CONVERT INTERSECTION OF SR 1924 (BARKER TEN MILE ROAD) AND SR 1935 (HOWELL ROAD) TO AN ALL WAY STOP. REALIGN NORTH LEG OF SR 1005 (TOLARSVILLE ROAD) AT SR 1935 (HOWELL ROAD) AND REMOVE SOUTH LEG. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 428000 | FY 2023: 4000; FY 2024: 424000
HS-2006D | HIGHWAY | SR 1935 (HOWELL ROAD) | CONVERT INTERSECTION OF SR 1924 (BARKER TEN MILE ROAD) AND SR 1935 (HOWELL ROAD) TO AN ALL WAY STOP. REALIGN NORTH LEG OF SR 1005 (TOLARSVILLE ROAD) AT SR 1935 (HOWELL ROAD) AND REMOVE SOUTH LEG. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | RIGHT-OF-WAY | 15000
HS-2006E | HIGHWAY | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS AT VARIOUS LOCATIONS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 4715000 | FY 2023: 3983000; FY 2024: 692000
HS-2006F | HIGHWAY | NC 211 | NC 211 FROM THE BRUNSWICK COUNTY LINE TO NC 214. INSTALL RUMBLE STRIPES. | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 574000 | FY 2023: 574000
HS-2006G | HIGHWAY | SR 1835 (ROCK HILL ROAD) | SR 1835 (ROCK HILL ROAD) AT SR 1838 (DUNN ROAD) IN EASTOVER. REALIGN SR 1838 (DUNN ROAD) TO FORM A T-INTERSECTION WITH SR 1835 (ROCK HILL ROAD) AND REMOVE SLIP LANES. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 336000 | FY 2023: 336000
HS-2006H | HIGHWAY | NC 27 | NC 24/27 FROM THE MOORE COUNTY LINE AND THE NC 24/27 SPLIT, NC 27 FROM NC 24 TO LILLINGTON, NC 27 FROM US 421 TO COATS, AND NC 27 FROM COATS TO THE JOHNSTON COUNTY LINE. INSTALL RUMBLE STRIPES, RUMBLE STRIPS, AND LONG-LIFE PAVEMENT MARKINGS. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 1065000 | FY 2023: 754000; FY 2024: 311000
HS-2006I | HIGHWAY | NC 710 | NC 710 AT SR 1340 (PROSPECT ROAD). CONSTRUCT ROUNDABOUT. | 6 | Lumber River RPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 80000 | FY 2024: 80000
HS-2006I | HIGHWAY | NC 710 | NC 710 AT SR 1340 (PROSPECT ROAD). CONSTRUCT ROUNDABOUT. | 6 | Lumber River RPO |  | REGION C |  | HSIP | CONSTRUCTION | 2262000 | FY 2025: 1768000; FY 2026: 494000
HS-2006J | HIGHWAY | US 501/NC 130 | US 501/NC 130 NEAR SR 1134 (KITCHEN ROAD). CURVE IMPROVEMENTS. | 6 | Lumber River RPO |  | REGION C |  | HSIP | CONSTRUCTION | 410000 | FY 2025: 410000
HS-2006K | HIGHWAY | SR 1441 (CHALYBEATE SPRINGS ROAD) | FROM NC 55 TO US 401. CURVE AND PAVEMENT MARKING IMPROVEMENTS. | 6 | Capital Area MPO |  | DIVISION 6 |  | HSIP | CONSTRUCTION | 822000 | FY 2025: 822000
HS-2006L | HIGHWAY | NC 87 | NC 87 AT SR 1004 (TAR HEEL ROAD) AND SR 1316 (TAR HEEL FERRY ROAD). REVISE TRAFFIC SIGNAL. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 80000 | FY 2023: 80000
HS-2006M | HIGHWAY | SR 1325 (GUM SPRINGS ROAD) | SR 1325 (GUM SPRINGS ROAD) NEAR SR 1327. CURVE IMPROVEMENTS. | 6 | Mid-Carolina RPO |  | DIVISION 6 |  | HSIP | CONSTRUCTION | 174000 | FY 2024: 174000
HS-2006N | HIGHWAY | SR 1596 (GLENSFORD DRIVE) | FROM US 401 (RAEFORD ROAD) AND SR 1400 (CLIFFDALE ROAD) IN FAYETTEVILLE. PAVEMENT MARKING AND SIGNING IMPROVEMENTS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | HSIP | CONSTRUCTION | 81000 | FY 2024: 81000
HS-2006O | HIGHWAY | SR 1596 (GLENSFORD DRIVE) | SR 1596 (GLENSFORD DRIVE) AT BEREAN BAPTIST ACADEMY AND AT CHAMBERSURG ROAD IN FAYETTEVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS WITH REFUGE ISLANDS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | HSIP | CONSTRUCTION | 250000 | FY 2024: 250000
HS-2006P | HIGHWAY | SR 3950 (RAMSEY STREET) | SR 3950 (RAMSEY STREET) AT RAILROAD BRIDGE 250216 IN FAYETTEVILLE. INSTALL GUARDRAIL. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | HSIP | CONSTRUCTION | 191000 | FY 2024: 191000
HS-2006Q | HIGHWAY | SR 1532 (LANGDON ROAD) | SR 1532 (LANGDON ROAD) AT BRIDGE 420015. UPGRADE GUARDRAIL. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 190000 | FY 2023: 2000; FY 2024: 188000
HS-2006Q | HIGHWAY | SR 1532 (LANGDON ROAD) | SR 1532 (LANGDON ROAD) AT BRIDGE 420015. UPGRADE GUARDRAIL. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | RIGHT-OF-WAY | 60000 | FY 2023: 60000
HS-2006R | HIGHWAY | I-95 | I-95 FROM MILEMARKER 2.0 TO MILEMARKER 12.45. INSTALL CABLE MEDIAN BARRIER. | 6 | Lumber River RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 815000 | FY 2024: 815000
HS-2006S | HIGHWAY | US 501 | FROM NC 130 TO THE SCOTLAND COUNTY LINE. INSTALL RUMBLE STRIPES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 222000 | FY 2023: 2000; FY 2024: 220000
HS-2006T | HIGHWAY | NC 72 | FROM US 74 TO NC 41 / NC 211. INSTALL RUMBLE STRIPES AND RAISED PAVEMENT MARKERS. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 427000 | FY 2023: 4000; FY 2024: 423000
HS-2006U | HIGHWAY | NC 72 | FROM NC 711 TO NC 710. INSTALL RUMBLE STRIPES AND RAISED PAVEMENT MARKERS. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 505000 | FY 2023: 5000; FY 2024: 500000
HS-2006V | HIGHWAY | SR 1600 (MCARTHUR ROAD) | SR 1600 (MCARTHUR ROAD) AT SR 1615 (ROSEHILL ROAD/STACY WEAVER ROAD) IN FAYETTEVILLE. CONSTRUCT SIGNALIZED PEDESTRIAN ACCOMMODATIONS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | HSIP | CONSTRUCTION | 190000 | FY 2024: 190000
HS-2006W | HIGHWAY | US 401 | BETWEEN FAYETTEVILLE AND HARNETT COUNTY (MILEPOST 20 - 27.7), BETWEEN CUMBERLAND COUNTY AND LILLINGTON (MILEPOST 0 - 9.5), AND BETWEEN LILLINGTON AND WAKE COUNTY (MILEPOST 12.5 - 22.1). INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS. | 6 | Mid-Carolina RPO, Capital Area MPO, Fayetteville Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 975000 | FY 2023: 975000
HS-2006X | HIGHWAY | US 401 (SKIBO ROAD) | AT SR 1007 (ALL AMERICAN FREEWAY) NORTHBOUND AND SOUTHBOUND RAMPS IN FAYETTEVILLE. INSTALL SIGNALIZED PEDESTRIAN ACCOMMODATIONS. | 6 | Fayetteville Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 880000 | FY 2024: 880000
HS-2006Y | HIGHWAY | SR 1115 (BUFFALO LAKE ROAD) | FROM NC 27 TO NC 87. INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 235000 | FY 2023: 235000
HS-2007A | HIGHWAY | I-85 BUSINESS/US29/70 | I-85 BUSINESS/US 29/70 SOUTHBOUND AND NORTHBOUND FROM RANDOLPH COUNTY LINE TO NORTH OF SR 1145 (RIVERDALE DRIVE) IN HIGH POINT. INSTALL GUARDRAIL. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | REGION D |  | HSIP | CONSTRUCTION | 540000
HS-2007B | HIGHWAY | I-85 BUSINESS/US29/70 | I-85 BUSINESS/US 29/70 NORTHBOUND FROM NORTH OF SR 1145 (RIVERDALE DRIVE) TO I-85 IN HIGH POINT. INSTALL GUARDRAIL. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | REGION D |  | HSIP | CONSTRUCTION | 270000
HS-2007C | HIGHWAY | VARIOUS | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. | 7 | Burlington-Graham MPO, Greensboro Urban Area MPO, Piedmont Triad RPO, Triangle Area RPO | UNDER CONSTRUCTION | DIVISION 7 |  | HSIP | CONSTRUCTION | 1717000 | FY 2023: 128000
HS-2007D | HIGHWAY | I-74 AND US 29/70 | I-74 AND US 29/70 (I-85 BUSINESS INTERCHANGE). UPGRADE SIGNALS, PAVEMENT MARKINGS, AND SIGNING. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 400000 | FY 2023: 400000
HS-2007E | HIGHWAY | NC 62 | NC 62 FROM WEST OF SR 1138 (TOM BALL ROAD) TO WEST OF THE ALAMANCE COUNTY LINE. INSTALL PAVEMENT MARKINGS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  | HSIP | CONSTRUCTION | 802000 | FY 2023: 730000; FY 2024: 72000
HS-2007F | HIGHWAY | NC 87 | NC 87 AT I-40 EASTBOUND ON-RAMP. INSTALL PEDESTRIAN ACCOMMODATIONS. | 7 | Burlington-Graham MPO |  | REGION D |  | HSIP | CONSTRUCTION | 87000 | FY 2023: 87000
HS-2008A | HIGHWAY | US 74 | RICHMOND COUNTY LINE TO SR 1363. UPGRADE GUARDRAIL. | 8 | Lumber River RPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 360000
HS-2008B | HIGHWAY | VARIOUS | VARIOUS NHS AND PRIMARY ROUTES IN DIVISION 8, DISTRICT 2. UPGRADE GUARDRAIL. | 8 | Triangle Area RPO, Lumber River RPO | UNDER CONSTRUCTION | REGION E |  | HSIP | CONSTRUCTION | 250000
HS-2008C | HIGHWAY | VARIOUS | VARIOUS SECONDARY ROUTES IN CHATHAM, LEE, HOKE, RANDOLPH AND SCOTLAND COUNTIES. INSTALL LONG LIFE PAVEMENT MARKINGS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Fayetteville Area MPO, Durham-Chapel Hill-Carrboro MPO |  | REGION E |  | HSIP | CONSTRUCTION | 1580000 | FY 2023: 491000
HS-2008D | HIGHWAY | US 421 | CHATHAM COUNTY LINE TO THE GUILFORD COUNTY LINE. INSTALL 1 MILE AND .5 MILE MARKERS AND REVISE EXIT NUMBER SIGNS. | 8 | Piedmont Triad RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 50000 | FY 2023: 50000
HS-2008E | HIGHWAY | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 8 | Lumber River RPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 413000 | FY 2023: 413000
HS-2008E | HIGHWAY | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 8 | Lumber River RPO |  | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 67000 | FY 2023: 67000
HS-2008E | HIGHWAY | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 8 | Lumber River RPO |  | STATEWIDE MOBILITY |  | HSIP | UTILITIES | 17000 | FY 2023: 17000
HS-2008E | HIGHWAY | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 8 | Lumber River RPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 33000 | FY 2023: 33000
HS-2008E | HIGHWAY | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 8 | Lumber River RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 207000 | FY 2023: 207000
HS-2008E | HIGHWAY | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 8 | Lumber River RPO |  | STATEWIDE MOBILITY |  | T | UTILITIES | 33000 | FY 2023: 33000
HS-2008F | HIGHWAY | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 8 | Triangle Area RPO |  | REGION E |  | T | UTILITIES | 167000 | FY 2023: 167000
HS-2008F | HIGHWAY | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 8 | Triangle Area RPO |  | REGION E |  | HSIP | CONSTRUCTION | 300000 | FY 2024: 300000
HS-2008F | HIGHWAY | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 8 | Triangle Area RPO |  | REGION E |  | HSIP | RIGHT-OF-WAY | 167000 | FY 2023: 167000
HS-2008F | HIGHWAY | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 8 | Triangle Area RPO |  | REGION E |  | HSIP | UTILITIES | 83000 | FY 2023: 83000
HS-2008F | HIGHWAY | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 600000 | FY 2024: 600000
HS-2008F | HIGHWAY | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 8 | Triangle Area RPO |  | REGION E |  | T | RIGHT-OF-WAY | 333000 | FY 2023: 333000
HS-2009A | HIGHWAY | VARIOUS | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Urban Area MPO |  | DIVISION 9 |  | HSIP | CONSTRUCTION | 1900000
HS-2009B | HIGHWAY | US 64 | US 64 FROM SR 2782 (BOWERS ROAD TO EAST OF SR 2012 / SR 2227 (HEATH CHURCH ROAD / NEW BOWERS ROAD). CONSTRUCT 4 REDUCED CONFLICT INTERSECTIONS AND LEFT-OVER WITH U-TURN BULB EAST OF SR 2012 / SR 2227. | 9 | High Point Urban Area MPO | IN PROGRESS | REGION D |  | HSIP | UTILITIES | 20000 | FY 2023: 20000
HS-2009B | HIGHWAY | US 64 | US 64 FROM SR 2782 (BOWERS ROAD TO EAST OF SR 2012 / SR 2227 (HEATH CHURCH ROAD / NEW BOWERS ROAD). CONSTRUCT 4 REDUCED CONFLICT INTERSECTIONS AND LEFT-OVER WITH U-TURN BULB EAST OF SR 2012 / SR 2227. | 9 | High Point Urban Area MPO | IN PROGRESS | REGION D |  | HSIP | CONSTRUCTION | 1500000 | FY 2023: 15000; FY 2024: 1485000
HS-2009C | HIGHWAY | US 29 / US 70 | US 29 / US 70, VICINITY OF FLEET DARR ROAD WEST OF SR 2123 (LEXINGTON AVENUE) CONNECTOR. INSTALL DIRECTIONAL LEFTOVERS. | 9 | High Point Urban Area MPO |  | REGION D |  | HSIP | CONSTRUCTION | 500000 | FY 2026: 500000
HS-2009D | HIGHWAY | SR 1007 (JAKE ALEXANDER BOULEVARD) | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  | HSIP | RIGHT-OF-WAY | 50000
HS-2009D | HIGHWAY | SR 1007 (JAKE ALEXANDER BOULEVARD) | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  | HSIP | UTILITIES | 20000
HS-2009D | HIGHWAY | SR 1007 (JAKE ALEXANDER BOULEVARD) | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  | HSIP | CONSTRUCTION | 350000 | FY 2023: 274000; FY 2024: 76000
HS-2009E | HIGHWAY | SR 1002 (OLD CONCORD ROAD) | SR 1002 (OLD CONCORD ROAD) FROM JAKE ALEXANDER BOULEVARD IN SALISBURY TO THE CABARRUS COUNTY LINE. INSTALL PAVEMENT MARKINGS. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | HSIP | CONSTRUCTION | 396000 | FY 2023: 396000
HS-2009F | HIGHWAY | NC 109 | NC 109. FORSYTH COUNTY FROM MILE POST 0.256 TO DAVIDSON COUNTY MILE POST 38.367. INSTALL CENTERLINE AND EDGELINE SINUSOIDAL RUMBLESTRIPES. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | REGION D |  | HSIP | CONSTRUCTION | 600000 | FY 2023: 600000
HS-2009G | HIGHWAY | NC (REYNOLDS ROAD) | NC 67 (REYNOLDA ROAD) AT BETHABARA PARK BOULEVARD. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND OTHER PEDESTRIAN ACCOMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | HSIP | UTILITIES | 60000 | FY 2023: 60000
HS-2009G | HIGHWAY | NC (REYNOLDS ROAD) | NC 67 (REYNOLDA ROAD) AT BETHABARA PARK BOULEVARD. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND OTHER PEDESTRIAN ACCOMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | HSIP | CONSTRUCTION | 331000 | FY 2024: 331000
HS-2009G | HIGHWAY | NC (REYNOLDS ROAD) | NC 67 (REYNOLDA ROAD) AT BETHABARA PARK BOULEVARD. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND OTHER PEDESTRIAN ACCOMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | HSIP | RIGHT-OF-WAY | 25000 | FY 2023: 25000
HS-2010A | HIGHWAY | NC 24, NC 27 | SR 3110 (ARLINGTON CHURCH ROAD) NEAR CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | REGION E |  | HSIP | RIGHT-OF-WAY | 175000
HS-2010A | HIGHWAY | NC 24, NC 27 | SR 3110 (ARLINGTON CHURCH ROAD) NEAR CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | REGION E |  | HSIP | CONSTRUCTION | 1350000 | FY 2023: 1350000
HS-2010B | HIGHWAY | I-277 | INSTALL SMART CUSHIONS AT VARIOUS EXITS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 144000
HS-2010C | HIGHWAY | NC 218 | US 74 IN ANSON COUNTY TO US 601 IN UNION COUNTY, AND FROM MILL GROVE ROAD IN UNION COUNTY TO I-485 IN MECKLENBURG COUNTY. INSTALL MILLED RUMBLE STRIPS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | REGION E |  | HSIP | CONSTRUCTION | 616000 | FY 2023: 121000
HS-2010D | HIGHWAY | NC 24/27 | SR 1120 (BETHEL SCHOOL ROAD) INTERSECTION. INSTALL A REDUCED CONFLICT INTERSECTION (RCI) WITH UNSIGNALIZED BULBOUTS. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | HSIP | CONSTRUCTION | 392000 | FY 2024: 4000; FY 2025: 388000
HS-2010D | HIGHWAY | NC 24/27 | SR 1120 (BETHEL SCHOOL ROAD) INTERSECTION. INSTALL A REDUCED CONFLICT INTERSECTION (RCI) WITH UNSIGNALIZED BULBOUTS. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | HSIP | RIGHT-OF-WAY | 301000 | FY 2023: 301000
HS-2010E | HIGHWAY | NC 49 (SOUTH TRYON STREET) | NC 49 (SOUTH TRYON STREET) AT GENERAL DRIVE; AND, NC 49 (SOUTH TRYON STREET) AT SR 1347 (NEVADA BOULEVARD). INSTALL TRAFFIC SIGNAL AT NC 49 AND GENERAL DRIVE, AND CONVERT NC 49 AT SR 1347 (NEVADA BOULEVARD) TO A DIRECTIONAL CROSSOVER. | 10 | Charlotte Regional TPO |  | REGION E |  | HSIP | UTILITIES | 25000 | FY 2025: 25000
HS-2010E | HIGHWAY | NC 49 (SOUTH TRYON STREET) | NC 49 (SOUTH TRYON STREET) AT GENERAL DRIVE; AND, NC 49 (SOUTH TRYON STREET) AT SR 1347 (NEVADA BOULEVARD). INSTALL TRAFFIC SIGNAL AT NC 49 AND GENERAL DRIVE, AND CONVERT NC 49 AT SR 1347 (NEVADA BOULEVARD) TO A DIRECTIONAL CROSSOVER. | 10 | Charlotte Regional TPO |  | REGION E |  | HSIP | CONSTRUCTION | 534000 | FY 2025: 534000
HS-2010F | HIGHWAY | NC 24/27 | NC 24/27 AND SR 1100 (PINE BLUFF ROAD/ REED MINE ROAD) NEAR LOCUST. INSTALL A REDUCED CONFLICT INTERSECTION. | 10 | Cabarrus-Rowan MPO |  | REGION E |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2023: 5000
HS-2010F | HIGHWAY | NC 24/27 | NC 24/27 AND SR 1100 (PINE BLUFF ROAD/ REED MINE ROAD) NEAR LOCUST. INSTALL A REDUCED CONFLICT INTERSECTION. | 10 | Cabarrus-Rowan MPO |  | REGION E |  | HSIP | CONSTRUCTION | 747000 | FY 2025: 747000
HS-2010G | HIGHWAY | NC 51 | NC 51 AND POLK STREET. INSTALL PEDESTRIAN SIGNALS AND ACCOMMODATIONS. | 10 | Charlotte Regional TPO |  | REGION E |  | HSIP | CONSTRUCTION | 144000 | FY 2024: 144000
HS-2010H | HIGHWAY | NC 49 | SR 1155 (ZION CHURCH ROAD) INTERSECTION NEAR CONCORD. INSTALL REDUCED CONFLICT INTERSECTION WITH SIGNALIZED BULBOUTS. | 10 | Cabarrus-Rowan MPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 105000 | FY 2024: 105000
HS-2010H | HIGHWAY | NC 49 | SR 1155 (ZION CHURCH ROAD) INTERSECTION NEAR CONCORD. INSTALL REDUCED CONFLICT INTERSECTION WITH SIGNALIZED BULBOUTS. | 10 | Cabarrus-Rowan MPO |  | STATEWIDE MOBILITY |  | HSIP | UTILITIES | 70000 | FY 2024: 70000
HS-2010H | HIGHWAY | NC 49 | SR 1155 (ZION CHURCH ROAD) INTERSECTION NEAR CONCORD. INSTALL REDUCED CONFLICT INTERSECTION WITH SIGNALIZED BULBOUTS. | 10 | Cabarrus-Rowan MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 1949000 | FY 2025: 783000; FY 2026: 1166000
HS-2010I | HIGHWAY | NC 16 (PROVIDENCE ROAD) | SR 1307 (BONDS GROVE CHURCH ROAD) INTERSECTION NEAR MARVIN. WIDEN ROAD, ADD TURN LANE, AND INSTALL TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO |  | REGION E |  | HSIP | RIGHT-OF-WAY | 120000 | FY 2024: 120000
HS-2010I | HIGHWAY | NC 16 (PROVIDENCE ROAD) | SR 1307 (BONDS GROVE CHURCH ROAD) INTERSECTION NEAR MARVIN. WIDEN ROAD, ADD TURN LANE, AND INSTALL TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO |  | REGION E |  | HSIP | UTILITIES | 120000 | FY 2024: 120000
HS-2010I | HIGHWAY | NC 16 (PROVIDENCE ROAD) | SR 1307 (BONDS GROVE CHURCH ROAD) INTERSECTION NEAR MARVIN. WIDEN ROAD, ADD TURN LANE, AND INSTALL TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO |  | REGION E |  | HSIP | CONSTRUCTION | 859000 | FY 2025: 495000; FY 2026: 364000
HS-2010J | HIGHWAY | NC 73 (SAM FURR ROAD) | SR 5544 (CATAWBA AVENUE) INTERSECTION. INSTALL PEDESTRIAN ACCOMMODATIONS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | REGION E |  | HSIP | CONSTRUCTION | 108000 | FY 2023: 108000
HS-2010K | HIGHWAY | NC 24/NC 27 | LEONARD AVENUE. INSTALL AUDIBLE PEDESTRIAN SIGNALS. | 10 | Rocky River RPO |  | REGION E |  | HSIP | CONSTRUCTION | 15000 | FY 2023: 15000
HS-2010L | HIGHWAY | SR 5901 (BILLY GRAHAM PARKWAY) | NC 49 (TRYON ROAD) TO I-85. INSTALL GUARDRAIL. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 960000 | FY 2023: 960000
HS-2011A | HIGHWAY | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 11 |  | HSIP | CONSTRUCTION | 1816000
HS-2011B | HIGHWAY | US 221 / US 321 | DEERFIELD ROAD TO BOONE MALL. INSTALL PEDESTRIAN COUNTDOWN HEADS AND FLASHING YELLOW ARROWS AT VARIOUS INTERSECTIONS. | 11 | High Country RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 116000
HS-2011C | HIGHWAY | SR 1511 (ROSEBORO ROAD) | INSTALL SHOULDER GUARDRAIL. | 11 | High Country RPO | UNDER CONSTRUCTION. | DIVISION 11 |  | HSIP | CONSTRUCTION | 7000
HS-2011D | HIGHWAY | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 11 |  | HSIP | CONSTRUCTION | 855000
HS-2011E | HIGHWAY | NC 16 | US 221 TO THE VIRGINIA STATE LINE. INSTALL NEW AND UPGRADE EXISTING GUARDRAIL. | 11 | High Country RPO | UNDER CONSTRUCTION. | REGION F |  | HSIP | CONSTRUCTION | 1425000 | FY 2023: 1425000
HS-2012A | HIGHWAY | SR 1849 (MOUNT PLEASANT ROAD) | INSTALL GUARDRAIL ON BRIDGE 163 ON SR 1849 OVER MOUNTAIN CREEK PORTION OF LAKE NORMAN | 12 | Greater Hickory MPO | COMPLETE | DIVISION 12 |  | HSIP | CONSTRUCTION | 85000
HS-2012B | HIGHWAY | SR 1844 (SLANTING BRIDGE ROAD) | UPGRADE GUARDRAIL AND END UNITS AT BRIDGE 23 | 12 | Greater Hickory MPO | COMPLETE | DIVISION 12 |  | HSIP | CONSTRUCTION | 372000
HS-2012C | HIGHWAY | SR 1125 (SHEARERS ROAD) | SR 1147 (ROCKY RIVER ROAD) INTERSECTION. INSTALL TRAFFIC SIGNAL. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 12 |  | HSIP | ENGINEERING | 20000
HS-2012C | HIGHWAY | SR 1125 (SHEARERS ROAD) | SR 1147 (ROCKY RIVER ROAD) INTERSECTION. INSTALL TRAFFIC SIGNAL. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 12 |  | HSIP | CONSTRUCTION | 190000 | FY 2023: 188000
HS-2012D | HIGHWAY | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ON APPROXIMATELY 65 SECONDARY ROADS. | 12 | Cabarrus-Rowan MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 12 |  | HSIP | CONSTRUCTION | 3615000 | FY 2023: 2263000; FY 2024: 1352000
HS-2012E | HIGHWAY | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ON APPROXIMATELY 59 SECONDARY ROADS. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | HSIP | CONSTRUCTION | 2675000 | FY 2023: 1912000; FY 2024: 763000
HS-2012F | HIGHWAY | SR 1360 (BETH HAVEN CHURCH ROAD) | SR 1373 (WINGATE HILL ROAD/ FORNEY HILL ROAD). INSTALL ALL WAY STOP, UPGRADE SIGNS AND PAVEMENT MARKINGS, AND IMPROVE SHOULDERS. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | HSIP | CONSTRUCTION | 25000 | FY 2023: 25000
HS-2013A | HIGHWAY | US 321 | BRIDGES #366 AND #367 AT THE CATAWBA COUNTY LINE. INSTALL GUARDRAIL. | 13 | Greater Hickory MPO | COMPLETE | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 92000
HS-2013B | HIGHWAY | NC 226 | US 19E TO SR 1250 (SNOW CREEK ROAD). UPGRADE GUARDRAIL. | 13 | High Country RPO | COMPLETE | REGION G |  | HSIP | CONSTRUCTION | 290000
HS-2013C | HIGHWAY | NC 181 | US 64 TO SR 1405 (BROWN MOUNTAIN BEACH ROAD). UPGRADE GUARDRAIL. | 13 | Greater Hickory MPO | COMPLETE | REGION G |  | HSIP | CONSTRUCTION | 195000
HS-2013D | HIGHWAY | NC 226 | SR 1250 (SNOW CREEK ROAD) TO NC 261. UPGRADE GUARDRAIL. | 13 | High Country RPO | COMPLETE | REGION G |  | HSIP | CONSTRUCTION | 272000
HS-2013E | HIGHWAY | US 64/NC 18 | NC 181 TO CALDWELL COUNTY LINE. UPGRADE GUARDRAIL. | 13 | Greater Hickory MPO | COMPLETE | REGION G |  | HSIP | CONSTRUCTION | 385000
HS-2013F | HIGHWAY | US 321, US 70, US 19E, US 221A | UPGRADE GUARDRAIL. | 13 | Greater Hickory MPO, Foothills RPO, High Country RPO | COMPLETE | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 348000
HS-2013G | HIGHWAY | SR 1510 (HUDLOW ROAD) | US 221A TO NC 64. UPGRADE GUARDRAIL. | 13 | Foothills RPO | UNDER CONSTRUCTION. | DIVISION 13 |  | HSIP | CONSTRUCTION | 497000 | FY 2023: 497000
HS-2013H | HIGHWAY | US 221 | NC 226/ US 221 BUS TO US 70. IMPROVE PAVEMENT. | 13 | Foothills RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 530000 | FY 2023: 530000
HS-2013I | HIGHWAY | SR 1318 (BIG LAUREL ROAD) | SR 1340 TO SR 1636 NEAR MARS HILL. INSTALL GUARDRAIL. | 13 | Land-of-Sky RPO |  | DIVISION 13 |  | HSIP | CONSTRUCTION | 525000 | FY 2024: 525000
HS-2013J | HIGHWAY | US 19W | SR 1454 TO SR 1382 NEAR BURNSVILLE. INSTALL GUARDRAIL. | 13 | High Country RPO |  | REGION G |  | HSIP | CONSTRUCTION | 1230000 | FY 2024: 1230000
HS-2013K | HIGHWAY | SR 1003 (REEMS CREEK ROAD) | SR 2106 TO SR 2114 NEAR WEAVERVILLE. INSTALL GUARDRAIL. | 13 | French Broad River MPO |  | DIVISION 13 |  | HSIP | CONSTRUCTION | 440000 | FY 2024: 440000
HS-2013L | HIGHWAY | NC 226 | US 19 TO SR 1164/ SR 1250 (SNOW CREEK ROAD) NEAR SPRUCE PINE. INSTALL GUARDRAIL. | 13 | High Country RPO |  | REGION G |  | HSIP | CONSTRUCTION | 925000 | FY 2023: 925000
HS-2013M | HIGHWAY | SR 1135 (OLD FORT/ SUGARHILL ROAD) | SR 1103 TO SR 1001 NEAR OLD FORT. INSTALL GUARDRAIL. | 13 | Foothills RPO |  | DIVISION 13 |  | HSIP | CONSTRUCTION | 717000 | FY 2023: 717000
HS-2013N | HIGHWAY | SR 1006 (BOSTIC-SUNSHINE HIGHWAY) | SR 1007 TO NC 226 NEAR BOSTIC. INSTALL GUARDRAIL. | 13 | Foothills RPO |  | DIVISION 13 |  | HSIP | CONSTRUCTION | 951000 | FY 2024: 951000
HS-2014A | HIGHWAY | US 64/NC 28 | INSTALL CENTERLINE RUMBLESTRIPS, LONG LIFE PAVEMENT MARKINGS, AND INTERMITTMENT PAVED SHOULDERS FROM SR 1560 TO SR 1533, NEAR FRANKLIN. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 1200000
HS-2014B | HIGHWAY | SR 1157 (CULLOWHEE MOUNTAIN ROAD) | INSTALL GUARDRAIL FROM MILEPOST 2.6 TO 6.6, NEAR CULLOWHEE. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | HSIP | CONSTRUCTION | 110000 | FY 2023: 30000
HS-2014C | HIGHWAY | VARIOUS | INSTALL SNOWPLOWABLE MARKERS AND PAVEMENT MARKINGS FOR WRONG WAY RAMP ARROWS ON VARIOUS FREEWAY RAMPS. | 14 | Southwestern RPO, Foothills RPO, French Broad River MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 50000 | FY 2023: 15000; FY 2024: 35000
HS-2014D | HIGHWAY | SR 1325 (CENTENNIAL DRIVE) | INSTALL RECTANGULAR RAPID FLASHING BEACONS (RRFB) AT THREE MIDBLOCK CROSSINGS NEAR SR 1169 (CENTRAL DRIVE). | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | HSIP | CONSTRUCTION | 59000 | FY 2023: 58000
HS-2014E | HIGHWAY | US 74 | IMPROVE PAVEMENT FROM SR 1392 TO EAST OF SR 1388 AND FROM JACKSON COUNTY LINE TO BRIDGES 107 AND 110. | 14 | French Broad River MPO, Southwestern RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 975000 | FY 2023: 882000; FY 2024: 93000
HS-2014F | HIGHWAY | SR 1100 (OLD HIGHWAY 64 WEST) | SR 1135 (SETTAWIG ROAD) NEAR BRASSTOWN. WIDEN AND INSTALL GUARDRAIL. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 16000 | FY 2023: 16000
HS-2014F | HIGHWAY | SR 1100 (OLD HIGHWAY 64 WEST) | SR 1135 (SETTAWIG ROAD) NEAR BRASSTOWN. WIDEN AND INSTALL GUARDRAIL. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | HSIP | CONSTRUCTION | 320000 | FY 2023: 129000; FY 2024: 191000
HS-2014G | HIGHWAY | NC 143 | LONG HUNGRY ROAD INTERSECTION. IMPROVE ALIGNMENT AND SUPERELEVATION. | 14 | Southwestern RPO |  | REGION G |  | HSIP | CONSTRUCTION | 515000 | FY 2024: 515000
HS-2014G | HIGHWAY | NC 143 | LONG HUNGRY ROAD INTERSECTION. IMPROVE ALIGNMENT AND SUPERELEVATION. | 14 | Southwestern RPO |  | REGION G |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2024: 2000
HS-2014H | HIGHWAY | VARIOUS | US 23 BUSINESS (HAYWOOD ROAD) AT CHURCH STREET AND SR 1557 (FRONT STREET) AT SR 1558 (DEPOT STREET). INSTALL RECTANGULAR RAPID FLASHING BEACON (RRFB) AND UPGRADE CURB RAMPS. | 14 | Southwestern RPO |  | REGION G |  | HSIP | CONSTRUCTION | 96000 | FY 2023: 96000
HS-2014I | HIGHWAY | US 25 BUSINESS (ASHEVILLE HIGHWAY) | HENDERSONVILLE CITY LIMIT TO SR 1534. INSTALL RUMBLE STRIPS WITH LONG LIFE PAVEMENT MARKINGS. | 14 | French Broad River MPO |  | REGION G |  | HSIP | CONSTRUCTION | 140000 | FY 2023: 140000
HS-2014J | HIGHWAY | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS SECONDARY ROUTES. | 14 | French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | HSIP | CONSTRUCTION | 2570000 | FY 2023: 2570000
HS-2014K | HIGHWAY | US 19 | HOLSTON VILLAGE ROAD AND SR 1197 (GOLF COURSE ROAD). UPGRADE INTERSECTIONS. | 14 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 110000 | FY 2023: 110000
HS-2014L | HIGHWAY | US 64 | SR 1574 (FRUITLAND ROAD), SR 1006 (HOWARD GAP ROAD), SR 1519 (THOMPSON STREET)/ SR 1751 (FREEMAN STREET), SR 1749 (ORR'S CAMP ROAD)/ SR 1634 (CAROLINA AVENUE). UPGRADE INTERSECTIONS. | 14 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 570000 | FY 2023: 570000
HS-2014M | HIGHWAY | US 64 (ASHEVILLE HIGHWAY) | SR 1592 (HOSPITAL DRIVE)/ STRAUS PARKWAY. UPGRADE INTERSECTION. | 14 | Land-of-Sky RPO, French Broad River MPO |  | REGION G |  | HSIP | CONSTRUCTION | 225000 | FY 2023: 225000
HS-2014N | HIGHWAY | US 64 (7TH AVENUE) | NORTH GROVE STREET/ 7TH AVENUE. UPGRADE INTERSECTION. | 14 | French Broad River MPO |  | REGION G |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
HS-2014O | HIGHWAY | US 64 | SR 1586 (SOUTH MILLS GAP ROAD)/ TUTTLE ROAD. INSTALL TRAFFIC SIGNAL. | 14 | French Broad River MPO |  | REGION G |  | HSIP | CONSTRUCTION | 55000 | FY 2023: 55000
HS-2014P | HIGHWAY | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS PRIMARY AND SECONDARY ROUTES. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 2955000 | FY 2024: 2955000
HS-2014Q | HIGHWAY | US 64, US 25 BUSINESS | UPGRADE SIGNAL SYSTEM AT 33 INTERSECTIONS ALONG US 64 AND US 25 BUSINESS. | 14 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 225000 | FY 2023: 225000
HS-2014R | HIGHWAY | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS PRIMARY AND SECONDARY ROUTES. | 14 | Foothills RPO, French Broad River MPO, Land-of-Sky RPO, Southwestern RPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 1225000 | FY 2023: 1225000
HS-9999DIV | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | CONSTRUCTION | 224403000 |  | 8367000 | 13338000 | 15801000 | 20761000 | 20711000 | 20576000 | 20734000 | 20823000 | 20823000 | 20823000 | 41646000
HS-9999REG | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | CONSTRUCTION | 224453000 |  | 8367000 | 13388000 | 15801000 | 20761000 | 20711000 | 20576000 | 20734000 | 20823000 | 20823000 | 20823000 | 41646000
HS-9999SW | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 299269000 |  | 11156000 | 17850000 | 21068000 | 27682000 | 27614000 | 27434000 | 27645000 | 27764000 | 27764000 | 27764000 | 55528000
HV-0001 | HIGHWAY | VARIOUS | CONSTRUCTION OF ELECTRIC VEHICLE SUPPLY EQUIPMENT ALONG NORTH CAROLINA'S ALTERNATIVE CORRIDORS AND NEVI PLANNING. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | NEVI | ENGINEERING | 500000 | FY 2023: 500000
HV-0001 | HIGHWAY | VARIOUS | CONSTRUCTION OF ELECTRIC VEHICLE SUPPLY EQUIPMENT ALONG NORTH CAROLINA'S ALTERNATIVE CORRIDORS AND NEVI PLANNING. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | NEVI | ENGINEERING | 721000 | FY 2023: 721000
HV-9999 | HIGHWAY | VARIOUS | NATIONAL ELECTRIC VEHICLE INFRASTRUCTURE PROGRAM (NEVI) - UNPROGRAMMED BALANCE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | NEVI | CONSTRUCTION | 271079000 | 38859000 | 23222000 | 23222000 | 23222000 | 23222000 | 23222000 | 23222000 | 23222000 | 23222000 | 23222000 | 23222000
I-0305 | HIGHWAY | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | 5, 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5967, I-5984 AND U-5845 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 4343000
I-0305 | HIGHWAY | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | 5, 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5967, I-5984 AND U-5845 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 17900000
I-0305 | HIGHWAY | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | 5, 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5967, I-5984 AND U-5845 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1200000
I-0305 | HIGHWAY | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | 5, 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5967, I-5984 AND U-5845 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 120898000
I-0911 | HIGHWAY | I-40 | WEST OF NC 801 IN BERMUDA RUN TO WEST OF SR 1122 (JONESTOWN ROAD) IN WINSTON-SALEM. ADD LANES. | 9 | Winston-Salem Urban Area MPO | PARTS B AND C COMPLETE |  |  |  |  | 77937000
I-0911A | HIGHWAY | I-40 | WEST OF NC 801 IN DAVIE COUNTY TO SR 1101 (HARPER ROAD) IN FORSYTH COUNTY. | 9 | Winston-Salem Urban Area MPO | COMPLETE; DESIGN-BUILD PROJECT; BUILD NC BONDS: $27.889 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION D |  | T | BUILD NC CON | 35894000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 4785000
I-0914 | HIGHWAY | I-85 | US 158 (MILE POST 213.5) IN VANCE COUNTY TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION AND SIGN UPGRADES. | 5 | Kerr-Tar RPO |  | PRE-STI (TRANSITION) |  |  |  | 164443000
I-2304 | HIGHWAY | I-85 | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO US 29 / US 52 / US 70 / BUSINESS 85 IN DAVIDSON COUNTY. ADDITIONAL LANES AND YADKIN RIVER BRIDGE RECONSTRUCTION. (PROJECT INCLUDES B-3833). | 9 | High Point Urban Area MPO, Cabarrus-Rowan MPO | INCLUDES B-3833; TIGER AWARD / INTERSTATE MAINTENANCE DISCRETIONARY FUNDING $11.7 MILLION; GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS | PRE-STI (TRANSITION) |  |  |  | 291988000
I-2304AC | HIGHWAY | I-85 | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO NORTH OF NC 150 IN DAVIDSON COUNTY, INCLUDING YADKIN RIVER BRIDGE | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC | EXEMPT |  | NHP | GARVEE ROW | 1066000
I-2304AC | HIGHWAY | I-85 | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO NORTH OF NC 150 IN DAVIDSON COUNTY, INCLUDING YADKIN RIVER BRIDGE | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC | EXEMPT |  | NHP | GARVEE CON | 8220000
I-2304AD | HIGHWAY | I-85 | NORTH OF NC 150 TO US 29-70-52/BUSINESS 85 IN DAVIDSON COUNTY | 9 | High Point Urban Area MPO | COMPLETE; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021 | PRE-STI (TRANSITION) |  | NHP | GARVEE ROW | 984000
I-2513 | HIGHWAY | I-26/I-240 | I-26 CONNECTOR, I-40 TO US 19/US 23. CONSTRUCT MULTI-LANE FREEWAY, PART ON NEW LOCATION. | 13 | French Broad River MPO | [5 empty] | 17496000
I-2513AA | HIGHWAY | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | HP | CONSTRUCTION | 4000000 | FY 2024: 4000000
I-2513AA | HIGHWAY | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHFP | RIGHT-OF-WAY | 1900000 | FY 2023: 1182000; FY 2024: 338000; FY 2025: 190000; FY 2026: 190000
I-2513AA | HIGHWAY | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHFP | UTILITIES | 100000 | FY 2023: 100000
I-2513AA | HIGHWAY | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 24851000 | FY 2024: 8614000; FY 2025: 10475000; FY 2026: 5762000
I-2513AA | HIGHWAY | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 849000 | FY 2024: 294000; FY 2025: 358000; FY 2026: 197000
I-2513AB | HIGHWAY | I-26, I-40 | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | REGION G |  | HP | CONSTRUCTION | 6250000 | FY 2024: 6250000
I-2513AB | HIGHWAY | I-26, I-40 | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | REGION G |  | NHP | RIGHT-OF-WAY | 3400000 | FY 2023: 2116000; FY 2024: 604000; FY 2025: 340000; FY 2026: 340000
I-2513AB | HIGHWAY | I-26, I-40 | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | REGION G |  | NHP | CONSTRUCTION | 13950000 | FY 2024: 5790000; FY 2025: 6521000; FY 2026: 1639000
I-2513AC | HIGHWAY | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE); $22.5M FOR CONSTRUCTION, PAYBACK 2026-2040 (FY 2026 / YR 8 SALE). | REGION G |  | T | BUILD NC CON | 58305000 |  | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 19435000
I-2513AC | HIGHWAY | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE); $22.5M FOR CONSTRUCTION, PAYBACK 2026-2040 (FY 2026 / YR 8 SALE). | REGION G |  | T | CONSTRUCTION | 92700000 | FY 2024: 0; FY 2025: 11971000; FY 2026: 17996000; FY 2027: 35596000; FY 2028: 27137000
I-2513AC | HIGHWAY | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE); $22.5M FOR CONSTRUCTION, PAYBACK 2026-2040 (FY 2026 / YR 8 SALE). | REGION G |  | T | BUILD NC CON | 28965000 |  |  |  | 1931000 | 1931000 | 1931000 | 1931000 | 1931000 | 1931000 | 1931000 | 1931000 | 13517000
I-2513AC | HIGHWAY | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE); $22.5M FOR CONSTRUCTION, PAYBACK 2026-2040 (FY 2026 / YR 8 SALE). | REGION G |  | T | RIGHT-OF-WAY | 29500000 | FY 2023: 21500000; FY 2024: 4000000; FY 2025: 4000000
I-2513AC | HIGHWAY | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE); $22.5M FOR CONSTRUCTION, PAYBACK 2026-2040 (FY 2026 / YR 8 SALE). | REGION G |  | T | BUILD NC ROW | 13515000 | 1802000 | 901000 | 901000 | 901000 | 901000 | 901000 | 901000 | 901000 | 901000 | 901000 | 901000 | 2703000
I-2513AC | HIGHWAY | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE); $22.5M FOR CONSTRUCTION, PAYBACK 2026-2040 (FY 2026 / YR 8 SALE). | REGION G |  | T | UTILITIES | 3750000 | FY 2023: 1875000; FY 2024: 1875000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 193050000 |  |  |  |  | 12870000 | 12870000 | 12870000 | 12870000 | 12870000 | 12870000 | 12870000 | 102960000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 50000000 | FY 2027: 25000000; FY 2028: 25000000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 25000000 | FY 2025: 12500000; FY 2026: 12500000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 322000000 | FY 2024: 70840000; FY 2025: 83720000; FY 2026: 70840000; FY 2027: 54740000; FY 2028: 41860000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 96525000 |  |  | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 38610000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | NHP | UTILITIES | 23200000 | FY 2024: 7733000; FY 2025: 7733000; FY 2026: 7734000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 53000000 | FY 2024: 21200000; FY 2025: 21200000; FY 2026: 5300000; FY 2027: 5300000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | NHP | GARVEE ROW | 96525000 |  |  | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 38610000
I-2513B | HIGHWAY | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D. | STATEWIDE MOBILITY |  | S(M) | RIGHT-OF-WAY | 25000000 | FY 2025: 12500000; FY 2026: 12500000
I-2513C | HIGHWAY | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS | 13 | French Broad River MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4075000
I-2513C | HIGHWAY | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS | 13 | French Broad River MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 17400000
I-2513C | HIGHWAY | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS | 13 | French Broad River MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 185001000
I-2513D | HIGHWAY | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | DIVISION 13 |  | BGANY | UTILITIES | 3100000 | FY 2024: 1550000; FY 2025: 1550000
I-2513D | HIGHWAY | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | DIVISION 13 |  | BGANY | CONSTRUCTION | 13100000 | FY 2024: 7863000; FY 2025: 5237000
I-2513D | HIGHWAY | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET) | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 15300000 | FY 2024: 6120000; FY 2025: 6120000; FY 2026: 3060000
I-2808 | HIGHWAY | I-77 | SOUTH OF SR 1125 (MILE MARKER 71) IN YADKIN COUNTY TO US 21 BYPASS (MILE MARKER 83.5) IN SURRY COUNTY (EXIT 83). PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | SECTION A - GARVEE BOND FUNDING $35 MILLION; PAYBACK FY 2007 - FY 2018. SEGMENT B TO BE ACCOMPLISHED UNDER I-5912. |  |  |  |  | 79239000
I-3306 | HIGHWAY | I-40 | I-85 IN ORANGE COUNTY TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM COUNTY. WIDEN TO SIX LANES AND INSTALL ITS. | 5, 7 | Durham-Chapel Hill-Carrboro MPO | [5 empty] | 88683000
I-3306A | HIGHWAY | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 17000000 | FY 2023: 4250000; FY 2024: 4250000
I-3306A | HIGHWAY | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | STATEWIDE MOBILITY |  | NHP | UTILITIES | 628000
I-3306A | HIGHWAY | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 65637000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 8749000
I-3306A | HIGHWAY | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 220928000 | FY 2023: 75530000; FY 2024: 57146000; FY 2025: 54202000
I-3306A | HIGHWAY | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | STATEWIDE MOBILITY |  | S(M) | RIGHT-OF-WAY | 10724000
I-3306AC | HIGHWAY | I-40 | NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTIONS FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  | NHP | CONSTRUCTION | 4350000 | FY 2026: 4046000; FY 2027: 304000
I-3306AC | HIGHWAY | I-40 | NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTIONS FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  | NHP | RIGHT-OF-WAY | 550000 | FY 2024: 550000
I-3306AC | HIGHWAY | I-40 | NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTIONS FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  | NHP | UTILITIES | 450000 | FY 2024: 450000
I-3306AD | HIGHWAY | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. TOWING CONTRACT FOR I-3306A CONSTRUCTION. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 2280000 | FY 2023: 2280000
I-3318 | HIGHWAY | I-95 | US 70 (EXIT 97) TO US 301 (EXIT 107). PAVEMENT AND BRIDGE REHABILITATION. | 4 | Upper Coastal Plain RPO | [5 empty] | 27566000
I-3802 | HIGHWAY | I-85 | NC 73 IN CABARRUS COUNTY (EXIT 55) TO US 29 / US 601 CONNECTOR (EXIT 68) IN ROWAN COUNTY. WIDEN TO EIGHT LANES. | 9, 10 | Cabarrus-Rowan MPO | SEGMENT B INCLUDES B-5365 AND I-3610 |  |  |  |  | 414875000
I-3802AA | HIGHWAY | I-85 | ITS FOR I-3802 A | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | CMAQ | CONSTRUCTION | 1630000 | FY 2023: 1630000
I-3803 | HIGHWAY | I-85 | US 29/NC 49 CONNECTOR, MECKLENBURG COUNTY TO NC 73 IN CABARRUS COUNTY. WIDEN TO 8-LANES. (COORDINATE WITH U-3415). | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | GARVEE BOND FUNDING - SEGMENT B: $103M FOR CONSTRUCTION, PAYBACK FY 2010-2021 |  |  |  |  | 296735000
I-3803B | HIGHWAY | I-85 | SOUTH OF SR 2894 (CONCORD MILLS - BRUTON SMITH BOULEVARD) TO NC 73 IN CABARRUS COUNTY. WIDEN TO 8-LANES. | 10 | Cabarrus-Rowan MPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 22592000
I-3819 | HIGHWAY | I-40/I-77 | STATESVILLE, MODIFICATION OF I-40/I-77 INTERCHANGE AREA. | 12 | Charlotte Regional TPO | GARVEE BOND FUNDING - SEGMENT A: $10M FOR CONSTRUCTION, PAYBACK FY 2012-2023 |  |  |  |  | 186182000
I-3819A | HIGHWAY | I-40/I-77 | INITIAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 12 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 4388000 | FY 2023: 1097000
I-3819B | HIGHWAY | I-40/I-77 | FINAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | STATEWIDE MOBILITY |  | T | BUILD NC CON | 142590000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 19012000
I-3819B | HIGHWAY | I-40/I-77 | FINAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 216075000 | FY 2023: 128342000
I-4400 | HIGHWAY | I-26 | US 25 TO NC 280. WIDEN TO ADD ADDITIONAL LANES. | 13, 14 | French Broad River MPO | [5 empty] | 246000000
I-4400A | HIGHWAY | I-26 | US 25 TO US 64 | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 1600000 | [11 empty] | 1600000
I-4400A | HIGHWAY | I-26 | US 25 TO US 64 | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | UTILITIES | 500000 | [11 empty] | 500000
I-4400A | HIGHWAY | I-26 | US 25 TO US 64 | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 114800000 | [11 empty] | 114800000
I-4400BA | HIGHWAY | I-26 | US 64 INTERCHANGE IMPROVEMENTS | 14 | French Broad River MPO |  | DIVISION 14 |  | T | UTILITIES | 400000 | FY 2027: 400000
I-4400BA | HIGHWAY | I-26 | US 64 INTERCHANGE IMPROVEMENTS | 14 | French Broad River MPO |  | DIVISION 14 |  | T | CONSTRUCTION | 29100000 | FY 2029: 5292000; FY 2030: 13213000; FY 2031: 8655000; FY 2032: 1940000
I-4400BB | HIGHWAY | I-26 | US 64 TO US 25 BUSINESS | 14 | French Broad River MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $43,911,307 FOR CONSTRUCTION, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 52752000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000
I-4400C | HIGHWAY | I-26 | US 25 BUSINESS TO NC 280 | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035 | REGION G |  | NHP | GARVEE CON | 36036000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000
I-4400C | HIGHWAY | I-26 | US 25 BUSINESS TO NC 280 | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035 | REGION G |  | NHP | GARVEE CON | 25740000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 3432000
I-4409 | HIGHWAY | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 13 | French Broad River MPO |  | DIVISION 13 |  | NHP | RIGHT-OF-WAY | 6300000 | FY 2023: 63000; FY 2024: 2817000; FY 2025: 2160000; FY 2026: 630000; FY 2027: 630000
I-4409 | HIGHWAY | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 13 | French Broad River MPO |  | DIVISION 13 |  | NHP | UTILITIES | 900000 | FY 2023: 450000; FY 2024: 450000
I-4409 | HIGHWAY | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 13 | French Broad River MPO |  | DIVISION 13 |  |  |  | 2400000
I-4409 | HIGHWAY | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 13 | French Broad River MPO |  | DIVISION 13 |  | NHP | CONSTRUCTION | 24700000 | FY 2025: 1952000; FY 2026: 12098000; FY 2027: 8670000; FY 2028: 1980000
I-4700 | HIGHWAY | I-26 | NC 280 (EXIT 40) TO I-40 AT ASHEVILLE. ADD ADDITIONAL LANES. | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  |  |  | 318380000
I-4700 | HIGHWAY | I-26 | NC 280 (EXIT 40) TO I-40 AT ASHEVILLE. ADD ADDITIONAL LANES. | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 62468000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000
I-4729 | HIGHWAY | I-26 | US 74/NC 108 INTERCHANGE (EXIT 67). REVISE INTERCHANGE AND CONSTRUCT IMPROVEMENTS TO NC 108. | 14 | Foothills RPO | [5 empty] | 33579000
I-4729B | HIGHWAY | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | REGION G |  | T | CONSTRUCTION | 22598000 | FY 2029: 3958000; FY 2030: 11283000; FY 2031: 7357000
I-4729B | HIGHWAY | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | REGION G |  | T | RIGHT-OF-WAY | 10200000 | FY 2027: 1250000; FY 2028: 2500000; FY 2029: 1250000
I-4729B | HIGHWAY | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | REGION G |  | T | UTILITIES | 2000000 | FY 2027: 1000000
I-4739 | HIGHWAY | I-40 | ACCESS IMPROVEMENTS IN THE VICINITY OF EXISTING I-40/NC 42 INTERCHANGE (EXIT 312). | 4 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033. | STATEWIDE MOBILITY |  | NHP | GARVEE ROW | 19305000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000
I-4739 | HIGHWAY | I-40 | ACCESS IMPROVEMENTS IN THE VICINITY OF EXISTING I-40/NC 42 INTERCHANGE (EXIT 312). | 4 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033. | STATEWIDE MOBILITY |  |  |  | 57928000
I-4739 | HIGHWAY | I-40 | ACCESS IMPROVEMENTS IN THE VICINITY OF EXISTING I-40/NC 42 INTERCHANGE (EXIT 312). | 4 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 40137000
I-4744 | HIGHWAY | I-40 | SR 1728 (WADE AVENUE) TO I-440 / US 1 / US 64. WIDEN TO SIX LANES. | 5 | Capital Area MPO | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020 | PRE-STI (TRANSITION) |  |  |  | 69363000
I-4744 | HIGHWAY | I-40 | SR 1728 (WADE AVENUE) TO I-440 / US 1 / US 64. WIDEN TO SIX LANES. | 5 | Capital Area MPO | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020 | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 4635000
I-4750 | HIGHWAY | I-77 | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150. WIDEN AND RECONSTRUCT ROADWAY. | 10, 12 | Charlotte Regional TPO | FUNDING FOR I-4750 AA INCLUDED IN I-5405 |  |  |  |  | 8681000
I-4750AB | HIGHWAY | I-77 | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150 (EXIT 36). CONSTRUCT ONE ADDITIONAL LANE IN EACH DIRECTION. | 10, 12 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | UTILITIES | 675000 | [11 empty] | 675000
I-4750AB | HIGHWAY | I-77 | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150 (EXIT 36). CONSTRUCT ONE ADDITIONAL LANE IN EACH DIRECTION. | 10, 12 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 133000000 | [11 empty] | 133000000
I-4750AB | HIGHWAY | I-77 | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150 (EXIT 36). CONSTRUCT ONE ADDITIONAL LANE IN EACH DIRECTION. | 10, 12 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 10500000 | [11 empty] | 10500000
I-4759 | HIGHWAY | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  | BGANY | GARVEE ROW | 1582000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000
I-4759 | HIGHWAY | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  | BGANY | RIGHT-OF-WAY | 10000000
I-4759 | HIGHWAY | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  | BGANY | UTILITIES | 700000
I-4759 | HIGHWAY | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  | BGANY | CONSTRUCTION | 35200000 | FY 2026: 8800000; FY 2027: 8800000; FY 2028: 8800000; FY 2029: 8800000
I-4759 | HIGHWAY | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  | BGDA | RIGHT-OF-WAY | 4000000
I-4759 | HIGHWAY | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | STATEWIDE MOBILITY |  |  |  | 4148000
I-4906 | HIGHWAY | I-95 | CUMBERLAND COUNTY LINE TO THE JOHNSTON COUNTY LINE. PAVEMENT REPAIR. | 6 | Mid-Carolina RPO | COMPLETED. GARVEE BOND FUNDING $3.15 MILLION; PAYBACK FY 2008 - FY 2019. | PRE-STI (TRANSITION) |  |  |  | 6384000
I-4928 | HIGHWAY | I-85 | CONSTRUCT NEW I-85 NBL WEIGH STATION FROM SR 1302 (CROWDERS MOUNTAIN ROAD) TO SR 1307 (EDGEWOOD ROAD). | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 34475000
I-5000 | HIGHWAY | I-85 | I-85/US 321. GEOMETRIC SAFETY IMPROVEMENTS TO INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 27078000
I-5008 | HIGHWAY | I-40 | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | 13 | Greater Hickory MPO | PROJECT TO BE LET WITH I-5875. | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1241000
I-5008 | HIGHWAY | I-40 | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | 13 | Greater Hickory MPO | PROJECT TO BE LET WITH I-5875. | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4200000
I-5008 | HIGHWAY | I-40 | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | 13 | Greater Hickory MPO | PROJECT TO BE LET WITH I-5875. | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1600000
I-5008 | HIGHWAY | I-40 | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | 13 | Greater Hickory MPO | PROJECT TO BE LET WITH I-5875. | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 29600000
I-5009 | HIGHWAY | I-40 | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | 13 | Greater Hickory MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 6100000
I-5009 | HIGHWAY | I-40 | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | 13 | Greater Hickory MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 16400000
I-5009 | HIGHWAY | I-40 | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | 13 | Greater Hickory MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 675000
I-5009 | HIGHWAY | I-40 | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | 13 | Greater Hickory MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 26200000
I-5106 | HIGHWAY | I-77 | MILE MARKER 57.83 TO MILE POST 61.74. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  |  |  | 6037000
I-5106 | HIGHWAY | I-77 | MILE MARKER 57.83 TO MILE POST 61.74. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 439000
I-5108 | HIGHWAY | I-40 | MILE MARKER 45 TO MILE MARKER 50. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING $4.67 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  |  |  | 7027000
I-5108 | HIGHWAY | I-40 | MILE MARKER 45 TO MILE MARKER 50. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING $4.67 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 512000
I-5109 | HIGHWAY | I-40 | HAYWOOD COUNTY LINE TO MILE MARKER 43 IN BUNCOMBE COUNTY. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING $6.1 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 669000
I-5109 | HIGHWAY | I-40 | HAYWOOD COUNTY LINE TO MILE MARKER 43 IN BUNCOMBE COUNTY. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING $6.1 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  |  |  | 9009000
I-5110 | HIGHWAY | FUTURE I-73 | NC 68 TO GREENSBORO WESTERN LOOP. SIX-LANE FREEWAY ON NEW LOCATION. | 7 | Greensboro Urban Area MPO | COMBINED WITH R-2413A AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 152283000
I-5111 | HIGHWAY | I-40 | I-440 / US 64 (EXIT 301) TO NC 42 (EXIT 312). ADD 2 GENERAL-PURPOSE LANES IN EACH DIRECTION. | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK 2019-2033. |  |  |  |  | 323026000
I-5111REG | HIGHWAY | I-40 | WAKE COUNTY LINE TO NC 42. | 4 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION A |  | NHP | GARVEE ROW | 3479000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000
I-5111REG | HIGHWAY | I-40 | WAKE COUNTY LINE TO NC 42. | 4 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION A |  | NHP | CONSTRUCTION | 23795000
I-5111SW | HIGHWAY | I-40 | I-440 / US 64 (EXIT 301) TO JOHNSTON COUNTY LINE. | 5 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | STATEWIDE MOBILITY |  | NHP | GARVEE ROW | 15826000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000
I-5111SW | HIGHWAY | I-40 | I-440 / US 64 (EXIT 301) TO JOHNSTON COUNTY LINE. | 5 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 108398000
I-5112 | HIGHWAY | I-40; SR 1728 (WADE AVENUE) | EAST OF I-540 TO WADE AVENUE (EXIT 289) INCLUDING RAMPS, AND SR 1728 (WADE AVENUE) FROM I-40 TO SR 3009 (EDWARDS MILL ROAD). MILL AND RESURFACE ROADWAY, SHOULDERS AND RAMPS. | 5 | Capital Area MPO | PROJECT COMPLETE - GARVEE BOND FUNDING $5.8 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  | BGANY | GARVEE CON | 45000
I-5112 | HIGHWAY | I-40; SR 1728 (WADE AVENUE) | EAST OF I-540 TO WADE AVENUE (EXIT 289) INCLUDING RAMPS, AND SR 1728 (WADE AVENUE) FROM I-40 TO SR 3009 (EDWARDS MILL ROAD). MILL AND RESURFACE ROADWAY, SHOULDERS AND RAMPS. | 5 | Capital Area MPO | PROJECT COMPLETE - GARVEE BOND FUNDING $5.8 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 592000
I-5112 | HIGHWAY | I-40; SR 1728 (WADE AVENUE) | EAST OF I-540 TO WADE AVENUE (EXIT 289) INCLUDING RAMPS, AND SR 1728 (WADE AVENUE) FROM I-40 TO SR 3009 (EDWARDS MILL ROAD). MILL AND RESURFACE ROADWAY, SHOULDERS AND RAMPS. | 5 | Capital Area MPO | PROJECT COMPLETE - GARVEE BOND FUNDING $5.8 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020 | PRE-STI (TRANSITION) |  |  |  | 8673000
I-5309 | HIGHWAY | I-40 /I-85 | EAST OF GUILFORD COUNTY LINE TO EAST OF NC 49. PAVEMENT REHABILITATION. | 7 | Burlington-Graham MPO | CONSTRUCTION COMPLETED - PROJECT COST INCLUDES I-5836 CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 14411000
I-5504 | HIGHWAY | I-26 | NC 191 (BREVARD ROAD). UPGRADE INTERCHANGE. | 13 | French Broad River MPO | UNDER CONSTRUCTION AS DESIGN-BUILD PROJECT | STATEWIDE MOBILITY |  |  |  | 53784000
I-5505 | HIGHWAY | I-85 | US 52 (INNES STREET) AND US 601 (JAKE ALEXANDER BOULEVARD) INTERCHANGES. STABILIZE SLOPES, REPLACE EMERGENCY LANE / SHOULDER , AND RESEAL JOINTS. | 9 | Cabarrus-Rowan MPO | CONSTRUCTION INCLUDED WITH I-5741 |  |  |  |  | 300000
I-5506 | HIGHWAY | I-40 | SR 1002 (AVIATION PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 1002 TO SR 3015 (AIRPORT BOULEVARD). | 5 | Capital Area MPO | PROJECT COMPLETE. | STATEWIDE MOBILITY |  |  |  | 25333000
I-5507 | HIGHWAY | I-485 | I-485, I-77 SOUTH OF CHARLOTTE TO US 74 (INDEPENDENCE BOULEVARD). ADD ONE EXPRESS LANE IN EACH DIRECTION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT | STATEWIDE MOBILITY |  |  |  | 25492000
I-5507 | HIGHWAY | I-485 | I-485, I-77 SOUTH OF CHARLOTTE TO US 74 (INDEPENDENCE BOULEVARD). ADD ONE EXPRESS LANE IN EACH DIRECTION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 458656000 | FY 2023: 19300000; FY 2024: 93600000; FY 2025: 39000000
I-5606 | HIGHWAY | I-77 | EXIT 45 TO EXIT 54, EXCLUDING PROJECT AREA FOR I-3819 A. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO | COMPLETE |  |  |  |  | 10077000
I-5700 | HIGHWAY | I-40 | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | STATEWIDE MOBILITY |  |  |  | 26914000
I-5700 | HIGHWAY | I-40 | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 3333000
I-5700 | HIGHWAY | I-40 | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 12870000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000
I-5700 | HIGHWAY | I-40 | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 35530000
I-5701 | HIGHWAY | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 67700000 | FY 2027: 22412000; FY 2028: 23566000; FY 2029: 16262000; FY 2030: 5460000
I-5701 | HIGHWAY | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703 | STATEWIDE MOBILITY |  |  |  | 750000
I-5701 | HIGHWAY | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703 | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 0 | FY 2027: 0
I-5701 | HIGHWAY | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703 | STATEWIDE MOBILITY |  | NHP | UTILITIES | 1100000 | FY 2027: 550000; FY 2028: 550000
I-5703 | HIGHWAY | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 119100000 | FY 2027: 32273000; FY 2028: 35785000; FY 2029: 27522000; FY 2030: 19660000; FY 2031: 3860000
I-5703 | HIGHWAY | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701 | STATEWIDE MOBILITY |  | NHP | UTILITIES | 3600000 | FY 2027: 1800000; FY 2028: 1800000
I-5703 | HIGHWAY | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701 | STATEWIDE MOBILITY |  |  |  | 750000
I-5703 | HIGHWAY | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701 | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 29600000 | FY 2027: 11840000; FY 2028: 11840000; FY 2029: 2960000; FY 2030: 2960000
I-5707 | HIGHWAY | I-40 | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  |  |  | 1780000
I-5707 | HIGHWAY | I-40 | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 900000 | FY 2025: 900000
I-5707 | HIGHWAY | I-40 | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | UTILITIES | 205000 | FY 2025: 205000
I-5707 | HIGHWAY | I-40 | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 8200000 | FY 2027: 1188000; FY 2028: 6212000; FY 2029: 800000
I-5708 | HIGHWAY | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | STATEWIDE MOBILITY |  |  |  | 11165000
I-5708 | HIGHWAY | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | STATEWIDE MOBILITY |  | NHP | GARVEE ROW | 1736000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000
I-5708 | HIGHWAY | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 9100000 | FY 2026: 3899000; FY 2027: 5201000
I-5711 | HIGHWAY | I-40 / I-85 | SR 1007 (MEBANE-OAKS ROAD) IN MEBANE. INTERCHANGE IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; GARVEE BONDS: $2M FOR CONSTRUCTION - PAYBCK 2021-2035 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 723000
I-5711 | HIGHWAY | I-40 / I-85 | SR 1007 (MEBANE-OAKS ROAD) IN MEBANE. INTERCHANGE IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; GARVEE BONDS: $2M FOR CONSTRUCTION - PAYBCK 2021-2035 | STATEWIDE MOBILITY |  |  |  | 5476000
I-5711 | HIGHWAY | I-40 / I-85 | SR 1007 (MEBANE-OAKS ROAD) IN MEBANE. INTERCHANGE IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; GARVEE BONDS: $2M FOR CONSTRUCTION - PAYBCK 2021-2035 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 2580000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 344000
I-5711 | HIGHWAY | I-40 / I-85 | SR 1007 (MEBANE-OAKS ROAD) IN MEBANE. INTERCHANGE IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; GARVEE BONDS: $2M FOR CONSTRUCTION - PAYBCK 2021-2035 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 9830000
I-5712 | HIGHWAY | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 18600000 | FY 2028: 9658000; FY 2029: 7700000; FY 2030: 1242000
I-5712 | HIGHWAY | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | NHP | UTILITIES | 800000 | FY 2026: 400000; FY 2027: 400000
I-5712 | HIGHWAY | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 12700000 | FY 2026: 2903000; FY 2027: 5806000; FY 2028: 1451000; FY 2029: 1270000; FY 2030: 1270000
I-5712 | HIGHWAY | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  |  |  | 400000
I-5714 | HIGHWAY | I-77 | SR 2136 (GILEAD ROAD) INTERCHANGE. UPGRADE EXISTING INTERCHANGE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 13600000
I-5715 | HIGHWAY | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  |  |  | 4500000
I-5715 | HIGHWAY | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 19000000 | FY 2023: 1164000; FY 2024: 7019000; FY 2025: 7019000; FY 2026: 1899000; FY 2027: 1899000
I-5715 | HIGHWAY | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | UTILITIES | 3000000 | FY 2023: 1500000; FY 2024: 1500000
I-5715 | HIGHWAY | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 61800000 | FY 2026: 618000; FY 2027: 28124000; FY 2028: 22985000; FY 2029: 10073000
I-5716 | HIGHWAY | I-40 | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  |  |  | 400000
I-5716 | HIGHWAY | I-40 | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 8500000 | FY 2026: 85000; FY 2027: 6978000; FY 2028: 1437000
I-5718 | HIGHWAY | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-277 INTERCHANGES, AND INSTALL RAMP METERS. | 10 | Charlotte Regional TPO | [5 empty] | 5000000
I-5718A | HIGHWAY | I-77 | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BOND R | CONSTRUCTION | 493000000
I-5718A | HIGHWAY | I-77 | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 207000000
I-5718A | HIGHWAY | I-77 | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 660000000
I-5718A | HIGHWAY | I-77 | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 30900000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 34000000 | FY 2027: 17000000; FY 2028: 17000000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | DP | RIGHT-OF-WAY | 10000000 | FY 2024: 10000000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 10586000 | FY 2024: 10586000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 172870000 | FY 2024: 206000; FY 2025: 49556000; FY 2026: 100700000; FY 2027: 8000; FY 2028: 22400000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | UTILITIES | 33501000 | FY 2024: 11167000; FY 2025: 11167000; FY 2026: 11167000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | UTILITIES | 7500000 | FY 2024: 7500000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 17901000 | FY 2024: 179000; FY 2025: 6982000; FY 2026: 7160000; FY 2027: 1790000; FY 2028: 1790000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 2500000 | FY 2024: 2500000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 20000000 | FY 2025: 10000000; FY 2026: 10000000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | S(M) | RIGHT-OF-WAY | 20000000 | FY 2025: 10000000; FY 2026: 10000000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 132555000 |  |  |  |  | 8837000 | 8837000 | 8837000 | 8837000 | 8837000 | 8837000 | 8837000 | 70696000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 77220000 |  |  | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 30888000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | NHP | GARVEE ROW | 77220000 |  |  | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 30888000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | DP | UTILITIES | 30000000 | FY 2024: 30000000
I-5719 | HIGHWAY | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). GARVEE BOND FUNDING: $60M FOR ROW, $163M FOR CONSTRUCTION (2 SALES). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 42344000 | FY 2024: 42344000
I-5719A | HIGHWAY | I-85 | IMPLEMENT FLOOD RISK, VULNERABILITY ASSESSMENT, AND FLOOD WARNING SYSTEM ALONG THE I-85 CORRIDOR. | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | DP | IMPLEMENTATION | 160000 | FY 2024: 160000
I-5719A | HIGHWAY | I-85 | IMPLEMENT FLOOD RISK, VULNERABILITY ASSESSMENT, AND FLOOD WARNING SYSTEM ALONG THE I-85 CORRIDOR. | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | IMPLEMENTATION | 40000 | FY 2024: 40000
I-5719B | HIGHWAY | I-85 | INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 560000 | FY 2025: 560000
I-5719B | HIGHWAY | I-85 | INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 140000 | FY 2025: 140000
I-5719C | HIGHWAY | I-85 | SOUTH CAROLINA STATE LINE TO NC 273. INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT, INCIDENT MANAGEMENT, STATEWIDE RESILIENCE, BROADBAND (SOUTH CAROLINA STATE LINE TO US 74), CONNECTED VEHICLE TECHNOLOGY, AND TRAVELER INFORMATION. | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 16936000 | FY 2025: 16936000
I-5719C | HIGHWAY | I-85 | SOUTH CAROLINA STATE LINE TO NC 273. INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT, INCIDENT MANAGEMENT, STATEWIDE RESILIENCE, BROADBAND (SOUTH CAROLINA STATE LINE TO US 74), CONNECTED VEHICLE TECHNOLOGY, AND TRAVELER INFORMATION. | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 4234000 | FY 2025: 4234000
I-5729 | HIGHWAY | I-85 |  | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 11315000
I-5734 | HIGHWAY | I-40 | 1.3 MILES EAST OF SR 1850 (SANDY RIDGE ROAD) TO 1.1 MILES EAST OF SR 1556 (GALLIMORE DAIRY ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION - PRIOR YEAR COST IS FOR BRIDGE PRESERVATION; PAVEMENT REHABILITATION COST INCLUDED IN I-5762 | STATEWIDE MOBILITY |  |  |  | 2120000
I-5736 | HIGHWAY | I-74 / US 311 | FORSYTH COUNTY LINE TO SR 1300 (GREEN ROAD) IN HIGH POINT. PAVEMENT REHABILITATION. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION - AMOUNT INCLUDES I-5767 CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 17293000
I-5737 | HIGHWAY | I-73 | SOUTH OF SR 2269 (VISION DRIVE) TO NORTH OF SR 1712 (PINEVIEW STREET). PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 100000
I-5738 | HIGHWAY | I-85 | SOUTH OF SR 1009 (MAIN STREET) TO NORTH OF SR 1912 (LUNAR DRIVE) IN ARCHDALE. PAVEMENT REHABILITATION. | 8 | High Point Urban Area MPO | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789 | STATEWIDE MOBILITY |  |  |  | 150000
I-5740 | HIGHWAY | I-85 | SR 2205 (OLD US 64) TO 0.4 MILES NORTH OF US 64. PAVEMENT REHABILITATION. | 9 | High Point Urban Area MPO | COMPLETE | STATEWIDE MOBILITY |  |  |  | 3217000
I-5746 | HIGHWAY | I-277 | I-77 TO EAST 10TH STREET. RESURFACING AND BRIDGE REHABILITATION. | 10 | Charlotte Regional TPO | [5 empty] | 20898000
I-5746C | HIGHWAY | I-277 (BROOKSHIRE FRWY) | I-77 TO EAST 10TH STREET. RESURFACE ROADWAY AND REHABILITATE BRIDGES FROM JOHNSON STREET TO EAST 10TH STREET. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 29400000 | FY 2023: 11765000; FY 2024: 2774000
I-5762 | HIGHWAY | I-40 | FORSYTH COUNTY LINE TO 1.3 MILES EAST OF SR 1850 (SANDY RIDGE ROAD). PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | UNDER CONSTRUCTION - INCLUDES CONSTRUCTION COST FOR I-5734 | STATEWIDE MOBILITY |  |  |  | 9760000
I-5763 | HIGHWAY | I-73 | US 311 TO 0.6 MILE NORTH OF SR 1938 (HOCKETT DAIRY ROAD). PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO, High Point Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 9050000
I-5765 | HIGHWAY | I-40 | 0.5 MILES WEST OF US 601 TO 1.2 MILES EAST OF SR 1410 (FARMINGTON ROAD). PAVEMENT REHABILITATION. | 9 | Northwest Piedmont RPO | COMPLETE | STATEWIDE MOBILITY |  |  |  | 11975000
I-5766 | HIGHWAY | I-40 | 1.3 MILES EAST OF NC 150 (PETERS CREEK PARKWAY) TO NC 109 (THOMASVILLE ROAD) IN WINSTON-SALEM. PAVEMENT REHABILITATION. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION - COORDINATE WITH I-5857 | STATEWIDE MOBILITY |  |  |  | 15135000
I-5767 | HIGHWAY | I-74 / US 311 | I-40 TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | 9 | Winston-Salem Urban Area MPO, High Point Urban Area MPO | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED IN I-5736 | STATEWIDE MOBILITY |  |  |  | 100000
I-5769 | HIGHWAY | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 1013000
I-5769 | HIGHWAY | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 60000
I-5769 | HIGHWAY | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 240000
I-5769 | HIGHWAY | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 10069000
I-5769 | HIGHWAY | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 3915000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000
I-5769 | HIGHWAY | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  |  |  | 292000
I-5770 | HIGHWAY | I-85 | CONCRETE PAVEMENT JOINT 0.3 MILES SOUTH OF NC 16 TO CONCRETE PAVEMENT JOINT SOUTH OF SR 1601 (MOORES CHAPEL ROAD). PAVEMENT AND BRIDGE REHABILITATION. | 10 | Charlotte Regional TPO | PROJECT COMBINED WITH I-5796 - UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 15680000
I-5780 | HIGHWAY | I-40 | JOHNSTON COUNTY LINE (MILE MARKER 340) TO DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10268000
I-5780 | HIGHWAY | I-40 | JOHNSTON COUNTY LINE (MILE MARKER 340) TO DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 5587000
I-5780 | HIGHWAY | I-40 | JOHNSTON COUNTY LINE (MILE MARKER 340) TO DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 4579000
I-5781 | HIGHWAY | I-40 | SR 1010 (CLEVELAND ROAD) (MILE MARKER 312.2) TO WEST OF SR 1211 (MORGAN ROAD) (MILE MARKER 328.5). PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. NATIONAL HIGHWAY FREIGHT PROGRAM PROJECT. | STATEWIDE MOBILITY |  |  |  | 11795000
I-5786 | HIGHWAY | I-95 | SOUTH OF SR 1001 (LIZZIE MILL ROAD) TO THE JOHNSTON/WILSON COUNTY LINE NORTH OF NC 222. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 70484000
I-5789 | HIGHWAY | I-85 | SR 1113 (KIVETT DRIVE) TO 0.4 MILE NORTH OF I-85 BUSINESS IN HIGH POINT. PAVEMENT REHABILITATION. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDES I-5738 AND I-5821 | STATEWIDE MOBILITY |  |  |  | 17000000
I-5790 | HIGHWAY | I-85 | 0.2 MILE NORTH OF SR 3039 (NELSON FARM ROAD) TO 1.3 MILES NORTH OF SR 3029 (YOUNGS MILL ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION - AMOUNT INCLUDES I-5855 CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 12012000
I-5794 | HIGHWAY | I-40 | 0.3 MILE WEST OF NC 801 IN DAVIE COUNTY TO SR 1101 (HARPER ROAD) IN FORSYTH COUNTY. PAVEMENT REHABILITATION. | 9 | Winston-Salem Urban Area MPO | COMPLETE | STATEWIDE MOBILITY |  |  |  | 1825000
I-5795 | HIGHWAY | I-40 | 0.3 MILE EAST OF SR 3153 (HANES MALL BOULEVARD) TO 0.9 MILE EAST OF NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM AND SR 2747 (CLEMMONSVILLE ROAD) IN WINSTON-SALEM TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION AND REHABILITATION OF BRIDGES 330161, 330162, 330444, 330448, 330449,330508, AND 330509. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 100000
I-5795 | HIGHWAY | I-40 | 0.3 MILE EAST OF SR 3153 (HANES MALL BOULEVARD) TO 0.9 MILE EAST OF NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM AND SR 2747 (CLEMMONSVILLE ROAD) IN WINSTON-SALEM TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION AND REHABILITATION OF BRIDGES 330161, 330162, 330444, 330448, 330449,330508, AND 330509. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 11318000 | FY 2023: 439000
I-5795 | HIGHWAY | I-40 | 0.3 MILE EAST OF SR 3153 (HANES MALL BOULEVARD) TO 0.9 MILE EAST OF NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM AND SR 2747 (CLEMMONSVILLE ROAD) IN WINSTON-SALEM TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION AND REHABILITATION OF BRIDGES 330161, 330162, 330444, 330448, 330449,330508, AND 330509. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 12496000 | FY 2023: 486000
I-5796 | HIGHWAY | I-85 | 0.1 MILE NORTH OF SR 5901 (BILLY GRAHAM PKWY) TO 0.3 MILE SOUTH OF NC 16 AT MILE MARKER 35.93. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | TO BE LET WITH I-5770 - UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 525000
I-5798 | HIGHWAY | I-485 | I-85 TO ROCKY RIVER ROAD. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMPLETE | STATEWIDE MOBILITY |  |  |  | 13027000
I-5805 | HIGHWAY | I-40 | SR 2158 (OLD MOCKSVILLE ROAD) TO DAVIE COUNTY LINE. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5805 | HIGHWAY | I-40 | SR 2158 (OLD MOCKSVILLE ROAD) TO DAVIE COUNTY LINE. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 70500000 | FY 2028: 18255000; FY 2029: 24328000; FY 2030: 18069000; FY 2031: 9848000
I-5811 | HIGHWAY | I-40 | WEST OF I-73 / US 421 TO HOLDEN ROAD IN GREENSBORO. PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 2225000
I-5812 | HIGHWAY | I-40 / BUSINESS 85 I-40 / I-85 I-85 | I-40 / BUSINESS 85, EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) TO I-85; I-85 NORTH OF SR 3000 (MCCONNELL ROAD) TO I-40; I-40 / I-85, WEST OF SR 3048 (MOUNT HOPE CHURCH ROAD) TO EAST OF SR 3056 (ROCK CREEK DAIRY ROAD). PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 9882000
I-5821 | HIGHWAY | I-85 | RANDOLPH COUNTY LINE TO SR 1113 (KIVETT DRIVE). PAVEMENT REHABILITATION. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789 | STATEWIDE MOBILITY |  |  |  | 100000
I-5823 | HIGHWAY | I-40 | IREDELL COUNTY LINE TO 0.5 MILE WEST OF US 601. PAVEMENT REHABILITATION. | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 64408000
I-5826 | HIGHWAY | I-85 | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 5694000
I-5826 | HIGHWAY | I-85 | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 666000
I-5826 | HIGHWAY | I-85 | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  |  |  | 217000
I-5826 | HIGHWAY | I-85 | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 2580000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000
I-5828 | HIGHWAY | I-485 | I-77 TO NC 49. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS | STATEWIDE MOBILITY |  |  |  | 310000
I-5828 | HIGHWAY | I-485 | I-77 TO NC 49. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS | STATEWIDE MOBILITY |  | HFB | CONSTRUCTION | 2900000 | FY 2025: 1970000; FY 2026: 930000
I-5828 | HIGHWAY | I-485 | I-77 TO NC 49. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 9050000 | FY 2025: 6149000; FY 2026: 2901000
I-5829 | HIGHWAY | I-77 | MILE MARKER 91 TO MILE MARKER 95. PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION |  |  |  |  | 3050000
I-5829A | HIGHWAY | I-77 | MILE MARKER 91 TO MILE MARKER 95. DIAMOND GRINDING | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 3600000 | FY 2023: 1800000
I-5831 | HIGHWAY | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. PAVEMENT AND BRIDGE REHABILITATION. | 13 | Land-of-Sky RPO | [5 empty] | 10000
I-5831A | HIGHWAY | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. REPLACE CURB AND DRAINAGE BOXES, AND REHABILITATE BRIDGES. | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 8728000 | FY 2023: 5835000; FY 2024: 1098000
I-5831B | HIGHWAY | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. REHABILITATE PAVEMENT. | 13 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 9000000 | FY 2025: 4470000; FY 2026: 4530000
I-5834 | HIGHWAY | I-40 | MILE MARKER 27 TO MILE MARKER 34. PAVEMENT REHABILITATION. | 14 | French Broad River MPO, Land-of-Sky RPO | 6-13-2022: $2.566M IN NHPIM FUNDS SWITCHED WITH $2.566M IN BGDA AS PART OF FUND SWAP. |  |  |  |  | 5000000
I-5834A | HIGHWAY | I-40 | MILE MARKER 27 TO MILE MARKER 30. PAVEMENT REHABILITATION. | 14 | French Broad River MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGDA | CONSTRUCTION | 2566000 | FY 2023: 1037000
I-5834A | HIGHWAY | I-40 | MILE MARKER 27 TO MILE MARKER 30. PAVEMENT REHABILITATION. | 14 | French Broad River MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 4733000 | FY 2023: 1913000
I-5834B | HIGHWAY | I-40 | MILE MARKER 30 TO MILE MARKER 34. PAVEMENT REHABILITATION. | 14 | French Broad River MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 13475000 | FY 2023: 7317000; FY 2024: 1357000
I-5836 | HIGHWAY | I-40 / I-85 | 0.2 MILE EAST OF NC 49 TO 0.2 MILE EAST OF NC 54 IN GRAHAM. PAVEMENT REHABILITATION. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION - CONSTRUCTION FUNDED UNDER I-5309 | STATEWIDE MOBILITY |  |  |  | 100000
I-5837 | HIGHWAY | I-85 | GASTON COUNTY LINE TO 0.7 MILES NORTH OF GASTON COUNTY LINE. INCLUDES RAMPS FROM GASTON COUNTY LINE TO GLENWOOD AVENUE. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3368000 | FY 2023: 874000
I-5837 | HIGHWAY | I-85 | GASTON COUNTY LINE TO 0.7 MILES NORTH OF GASTON COUNTY LINE. INCLUDES RAMPS FROM GASTON COUNTY LINE TO GLENWOOD AVENUE. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 60000
I-5838 | HIGHWAY | I-85 | REHABIILITATE BRIDGES 590203 (I-85 NB) AND 590204 (I-85 SB) OVER SEABOARD COASTLINE RAILROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 900000 | FY 2023: 900000
I-5838 | HIGHWAY | I-85 | REHABIILITATE BRIDGES 590203 (I-85 NB) AND 590204 (I-85 SB) OVER SEABOARD COASTLINE RAILROAD. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10000
I-5850 | HIGHWAY | I-95 | NORTH OF US 301 (MILE MARKER 22) TO CUMBERLAND COUNTY LINE (MILE MARKER 40). PAVEMENT REHABILITATION. | 6 | Lumber River RPO, Fayetteville Area MPO |  | STATEWIDE MOBILITY |  |  |  | 19090000
I-5852 | HIGHWAY | I-73 | I-85 TO SR 2085 (BRYAN BOULEVARD) IN GREENSBORO. PAVEMENT AND BRIDGE REHABILITATION. | 7 | Greensboro Urban Area MPO | [5 empty] | 20272000
I-5853 | HIGHWAY | I-85 / US 29 / US 70 | 1 MILE SOUTH OF SR 1129 (GROOMETOWN ROAD) TO 0.3 MILE NORTH OF SR 1129 (GROOMETOWN ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 6076000
I-5854 | HIGHWAY | I-85 | NORTH OF I-73 / US 421 INTERCHANGE TO SR 3300 (SOUTH ELM-EUGENE STREET). PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 8692000
I-5855 | HIGHWAY | I-85 | SR 3300 (SOUTH ELM-EUGENE STREET) TO 0.2 MILE NORTH OF SR 3039 (NELSON FARM ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED IN I-5790 | STATEWIDE MOBILITY |  |  |  | 100000
I-5858 | HIGHWAY | I-85 | US 29 / US 601 IN CHINA GROVE TO US 601 (JAKE ALEXANDER BOULEVARD) IN SALISBURY AND FROM SOUTH OF US 52 IN SALISBURY TO NORTH OF SR 2120 (LONG FERRY ROAD) IN SPENCER. PAVEMENT REHABILITATION. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | STATEWIDE MOBILITY |  |  |  | 11072000
I-5858 | HIGHWAY | I-85 | US 29 / US 601 IN CHINA GROVE TO US 601 (JAKE ALEXANDER BOULEVARD) IN SALISBURY AND FROM SOUTH OF US 52 IN SALISBURY TO NORTH OF SR 2120 (LONG FERRY ROAD) IN SPENCER. PAVEMENT REHABILITATION. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 12012000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000
I-5861 | HIGHWAY | I-485 | PAVEMENT AND BRIDGE REHABILITATION AT OAKDALE ROAD INTERCHANGE AT MILEMARKER 17.2. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 1000000 | FY 2023: 10000; FY 2024: 990000
I-5861 | HIGHWAY | I-485 | PAVEMENT AND BRIDGE REHABILITATION AT OAKDALE ROAD INTERCHANGE AT MILEMARKER 17.2. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 710000
I-5864 | HIGHWAY | I-77 | MILEMARKER 71.8 TO MILEMARKER 75.8. PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | COMBINE WITH I-5865 FOR LETTING. | STATEWIDE MOBILITY |  |  |  | 10000
I-5864 | HIGHWAY | I-77 | MILEMARKER 71.8 TO MILEMARKER 75.8. PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | COMBINE WITH I-5865 FOR LETTING. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 6285000 | FY 2028: 2134000; FY 2029: 4151000
I-5865 | HIGHWAY | I-77 | MILEMARKER 75.8 TO US 21 (EXIT 79). PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | COMBINE WITH I-5864 FOR LETTING. | STATEWIDE MOBILITY |  |  |  | 50000
I-5865 | HIGHWAY | I-77 | MILEMARKER 75.8 TO US 21 (EXIT 79). PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | COMBINE WITH I-5864 FOR LETTING. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 2990000 | FY 2028: 1824000; FY 2029: 1166000
I-5870 | HIGHWAY | I-440 / US 1 | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3000000
I-5870 | HIGHWAY | I-440 / US 1 | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 213701000
I-5870 | HIGHWAY | I-440 / US 1 | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 193101000
I-5870 | HIGHWAY | I-440 / US 1 | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 5000000
I-5873 | HIGHWAY | I-40 | NC 54 IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION | REGION C |  |  |  | 4800000
I-5874 | HIGHWAY | I-40 | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | 13 | Greater Hickory MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2469000
I-5874 | HIGHWAY | I-40 | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | 13 | Greater Hickory MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1600000
I-5874 | HIGHWAY | I-40 | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | 13 | Greater Hickory MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 300000
I-5874 | HIGHWAY | I-40 | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | 13 | Greater Hickory MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 17500000
I-5875 | HIGHWAY | I-40 | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | 13 | Greater Hickory MPO | PROJECT TO BE LET WITH I-5008 | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 7120000
I-5875 | HIGHWAY | I-40 | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | 13 | Greater Hickory MPO | PROJECT TO BE LET WITH I-5008 | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1500000
I-5875 | HIGHWAY | I-40 | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | 13 | Greater Hickory MPO | PROJECT TO BE LET WITH I-5008 | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 600000
I-5875 | HIGHWAY | I-40 | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | 13 | Greater Hickory MPO | PROJECT TO BE LET WITH I-5008 | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 20700000
I-5877 | HIGHWAY | I-95 | SR 1811 (BUD HAWKINS ROAD) (EXIT 70) AND SR 1001 (LONG BRANCH ROAD) (EXIT 71). IMPROVE INTERCHANGES. | 6 | Mid-Carolina RPO | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 2649000
I-5877 | HIGHWAY | I-95 | SR 1811 (BUD HAWKINS ROAD) (EXIT 70) AND SR 1001 (LONG BRANCH ROAD) (EXIT 71). IMPROVE INTERCHANGES. | 6 | Mid-Carolina RPO | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 69733000
I-5877 | HIGHWAY | I-95 | SR 1811 (BUD HAWKINS ROAD) (EXIT 70) AND SR 1001 (LONG BRANCH ROAD) (EXIT 71). IMPROVE INTERCHANGES. | 6 | Mid-Carolina RPO | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 3304000 | FY 2023: 1000000; FY 2024: 1000000; FY 2025: 1304000
I-5878 | HIGHWAY | I-95 | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). IMPROVE INTERCHANGES. | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 12000000
I-5878 | HIGHWAY | I-95 | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). IMPROVE INTERCHANGES. | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 78860000 | FY 2023: 0; FY 2024: 18199000; FY 2025: 18199000; FY 2026: 14500000; FY 2027: 3770000
I-5878A | HIGHWAY | I-95 | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). CLEARING FOR UTILITIES. | 6 | Mid-Carolina RPO | COMPLETED. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 139000
I-5879 | HIGHWAY | I-95 | SR 1536 (CARTHAGE ROAD/WEST CARTHAGE ROAD) (EXIT 19). IMPROVE INTERCHANGE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | DIVISION 6 |  |  |  | 1140000
I-5879 | HIGHWAY | I-95 | SR 1536 (CARTHAGE ROAD/WEST CARTHAGE ROAD) (EXIT 19). IMPROVE INTERCHANGE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | DIVISION 6 |  | NHP | CONSTRUCTION | 15028000 | FY 2023: 5861000
I-5880 | HIGHWAY | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | T | CONSTRUCTION | 24000000 | FY 2025: 8778000; FY 2026: 10919000; FY 2027: 4303000
I-5880 | HIGHWAY | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | 9 | Winston-Salem Urban Area MPO |  | REGION D |  |  |  | 1835000
I-5880 | HIGHWAY | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | NHP | RIGHT-OF-WAY | 2600000 | FY 2023: 416000; FY 2024: 1248000; FY 2025: 416000; FY 2026: 260000; FY 2027: 260000
I-5880 | HIGHWAY | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | NHP | UTILITIES | 800000 | FY 2023: 800000
I-5883 | HIGHWAY | I-95 | SR 1808 (JONESBORO ROAD) (EXIT 75) AND SR 1709 (HODGES CHAPEL ROAD) (EXIT 77). IMPROVE INTERCHANGES. | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 8975000
I-5883 | HIGHWAY | I-95 | SR 1808 (JONESBORO ROAD) (EXIT 75) AND SR 1709 (HODGES CHAPEL ROAD) (EXIT 77). IMPROVE INTERCHANGES. | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 100613000 | FY 2023: 0; FY 2024: 23219000; FY 2025: 41719000; FY 2026: 0; FY 2027: 4810000
I-5886 | HIGHWAY | I-40 | US 25A (SWEETEN CREEK ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | 13 | French Broad River MPO | COMPLETE | DIVISION 13 |  |  |  | 1201000
I-5888 | HIGHWAY | I-40 | MILE MARKER 37 TO MILE MARKER 44. REHABILIATE PAVEMENT AND BRIDGES. | 13 | French Broad River MPO | [5 empty] | 12099000
I-5888B | HIGHWAY | I-40 | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE BRIDGES. | 13 | French Broad River MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 4110000 | FY 2025: 2623000; FY 2026: 1487000
I-5889 | HIGHWAY | I-40 | MILE MARKER 45.25 TO MILE MARKER 50. REHABILTATE PAVEMENT AND PRESERVE BRIDGES. | 13 | French Broad River MPO | [5 empty] | 10123000
I-5889B | HIGHWAY | I-40 | MILE MARKER 45.25 TO MILE MARKER 50. REHABILITATE PAVEMENT AND PRESERVE BRIDGES 100352, 100356, 100344, 100347, 100339, AND 100334. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 6559000 | FY 2023: 2268000; FY 2024: 3052000; FY 2025: 1239000
I-5889B | HIGHWAY | I-40 | MILE MARKER 45.25 TO MILE MARKER 50. REHABILITATE PAVEMENT AND PRESERVE BRIDGES 100352, 100356, 100344, 100347, 100339, AND 100334. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 13850000 | FY 2023: 4790000; FY 2024: 6444000; FY 2025: 2616000
I-5890 | HIGHWAY | I-40 | MILEMARKER 55 TO MILEMARKER 67.5. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033. | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 23160000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000
I-5890 | HIGHWAY | I-40 | MILEMARKER 55 TO MILEMARKER 67.5. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033. | STATEWIDE MOBILITY |  |  |  | 15125000
I-5898 | HIGHWAY | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  |  |  | 937000
I-5898 | HIGHWAY | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | T | RIGHT-OF-WAY | 1500000 | FY 2023: 700000; FY 2024: 700000
I-5898 | HIGHWAY | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | T | UTILITIES | 1600000 | FY 2023: 800000
I-5898 | HIGHWAY | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | T | CONSTRUCTION | 14000000 | FY 2025: 6726000; FY 2026: 6781000; FY 2027: 493000
I-5900 | HIGHWAY | I-40 | MILE MARKER 73 TO MILE MARKER 81. PAVEMENT REHABILITATION. | 13 | Foothills RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 10750000 | FY 2027: 3872000; FY 2028: 5098000; FY 2029: 1780000
I-5900 | HIGHWAY | I-40 | MILE MARKER 73 TO MILE MARKER 81. PAVEMENT REHABILITATION. | 13 | Foothills RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 14349000 | FY 2027: 5168000; FY 2028: 6805000; FY 2029: 2376000
I-5900 | HIGHWAY | I-40 | MILE MARKER 73 TO MILE MARKER 81. PAVEMENT REHABILITATION. | 13 | Foothills RPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5901 | HIGHWAY | I-240 | MILEMARKER 4 TO MILEMARKER 9. PAVEMENT REHABILITATION. | 13 | French Broad River MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 20906000 | FY 2025: 7252000; FY 2026: 9708000; FY 2027: 3946000
I-5901 | HIGHWAY | I-240 | MILEMARKER 4 TO MILEMARKER 9. PAVEMENT REHABILITATION. | 13 | French Broad River MPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5904 | HIGHWAY | I-485 | BLAIR ROAD TO IDLEWILD ROAD. PAVEMENT REHABILITATION | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  |  |  | 660000
I-5904 | HIGHWAY | I-485 | BLAIR ROAD TO IDLEWILD ROAD. PAVEMENT REHABILITATION | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 7785000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000
I-5904 | HIGHWAY | I-485 | BLAIR ROAD TO IDLEWILD ROAD. PAVEMENT REHABILITATION | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 2016000
I-5905 | HIGHWAY | I-85 | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGDA | CONSTRUCTION | 13217000 | FY 2023: 3949000
I-5905 | HIGHWAY | I-85 | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 100000
I-5905 | HIGHWAY | I-85 | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 3304000 | FY 2023: 987000
I-5905 | HIGHWAY | I-85 | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 1067000 | FY 2023: 319000
I-5907 | HIGHWAY | I-74 | I-77 TO US 601. PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10000
I-5907 | HIGHWAY | I-74 | I-77 TO US 601. PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 5543000 | FY 2023: 4906000
I-5912 | HIGHWAY | I-77 | US 21 IN YADKIN COUNTY (EXIT 79) TO MILEMARKER 83.4 IN SURRY COUNTY . PAVEMENT REHABILITATION. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 57425000
I-5915 | HIGHWAY | I-40 | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT AND BRIDGE REHABILITATION. | 12 | Charlotte Regional TPO, Greater Hickory MPO | [5 empty] | 13150000
I-5915B | HIGHWAY | I-40 | BRIDGE REHABILITATION. | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 2153000 | FY 2023: 1065000; FY 2024: 1088000
I-5915B | HIGHWAY | I-40 | BRIDGE REHABILITATION. | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 2368000 | FY 2023: 1171000; FY 2024: 1197000
I-5915B | HIGHWAY | I-40 | BRIDGE REHABILITATION. | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGDA | CONSTRUCTION | 7319000 | FY 2023: 3620000; FY 2024: 3699000
I-5918 | HIGHWAY | I-77 | MILEMARKER 36.5 TO MILEMARKER 50.0. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 24400000 | FY 2025: 10440000; FY 2026: 11070000; FY 2027: 2890000
I-5918 | HIGHWAY | I-77 | MILEMARKER 36.5 TO MILEMARKER 50.0. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5919 | HIGHWAY | I-77 | MILEMARKER 53.7 TO MILEMARKER 56.8. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5919 | HIGHWAY | I-77 | MILEMARKER 53.7 TO MILEMARKER 56.8. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 10500000 | FY 2025: 4227000; FY 2026: 6273000
I-5920 | HIGHWAY | I-77 | MILE MARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3820000 | FY 2028: 1349000; FY 2029: 1888000; FY 2030: 583000
I-5920 | HIGHWAY | I-77 | MILE MARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5920 | HIGHWAY | I-77 | MILE MARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | 12 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 15459000 | FY 2028: 5459000; FY 2029: 7640000; FY 2030: 2360000
I-5921 | HIGHWAY | I-85 | CLEVELAND COUNTY LINE TO MILE MARKER 14. PAVEMENT REHABILITATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 16830000 | FY 2025: 4597000; FY 2026: 9503000; FY 2027: 2730000
I-5921 | HIGHWAY | I-85 | CLEVELAND COUNTY LINE TO MILE MARKER 14. PAVEMENT REHABILITATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5924 | HIGHWAY | I-40 | MILE MARKER 15 TO MILE MARKER 20.5. PAVEMENT REHABILITATION. | 14 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5924 | HIGHWAY | I-40 | MILE MARKER 15 TO MILE MARKER 20.5. PAVEMENT REHABILITATION. | 14 | Land-of-Sky RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 10900000 | FY 2028: 3628000; FY 2029: 5806000; FY 2030: 1466000
I-5925 | HIGHWAY | I-26 | MILE MARKER 50 TO POLK COUNTY LINE. PAVEMENT REHABILITATION. | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  |  |  | 1000000
I-5925 | HIGHWAY | I-26 | MILE MARKER 50 TO POLK COUNTY LINE. PAVEMENT REHABILITATION. | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 15199000 | FY 2025: 5057000; FY 2026: 8105000; FY 2027: 2037000
I-5926 | HIGHWAY | I-26 | HENDERSON COUNTY LINE TO MILE MARKER 65. PAVEMENT REHABILITATION. | 14 | Foothills RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 13999000 | FY 2025: 4658000; FY 2026: 7465000; FY 2027: 1876000
I-5927 | HIGHWAY | I-26 | MILE MARKER 65 TO SOUTH CAROLINA STATE LINE. PAVEMENT REHABILITATION. | 14 | Foothills RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 1000000
I-5927 | HIGHWAY | I-26 | MILE MARKER 65 TO SOUTH CAROLINA STATE LINE. PAVEMENT REHABILITATION. | 14 | Foothills RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 19600000 | FY 2023: 5703000; FY 2024: 9693000; FY 2025: 4204000
I-5928 | HIGHWAY | I-40 | MILE MARKER 34 TO BUNCOMBE COUNTY LINE. PAVEMENT REHABILITATION. | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 8440000 | FY 2028: 3345000; FY 2029: 4672000; FY 2030: 423000
I-5928 | HIGHWAY | I-40 | MILE MARKER 34 TO BUNCOMBE COUNTY LINE. PAVEMENT REHABILITATION. | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 311000 | FY 2028: 123000; FY 2029: 172000; FY 2030: 16000
I-5928 | HIGHWAY | I-40 | MILE MARKER 34 TO BUNCOMBE COUNTY LINE. PAVEMENT REHABILITATION. | 14 | French Broad River MPO |  | STATEWIDE MOBILITY |  |  |  | 1000000
I-5932 | HIGHWAY | I-95 | NC 481 (MILE MARKER 154) TO MILE MARKER 167. PAVEMENT REHABILITATION. | 4 | Peanut Belt RPO | [5 empty] | 110000
I-5932A | HIGHWAY | I-95 | NC 561 (MILE MARKER 160) TO MILE MARKER 167. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 7376000 | FY 2023: 1371000
I-5932B | HIGHWAY | I-95 | NC 481 (MILE MARKER 154) TO NC 561 (MILE MARKER 160). | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 7823000 | FY 2023: 1454000
I-5934 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) (MILE MARKER 137.4) TO SR 1544 (NORTH HALIFAX ROAD) (MILE MARKER 142.1). PAVEMENT AND BRIDGE REHABILITATION. | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5934 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) (MILE MARKER 137.4) TO SR 1544 (NORTH HALIFAX ROAD) (MILE MARKER 142.1). PAVEMENT AND BRIDGE REHABILITATION. | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 1070000 | FY 2024: 414000; FY 2025: 656000
I-5934 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) (MILE MARKER 137.4) TO SR 1544 (NORTH HALIFAX ROAD) (MILE MARKER 142.1). PAVEMENT AND BRIDGE REHABILITATION. | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 4380000 | FY 2024: 1694000; FY 2025: 2686000
I-5936 | HIGHWAY | I-95 | JOHNSTON COUNTY LINE (MILE MARKER 108.2) TO NORTH OF SR 1116 (GOVERNOR HUNT ROAD) (MILE MARKER 114.5). PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 1000
I-5936 | HIGHWAY | I-95 | JOHNSTON COUNTY LINE (MILE MARKER 108.2) TO NORTH OF SR 1116 (GOVERNOR HUNT ROAD) (MILE MARKER 114.5). PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3303000
I-5938 | HIGHWAY | I-74 | NC 710 TO NC 41. PAVEMENT AND BRIDGE REHABILITATION. | 6 | Lumber River RPO |  | STATEWIDE MOBILITY |  |  |  | 19142000
I-5939 | HIGHWAY | I-95 | SOUTH CAROLINA STATE LINE (MILE MARKER 0.0) TO I-74 (MILE MARKER 13). PAVEMENT REHABILITATION. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10000
I-5939 | HIGHWAY | I-95 | SOUTH CAROLINA STATE LINE (MILE MARKER 0.0) TO I-74 (MILE MARKER 13). PAVEMENT REHABILITATION. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGIM | CONSTRUCTION | 20098000 | FY 2023: 6006000
I-5940 | HIGHWAY | I-40 | DUPLIN COUNTY LINE (MILE MARKER 360) TO WEST OF US 117 (MILE MARKER 390). PAVEMENT AND BRIDGE REHABILITATION. | 3 | Eastern Carolina RPO, Cape Fear RPO | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 13159000
I-5940 | HIGHWAY | I-40 | DUPLIN COUNTY LINE (MILE MARKER 360) TO WEST OF US 117 (MILE MARKER 390). PAVEMENT AND BRIDGE REHABILITATION. | 3 | Eastern Carolina RPO, Cape Fear RPO | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGIM | CONSTRUCTION | 500000 | FY 2023: 500000
I-5940 | HIGHWAY | I-40 | DUPLIN COUNTY LINE (MILE MARKER 360) TO WEST OF US 117 (MILE MARKER 390). PAVEMENT AND BRIDGE REHABILITATION. | 3 | Eastern Carolina RPO, Cape Fear RPO | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGIM | GARVEE CON | 28826000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000
I-5941 | HIGHWAY | I-85 | ORANGE COUNTY LINE TO US 15 / US 501 IN DURHAM. PAVEMENT REHABILITATION | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 11880000 | FY 2024: 5539000; FY 2025: 5379000; FY 2026: 962000
I-5941 | HIGHWAY | I-85 | ORANGE COUNTY LINE TO US 15 / US 501 IN DURHAM. PAVEMENT REHABILITATION | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 4920000 | FY 2024: 2294000; FY 2025: 2228000; FY 2026: 398000
I-5943 | HIGHWAY | I-40 | SR 1728 (WADE AVENUE) TO I-440 / US 1 IN RALEIGH. PAVEMENT AND BRIDGE REHABILITATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 10000
I-5943 | HIGHWAY | I-40 | SR 1728 (WADE AVENUE) TO I-440 / US 1 IN RALEIGH. PAVEMENT AND BRIDGE REHABILITATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 18419000 | FY 2023: 10608000; FY 2024: 2616000
I-5944 | HIGHWAY | I-87 / US 64 / US 264 | I-440 IN RALEIGH TO SR 1003 (ROLESVILLE ROAD). PAVEMENT REHABILITATION. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 12350000 | FY 2029: 5102000; FY 2030: 5248000; FY 2031: 2000000
I-5944 | HIGHWAY | I-87 / US 64 / US 264 | I-440 IN RALEIGH TO SR 1003 (ROLESVILLE ROAD). PAVEMENT REHABILITATION. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 16250000 | FY 2029: 6713000; FY 2030: 6905000; FY 2031: 2632000
I-5945 | HIGHWAY | I-540 | TRIANGLE TOWNE CENTER BOULEVARD IN RALEIGH TO I-495 / US 64 / US 264 IN KNIGHTDALE. PAVEMENT REHABILITATION. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 11650000 | FY 2029: 4460000; FY 2030: 4957000; FY 2031: 2233000
I-5945 | HIGHWAY | I-540 | TRIANGLE TOWNE CENTER BOULEVARD IN RALEIGH TO I-495 / US 64 / US 264 IN KNIGHTDALE. PAVEMENT REHABILITATION. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 16250000 | FY 2029: 6221000; FY 2030: 6914000; FY 2031: 3115000
I-5946 | HIGHWAY | I-73 / I-74 | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | 8 | Lumber River RPO | [5 empty] | 3718000
I-5946B | HIGHWAY | I-73/I-74 | SR 1455 (FIRE TOWER ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | 8 | Lumber River RPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | BGIM | CONSTRUCTION | 6812000 | FY 2023: 1430000
I-5947 | HIGHWAY | I-73 / I-74 / US 220 | MONTGOMERY COUNTY LINE TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO | [5 empty] | 4735000
I-5947A | HIGHWAY | I-73/74 | MONTGOMERY COUNTY LINE TO NC 211. PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO |  | STATEWIDE MOBILITY |  | BGIM | CONSTRUCTION | 15901000 | FY 2025: 6362000; FY 2026: 8816000; FY 2027: 723000
I-5947B | HIGHWAY | I-73/74 | NC 211 TO NC 24/27. PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - LET WITH I-5946A | STATEWIDE MOBILITY |  | BGIM | CONSTRUCTION | 6900000 | FY 2023: 5500000; FY 2024: 1400000
I-5947C | HIGHWAY | I-73/74 | NC 24/27 TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO |  | STATEWIDE MOBILITY |  | BGIM | CONSTRUCTION | 13600000 | FY 2026: 6112000; FY 2027: 7488000
I-5948 | HIGHWAY | I-73 / I-74 / US 220 | MONTGOMERY COUNTY LINE TO NORTH OF SR 1462 (PARK DRIVE) IN ASHEBORO. PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO |  | STATEWIDE MOBILITY |  |  |  | 832000
I-5948 | HIGHWAY | I-73 / I-74 / US 220 | MONTGOMERY COUNTY LINE TO NORTH OF SR 1462 (PARK DRIVE) IN ASHEBORO. PAVEMENT REHABILITATION. | 8 | Piedmont Triad RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 17001000 | FY 2026: 6030000; FY 2027: 9103000; FY 2028: 1868000
I-5950 | HIGHWAY | I-85 | I-285 / US 29 / US 52 / US 70 TO NORTH OF US 64. PAVEMENT REHABILITATION. | 9 | High Point Urban Area MPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5950 | HIGHWAY | I-85 | I-285 / US 29 / US 52 / US 70 TO NORTH OF US 64. PAVEMENT REHABILITATION. | 9 | High Point Urban Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 28542000 | FY 2023: 16717000; FY 2024: 11540000
I-5952 | HIGHWAY | I-40 | SR 1101 (HARPER ROAD) IN CLEMMONS TO EAST OF US 421 / BUSINESS 40 IN WINSTON-SALEM. PAVEMENT REHABILITATION. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION. DELETE I-5952A. WORK ACCOMPLISHED UNDER I-5795. | STATEWIDE MOBILITY |  |  |  | 20204000
I-5953 | HIGHWAY | I-785 / I-840 | I-85 TO US 70. PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 2675000
I-5954 | HIGHWAY | I-40 / I-85 | EAST OF NC 54 IN GRAHAM IN ALAMANCE COUNTY TO WEST OF SR 1114 (BUCKHORN ROAD) IN ORANGE COUINTY. PAVEMENT REHABILITATION. | 7 | Burlington-Graham MPO | COMPLETED | STATEWIDE MOBILITY |  |  |  | 11179000
I-5955 | HIGHWAY | I-40 | SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356 | STATEWIDE MOBILITY |  |  |  | 150000
I-5955 | HIGHWAY | I-40 | SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. PAVEMENT REHABILITATION. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356 | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 8900000 | FY 2023: 90000; FY 2024: 6649000; FY 2025: 2161000
I-5955A | HIGHWAY | I-40 | I-40, SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. REHABILITATE BRIDGES 400678, 400367, 400364, 400357, 400349, 400348, 400340, 400339, 400336, 400329, 400327, 400299, 400291, AND 400285. | 7 | Greensboro Urban Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 10100000 | FY 2024: 101000; FY 2025: 7546000; FY 2026: 2453000
I-5956 | HIGHWAY | I-40 / I-85 | EAST OF SR 3056 (ROCK CREEK DAIRY ROAD) IN GUILFORD COUNTY TO WEST OF SR 1226 (UNIVERSITY DRIVE) IN ALAMANCE COUNTY. PAVEMENT REHABILITATION. | 7 | Burlington-Graham MPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 4702000
I-5958 | HIGHWAY | I-40 / I-85 | WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1006 (ORANGE GROVE ROAD). PAVEMENT REHABILITATION. | 7 | Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO |  | STATEWIDE MOBILITY |  |  |  | 150000
I-5958 | HIGHWAY | I-40 / I-85 | WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1006 (ORANGE GROVE ROAD). PAVEMENT REHABILITATION. | 7 | Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 8750000 | FY 2027: 6440000; FY 2028: 2310000
I-5958 | HIGHWAY | I-40 / I-85 | WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1006 (ORANGE GROVE ROAD). PAVEMENT REHABILITATION. | 7 | Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 750000 | FY 2027: 552000; FY 2028: 198000
I-5962 | HIGHWAY | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | STATEWIDE MOBILITY |  |  |  | 2500000
I-5962 | HIGHWAY | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 3000000 | FY 2027: 30000; FY 2028: 1000000; FY 2029: 1370000; FY 2030: 300000; FY 2031: 300000
I-5962 | HIGHWAY | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | STATEWIDE MOBILITY |  | NHP | UTILITIES | 500000 | FY 2027: 500000
I-5962 | HIGHWAY | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 33861000 | FY 2029: 339000; FY 2030: 13855000; FY 2031: 13271000; FY 2032: 6396000
I-5962 | HIGHWAY | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 2240000 | FY 2029: 22000; FY 2030: 917000; FY 2031: 878000; FY 2032: 423000
I-5963 | HIGHWAY | I-485 | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 28899000
I-5963 | HIGHWAY | I-485 | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 6200000
I-5963 | HIGHWAY | I-485 | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 11100000
I-5963 | HIGHWAY | I-485 | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1300000
I-5964 | HIGHWAY | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | ELM-EUGENE STREET IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 575000 | FY 2023: 200000; FY 2024: 375000
I-5964 | HIGHWAY | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | ELM-EUGENE STREET IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 250000
I-5965 | HIGHWAY | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1000000
I-5965 | HIGHWAY | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 11000000
I-5965 | HIGHWAY | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3732000
I-5965 | HIGHWAY | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 109200000
I-5966 | HIGHWAY | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 700000 | FY 2028: 700000
I-5966 | HIGHWAY | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHP | UTILITIES | 138000 | FY 2028: 138000
I-5966 | HIGHWAY | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  |  |  | 500000
I-5966 | HIGHWAY | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 47701000 | FY 2031: 15103000; FY 2032: 18123000; FY 2033: 11835000 | 2640000
I-5967 | HIGHWAY | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  |  |  | 1000000
I-5967 | HIGHWAY | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 52800000 | FY 2028: 7040000; FY 2029: 16896000; FY 2030: 16896000; FY 2031: 1408000; FY 2032: 10560000
I-5967 | HIGHWAY | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | UTILITIES | 1200000 | FY 2028: 600000; FY 2029: 600000
I-5967 | HIGHWAY | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 57200000 | FY 2031: 22623000; FY 2032: 21630000; FY 2033: 10327000 | 2620000
I-5968 | HIGHWAY | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHP | UTILITIES | 10000 | FY 2028: 10000
I-5968 | HIGHWAY | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 20502000 | FY 2030: 7409000; FY 2031: 10012000; FY 2032: 3081000
I-5968 | HIGHWAY | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  |  |  | 1140000
I-5968 | HIGHWAY | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 3200000 | FY 2028: 819000; FY 2029: 1229000; FY 2030: 512000; FY 2031: 320000; FY 2032: 320000
I-5970 | HIGHWAY | I-440 / US 1 | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 200000
I-5970 | HIGHWAY | I-440 / US 1 | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 48399000
I-5970 | HIGHWAY | I-440 / US 1 | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3300000
I-5970 | HIGHWAY | I-440 / US 1 | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 89899000
I-5971 | HIGHWAY | I-40 | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | 13 | Greater Hickory MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2300000
I-5971 | HIGHWAY | I-40 | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | 13 | Greater Hickory MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1300000
I-5971 | HIGHWAY | I-40 | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | 13 | Greater Hickory MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 200000
I-5971 | HIGHWAY | I-40 | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | 13 | Greater Hickory MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 21500000
I-5972 | HIGHWAY | I-95 | US 70 BUSINESS. UPGRADE INTERCHANGE. | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS | REGION A |  |  |  | 4700000
I-5972 | HIGHWAY | I-95 | US 70 BUSINESS. UPGRADE INTERCHANGE. | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS | REGION A |  | NHFP | CONSTRUCTION | 9732000 | FY 2024: 4088000; FY 2025: 4184000; FY 2026: 1460000
I-5972 | HIGHWAY | I-95 | US 70 BUSINESS. UPGRADE INTERCHANGE. | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS | REGION A |  | NHP | CONSTRUCTION | 24768000 | FY 2024: 10402000; FY 2025: 10651000; FY 2026: 3715000
I-5973 | HIGHWAY | I-485 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3.5M FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | REGION E |  | T | BUILD NC CON | 4500000 | 600000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 900000
I-5973 | HIGHWAY | I-485 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3.5M FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | REGION E |  | T | CONSTRUCTION | 3500000 | FY 2023: 0; FY 2024: 2370000; FY 2025: 1130000
I-5973 | HIGHWAY | I-485 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3.5M FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | REGION E |  |  |  | 2200000
I-5973 | HIGHWAY | I-485 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3.5M FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | REGION E |  | T | UTILITIES | 195000
I-5974 | HIGHWAY | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | REGION A |  |  |  | 2000000
I-5974 | HIGHWAY | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | REGION A |  | NHP | RIGHT-OF-WAY | 13695000 | FY 2026: 4383000; FY 2027: 6574000; FY 2028: 0; FY 2029: 1369000; FY 2030: 1369000
I-5974 | HIGHWAY | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | REGION A |  | NHP | UTILITIES | 2026000 | FY 2026: 1013000; FY 2027: 1013000
I-5974 | HIGHWAY | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | REGION A |  | NHP | CONSTRUCTION | 48399000 | FY 2028: 17519000; FY 2029: 18360000; FY 2030: 12520000
I-5975 | HIGHWAY | I-40 | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | UTILITIES | 100000 | [11 empty] | 100000
I-5975 | HIGHWAY | I-40 | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 5200000 | [11 empty] | 5200000
I-5975 | HIGHWAY | I-40 | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 2660000 | [11 empty] | 2660000
I-5975 | HIGHWAY | I-40 | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 13 | Greater Hickory MPO |  | NOT FUNDED |  |  |  | 2400000
I-5979 | HIGHWAY | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | NHP | RIGHT-OF-WAY | 500000
I-5979 | HIGHWAY | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | NHP | UTILITIES | 210000
I-5979 | HIGHWAY | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | NHP | CONSTRUCTION | 6700000 | FY 2024: 5297000; FY 2025: 1403000
I-5979 | HIGHWAY | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  |  |  | 1092000
I-5980 | HIGHWAY | I-40 | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 7 | High Point Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 33700000
I-5980 | HIGHWAY | I-40 | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 7 | High Point Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1000000
I-5980 | HIGHWAY | I-40 | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 7 | High Point Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3400000
I-5980 | HIGHWAY | I-40 | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 7 | High Point Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3824000
I-5981 | HIGHWAY | I-40 | I-74 US 311 IN WINSTON-SALEM TO US 421 / BUSINESS 40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 7, 9 | Winston-Salem Urban Area MPO, High Point Urban Area MPO | [5 empty] | 2010000
I-5981A | HIGHWAY | I-40 | I-74 / US 311 TO SR 2643 (UNION CROSS ROAD). | 9 | Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 5300000
I-5981A | HIGHWAY | I-40 | I-74 / US 311 TO SR 2643 (UNION CROSS ROAD). | 9 | Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1100000
I-5981A | HIGHWAY | I-40 | I-74 / US 311 TO SR 2643 (UNION CROSS ROAD). | 9 | Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 61293000
I-5981B | HIGHWAY | I-40 | SR 2643 (UNION CROSS ROAD) TO NC 66. | 9 | Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1200000
I-5981B | HIGHWAY | I-40 | SR 2643 (UNION CROSS ROAD) TO NC 66. | 9 | Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1000000
I-5981B | HIGHWAY | I-40 | SR 2643 (UNION CROSS ROAD) TO NC 66. | 9 | Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 38194000
I-5981C | HIGHWAY | I-40 | NC 66 TO US 421 / BUSINESS 40. | 7, 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 200000
I-5981C | HIGHWAY | I-40 | NC 66 TO US 421 / BUSINESS 40. | 7, 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 200000
I-5981C | HIGHWAY | I-40 | NC 66 TO US 421 / BUSINESS 40. | 7, 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 38798000
I-5984 | HIGHWAY | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-305 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1000000
I-5984 | HIGHWAY | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-305 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 58200000
I-5984 | HIGHWAY | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-305 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2100000
I-5984 | HIGHWAY | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-305 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 44099000
I-5985 | HIGHWAY | I-85 | SOUTH CAROLINA STATE LINE TO US 321. ADD ADDITIONAL LANES. | 12 | Gaston-Cleveland-Lincoln MPO | [5 empty] | 2000000
I-5985A | HIGHWAY | I-85 | SOUTH CAROLINA STATE LINE TO US 74 | 12 | Gaston-Cleveland-Lincoln MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 150300000
I-5985A | HIGHWAY | I-85 | SOUTH CAROLINA STATE LINE TO US 74 | 12 | Gaston-Cleveland-Lincoln MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3500000
I-5985A | HIGHWAY | I-85 | SOUTH CAROLINA STATE LINE TO US 74 | 12 | Gaston-Cleveland-Lincoln MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 3200000
I-5985B | HIGHWAY | I-85 | US 74 TO US 321 | 12 | Gaston-Cleveland-Lincoln MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 4900000
I-5985B | HIGHWAY | I-85 | US 74 TO US 321 | 12 | Gaston-Cleveland-Lincoln MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 219400000
I-5985B | HIGHWAY | I-85 | US 74 TO US 321 | 12 | Gaston-Cleveland-Lincoln MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 8800000
I-5986 | HIGHWAY | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 4, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Upper Coastal Plain RPO | [5 empty] | 143850000
I-5986A | HIGHWAY | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 375400000 | FY 2023: 93850000
I-5986A | HIGHWAY | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 30400000
I-5986A | HIGHWAY | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | STATEWIDE MOBILITY |  | T | UTILITIES | 2000000 | FY 2023: 500000; FY 2024: 1500000
I-5986B | HIGHWAY | I-95 | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 92456000 | FY 2023: 0; FY 2024: 21336000; FY 2025: 21337000; FY 2026: 17000000; FY 2027: 4420000
I-5986B | HIGHWAY | I-95 | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 42100000
I-5986B | HIGHWAY | I-95 | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | STATEWIDE MOBILITY |  | T | UTILITIES | 700000
I-5986BA | HIGHWAY | I-95 | SR 1001 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). CLEARING FOR UTILITIES. | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 144000
I-5986C | HIGHWAY | I-95 | INSTALL BROADBAND FIBER ALONG I-95 FROM SOUTH CAROLINA LINE TO VIRGINIA STATE LINE. | 1, 4, 6 | Upper Coastal Plain RPO, Lumber River RPO, Peanut Belt RPO, Fayetteville Area MPO, Mid-Carolina RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 16600000 | FY 2023: 4764000
I-5986C | HIGHWAY | I-95 | INSTALL BROADBAND FIBER ALONG I-95 FROM SOUTH CAROLINA LINE TO VIRGINIA STATE LINE. | 1, 4, 6 | Upper Coastal Plain RPO, Lumber River RPO, Peanut Belt RPO, Fayetteville Area MPO, Mid-Carolina RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 11067000 | FY 2023: 3176000
I-5987 | HIGHWAY | I-95 | SOUTH OF US 301 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO, Fayetteville Area MPO | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | REGION C |  |  |  | 1010000
I-5987A | HIGHWAY | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | CONSTRUCTION | 203079000 | FY 2023: 0; FY 2024: 35472000; FY 2025: 68179000; FY 2026: 56816000; FY 2027: 42612000
I-5987A | HIGHWAY | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | BUILD NC CON | 41190000 |  | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 13730000
I-5987A | HIGHWAY | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | RIGHT-OF-WAY | 3395000
I-5987A | HIGHWAY | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | UTILITIES | 3075000 | FY 2023: 700000; FY 2024: 1500000
I-5987A | HIGHWAY | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | BUILD NC CON | 63060000 | 8408000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 12612000
I-5987AA | HIGHWAY | I-95 | CONSTRUCT WEIGH IN MOTION STATION. | 6 | Lumber River RPO | O FUNDS REPRESENT STATE PRIMARY MAINTENANCE FUNDS FOR WEIGH STATIONS. | REGION C |  | O | CONSTRUCTION | 2400000 | FY 2025: 2400000
I-5987B | HIGHWAY | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | RIGHT-OF-WAY | 3581000
I-5987B | HIGHWAY | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | UTILITIES | 2300000
I-5987B | HIGHWAY | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | BUILD NC CON | 63060000 | 8408000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 4204000 | 12612000
I-5987B | HIGHWAY | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | BUILD NC CON | 41190000 |  | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 2746000 | 13730000
I-5987B | HIGHWAY | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $49,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | REGION C |  | T | CONSTRUCTION | 244369000 | FY 2023: 16074000; FY 2024: 49342000; FY 2025: 71581000; FY 2026: 61820000; FY 2027: 45552000
I-5987C | HIGHWAY | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 6 | Lumber River RPO, Fayetteville Area MPO |  | REGION C |  | DP | ENGINEERING | 250000
I-5987C | HIGHWAY | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 6 | Lumber River RPO, Fayetteville Area MPO |  | REGION C |  | T | ENGINEERING | 65000
I-5990 | HIGHWAY | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | NHP | CONSTRUCTION | 9600000 | FY 2024: 96000; FY 2025: 6328000; FY 2026: 3176000
I-5990 | HIGHWAY | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  |  |  | 2010000
I-5990 | HIGHWAY | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | NHP | RIGHT-OF-WAY | 2500000 | FY 2023: 25000; FY 2024: 1975000; FY 2025: 250000; FY 2026: 250000
I-5990 | HIGHWAY | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | NHP | UTILITIES | 1100000 | FY 2023: 550000; FY 2024: 550000
I-5991 | HIGHWAY | I-40 | US 321 TO NC 16. WIDEN TO SIX LANES. | 12 | Greater Hickory MPO | [5 empty] | 500000
I-5991A | HIGHWAY | I-40 | US 321 TO SR 1476 (FAIRGROVE CHURCH ROAD). WIDEN TO SIX LANES. | 12 | Greater Hickory MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 69300000
I-5991A | HIGHWAY | I-40 | US 321 TO SR 1476 (FAIRGROVE CHURCH ROAD). WIDEN TO SIX LANES. | 12 | Greater Hickory MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 600000
I-5991B | HIGHWAY | I-40 | SR 1476 (FAIRGROVE CHURCH ROAD) TO NC 16. WIDEN TO SIX LANES. | 12 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 4600000 | [11 empty] | 4600000
I-5991B | HIGHWAY | I-40 | SR 1476 (FAIRGROVE CHURCH ROAD) TO NC 16. WIDEN TO SIX LANES. | 12 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 85000000 | [11 empty] | 85000000
I-5992 | HIGHWAY | I-77 | MILE MARKER 11 TO MILE MARKER 20 AND MILE MARKER 24.5 TO MILE MARKER 37. REHABILITATE PAVEMENT. | 10, 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  |  |  | 25600000
I-5993 | HIGHWAY | I-40 | US 15 / US 501 TO EAST OF NC 147. PAVEMENT REHABILITATION. | 5 | Durham-Chapel Hill-Carrboro MPO | TO BE LET WITH I-5994 | STATEWIDE MOBILITY |  |  |  | 10000
I-5993 | HIGHWAY | I-40 | US 15 / US 501 TO EAST OF NC 147. PAVEMENT REHABILITATION. | 5 | Durham-Chapel Hill-Carrboro MPO | TO BE LET WITH I-5994 | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 37326000 | FY 2026: 5000000; FY 2027: 17000000; FY 2028: 15326000
I-5995 | HIGHWAY | I-40 | EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | Combined with I-5996. | STATEWIDE MOBILITY |  |  |  | 10000
I-5995 | HIGHWAY | I-40 | EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | Combined with I-5996. | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 11880000 | FY 2026: 5312000; FY 2027: 5589000; FY 2028: 979000
I-5995 | HIGHWAY | I-40 | EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | Combined with I-5996. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 20520000 | FY 2026: 9175000; FY 2027: 9654000; FY 2028: 1691000
I-5997 | HIGHWAY | I-440 / US 1 | SR 1728 (WADE AVENUE) TO SR 2000 (WAKE FOREST ROAD) IN RALEIGH. PAVEMENT REHABILITATION. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-5997 | HIGHWAY | I-440 / US 1 | SR 1728 (WADE AVENUE) TO SR 2000 (WAKE FOREST ROAD) IN RALEIGH. PAVEMENT REHABILITATION. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 23100000 | FY 2024: 15000000; FY 2025: 8100000
I-5998 | HIGHWAY | I-540 | I-40 IN DURHAM TO US 70 IN RALEIGH. PAVEMENT REHABILITATION. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5999 AND I-6000 | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 14999000 | FY 2026: 6874000; FY 2027: 6960000; FY 2028: 1165000
I-5999 | HIGHWAY | I-540 | US 70 (GLENWOOD AVENUE) TO EAST OF TRIANGLE TOWN BOULEVARD IN RALEIGH. PAVEMENT REHABILITATION. | 5 | Capital Area MPO | COORDINATE WITH I-5998 AND I-6000; | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 12000000 | FY 2024: 10000000; FY 2025: 2000000
I-6000 | HIGHWAY | I-540 | I-40 IN DURHAM TO US 1 IN RALEIGH. BRIDGE PRESERVATION / REHABILITATION. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5998 AND I-5999 | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 7600000 | FY 2027: 5542000; FY 2028: 2058000
I-6000 | HIGHWAY | I-540 | I-40 IN DURHAM TO US 1 IN RALEIGH. BRIDGE PRESERVATION / REHABILITATION. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5998 AND I-5999 | STATEWIDE MOBILITY |  |  |  | 10000
I-6001 | HIGHWAY | I-87 / FUTURE I-87 / US 64 / US 264 | SR 1003 (ROLESVILLE ROAD) TO NASH COUNTY LINE. PAVEMENT REHABILITATION. | 5 | Capital Area MPO, Kerr-Tar RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 9000000 | FY 2025: 1500000; FY 2026: 4500000; FY 2027: 3000000
I-6001 | HIGHWAY | I-87 / FUTURE I-87 / US 64 / US 264 | SR 1003 (ROLESVILLE ROAD) TO NASH COUNTY LINE. PAVEMENT REHABILITATION. | 5 | Capital Area MPO, Kerr-Tar RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 21000000 | FY 2025: 3500000; FY 2026: 10500000; FY 2027: 7000000
I-6003 | HIGHWAY | I-40 | SR 1436 (PINEBROOK SCHOOL ROAD) TO WEST OF NC 801. PAVEMENT REHABILITATION. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 7677000 | FY 2023: 1216000
I-6004 | HIGHWAY | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  |  |  | 10000
I-6004 | HIGHWAY | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | NHP | RIGHT-OF-WAY | 1400000 | FY 2026: 420000; FY 2027: 560000; FY 2028: 140000; FY 2029: 140000; FY 2030: 140000
I-6004 | HIGHWAY | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | NHP | UTILITIES | 429000 | FY 2026: 429000
I-6004 | HIGHWAY | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | NHP | CONSTRUCTION | 10900000 | FY 2027: 6842000; FY 2028: 4058000
I-6005 | HIGHWAY | I-87 / US 64 / US 264 | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 167000
I-6005 | HIGHWAY | I-87 / US 64 / US 264 | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 2700000
I-6005 | HIGHWAY | I-87 / US 64 / US 264 | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 100000
I-6005 | HIGHWAY | I-87 / US 64 / US 264 | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 53699000
I-6006 | HIGHWAY | I-40 SR 1728 (WADE AVENUE) | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 500000
I-6006 | HIGHWAY | I-40 SR 1728 (WADE AVENUE) | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 500000
I-6006 | HIGHWAY | I-40 SR 1728 (WADE AVENUE) | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
I-6006 | HIGHWAY | I-40 SR 1728 (WADE AVENUE) | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 114999000
I-6007 | HIGHWAY | I-87 / US 64 / US 264 | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
I-6007 | HIGHWAY | I-87 / US 64 / US 264 | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4601000
I-6007 | HIGHWAY | I-87 / US 64 / US 264 | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1300000
I-6007 | HIGHWAY | I-87 / US 64 / US 264 | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 16199000
I-6009 | HIGHWAY | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | 7 | Burlington-Graham MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 700000
I-6009 | HIGHWAY | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | 7 | Burlington-Graham MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 100000
I-6009 | HIGHWAY | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | 7 | Burlington-Graham MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
I-6009 | HIGHWAY | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | 7 | Burlington-Graham MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1000000
I-6010 | HIGHWAY | I-85 / US 15 | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  |  |  | 10000
I-6010 | HIGHWAY | I-85 / US 15 | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 10417000 | [11 empty] | 10417000
I-6010 | HIGHWAY | I-85 / US 15 | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | NHP | UTILITIES | 1774000 | [11 empty] | 1774000
I-6010 | HIGHWAY | I-85 / US 15 | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 55301000 | [11 empty] | 55301000
I-6011 | HIGHWAY | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | 6 | Cape Fear RPO, Lumber River RPO |  | NOT FUNDED |  | T | UTILITIES | 1469000 | [11 empty] | 1469000
I-6011 | HIGHWAY | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | 6 | Cape Fear RPO, Lumber River RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 169100000 | [11 empty] | 169100000
I-6011 | HIGHWAY | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | 6 | Cape Fear RPO, Lumber River RPO |  | NOT FUNDED |  |  |  | 10000
I-6011 | HIGHWAY | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | 6 | Cape Fear RPO, Lumber River RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 179000 | [11 empty] | 179000
I-6011A | HIGHWAY | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | 6 | Lumber River RPO |  | DIVISION 6 |  | BGLT5 | UTILITIES | 352000 | FY 2025: 352000
I-6011A | HIGHWAY | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | 6 | Lumber River RPO |  | DIVISION 6 |  | BGLT5 | CONSTRUCTION | 7400000 | FY 2027: 2579000; FY 2028: 4821000
I-6011A | HIGHWAY | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | 6 | Lumber River RPO |  | DIVISION 6 |  | BGLT5 | RIGHT-OF-WAY | 55000 | FY 2025: 55000
I-6012 | HIGHWAY | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1800000
I-6012 | HIGHWAY | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 11500000
I-6012 | HIGHWAY | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 200000
I-6012 | HIGHWAY | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
I-6013 | HIGHWAY | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 200000
I-6013 | HIGHWAY | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 16000000
I-6013 | HIGHWAY | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 900000
I-6014 | HIGHWAY | I-77 | I-85 INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 96100000
I-6014 | HIGHWAY | I-77 | I-85 INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1100000
I-6014 | HIGHWAY | I-77 | I-85 INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 500000
I-6015 | HIGHWAY | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHNAGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | CONSTRUCTION | 9999000 | [11 empty] | 9999000
I-6015 | HIGHWAY | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHNAGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 8400000 | [11 empty] | 8400000
I-6015 | HIGHWAY | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHNAGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | UTILITIES | 1100000 | [11 empty] | 1100000
I-6016 | HIGHWAY | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 2600000
I-6016 | HIGHWAY | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1400000
I-6016 | HIGHWAY | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 31900000
I-6017 | HIGHWAY | I-85 | SR 2472 (MALLARD CREEK CHURCH ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 13099000 | [11 empty] | 13099000
I-6017 | HIGHWAY | I-85 | SR 2472 (MALLARD CREEK CHURCH ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 1100000 | [11 empty] | 1100000
I-6017 | HIGHWAY | I-85 | SR 2472 (MALLARD CREEK CHURCH ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | UTILITIES | 1800000 | [11 empty] | 1800000
I-6018 | HIGHWAY | I-40 | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | 13 | French Broad River MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 117200000 | [11 empty] | 117200000
I-6018 | HIGHWAY | I-40 | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | 13 | French Broad River MPO |  | NOT FUNDED |  | NHP | UTILITIES | 700000 | [11 empty] | 700000
I-6018 | HIGHWAY | I-40 | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | 13 | French Broad River MPO |  | NOT FUNDED |  |  |  | 10000
I-6018 | HIGHWAY | I-40 | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | 13 | French Broad River MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 4000000 | [11 empty] | 4000000
I-6019 | HIGHWAY | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 14900000 | [11 empty] | 14900000
I-6019 | HIGHWAY | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | UTILITIES | 4700000 | [11 empty] | 4700000
I-6019 | HIGHWAY | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 20701000 | [11 empty] | 20701000
I-6020 | HIGHWAY | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 10000000 | [11 empty] | 10000000
I-6020 | HIGHWAY | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 15299000 | [11 empty] | 15299000
I-6020 | HIGHWAY | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | UTILITIES | 2000000 | [11 empty] | 2000000
I-6021 | HIGHWAY | I-40 | SR 2838 (PORTERS COVE ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 13 | French Broad River MPO |  | NOT FUNDED |  |  |  | 10000
I-6021 | HIGHWAY | I-40 | SR 2838 (PORTERS COVE ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 13 | French Broad River MPO |  | NOT FUNDED |  | NHP | UTILITIES | 200000 | [11 empty] | 200000
I-6021 | HIGHWAY | I-40 | SR 2838 (PORTERS COVE ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 13 | French Broad River MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 1700000 | [11 empty] | 1700000
I-6022A | HIGHWAY | I-277 | KENILWORTH AVENUE TO NORTH DAVIDSON STREET AND US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO PECAN AVENUE. UPGRADE INTERCHANGES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 250401000 | [11 empty] | 250401000
I-6022A | HIGHWAY | I-277 | KENILWORTH AVENUE TO NORTH DAVIDSON STREET AND US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO PECAN AVENUE. UPGRADE INTERCHANGES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 55600000 | [11 empty] | 55600000
I-6022A | HIGHWAY | I-277 | KENILWORTH AVENUE TO NORTH DAVIDSON STREET AND US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO PECAN AVENUE. UPGRADE INTERCHANGES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | UTILITIES | 1100000 | [11 empty] | 1100000
I-6022B | HIGHWAY | I-277 | NORTH DAVIDSON STREET TO GRAHAM STREET. UPGRADE INTERCHANGES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 49634000 | [11 empty] | 49634000
I-6022B | HIGHWAY | I-277 | NORTH DAVIDSON STREET TO GRAHAM STREET. UPGRADE INTERCHANGES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 49633000 | [11 empty] | 49633000
I-6022B | HIGHWAY | I-277 | NORTH DAVIDSON STREET TO GRAHAM STREET. UPGRADE INTERCHANGES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | UTILITIES | 200000 | [11 empty] | 200000
I-6022B | HIGHWAY | I-277 | NORTH DAVIDSON STREET TO GRAHAM STREET. UPGRADE INTERCHANGES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 49633000 | [11 empty] | 49633000
I-6026 | HIGHWAY | US 17 (FUTURE I-87) | PASQUOTANK COUNTY LINE TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY |  |  |  | 10000
I-6026 | HIGHWAY | US 17 (FUTURE I-87) | PASQUOTANK COUNTY LINE TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 8400000 | FY 2025: 4946000; FY 2026: 3454000
I-6027 | HIGHWAY | US 17 (FUTURE I-87) | BERTIE COUNTY LINE TO PERQUIMANS COUNTY LINE. PAVEMENT REHABILITATION. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3250000 | FY 2029: 2433000; FY 2030: 817000
I-6027 | HIGHWAY | US 17 (FUTURE I-87) | BERTIE COUNTY LINE TO PERQUIMANS COUNTY LINE. PAVEMENT REHABILITATION. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 5000000 | FY 2029: 3743000; FY 2030: 1257000
I-6028 | HIGHWAY | US 13/US 64 (FUTURE I-87) | EDGECOMBE COUNTY LINE TO US 13/17 AND US 64 INTERCHANGE. PAVEMENT REHABILITATION. | 1 | Mid-East RPO | "A" BREAK DELETED, WORK WAS COMPLETED WITH CONTRACT RESURFACING. | STATEWIDE MOBILITY |  |  |  | 10000
I-6028B | HIGHWAY | US 64 (FUTURE I-87) | US 64 ALTERNATE TO NC 125. | 1 | Mid-East RPO | COMPLETED. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 5873000
I-6028C | HIGHWAY | US 64 (FUTURE I-87) | NC 125 TO US 13/17 AND US 64 INTERCHANGE. | 1 | Mid-East RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 6000000 | FY 2023: 1809000
I-6029 | HIGHWAY | US 17 (FUTURE I-87) | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | 1 | Albemarle RPO | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | STATEWIDE MOBILITY |  |  |  | 10000
I-6029 | HIGHWAY | US 17 (FUTURE I-87) | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | 1 | Albemarle RPO | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 5625000
I-6029 | HIGHWAY | US 17 (FUTURE I-87) | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | 1 | Albemarle RPO | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 4125000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000
I-6029 | HIGHWAY | US 17 (FUTURE I-87) | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | 1 | Albemarle RPO | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 2136000
I-6030 | HIGHWAY | US 17 (FUTURE I-87) | SR 1101 (EAST BEAR SWAMP ROAD) TO US 17 BUSINESS NORTH OF HERTFORD. PAVEMENT REHABILITATION. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 5000000 | FY 2025: 5000000
I-6032 | HIGHWAY | US 264 (FUTURE I-587) | PITT COUNTY LINE TO WILSON COUNTY LINE. PAVEMENT REHABILITATION. | 2 | Eastern Carolina RPO | COMPLETED. TO BE LET WITH I-6035. GARVEE BOND FUNDING: $4,020,000 FOR CON, PAYBACK FY 2019-2033. | STATEWIDE MOBILITY |  |  |  | 7165000
I-6032 | HIGHWAY | US 264 (FUTURE I-587) | PITT COUNTY LINE TO WILSON COUNTY LINE. PAVEMENT REHABILITATION. | 2 | Eastern Carolina RPO | COMPLETED. TO BE LET WITH I-6035. GARVEE BOND FUNDING: $4,020,000 FOR CON, PAYBACK FY 2019-2033. | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 4830000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000
I-6035 | HIGHWAY | US 264/US 258 (FUTURE I-587) | GREENE COUNTY LINE TO SR 1467 (STANTONSBURG ROAD) INTERCHANGE (GREENVILLE SOUTHWEST BYPASS). PAVEMENT REHABILITATION. | 2 | Mid-East RPO, Greenville Urban Area MPO | UNDER CONSTRUCTION. TO BE LET WITH I-6032. GARVEE BOND FUNDING $12M FOR CON, PAYBACK FY 2019-2033. | STATEWIDE MOBILITY |  |  |  | 21960000
I-6035 | HIGHWAY | US 264/US 258 (FUTURE I-587) | GREENE COUNTY LINE TO SR 1467 (STANTONSBURG ROAD) INTERCHANGE (GREENVILLE SOUTHWEST BYPASS). PAVEMENT REHABILITATION. | 2 | Mid-East RPO, Greenville Urban Area MPO | UNDER CONSTRUCTION. TO BE LET WITH I-6032. GARVEE BOND FUNDING $12M FOR CON, PAYBACK FY 2019-2033. | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 14420000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000
I-6036 | HIGHWAY | I-140 | US 17 TO NORTH OF US 74. PAVEMENT REHABILITATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10000
I-6036 | HIGHWAY | I-140 | US 17 TO NORTH OF US 74. PAVEMENT REHABILITATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 8500000 | FY 2023: 85000; FY 2024: 6597000; FY 2025: 1818000
I-6037 | HIGHWAY | I-140 | US 421 TO I-40. PAVEMENT AND BRIDGE REHABILITATION. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 7300000 | FY 2028: 3985000; FY 2029: 3315000
I-6039 | HIGHWAY | I-40 | I-40 FROM END I-40 (MILE MARKER 420) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 13200000 | FY 2023: 1268000; FY 2024: 9521000; FY 2025: 2411000
I-6040 | HIGHWAY | I-40 | WEST OF US 117 (MILE MARKER 388) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 19768000 | FY 2023: 11635000; FY 2024: 6521000
I-6041 | HIGHWAY | US 64 (FUTURE I-87) | SR 1225 (KINGSBORO ROAD) TO NC 33. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | STATEWIDE MOBILITY |  | HP | CONSTRUCTION | 7000000 | FY 2023: 7000000
I-6041 | HIGHWAY | US 64 (FUTURE I-87) | SR 1225 (KINGSBORO ROAD) TO NC 33. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 22900000 | FY 2023: 774000; FY 2024: 22126000
I-6041 | HIGHWAY | US 64 (FUTURE I-87) | SR 1225 (KINGSBORO ROAD) TO NC 33. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | STATEWIDE MOBILITY |  |  |  | 10000
I-6041A | HIGHWAY | US 64 (FUTURE I-87) | REHABILITATE BRIDGES 320104, 320155, 320148, 320153, 320154, 320156, 320157, 320320, 320325, AND 320326. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 4000000 | FY 2023: 750000
I-6042 | HIGHWAY | US 64 (FUTURE I-87) | NC 33 TO MARTIN COUNTY LINE. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | STATEWIDE MOBILITY |  | HP | CONSTRUCTION | 5300000 | FY 2023: 5300000
I-6042 | HIGHWAY | US 64 (FUTURE I-87) | NC 33 TO MARTIN COUNTY LINE. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 14400000 | FY 2023: 413000; FY 2024: 13987000
I-6042A | HIGHWAY | US 64 (FUTURE I-87) | REHABILITATE BRIDGE 320327 AND 320328. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 300000
I-6044 | HIGHWAY | US 70 (FUTURE I-42) | SR 1003 (BUFFALO ROAD) TO WAYNE COUNTY LINE. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132 FOR CONSTRUCTION, PAYBACK FY 2019-2033. | STATEWIDE MOBILITY |  |  |  | 2137000
I-6044 | HIGHWAY | US 70 (FUTURE I-42) | SR 1003 (BUFFALO ROAD) TO WAYNE COUNTY LINE. PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132 FOR CONSTRUCTION, PAYBACK FY 2019-2033. | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 6090000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000
I-6045 | HIGHWAY | US 64 (FUTURE I-87) | SR 1306 (SOUTH OLD FRANKLIN ROAD) TO SR 1603 (OLD CARRIAGE ROAD). PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10000
I-6045 | HIGHWAY | US 64 (FUTURE I-87) | SR 1306 (SOUTH OLD FRANKLIN ROAD) TO SR 1603 (OLD CARRIAGE ROAD). PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 15831000 | FY 2023: 3051000; FY 2024: 9385000; FY 2025: 3395000
I-6045 | HIGHWAY | US 64 (FUTURE I-87) | SR 1306 (SOUTH OLD FRANKLIN ROAD) TO SR 1603 (OLD CARRIAGE ROAD). PAVEMENT REHABILITATION. | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 3479000 | FY 2023: 670000; FY 2024: 2063000; FY 2025: 746000
I-6045A | HIGHWAY | US 64 (FUTURE I-87) | BRIDGE REHABILITATION FOR 630072 AND 630074. | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 520000
I-6046 | HIGHWAY | US 64 (FUTURE I-87) | SR 1603 (OLD CARRIAGE ROAD) TO SR 1225 (KINGSBORO ROAD). PAVEMENT REHABILITATION. | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 24006000 | FY 2023: 17652000; FY 2024: 4379000
I-6046 | HIGHWAY | US 64 (FUTURE I-87) | SR 1603 (OLD CARRIAGE ROAD) TO SR 1225 (KINGSBORO ROAD). PAVEMENT REHABILITATION. | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10000
I-6047 | HIGHWAY | I-795 | WILSON COUNTY LINE TO SR 2075 (ASH STREET). UPGRADE GUARDRAIL, SHOULDER AND MEDIAN REPAIRS. | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 2033000
I-6047 | HIGHWAY | I-795 | WILSON COUNTY LINE TO SR 2075 (ASH STREET). UPGRADE GUARDRAIL, SHOULDER AND MEDIAN REPAIRS. | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034. | STATEWIDE MOBILITY |  |  |  | 10000
I-6047 | HIGHWAY | I-795 | WILSON COUNTY LINE TO SR 2075 (ASH STREET). UPGRADE GUARDRAIL, SHOULDER AND MEDIAN REPAIRS. | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034. | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 4860000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000
I-6048 | HIGHWAY | US 117 (FUTURE I-795) | US 70 TO DUPLIN COUNTY LINE. PAVEMENT AND BRIDGE REHABILITATION. | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10000
I-6048 | HIGHWAY | US 117 (FUTURE I-795) | US 70 TO DUPLIN COUNTY LINE. PAVEMENT AND BRIDGE REHABILITATION. | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 7892000 | FY 2023: 2161000
I-6052 | HIGHWAY | I-277 (BROOKSHIRE FREEWAY) | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | 10 | Charlotte Regional TPO | $5M IN NHPIM FUNDS SWITCHED WITH $5M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 10000
I-6052 | HIGHWAY | I-277 (BROOKSHIRE FREEWAY) | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | 10 | Charlotte Regional TPO | $5M IN NHPIM FUNDS SWITCHED WITH $5M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGDA | CONSTRUCTION | 5000000 | FY 2023: 2390000; FY 2024: 2610000
I-6052 | HIGHWAY | I-277 (BROOKSHIRE FREEWAY) | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | 10 | Charlotte Regional TPO | $5M IN NHPIM FUNDS SWITCHED WITH $5M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHFP | CONSTRUCTION | 8550000 | FY 2023: 4084000; FY 2024: 4466000
I-6052 | HIGHWAY | I-277 (BROOKSHIRE FREEWAY) | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | 10 | Charlotte Regional TPO | $5M IN NHPIM FUNDS SWITCHED WITH $5M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 1250000 | FY 2023: 597000; FY 2024: 653000
I-6053 | HIGHWAY | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
I-6053 | HIGHWAY | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 26973000 | [11 empty] | 26973000
I-6053 | HIGHWAY | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | UTILITIES | 655000 | [11 empty] | 655000
I-6053 | HIGHWAY | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 24300000 | [11 empty] | 24300000
I-6054 | HIGHWAY | I-40 | US 74 (SMOKY MOUNTAIN EXPRESSWAY) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | 13, 14 | French Broad River MPO | [5 empty] | 10000
I-6054A | HIGHWAY | I-40 | US 74 (SMOKY MOUNTAIN EXPRESSWAY) TO NC 215 (CHAMPION DRIVE). ADD ADDITIONAL LANES. | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 57300000 | [11 empty] | 57300000
I-6054A | HIGHWAY | I-40 | US 74 (SMOKY MOUNTAIN EXPRESSWAY) TO NC 215 (CHAMPION DRIVE). ADD ADDITIONAL LANES. | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | UTILITIES | 500000 | [11 empty] | 500000
I-6054A | HIGHWAY | I-40 | US 74 (SMOKY MOUNTAIN EXPRESSWAY) TO NC 215 (CHAMPION DRIVE). ADD ADDITIONAL LANES. | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 2700000 | [11 empty] | 2700000
I-6054B | HIGHWAY | I-40 | NC 215 (CHAMPION DRIVE) TO SR 1200 (WIGGINS ROAD). ADD ADDITIONAL LANES. | 13, 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | UTILITIES | 700000 | [11 empty] | 700000
I-6054B | HIGHWAY | I-40 | NC 215 (CHAMPION DRIVE) TO SR 1200 (WIGGINS ROAD). ADD ADDITIONAL LANES. | 13, 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 163500000 | [11 empty] | 163500000
I-6054B | HIGHWAY | I-40 | NC 215 (CHAMPION DRIVE) TO SR 1200 (WIGGINS ROAD). ADD ADDITIONAL LANES. | 13, 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 5300000 | [11 empty] | 5300000
I-6054C | HIGHWAY | I-40 | SR 1200 (WIGGINS ROAD) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | 13 | French Broad River MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 13900000 | [11 empty] | 13900000
I-6054C | HIGHWAY | I-40 | SR 1200 (WIGGINS ROAD) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | 13 | French Broad River MPO |  | NOT FUNDED |  | NHP | UTILITIES | 4700000 | [11 empty] | 4700000
I-6054C | HIGHWAY | I-40 | SR 1200 (WIGGINS ROAD) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | 13 | French Broad River MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 200199000 | [11 empty] | 200199000
I-6055 | HIGHWAY | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 8 | Lumber River RPO |  | REGION E |  |  |  | 10000
I-6055 | HIGHWAY | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 8 | Lumber River RPO |  | REGION E |  | T | CONSTRUCTION | 187500000 | FY 2031: 23101000; FY 2032: 52124000; FY 2033: 47126000 | 65149000
I-6055 | HIGHWAY | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 8 | Lumber River RPO |  | REGION E |  | T | RIGHT-OF-WAY | 27600000 | FY 2028: 1380000; FY 2029: 8280000; FY 2030: 8280000; FY 2031: 4140000; FY 2032: 5520000
I-6055 | HIGHWAY | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 8 | Lumber River RPO |  | REGION E |  | T | UTILITIES | 8584000 | FY 2028: 4292000; FY 2029: 4292000
I-6056 | HIGHWAY | I-77 | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
I-6056 | HIGHWAY | I-77 | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 300000 | [11 empty] | 300000
I-6056 | HIGHWAY | I-77 | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | UTILITIES | 200000 | [11 empty] | 200000
I-6056 | HIGHWAY | I-77 | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 8200000 | [11 empty] | 8200000
I-6058 | HIGHWAY | I-40 | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 4300000 | [11 empty] | 4300000
I-6058 | HIGHWAY | I-40 | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | 13 | Greater Hickory MPO |  | NOT FUNDED |  |  |  | 10000
I-6058 | HIGHWAY | I-40 | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 300000 | [11 empty] | 300000
I-6058 | HIGHWAY | I-40 | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | UTILITIES | 1100000 | [11 empty] | 1100000
I-6059 | HIGHWAY | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 600000
I-6059 | HIGHWAY | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 200000
I-6059 | HIGHWAY | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 7100000
I-6061 | HIGHWAY | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 10000
I-6061 | HIGHWAY | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 1300000 | FY 2027: 347000; FY 2028: 594000; FY 2029: 99000; FY 2030: 130000; FY 2031: 130000
I-6061 | HIGHWAY | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | UTILITIES | 1900000 | FY 2027: 950000; FY 2028: 950000
I-6061 | HIGHWAY | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 17199000 | FY 2029: 7383000; FY 2030: 8948000; FY 2031: 868000
I-6062 | HIGHWAY | I-95 | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 10000
I-6062 | HIGHWAY | I-95 | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 3600000 | FY 2027: 36000; FY 2028: 1610000; FY 2029: 1234000; FY 2030: 360000; FY 2031: 360000
I-6062 | HIGHWAY | I-95 | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | UTILITIES | 1300000 | FY 2027: 650000; FY 2028: 650000
I-6062 | HIGHWAY | I-95 | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 19000000 | FY 2029: 190000; FY 2030: 12544000; FY 2031: 6266000
I-6063 | HIGHWAY | I-40 | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 22120000
I-6063 | HIGHWAY | I-40 | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | NHPIM | GARVEE CON | 6435000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000
I-6063 | HIGHWAY | I-40 | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  |  |  | 10000
I-6063 | HIGHWAY | I-40 | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 1667000
I-6064 | HIGHWAY | I-95 | MILE MARKER 13 TO MILE MARKER 22. WIDEN TO EIGHT LANES AND PAVEMENT REHABILITATION. | 6 | Lumber River RPO | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. PROJECT LET WITH I-5879. |  |  |  |  | 10000
I-6064A | HIGHWAY | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | T | CONSTRUCTION | 201441000 | FY 2023: 0; FY 2024: 44553000; FY 2025: 47888000; FY 2026: 90000000; FY 2027: 19000000
I-6064A | HIGHWAY | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | DP | RIGHT-OF-WAY | 2470000
I-6064A | HIGHWAY | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | DP | UTILITIES | 2600000
I-6064A | HIGHWAY | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | DP | CONSTRUCTION | 16930000
I-6064A | HIGHWAY | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | T | RIGHT-OF-WAY | 617000
I-6064A | HIGHWAY | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | T | UTILITIES | 650000
I-6064B | HIGHWAY | I-95 | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 85946000 | FY 2023: 3162000; FY 2024: 23613000; FY 2025: 11171000; FY 2026: 40000000; FY 2027: 8000000
I-6064B | HIGHWAY | I-95 | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 7429000
I-6064B | HIGHWAY | I-95 | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN TO EIGHT LANES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | UTILITIES | 2025000
I-6064C | HIGHWAY | I-95 | MILE MARKER 13 TO MILE MARKER 22. PAVEMENT REHABILITATION. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHPIM | CONSTRUCTION | 131492000 | FY 2023: 38018000; FY 2024: 32878000; FY 2025: 23874000
I-6064D | HIGHWAY | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 6 | Lumber River RPO |  | STATEWIDE MOBILITY |  | DP | ENGINEERING | 250000
I-6064D | HIGHWAY | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 6 | Lumber River RPO |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 65000
I-6065 | HIGHWAY | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | EXEMPT |  | S(M) | RIGHT-OF-WAY | 20000 | FY 2024: 20000
I-6065 | HIGHWAY | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | EXEMPT |  | T(DA) | CONSTRUCTION | 36663000 | FY 2025: 8427000; FY 2026: 16453000; FY 2027: 9274000; FY 2028: 2509000
I-6065 | HIGHWAY | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | EXEMPT |  | S(M) | CONSTRUCTION | 9167000 | FY 2025: 2107000; FY 2026: 4113000; FY 2027: 2319000; FY 2028: 628000
I-6065 | HIGHWAY | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | EXEMPT |  | BA | ENGINEERING | 190000
I-6065 | HIGHWAY | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | EXEMPT |  | S(M) | ENGINEERING | 24000 | FY 2023: 24000
I-6065 | HIGHWAY | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | EXEMPT |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2024: 80000
I-6065 | HIGHWAY | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | EXEMPT |  | BGDA | ENGINEERING | 760000
I-6065 | HIGHWAY | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | EXEMPT |  | BGDA | ENGINEERING | 96000 | FY 2023: 96000
M-0219 | HIGHWAY | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  |  |  | 4258000
M-0219DIV | HIGHWAY | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 1200000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 150000
M-0219REG | HIGHWAY | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 1200000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 150000
M-0219SW | HIGHWAY | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 1600000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 200000
M-0360 | HIGHWAY | VARIOUS | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 17088000
M-0360DIV | HIGHWAY | VARIOUS | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 1200000 | FY 2023: 300000
M-0360REG | HIGHWAY | VARIOUS | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 1200000 | FY 2023: 300000
M-0360SW | HIGHWAY | VARIOUS | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 1600000 | FY 2023: 400000
M-0376 | HIGHWAY | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 12931000
M-0376DIV | HIGHWAY | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 4320000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 540000
M-0376REG | HIGHWAY | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 4320000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 540000
M-0376SW | HIGHWAY | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 5670000 | 360000 | 360000 | 360000 | 270000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 720000
M-0379 | HIGHWAY | VARIOUS | SCOUR EVALUATION PROGRAM OF EXISTING BRIDGES. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 3100000
M-0391 | HIGHWAY | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 4076000
M-0391DIV | HIGHWAY | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 1920000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 240000
M-0391REG | HIGHWAY | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 1920000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 240000
M-0391SW | HIGHWAY | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 2560000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 320000
M-0392 | HIGHWAY | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 4180000
M-0392DIV | HIGHWAY | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 768000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 96000
M-0392REG | HIGHWAY | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 768000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 96000
M-0392SW | HIGHWAY | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 1024000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 128000
M-0414 | HIGHWAY | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM | 99 | STATEWIDE PROJECT |  |  |  | BGOFF | IMPLEMENTATION | 12800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 1600000
M-0414 | HIGHWAY | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM | 99 | STATEWIDE PROJECT |  |  |  | L | IMPLEMENTATION | 3200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 400000
M-0418 | HIGHWAY | VARIOUS | STORM WATER RUNOFF. RESEARCH, DESIGN, CONSTRUCT, MAINTAIN AND MONITOR STORM WATER DRAINAGE FROM 50 BRIDGES OVER WATERWAYS. (HB 2346, SECTION 25.18) | 99 | STATEWIDE PROJECT | UNDER CONSTRUCTION | DIVISION SW |  |  |  | 6994000
M-0451 | HIGHWAY | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | 99 | STATEWIDE PROJECT | [5 empty] | 712000
M-0451DIV | HIGHWAY | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 336000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 42000
M-0451REG | HIGHWAY | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 336000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 42000
M-0451SW | HIGHWAY | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 448000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 56000
M-0452 | HIGHWAY | VARIOUS | TOLLING/FINANCIAL FEASIBILITY STUDIES. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  |  |  | 1064000
M-0452 | HIGHWAY | VARIOUS | TOLLING/FINANCIAL FEASIBILITY STUDIES. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 3200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 400000
M-0479 | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT | [5 empty] | 7000000
M-0479ADIV | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 7200000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 900000
M-0479AREG | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 7200000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 900000
M-0479ASW | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 1200000
M-0479BDIV | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 2400000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 300000
M-0479BREG | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 2400000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 300000
M-0479BSW | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 3200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 400000
M-0479DIV | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 24000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 3000000
M-0479REG | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 24000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 3000000
M-0479SW | HIGHWAY | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 32000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 4000000
M-0482 | HIGHWAY | VARIOUS | FEDERAL STATE TRANSPORTATION INNOVATION COUNCIL (STIC) INCENTIVE FUNDED PROJECTS | 99 | STATEWIDE PROJECT | DP FUNDS REPRESENT FEDERAL STIC FUNDS. | EXEMPT |  | DP | IMPLEMENTATION | 400000 | FY 2023: 100000; FY 2024: 100000; FY 2025: 100000; FY 2026: 100000
M-0482 | HIGHWAY | VARIOUS | FEDERAL STATE TRANSPORTATION INNOVATION COUNCIL (STIC) INCENTIVE FUNDED PROJECTS | 99 | STATEWIDE PROJECT | DP FUNDS REPRESENT FEDERAL STIC FUNDS. | EXEMPT |  | S(M) | IMPLEMENTATION | 100000 | FY 2023: 25000; FY 2024: 25000; FY 2025: 25000; FY 2026: 25000
M-0505 | HIGHWAY | VARIOUS | TRANSPORTATION PROGRAM MANAGEMENT UNIT (TPMU) OVERSIGHT FOR LOCALLY-ADMINISTERED PROJECTS INCLUDING PREPARATION OF AGREEMENTS AND FUNDING AUTHORIZATION REQUESTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  |  |  | 535000
M-0505 | HIGHWAY | VARIOUS | TRANSPORTATION PROGRAM MANAGEMENT UNIT (TPMU) OVERSIGHT FOR LOCALLY-ADMINISTERED PROJECTS INCLUDING PREPARATION OF AGREEMENTS AND FUNDING AUTHORIZATION REQUESTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 4800000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 600000
M-0515 | HIGHWAY | VARIOUS | RIGHT-OF-WAY BRANCH, REVIEW OF LOCAL PUBLIC AGENCY (LPA) PROJECTS BY THE APPRAISAL SECTION. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  |  |  | 250000
M-0515 | HIGHWAY | VARIOUS | RIGHT-OF-WAY BRANCH, REVIEW OF LOCAL PUBLIC AGENCY (LPA) PROJECTS BY THE APPRAISAL SECTION. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | RIGHT-OF-WAY | 4000000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 500000
M-0521 | HIGHWAY | VARIOUS | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 384000
M-0521DIV | HIGHWAY | VARIOUS | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE DIVISION TIER. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 100000
M-0521REG | HIGHWAY | VARIOUS | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE REGIONAL TIER. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 100000
M-0521SW | HIGHWAY | VARIOUS | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE STATEWIDE TIER. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 100000
M-0534 | HIGHWAY | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 2000000
M-0534DIV | HIGHWAY | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 1200000
M-0534REG | HIGHWAY | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 1200000
M-0534SW | HIGHWAY | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 12800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 1600000
M-0539DIV | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | MITIGATION | 43200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 5400000
M-0539REG | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | MITIGATION | 43200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 5400000
M-0539SW | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | MITIGATION | 57600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 7200000
M-0552ADIV | HIGHWAY | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 150000 | FY 2023: 75000
M-0552AREG | HIGHWAY | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 150000 | FY 2023: 75000
M-0552ASW | HIGHWAY | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 200000 | FY 2023: 100000
M-0552BDIV | HIGHWAY | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 324000 | FY 2023: 108000
M-0552BREG | HIGHWAY | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 324000 | FY 2023: 108000
M-0552BSW | HIGHWAY | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 432000 | FY 2023: 144000
M-0552CDIV | HIGHWAY | VARIOUS | DIGITAL DELIVERY INITIATIVE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 150000 | FY 2023: 75000; FY 2024: 75000
M-0552CREG | HIGHWAY | VARIOUS | DIGITAL DELIVERY INITIATIVE. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 150000 | FY 2023: 75000; FY 2024: 75000
M-0552CSW | HIGHWAY | VARIOUS | DIGITAL DELIVERY INITIATIVE. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 200000 | FY 2023: 100000; FY 2024: 100000
M-0553A | HIGHWAY | VARIOUS | INTEGRATED PROJECT DELIVERY | 99 | STATEWIDE PROJECT |  | EXEMPT |  | T | ENGINEERING | 10500000 | FY 2023: 6000000
M-0553B | HIGHWAY | VARIOUS | TRAINING AND SPECIAL PROJECTS | 99 | STATEWIDE PROJECT |  | EXEMPT |  | T | ENGINEERING | 2000000 | FY 2023: 1000000
M-0554DIV | HIGHWAY | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 105000000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 15000000
M-0554REG | HIGHWAY | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 105000000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 15000000
M-0554SW | HIGHWAY | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 140000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 20000000
M-0555DIV | HIGHWAY | VARIOUS | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | UTILITIES | 1365000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 210000
M-0555REG | HIGHWAY | VARIOUS | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | UTILITIES | 1365000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 210000
M-0555SW | HIGHWAY | VARIOUS | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | UTILITIES | 1820000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 280000
M-0557A | HIGHWAY | STATEWIDE | HAZARD CHARACTERIZATION AND WARNING TOOLS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | PROTCT | ENGINEERING | 3360000 | FY 2023: 840000; FY 2024: 840000; FY 2025: 840000; FY 2026: 840000
M-0557B | HIGHWAY | STATEWIDE | HAZARD CORRIDOR VULNERABILITY ASSESSMENTS. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | PROTCT | ENGINEERING | 1400000 | FY 2023: 350000; FY 2024: 350000; FY 2025: 350000; FY 2026: 350000
M-0557C | HIGHWAY | STATEWIDE | GEOTECHNICAL ASSET MANAGEMENT (GAM) DATABASE AND LANDSLIDE MITIGATION PLANNING | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | PROTCT | ENGINEERING | 2240000 | FY 2023: 560000; FY 2024: 560000; FY 2025: 560000; FY 2026: 560000
P-2918 | RAIL | PIEDMONT CORRIDOR | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "S" FUNDING REFLECTS STATE RAIL FUNDS | EXEMPT |  |  |  | 186176000
P-2918 | RAIL | PIEDMONT CORRIDOR | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "S" FUNDING REFLECTS STATE RAIL FUNDS | EXEMPT |  | CMAQ | OPERATIONS | 14069000
P-2918 | RAIL | PIEDMONT CORRIDOR | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "S" FUNDING REFLECTS STATE RAIL FUNDS | EXEMPT |  | S | OPERATIONS | 3517000
P-5005 | RAIL | CSXT RR | CONGESTION MITIGATION CROSSOVERS. | 4, 5 | Peanut Belt RPO, Capital Area MPO, Rocky Mount Urban Area MPO | IN PROGRESS. |  |  |  |  | 26561000
P-5200 | RAIL | PIEDMONT AND NORTHERN RAILROAD | RAIL CORRIDOR BETWEEN GASTONIA AND MOUNT HOLLY INCLUDING THE BELMONT SPUR. REACTIVATION OF RAIL CORRIDOR | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO | [5 empty] | 7897000
P-5200D | RAIL | P & N CORRIDOR REACTIVIATION | BELMONT SPUR. | 12 | Gaston-Cleveland-Lincoln MPO |  | PRE-STI (TRANSITION) |  | BGANY | CONSTRUCTION | 850000 | FY 2023: 850000
P-5200D | RAIL | P & N CORRIDOR REACTIVIATION | BELMONT SPUR. | 12 | Gaston-Cleveland-Lincoln MPO |  | PRE-STI (TRANSITION) |  | BGANY | RIGHT-OF-WAY | 50000 | FY 2023: 50000
P-5205 | RAIL | PIEDMONT CORRIDOR | GRAHAM TO HAW RIVER. SIDING AND CURVE REALIGNMENT. | 7 | Burlington-Graham MPO | COMPLETED | PRE-STI (TRANSITION) |  |  |  | 11605000
P-5208 | RAIL | PIEDMONT CORRIDOR | PIEDMONT CORRIDOR, RESTORE DOUBLE TRACK, HAYDOCK TO JUNKER. | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 151176000
P-5500 | RAIL | NCRR | RALEIGH UNION STATION PROJECT - PHASE I. CONSTRUCT RALEIGH TRAIN STATION AND ASSOCIATED RAIL TRACK AND SIDING IMPROVEMENTS TO INCREASE PASSENGER AND FREIGHT CAPACITY. | 5 | Capital Area MPO | DP FUNDS - FEDERAL TIGER GRANT; O FUNDS - STATE LEGISLATIVE ALLOCATION FOR RAIL; PROJECT INCLUDES IN-KIND PROPERTY CONTRIBUTION BY TRIANGLE TRANSIT (CONTINGENT ON TT BOARD OF TRUSTEES APPROVAL) - 4 PARCELS TOTALING 3.5 ACRES WITH TAX VALUE OF $2.9 MILLION | PRE-STI (TRANSITION) |  |  |  | 39875000
P-5602 | RAIL | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 4170000
P-5602DIV | RAIL | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | ENGINEERING | 4800000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 600000
P-5602REG | RAIL | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | ENGINEERING | 4800000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 600000
P-5602SW | RAIL | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | ENGINEERING | 6400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 800000
P-5700 | RAIL | NORFOLK SOUTHERN MAINLINE | NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. | 7 | Greensboro Urban Area MPO | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION | DIVISION 7 |  |  |  | 200000
P-5700 | RAIL | NORFOLK SOUTHERN MAINLINE | NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. | 7 | Greensboro Urban Area MPO | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION | DIVISION 7 |  | O | CONSTRUCTION | 850000 | FY 2024: 850000
P-5700 | RAIL | NORFOLK SOUTHERN MAINLINE | NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. | 7 | Greensboro Urban Area MPO | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION | DIVISION 7 |  | T | CONSTRUCTION | 850000 | FY 2024: 850000
P-5701 | RAIL | NORFOLK SOUTHERN H LINE | MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PLATFORM, PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION. "OTHER" FUNDING REFLECTS PARTICIPATION BY TRIANGLE TRANSIT. | DIVISION 7 |  |  |  | 810000
P-5701A | RAIL | NORFOLK SOUTHERN H LINE | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | T | CONSTRUCTION | 6290000 | FY 2023: 3095000; FY 2024: 3095000
P-5701A | RAIL | NORFOLK SOUTHERN H LINE | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | O | CONSTRUCTION | 570000
P-5701B | RAIL | NORFOLK SOUTHERN H LINE | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT STATION PLATFORM AND REALIGN CURVE AT MILEPOST 41.4. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | T | CONSTRUCTION | 1000000 | FY 2023: 500000; FY 2024: 500000
P-5702 | RAIL | NORFOLK SOUTHERN MAIN LINE (TRACK MILEPOST 376) | ESTABLISH A NEW THOROUGHBRED BULK TRANSFER (TBT) FACILITY IN CHARLOTTE. | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN CORPORATION | DIVISION 10 |  | O | CONSTRUCTION | 488000
P-5702 | RAIL | NORFOLK SOUTHERN MAIN LINE (TRACK MILEPOST 376) | ESTABLISH A NEW THOROUGHBRED BULK TRANSFER (TBT) FACILITY IN CHARLOTTE. | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN CORPORATION | DIVISION 10 |  | T | CONSTRUCTION | 488000
P-5702 | RAIL | NORFOLK SOUTHERN MAIN LINE (TRACK MILEPOST 376) | ESTABLISH A NEW THOROUGHBRED BULK TRANSFER (TBT) FACILITY IN CHARLOTTE. | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN CORPORATION | DIVISION 10 |  |  |  | 10000
P-5704 | RAIL | CSX SF LINE | MILEPOST 311.8 TO MILEPOST 316.9. 10,000 FEET SIDING EXTENSION AT STOUTS IN UNION COUNTY. | 10 | Charlotte Regional TPO | COMPLETE - OTHER FUNDING PROVIDED BY CSX CORPORATION | REGION E |  |  |  | 9520000
P-5704 | RAIL | CSX SF LINE | MILEPOST 311.8 TO MILEPOST 316.9. 10,000 FEET SIDING EXTENSION AT STOUTS IN UNION COUNTY. | 10 | Charlotte Regional TPO | COMPLETE - OTHER FUNDING PROVIDED BY CSX CORPORATION | REGION E |  | O | CONSTRUCTION | 2000000
P-5704 | RAIL | CSX SF LINE | MILEPOST 311.8 TO MILEPOST 316.9. 10,000 FEET SIDING EXTENSION AT STOUTS IN UNION COUNTY. | 10 | Charlotte Regional TPO | COMPLETE - OTHER FUNDING PROVIDED BY CSX CORPORATION | REGION E |  | T | CONSTRUCTION | 2000000
P-5705 | RAIL | CHARLOTTE | CHARLOTTE GATEWAY STATION. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS |  |  |  |  | 89614000
P-5705A | RAIL | CHARLOTTE | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 8420000 | FY 2023: 1701000; FY 2024: 5814000; FY 2025: 905000
P-5705A | RAIL | CHARLOTTE | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 2578000 | FY 2023: 521000; FY 2024: 1780000; FY 2025: 277000
P-5705A | RAIL | CHARLOTTE | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | DP | RIGHT-OF-WAY | 500000
P-5706 | RAIL | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | 5 | Durham-Chapel Hill-Carrboro MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | STATEWIDE MOBILITY |  |  |  | 4928000
P-5706 | RAIL | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | 5 | Durham-Chapel Hill-Carrboro MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 11243000 | FY 2023: 125000; FY 2024: 1125000; FY 2025: 9993000
P-5706 | RAIL | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | 5 | Durham-Chapel Hill-Carrboro MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | UTILITIES | 2604000 | FY 2023: 1302000; FY 2024: 1302000
P-5706 | RAIL | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | 5 | Durham-Chapel Hill-Carrboro MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 33801000 | FY 2028: 4667000; FY 2029: 13904000; FY 2030: 10294000; FY 2031: 4936000
P-5707 | RAIL | CSX S LINE | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | CONSTRUCTION | 32100000 | FY 2024: 6145000; FY 2025: 12991000; FY 2026: 9026000; FY 2027: 3938000
P-5707 | RAIL | CSX S LINE | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION C |  |  |  | 3420000
P-5708 | RAIL | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT HARRISON AVENUE CROSSING (734755X) IN CARY. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 15774000
P-5708 | RAIL | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT HARRISON AVENUE CROSSING (734755X) IN CARY. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 826000
P-5708 | RAIL | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT HARRISON AVENUE CROSSING (734755X) IN CARY. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6000000
P-5709 | RAIL | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | O | CONSTRUCTION | 1005000 | FY 2024: 10000; FY 2025: 590000; FY 2026: 309000; FY 2027: 96000
P-5709 | RAIL | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | T | RIGHT-OF-WAY | 3484000 | FY 2023: 2613000
P-5709 | RAIL | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | T | UTILITIES | 1566000 | FY 2023: 1174000
P-5709 | RAIL | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | T | CONSTRUCTION | 19095000 | FY 2024: 191000; FY 2025: 11213000; FY 2026: 5863000; FY 2027: 1828000
P-5711 | RAIL | CSX A LINE | CONSTRUCT FREIGHT RAIL AND INTERMODAL TERMINAL INFRASTRUCTURE (CCX) ALONG NATIONAL GATEWAY CORRIDOR. | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO |  | STATEWIDE MOBILITY |  |  |  | 94739000
P-5711A | RAIL | CSX A LINE | CCX INTERMODAL TERMINAL AND TRACK IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 43100000
P-5713 | RAIL | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 268000 | FY 2027: 148000; FY 2028: 105000; FY 2029: 15000
P-5713 | RAIL | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 3431000 | FY 2025: 858000; FY 2026: 1715000; FY 2027: 858000
P-5713 | RAIL | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | STATEWIDE MOBILITY |  | T | UTILITIES | 952000 | FY 2025: 952000
P-5713 | RAIL | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 8633000 | FY 2027: 4764000; FY 2028: 3387000; FY 2029: 482000
P-5714 | RAIL | NCRR NORFOLK SOUTHERN | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | O | CONSTRUCTION | 1500000 | FY 2025: 1500000
P-5714 | RAIL | NCRR NORFOLK SOUTHERN | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | T | CONSTRUCTION | 1600000 | FY 2025: 1600000
P-5715 | RAIL | CSX | CROSSING 630607N AT NEW HOPE CHURCH ROAD IN RALEIGH. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD | REGION C |  |  |  | 9832000
P-5715 | RAIL | CSX | CROSSING 630607N AT NEW HOPE CHURCH ROAD IN RALEIGH. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD | REGION C |  | DP | CONSTRUCTION | 999000 | FY 2024: 376000; FY 2025: 431000; FY 2026: 192000
P-5715 | RAIL | CSX | CROSSING 630607N AT NEW HOPE CHURCH ROAD IN RALEIGH. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD | REGION C |  | T | CONSTRUCTION | 18002000 | FY 2024: 6771000; FY 2025: 7767000; FY 2026: 3464000
P-5717 | RAIL | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  |  |  | 1200000
P-5717 | RAIL | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | T | RIGHT-OF-WAY | 8900000
P-5717 | RAIL | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | T | UTILITIES | 1878000
P-5717 | RAIL | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | T | CONSTRUCTION | 30700000 | FY 2024: 5298000; FY 2025: 13532000; FY 2026: 9056000; FY 2027: 2814000
P-5718 | RAIL | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | "O"FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 22610000
P-5718 | RAIL | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | "O"FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3344000
P-5718 | RAIL | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | "O"FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 1188000
P-5718 | RAIL | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | "O"FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3681000
P-5718 | RAIL | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | "O"FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 29344000
P-5719 | RAIL | PIEDMONT CORRIDOR | PURCHASE AND REFURBISH RAIL CARS FOR PIEDMONT SERVICE EXPANSION. | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP FOR STATE OF GOOD REPAIR GRANT |  |  |  |  | 9637000
P-5719C | RAIL | PIEDMONT CORRIDOR | NEW TRAINS AND MAINTENANCE FACILITY. | 5, 7, 9, 10 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION. | REGION C, D, E |  | DP | CONSTRUCTION | 156888000 | FY 2023: 156888000
P-5719C | RAIL | PIEDMONT CORRIDOR | NEW TRAINS AND MAINTENANCE FACILITY. | 5, 7, 9, 10 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION. | REGION C, D, E |  | T | CONSTRUCTION | 55640000 | FY 2024: 27820000; FY 2025: 27820000
P-5720 | RAIL | CSX | CROSSING 630601X AT SR 2006 (DURANT ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307 | REGION C |  | T | CONSTRUCTION | 18200000 | FY 2024: 6845000; FY 2025: 7853000; FY 2026: 3502000
P-5720 | RAIL | CSX | CROSSING 630601X AT SR 2006 (DURANT ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307 | REGION C |  |  |  | 8853000
P-5721 | RAIL | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | 7 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 2035000 | FY 2024: 102000; FY 2025: 1933000
P-5721 | RAIL | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | 7 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | STATEWIDE MOBILITY |  |  |  | 407000
P-5721 | RAIL | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | 7 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 2035000 | FY 2024: 2035000
P-5722 | RAIL | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD. | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  |  |  | 204000
P-5722 | RAIL | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD. | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | O | CONSTRUCTION | 1019000 | FY 2025: 1019000
P-5722 | RAIL | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD. | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | T | CONSTRUCTION | 1019000 | FY 2025: 51000; FY 2026: 968000
P-5724 | RAIL | CSX | RAIL SPUR FOR INDUSTRIAL ACCESS. CONSTRUCT SPINE TRACK AND TURNOUTS, AND REHABILITATE EXISTING TRACK SECTIONS. | 8 | Lumber River RPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CSX; "O" FUNDING INCLUDES PARTICIPATION BY NORTH CAROLINA RAILROAD, LAURINBURG-MAXTON AIRPORT, RAIL INDUSTRIIAL ACCESS PROGRAM, AND COMMUNITY DEVELOPMENT BLOCK GRANT PROGRAM | DIVISION 8 |  |  |  | 9795000
P-5725 | RAIL | KANNAPOLIS | CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL, SIGNALING EQUIPMENT | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  |  |  | 1850000
P-5725 | RAIL | KANNAPOLIS | CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL, SIGNALING EQUIPMENT | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | CONSTRUCTION | 10099000 | FY 2024: 936000; FY 2025: 6535000; FY 2026: 2628000
P-5726 | RAIL | RAILROAD NORFOLK SOUTHERN | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | 9 | Cabarrus-Rowan MPO |  | REGION D |  |  |  | 4108000
P-5726 | RAIL | RAILROAD NORFOLK SOUTHERN | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | L | CONSTRUCTION | 959000 | FY 2025: 196000; FY 2026: 550000; FY 2027: 213000
P-5726 | RAIL | RAILROAD NORFOLK SOUTHERN | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | 9 | Cabarrus-Rowan MPO |  | REGION D |  | T | CONSTRUCTION | 8641000 | FY 2025: 1765000; FY 2026: 4957000; FY 2027: 1919000
P-5726A | RAIL | NORFOLK SOUTHERN | SALISBURY TRAIN STATION SECOND PLATFORM AND PEDESTRIAN UNDERPASS. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | REGION D |  | T | CONSTRUCTION | 2500000 | FY 2024: 374000; FY 2025: 2126000
P-5726B | RAIL | NORFOLK SOUTHERN | SALISBURY NORFOLK SOUTHERN CROSSOVER RELOCATION. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | REGION D |  | T | CONSTRUCTION | 4000000 | FY 2023: 40000; FY 2024: 2851000; FY 2025: 1109000
P-5730 | RAIL | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | 10 | Charlotte Regional TPO |  | REGION E |  | O | CONSTRUCTION | 835000 | FY 2025: 8000; FY 2026: 408000; FY 2027: 318000; FY 2028: 101000
P-5730 | RAIL | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 4400000 | FY 2024: 1100000; FY 2025: 2200000; FY 2026: 1100000
P-5730 | RAIL | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | 10 | Charlotte Regional TPO |  | REGION E |  |  |  | 2000000
P-5730 | RAIL | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 15865000 | FY 2025: 159000; FY 2026: 7758000; FY 2027: 6038000; FY 2028: 1910000
P-5731 | RAIL | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | DIVISION 9 |  | T | CONSTRUCTION | 8550000 | FY 2025: 2651000; FY 2026: 3163000; FY 2027: 2137000; FY 2028: 599000
P-5731 | RAIL | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | DIVISION 9 |  |  |  | 50000
P-5731 | RAIL | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | DIVISION 9 |  | DP | CONSTRUCTION | 14050000 | FY 2025: 4356000; FY 2026: 5198000; FY 2027: 3512000; FY 2028: 984000
P-5731 | RAIL | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | DIVISION 9 |  | L | RIGHT-OF-WAY | 4500000 | FY 2024: 4500000
P-5731 | RAIL | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | DIVISION 9 |  | L | CONSTRUCTION | 2400000 | FY 2025: 744000; FY 2026: 888000; FY 2027: 600000; FY 2028: 168000
P-5731 | RAIL | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | DIVISION 9 |  | T | RIGHT-OF-WAY | 2400000 | FY 2024: 2400000
P-5732 | RAIL | NCRR | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTI-MODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | EXEMPT |  | O | CONSTRUCTION | 2138000 | FY 2024: 21000; FY 2025: 1151000; FY 2026: 880000; FY 2027: 86000
P-5732 | RAIL | NCRR | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTI-MODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | EXEMPT |  | DP | CONSTRUCTION | 10950000 | FY 2024: 110000; FY 2025: 5895000; FY 2026: 4505000; FY 2027: 440000
P-5732 | RAIL | NCRR | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTI-MODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | EXEMPT |  | L | CONSTRUCTION | 2612000 | FY 2024: 2612000
P-5733 | RAIL | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  |  |  | 30000
P-5733 | RAIL | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 300000 | FY 2026: 248000; FY 2027: 52000
P-5733 | RAIL | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | T | RIGHT-OF-WAY | 600000 | FY 2025: 600000
P-5733 | RAIL | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | T | CONSTRUCTION | 2300000 | FY 2026: 1905000; FY 2027: 395000
P-5734 | RAIL | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718 | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 835000 | FY 2029: 162000; FY 2030: 407000; FY 2031: 266000
P-5734 | RAIL | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718 | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 21000000 | FY 2027: 5250000; FY 2028: 10500000; FY 2029: 5250000
P-5734 | RAIL | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718 | STATEWIDE MOBILITY |  |  |  | 3000000
P-5734 | RAIL | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718 | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 15865000 | FY 2029: 3075000; FY 2030: 7733000; FY 2031: 5057000
P-5735 | RAIL | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1270000
P-5735 | RAIL | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 810000
P-5735 | RAIL | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3500000
P-5735 | RAIL | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 11890000
P-5736 | RAIL | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | STATEWIDE MOBILITY |  |  |  | 300000
P-5736 | RAIL | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 2996000 | FY 2029: 752000; FY 2030: 2244000
P-5736 | RAIL | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 4000 | FY 2029: 1000; FY 2030: 3000
P-5736 | RAIL | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 200000 | FY 2028: 200000
P-5737 | RAIL | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD | STATEWIDE MOBILITY |  |  |  | 2010000
P-5737 | RAIL | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 9000000 | FY 2025: 90000; FY 2026: 4657000; FY 2027: 3170000; FY 2028: 1083000
P-5737 | RAIL | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 6111000
P-5737 | RAIL | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD | STATEWIDE MOBILITY |  | T | UTILITIES | 1220000
P-5737 | RAIL | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 13200000 | FY 2025: 132000; FY 2026: 6830000; FY 2027: 4650000; FY 2028: 1588000
P-5738 | RAIL | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | NOT FUNDED |  |  |  | 1200000
P-5738 | RAIL | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | NOT FUNDED |  | O | CONSTRUCTION | 574000 | [11 empty] | 574000
P-5738 | RAIL | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | NOT FUNDED |  | T | RIGHT-OF-WAY | 1800000 | [11 empty] | 1800000
P-5738 | RAIL | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | NOT FUNDED |  | T | CONSTRUCTION | 10924000 | [11 empty] | 10924000
P-5739 | RAIL | CSX S LINE | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION | NOT FUNDED |  | T | CONSTRUCTION | 13680000 | [11 empty] | 13680000
P-5739 | RAIL | CSX S LINE | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION | NOT FUNDED |  |  |  | 1440000
P-5739 | RAIL | CSX S LINE | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION | NOT FUNDED |  | O | CONSTRUCTION | 721000 | [11 empty] | 721000
P-5739 | RAIL | CSX S LINE | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION | NOT FUNDED |  | T | RIGHT-OF-WAY | 2200000 | [11 empty] | 2200000
P-5740 | RAIL | CSX SE LINE | WILMINGTON BELTLINE SPEED IMPROVEMENT PROJECT. | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT FEDERAL CRISI GRANT. | STATEWIDE MOBILITY |  |  |  | 4080000
P-5740A | RAIL | CSX SE LINE | TIE AND RAIL REHABILITATION, CURVE REALIGNMENT, AND UPGRADE RAIL BRIDGES. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 17478000 | FY 2023: 8739000; FY 2024: 8739000
P-5740A | RAIL | CSX SE LINE | TIE AND RAIL REHABILITATION, CURVE REALIGNMENT, AND UPGRADE RAIL BRIDGES. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 15522000 | FY 2023: 15522000
P-5740B | RAIL | CSX SE LINE | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 2543000 | FY 2024: 301000; FY 2025: 2033000; FY 2026: 209000
P-5740B | RAIL | CSX SE LINE | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 600000 | FY 2023: 600000
P-5740B | RAIL | CSX SE LINE | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1806000 | FY 2024: 214000; FY 2025: 1443000; FY 2026: 149000
P-5740C | RAIL | CSX SE LINE | INSTALLATION OF RAILROAD GRADE CROSSING SIGNALS AND GATES AT VARIOUS AT-GRADE CROSSINGS. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 4108000 | FY 2023: 2054000; FY 2024: 2054000
P-5740C | RAIL | CSX SE LINE | INSTALLATION OF RAILROAD GRADE CROSSING SIGNALS AND GATES AT VARIOUS AT-GRADE CROSSINGS. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 5792000 | FY 2023: 5792000
P-5741 | RAIL | CSX A LINE | CONSTRUCT NEW MAIN TRACK BETWEEN MILE POST A-80.7 AND MILE POST A-82.4 INCLUDING REHABILITATION OF CSX SA-LINE BRIDGE OVER ROANOKE RIVER. NEW CONNECTION BETWEEN A-LINE AND SA-LINE AT MILE POST A-80.7. RECONSTRUCT MAIN TRACK BETWEEN MILE POST A-82.4 AND MILE POST A-84.7. CREATE SECOND MAIN. | 1, 4 | Peanut Belt RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 62000000
P-5741 | RAIL | CSX A LINE | CONSTRUCT NEW MAIN TRACK BETWEEN MILE POST A-80.7 AND MILE POST A-82.4 INCLUDING REHABILITATION OF CSX SA-LINE BRIDGE OVER ROANOKE RIVER. NEW CONNECTION BETWEEN A-LINE AND SA-LINE AT MILE POST A-80.7. RECONSTRUCT MAIN TRACK BETWEEN MILE POST A-82.4 AND MILE POST A-84.7. CREATE SECOND MAIN. | 1, 4 | Peanut Belt RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 6200000
P-5741 | RAIL | CSX A LINE | CONSTRUCT NEW MAIN TRACK BETWEEN MILE POST A-80.7 AND MILE POST A-82.4 INCLUDING REHABILITATION OF CSX SA-LINE BRIDGE OVER ROANOKE RIVER. NEW CONNECTION BETWEEN A-LINE AND SA-LINE AT MILE POST A-80.7. RECONSTRUCT MAIN TRACK BETWEEN MILE POST A-82.4 AND MILE POST A-84.7. CREATE SECOND MAIN. | 1, 4 | Peanut Belt RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5000000
P-5742 | RAIL | NS/NCRR EC LINE | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | 2 | Down East RPO | OTHER FUNDS PROVIDED BY NS. | NOT FUNDED |  |  |  | 1300000
P-5742 | RAIL | NS/NCRR EC LINE | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | 2 | Down East RPO | OTHER FUNDS PROVIDED BY NS. | NOT FUNDED |  | O | CONSTRUCTION | 650000 | [11 empty] | 650000
P-5742 | RAIL | NS/NCRR EC LINE | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | 2 | Down East RPO | OTHER FUNDS PROVIDED BY NS. | NOT FUNDED |  | T | RIGHT-OF-WAY | 2000000 | [11 empty] | 2000000
P-5742 | RAIL | NS/NCRR EC LINE | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | 2 | Down East RPO | OTHER FUNDS PROVIDED BY NS. | NOT FUNDED |  | T | CONSTRUCTION | 12350000 | [11 empty] | 12350000
P-5743 | RAIL | NS/NCRR H LINE | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | 4 | Capital Area MPO | OTHER FUNDS PROVIDED BY NS. | NOT FUNDED |  | T | RIGHT-OF-WAY | 3000000 | [11 empty] | 3000000
P-5743 | RAIL | NS/NCRR H LINE | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | 4 | Capital Area MPO | OTHER FUNDS PROVIDED BY NS. | NOT FUNDED |  | O | CONSTRUCTION | 530000 | [11 empty] | 530000
P-5743 | RAIL | NS/NCRR H LINE | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | 4 | Capital Area MPO | OTHER FUNDS PROVIDED BY NS. | NOT FUNDED |  |  |  | 652000
P-5743 | RAIL | NS/NCRR H LINE | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | 4 | Capital Area MPO | OTHER FUNDS PROVIDED BY NS. | NOT FUNDED |  | T | CONSTRUCTION | 10570000 | [11 empty] | 10570000
P-5744 | RAIL | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | STATEWIDE MOBILITY |  | T | UTILITIES | 826000 | FY 2025: 826000
P-5744 | RAIL | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 5766000 | FY 2027: 3344000; FY 2028: 2212000; FY 2029: 210000
P-5744 | RAIL | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 5820000 | FY 2025: 1455000; FY 2026: 2910000; FY 2027: 1455000
P-5744 | RAIL | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 250000 | FY 2027: 145000; FY 2028: 96000; FY 2029: 9000
P-5744 | RAIL | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 3110000 | FY 2027: 1804000; FY 2028: 1193000; FY 2029: 113000
P-5744 | RAIL | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | STATEWIDE MOBILITY |  | DP | RIGHT-OF-WAY | 31000 | FY 2025: 8000; FY 2026: 15000; FY 2027: 8000
P-5744 | RAIL | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | STATEWIDE MOBILITY |  |  |  | 1300000
P-5747 | RAIL | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | O | CONSTRUCTION | 743000 | FY 2026: 7000; FY 2027: 485000; FY 2028: 218000; FY 2029: 33000
P-5747 | RAIL | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | T | RIGHT-OF-WAY | 2300000 | FY 2025: 575000; FY 2026: 1150000; FY 2027: 575000
P-5747 | RAIL | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  | T | CONSTRUCTION | 14156000 | FY 2026: 142000; FY 2027: 9233000; FY 2028: 4147000; FY 2029: 634000
P-5747 | RAIL | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | REGION D |  |  |  | 1500000
P-5748A | RAIL | CSX SG LINE | CONSTRUCT RAIL SIDING IN WAXHAW | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | REGION E |  | T | CONSTRUCTION | 5894000 | FY 2023: 3543000; FY 2024: 1938000; FY 2025: 354000
P-5748B | RAIL | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | DP | CONSTRUCTION | 4700000 | FY 2024: 401000; FY 2025: 2607000; FY 2026: 1415000; FY 2027: 277000
P-5748B | RAIL | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | CONSTRUCTION | 13227000 | FY 2024: 1128000; FY 2025: 7338000; FY 2026: 3983000; FY 2027: 778000
P-5748B | RAIL | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | UTILITIES | 378000 | FY 2023: 378000
P-5748B | RAIL | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | RIGHT-OF-WAY | 5000000 | FY 2023: 5000000
P-5748B | RAIL | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | O | CONSTRUCTION | 250000 | FY 2024: 21000; FY 2025: 139000; FY 2026: 75000; FY 2027: 15000
P-5750 | RAIL | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON | 10 | Rocky River RPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS |  |  |  |  | 1600000
P-5750A | RAIL | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. | 10 | Rocky River RPO |  | REGION E |  | DP | CONSTRUCTION | 3200000 | FY 2024: 1145000; FY 2025: 1584000; FY 2026: 471000
P-5750A | RAIL | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. | 10 | Rocky River RPO |  | REGION E |  | T | RIGHT-OF-WAY | 600000 | FY 2024: 600000
P-5750A | RAIL | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. | 10 | Rocky River RPO |  | REGION E |  | T | CONSTRUCTION | 9837000 | FY 2024: 3520000; FY 2025: 4868000; FY 2026: 1449000
P-5750B | RAIL | CSX SF LINE | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. | 10 | Rocky River RPO |  | REGION E |  | T | CONSTRUCTION | 16380000 | FY 2026: 7379000; FY 2027: 6851000; FY 2028: 2150000
P-5751 | RAIL | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | DIVISION 9 |  | O | CONSTRUCTION | 709000 | FY 2031: 124000; FY 2032: 315000; FY 2033: 210000 | 60000
P-5751 | RAIL | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | DIVISION 9 |  | T | RIGHT-OF-WAY | 5000000 | FY 2028: 1250000; FY 2029: 2500000; FY 2030: 1250000
P-5751 | RAIL | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | DIVISION 9 |  | T | CONSTRUCTION | 21292000 | FY 2031: 3728000; FY 2032: 9455000; FY 2033: 6309000 | 1800000
P-5752 | RAIL | NCRR / NORFOLK SOUTHERN MAIN LINE | HOSKINS STREET IN HIGH POINT. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722351T. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 900000
P-5752 | RAIL | NCRR / NORFOLK SOUTHERN MAIN LINE | HOSKINS STREET IN HIGH POINT. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722351T. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2900000
P-5752 | RAIL | NCRR / NORFOLK SOUTHERN MAIN LINE | HOSKINS STREET IN HIGH POINT. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722351T. | 7 | High Point Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 18100000
P-5754 | RAIL | SR 2623 (TRAILER DRIVE) | IMPROVE AT-GRADE CROSSING WITH NORFOLK SOUTHERN RAILROAD (CROSSING NUMBER 910 618A, MP O4.11) | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN | EXEMPT |  | O | CONSTRUCTION | 1200000
P-5754 | RAIL | SR 2623 (TRAILER DRIVE) | IMPROVE AT-GRADE CROSSING WITH NORFOLK SOUTHERN RAILROAD (CROSSING NUMBER 910 618A, MP O4.11) | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN | EXEMPT |  | O | ENGINEERING | 50000
R-0204 | HIGHWAY | US 221 - NC 226 | SR 1434 TO SR 1153. WIDEN TO MULTI-LANES, WITH A BYPASS OF MARION. | 13 | Foothills RPO | [5 empty] | 38468000
R-0204D | HIGHWAY | US 221 | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | 13 | Foothills RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3000000 | [11 empty] | 3000000
R-0204D | HIGHWAY | US 221 | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | 13 | Foothills RPO |  | NOT FUNDED |  | T | UTILITIES | 500000 | [11 empty] | 500000
R-0204D | HIGHWAY | US 221 | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | 13 | Foothills RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 32500000 | [11 empty] | 32500000
R-0204E | HIGHWAY | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | 13 | Foothills RPO |  | DIVISION 13 |  | T | RIGHT-OF-WAY | 7999000 | FY 2025: 80000; FY 2026: 1665000; FY 2027: 2327000; FY 2028: 2327000; FY 2029: 1600000
R-0204E | HIGHWAY | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | 13 | Foothills RPO |  | DIVISION 13 |  | T | UTILITIES | 1200000 | FY 2025: 600000; FY 2026: 600000
R-0204E | HIGHWAY | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | 13 | Foothills RPO |  | DIVISION 13 |  | T | CONSTRUCTION | 38698000 | FY 2028: 387000; FY 2029: 12267000; FY 2030: 12926000; FY 2031: 9468000; FY 2032: 3650000
R-0211 | HIGHWAY | I-485 (CHARLOTTE SOUTHERN OUTER LOOP) | WEST OF I-77 TO US 74. MULTI-LANE FREEWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PROJECT LET WITH I-5507. |  |  |  |  | 271729000
R-0211EC | HIGHWAY | I-485 | SR 3468 (WEDDINGTON ROAD). CONSTRUCT INTERCHANGE. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | CONSTRUCTION | 9000000
R-0616 | HIGHWAY | NEW ROUTE | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | 11 | High Country RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 18200000 | [11 empty] | 18200000
R-0616 | HIGHWAY | NEW ROUTE | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | 11 | High Country RPO |  | NOT FUNDED |  | T | UTILITIES | 1100000 | [11 empty] | 1100000
R-0616 | HIGHWAY | NEW ROUTE | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | 11 | High Country RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 132201000 | [11 empty] | 132201000
R-0616 | HIGHWAY | NEW ROUTE | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | 11 | High Country RPO |  | NOT FUNDED |  |  |  | 1578000
R-0617 | HIGHWAY | NC 150 | NC 279 AT CHERRYVILLE TO RELOCATED US 321. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  |  |  | 37801000
R-0617BB | HIGHWAY | NC 150 | WEST OF INDIAN CREEK TO US 321 AT LINCOLNTON. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 40900000 | [11 empty] | 40900000
R-0617BB | HIGHWAY | NC 150 | WEST OF INDIAN CREEK TO US 321 AT LINCOLNTON. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | UTILITIES | 2500000 | [11 empty] | 2500000
R-0617BB | HIGHWAY | NC 150 | WEST OF INDIAN CREEK TO US 321 AT LINCOLNTON. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5300000 | [11 empty] | 5300000
R-0617C | HIGHWAY | NC 150 | US 321 AT LINCOLNTON TO US 321 BYPASS. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | UTILITIES | 3900000 | [11 empty] | 3900000
R-0617C | HIGHWAY | NC 150 | US 321 AT LINCOLNTON TO US 321 BYPASS. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 71600000 | [11 empty] | 71600000
R-0617C | HIGHWAY | NC 150 | US 321 AT LINCOLNTON TO US 321 BYPASS. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 600000 | [11 empty] | 600000
R-0623 | HIGHWAY | NC 24 / NC 27 | TROY BYPASS, WEST OF SR 1138 (DAIRY ROAD) TO EAST OF LITTLE RIVER. FOUR LANES, PART ON NEW LOCATION. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 62570000
R-1015 | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | Down East RPO, New Bern Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8M FOR RIGHT-OF-WAY, $2.2M FOR UTILITIES, AND $100M FOR CONSTRUCTION, PAYBACK FY 2019 - 2033. |  |  |  |  | 216113000
R-1015DIV | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | DIVISION 2 |  | NHP | UTILITIES | 1425000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000
R-1015DIV | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | DIVISION 2 |  | S(M) | CONSTRUCTION | 28380000
R-1015DIV | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | DIVISION 2 |  | S(M) | UTILITIES | 92000
R-1015DIV | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | DIVISION 2 |  | S(M) | RIGHT-OF-WAY | 158000
R-1015DIV | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | DIVISION 2 |  | NHP | GARVEE CON | 60060000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000
R-1015DIV | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | DIVISION 2 |  | NHP | GARVEE ROW | 2445000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000
R-1015DIV | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | DIVISION 2 |  | NHP | CONSTRUCTION | 25732000
R-1015REG | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION B |  | NHP | GARVEE CON | 60060000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000
R-1015REG | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION B |  | S(M) | CONSTRUCTION | 19916000
R-1015REG | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION B |  | S(M) | UTILITIES | 92000
R-1015REG | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION B |  | NHP | UTILITIES | 1425000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000
R-1015REG | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION B |  | NHP | GARVEE ROW | 2445000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000
R-1015REG | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION B |  | NHP | CONSTRUCTION | 25731000
R-1015REG | HIGHWAY | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | REGION B |  | S(M) | RIGHT-OF-WAY | 158000
R-2220 | HIGHWAY | US 64 | US 64, EAST OF I-85 BUSINESS IN LEXINGTON TO ASHEBORO BYPASS. WIDEN TO MULTI-LANES. | 8, 9 | High Point Urban Area MPO, Piedmont Triad RPO | [5 empty] | 18647000
R-2220B | HIGHWAY | US 64 | I-85 EAST OF LEXINGTON TO NC 109 | 9 | High Point Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 40572000 | [11 empty] | 40572000
R-2220B | HIGHWAY | US 64 | I-85 EAST OF LEXINGTON TO NC 109 | 9 | High Point Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 30992000 | [11 empty] | 30992000
R-2220B | HIGHWAY | US 64 | I-85 EAST OF LEXINGTON TO NC 109 | 9 | High Point Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 5635000 | [11 empty] | 5635000
R-2220C | HIGHWAY | US 64 | NC 109 TO SR 1409 (LAKE PARK ROAD) | 8, 9 | High Point Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 56452000 | [11 empty] | 56452000
R-2220C | HIGHWAY | US 64 | NC 109 TO SR 1409 (LAKE PARK ROAD) | 8, 9 | High Point Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 13746000 | [11 empty] | 13746000
R-2220C | HIGHWAY | US 64 | NC 109 TO SR 1409 (LAKE PARK ROAD) | 8, 9 | High Point Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 1650000 | [11 empty] | 1650000
R-2220DA | HIGHWAY | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | 8 | Piedmont Triad RPO |  | REGION E |  | T | RIGHT-OF-WAY | 6797000 | FY 2028: 1305000; FY 2029: 2610000; FY 2030: 1522000; FY 2031: 680000; FY 2032: 680000
R-2220DA | HIGHWAY | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | 8 | Piedmont Triad RPO |  | REGION E |  | T | UTILITIES | 7554000 | FY 2028: 3777000; FY 2029: 3777000
R-2220DA | HIGHWAY | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | 8 | Piedmont Triad RPO |  | REGION E |  | T | CONSTRUCTION | 52800000 | FY 2031: 8102000; FY 2032: 19282000; FY 2033: 15265000 | 10151000
R-2233 | HIGHWAY | US 221 | SOUTH CAROLINA STATE LINE TO NORTH OF SR 1366 (ROPER LOOP ROAD). WIDEN TO MULTI-LANES WITH BYPASS OF RUTHERFORDTON ON NEW LOCATION. | 13 | Foothills RPO | [5 empty] | 146177000
R-2233BA | HIGHWAY | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 13 | Foothills RPO | BUILD NC BONDS: $21.5M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE). | DIVISION 13 |  | T | RIGHT-OF-WAY | 14799000 | FY 2024: 2870000; FY 2025: 4305000; FY 2026: 4305000; FY 2027: 359000; FY 2028: 2960000
R-2233BA | HIGHWAY | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 13 | Foothills RPO | BUILD NC BONDS: $21.5M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE). | DIVISION 13 |  | T | CONSTRUCTION | 80699000 | FY 2027: 21978000; FY 2028: 6330000; FY 2029: 24230000; FY 2030: 18313000; FY 2031: 9848000
R-2233BA | HIGHWAY | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 13 | Foothills RPO | BUILD NC BONDS: $21.5M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE). | DIVISION 13 |  | T | BUILD NC CON | 27675000 | FY 2028: 1845000; FY 2029: 1845000; FY 2030: 1845000; FY 2031: 1845000; FY 2032: 1845000; FY 2033: 1845000 | 16605000
R-2233BA | HIGHWAY | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 13 | Foothills RPO | BUILD NC BONDS: $21.5M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE). | DIVISION 13 |  | T | UTILITIES | 3200000 | FY 2024: 1600000; FY 2025: 1600000
R-2233BB | HIGHWAY | US 221 | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | DIVISION 13 |  | T | RIGHT-OF-WAY | 20000000
R-2233BB | HIGHWAY | US 221 | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | DIVISION 13 |  | T | BUILD NC CON | 32175000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 6435000
R-2233BB | HIGHWAY | US 221 | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | DIVISION 13 |  | T | CONSTRUCTION | 100622000 | FY 2023: 827000; FY 2024: 32216000; FY 2025: 26091000; FY 2026: 26488000; FY 2027: 15000000
R-2246 | HIGHWAY | GEORGE LILES PARKWAY | NC 49 TO SOUTH OF I-85. WIDEN TO FOUR LANES DIVIDED, SOME NEW LOCATION. | 10 | Cabarrus-Rowan MPO | [5 empty] | 73291000
R-2246A | HIGHWAY | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD) | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | T | RIGHT-OF-WAY | 4100000 | FY 2028: 820000; FY 2029: 1640000; FY 2030: 820000; FY 2031: 410000; FY 2032: 410000
R-2246A | HIGHWAY | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD) | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | T | UTILITIES | 2900000 | FY 2028: 1450000; FY 2029: 1450000
R-2246A | HIGHWAY | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD) | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | T | CONSTRUCTION | 24100000 | FY 2030: 4704000; FY 2031: 11667000; FY 2032: 6164000; FY 2033: 1565000
R-2247 | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, I-40 TO US 52. FOUR LANE EXPRESSWAY ON NEW LOCATION., INCLUDING ITS DEPLOYMENT. | 9 | Winston-Salem Urban Area MPO | [5 empty] | 214599000
R-2247A | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | NOT FUNDED |  | NHP | CONSTRUCTION | 39101000 | [11 empty] | 39101000
R-2247A | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | NOT FUNDED |  | T | RIGHT-OF-WAY | 13200000 | [11 empty] | 13200000
R-2247A | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | NOT FUNDED |  | T | UTILITIES | 18900000 | [11 empty] | 18900000
R-2247B | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | NOT FUNDED |  | T | RIGHT-OF-WAY | 31900000 | [11 empty] | 31900000
R-2247B | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | NOT FUNDED |  | T | UTILITIES | 3000000 | [11 empty] | 3000000
R-2247B | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | NOT FUNDED |  | NHP | CONSTRUCTION | 149499000 | [11 empty] | 149499000
R-2247CA | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 140899000
R-2247CA | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 500000
R-2247CA | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 261000
R-2247CB | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 92000000
R-2247CB | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 11000000
R-2247CB | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 14000000
R-2247D | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | 9 | Winston-Salem Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2299000
R-2247D | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | 9 | Winston-Salem Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1200000
R-2247D | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | 9 | Winston-Salem Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 65000000
R-2247EA | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | NHP | CONSTRUCTION | 160198000 | FY 2030: 35000000; FY 2031: 42203000; FY 2032: 35328000; FY 2033: 26503000 | 21164000
R-2247EA | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | T | RIGHT-OF-WAY | 14700000 | FY 2028: 118000; FY 2029: 11642000; FY 2031: 1470000; FY 2032: 1470000
R-2247EA | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | 9 | Winston-Salem Urban Area MPO |  | REGION D |  | T | UTILITIES | 1100000 | FY 2028: 550000; FY 2029: 550000
R-2247EB | HIGHWAY | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE AT US 52 | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 83655000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000
R-2248 | HIGHWAY | I-485 (CHARLOTTE WESTERN OUTER LOOP) | WEST OF I-77 TO I-85 NORTH. FREEWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2010-2021 |  |  |  |  | 779653000
R-2248E | HIGHWAY | I-485 | EAST OF NC 115 (OLD STATESVILLE ROAD) TO I-85 NORTH | 10 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 10968000
R-2250 | HIGHWAY | NC 11/NC 903 (GREENVILLE SOUTHWEST BYPASS) | NC 11 TO US 264 (GREENVILLE BYPASS). CONSTRUCT FOUR LANE DIVIDED FACILITY ON NEW LOCATION WITH BYPASS OF WINTERVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | T | CONSTRUCTION | 750000 | FY 2023: 750000
R-2250 | HIGHWAY | NC 11/NC 903 (GREENVILLE SOUTHWEST BYPASS) | NC 11 TO US 264 (GREENVILLE BYPASS). CONSTRUCT FOUR LANE DIVIDED FACILITY ON NEW LOCATION WITH BYPASS OF WINTERVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  |  |  | 241492000
R-2301 | HIGHWAY | US 17 (NEW BERN BYPASS) | US 17 SOUTH OF NEW BERN TO US 17 NORTH OF NEW BERN. FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | 2 | New Bern Area MPO, Down East RPO | SECTION A GARVEE BOND FUNDING: $33.9 MILLION FOR CON, PAYBACK FY 2009-2020. |  |  |  |  | 78143000
R-2301A | HIGHWAY | US 17 NEW BERN BYPASS | US 17 SOUTH OF NEW BERN TO US 70. | 2 | New Bern Area MPO | COMPLETED. | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 3713000
R-2301B | HIGHWAY | US 17 NEW BERN BYPASS | US 70 TO US 17 NORTH OF NEW BERN. | 2 | Down East RPO, New Bern Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 146000000 | [11 empty] | 146000000
R-2301B | HIGHWAY | US 17 NEW BERN BYPASS | US 70 TO US 17 NORTH OF NEW BERN. | 2 | Down East RPO, New Bern Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 15800000 | [11 empty] | 15800000
R-2303 | HIGHWAY | NC 24 | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO I-40 IN DUPLIN COUNTY AT WARSAW. FOUR LANES DIVIDED, PART ON NEW LOCATION. | 3, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Eastern Carolina RPO | [5 empty] | 295231000
R-2303E | HIGHWAY | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 3 |  | T | ENGINEERING | 4395000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000
R-2303E | HIGHWAY | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 3 |  | T | CONSTRUCTION | 5486000
R-2303E | HIGHWAY | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 3 |  | T | BUILD NC CON | 25455000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 3394000
R-2303E | HIGHWAY | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 3 |  | T | BUILD NC CON | 5955000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000
R-2303E | HIGHWAY | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 3 |  | T | ENGINEERING | 660000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 88000
R-2303E | HIGHWAY | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 3 |  | T | BUILD NC ROW | 4395000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000
R-2303F | HIGHWAY | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | NOT FUNDED |  | T | CONSTRUCTION | 276700000 | [11 empty] | 276700000
R-2303F | HIGHWAY | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | NOT FUNDED |  | T | RIGHT-OF-WAY | 16800000 | [11 empty] | 16800000
R-2303F | HIGHWAY | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | NOT FUNDED |  | T | UTILITIES | 1960000 | [11 empty] | 1960000
R-2307 | HIGHWAY | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO US 21. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | SEGMENT B INCORPORATES WORK PREVIOUSLY UNDER I-5717. |  |  |  |  | 21114000
R-2307A | HIGHWAY | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $15.961 M FOR RIGHT-OF-WAY, PAYBACK FY 2027-2040 (FY 2026 / YR 8 SALE), BUILD NC BOND FUNDING: $18.736M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE) | REGION F |  | BGANY | CONSTRUCTION | 115901000 | FY 2030: 26211000; FY 2031: 33267000; FY 2032: 27625000; FY 2033: 20231000 | 8567000
R-2307A | HIGHWAY | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $15.961 M FOR RIGHT-OF-WAY, PAYBACK FY 2027-2040 (FY 2026 / YR 8 SALE), BUILD NC BOND FUNDING: $18.736M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE) | REGION F |  | T | BUILD NC ROW | 20536000 |  |  |  |  | 2739000 | 1369000 | 1369000 | 1369000 | 1369000 | 1369000 | 1369000 | 9583000
R-2307A | HIGHWAY | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $15.961 M FOR RIGHT-OF-WAY, PAYBACK FY 2027-2040 (FY 2026 / YR 8 SALE), BUILD NC BOND FUNDING: $18.736M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE) | REGION F |  | T | BUILD NC ROW | 24120000 | FY 2028: 1608000; FY 2029: 1608000; FY 2030: 1608000; FY 2031: 1608000; FY 2032: 1608000; FY 2033: 1608000 | 14472000
R-2307A | HIGHWAY | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $15.961 M FOR RIGHT-OF-WAY, PAYBACK FY 2027-2040 (FY 2026 / YR 8 SALE), BUILD NC BOND FUNDING: $18.736M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE) | REGION F |  | T | RIGHT-OF-WAY | 47603000 | FY 2027: 0; FY 2028: 5206000; FY 2029: 23942000; FY 2030: 1995000; FY 2031: 8230000; FY 2032: 8230000
R-2307A | HIGHWAY | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $15.961 M FOR RIGHT-OF-WAY, PAYBACK FY 2027-2040 (FY 2026 / YR 8 SALE), BUILD NC BOND FUNDING: $18.736M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE) | REGION F |  | T | UTILITIES | 17800000 | FY 2027: 8900000; FY 2028: 8900000
R-2307B | HIGHWAY | NC 150 | EAST OF SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | 12 | Charlotte Regional TPO, Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $5M IN STBG-DA FUNDS SWITCHED WITH $5M NHP AS PART OF FUND SWAP. | REGION F |  | NHP | CONSTRUCTION | 4000000 | FY 2025: 231000; FY 2026: 1160000; FY 2027: 1050000; FY 2028: 884000; FY 2029: 675000
R-2307B | HIGHWAY | NC 150 | EAST OF SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | 12 | Charlotte Regional TPO, Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $5M IN STBG-DA FUNDS SWITCHED WITH $5M NHP AS PART OF FUND SWAP. | REGION F |  | S(M) | CONSTRUCTION | 1001000 | FY 2025: 58000; FY 2026: 290000; FY 2027: 263000; FY 2028: 221000; FY 2029: 169000
R-2307B | HIGHWAY | NC 150 | EAST OF SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | 12 | Charlotte Regional TPO, Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $5M IN STBG-DA FUNDS SWITCHED WITH $5M NHP AS PART OF FUND SWAP. | REGION F |  | NHP | CONSTRUCTION | 159499000 | FY 2025: 9201000; FY 2026: 46247000; FY 2027: 41877000; FY 2028: 35241000; FY 2029: 26933000
R-2307BA | HIGHWAY | NC 150 | GOOD LUCK LANE TO MORRISON PLANTATION PARKWAY. EXTEND EASTBOUND RIGHT AND THROUGH LANE. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | REGION F |  | T | CONSTRUCTION | 1600000 | FY 2023: 1600000
R-2309 | HIGHWAY | US 220 | SR 2182 (HORSEPEN CREEK ROAD) TO US 220-NC 68 CONNECTOR (R-2413) IN GREENSBORO AND SUMMERFIELD. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO | [5 empty] | 75385000
R-2409 | HIGHWAY | US 64 | NC 107 AT CASHIERS TO US 178 AT ROSMAN. SAFETY IMPROVEMENTS AND CLIMBING LANES AT SELECTED LOCATIONS. | 14 | Land-of-Sky RPO, Southwestern RPO | DIVISION PROJECT |  |  |  |  | 28474000
R-2409D | HIGHWAY | US 64 | INDIAN CREEK TO FLAT CREEK VALLEY ROAD. WIDENING AND REALIGNMENT | 14 | Land-of-Sky RPO |  | NOT FUNDED |  | BGLT5 | CONSTRUCTION | 5000000 | [11 empty] | 5000000
R-2409D | HIGHWAY | US 64 | INDIAN CREEK TO FLAT CREEK VALLEY ROAD. WIDENING AND REALIGNMENT | 14 | Land-of-Sky RPO |  | NOT FUNDED |  | BGLT5 | RIGHT-OF-WAY | 1000000 | [11 empty] | 1000000
R-2413 | HIGHWAY | FUTURE I-73 | NC 68 AT SR 2011 (EDGEFIELD ROAD) IN GUILFORD COUNTY TO US 220-NC 68 INTERSECTION IN ROCKINGHAM COUNTY. FOUR-LANE FREEWAY, ON NEW LOCATION, NC 68 TO US 220 AND FOUR LANES ALONG US 220 TO NC 68 IN ROCKINGHAM COUNTY. | 7 | Greensboro Urban Area MPO, Piedmont Triad RPO |  | PRE-STI (TRANSITION) |  |  |  | 311602000
R-2501 | HIGHWAY | US 1 | SOUTH CAROLINA STATE LINE TO SR 1001 (MARSTON ROAD). WIDEN TO FOUR LANES WITH VARIABLE WIDTH MEDIAN WITH BYPASS OF ROCKINGHAM ON NEW LOCATION. | 8 | Lumber River RPO | [5 empty] | 28064000
R-2501A | HIGHWAY | US 1 | SOUTH CAROLINA STATE LINE TO SR 1104 (OSBORNE ROAD) | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | NOT FUNDED |  | T | CONSTRUCTION | 25700000 | [11 empty] | 25700000
R-2501A | HIGHWAY | US 1 | SOUTH CAROLINA STATE LINE TO SR 1104 (OSBORNE ROAD) | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | NOT FUNDED |  | T | RIGHT-OF-WAY | 4500000 | [11 empty] | 4500000
R-2501BA | HIGHWAY | US 1 | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | NOT FUNDED |  | T | RIGHT-OF-WAY | 5519000 | [11 empty] | 5519000
R-2501BA | HIGHWAY | US 1 | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | NOT FUNDED |  | T | UTILITIES | 908000 | [11 empty] | 908000
R-2501BA | HIGHWAY | US 1 | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | NOT FUNDED |  | T | CONSTRUCTION | 40500000 | [11 empty] | 40500000
R-2501BB | HIGHWAY | US 1 | US 74 BYPASS TO US 74 BUSINESS | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | NOT FUNDED |  | T | UTILITIES | 2523000 | [11 empty] | 2523000
R-2501BB | HIGHWAY | US 1 | US 74 BYPASS TO US 74 BUSINESS | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | NOT FUNDED |  | T | CONSTRUCTION | 67700000 | [11 empty] | 67700000
R-2501BB | HIGHWAY | US 1 | US 74 BYPASS TO US 74 BUSINESS | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | NOT FUNDED |  | T | RIGHT-OF-WAY | 13300000 | [11 empty] | 13300000
R-2501BC | HIGHWAY | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | 8 | Lumber River RPO | COORDINATE WITH R-5928 | NOT FUNDED |  | T | CONSTRUCTION | 101101000 | [11 empty] | 101101000
R-2501BC | HIGHWAY | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | 8 | Lumber River RPO | COORDINATE WITH R-5928 | NOT FUNDED |  | T | RIGHT-OF-WAY | 24248000 | [11 empty] | 24248000
R-2501BC | HIGHWAY | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | 8 | Lumber River RPO | COORDINATE WITH R-5928 | NOT FUNDED |  | T | UTILITIES | 6950000 | [11 empty] | 6950000
R-2501C | HIGHWAY | US 1 | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 8 |  | T | ENGINEERING | 217000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 49000
R-2501C | HIGHWAY | US 1 | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 8 |  | T | BUILD NC CON | 9015000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000
R-2501C | HIGHWAY | US 1 | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 8 |  | T | BUILD NC CON | 3960000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 300000
R-2511 | HIGHWAY | US 17 | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 1, 2 |  | T | RIGHT-OF-WAY | 10471000 | FY 2023: 1000000; FY 2024: 1000000; FY 2025: 1221000
R-2511 | HIGHWAY | US 17 | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 1, 2 |  | T | UTILITIES | 2200000
R-2511 | HIGHWAY | US 17 | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 1, 2 |  | T | CONSTRUCTION | 99343000 | FY 2023: 35764000; FY 2024: 26823000; FY 2025: 20862000; FY 2026: 14901000
R-2511 | HIGHWAY | US 17 | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 1, 2 |  |  |  | 16222000
R-2513 | HIGHWAY | US 17 | NC 43 TO SR 1438 (SPRUILL TOWN ROAD). WIDEN TO MULTI-LANES. | 2 | Down East RPO | [5 empty] | 1914000
R-2513A | HIGHWAY | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | 2 | Down East RPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 3000000 | FY 2026: 1252000; FY 2027: 1148000; FY 2028: 300000; FY 2029: 300000
R-2513A | HIGHWAY | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | 2 | Down East RPO |  | DIVISION 2 |  | T | UTILITIES | 2400000 | FY 2026: 1200000; FY 2027: 1200000
R-2513A | HIGHWAY | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | 2 | Down East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 15200000 | FY 2028: 152000; FY 2029: 8782000; FY 2030: 5864000; FY 2031: 402000
R-2513B | HIGHWAY | US 17 | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). | 2 | Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 800000 | [11 empty] | 800000
R-2513B | HIGHWAY | US 17 | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). | 2 | Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 16300000 | [11 empty] | 16300000
R-2513B | HIGHWAY | US 17 | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). | 2 | Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5800000 | [11 empty] | 5800000
R-2513C | HIGHWAY | US 17 | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). | 2 | Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 600000 | [11 empty] | 600000
R-2513C | HIGHWAY | US 17 | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). | 2 | Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 11300000 | [11 empty] | 11300000
R-2513C | HIGHWAY | US 17 | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). | 2 | Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2300000 | [11 empty] | 2300000
R-2513D | HIGHWAY | US 17 | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. | 2 | Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 4600000 | [11 empty] | 4600000
R-2513D | HIGHWAY | US 17 | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. | 2 | Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 600000 | [11 empty] | 600000
R-2513D | HIGHWAY | US 17 | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. | 2 | Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 21000000 | [11 empty] | 21000000
R-2513E | HIGHWAY | US 17 | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). | 2 | Mid-East RPO |  | NOT FUNDED |  | T | UTILITIES | 600000 | [11 empty] | 600000
R-2513E | HIGHWAY | US 17 | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). | 2 | Mid-East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 18300000 | [11 empty] | 18300000
R-2513E | HIGHWAY | US 17 | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). | 2 | Mid-East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 4600000 | [11 empty] | 4600000
R-2514 | HIGHWAY | US 17 | MULTI-LANES NORTH OF JACKSONVILLE TO NEW BERN BYPASS. WIDEN TO MULTI-LANES WITH BYPASSES OF BELGRADE, MAYSVILLE AND POLLOCKSVILLE ON NEW LOCATION. | 2, 3 | Down East RPO, Jacksonville Urban Area MPO | [5 empty] | 233049000
R-2520 | HIGHWAY | US 19E, NC 194 | MULTI-LANE SECTION EAST OF SPRUCE PINE TO US 221. WIDEN TO MULTI-LANES. | 11, 13 | High Country RPO | [5 empty] | 5169000
R-2520A | HIGHWAY | US 19E | MULTI-LANES EAST OF SPRUCE PINE TO SR 1106. WIDEN TO MULTI-LANES. | 11, 13 | High Country RPO |  | DIVISION 11, 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 14700000
R-2520A | HIGHWAY | US 19E | MULTI-LANES EAST OF SPRUCE PINE TO SR 1106. WIDEN TO MULTI-LANES. | 11, 13 | High Country RPO |  | DIVISION 11, 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4000000
R-2520A | HIGHWAY | US 19E | MULTI-LANES EAST OF SPRUCE PINE TO SR 1106. WIDEN TO MULTI-LANES. | 11, 13 | High Country RPO |  | DIVISION 11, 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 50801000
R-2520B | HIGHWAY | US 19E-NC 194 | SR 1106 TO US 221. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 25600000 | [11 empty] | 25600000
R-2520B | HIGHWAY | US 19E-NC 194 | SR 1106 TO US 221. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 4300000 | [11 empty] | 4300000
R-2522 | HIGHWAY | US 21 - NC 115 | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 16800000
R-2522 | HIGHWAY | US 21 - NC 115 | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3100000
R-2522 | HIGHWAY | US 21 - NC 115 | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 808000
R-2522 | HIGHWAY | US 21 - NC 115 | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 14900000
R-2527 | HIGHWAY | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | REGION E |  | T | BUILD NC ROW | 854000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 56000
R-2527 | HIGHWAY | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | REGION E |  |  |  | 200000
R-2527 | HIGHWAY | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | REGION E |  | BGLT5 | CONSTRUCTION | 106600000 | FY 2025: 24484000; FY 2026: 31398000; FY 2027: 25938000; FY 2028: 18586000; FY 2029: 6194000
R-2527 | HIGHWAY | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | REGION E |  | T | ENGINEERING | 7802000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 522000
R-2530 | HIGHWAY | NC 24/NC 27 | SR 1963 (ST. MARTIN ROAD) IN ALBEMARLE TO NC 73. WIDEN TO MULTI- LANES. (COORDINATE WITH B-4974). | 10 | Rocky River RPO | [5 empty] | 45876000
R-2530B | HIGHWAY | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | CONSTRUCTION | 27914000 | FY 2023: 6979000
R-2530B | HIGHWAY | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | ENGINEERING | 7620000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000
R-2530B | HIGHWAY | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | ENGINEERING | 420000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 56000
R-2530B | HIGHWAY | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | BUILD NC ROW | 5700000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000
R-2530B | HIGHWAY | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | BUILD NC UTL | 3600000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
R-2530B | HIGHWAY | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | BUILD NC CON | 15015000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000
R-2530B | HIGHWAY | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | BUILD NC CON | 47640000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 6352000
R-2536 | HIGHWAY | US 64 | ASHEBORO SOUTHERN BYPASS, US 64 WEST TO US 64 EAST. FOUR-LANE FREEWAY ON NEW LOCATION WITH INTERCHANGES AT US 220, NC 49 AND ZOO ACCESS AT NC 159. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT | PRE-STI (TRANSITION) |  |  |  | 373758000
R-2544 | HIGHWAY | US 64 | EAST OF SR 1153 (OLD FERRY LANDING ROAD) TO US 264. WIDEN TO MULTI-LANES. | 1 | Albemarle RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. |  |  |  |  | 8333000
R-2544A | HIGHWAY | US 64 | EAST OF SR 1153 (OLD FERRY LANDING ROAD) TO WEST OF SR 1102 (EAST LAKE ROAD). | 1 | Albemarle RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 14700000 | [11 empty] | 14700000
R-2544A | HIGHWAY | US 64 | EAST OF SR 1153 (OLD FERRY LANDING ROAD) TO WEST OF SR 1102 (EAST LAKE ROAD). | 1 | Albemarle RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 1175000 | [11 empty] | 1175000
R-2544A | HIGHWAY | US 64 | EAST OF SR 1153 (OLD FERRY LANDING ROAD) TO WEST OF SR 1102 (EAST LAKE ROAD). | 1 | Albemarle RPO |  | NOT FUNDED |  | T | UTILITIES | 315000 | [11 empty] | 315000
R-2544B | HIGHWAY | US 64 | WEST OF SR 1102 (EAST LAKE ROAD) TO EAST OF DARE COUNTY LANDFILL. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | UTILITIES | 1401000 | [11 empty] | 1401000
R-2544B | HIGHWAY | US 64 | WEST OF SR 1102 (EAST LAKE ROAD) TO EAST OF DARE COUNTY LANDFILL. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 23300000 | [11 empty] | 23300000
R-2544B | HIGHWAY | US 64 | WEST OF SR 1102 (EAST LAKE ROAD) TO EAST OF DARE COUNTY LANDFILL. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 1350000 | [11 empty] | 1350000
R-2544C | HIGHWAY | US 64 | EAST OF DARE COUNTY LANDFILL TO US 264. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | UTILITIES | 1860000 | [11 empty] | 1860000
R-2544C | HIGHWAY | US 64 | EAST OF DARE COUNTY LANDFILL TO US 264. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 46200000 | [11 empty] | 46200000
R-2544C | HIGHWAY | US 64 | EAST OF DARE COUNTY LANDFILL TO US 264. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 300000 | [11 empty] | 300000
R-2545 | HIGHWAY | US 64 | EAST OF COLUMBIA TO EAST OF THE ALLIGATOR RIVER. WIDEN TO MULTI-LANES. | 1 | Albemarle RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. |  |  |  |  | 4242000
R-2545AA | HIGHWAY | US 64 | EAST OF COLUMBIA TO WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 1825000 | [11 empty] | 1825000
R-2545AA | HIGHWAY | US 64 | EAST OF COLUMBIA TO WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | UTILITIES | 1395000 | [11 empty] | 1395000
R-2545AA | HIGHWAY | US 64 | EAST OF COLUMBIA TO WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 24800000 | [11 empty] | 24800000
R-2545AB | HIGHWAY | US 64 | WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER TO WEST OF ALLIGATOR RIVER. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | UTILITIES | 1611000 | [11 empty] | 1611000
R-2545AB | HIGHWAY | US 64 | WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER TO WEST OF ALLIGATOR RIVER. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 72500000 | [11 empty] | 72500000
R-2545AB | HIGHWAY | US 64 | WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER TO WEST OF ALLIGATOR RIVER. | 1 | Albemarle RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2025000 | [11 empty] | 2025000
R-2545B | HIGHWAY | US 64 | WEST OF ALLIGATOR RIVER TO EAST OF SR 1153 (OLD FERRY LANDING ROAD). | 1 | Albemarle RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3175000 | [11 empty] | 3175000
R-2545B | HIGHWAY | US 64 | WEST OF ALLIGATOR RIVER TO EAST OF SR 1153 (OLD FERRY LANDING ROAD). | 1 | Albemarle RPO |  | NOT FUNDED |  | T | UTILITIES | 1156000 | [11 empty] | 1156000
R-2545B | HIGHWAY | US 64 | WEST OF ALLIGATOR RIVER TO EAST OF SR 1153 (OLD FERRY LANDING ROAD). | 1 | Albemarle RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 503100000 | [11 empty] | 503100000
R-2553 | HIGHWAY | US 70 (FUTURE I-42) | EXISTING FREEWAY NEAR LAGRANGE TO EXISTING FREEWAY NEAR DOVER. UPGRADE ROADWAY TO FREEWAY, PART ON NEW LOCATION. | 2 | Eastern Carolina RPO | [5 empty] | 7924000
R-2553A | HIGHWAY | US 70 (FUTURE I-42) | EXISTING FREEWAY NEAR LAGRANGE TO SR 1522 (ALBERT SUGGS ROAD). | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 44000000 | [11 empty] | 44000000
R-2553A | HIGHWAY | US 70 (FUTURE I-42) | EXISTING FREEWAY NEAR LAGRANGE TO SR 1522 (ALBERT SUGGS ROAD). | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 45842000 | [11 empty] | 45842000
R-2553A | HIGHWAY | US 70 (FUTURE I-42) | EXISTING FREEWAY NEAR LAGRANGE TO SR 1522 (ALBERT SUGGS ROAD). | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | UTILITIES | 1447000 | [11 empty] | 1447000
R-2553B | HIGHWAY | US 70 (FUTURE I-42) | SR 1522 (ALBERT SUGGS ROAD) TO NC 148 (HARVEY PARKWAY). | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 55801000 | [11 empty] | 55801000
R-2553B | HIGHWAY | US 70 (FUTURE I-42) | SR 1522 (ALBERT SUGGS ROAD) TO NC 148 (HARVEY PARKWAY). | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 8300000 | [11 empty] | 8300000
R-2553B | HIGHWAY | US 70 (FUTURE I-42) | SR 1522 (ALBERT SUGGS ROAD) TO NC 148 (HARVEY PARKWAY). | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | UTILITIES | 6000000 | [11 empty] | 6000000
R-2553C | HIGHWAY | US 70 (FUTURE I-42) | NC 148 (HARVEY PARKWAY) TO US 70 EAST OF NC 58. | 2 | Eastern Carolina RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 82600000
R-2553C | HIGHWAY | US 70 (FUTURE I-42) | NC 148 (HARVEY PARKWAY) TO US 70 EAST OF NC 58. | 2 | Eastern Carolina RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3900000
R-2553C | HIGHWAY | US 70 (FUTURE I-42) | NC 148 (HARVEY PARKWAY) TO US 70 EAST OF NC 58. | 2 | Eastern Carolina RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 320701000
R-2553D | HIGHWAY | US 70 (FUTURE I-42) | EAST OF NC 58 TO EAST OF SR 1002 (WYSE FORK ROAD). | 2 | Eastern Carolina RPO, Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 14731000 | [11 empty] | 14731000
R-2553D | HIGHWAY | US 70 (FUTURE I-42) | EAST OF NC 58 TO EAST OF SR 1002 (WYSE FORK ROAD). | 2 | Eastern Carolina RPO, Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 1964000 | [11 empty] | 1964000
R-2553D | HIGHWAY | US 70 (FUTURE I-42) | EAST OF NC 58 TO EAST OF SR 1002 (WYSE FORK ROAD). | 2 | Eastern Carolina RPO, Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 60000000 | [11 empty] | 60000000
R-2553E | HIGHWAY | US 70 (FUTURE I-42) | EAST OF SR 1002 (WYSE FORK ROAD) TO EXISTING FREEWAY NEAR DOVER. | 2 | Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 6805000 | [11 empty] | 6805000
R-2553E | HIGHWAY | US 70 (FUTURE I-42) | EAST OF SR 1002 (WYSE FORK ROAD) TO EXISTING FREEWAY NEAR DOVER. | 2 | Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 1756000 | [11 empty] | 1756000
R-2553E | HIGHWAY | US 70 (FUTURE I-42) | EAST OF SR 1002 (WYSE FORK ROAD) TO EXISTING FREEWAY NEAR DOVER. | 2 | Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 53000000 | [11 empty] | 53000000
R-2555 | HIGHWAY | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO EAST OF SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | 10 | Charlotte Regional TPO | [5 empty] | 44964000
R-2555B | HIGHWAY | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 5/6 SALE). | DIVISION 10 |  | T | CONSTRUCTION | 12100000 | FY 2026: 0; FY 2027: 6509000; FY 2028: 5591000
R-2555B | HIGHWAY | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 5/6 SALE). | DIVISION 10 |  | L | CONSTRUCTION | 1199000 | FY 2026: 401000; FY 2027: 520000; FY 2028: 278000
R-2555B | HIGHWAY | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 5/6 SALE). | DIVISION 10 |  | T | BUILD NC CON | 15450000 |  |  | 2060000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 5150000
R-2561 | HIGHWAY | NC 87 | ELIZABETHTOWN BYPASS IN BLADEN COUNTY TO US 74/US 76 IN COLUMBUS COUNTY. WIDEN TO MULTI-LANES. | 6 | Cape Fear RPO, Mid-Carolina RPO | [5 empty] | 10957000
R-2561A | HIGHWAY | NC 87 | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. | 6 | Mid-Carolina RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 96100000 | [11 empty] | 96100000
R-2561A | HIGHWAY | NC 87 | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. | 6 | Mid-Carolina RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 13781000 | [11 empty] | 13781000
R-2561A | HIGHWAY | NC 87 | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. | 6 | Mid-Carolina RPO |  | NOT FUNDED |  | T | UTILITIES | 1654000 | [11 empty] | 1654000
R-2561B | HIGHWAY | NC 87 | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. | 6 | Cape Fear RPO, Mid-Carolina RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 57000000 | [11 empty] | 57000000
R-2561B | HIGHWAY | NC 87 | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. | 6 | Cape Fear RPO, Mid-Carolina RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 13437000 | [11 empty] | 13437000
R-2561B | HIGHWAY | NC 87 | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. | 6 | Cape Fear RPO, Mid-Carolina RPO |  | NOT FUNDED |  | T | UTILITIES | 1612000 | [11 empty] | 1612000
R-2561C | HIGHWAY | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | 6 | Cape Fear RPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 26512000
R-2561C | HIGHWAY | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | 6 | Cape Fear RPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4488000
R-2561C | HIGHWAY | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | 6 | Cape Fear RPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 85800000
R-2561CA | HIGHWAY | NC 87 | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | REGION C |  | BGLT5 | CONSTRUCTION | 29700000 | FY 2023: 1884000; FY 2024: 12625000; FY 2025: 10446000; FY 2026: 4745000
R-2561CA | HIGHWAY | NC 87 | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | REGION C |  | T | RIGHT-OF-WAY | 3304000
R-2561CA | HIGHWAY | NC 87 | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | REGION C |  | T | UTILITIES | 3000000
R-2561CB | HIGHWAY | NC 87 | CONSTRUCT DETOUR ROUTE. | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | REGION C |  | T | CONSTRUCTION | 900000 | FY 2023: 900000
R-2566 | HIGHWAY | NC 105 | US 221 TO SR 1107 (NC 105 BYPASS) IN BOONE. WIDEN TO MULTI-LANES. | 11 | High Country RPO | [5 empty] | 11735000
R-2566A | HIGHWAY | NC 105 | US 221 IN AVERY COUNTY TO SR 1136 (CLARKS CREEK ROAD) IN WATAUGA COUNTY. | 11 | High Country RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 60350000 | [11 empty] | 60350000
R-2566A | HIGHWAY | NC 105 | US 221 IN AVERY COUNTY TO SR 1136 (CLARKS CREEK ROAD) IN WATAUGA COUNTY. | 11 | High Country RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 1000000 | [11 empty] | 1000000
R-2566B | HIGHWAY | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $4M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | NHP | CONSTRUCTION | 87600000 | FY 2025: 876000; FY 2026: 29411000; FY 2027: 26908000; FY 2028: 19979000; FY 2029: 10426000
R-2566B | HIGHWAY | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $4M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | T | BUILD NC ROW | 5145000 | 343000 | 343000 | 343000 | 343000 | 343000 | 343000 | 343000 | 343000 | 343000 | 343000 | 343000 | 1029000
R-2566B | HIGHWAY | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $4M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | T | RIGHT-OF-WAY | 9220000 | FY 2023: 850000; FY 2024: 4185000; FY 2025: 4185000
R-2566B | HIGHWAY | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $4M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | T | UTILITIES | 13700000 | FY 2023: 6350000; FY 2024: 6350000
R-2566BA | HIGHWAY | NC 105 | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | DIVISION 11 |  | T | BUILD NC CON | 7980000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 1596000
R-2566BA | HIGHWAY | NC 105 | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | DIVISION 11 |  | T | UTILITIES | 2850000
R-2566BA | HIGHWAY | NC 105 | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | DIVISION 11 |  | T | CONSTRUCTION | 15700000 | FY 2023: 8224000; FY 2024: 6194000; FY 2025: 1282000
R-2566BB | HIGHWAY | NC 105 | SR 1658 (OLD SHULLS MILL ROAD) INTERSECTION. REALIGN SR 1658 (OLD SHULLS MILL ROAD). | 11 | High Country RPO | UNDER CONSTRUCTION. | REGION F |  | T | CONSTRUCTION | 1600000 | FY 2023: 1600000
R-2574 | HIGHWAY | US 158 (SHORTCUT ROAD) | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | 1 | Albemarle RPO |  | REGION A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 24151000
R-2574 | HIGHWAY | US 158 (SHORTCUT ROAD) | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | 1 | Albemarle RPO |  | REGION A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 5176000
R-2574 | HIGHWAY | US 158 (SHORTCUT ROAD) | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | 1 | Albemarle RPO |  | REGION A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 76201000
R-2574 | HIGHWAY | US 158 (SHORTCUT ROAD) | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | 1 | Albemarle RPO |  | REGION A | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3523000
R-2576 | HIGHWAY | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2024-2038. | DIVISION 1 |  | BOND R | RIGHT-OF-WAY | 16496000 | FY 2024: 165000; FY 2025: 6434000; FY 2026: 6597000; FY 2027: 1650000; FY 2028: 1650000
R-2576 | HIGHWAY | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2024-2038. | DIVISION 1 |  | S(M) | CONSTRUCTION | 43327000 | FY 2024: 10831000; FY 2025: 10832000; FY 2026: 10832000; FY 2027: 10832000
R-2576 | HIGHWAY | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2024-2038. | DIVISION 1 |  | BOND R | UTILITIES | 17412000 | FY 2024: 8706000; FY 2025: 8706000
R-2576 | HIGHWAY | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2024-2038. | DIVISION 1 |  |  |  | 44244000
R-2576 | HIGHWAY | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2024-2038. | DIVISION 1 |  | BGLT5 | GARVEE CON | 167280000 |  | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 55760000
R-2576 | HIGHWAY | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2024-2038. | DIVISION 1 |  | BOND R | CONSTRUCTION | 223397000 | FY 2024: 55849000; FY 2025: 55849000; FY 2026: 55849000; FY 2027: 55850000
R-2577 | HIGHWAY | US 158 | MULTLANES NORTH OF US 421 / I-40 BUSINESS IN WINSTON-SALEM TO US 220 IN STOKESDALE. WIDEN TO A FOUR LANE DIVIDED FACILITY | 7, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO | [5 empty] | 5058000
R-2577A | HIGHWAY | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 9 | Winston-Salem Urban Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE) | REGION D |  | T | RIGHT-OF-WAY | 36300000 | FY 2023: 12100000
R-2577A | HIGHWAY | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 9 | Winston-Salem Urban Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE) | REGION D |  | T | UTILITIES | 469000
R-2577A | HIGHWAY | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 9 | Winston-Salem Urban Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE) | REGION D |  | T | BUILD NC CON | 19305000 |  | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 6435000
R-2577A | HIGHWAY | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 9 | Winston-Salem Urban Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE) | REGION D |  | T | CONSTRUCTION | 54600000 | FY 2024: 7461000; FY 2025: 18918000; FY 2026: 15067000; FY 2027: 10430000; FY 2028: 2724000
R-2577B | HIGHWAY | US 158 | SR 1965 (BELEWS CREEK ROAD) IN FORSYTH COUNTY TO SR 2034 (ANTHONY ROAD) IN GUILFORD COUNTY. WIDEN TO MULTI-LANES. | 7, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 38800000
R-2577B | HIGHWAY | US 158 | SR 1965 (BELEWS CREEK ROAD) IN FORSYTH COUNTY TO SR 2034 (ANTHONY ROAD) IN GUILFORD COUNTY. WIDEN TO MULTI-LANES. | 7, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9700000
R-2577B | HIGHWAY | US 158 | SR 1965 (BELEWS CREEK ROAD) IN FORSYTH COUNTY TO SR 2034 (ANTHONY ROAD) IN GUILFORD COUNTY. WIDEN TO MULTI-LANES. | 7, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 60300000
R-2577C | HIGHWAY | US 158 | NORTH OF SR 2034 (ANTHONY ROAD) TO US 220. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 74608000 | [11 empty] | 74608000
R-2577C | HIGHWAY | US 158 | NORTH OF SR 2034 (ANTHONY ROAD) TO US 220. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 625000 | [11 empty] | 625000
R-2577C | HIGHWAY | US 158 | NORTH OF SR 2034 (ANTHONY ROAD) TO US 220. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 48400000 | [11 empty] | 48400000
R-2582 | HIGHWAY | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. WIDEN TO MULTI-LANES WITH BYPASS OF JACKSON, SOME NEW LOCATION. | 1 | Peanut Belt RPO | [5 empty] | 17713000
R-2582A | HIGHWAY | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 1 |  | T | ENGINEERING | 5130000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000
R-2582A | HIGHWAY | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 1 |  | T | CONSTRUCTION | 50214000 | FY 2023: 12714000; FY 2024: 17250000; FY 2025: 17250000; FY 2026: 3000000
R-2582A | HIGHWAY | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 1 |  | T | BUILD NC CON | 41265000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 5502000
R-2582A | HIGHWAY | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 1 |  | T | BUILD NC CON | 15330000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000
R-2582A | HIGHWAY | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 1 |  | T | ENGINEERING | 3690000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 492000
R-2582A | HIGHWAY | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 1 |  | T | BUILD NC ROW | 3345000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000
R-2582B | HIGHWAY | US 158/NC 46 | SR 1312 (ST. JOHN CHURCH ROAD) TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. | 1 | Peanut Belt RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5400000 | [11 empty] | 5400000
R-2582B | HIGHWAY | US 158/NC 46 | SR 1312 (ST. JOHN CHURCH ROAD) TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. | 1 | Peanut Belt RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 61400000 | [11 empty] | 61400000
R-2588 | HIGHWAY | NC 191 | US 25 IN HENDERSONVILLE TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | 14 | French Broad River MPO | [5 empty] | 1326000
R-2588A | HIGHWAY | NC 191 | US 25 TO SR 1381 (MOUNTAIN ROAD). | 14 | French Broad River MPO |  | NOT FUNDED |  | BGANY | RIGHT-OF-WAY | 15200000 | [11 empty] | 15200000
R-2588A | HIGHWAY | NC 191 | US 25 TO SR 1381 (MOUNTAIN ROAD). | 14 | French Broad River MPO |  | NOT FUNDED |  | BGANY | UTILITIES | 1800000 | [11 empty] | 1800000
R-2588A | HIGHWAY | NC 191 | US 25 TO SR 1381 (MOUNTAIN ROAD). | 14 | French Broad River MPO |  | NOT FUNDED |  | BGANY | CONSTRUCTION | 18800000 | [11 empty] | 18800000
R-2588B | HIGHWAY | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). BUILD NC BONDS: $17.7M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (YR 10 / 2028 SALE). | DIVISION 14 |  | NHP | UTILITIES | 15500000 | FY 2023: 7750000
R-2588B | HIGHWAY | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). BUILD NC BONDS: $17.7M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (YR 10 / 2028 SALE). | DIVISION 14 |  | T | RIGHT-OF-WAY | 9500000 | FY 2023: 2600000; FY 2024: 1900000
R-2588B | HIGHWAY | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). BUILD NC BONDS: $17.7M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (YR 10 / 2028 SALE). | DIVISION 14 |  | T | BUILD NC CON | 22785000 |  |  |  | 1519000 | 1519000 | 1519000 | 1519000 | 1519000 | 1519000 | 1519000 | 1519000 | 10633000
R-2588B | HIGHWAY | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). BUILD NC BONDS: $17.7M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (YR 10 / 2028 SALE). | DIVISION 14 |  | T | CONSTRUCTION | 94901000 | FY 2024: 24462000; FY 2025: 32236000; FY 2026: 8478000; FY 2027: 19353000; FY 2028: 10372000
R-2597 | HIGHWAY | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) IN RUTHERFORD COUNTY TO SR 1153 (GOOSE CREEK ROAD) IN MCDOWELL COUNTY. WIDEN TO MULTI-LANES. | 13 | Foothills RPO | [5 empty] | 10000
R-2597A | HIGHWAY | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) TO SR 1325 (NANNEY TOWN ROAD). WIDEN TO MULTI-LANES. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 69201000 | [11 empty] | 69201000
R-2597A | HIGHWAY | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) TO SR 1325 (NANNEY TOWN ROAD). WIDEN TO MULTI-LANES. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | UTILITIES | 3400000 | [11 empty] | 3400000
R-2597A | HIGHWAY | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) TO SR 1325 (NANNEY TOWN ROAD). WIDEN TO MULTI-LANES. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 12600000 | [11 empty] | 12600000
R-2597B | HIGHWAY | US 221 | SR 1325 (NANNEY TOWN ROAD) TO SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 7700000 | [11 empty] | 7700000
R-2597B | HIGHWAY | US 221 | SR 1325 (NANNEY TOWN ROAD) TO SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | UTILITIES | 1800000 | [11 empty] | 1800000
R-2597B | HIGHWAY | US 221 | SR 1325 (NANNEY TOWN ROAD) TO SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 42400000 | [11 empty] | 42400000
R-2597C | HIGHWAY | US 221 | SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION TO SR 1153 (GOOSE CREEK ROAD). | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 9800000 | [11 empty] | 9800000
R-2597C | HIGHWAY | US 221 | SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION TO SR 1153 (GOOSE CREEK ROAD). | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | UTILITIES | 5800000 | [11 empty] | 5800000
R-2597C | HIGHWAY | US 221 | SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION TO SR 1153 (GOOSE CREEK ROAD). | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 117500000 | [11 empty] | 117500000
R-2603 | HIGHWAY | NC 268 | NC 18 TO SR 1966 (AIRPORT ROAD). CONSTRUCT SIDEWALK FROM NC 18 TO SHAVER STREET. WIDEN TO FIVE-LANES FROM SHAVER STREET TO FAIRPLAINS ROAD. WIDEN TO FOUR-LANES DIVIDED FROM FAIRPLAINS ROAD TO SR 1966 (AIRPORT ROAD). | 11 | High Country RPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 35831000
R-2612 | HIGHWAY | US 421 | SR 3389 (WOODY MILL ROAD) AND SR 3418 (NEELLEY ROAD) SOUTH OF GREENSBORO. CONVERT AT-GRADE INTERSECTIONS TO INTERCHANGES. | 7 | Greensboro Urban Area MPO |  | EXEMPT |  |  |  | 41680000
R-2615 | HIGHWAY | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | REGION F |  | T | RIGHT-OF-WAY | 40900000 | FY 2027: 409000; FY 2028: 8515000; FY 2029: 11898000; FY 2030: 11898000; FY 2031: 8180000
R-2615 | HIGHWAY | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | REGION F |  | T | UTILITIES | 1500000 | FY 2027: 750000; FY 2028: 750000
R-2615 | HIGHWAY | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | REGION F |  | T | CONSTRUCTION | 50199000 | FY 2030: 502000; FY 2031: 15511000; FY 2032: 16345000; FY 2033: 11989000 | 5852000
R-2615 | HIGHWAY | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | REGION F |  |  |  | 750000
R-2632 | HIGHWAY | NC 73 | US 21 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH R-5706A & B. $7.273M IN NHP FUNDS SWITCHED WITH $7.237M IN BGDA AS PART OF FUND SWAP 8-9-22. |  |  |  |  | 30912000
R-2632AB | HIGHWAY | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | BGDA | CONSTRUCTION | 7273000 | FY 2026: 73000; FY 2027: 3047000; FY 2028: 2464000; FY 2029: 1376000; FY 2030: 313000
R-2632AB | HIGHWAY | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | S(M) | CONSTRUCTION | 1818000 | FY 2026: 18000; FY 2027: 762000; FY 2028: 616000; FY 2029: 344000; FY 2030: 78000
R-2632AB | HIGHWAY | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | NHP | CONSTRUCTION | 49309000 | FY 2026: 493000; FY 2027: 20655000; FY 2028: 16708000; FY 2029: 9331000; FY 2030: 2122000
R-2632AB | HIGHWAY | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | NHP | RIGHT-OF-WAY | 8300000 | FY 2023: 184000; FY 2024: 2213000; FY 2025: 2213000; FY 2026: 2030000; FY 2027: 1660000
R-2632AB | HIGHWAY | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | NHP | UTILITIES | 5100000 | FY 2023: 2550000; FY 2024: 2550000
R-2633 | HIGHWAY | I-140/US 17 (WILMINGTON BYPASS) | US 17 SOUTH OF NC 87 IN BRUNSWICK COUNTY TO I-40 IN NEW HANOVER COUNTY. FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | [5 empty] | 684220000
R-2633AA | HIGHWAY | I-140/US 17 WILMINGTON BYPASS | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. | 3 | Wilmington Urban Area MPO | COMPLETED. GARVEE BOND FUNDING: $31.05M FOR CONSTRUCTION, PAYBACK 2010 - 2021. | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 6810000
R-2633BA | HIGHWAY | I-140/US 17 WILMINGTON BYPASS | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO SR 1430 (CEDAR HILL ROAD). | 3 | Wilmington Urban Area MPO | COMPLETED. GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK 2014 - 2025. | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 30750000 | FY 2023: 5125000; FY 2024: 5125000; FY 2025: 5125000
R-2633BB | HIGHWAY | I-140/US 17 WILMINGTON BYPASS | SR 1430 (CEDAR HILL ROAD) TO WEST OF US 421 NORTH OF WILMINGTON. | 3 | Wilmington Urban Area MPO | COMPLETED. GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK 2013 - 2024. | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 51250000 | FY 2023: 10250000; FY 2024: 10250000
R-2707 | HIGHWAY | US 74 (SHELBY BYPASS) | FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | 12 | Gaston-Cleveland-Lincoln MPO | [5 empty] | 252509000
R-2707C | HIGHWAY | US 74 SHELBY BYPASS | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | REGION F |  | T | ENGINEERING | 75000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 10000
R-2707C | HIGHWAY | US 74 SHELBY BYPASS | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | REGION F |  | T | BUILD NC CON | 14595000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000
R-2707C | HIGHWAY | US 74 SHELBY BYPASS | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | REGION F |  | T | BUILD NC CON | 25740000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 3432000
R-2707D | HIGHWAY | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | REGION F |  | T | CONSTRUCTION | 55900000 | FY 2024: 0; FY 2025: 11948000; FY 2026: 24919000; FY 2027: 19033000
R-2707D | HIGHWAY | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | REGION F |  | T | BUILD NC ROW | 1290000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 258000
R-2707D | HIGHWAY | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | REGION F |  | T | RIGHT-OF-WAY | 17518000 | FY 2023: 8768000
R-2707D | HIGHWAY | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | REGION F |  | T | BUILD NC CON | 58305000 |  | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 3887000 | 19435000
R-2707E | HIGHWAY | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 (LONG BRANCH ROAD) TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | REGION F |  | T | CONSTRUCTION | 50399000 | FY 2024: 14149000; FY 2025: 17441000; FY 2026: 12722000; FY 2027: 6087000
R-2707E | HIGHWAY | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 (LONG BRANCH ROAD) TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | REGION F |  | T | RIGHT-OF-WAY | 13000000
R-2707E | HIGHWAY | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 (LONG BRANCH ROAD) TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | REGION F |  | T | BUILD NC ROW | 1290000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 258000
R-2721 | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), NC 55 (SOUTH) TO EAST OF US 401 SOUTH. FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | COORDINATE WITH U-5746; NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT | STATEWIDE MOBILITY |  |  |  | 387067000
R-2721A | HIGHWAY | NC 540 | NC 55 BYPASS TO EAST OF SR 1152 (HOLLY SPRINGS ROAD). CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 79500000
R-2721B | HIGHWAY | NC 540 | EAST OF SR 1152 (HOLLY SPRINGS ROAD) TO EAST OF US 401. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 63000000
R-2814 | HIGHWAY | US 401 | NORTH OF SR 2044 (LIGON MILL ROAD) TO NC 39 IN LOUISBURG. WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY, SOME NEW LOCATION. | 5 | Capital Area MPO, Kerr-Tar RPO | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 132392000
R-2814B | HIGHWAY | US 401 | ROLESVILLE BYPASS, NORTH OF SR 2225 (LOUISBURY ROAD) TO NC 96 ON NEW LOCATION | 5 | Capital Area MPO | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022 | PRE-STI (TRANSITION) |  | BGANY | GARVEE ROW | 1727000
R-2814B | HIGHWAY | US 401 | ROLESVILLE BYPASS, NORTH OF SR 2225 (LOUISBURY ROAD) TO NC 96 ON NEW LOCATION | 5 | Capital Area MPO | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022 | PRE-STI (TRANSITION) |  | BGANY | GARVEE CON | 7083000
R-2814C | HIGHWAY | US 401 | NC 96 TO SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING $33 MILLION FOR CONSTRUCTION - PAYBACK FY 2018 - FY 2032 | DIVISION 5 |  | BGLT5 | GARVEE CON | 36803000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000
R-2814D | HIGHWAY | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | 5 | Capital Area MPO, Kerr-Tar RPO |  | DIVISION 5 |  | BGLT5 | RIGHT-OF-WAY | 3049000 | FY 2028: 558000; FY 2029: 836000; FY 2030: 836000; FY 2031: 209000; FY 2032: 610000
R-2814D | HIGHWAY | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | 5 | Capital Area MPO, Kerr-Tar RPO |  | DIVISION 5 |  | BGLT5 | UTILITIES | 3200000 | FY 2028: 1600000; FY 2029: 1600000
R-2814D | HIGHWAY | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | 5 | Capital Area MPO, Kerr-Tar RPO |  | DIVISION 5 |  | BGLT5 | CONSTRUCTION | 48701000 | FY 2031: 13417000; FY 2032: 16781000; FY 2033: 12079000 | 6424000
R-2822 | HIGHWAY | NC 143 | NC 143, WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 14 | Southwestern RPO | [5 empty] | 2889000
R-2822B | HIGHWAY | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | REGION G |  | T | UTILITIES | 700000 | FY 2023: 700000
R-2822B | HIGHWAY | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | REGION G |  | T | CONSTRUCTION | 29201000 | FY 2025: 292000; FY 2026: 10456000; FY 2027: 10582000; FY 2028: 7012000; FY 2029: 859000
R-2822B | HIGHWAY | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | REGION G |  | T | RIGHT-OF-WAY | 1101000 | FY 2023: 143000; FY 2024: 246000; FY 2025: 246000; FY 2026: 246000; FY 2027: 220000
R-2828 | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), EAST OF US 401 TO I-40. CONSTRUCT FREEWAY ON NEW LOCATION. | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 135750000
R-2828 | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), EAST OF US 401 TO I-40. CONSTRUCT FREEWAY ON NEW LOCATION. | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT. | STATEWIDE MOBILITY |  |  |  | 441446000
R-2829 | HIGHWAY | NEW ROUTE (FUTURE NC 540) | EASTERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), I-40 TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | THE STIP ADDRESSES INFLATION BY DECREASING REVENUE, THEREFORE THE $350M SHOWN REPRESENTS THE $400M REQUIRED IN FY26. BOND R(T) FUNDING REPRESENTS THE $100M LOAN FROM NCDOT TO NC TURNPIKE AUTHORITY AND WILL BE REPAID AT FINANCIAL CLOSE. | STATEWIDE MOBILITY |  |  |  | 12945000
R-2829A | HIGHWAY | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BONDRT | RIGHT-OF-WAY | 25000000 | FY 2023: 5000000; FY 2024: 20000000
R-2829A | HIGHWAY | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 43750000 | FY 2026: 10937000; FY 2027: 10937000; FY 2028: 10938000; FY 2029: 10938000
R-2829A | HIGHWAY | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 168915000 |  |  |  | 11261000 | 11261000 | 11261000 | 11261000 | 11261000 | 11261000 | 11261000 | 11261000 | 78827000
R-2829A | HIGHWAY | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BONDRT | UTILITIES | 5000000 | FY 2023: 5000000
R-2829A | HIGHWAY | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BOND R | CONSTRUCTION | 140400000 | FY 2026: 140400000
R-2829A | HIGHWAY | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BOND R | UTILITIES | 3544000 | FY 2025: 1772000; FY 2026: 1772000
R-2829A | HIGHWAY | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BOND R | RIGHT-OF-WAY | 41809000 | FY 2025: 10452000; FY 2026: 20905000; FY 2027: 10452000
R-2829A | HIGHWAY | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BONDRT | CONSTRUCTION | 15000000 | FY 2023: 5000000; FY 2024: 10000000
R-2829B | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BONDRT | RIGHT-OF-WAY | 35000000 | FY 2023: 10000000; FY 2024: 25000000
R-2829B | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 168915000 |  |  |  | 11261000 | 11261000 | 11261000 | 11261000 | 11261000 | 11261000 | 11261000 | 11261000 | 78827000
R-2829B | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 43750000 | FY 2026: 10937000; FY 2027: 10937000; FY 2028: 10938000; FY 2029: 10938000
R-2829B | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BONDRT | UTILITIES | 5000000 | FY 2023: 5000000
R-2829B | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BOND R | UTILITIES | 500000 | FY 2025: 250000; FY 2026: 250000
R-2829B | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BOND R | RIGHT-OF-WAY | 33806000 | FY 2025: 8445000; FY 2026: 16890000; FY 2027: 8471000
R-2829B | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BOND R | CONSTRUCTION | 230902000 | FY 2026: 230902000
R-2829B | HIGHWAY | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $131.25 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 | STATEWIDE MOBILITY |  | BONDRT | CONSTRUCTION | 15000000 | FY 2023: 5000000; FY 2024: 10000000
R-2915 | HIGHWAY | US 221 | US 421 IN WATAUGA COUNTY TO US 221 BUSINESS/NC 88 IN JEFFERSON. WIDEN TO FOUR LANES DIVIDED. | 11 | High Country RPO | [5 empty] | 175463000
R-2915C | HIGHWAY | US 221 | NORTH OF SOUTH FORK NEW RIVER TO SOUTH OF NC 194 | 11 | High Country RPO | COMPLETE | DIVISION 11 |  | BGLT5 | CONSTRUCTION | 19700000
R-2915E | HIGHWAY | US 221 | US 221 BYPASS TO US 221 BUSINESS/NC 88 IN JEFFERSON | 11 | High Country RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 11 |  | T | CONSTRUCTION | 14444000 | FY 2023: 3611000
R-2915E | HIGHWAY | US 221 | US 221 BYPASS TO US 221 BUSINESS/NC 88 IN JEFFERSON | 11 | High Country RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 11 |  | T | BUILD NC CON | 27615000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 3682000
R-3100 | HIGHWAY | NC 16 | SR 1895 TO SR 1800 SOUTHEAST OF NEWTON. WIDEN TO FOUR LANES. | 12 | Greater Hickory MPO | [5 empty] | 74426000
R-3100A | HIGHWAY | NC 16 | SR 1895 (TOWER ROAD) TO SR 1814 (CALDWELL ROAD) | 12 | Greater Hickory MPO | COMPLETE; BUILD NC BOND FUNDING: $33.028 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | DIVISION 12 |  | T | BUILD NC CON | 42510000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 5668000
R-3300 | HIGHWAY | US 17 (HAMPSTEAD BYPASS) | US 17 BYPASS SOUTH OF HAMPSTEAD TO US 17 NORTH OF HAMPSTEAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | [5 empty] | 101547000
R-3300A | HIGHWAY | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | REGION B |  | T | BUILD NC CON | 25740000 |  |  |  | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 12012000
R-3300A | HIGHWAY | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | REGION B |  | T | CONSTRUCTION | 123700000 | FY 2026: 4429000; FY 2027: 40236000; FY 2028: 34488000; FY 2029: 25866000; FY 2030: 18681000
R-3300B | HIGHWAY | US 17 | NC 210 TO US 17 NORTH OF HAMPSTEAD. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). | REGION B |  | T | BUILD NC CON | 71820000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 14364000
R-3300B | HIGHWAY | US 17 | NC 210 TO US 17 NORTH OF HAMPSTEAD. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). | REGION B |  | T | CONSTRUCTION | 157732000 | FY 2023: 4928000; FY 2024: 53386000; FY 2025: 42709000; FY 2026: 56709000
R-3333 | HIGHWAY | US 401 | US 401 BUSINESS NORTH OF LAURINBURG TO US 401 BUSINESS EAST OF RAEFORD. CONSTRUCT PASSING LANES, TURN LANES, AND PAVED SHOULDERS. | 8 | Lumber River RPO, Fayetteville Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 273000 | [11 empty] | 273000
R-3333 | HIGHWAY | US 401 | US 401 BUSINESS NORTH OF LAURINBURG TO US 401 BUSINESS EAST OF RAEFORD. CONSTRUCT PASSING LANES, TURN LANES, AND PAVED SHOULDERS. | 8 | Lumber River RPO, Fayetteville Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 38800000 | [11 empty] | 38800000
R-3333 | HIGHWAY | US 401 | US 401 BUSINESS NORTH OF LAURINBURG TO US 401 BUSINESS EAST OF RAEFORD. CONSTRUCT PASSING LANES, TURN LANES, AND PAVED SHOULDERS. | 8 | Lumber River RPO, Fayetteville Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 15507000 | [11 empty] | 15507000
R-3403 | HIGHWAY | US 17 | MILLS STREET IN BRIDGETON TO NC 43. WIDEN TO MULTI-LANES. | 2 | Down East RPO, New Bern Area MPO |  | REGION B |  |  |  | 28147000
R-3403B | HIGHWAY | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | 2 | Down East RPO, New Bern Area MPO |  | REGION B |  | T | RIGHT-OF-WAY | 6000000 | FY 2027: 384000; FY 2028: 2304000; FY 2029: 2112000; FY 2030: 600000; FY 2031: 600000
R-3403B | HIGHWAY | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | 2 | Down East RPO, New Bern Area MPO |  | REGION B |  | T | UTILITIES | 4500000 | FY 2027: 2250000; FY 2028: 2250000
R-3403B | HIGHWAY | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | 2 | Down East RPO, New Bern Area MPO |  | REGION B |  | T | CONSTRUCTION | 71799000 | FY 2029: 718000; FY 2030: 25052000; FY 2031: 22012000; FY 2032: 15856000; FY 2033: 8161000
R-3410 | HIGHWAY | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 4 | Capital Area MPO |  | REGION A |  | BGANY | RIGHT-OF-WAY | 14697000 | FY 2027: 3359000; FY 2028: 6718000; FY 2029: 1680000; FY 2030: 1470000; FY 2031: 1470000
R-3410 | HIGHWAY | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 4 | Capital Area MPO |  | REGION A |  | BGANY | UTILITIES | 19600000 | FY 2027: 9800000; FY 2028: 9800000
R-3410 | HIGHWAY | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 4 | Capital Area MPO |  | REGION A |  |  |  | 2500000
R-3410 | HIGHWAY | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 4 | Capital Area MPO |  | REGION A |  | BGANY | CONSTRUCTION | 74200000 | FY 2029: 16489000; FY 2030: 23443000; FY 2031: 18385000; FY 2032: 12834000; FY 2033: 3049000
R-3419 | HIGHWAY | US 158 | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1000000
R-3419 | HIGHWAY | US 158 | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 20237000
R-3419 | HIGHWAY | US 158 | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9608000
R-3419 | HIGHWAY | US 158 | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 1 | Albemarle RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 137000000
R-3421 | HIGHWAY | US 220 / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS. FOUR LANES DIVIDED ON NEW LOCATION. | 8 | Lumber River RPO | BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 60762000
R-3421A | HIGHWAY | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | BUILD NC ROW | 5495000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 371000
R-3421A | HIGHWAY | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | CONSTRUCTION | 31909000 | FY 2023: 7977000
R-3421A | HIGHWAY | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | BUILD NC CON | 65983000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 8796000
R-3421A | HIGHWAY | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | BUILD NC CON | 8965000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 375000 | 750000
R-3421B | HIGHWAY | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) TO SOUTHWEST OF SR 1304 (HARRINGTON ROAD) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | BUILD NC CON | 39179000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 5223000
R-3421B | HIGHWAY | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) TO SOUTHWEST OF SR 1304 (HARRINGTON ROAD) | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION E |  | T | CONSTRUCTION | 44500000 | FY 2023: 11125000
R-3421CA | HIGHWAY | US 220/I-73/I-74 | SR 1336 (BILLY COVINGTON ROAD) | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 75000 | FY 2023: 75000
R-3421CA | HIGHWAY | US 220/I-73/I-74 | SR 1336 (BILLY COVINGTON ROAD) | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | T | UTILITIES | 25000 | FY 2023: 25000
R-3421CA | HIGHWAY | US 220/I-73/I-74 | SR 1336 (BILLY COVINGTON ROAD) | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 532000 | FY 2024: 5000; FY 2025: 527000
R-3430 | HIGHWAY | SR 1001 (MALCOLM BLVD/ CONNELLY SPRINGS ROAD) | US 70 TO SR 1933 (SOUTH-WEST BOULEVARD) IN LENOIR. MODERNIZE ROADWAY TO INCLUDE BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 11, 13 | Greater Hickory MPO | [5 empty] | 2807000
R-3430A | HIGHWAY | SR 1001 (MALCOLM BOULEVARD) | US 70 TO CATAWBA RIVER. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 20000000 | [11 empty] | 20000000
R-3430A | HIGHWAY | SR 1001 (MALCOLM BOULEVARD) | US 70 TO CATAWBA RIVER. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 10000000 | [11 empty] | 10000000
R-3430A | HIGHWAY | SR 1001 (MALCOLM BOULEVARD) | US 70 TO CATAWBA RIVER. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | T | UTILITIES | 1600000 | [11 empty] | 1600000
R-3430B | HIGHWAY | SR 1001 (CONNELLY SPRINGS ROAD) | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | HIGHWAY FUND |  | HFB | RIGHT-OF-WAY | 880000
R-3430B | HIGHWAY | SR 1001 (CONNELLY SPRINGS ROAD) | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | HIGHWAY FUND |  | HFB | UTILITIES | 370000
R-3430B | HIGHWAY | SR 1001 (CONNELLY SPRINGS ROAD) | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | HIGHWAY FUND |  | HFB | CONSTRUCTION | 20900000 | FY 2025: 3037000; FY 2026: 9215000; FY 2027: 6786000; FY 2028: 1862000
R-3430C | HIGHWAY | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGANY | UTILITIES | 4000000 | FY 2028: 2000000; FY 2029: 2000000
R-3430C | HIGHWAY | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGANY | CONSTRUCTION | 47000000 | FY 2031: 470000; FY 2032: 14798000; FY 2033: 15448000 | 16284000
R-3430C | HIGHWAY | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGANY | RIGHT-OF-WAY | 27500000 | FY 2028: 275000; FY 2029: 7725000; FY 2030: 8000000; FY 2031: 6000000; FY 2032: 5500000
R-3603 | HIGHWAY | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | 12 | Greater Hickory MPO | [5 empty] | 600000
R-3603A | HIGHWAY | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | DIVISION 12 |  | T | RIGHT-OF-WAY | 26900000 | FY 2024: 269000; FY 2025: 12028000; FY 2026: 9223000; FY 2027: 2690000; FY 2028: 2690000
R-3603A | HIGHWAY | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | DIVISION 12 |  | T | UTILITIES | 100000 | FY 2024: 100000
R-3603A | HIGHWAY | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | DIVISION 12 |  | T | CONSTRUCTION | 55101000 | FY 2026: 3202000; FY 2027: 19268000; FY 2028: 16378000; FY 2029: 11470000; FY 2030: 4783000
R-3608 | HIGHWAY | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2000000
R-3608 | HIGHWAY | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 15299000
R-3608 | HIGHWAY | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3800000
R-3608 | HIGHWAY | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 565000
R-3822 | HIGHWAY | NEW ROUTE | NC 125 TO SOUTH OF US 158. CONSTRUCT THREE LANE FACILITY ON NEW LOCATION. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH U-5725. CONSTRUCTION FUNDS SHOWN UNDER U-5725. | DIVISION 4 |  |  |  | 4972000
R-3825 | HIGHWAY | NC 42 | US 70 TO SR 1003 (BUFFALO ROAD). WIDEN TO MULTI-LANES. | 4 | Capital Area MPO | [5 empty] | 49175000
R-3825B | HIGHWAY | NC 42 | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | 4 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | BUILD NC CON | 20895000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000
R-3825B | HIGHWAY | NC 42 | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | 4 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | BUILD NC CON | 22755000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 3034000
R-3825B | HIGHWAY | NC 42 | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | 4 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | CONSTRUCTION | 24798000
R-3826 | HIGHWAY | NC 125 | SR 1182 (EAST COLLEGE ROAD) TO NC 125 NORTHWEST OF WILLIAMSTON. TWO LANES, PART ON NEW LOCATION. | 1 | Mid-East RPO | COMPLETED. | REGION A |  |  |  | 17607000
R-3830 | HIGHWAY | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | 8 | Triangle Area RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | DIVISION 8 |  | T | BUILD NC CON | 23175000 | 1545000 | 1545000 | 1545000 | 1545000 | 1545000 | 1545000 | 1545000 | 1545000 | 1545000 | 1545000 | 1545000 | 6180000
R-3830 | HIGHWAY | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | 8 | Triangle Area RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | DIVISION 8 |  |  |  | 19418000
R-3830 | HIGHWAY | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | 8 | Triangle Area RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | DIVISION 8 |  | T | CONSTRUCTION | 52872000 | FY 2023: 1421000; FY 2024: 26646000; FY 2025: 18427000; FY 2026: 6378000
R-3830 | HIGHWAY | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | 8 | Triangle Area RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | DIVISION 8 |  | T | BUILD NC ROW | 10228000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 680000
R-3830A | HIGHWAY | NC 42 | RAILROAD MITIGATION | 8 | Triangle Area RPO | UNDER CONSTRUCTION | DIVISION 8 |  | T | CONSTRUCTION | 1900000 | FY 2023: 800000
R-3833 | HIGHWAY | SR 1100 (BRAWLEY SCHOOL ROAD) | SR 1177 (CHUCKWOOD ROAD) TO US 21. WIDEN TO MULTI-LANES WITH INTERCHANGE AT I-77. | 12 | Charlotte Regional TPO | $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE. |  |  |  |  | 126721000
R-3833C | HIGHWAY | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21 | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | DIVISION 12 |  | T | BUILD NC CON | 12870000 |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 4290000
R-3833C | HIGHWAY | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21 | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | DIVISION 12 |  | T | CONSTRUCTION | 18710000 | FY 2024: 753000; FY 2025: 12235000; FY 2026: 5722000
R-3833C | HIGHWAY | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21 | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | DIVISION 12 |  | T | RIGHT-OF-WAY | 5050000
R-3833C | HIGHWAY | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21 | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | DIVISION 12 |  | L | CONSTRUCTION | 890000 | FY 2024: 334000; FY 2025: 379000; FY 2026: 177000
R-4045 | HIGHWAY | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | REGION F |  | T | RIGHT-OF-WAY | 3000000 | FY 2023: 30000; FY 2024: 1170000; FY 2025: 1200000; FY 2026: 300000; FY 2027: 300000
R-4045 | HIGHWAY | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | REGION F |  | T | UTILITIES | 1900000 | FY 2023: 950000; FY 2024: 950000
R-4045 | HIGHWAY | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | REGION F |  | T | CONSTRUCTION | 1762000 | FY 2023: 18000; FY 2024: 978000; FY 2025: 574000; FY 2026: 192000
R-4045 | HIGHWAY | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | REGION F |  | DP | CONSTRUCTION | 23239000 | FY 2023: 232000; FY 2024: 12902000; FY 2025: 7575000; FY 2026: 2530000
R-4073 | HIGHWAY | VARIOUS | ASPHALT MATERIALS TESTING LABORATORIES CORRECTIVE ACTION PLAN FOR GROUNDWATER CLEAN-UP AT 54 SITES. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 20234000
R-4428 | HIGHWAY | NC 711 | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | 6 | Lumber River RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1220000
R-4428 | HIGHWAY | NC 711 | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | 6 | Lumber River RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 11601000
R-4428 | HIGHWAY | NC 711 | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | 6 | Lumber River RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 900000
R-4428 | HIGHWAY | NC 711 | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | 6 | Lumber River RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9263000
R-4436 | HIGHWAY | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 43915000
R-4436DIV | HIGHWAY | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  | BG | CONSTRUCTION | 900000
R-4436REG | HIGHWAY | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. | 99 | STATEWIDE PROJECT | IN PROGRESS | REGION SW |  | BG | CONSTRUCTION | 900000
R-4436SW | HIGHWAY | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. | 99 | STATEWIDE PROJECT | IN PROGRESS | STATEWIDE MOBILITY |  | BG | CONSTRUCTION | 1200000
R-4457 | HIGHWAY | US 158 | NC 12. IMPROVE INTERSECTION. | 1 | Albemarle RPO |  | NOT FUNDED |  |  |  | 188000
R-4457 | HIGHWAY | US 158 | NC 12. IMPROVE INTERSECTION. | 1 | Albemarle RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 1100000 | [11 empty] | 1100000
R-4457 | HIGHWAY | US 158 | NC 12. IMPROVE INTERSECTION. | 1 | Albemarle RPO |  | NOT FUNDED |  | NHP | UTILITIES | 400000 | [11 empty] | 400000
R-4457 | HIGHWAY | US 158 | NC 12. IMPROVE INTERSECTION. | 1 | Albemarle RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 5800000 | [11 empty] | 5800000
R-4463 | HIGHWAY | NC 43 CONNECTOR | NC 43/NC 55 TO US 17 IN NEW BERN. CONSTRUCT ROUTE ON NEW LOCATION WITH INTERCHANGE AT US 70. | 2 | New Bern Area MPO | [5 empty] | 61329000
R-4463A | HIGHWAY | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | CONSTRUCTION | 24500000 | FY 2025: 4849000; FY 2026: 11169000; FY 2027: 7226000; FY 2028: 1256000
R-4463A | HIGHWAY | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | UTILITIES | 1000000 | FY 2023: 500000; FY 2024: 500000
R-4463A | HIGHWAY | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | RIGHT-OF-WAY | 3200000 | FY 2023: 1600000; FY 2024: 1600000
R-4463A | HIGHWAY | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | BUILD NC ROW | 240000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
R-4463A | HIGHWAY | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | ENGINEERING | 1725000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000
R-4467 | HIGHWAY | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | ENGINEERING | 2415000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 322000
R-4467 | HIGHWAY | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | BUILD NC CON | 3570000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000
R-4467 | HIGHWAY | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | BUILD NC CON | 49035000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 6538000
R-4467 | HIGHWAY | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | CONSTRUCTION | 12907000 | FY 2023: 8405000
R-4467 | HIGHWAY | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  |  |  | 12519000
R-4705 | HIGHWAY | SR 1142 (PRISON CAMP ROAD) | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | 1 | Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 1 |  |  |  | 6000000
R-4705 | HIGHWAY | SR 1142 (PRISON CAMP ROAD) | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | 1 | Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | BGLT5 | UTILITIES | 2100000 | FY 2023: 2100000
R-4705 | HIGHWAY | SR 1142 (PRISON CAMP ROAD) | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | 1 | Mid-East RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | BGLT5 | CONSTRUCTION | 48147000 | FY 2023: 26902000; FY 2024: 11037000; FY 2025: 7535000
R-4707 | HIGHWAY | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $25 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | REGION D |  |  |  | 10407000
R-4707 | HIGHWAY | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $25 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | REGION D |  | T | ENGINEERING | 4019000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000
R-4707 | HIGHWAY | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $25 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | REGION D |  | T | BUILD NC ROW | 5824000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000
R-4707 | HIGHWAY | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $25 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | REGION D |  | T | BUILD NC CON | 34320000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 4290000 | 6435000
R-4707 | HIGHWAY | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $25 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | REGION D |  | T | CONSTRUCTION | 28340000 | FY 2023: 0; FY 2024: 6355000; FY 2025: 3146000
R-4734 | HIGHWAY | NC 109 | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTI-LANES. | 9 | High Point Urban Area MPO |  | DIVISION 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1000000
R-4734 | HIGHWAY | NC 109 | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTI-LANES. | 9 | High Point Urban Area MPO |  | DIVISION 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 132097000
R-4734 | HIGHWAY | NC 109 | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTI-LANES. | 9 | High Point Urban Area MPO |  | DIVISION 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 500000
R-4734 | HIGHWAY | NC 109 | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTI-LANES. | 9 | High Point Urban Area MPO |  | DIVISION 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1337000
R-4746 | HIGHWAY | US 70/NC 12 | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | 2 | Down East RPO |  | NOT FUNDED |  |  |  | 10000
R-4746 | HIGHWAY | US 70/NC 12 | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | 2 | Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 30900000 | [11 empty] | 30900000
R-4746 | HIGHWAY | US 70/NC 12 | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | 2 | Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 9100000 | [11 empty] | 9100000
R-4746 | HIGHWAY | US 70/NC 12 | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | 2 | Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 71199000 | [11 empty] | 71199000
R-4751 | HIGHWAY | US 19 | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 25000000 | [11 empty] | 25000000
R-4751 | HIGHWAY | US 19 | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 4900000 | [11 empty] | 4900000
R-4751 | HIGHWAY | US 19 | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  |  |  | 1300000
R-4751 | HIGHWAY | US 19 | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 75000000 | [11 empty] | 75000000
R-4753 | HIGHWAY | NC 107 | SR 1002 TO NC 281. UPGRADE EXISTING ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION | DIVISION 14 |  |  |  | 50599000
R-4757 | HIGHWAY | SR 1206 (ALCOVE ROAD) | RELOCATION OF ROADWAY IN MOORESVILLE. | 12 | Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY - PLANNING BY TOWN OF MOORESVILLE |  |  |  |  | 745000
R-5014 | HIGHWAY | SR 1217 (COLLINGTON ROAD) | DEAD END TO US 158 (CROATON HIGHWAY) IN KILL DEVIL HILLS. OPERATIONAL-SAFETY IMPROVEMENTS. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  |  |  | 2525000
R-5014 | HIGHWAY | SR 1217 (COLLINGTON ROAD) | DEAD END TO US 158 (CROATON HIGHWAY) IN KILL DEVIL HILLS. OPERATIONAL-SAFETY IMPROVEMENTS. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | BG5200 | CONSTRUCTION | 22368000 | FY 2023: 14318000
R-5020 | HIGHWAY | US 701 BYPASS (MADISON STREET- POWELL BOULEVARD) | SOUTH OF SR 1166 (PLEASANT PLAINS ROAD) TO NORTH OF US 74/US 76 BYPASS IN WHITEVILLE. WIDEN TO MULTI-LANE FACILITY. | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. |  |  |  |  | 15050000
R-5020A | HIGHWAY | US 701 BYPASS | SR 1166 (PLEASANT PLAINS CHURCH ROAD) TO SR 1437 (VIRGIL AVENUE). | 6 | Cape Fear RPO |  | REGION C |  | NHP | CONSTRUCTION | 47299000 | FY 2029: 14809000; FY 2030: 17634000; FY 2031: 12326000; FY 2032: 2530000
R-5020B | HIGHWAY | US 701 BYPASS | SR 1437 (VIRGIL AVENUE) TO US 74/US 76. | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | CONSTRUCTION | 32485000 | FY 2023: 10828000; FY 2024: 10829000
R-5021 | HIGHWAY | NC 211 | SR 1500 (MIDWAY ROAD) TO NC 87. WIDEN TO FOUR LANES. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BG5200 | CONSTRUCTION | 239876000 | FY 2023: 42462000; FY 2024: 34843000; FY 2025: 24649000; FY 2026: 8285000
R-5021 | HIGHWAY | NC 211 | SR 1500 (MIDWAY ROAD) TO NC 87. WIDEN TO FOUR LANES. | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 36068000
R-5100 | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | I-77 TO NC 150. WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | COORDINATE WITH U-5817. |  |  |  |  | 1373000
R-5100A | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | RIGHT-OF-WAY | 4800000 | FY 2023: 2400000
R-5100A | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | UTILITIES | 5300000 | FY 2023: 2650000
R-5100A | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | BUILD NC ROW | 3855000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 771000
R-5100A | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | BUILD NC ROW | 195000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000
R-5100A | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | ENGINEERING | 600000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
R-5100A | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | CONSTRUCTION | 39299000 | FY 2025: 11611000; FY 2026: 14016000; FY 2027: 9821000; FY 2028: 3851000
R-5100B | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | BUILD NC ROW | 450000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
R-5100B | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | BUILD NC ROW | 2565000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 513000
R-5100B | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | RIGHT-OF-WAY | 6500000
R-5100B | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | UTILITIES | 1300000 | FY 2023: 650000
R-5100B | HIGHWAY | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | DIVISION 12 |  | T | CONSTRUCTION | 5900000 | FY 2025: 59000; FY 2026: 3910000; FY 2027: 1931000
R-5113 | HIGHWAY | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  |  |  | 512000
R-5113 | HIGHWAY | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | CONSTRUCTION | 42600000 | FY 2031: 6349000; FY 2032: 16265000; FY 2033: 12749000 | 7237000
R-5113 | HIGHWAY | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 38600000 | FY 2028: 386000; FY 2029: 10643000; FY 2030: 13234000; FY 2031: 6617000; FY 2032: 7720000
R-5113 | HIGHWAY | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | UTILITIES | 9700000 | FY 2028: 4850000; FY 2029: 4850000
R-5311 | HIGHWAY | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. WIDEN TO MULTI-LANES. | 1 | Peanut Belt RPO | [5 empty] | 20809000
R-5311B | HIGHWAY | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | 1 | Peanut Belt RPO |  | REGION A |  | T | RIGHT-OF-WAY | 6300000 | FY 2028: 63000; FY 2029: 2097000; FY 2030: 2880000; FY 2031: 630000; FY 2032: 630000
R-5311B | HIGHWAY | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | 1 | Peanut Belt RPO |  | REGION A |  | T | UTILITIES | 1200000 | FY 2028: 600000; FY 2029: 600000
R-5311B | HIGHWAY | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | 1 | Peanut Belt RPO |  | REGION A |  | T | CONSTRUCTION | 101401000 | FY 2031: 1014000; FY 2032: 29675000; FY 2033: 27630000 | 43082000
R-5516 | HIGHWAY | US 70 | SLOCUMB ROAD AT CHERRY POINT MILITARY BASE. CONSTRUCT INTERCHANGE. | 2 | Down East RPO | COMPLETE | PRE-STI (TRANSITION) |  |  |  | 37680000
R-5600 | HIGHWAY | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT OF WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | REGION G |  |  |  | 3825000
R-5600 | HIGHWAY | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT OF WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | REGION G |  | T | UTILITIES | 7200000
R-5600 | HIGHWAY | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT OF WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | REGION G |  | T | RIGHT-OF-WAY | 32700000 | FY 2023: 10900000; FY 2024: 10900000
R-5600 | HIGHWAY | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT OF WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | REGION G |  | NHP | CONSTRUCTION | 56199000 | FY 2025: 14791000; FY 2026: 18792000; FY 2027: 13995000; FY 2028: 8621000
R-5600 | HIGHWAY | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT OF WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | REGION G |  | T | BUILD NC ROW | 25740000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 5148000
R-5605 | HIGHWAY | DAVIDSON RIVER VILLAGE CONNECTOR | US 64 TO US 276/US 64 IN PISGAH FOREST. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2.592M FOR CON, PAYBACK FY 2020-2034 (FY 2019/ YR 1 SALE) | DIVISION 14 |  | T | BUILD NC CON | 3345000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000
R-5605 | HIGHWAY | DAVIDSON RIVER VILLAGE CONNECTOR | US 64 TO US 276/US 64 IN PISGAH FOREST. | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2.592M FOR CON, PAYBACK FY 2020-2034 (FY 2019/ YR 1 SALE) | DIVISION 14 |  |  |  | 11248000
R-5701 | HIGHWAY | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | 3 | Cape Fear RPO |  | REGION B |  | T | CONSTRUCTION | 1450000 | FY 2027: 14000; FY 2028: 1436000
R-5701 | HIGHWAY | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | 3 | Cape Fear RPO |  | REGION B |  | T | UTILITIES | 172000 | FY 2025: 172000
R-5701 | HIGHWAY | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | 3 | Cape Fear RPO |  | REGION B |  |  |  | 1000000
R-5701 | HIGHWAY | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | 3 | Cape Fear RPO |  | REGION B |  | L | RIGHT-OF-WAY | 45000 | FY 2025: 45000
R-5701 | HIGHWAY | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | 3 | Cape Fear RPO |  | REGION B |  | T | RIGHT-OF-WAY | 10000 | FY 2025: 10000
R-5703 | HIGHWAY | NC 148 (CF HARVEY PARKWAY) | NC 58 TO NC 11. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | REGION B |  |  |  | 45690000
R-5703 | HIGHWAY | NC 148 (CF HARVEY PARKWAY) | NC 58 TO NC 11. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | REGION B |  | T | BUILD NC CON | 46275000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000
R-5703 | HIGHWAY | NC 148 (CF HARVEY PARKWAY) | NC 58 TO NC 11. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | REGION B |  | T | CONSTRUCTION | 28334000
R-5704 | HIGHWAY | NC 87 | SR 1998 (WENTWORTH STREET) / SR 1001 (SANDY CROSS ROAD). INTERSECTION REALIGNMENT. | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | REGION D |  |  |  | 2884000
R-5705 | HIGHWAY | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 42 IN FUQUAY-VARINA. WIDEN TO MULTI-LANES. PART ON NEW LOCATION. | 5, 6 | Capital Area MPO | [5 empty] | 3663000
R-5705A | HIGHWAY | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | 6 | Capital Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | RIGHT-OF-WAY | 28835000 | FY 2023: 17000000
R-5705A | HIGHWAY | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | 6 | Capital Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | UTILITIES | 3100000
R-5705A | HIGHWAY | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | 6 | Capital Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | CONSTRUCTION | 59200000 | FY 2024: 13024000; FY 2025: 21904000; FY 2026: 17168000; FY 2027: 7104000
R-5705B | HIGHWAY | NC 55 | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. | REGION C |  | T | RIGHT-OF-WAY | 25171000 | FY 2023: 15000000
R-5705B | HIGHWAY | NC 55 | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. | REGION C |  | T | UTILITIES | 1300000
R-5705B | HIGHWAY | NC 55 | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. | REGION C |  | T | CONSTRUCTION | 70722000 | FY 2023: 13437000; FY 2024: 27581000; FY 2025: 21217000; FY 2026: 8487000
R-5705C | HIGHWAY | NC 55 | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 8170000 | [11 empty] | 8170000
R-5705C | HIGHWAY | NC 55 | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | UTILITIES | 1386000 | [11 empty] | 1386000
R-5705C | HIGHWAY | NC 55 | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 17900000 | [11 empty] | 17900000
R-5706 | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO US 29. WIDEN TO MULTI-LANES. | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | COORDINATE WITH R-2632AB. |  |  |  |  | 1350000
R-5706A | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO |  | REGION E |  | NHP | RIGHT-OF-WAY | 9700000 | FY 2024: 2299000; FY 2025: 3449000; FY 2026: 2012000; FY 2027: 970000; FY 2028: 970000
R-5706A | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO |  | REGION E |  | NHP | UTILITIES | 2000000 | FY 2024: 1000000; FY 2025: 1000000
R-5706A | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO |  | REGION E |  | NHP | CONSTRUCTION | 31999000 | FY 2026: 320000; FY 2027: 16641000; FY 2028: 10684000; FY 2029: 4354000
R-5706BA | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO I-85. | 10 | Cabarrus-Rowan MPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 26000000
R-5706BA | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO I-85. | 10 | Cabarrus-Rowan MPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 6500000
R-5706BA | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO I-85. | 10 | Cabarrus-Rowan MPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 139000000
R-5706BB | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | I-85 TO US 29. | 10 | Cabarrus-Rowan MPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 5280000
R-5706BB | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | I-85 TO US 29. | 10 | Cabarrus-Rowan MPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 11220000
R-5706BB | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | I-85 TO US 29. | 10 | Cabarrus-Rowan MPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 8000000
R-5706BB | HIGHWAY | NC 73 (DAVIDSON HIGHWAY) | I-85 TO US 29. | 10 | Cabarrus-Rowan MPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 50700000
R-5707 | HIGHWAY | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION C |  | T | ENGINEERING | 989000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 131000
R-5707 | HIGHWAY | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION C |  | T | CONSTRUCTION | 528000
R-5707 | HIGHWAY | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION C |  |  |  | 1652000
R-5707 | HIGHWAY | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION C |  | T | BUILD NC CON | 3451000 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000 | 231000
R-5707 | HIGHWAY | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION C |  | T | BUILD NC CON | 1009000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 138000
R-5709 | HIGHWAY | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Lumber River RPO, Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  |  |  | 6457000
R-5709 | HIGHWAY | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Lumber River RPO, Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | RIGHT-OF-WAY | 59423000 | FY 2023: 19807000
R-5709 | HIGHWAY | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Lumber River RPO, Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | UTILITIES | 4976000 | FY 2023: 1658000
R-5709 | HIGHWAY | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Lumber River RPO, Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | CONSTRUCTION | 166299000 | FY 2024: 7719000; FY 2025: 50060000; FY 2026: 44878000; FY 2027: 36625000; FY 2028: 27017000
R-5709A | HIGHWAY | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. CLEARING, GRUBBING, AND EROSION CONTROL. | 8 | Lumber River RPO, Triangle Area RPO | UNDER CONSTRUCTION | REGION E |  | T | CONSTRUCTION | 17625000 | FY 2023: 8737000; FY 2024: 2912000
R-5711 | HIGHWAY | US 21 | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  |  |  | 915000
R-5711 | HIGHWAY | US 21 | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  | T | CONSTRUCTION | 2950000 | FY 2025: 2305000; FY 2026: 645000
R-5712 | HIGHWAY | NC 16 BUSINESS | INTERSECTION OF NC 16 BUSINESS AND SR 1439 (UNITY CHURCH ROAD)/SR 1387 (TRIANGLE CIRCLE). ADD TURN LANES. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  |  |  | 2152000
R-5712 | HIGHWAY | NC 16 BUSINESS | INTERSECTION OF NC 16 BUSINESS AND SR 1439 (UNITY CHURCH ROAD)/SR 1387 (TRIANGLE CIRCLE). ADD TURN LANES. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  | T | CONSTRUCTION | 2300000 | FY 2023: 23000; FY 2024: 2277000
R-5713 | HIGHWAY | US 74 | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  |  |  | 830000
R-5713 | HIGHWAY | US 74 | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | T | CONSTRUCTION | 1950000 | FY 2024: 437000; FY 2025: 1513000
R-5714 | HIGHWAY | US 601 | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  | T | CONSTRUCTION | 11700000 | FY 2025: 117000; FY 2026: 5569000; FY 2027: 4871000; FY 2028: 1143000
R-5714 | HIGHWAY | US 601 | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  |  |  | 785000
R-5714 | HIGHWAY | US 601 | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  | T | RIGHT-OF-WAY | 1615000
R-5717 | HIGHWAY | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN EXISTING LANES, WIDEN EXISTING SHOULDERS, AND INTERSECTION IMPROVEMENTS. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | T | CONSTRUCTION | 23700000 | FY 2024: 1659000; FY 2025: 10902000; FY 2026: 7821000; FY 2027: 3318000
R-5717 | HIGHWAY | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN EXISTING LANES, WIDEN EXISTING SHOULDERS, AND INTERSECTION IMPROVEMENTS. | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  |  |  | 2181000
R-5717B | HIGHWAY | SR 1224 (OLD SWAMP ROAD) | REPLACE BRIDGE 140013 OVER JOYCE CREEK. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | CONSTRUCTION | 1400000 | FY 2024: 322000; FY 2025: 1078000
R-5718 | HIGHWAY | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  |  |  | 500000
R-5718 | HIGHWAY | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  | BG5200 | CONSTRUCTION | 14300000 | FY 2025: 143000; FY 2026: 7302000; FY 2027: 5856000; FY 2028: 999000
R-5718 | HIGHWAY | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  | T | RIGHT-OF-WAY | 6937000
R-5718 | HIGHWAY | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  | T | UTILITIES | 1190000
R-5720 | HIGHWAY | SR 1770 (EASTERN AVENUE) | SR 1003 (RED OAK ROAD) TO SR 1603 (OLD CARRIAGE ROAD) IN ROCKY MOUNT. WIDEN TO MULTI-LANES. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTION FUNDS SHOWN UNDER U-5026. | DIVISION 4 |  | T | RIGHT-OF-WAY | 12252000
R-5720 | HIGHWAY | SR 1770 (EASTERN AVENUE) | SR 1003 (RED OAK ROAD) TO SR 1603 (OLD CARRIAGE ROAD) IN ROCKY MOUNT. WIDEN TO MULTI-LANES. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTION FUNDS SHOWN UNDER U-5026. | DIVISION 4 |  | T | UTILITIES | 1470000
R-5720 | HIGHWAY | SR 1770 (EASTERN AVENUE) | SR 1003 (RED OAK ROAD) TO SR 1603 (OLD CARRIAGE ROAD) IN ROCKY MOUNT. WIDEN TO MULTI-LANES. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTION FUNDS SHOWN UNDER U-5026. | DIVISION 4 |  |  |  | 1000000
R-5721 | HIGHWAY | NC 73 | NC 16 IN LINCOLN COUNTY TO SR 5544 (WEST CATAWBA AVENUE) IN MECKLENBURG COUNTY. WIDEN TO MULTI-LANES. | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | COORDINATE WITH U-5765. |  |  |  |  | 3015000
R-5721A | HIGHWAY | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO |  | REGION E, F |  | T | RIGHT-OF-WAY | 46399000 | FY 2026: 464000; FY 2027: 11909000; FY 2028: 13498000; FY 2029: 11248000; FY 2030: 9280000
R-5721A | HIGHWAY | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO |  | REGION E, F |  | T | UTILITIES | 10400000 | FY 2026: 5200000; FY 2027: 5200000
R-5721A | HIGHWAY | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO |  | REGION E, F |  | T | CONSTRUCTION | 102002000 | FY 2029: 1020000; FY 2030: 30569000; FY 2031: 29108000; FY 2032: 23826000; FY 2033: 17479000
R-5721B | HIGHWAY | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | REGION E |  | T | CONSTRUCTION | 13365000 | FY 2026: 134000; FY 2027: 6360000; FY 2028: 4739000; FY 2029: 2132000
R-5721B | HIGHWAY | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | REGION E |  | T | CONSTRUCTION | 4484000 | FY 2026: 45000; FY 2027: 2134000; FY 2028: 1590000; FY 2029: 715000
R-5721B | HIGHWAY | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | REGION E |  | T | CONSTRUCTION | 9969000 | FY 2026: 100000; FY 2027: 4744000; FY 2028: 3535000; FY 2029: 1590000
R-5721B | HIGHWAY | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | REGION E |  | BA | RIGHT-OF-WAY | 5923000 | FY 2023: 131000; FY 2024: 1570000; FY 2025: 1606000; FY 2026: 1439000; FY 2027: 1177000
R-5721B | HIGHWAY | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | REGION E |  | T | RIGHT-OF-WAY | 9513000 | FY 2023: 211000; FY 2024: 2537000; FY 2025: 2537000; FY 2026: 2326000; FY 2027: 1902000
R-5721B | HIGHWAY | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | REGION E |  | T | CONSTRUCTION | 282000 | FY 2026: 3000; FY 2027: 134000; FY 2028: 100000; FY 2029: 45000
R-5721B | HIGHWAY | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | REGION E |  | T | UTILITIES | 3000000 | FY 2023: 1500000; FY 2024: 1500000
R-5724 | HIGHWAY | US 15 / US 501 | SOUTH OF US 64 BUSINESS TO POWELL PLACE LANE IN PITTSBORO. WIDEN TO MULTI-LANES, MILL AND RESURFACE, AND CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. | 8 | Triangle Area RPO | [5 empty] | 2354000
R-5724A | HIGHWAY | US 15 / US 501 | US 15 / US 501, SOUTH OF US 64 BUSINESS TO NORTH OF US 64 BUSINESS. CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. | 8 | Triangle Area RPO | UNDER CONSTRUCTION | DIVISION 8 |  | T | CONSTRUCTION | 4000000
R-5724B | HIGHWAY | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | CONSTRUCTION | 10199000 | FY 2026: 1583000; FY 2027: 6430000; FY 2028: 2186000
R-5724B | HIGHWAY | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | RIGHT-OF-WAY | 3900000 | FY 2023: 809000; FY 2024: 1387000; FY 2025: 924000; FY 2026: 390000; FY 2027: 390000
R-5724B | HIGHWAY | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | UTILITIES | 1300000 | FY 2023: 650000; FY 2024: 650000
R-5725 | HIGHWAY | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | COORDINATE WITH U-6127. RIGHT OF WAY IN PROGRESS | REGION D |  | T | CONSTRUCTION | 7300000 | FY 2023: 73000; FY 2024: 5233000; FY 2025: 1994000
R-5725 | HIGHWAY | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | COORDINATE WITH U-6127. RIGHT OF WAY IN PROGRESS | REGION D |  | T | UTILITIES | 500000
R-5725 | HIGHWAY | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | COORDINATE WITH U-6127. RIGHT OF WAY IN PROGRESS | REGION D |  |  |  | 925000
R-5725 | HIGHWAY | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | COORDINATE WITH U-6127. RIGHT OF WAY IN PROGRESS | REGION D |  | T | RIGHT-OF-WAY | 1287000
R-5726 | HIGHWAY | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  |  |  | 18233000
R-5726 | HIGHWAY | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | CONSTRUCTION | 32499000 | FY 2025: 8224000; FY 2026: 13542000; FY 2027: 9020000; FY 2028: 1713000
R-5726A | HIGHWAY | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). CLEARING, GRUBBING, AND EROSION CONTROL. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 5404000 | FY 2023: 4162000; FY 2024: 1188000
R-5727 | HIGHWAY | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 2 | Down East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 62700000 | FY 2029: 9575000; FY 2030: 22317000; FY 2031: 17517000; FY 2032: 12101000; FY 2033: 1190000
R-5727 | HIGHWAY | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 2 | Down East RPO |  | DIVISION 2 |  | T | UTILITIES | 1300000 | FY 2027: 650000; FY 2028: 650000
R-5727 | HIGHWAY | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 2 | Down East RPO |  | DIVISION 2 |  |  |  | 2250000
R-5727 | HIGHWAY | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 2 | Down East RPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 12701000 | FY 2027: 968000; FY 2028: 5806000; FY 2029: 3387000; FY 2030: 1270000; FY 2031: 1270000
R-5728 | HIGHWAY | US 601 | SOUTH SALISBURY STREET IN MOCKSVILLE. INTERSECTION IMPROVEMENTS. | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | REGION D |  |  |  | 2350000
R-5730 | HIGHWAY | SR 1605 (OLD US 421) | SR 1146 (SHACKTOWN ROAD) TO SR 1711 (SPEER BRIDGE ROAD). CONSTRUCT NEW ROADWAY TO REALIGN SR 1605 WITH SR 1711 AND CONSTRUCT A ROUNDABOUT AT THE INTERSECTION WITH SR 1146. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | DIVISION 11 |  |  |  | 1350000
R-5730 | HIGHWAY | SR 1605 (OLD US 421) | SR 1146 (SHACKTOWN ROAD) TO SR 1711 (SPEER BRIDGE ROAD). CONSTRUCT NEW ROADWAY TO REALIGN SR 1605 WITH SR 1711 AND CONSTRUCT A ROUNDABOUT AT THE INTERSECTION WITH SR 1146. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | DIVISION 11 |  | T | CONSTRUCTION | 3216000 | FY 2023: 3184000
R-5734 | HIGHWAY | US 23/US 441 | US 64 TO SR 1649 (PRENTISS BRIDGE ROAD). IMPLEMENT ACCESS MANAGEMENT STRATEGIES. | 14 | Southwestern RPO | SEGMENT A INCLUDES THE REPLACEMENT OF BRIDGE 314 FORMERLY SCHEDULED TO BE REPLACED UNDER 17BP.14.R.154 |  |  |  |  | 10808000
R-5734A | HIGHWAY | US 23/US 441 | US 64 TO SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE). | 14 | Southwestern RPO | COMPLETE; BUILD NC BOND FUNDING: $1.788 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $9.797 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 14 |  | T | ENGINEERING | 2310000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 308000
R-5734A | HIGHWAY | US 23/US 441 | US 64 TO SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE). | 14 | Southwestern RPO | COMPLETE; BUILD NC BOND FUNDING: $1.788 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $9.797 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 14 |  | T | BUILD NC CON | 12600000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 1680000
R-5734B | HIGHWAY | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 13800000 | [11 empty] | 13800000
R-5734B | HIGHWAY | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 3200000 | [11 empty] | 3200000
R-5734B | HIGHWAY | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 26600000 | [11 empty] | 26600000
R-5734C | HIGHWAY | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 600000 | [11 empty] | 600000
R-5734C | HIGHWAY | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 53600000 | [11 empty] | 53600000
R-5734C | HIGHWAY | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5000000 | [11 empty] | 5000000
R-5735 | HIGHWAY | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | DIVISION 14 |  |  |  | 4038000
R-5735 | HIGHWAY | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | DIVISION 14 |  | T | ENGINEERING | 2670000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000
R-5735 | HIGHWAY | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | DIVISION 14 |  | T | ENGINEERING | 30000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 4000
R-5735 | HIGHWAY | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | DIVISION 14 |  | T | BUILD NC ROW | 4815000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000
R-5735 | HIGHWAY | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | DIVISION 14 |  | T | BUILD NC CON | 5805000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000
R-5735 | HIGHWAY | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | DIVISION 14 |  | T | BUILD NC CON | 9585000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 1278000
R-5736 | HIGHWAY | US 601 | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | 9 | Northwest Piedmont RPO |  | DIVISION 9 |  |  |  | 830000
R-5736 | HIGHWAY | US 601 | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | 9 | Northwest Piedmont RPO |  | DIVISION 9 |  | BGANY | CONSTRUCTION | 17001000 | FY 2028: 170000; FY 2029: 9271000; FY 2030: 6020000; FY 2031: 1540000
R-5736 | HIGHWAY | US 601 | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | 9 | Northwest Piedmont RPO |  | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 5000000 | FY 2026: 381000; FY 2027: 2286000; FY 2028: 1333000; FY 2029: 500000; FY 2030: 500000
R-5736 | HIGHWAY | US 601 | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | 9 | Northwest Piedmont RPO |  | DIVISION 9 |  | BGANY | UTILITIES | 800000 | FY 2026: 800000
R-5737 | HIGHWAY | US 29 / US 70 / BUSINESS 85 | SR 1798 (OLD GREENSBORO ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION; INCLUDES PARTICIPATION BY DAVIDSON COUNTY COMMUNITY COLLEGE | DIVISION 9 |  |  |  | 6400000
R-5737 | HIGHWAY | US 29 / US 70 / BUSINESS 85 | SR 1798 (OLD GREENSBORO ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION; INCLUDES PARTICIPATION BY DAVIDSON COUNTY COMMUNITY COLLEGE | DIVISION 9 |  | T | CONSTRUCTION | 29777000 | FY 2023: 12976000; FY 2024: 8445000; FY 2025: 1915000
R-5738 | HIGHWAY | SR 1208 (WEST KITTY HAWK ROAD) | SR 1210 (BOB PERRY ROAD) TO IVY LANE. UPGRADE FACILITY AND REPLACE BRIDGE 270040. | 1 | Albemarle RPO | COMPLETED. BUILD NC BOND FUNDING: $3,561,232 FOR CONSTRUCTION PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | DIVISION 1 |  |  |  | 668000
R-5738 | HIGHWAY | SR 1208 (WEST KITTY HAWK ROAD) | SR 1210 (BOB PERRY ROAD) TO IVY LANE. UPGRADE FACILITY AND REPLACE BRIDGE 270040. | 1 | Albemarle RPO | COMPLETED. BUILD NC BOND FUNDING: $3,561,232 FOR CONSTRUCTION PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | DIVISION 1 |  | T | BUILD NC CON | 4646000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000
R-5739 | HIGHWAY | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  |  |  | 1185000
R-5739 | HIGHWAY | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | T | CONSTRUCTION | 28099000 | FY 2025: 5768000; FY 2026: 11507000; FY 2027: 8493000; FY 2028: 2331000
R-5739 | HIGHWAY | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | T | RIGHT-OF-WAY | 2765000
R-5739 | HIGHWAY | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | T | UTILITIES | 10800000 | FY 2023: 5400000
R-5740 | HIGHWAY | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 1 |  |  |  | 893000
R-5740 | HIGHWAY | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 1 |  | T | ENGINEERING | 1035000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000
R-5740 | HIGHWAY | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 1 |  | T | BUILD NC ROW | 765000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000
R-5740 | HIGHWAY | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 1 |  | T | CONSTRUCTION | 5841000 | FY 2023: 1054000
R-5742 | HIGHWAY | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 14 |  | T | ENGINEERING | 2490000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000
R-5742 | HIGHWAY | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 14 |  | T | BUILD NC CON | 17085000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 2278000
R-5742 | HIGHWAY | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 14 |  | T | BUILD NC CON | 10992000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 1374000
R-5742 | HIGHWAY | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 14 |  | T | ENGINEERING | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 2000
R-5742 | HIGHWAY | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 14 |  |  |  | 4133000
R-5742 | HIGHWAY | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 14 |  | T | BUILD NC ROW | 540000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000
R-5745 | HIGHWAY | US 64/NC 90/NC 18 (WILKESBORO BLVD) | INTERSECTION OF US 64/NC 90/NC 18 (WILKESBORO BOULEVARD) AND US 64/NC 90 (TAYLORSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | COMPLETE; BUILD NC BOND FUNDING: $1.313M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 11 |  |  |  | 3521000
R-5745 | HIGHWAY | US 64/NC 90/NC 18 (WILKESBORO BLVD) | INTERSECTION OF US 64/NC 90/NC 18 (WILKESBORO BOULEVARD) AND US 64/NC 90 (TAYLORSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | COMPLETE; BUILD NC BOND FUNDING: $1.313M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 11 |  | T | BUILD NC CON | 1695000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000
R-5748 | HIGHWAY | SR 1127 (KANUGA ROAD) | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | 14 | French Broad River MPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 12500000
R-5748 | HIGHWAY | SR 1127 (KANUGA ROAD) | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | 14 | French Broad River MPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 17600000
R-5748 | HIGHWAY | SR 1127 (KANUGA ROAD) | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | 14 | French Broad River MPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 22099000
R-5748 | HIGHWAY | SR 1127 (KANUGA ROAD) | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | 14 | French Broad River MPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1530000
R-5751 | HIGHWAY | US 74 | NC 72/NC 130. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  |  |  | 950000
R-5751 | HIGHWAY | US 74 | NC 72/NC 130. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | T | RIGHT-OF-WAY | 325000
R-5751 | HIGHWAY | US 74 | NC 72/NC 130. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | T | CONSTRUCTION | 28285000 | FY 2023: 1680000; FY 2024: 13772000; FY 2025: 10016000; FY 2026: 2817000
R-5753 | HIGHWAY | VARIOUS | FEDERAL LANDS TRANSPORTATION PROGRAM (FLTP) AND EMERGENCY RELIEF FOR FEDERALLY OWNED ROADS (ERFO). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO FEDERAL LANDS. | 99 | STATEWIDE PROJECT | PROGRAM IN PROGRESS | EXEMPT |  | ERFO | CONSTRUCTION | 670000
R-5753 | HIGHWAY | VARIOUS | FEDERAL LANDS TRANSPORTATION PROGRAM (FLTP) AND EMERGENCY RELIEF FOR FEDERALLY OWNED ROADS (ERFO). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO FEDERAL LANDS. | 99 | STATEWIDE PROJECT | PROGRAM IN PROGRESS | EXEMPT |  | FLTP | CONSTRUCTION | 89585000 | FY 2023: 7090000; FY 2024: 1700000; FY 2025: 48868000; FY 2026: 1936000; FY 2027: 117000
R-5753A | HIGHWAY | VARIOUS | DEPLOYMENT OF AUTOMATED SHUTTLE AT WRIGHT BROTHERS NATIONAL MEMORIAL. | 1 | Albemarle RPO |  | EXEMPT |  | FLTP | IMPLEMENTATION | 95000
R-5757 | HIGHWAY | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | BGLT5 | UTILITIES | 4122000 | FY 2023: 2061000; FY 2024: 2061000
R-5757 | HIGHWAY | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  |  |  | 1338000
R-5757 | HIGHWAY | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | BGLT5 | RIGHT-OF-WAY | 3200000 | FY 2023: 3200000
R-5757A | HIGHWAY | NC 305 | HERTFORD COUNTY LINE TO NORTH OF SR 1503 (LASKER ROAD). UPGRADE ROADWAY. | 1 | Peanut Belt RPO |  | DIVISION 1 |  | BGLT5 | CONSTRUCTION | 19000000 | FY 2025: 4750000; FY 2026: 7790000; FY 2027: 6460000
R-5757B | HIGHWAY | NC 305 | NORTH OF SR 1503 (LASKER ROAD) TO SEABOARD TOWN LIMITS. UPGRADE ROADWAY. | 1 | Peanut Belt RPO |  | DIVISION 1 |  | BGLT5 | CONSTRUCTION | 20700000 | FY 2025: 5175000; FY 2026: 8487000; FY 2027: 7038000
R-5759 | HIGHWAY | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); | DIVISION 11 |  | T | BUILD NC ROW | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 3000
R-5759 | HIGHWAY | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); | DIVISION 11 |  | T | CONSTRUCTION | 27300000 | FY 2024: 273000; FY 2025: 10061000; FY 2026: 10074000; FY 2027: 6892000
R-5759 | HIGHWAY | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); | DIVISION 11 |  | T | RIGHT-OF-WAY | 12600000 | FY 2023: 6300000; FY 2024: 3150000
R-5759 | HIGHWAY | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); | DIVISION 11 |  |  |  | 1000000
R-5759 | HIGHWAY | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); | DIVISION 11 |  | T | UTILITIES | 900000 | FY 2023: 450000
R-5759 | HIGHWAY | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); | DIVISION 11 |  | T | ENGINEERING | 1365000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000
R-5761 | HIGHWAY | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 10000
R-5761 | HIGHWAY | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 2200000 | FY 2027: 1112000; FY 2028: 648000; FY 2029: 220000; FY 2030: 220000
R-5761 | HIGHWAY | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 13300000 | FY 2029: 2985000; FY 2030: 7367000; FY 2031: 2948000
R-5761 | HIGHWAY | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | UTILITIES | 500000 | FY 2027: 500000
R-5762 | HIGHWAY | NC 16 | INTERSECTION OF NC 16 AND SR 1609 (COUNTY HOME ROAD). CONSTRUCT INTERSECTION IMPROVMENTS. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  |  |  | 210000
R-5762 | HIGHWAY | NC 16 | INTERSECTION OF NC 16 AND SR 1609 (COUNTY HOME ROAD). CONSTRUCT INTERSECTION IMPROVMENTS. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | T | RIGHT-OF-WAY | 120000
R-5762 | HIGHWAY | NC 16 | INTERSECTION OF NC 16 AND SR 1609 (COUNTY HOME ROAD). CONSTRUCT INTERSECTION IMPROVMENTS. | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 12 |  | T | CONSTRUCTION | 635000 | FY 2023: 6000; FY 2024: 629000
R-5763 | HIGHWAY | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 14 |  |  |  | 1770000
R-5763 | HIGHWAY | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 14 |  | T | RIGHT-OF-WAY | 17400000 | FY 2023: 8200000; FY 2024: 8200000
R-5763 | HIGHWAY | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 14 |  | T | UTILITIES | 2400000 | FY 2023: 1200000
R-5763 | HIGHWAY | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 14 |  | T | CONSTRUCTION | 40200000 | FY 2025: 402000; FY 2026: 14919000; FY 2027: 13100000; FY 2028: 8826000; FY 2029: 2953000
R-5766 | HIGHWAY | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO US 158 / US 29 BUSINESS (FREEWAY DRIVE) IN REIDSVILLE. UPGRADE ROADWAY. | 7 | Piedmont Triad RPO | [5 empty] | 1200000
R-5766A | HIGHWAY | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | CONSTRUCTION | 13101000 | FY 2026: 131000; FY 2027: 7740000; FY 2028: 4586000; FY 2029: 644000
R-5766A | HIGHWAY | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | UTILITIES | 2200000 | FY 2024: 1100000; FY 2025: 1100000
R-5766A | HIGHWAY | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 8700000 | FY 2024: 30000; FY 2025: 2953000; FY 2026: 3977000; FY 2027: 870000; FY 2028: 870000
R-5766B | HIGHWAY | NC 65 / NC 87 | SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) TO SR 2413 (VANCE STREET EXTENSION) | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | UTILITIES | 900000 | FY 2024: 900000
R-5766B | HIGHWAY | NC 65 / NC 87 | SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) TO SR 2413 (VANCE STREET EXTENSION) | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | CONSTRUCTION | 8800000 | FY 2026: 88000; FY 2027: 5813000; FY 2028: 2899000
R-5766B | HIGHWAY | NC 65 / NC 87 | SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) TO SR 2413 (VANCE STREET EXTENSION) | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 4000000 | FY 2024: 14000; FY 2025: 1357000; FY 2026: 1829000; FY 2027: 400000; FY 2028: 400000
R-5766C | HIGHWAY | NC 65 / NC 87 | SR 2413 (VANCE STREET EXTENSION) TO US 158 / US 29 BUSINESS IN REIDSVILLE | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 5900000 | FY 2024: 20000; FY 2025: 2003000; FY 2026: 2697000; FY 2027: 590000; FY 2028: 590000
R-5766C | HIGHWAY | NC 65 / NC 87 | SR 2413 (VANCE STREET EXTENSION) TO US 158 / US 29 BUSINESS IN REIDSVILLE | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | UTILITIES | 1700000 | FY 2024: 850000; FY 2025: 850000
R-5766C | HIGHWAY | NC 65 / NC 87 | SR 2413 (VANCE STREET EXTENSION) TO US 158 / US 29 BUSINESS IN REIDSVILLE | 7 | Piedmont Triad RPO |  | DIVISION 7 |  | T | CONSTRUCTION | 14900000 | FY 2026: 149000; FY 2027: 8188000; FY 2028: 5266000; FY 2029: 1297000
R-5768 | HIGHWAY | US 311 | NC 65 IN WALNUT COVE. UPGRADE INTERSECTION AND IMPROVE RAILROAD CROSSING. | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | DIVISION 9 |  | BGLT5 | CONSTRUCTION | 3040000 | FY 2023: 2372000; FY 2024: 668000
R-5768 | HIGHWAY | US 311 | NC 65 IN WALNUT COVE. UPGRADE INTERSECTION AND IMPROVE RAILROAD CROSSING. | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | DIVISION 9 |  | T | CONSTRUCTION | 760000 | FY 2023: 593000; FY 2024: 167000
R-5768 | HIGHWAY | US 311 | NC 65 IN WALNUT COVE. UPGRADE INTERSECTION AND IMPROVE RAILROAD CROSSING. | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 2500000
R-5771 | HIGHWAY | SR 1690 (BROADPOINTE DRIVE) | IMPROVE EXISTING SR 1690 (BROADPOINTE DRIVE) TO 24 FEET PAVED ROADWAY AND REPLACE BRIDGE 440107. | 14 | French Broad River MPO | ARC PROJECT NO. 18340 - UNDER CONSTRUCTION | EXEMPT |  |  |  | 1865000
R-5772 | HIGHWAY | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  |  |  | 1000000
R-5772 | HIGHWAY | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | RIGHT-OF-WAY | 3000000 | FY 2025: 30000; FY 2026: 999000; FY 2027: 1371000; FY 2028: 300000; FY 2029: 300000
R-5772 | HIGHWAY | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | UTILITIES | 1500000 | FY 2025: 750000; FY 2026: 750000
R-5772 | HIGHWAY | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | CONSTRUCTION | 10448000 | FY 2027: 104000; FY 2028: 4744000; FY 2029: 4258000; FY 2030: 1342000
R-5775 | HIGHWAY | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE MATCH IS SPOT SAFETY (SS-4911 AL); $487KM IN BGANY USED AS PART OF FUND SWAP. | EXEMPT |  |  |  | 500000
R-5775 | HIGHWAY | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE MATCH IS SPOT SAFETY (SS-4911 AL); $487KM IN BGANY USED AS PART OF FUND SWAP. | EXEMPT |  | S(M) | CONSTRUCTION | 210000 | FY 2023: 73000
R-5775 | HIGHWAY | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE MATCH IS SPOT SAFETY (SS-4911 AL); $487KM IN BGANY USED AS PART OF FUND SWAP. | EXEMPT |  | S(M) | CONSTRUCTION | 177000 | FY 2023: 61000
R-5775 | HIGHWAY | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE MATCH IS SPOT SAFETY (SS-4911 AL); $487KM IN BGANY USED AS PART OF FUND SWAP. | EXEMPT |  | BGDA | CONSTRUCTION | 353000 | FY 2023: 122000
R-5775 | HIGHWAY | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE MATCH IS SPOT SAFETY (SS-4911 AL); $487KM IN BGANY USED AS PART OF FUND SWAP. | EXEMPT |  | BGANY | CONSTRUCTION | 487000 | FY 2023: 169000
R-5775 | HIGHWAY | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE MATCH IS SPOT SAFETY (SS-4911 AL); $487KM IN BGANY USED AS PART OF FUND SWAP. | EXEMPT |  | BGANY | CONSTRUCTION | 708000 | FY 2023: 246000
R-5777 | HIGHWAY | US 70 | SR 1124 (GRANTHAM ROAD) TO THE PROPOSED US 70 HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY. | 2 | New Bern Area MPO | [5 empty] | 2260000
R-5777A | HIGHWAY | US 70 | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | New Bern Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 47438000
R-5777A | HIGHWAY | US 70 | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | New Bern Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713. | STATEWIDE MOBILITY |  | T | UTILITIES | 300000
R-5777A | HIGHWAY | US 70 | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | New Bern Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 50778000 | FY 2023: 9099000; FY 2024: 7766000; FY 2025: 15220000
R-5777B | HIGHWAY | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | ENGINEERING | 105000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000
R-5777B | HIGHWAY | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | BUILD NC ROW | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
R-5777B | HIGHWAY | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | RIGHT-OF-WAY | 47432000
R-5777B | HIGHWAY | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | UTILITIES | 300000
R-5777B | HIGHWAY | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | REGION B |  | T | CONSTRUCTION | 50778000 | FY 2023: 9099000; FY 2024: 7766000; FY 2025: 15220000
R-5777C | HIGHWAY | US 70 | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 278703000 | FY 2023: 21000000; FY 2024: 48640000; FY 2025: 46049000; FY 2026: 67654000; FY 2027: 95360000
R-5777C | HIGHWAY | US 70 | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | UTILITIES | 13344000 | FY 2023: 6672000; FY 2024: 6672000
R-5777C | HIGHWAY | US 70 | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 29129000 | FY 2023: 291000; FY 2024: 11361000; FY 2025: 11651000; FY 2026: 2913000; FY 2027: 2913000
R-5777D | HIGHWAY | US 70 | INSTALL BROADBAND FIBER ALONG US 70 FROM I-40 TO PORT OF MOREHEAD CITY. | 2, 4, 5 | Down East RPO, Eastern Carolina RPO, New Bern Area MPO, Upper Coastal Plain RPO, Goldsboro Urban Area MPO, Capital Area MPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5986C, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 14600000 | FY 2023: 5493000
R-5777D | HIGHWAY | US 70 | INSTALL BROADBAND FIBER ALONG US 70 FROM I-40 TO PORT OF MOREHEAD CITY. | 2, 4, 5 | Down East RPO, Eastern Carolina RPO, New Bern Area MPO, Upper Coastal Plain RPO, Goldsboro Urban Area MPO, Capital Area MPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5986C, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | STATEWIDE MOBILITY |  | DP | CONSTRUCTION | 11400000 | FY 2023: 4289000
R-5779 | HIGHWAY | SR 1631 (CROSSROADS PARKWAY) | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | 13 | French Broad River MPO | COMPLETE. UNDER CONSTRUCTION. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170) | DIVISION 13 |  |  |  | 769000
R-5779 | HIGHWAY | SR 1631 (CROSSROADS PARKWAY) | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | 13 | French Broad River MPO | COMPLETE. UNDER CONSTRUCTION. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170) | DIVISION 13 |  | ADHSL | CONSTRUCTION | 1611000
R-5779 | HIGHWAY | SR 1631 (CROSSROADS PARKWAY) | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | 13 | French Broad River MPO | COMPLETE. UNDER CONSTRUCTION. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170) | DIVISION 13 |  | O | CONSTRUCTION | 950000
R-5779 | HIGHWAY | SR 1631 (CROSSROADS PARKWAY) | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | 13 | French Broad River MPO | COMPLETE. UNDER CONSTRUCTION. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170) | DIVISION 13 |  | T | CONSTRUCTION | 1510000
R-5781 | HIGHWAY | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 1 |  |  |  | 3855000
R-5781 | HIGHWAY | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 1 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5781 | HIGHWAY | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 1 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5782 | HIGHWAY | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 2 |  |  |  | 2827000
R-5782 | HIGHWAY | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 2 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5782 | HIGHWAY | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 2 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5783 | HIGHWAY | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 3 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5783 | HIGHWAY | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 3 |  |  |  | 3780000
R-5783 | HIGHWAY | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 3 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5784 | HIGHWAY | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. S FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 4 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5784 | HIGHWAY | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. S FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 4 |  |  |  | 5247000
R-5784 | HIGHWAY | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. S FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 4 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5785 | HIGHWAY | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  |  |  | 4517000
R-5785 | HIGHWAY | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | S | CONSTRUCTION | 200000 | FY 2023: 200000
R-5785 | HIGHWAY | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | TA | CONSTRUCTION | 800000 | FY 2023: 800000
R-5786 | HIGHWAY | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | UNDER CONSTRUCTION. S FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 6 |  |  |  | 7383000
R-5786 | HIGHWAY | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | UNDER CONSTRUCTION. S FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 6 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5786 | HIGHWAY | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | UNDER CONSTRUCTION. S FUNDS REFLECT STATE HIGHWAY FUNDS. | DIVISION 6 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5787 | HIGHWAY | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 7 |  |  |  | 5689000
R-5787 | HIGHWAY | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 7 |  | S | CONSTRUCTION | 720000 | FY 2023: 200000; FY 2024: 20000
R-5787 | HIGHWAY | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 7 |  | TA | CONSTRUCTION | 2880000 | FY 2023: 800000; FY 2024: 80000
R-5788 | HIGHWAY | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 8 |  | TA | CONSTRUCTION | 2880000 | FY 2023: 800000; FY 2024: 80000
R-5788 | HIGHWAY | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 8 |  |  |  | 2485000
R-5788 | HIGHWAY | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 8 |  | S | CONSTRUCTION | 720000 | FY 2023: 200000; FY 2024: 20000
R-5789 | HIGHWAY | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 9 |  | TA | CONSTRUCTION | 2880000 | FY 2023: 800000; FY 2024: 80000
R-5789 | HIGHWAY | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 9 |  |  |  | 4733000
R-5789 | HIGHWAY | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS | DIVISION 9 |  | S | CONSTRUCTION | 720000 | FY 2023: 200000; FY 2024: 20000
R-5790 | HIGHWAY | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 10 |  |  |  | 3990000
R-5790 | HIGHWAY | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 10 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5790 | HIGHWAY | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 10 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5791 | HIGHWAY | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 11 |  |  |  | 632000
R-5791 | HIGHWAY | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 11 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5791 | HIGHWAY | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 11 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5792 | HIGHWAY | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 12 |  |  |  | 6841000
R-5792 | HIGHWAY | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 12 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5792 | HIGHWAY | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 12 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5793 | HIGHWAY | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 13 |  |  |  | 7540000
R-5793 | HIGHWAY | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 13 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5793 | HIGHWAY | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 13 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5794 | HIGHWAY | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 14 |  |  |  | 5749000
R-5794 | HIGHWAY | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 14 |  | S | CONSTRUCTION | 700000 | FY 2023: 200000
R-5794 | HIGHWAY | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS | DIVISION 14 |  | TA | CONSTRUCTION | 2800000 | FY 2023: 800000
R-5795 | HIGHWAY | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | 4 | Upper Coastal Plain RPO |  | REGION A |  |  |  | 50000
R-5795 | HIGHWAY | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | 4 | Upper Coastal Plain RPO |  | REGION A |  | T | RIGHT-OF-WAY | 4630000 | FY 2027: 889000; FY 2028: 1778000; FY 2029: 1037000; FY 2030: 463000; FY 2031: 463000
R-5795 | HIGHWAY | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | 4 | Upper Coastal Plain RPO |  | REGION A |  | T | UTILITIES | 4400000 | FY 2027: 2200000; FY 2028: 2200000
R-5795 | HIGHWAY | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | 4 | Upper Coastal Plain RPO |  | REGION A |  | T | CONSTRUCTION | 11700000 | FY 2029: 2701000; FY 2030: 6570000; FY 2031: 2429000
R-5796 | HIGHWAY | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | REGION A |  |  |  | 750000
R-5796 | HIGHWAY | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | REGION A |  | T | RIGHT-OF-WAY | 2576000 | FY 2024: 824000; FY 2025: 1236000; FY 2026: 258000; FY 2027: 258000
R-5796 | HIGHWAY | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | REGION A |  | T | UTILITIES | 1570000 | FY 2024: 785000; FY 2025: 785000
R-5796 | HIGHWAY | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | REGION A |  | T | BUILD NC CON | 6435000 |  |  |  | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 3003000
R-5796 | HIGHWAY | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | REGION A |  | T | CONSTRUCTION | 7300000 | FY 2025: 123000; FY 2026: 1519000; FY 2027: 5658000
R-5797 | HIGHWAY | US 74 | SR 1506 (BOARDMAN ROAD). UPGRADE AT-GRADE INTERSECTION TO AN INTERCHANGE. | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | REGION C |  |  |  | 3000000
R-5797 | HIGHWAY | US 74 | SR 1506 (BOARDMAN ROAD). UPGRADE AT-GRADE INTERSECTION TO AN INTERCHANGE. | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | REGION C |  | T | CONSTRUCTION | 18620000 | FY 2023: 9167000
R-5798 | HIGHWAY | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | 10 | Rocky River RPO |  | STATEWIDE MOBILITY |  | BGANY | CONSTRUCTION | 21300000 | FY 2029: 9938000; FY 2030: 8207000; FY 2031: 213000; FY 2032: 2942000
R-5798 | HIGHWAY | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | 10 | Rocky River RPO |  | STATEWIDE MOBILITY |  | BGANY | UTILITIES | 4900000 | FY 2025: 2450000; FY 2026: 2450000
R-5798 | HIGHWAY | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | 10 | Rocky River RPO |  | STATEWIDE MOBILITY |  | BGANY | RIGHT-OF-WAY | 14800000 | FY 2025: 3330000; FY 2026: 4440000; FY 2027: 1480000; FY 2028: 4070000; FY 2029: 1480000
R-5798 | HIGHWAY | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | 10 | Rocky River RPO |  | STATEWIDE MOBILITY |  |  |  | 1695000
R-5799 | HIGHWAY | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | REGION G |  | T | BUILD NC ROW | 1290000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 258000
R-5799 | HIGHWAY | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | REGION G |  | T | RIGHT-OF-WAY | 4600000 | FY 2023: 2300000
R-5799 | HIGHWAY | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | REGION G |  | T | UTILITIES | 600000
R-5799 | HIGHWAY | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | REGION G |  | T | CONSTRUCTION | 16000000 | FY 2024: 5403000; FY 2025: 7359000; FY 2026: 3238000
R-5799 | HIGHWAY | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | REGION G |  |  |  | 1525000
R-5800 | HIGHWAY | US 64, US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | REGION G |  |  |  | 250000
R-5800 | HIGHWAY | US 64, US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | REGION G |  | T | CONSTRUCTION | 17802000 | FY 2025: 4907000; FY 2026: 8406000; FY 2027: 4489000
R-5800 | HIGHWAY | US 64, US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | REGION G |  | T | RIGHT-OF-WAY | 14799000 | FY 2023: 1973000; FY 2024: 7893000; FY 2025: 1973000; FY 2026: 1480000; FY 2027: 1480000
R-5800 | HIGHWAY | US 64, US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | REGION G |  | T | UTILITIES | 3900000 | FY 2023: 1950000; FY 2024: 1950000
R-5804 | HIGHWAY | NC 226 | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | 13 | High Country RPO |  | NOT FUNDED |  |  |  | 4380000
R-5804 | HIGHWAY | NC 226 | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | 13 | High Country RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 15900000 | [11 empty] | 15900000
R-5804 | HIGHWAY | NC 226 | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | 13 | High Country RPO |  | NOT FUNDED |  | T | UTILITIES | 3200000 | [11 empty] | 3200000
R-5804 | HIGHWAY | NC 226 | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | 13 | High Country RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 33298000 | [11 empty] | 33298000
R-5806 | HIGHWAY | SR 1336 (HARVEY POINT ROAD) | US 17 TO SR 1350 (CHURCHES LANE). MODERNIZE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  |  |  | 185000
R-5806 | HIGHWAY | SR 1336 (HARVEY POINT ROAD) | US 17 TO SR 1350 (CHURCHES LANE). MODERNIZE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | BGLT5 | CONSTRUCTION | 3900000 | FY 2023: 2469000
R-5807 | HIGHWAY | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 1 | Albemarle RPO |  | DIVISION 1 |  |  |  | 750000
R-5807 | HIGHWAY | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 1 | Albemarle RPO |  | DIVISION 1 |  | BGLT5 | RIGHT-OF-WAY | 508000 | FY 2024: 508000
R-5807 | HIGHWAY | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 1 | Albemarle RPO |  | DIVISION 1 |  | BGLT5 | UTILITIES | 9232000 | FY 2024: 4616000; FY 2025: 4616000
R-5807 | HIGHWAY | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 1 | Albemarle RPO |  | DIVISION 1 |  | BGLT5 | CONSTRUCTION | 19700000 | FY 2027: 197000; FY 2028: 8642000; FY 2029: 7217000; FY 2030: 3644000
R-5808 | HIGHWAY | US 158 | SR 1002 (ACORN HILL ROAD) TO PASQUOTANK COUNTY LINE. MODERNIZE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | NHP | CONSTRUCTION | 19700000 | FY 2023: 197000; FY 2024: 11032000; FY 2025: 7486000; FY 2026: 985000
R-5808 | HIGHWAY | US 158 | SR 1002 (ACORN HILL ROAD) TO PASQUOTANK COUNTY LINE. MODERNIZE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  |  |  | 800000
R-5808 | HIGHWAY | US 158 | SR 1002 (ACORN HILL ROAD) TO PASQUOTANK COUNTY LINE. MODERNIZE ROADWAY. | 1 | Albemarle RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | NHP | RIGHT-OF-WAY | 93000
R-5809 | HIGHWAY | NC 45 | HERTFORD COUNTY LINE TO WASHINGTON COUNTY LINE. MODERNIZE ROADWAY. | 1 | Peanut Belt RPO | [5 empty] | 2219000
R-5809A | HIGHWAY | NC 45 | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | T | UTILITIES | 4420000 | FY 2023: 2210000; FY 2024: 2210000
R-5809A | HIGHWAY | NC 45 | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | T | CONSTRUCTION | 17399000 | FY 2024: 174000; FY 2025: 7865000; FY 2026: 6484000; FY 2027: 2876000
R-5809A | HIGHWAY | NC 45 | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | T | RIGHT-OF-WAY | 5000 | FY 2023: 5000
R-5809B | HIGHWAY | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. | 1 | Peanut Belt RPO |  | DIVISION 1 |  | T | RIGHT-OF-WAY | 3012000 | FY 2025: 30000; FY 2026: 1205000; FY 2027: 1205000; FY 2028: 301000; FY 2029: 271000
R-5809B | HIGHWAY | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. | 1 | Peanut Belt RPO |  | DIVISION 1 |  | T | UTILITIES | 12944000 | FY 2025: 6472000; FY 2026: 6472000
R-5809B | HIGHWAY | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. | 1 | Peanut Belt RPO |  | DIVISION 1 |  | T | CONSTRUCTION | 33498000 | FY 2027: 335000; FY 2028: 12912000; FY 2029: 11343000; FY 2030: 8908000
R-5810 | HIGHWAY | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | 1 | Mid-East RPO |  | DIVISION 1 |  | T | UTILITIES | 720000 | FY 2025: 720000
R-5810 | HIGHWAY | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | 1 | Mid-East RPO |  | DIVISION 1 |  | T | RIGHT-OF-WAY | 30000 | FY 2025: 30000
R-5810 | HIGHWAY | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | 1 | Mid-East RPO |  | DIVISION 1 |  | BGLT5 | CONSTRUCTION | 8100000 | FY 2027: 81000; FY 2028: 5301000; FY 2029: 2718000
R-5810 | HIGHWAY | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | 1 | Mid-East RPO |  | DIVISION 1 |  |  |  | 500000
R-5811 | HIGHWAY | NC 461 | NC 45 TO END OF STATE MAINTENANCE. MODERNIZE ROADWAY. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | T | CONSTRUCTION | 5252000 | FY 2023: 4188000; FY 2024: 1064000
R-5811 | HIGHWAY | NC 461 | NC 45 TO END OF STATE MAINTENANCE. MODERNIZE ROADWAY. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | DIVISION 1 |  |  |  | 310000
R-5812 | HIGHWAY | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 2 |  | T | BUILD NC CON | 4455000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000
R-5812 | HIGHWAY | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 2 |  | T | BUILD NC CON | 4050000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 540000
R-5812 | HIGHWAY | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 2 |  | T | ENGINEERING | 60000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 8000
R-5812 | HIGHWAY | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 2 |  | T | ENGINEERING | 1230000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000
R-5812 | HIGHWAY | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 2 |  | L | CONSTRUCTION | 20000
R-5812 | HIGHWAY | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 2 |  | T | CONSTRUCTION | 640000
R-5813 | HIGHWAY | US 70 | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONVERT AT GRADE INTERSECTION TO INTERCHANGE. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  |  |  | 750000
R-5813 | HIGHWAY | US 70 | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONVERT AT GRADE INTERSECTION TO INTERCHANGE. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 10100000 | [11 empty] | 10100000
R-5813 | HIGHWAY | US 70 | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONVERT AT GRADE INTERSECTION TO INTERCHANGE. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | UTILITIES | 2797000 | [11 empty] | 2797000
R-5813 | HIGHWAY | US 70 | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONVERT AT GRADE INTERSECTION TO INTERCHANGE. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 69900000 | [11 empty] | 69900000
R-5814 | HIGHWAY | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 11900000 | FY 2027: 119000; FY 2028: 5481000; FY 2029: 3920000; FY 2030: 1190000; FY 2031: 1190000
R-5814 | HIGHWAY | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | T | UTILITIES | 3400000 | FY 2027: 1700000; FY 2028: 1700000
R-5814 | HIGHWAY | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  |  |  | 2000000
R-5814 | HIGHWAY | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 31302000 | FY 2029: 5831000; FY 2030: 13483000; FY 2031: 9107000; FY 2032: 2881000
R-5816 | HIGHWAY | NC 58 (WEST FORT MACON) | ATLANTIC BEACH CAUSEWAY. ADD RIGHT TURN LANE. | 2 | Down East RPO | UNDER CONSTRUCTION. | REGION B |  |  |  | 100000
R-5816 | HIGHWAY | NC 58 (WEST FORT MACON) | ATLANTIC BEACH CAUSEWAY. ADD RIGHT TURN LANE. | 2 | Down East RPO | UNDER CONSTRUCTION. | REGION B |  | T | RIGHT-OF-WAY | 600000
R-5816 | HIGHWAY | NC 58 (WEST FORT MACON) | ATLANTIC BEACH CAUSEWAY. ADD RIGHT TURN LANE. | 2 | Down East RPO | UNDER CONSTRUCTION. | REGION B |  | T | CONSTRUCTION | 1650000 | FY 2023: 1650000
R-5819 | HIGHWAY | US 74/US 76 | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | 6 | Cape Fear RPO | COMBINE WITH R-5820. UNDER CONSTRUCTION. | REGION C |  | T | UTILITIES | 129000
R-5819 | HIGHWAY | US 74/US 76 | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | 6 | Cape Fear RPO | COMBINE WITH R-5820. UNDER CONSTRUCTION. | REGION C |  | T | CONSTRUCTION | 11665000 | FY 2023: 5353000; FY 2024: 4946000; FY 2025: 1274000
R-5819 | HIGHWAY | US 74/US 76 | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | 6 | Cape Fear RPO | COMBINE WITH R-5820. UNDER CONSTRUCTION. | REGION C |  | T | RIGHT-OF-WAY | 346000
R-5819 | HIGHWAY | US 74/US 76 | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | 6 | Cape Fear RPO | COMBINE WITH R-5820. UNDER CONSTRUCTION. | REGION C |  |  |  | 500000
R-5819A | HIGHWAY | US 74 / 76 | ADVANCED CONSTRUCTION OF TEMPORARY REDUCED CONFLICT INTERSECTIONS AT SR 1735 (CHAUNCEY TOWN ROAD) AND SR 1740 (OLD LAKE ROAD). | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | REGION C |  | T | CONSTRUCTION | 2300000
R-5820 | HIGHWAY | US 74/US 76 | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 6 | Cape Fear RPO | COMBINE WITH R-5819. UNDER CONSTRUCTION. | REGION C |  |  |  | 850000
R-5820 | HIGHWAY | US 74/US 76 | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 6 | Cape Fear RPO | COMBINE WITH R-5819. UNDER CONSTRUCTION. | REGION C |  | T | RIGHT-OF-WAY | 931000
R-5820 | HIGHWAY | US 74/US 76 | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 6 | Cape Fear RPO | COMBINE WITH R-5819. UNDER CONSTRUCTION. | REGION C |  | T | UTILITIES | 1297000
R-5820 | HIGHWAY | US 74/US 76 | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 6 | Cape Fear RPO | COMBINE WITH R-5819. UNDER CONSTRUCTION. | REGION C |  | T | CONSTRUCTION | 50713000 | FY 2023: 23271000; FY 2024: 21505000; FY 2025: 5538000
R-5821 | HIGHWAY | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS, AND IMPROVE SR 1006 INTERSECTION. | 7 | Durham-Chapel Hill-Carrboro MPO, Triangle Area RPO | [5 empty] | 2430000
R-5821A | HIGHWAY | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9700000
R-5821A | HIGHWAY | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 7000000
R-5821A | HIGHWAY | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
R-5822 | HIGHWAY | NC 86 | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | 7 | Piedmont Triad RPO | SCOPE INCLUDES SPOT ID H170625 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 800000
R-5822 | HIGHWAY | NC 86 | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | 7 | Piedmont Triad RPO | SCOPE INCLUDES SPOT ID H170625 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 300000
R-5822 | HIGHWAY | NC 86 | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | 7 | Piedmont Triad RPO | SCOPE INCLUDES SPOT ID H170625 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 183000
R-5822 | HIGHWAY | NC 86 | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | 7 | Piedmont Triad RPO | SCOPE INCLUDES SPOT ID H170625 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 14200000
R-5823 | HIGHWAY | NC 65 / NC 68 | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTI-LANES. | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | DIVISION 7 |  | BGLT5 | RIGHT-OF-WAY | 10500000 | FY 2024: 5250000; FY 2025: 5250000
R-5823 | HIGHWAY | NC 65 / NC 68 | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTI-LANES. | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | DIVISION 7 |  | BGLT5 | UTILITIES | 424000 | FY 2024: 424000
R-5823 | HIGHWAY | NC 65 / NC 68 | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTI-LANES. | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | DIVISION 7 |  |  |  | 400000
R-5823 | HIGHWAY | NC 65 / NC 68 | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTI-LANES. | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | DIVISION 7 |  | BGLT5 | CONSTRUCTION | 28200000 | FY 2026: 282000; FY 2027: 14379000; FY 2028: 9683000; FY 2029: 3856000
R-5824 | HIGHWAY | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | 8 | Triangle Area RPO |  | REGION E |  |  |  | 1565000
R-5824 | HIGHWAY | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | 8 | Triangle Area RPO |  | REGION E |  | T | RIGHT-OF-WAY | 2400000 | FY 2024: 2006000; FY 2025: 394000
R-5824 | HIGHWAY | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | 8 | Triangle Area RPO |  | REGION E |  | T | UTILITIES | 1100000 | FY 2024: 1100000
R-5824 | HIGHWAY | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 30999000 | FY 2027: 310000; FY 2028: 12265000; FY 2029: 11811000; FY 2030: 6613000
R-5825 | HIGHWAY | NC 751 | SR 1731 (O'KELLY CHAPEL ROAD). UPGRADE AND REALIGN INTERSECTION. | 8 | Durham-Chapel Hill-Carrboro MPO | ROW in progress. | DIVISION 8 |  | T | CONSTRUCTION | 1251000 | FY 2023: 125000; FY 2024: 1126000
R-5825 | HIGHWAY | NC 751 | SR 1731 (O'KELLY CHAPEL ROAD). UPGRADE AND REALIGN INTERSECTION. | 8 | Durham-Chapel Hill-Carrboro MPO | ROW in progress. | DIVISION 8 |  |  |  | 396000
R-5826 | HIGHWAY | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO NC 24 / NC 27. UPGRADE ROADWAY, INCLUDING PAVED SHOULDERS, TURN LANES AND SIGNALS. | 8 | Piedmont Triad RPO | [5 empty] | 2285000
R-5826A | HIGHWAY | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3700000 | [11 empty] | 3700000
R-5826A | HIGHWAY | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | UTILITIES | 250000 | [11 empty] | 250000
R-5826A | HIGHWAY | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 9200000 | [11 empty] | 9200000
R-5826B | HIGHWAY | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | RIGHT-OF-WAY | 438000 | FY 2023: 394000; FY 2024: 44000
R-5826B | HIGHWAY | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | UTILITIES | 240000 | FY 2023: 240000
R-5826B | HIGHWAY | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | CONSTRUCTION | 11000000 | FY 2026: 6245000; FY 2027: 4755000
R-5826C | HIGHWAY | NC 109 | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3000000 | [11 empty] | 3000000
R-5826C | HIGHWAY | NC 109 | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | UTILITIES | 299000 | [11 empty] | 299000
R-5826C | HIGHWAY | NC 109 | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 18000000 | [11 empty] | 18000000
R-5828 | HIGHWAY | US 311 (NORTH MAIN STREET) | SR 1918 (FIRST STREET) IN WALNUT COVE. CONSTRUCT ROUNDABOUT. | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 1517000
R-5828 | HIGHWAY | US 311 (NORTH MAIN STREET) | SR 1918 (FIRST STREET) IN WALNUT COVE. CONSTRUCT ROUNDABOUT. | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | DIVISION 9 |  | T | CONSTRUCTION | 3050000 | FY 2023: 2167000
R-5829 | HIGHWAY | US 70 | US 70 BYPASS TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO | [5 empty] | 2000000
R-5829A | HIGHWAY | US 70 | US 70 BYPASS TO WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET). UPGRADE TO FREEWAY STANDARDS. | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO, Upper Coastal Plain RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 40072000
R-5829A | HIGHWAY | US 70 | US 70 BYPASS TO WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET). UPGRADE TO FREEWAY STANDARDS. | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO, Upper Coastal Plain RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7908000
R-5829A | HIGHWAY | US 70 | US 70 BYPASS TO WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET). UPGRADE TO FREEWAY STANDARDS. | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO, Upper Coastal Plain RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 101599000
R-5829B | HIGHWAY | US 70 | WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET) TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 13077000
R-5829B | HIGHWAY | US 70 | WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET) TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 71902000
R-5829B | HIGHWAY | US 70 | WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET) TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | 4 | Upper Coastal Plain RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4774000
R-5830 | HIGHWAY | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  |  |  | 350000
R-5830 | HIGHWAY | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | RIGHT-OF-WAY | 5800000 | FY 2024: 58000; FY 2025: 4582000; FY 2026: 580000; FY 2027: 580000
R-5830 | HIGHWAY | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | UTILITIES | 1200000 | FY 2024: 600000; FY 2025: 600000
R-5830 | HIGHWAY | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | CONSTRUCTION | 6200000 | FY 2025: 62000; FY 2026: 3779000; FY 2027: 2359000
R-5831 | HIGHWAY | US 601 | US 601 (CAROLINA AVENUE) AND NC 67 (MAIN STREET). UPGRADE INTERSECTION. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  |  |  | 440000
R-5831 | HIGHWAY | US 601 | US 601 (CAROLINA AVENUE) AND NC 67 (MAIN STREET). UPGRADE INTERSECTION. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  | T | UTILITIES | 650000 | FY 2023: 650000
R-5831 | HIGHWAY | US 601 | US 601 (CAROLINA AVENUE) AND NC 67 (MAIN STREET). UPGRADE INTERSECTION. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  | T | CONSTRUCTION | 3900000 | FY 2024: 501000; FY 2025: 3399000
R-5832 | HIGHWAY | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  |  |  | 550000
R-5832 | HIGHWAY | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | RIGHT-OF-WAY | 12800000 | FY 2024: 4096000; FY 2025: 6144000; FY 2026: 1280000; FY 2027: 1280000
R-5832 | HIGHWAY | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | UTILITIES | 4600000 | FY 2024: 2300000; FY 2025: 2300000
R-5832 | HIGHWAY | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | 11 | High Country RPO |  | DIVISION 11 |  | T | CONSTRUCTION | 32700000 | FY 2025: 327000; FY 2026: 10330000; FY 2027: 10745000; FY 2028: 7784000; FY 2029: 3514000
R-5833 | HIGHWAY | US 221 BUSINESS | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT REDUCED CONFLICT INTERSECTION. | 11 | High Country RPO |  | NOT FUNDED |  | T | UTILITIES | 50000 | [11 empty] | 50000
R-5833 | HIGHWAY | US 221 BUSINESS | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT REDUCED CONFLICT INTERSECTION. | 11 | High Country RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 2800000 | [11 empty] | 2800000
R-5833 | HIGHWAY | US 221 BUSINESS | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT REDUCED CONFLICT INTERSECTION. | 11 | High Country RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 1100000 | [11 empty] | 1100000
R-5833 | HIGHWAY | US 221 BUSINESS | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT REDUCED CONFLICT INTERSECTION. | 11 | High Country RPO |  | NOT FUNDED |  |  |  | 250000
R-5836 | HIGHWAY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $16M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | BGANY | RIGHT-OF-WAY | 3100000 | FY 2024: 413000; FY 2025: 1240000; FY 2026: 827000; FY 2027: 310000; FY 2028: 310000
R-5836 | HIGHWAY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $16M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | BGANY | UTILITIES | 1700000 | FY 2024: 850000; FY 2025: 850000
R-5836 | HIGHWAY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $16M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | T | BUILD NC CON | 21968000 | FY 2028: 1373000; FY 2029: 1373000; FY 2030: 1373000; FY 2031: 1373000; FY 2032: 1373000; FY 2033: 1373000 | 13730000
R-5836 | HIGHWAY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $16M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | T | CONSTRUCTION | 60000000 | FY 2026: 760000; FY 2027: 21127000; FY 2028: 12850000; FY 2029: 13099000; FY 2030: 12164000
R-5836 | HIGHWAY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $16M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  |  |  | 3350000
R-5837 | HIGHWAY | US 25 | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | 13 | Land-of-Sky RPO |  | NOT FUNDED |  |  |  | 4500000
R-5837 | HIGHWAY | US 25 | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | 13 | Land-of-Sky RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 18500000 | [11 empty] | 18500000
R-5837 | HIGHWAY | US 25 | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | 13 | Land-of-Sky RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5100000 | [11 empty] | 5100000
R-5837 | HIGHWAY | US 25 | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | 13 | Land-of-Sky RPO |  | NOT FUNDED |  | T | UTILITIES | 9700000 | [11 empty] | 9700000
R-5839 | HIGHWAY | NC 28 (FONTANA ROAD) | US 129 TO NC 143. UPGRADE ROADWAY. | 14 | Southwestern RPO | [5 empty] | 930000
R-5839A | HIGHWAY | NC 28 | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 1520000 | [11 empty] | 1520000
R-5839A | HIGHWAY | NC 28 | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 200000 | [11 empty] | 200000
R-5839A | HIGHWAY | NC 28 | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 312700000 | [11 empty] | 312700000
R-5839BA | HIGHWAY | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | DIVISION 14 |  | T | UTILITIES | 200000 | FY 2027: 200000
R-5839BA | HIGHWAY | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | DIVISION 14 |  | T | CONSTRUCTION | 13001000 | FY 2029: 130000; FY 2030: 5909000; FY 2031: 5263000; FY 2032: 1699000
R-5839BA | HIGHWAY | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | DIVISION 14 |  | T | RIGHT-OF-WAY | 100000 | FY 2027: 100000
R-5839BB | HIGHWAY | NC 28 | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 46332000 | [11 empty] | 46332000
R-5839BB | HIGHWAY | NC 28 | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 80000 | [11 empty] | 80000
R-5839BB | HIGHWAY | NC 28 | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 37000000 | [11 empty] | 37000000
R-5839C | HIGHWAY | NC 28 | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 90000 | [11 empty] | 90000
R-5839C | HIGHWAY | NC 28 | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 20000 | [11 empty] | 20000
R-5839C | HIGHWAY | NC 28 | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 58300000 | [11 empty] | 58300000
R-5839D | HIGHWAY | NC 28 | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 730000 | [11 empty] | 730000
R-5839D | HIGHWAY | NC 28 | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 80000 | [11 empty] | 80000
R-5839D | HIGHWAY | NC 28 | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 57500000 | [11 empty] | 57500000
R-5839E | HIGHWAY | NC 28 | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 60000 | [11 empty] | 60000
R-5839E | HIGHWAY | NC 28 | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 100000 | [11 empty] | 100000
R-5839E | HIGHWAY | NC 28 | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 22000000 | [11 empty] | 22000000
R-5840 | HIGHWAY | NC 9 | US 74 TO NC 108. ADD PAVED SHOULDERS. | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | T | UTILITIES | 1400000
R-5840 | HIGHWAY | NC 9 | US 74 TO NC 108. ADD PAVED SHOULDERS. | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | T | CONSTRUCTION | 8600000 | FY 2025: 2901000; FY 2026: 4461000; FY 2027: 1238000
R-5840 | HIGHWAY | NC 9 | US 74 TO NC 108. ADD PAVED SHOULDERS. | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  |  |  | 1015000
R-5840 | HIGHWAY | NC 9 | US 74 TO NC 108. ADD PAVED SHOULDERS. | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | T | RIGHT-OF-WAY | 2200000 | FY 2023: 2100000
R-5841 | HIGHWAY | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO APPROXIMATELY 1 MILE NORTH OF SR 1157 (PINE CREEK ROAD). WIDEN PAVEMENT TO 24 FEET WITH 5 FEET PAVED SHOULDERS. | 14 | Southwestern RPO | [5 empty] | 2555000
R-5841A | HIGHWAY | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2599000 | [11 empty] | 2599000
R-5841A | HIGHWAY | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 200000 | [11 empty] | 200000
R-5841A | HIGHWAY | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM. | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 17899000 | [11 empty] | 17899000
R-5841B | HIGHWAY | NC 107 | 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM TO APPROXIMATELY 1 MILE NORTH OF SR 1157 (PINE CREEK ROAD). | 14 | Southwestern RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 102800000 | [11 empty] | 102800000
R-5841B | HIGHWAY | NC 107 | 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM TO APPROXIMATELY 1 MILE NORTH OF SR 1157 (PINE CREEK ROAD). | 14 | Southwestern RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 6400000 | [11 empty] | 6400000
R-5841B | HIGHWAY | NC 107 | 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM TO APPROXIMATELY 1 MILE NORTH OF SR 1157 (PINE CREEK ROAD). | 14 | Southwestern RPO |  | NOT FUNDED |  | T | UTILITIES | 300000 | [11 empty] | 300000
R-5843 | HIGHWAY | SR 1321 (BRYSON WALK), SR 1336 (DEPOT STREET) | SR 1323 (SLOPE STREET) TO SR 1336 (DEEP CREEK ROAD). IMPROVE INTERSECTIONS. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  |  |  | 700000
R-5843 | HIGHWAY | SR 1321 (BRYSON WALK), SR 1336 (DEPOT STREET) | SR 1323 (SLOPE STREET) TO SR 1336 (DEEP CREEK ROAD). IMPROVE INTERSECTIONS. | 14 | Southwestern RPO | UNDER CONSTRUCTION. | DIVISION 14 |  | T | CONSTRUCTION | 3629000 | FY 2023: 2079000
R-5847 | HIGHWAY | US 64 | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | 14 | Southwestern RPO | WORK FOR B-5911 INCLUDED. | NOT FUNDED |  |  |  | 1850000
R-5847 | HIGHWAY | US 64 | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | 14 | Southwestern RPO | WORK FOR B-5911 INCLUDED. | NOT FUNDED |  | T | RIGHT-OF-WAY | 32000000 | [11 empty] | 32000000
R-5847 | HIGHWAY | US 64 | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | 14 | Southwestern RPO | WORK FOR B-5911 INCLUDED. | NOT FUNDED |  | T | UTILITIES | 6000000 | [11 empty] | 6000000
R-5847 | HIGHWAY | US 64 | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | 14 | Southwestern RPO | WORK FOR B-5911 INCLUDED. | NOT FUNDED |  | T | CONSTRUCTION | 95901000 | [11 empty] | 95901000
R-5849 | HIGHWAY | NEW ROUTE | CONSTRUCT IMPROVEMENTS TO SR 1313 (WASHBURN SWITCH ROAD) AND A NEW 3-LANE ROAD OFF SR 1313 (WASHBURN SWITCH ROAD) FOR ACCESS TO NEW INDUSTRIAL SITES. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | DIVISION 12 |  |  |  | 1975000
R-5850 | HIGHWAY | NC 53 | US 117 BYPASS TO SR 1509 (STAG PARK ROAD). WIDEN TO MULTI-LANES. | 3 | Cape Fear RPO |  | NOT FUNDED |  | BGLT5 | UTILITIES | 1908000 | [11 empty] | 1908000
R-5850 | HIGHWAY | NC 53 | US 117 BYPASS TO SR 1509 (STAG PARK ROAD). WIDEN TO MULTI-LANES. | 3 | Cape Fear RPO |  | NOT FUNDED |  | BGLT5 | CONSTRUCTION | 6300000 | [11 empty] | 6300000
R-5850 | HIGHWAY | NC 53 | US 117 BYPASS TO SR 1509 (STAG PARK ROAD). WIDEN TO MULTI-LANES. | 3 | Cape Fear RPO |  | NOT FUNDED |  |  |  | 500000
R-5850 | HIGHWAY | NC 53 | US 117 BYPASS TO SR 1509 (STAG PARK ROAD). WIDEN TO MULTI-LANES. | 3 | Cape Fear RPO |  | NOT FUNDED |  | BGLT5 | RIGHT-OF-WAY | 5900000 | [11 empty] | 5900000
R-5851 | HIGHWAY | US 17 | NC 904. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 3 | Grand Strand Area Transportation Study |  | NOT FUNDED |  |  |  | 500000
R-5851 | HIGHWAY | US 17 | NC 904. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 3 | Grand Strand Area Transportation Study |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 850000 | [11 empty] | 850000
R-5851 | HIGHWAY | US 17 | NC 904. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 3 | Grand Strand Area Transportation Study |  | NOT FUNDED |  | T | UTILITIES | 115000 | [11 empty] | 115000
R-5851 | HIGHWAY | US 17 | NC 904. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 3 | Grand Strand Area Transportation Study |  | NOT FUNDED |  | T | CONSTRUCTION | 4950000 | [11 empty] | 4950000
R-5853 | HIGHWAY | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | 2, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | DIVISION 2, 4 |  | T | RIGHT-OF-WAY | 2488000 | FY 2025: 25000; FY 2026: 1169000; FY 2027: 796000; FY 2028: 249000; FY 2029: 249000
R-5853 | HIGHWAY | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | 2, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | DIVISION 2, 4 |  | T | UTILITIES | 3040000 | FY 2025: 1520000; FY 2026: 1520000
R-5853 | HIGHWAY | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | 2, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | DIVISION 2, 4 |  |  |  | 10000
R-5853 | HIGHWAY | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | 2, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | DIVISION 2, 4 |  | T | CONSTRUCTION | 8800000 | FY 2027: 897000; FY 2028: 5831000; FY 2029: 2072000
R-5854 | HIGHWAY | SR 1410 (FARMINGTON ROAD) | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 400000
R-5854 | HIGHWAY | SR 1410 (FARMINGTON ROAD) | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | RIGHT-OF-WAY | 100000 | FY 2023: 100000
R-5854 | HIGHWAY | SR 1410 (FARMINGTON ROAD) | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | UTILITIES | 300000 | FY 2023: 300000
R-5854 | HIGHWAY | SR 1410 (FARMINGTON ROAD) | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | CONSTRUCTION | 1900000 | FY 2025: 1900000
R-5857 | HIGHWAY | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 3 | Grand Strand Area Transportation Study | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 770000 | FY 2023: 770000
R-5857 | HIGHWAY | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 3 | Grand Strand Area Transportation Study | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | UTILITIES | 330000 | FY 2023: 330000
R-5857 | HIGHWAY | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 3 | Grand Strand Area Transportation Study | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  |  |  | 500000
R-5857 | HIGHWAY | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 3 | Grand Strand Area Transportation Study | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 21600000 | FY 2026: 216000; FY 2027: 9605000; FY 2028: 8552000; FY 2029: 3227000
R-5858 | HIGHWAY | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | 2 | Down East RPO | RIGHT OF WAY IN PROGRESS. | STATEWIDE MOBILITY |  |  |  | 700000
R-5858 | HIGHWAY | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | 2 | Down East RPO | RIGHT OF WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 750000 | FY 2023: 750000
R-5858 | HIGHWAY | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | 2 | Down East RPO | RIGHT OF WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 6000000 | FY 2026: 2778000; FY 2027: 3222000
R-5860 | HIGHWAY | US 52 | PROPOSED MISENHEIMER BYPASS TO GRANITE QUARRY BYPASS. | 9, 10 | Cabarrus-Rowan MPO |  | DIVISION 9, 10 |  |  |  | 10000
R-5860A | HIGHWAY | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. UPGRADE ROADWAY AND ACCESS MANAGEMENT. | 9, 10 | Cabarrus-Rowan MPO |  | DIVISION 9, 10 |  | T | UTILITIES | 846000 | FY 2027: 846000
R-5860A | HIGHWAY | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. UPGRADE ROADWAY AND ACCESS MANAGEMENT. | 9, 10 | Cabarrus-Rowan MPO |  | DIVISION 9, 10 |  | T | CONSTRUCTION | 39320000 | FY 2029: 6106000; FY 2030: 15474000; FY 2031: 11626000; FY 2032: 6114000
R-5860A | HIGHWAY | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. UPGRADE ROADWAY AND ACCESS MANAGEMENT. | 9, 10 | Cabarrus-Rowan MPO |  | DIVISION 9, 10 |  | T | RIGHT-OF-WAY | 7048000 | FY 2027: 564000; FY 2028: 3383000; FY 2029: 1691000; FY 2030: 705000; FY 2031: 705000
R-5860B | HIGHWAY | US 52 | PROPOSED ROCKWELL BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | 9 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | UTILITIES | 500000 | [11 empty] | 500000
R-5860B | HIGHWAY | US 52 | PROPOSED ROCKWELL BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | 9 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 22300000 | [11 empty] | 22300000
R-5860B | HIGHWAY | US 52 | PROPOSED ROCKWELL BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | 9 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 8200000 | [11 empty] | 8200000
R-5860C | HIGHWAY | US 52 | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | 9 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5500000 | [11 empty] | 5500000
R-5860C | HIGHWAY | US 52 | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | 9 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | UTILITIES | 900000 | [11 empty] | 900000
R-5860C | HIGHWAY | US 52 | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT FACILITY ON NEW LOCATION. | 9 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 36500000 | [11 empty] | 36500000
R-5861 | HIGHWAY | US 19/129 | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | BGLT5 | CONSTRUCTION | 54900000 | FY 2024: 7495000; FY 2025: 18980000; FY 2026: 15126000; FY 2027: 10476000; FY 2028: 2823000
R-5861 | HIGHWAY | US 19/129 | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | T | RIGHT-OF-WAY | 11400000 | FY 2023: 5700000
R-5861 | HIGHWAY | US 19/129 | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  |  |  | 2700000
R-5861 | HIGHWAY | US 19/129 | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | T | UTILITIES | 1100000
R-5863 | HIGHWAY | US 64 BUSINESS | US 64 TO SR 1307 (MAIN STREET). UPGRADE ROADWAY. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  |  |  | 200000
R-5863 | HIGHWAY | US 64 BUSINESS | US 64 TO SR 1307 (MAIN STREET). UPGRADE ROADWAY. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | T | RIGHT-OF-WAY | 4200000
R-5863 | HIGHWAY | US 64 BUSINESS | US 64 TO SR 1307 (MAIN STREET). UPGRADE ROADWAY. | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | T | CONSTRUCTION | 6100000 | FY 2023: 61000; FY 2024: 3957000; FY 2025: 2082000
R-5865 | HIGHWAY | US 276 | US 64 TO AVERY CREEK TRAIL HEAD. WIDEN TO 3-LANES WITH BICYCLE LANES. NC FLAP DOT 276(1). | 14 | Land-of-Sky RPO | STATE MATCHING FUNDS FROM DIVISION 14 MAINTENANCE FUNDING; FLAP PROJECT NC 35. | EXEMPT |  | S(M) | CONSTRUCTION | 628000 | [11 empty] | 628000
R-5865 | HIGHWAY | US 276 | US 64 TO AVERY CREEK TRAIL HEAD. WIDEN TO 3-LANES WITH BICYCLE LANES. NC FLAP DOT 276(1). | 14 | Land-of-Sky RPO | STATE MATCHING FUNDS FROM DIVISION 14 MAINTENANCE FUNDING; FLAP PROJECT NC 35. | EXEMPT |  |  |  | 250000
R-5865 | HIGHWAY | US 276 | US 64 TO AVERY CREEK TRAIL HEAD. WIDEN TO 3-LANES WITH BICYCLE LANES. NC FLAP DOT 276(1). | 14 | Land-of-Sky RPO | STATE MATCHING FUNDS FROM DIVISION 14 MAINTENANCE FUNDING; FLAP PROJECT NC 35. | EXEMPT |  | FLAP | CONSTRUCTION | 2519000 | [11 empty] | 2519000
R-5866 | HIGHWAY | NC 87 | IMPROVE ROADWAY FOR SMITHFIELD FOODS PROCESSING CENTER. | 6 | Mid-Carolina RPO | COMPLETED. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SMITHFIELD FOODS PROCESSING. | REGION C |  |  |  | 2945000
R-5866 | HIGHWAY | NC 87 | IMPROVE ROADWAY FOR SMITHFIELD FOODS PROCESSING CENTER. | 6 | Mid-Carolina RPO | COMPLETED. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SMITHFIELD FOODS PROCESSING. | REGION C |  | T | CONSTRUCTION | 1042000
R-5868 | HIGHWAY | NEW ROUTE | SR 1252 (DUNBAR ROAD) TO SR 1225 (KINGSBORO ROAD). CONSTRUCT TWO LANE ROAD ON NEW LOCATION AND IMPROVEMENTS TO SR 1225 TO SERVE KINGSBORO MEGASITE. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. THIS IN AN ECONOMIC DEVELOPMENT PROJECT FOR TRIANGLE TYRE. | DIVISION 4 |  |  |  | 23910000
R-5869 | HIGHWAY | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY AND CONVERT INTERSECTIONS TO INTERCHANGES. | 1 | Albemarle RPO | [5 empty] | 10000
R-5869A | HIGHWAY | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | RIGHT-OF-WAY | 6000000 | FY 2028: 60000; FY 2029: 2226000; FY 2030: 2514000; FY 2031: 600000; FY 2032: 600000
R-5869A | HIGHWAY | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | UTILITIES | 900000 | FY 2028: 450000; FY 2029: 450000
R-5869A | HIGHWAY | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | CONSTRUCTION | 30000000 | FY 2031: 300000; FY 2032: 12767000; FY 2033: 10210000 | 6723000
R-5869B | HIGHWAY | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | RIGHT-OF-WAY | 4200000 | FY 2028: 480000; FY 2029: 1920000; FY 2030: 960000; FY 2031: 420000; FY 2032: 420000
R-5869B | HIGHWAY | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | UTILITIES | 2000000 | FY 2028: 1000000; FY 2029: 1000000
R-5869B | HIGHWAY | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | CONSTRUCTION | 30000000 | FY 2032: 5715000; FY 2033: 13509000 | 10776000
R-5869C | HIGHWAY | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. | 1 | Albemarle RPO | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 3500000 | [11 empty] | 3500000
R-5869C | HIGHWAY | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. | 1 | Albemarle RPO | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | UTILITIES | 1000000 | [11 empty] | 1000000
R-5869C | HIGHWAY | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. | 1 | Albemarle RPO | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | CONSTRUCTION | 135000000 | [11 empty] | 135000000
R-5870 | HIGHWAY | ALEXANDER COUNTY | CONSTRUCT ACCESS ROAD INTO ALEXANDER INDUSTRIAL PARK. | 12 | Greater Hickory MPO | COMPLETE - ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING. | EXEMPT |  | T | CONSTRUCTION | 500000
R-5870 | HIGHWAY | ALEXANDER COUNTY | CONSTRUCT ACCESS ROAD INTO ALEXANDER INDUSTRIAL PARK. | 12 | Greater Hickory MPO | COMPLETE - ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING. | EXEMPT |  |  |  | 325000
R-5870 | HIGHWAY | ALEXANDER COUNTY | CONSTRUCT ACCESS ROAD INTO ALEXANDER INDUSTRIAL PARK. | 12 | Greater Hickory MPO | COMPLETE - ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING. | EXEMPT |  | ADHSL | CONSTRUCTION | 1175000
R-5871 | HIGHWAY | US 74 | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Rocky River RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 10800000
R-5871 | HIGHWAY | US 74 | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Rocky River RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3900000
R-5871 | HIGHWAY | US 74 | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Rocky River RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1000000
R-5871 | HIGHWAY | US 74 | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Rocky River RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 10400000
R-5872 | HIGHWAY | US 421 | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | 11 | High Country RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 3100000
R-5872 | HIGHWAY | US 421 | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | 11 | High Country RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
R-5872 | HIGHWAY | US 421 | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | 11 | High Country RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 5000000
R-5872 | HIGHWAY | US 421 | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | 11 | High Country RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 200000
R-5873 | HIGHWAY | US 74 | NC 108 INTERCHANGE. IMPROVE INTERCHANGE. | 14 | Foothills RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 3200000
R-5873 | HIGHWAY | US 74 | NC 108 INTERCHANGE. IMPROVE INTERCHANGE. | 14 | Foothills RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
R-5873 | HIGHWAY | US 74 | NC 108 INTERCHANGE. IMPROVE INTERCHANGE. | 14 | Foothills RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 200000
R-5874 | HIGHWAY | US 321 | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | 11 | High Country RPO |  | NOT FUNDED |  |  |  | 10000
R-5874 | HIGHWAY | US 321 | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | 11 | High Country RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 5700000 | [11 empty] | 5700000
R-5874 | HIGHWAY | US 321 | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | 11 | High Country RPO |  | NOT FUNDED |  | NHP | UTILITIES | 1000000 | [11 empty] | 1000000
R-5874 | HIGHWAY | US 321 | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | 11 | High Country RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 7799000 | [11 empty] | 7799000
R-5876 | HIGHWAY | I-74 (CAROLINA BAYS PARKWAY EXTENSION) | FROM SC STATE LINE TO US 17 AT NC 130. CONSTRUCT FREEWAY ON NEW LOCATION. | 3 | Cape Fear RPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | O | CONSTRUCTION | 232800000 | [11 empty] | 232800000
R-5876 | HIGHWAY | I-74 (CAROLINA BAYS PARKWAY EXTENSION) | FROM SC STATE LINE TO US 17 AT NC 130. CONSTRUCT FREEWAY ON NEW LOCATION. | 3 | Cape Fear RPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | O | RIGHT-OF-WAY | 128600000 | [11 empty] | 128600000
R-5876 | HIGHWAY | I-74 (CAROLINA BAYS PARKWAY EXTENSION) | FROM SC STATE LINE TO US 17 AT NC 130. CONSTRUCT FREEWAY ON NEW LOCATION. | 3 | Cape Fear RPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | O | UTILITIES | 5300000 | [11 empty] | 5300000
R-5877 | HIGHWAY | US 17 | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | 3 | Cape Fear RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 11900000 | [11 empty] | 11900000
R-5877 | HIGHWAY | US 17 | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | 3 | Cape Fear RPO |  | NOT FUNDED |  | NHP | UTILITIES | 2100000 | [11 empty] | 2100000
R-5877 | HIGHWAY | US 17 | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | 3 | Cape Fear RPO |  | NOT FUNDED |  |  |  | 260000
R-5877 | HIGHWAY | US 17 | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | 3 | Cape Fear RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 6000000 | [11 empty] | 6000000
R-5878 | HIGHWAY | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 10 | Rocky River RPO | [5 empty] | 10000
R-5878A | HIGHWAY | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 10 | Rocky River RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 104300000 | [11 empty] | 104300000
R-5878A | HIGHWAY | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 10 | Rocky River RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 4000000 | [11 empty] | 4000000
R-5878A | HIGHWAY | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 10 | Rocky River RPO |  | NOT FUNDED |  | NHP | UTILITIES | 600000 | [11 empty] | 600000
R-5878B | HIGHWAY | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 10 | Rocky River RPO |  | REGION E |  | T | CONSTRUCTION | 134100000 | FY 2030: 14932000; FY 2031: 43633000; FY 2032: 35810000; FY 2033: 23566000 | 16159000
R-5878B | HIGHWAY | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 10 | Rocky River RPO |  | REGION E |  | T | UTILITIES | 3200000 | FY 2028: 1600000; FY 2029: 1600000
R-5878B | HIGHWAY | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 10 | Rocky River RPO |  | REGION E |  | T | RIGHT-OF-WAY | 32400000 | FY 2028: 2469000; FY 2029: 14811000; FY 2030: 8640000; FY 2031: 3240000; FY 2032: 3240000
R-5879 | HIGHWAY | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | 1 | Mid-East RPO |  | REGION A |  |  |  | 10000
R-5879 | HIGHWAY | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | 1 | Mid-East RPO |  | REGION A |  | NHP | RIGHT-OF-WAY | 100000 | FY 2025: 100000
R-5879 | HIGHWAY | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | 1 | Mid-East RPO |  | REGION A |  | NHP | UTILITIES | 200000 | FY 2025: 200000
R-5879 | HIGHWAY | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | 1 | Mid-East RPO |  | REGION A |  | NHP | CONSTRUCTION | 2350000 | FY 2027: 1777000; FY 2028: 573000
R-5880 | HIGHWAY | US 221 | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 500000 | [11 empty] | 500000
R-5880 | HIGHWAY | US 221 | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | UTILITIES | 400000 | [11 empty] | 400000
R-5880 | HIGHWAY | US 221 | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  |  |  | 10000
R-5880 | HIGHWAY | US 221 | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 2500000 | [11 empty] | 2500000
R-5881 | HIGHWAY | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION. | 14 | Southwestern RPO |  | REGION G |  | T | CONSTRUCTION | 6700000 | FY 2030: 906000; FY 2031: 3964000; FY 2032: 1830000
R-5881 | HIGHWAY | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION. | 14 | Southwestern RPO |  | REGION G |  |  |  | 10000
R-5881 | HIGHWAY | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION. | 14 | Southwestern RPO |  | REGION G |  | T | RIGHT-OF-WAY | 14900000 | FY 2028: 3725000; FY 2029: 7450000; FY 2030: 3725000
R-5881 | HIGHWAY | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION. | 14 | Southwestern RPO |  | REGION G |  | T | UTILITIES | 800000 | FY 2028: 400000; FY 2029: 400000
R-5882 | HIGHWAY | US 64 (SOUTH BROAD STREET) | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | 14 | Land-of-Sky RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 1900000 | [11 empty] | 1900000
R-5882 | HIGHWAY | US 64 (SOUTH BROAD STREET) | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | 14 | Land-of-Sky RPO |  | NOT FUNDED |  | T | UTILITIES | 1200000 | [11 empty] | 1200000
R-5882 | HIGHWAY | US 64 (SOUTH BROAD STREET) | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | 14 | Land-of-Sky RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 4400000 | [11 empty] | 4400000
R-5882 | HIGHWAY | US 64 (SOUTH BROAD STREET) | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | 14 | Land-of-Sky RPO |  | NOT FUNDED |  |  |  | 10000
R-5884 | HIGHWAY | NC 58 (EMERALD DRIVE) | LOON STREET. INSTALL ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  |  |  | 10000
R-5884 | HIGHWAY | NC 58 (EMERALD DRIVE) | LOON STREET. INSTALL ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 300000 | [11 empty] | 300000
R-5884 | HIGHWAY | NC 58 (EMERALD DRIVE) | LOON STREET. INSTALL ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 300000 | [11 empty] | 300000
R-5884 | HIGHWAY | NC 58 (EMERALD DRIVE) | LOON STREET. INSTALL ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 1400000 | [11 empty] | 1400000
R-5885 | HIGHWAY | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  |  |  | 1110000
R-5885 | HIGHWAY | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 15304000 | [11 empty] | 15304000
R-5885 | HIGHWAY | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 802000 | [11 empty] | 802000
R-5885 | HIGHWAY | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 28699000 | [11 empty] | 28699000
R-5885A | HIGHWAY | NC 24 (WEST CORBETT AVENUE) | REPLACE CULVERT EAST OF WEST SHORE DRIVE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | NHP | RIGHT-OF-WAY | 115000 | FY 2025: 115000
R-5885A | HIGHWAY | NC 24 (WEST CORBETT AVENUE) | REPLACE CULVERT EAST OF WEST SHORE DRIVE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | NHP | UTILITIES | 84000 | FY 2025: 84000
R-5885A | HIGHWAY | NC 24 (WEST CORBETT AVENUE) | REPLACE CULVERT EAST OF WEST SHORE DRIVE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | NHP | CONSTRUCTION | 1500000 | FY 2027: 357000; FY 2028: 1143000
R-5886 | HIGHWAY | NC 58 (EMERALD DRIVE) | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 300000 | [11 empty] | 300000
R-5886 | HIGHWAY | NC 58 (EMERALD DRIVE) | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 1600000 | [11 empty] | 1600000
R-5886 | HIGHWAY | NC 58 (EMERALD DRIVE) | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  |  |  | 10000
R-5886 | HIGHWAY | NC 58 (EMERALD DRIVE) | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 1700000 | [11 empty] | 1700000
R-5887 | HIGHWAY | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5, 8 | Triangle Area RPO, Capital Area MPO |  | REGION C, E |  |  |  | 10000
R-5887 | HIGHWAY | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5, 8 | Triangle Area RPO, Capital Area MPO |  | REGION C, E |  | NHP | RIGHT-OF-WAY | 3299000 | FY 2027: 918000; FY 2028: 1377000; FY 2029: 344000; FY 2030: 330000; FY 2031: 330000
R-5887 | HIGHWAY | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5, 8 | Triangle Area RPO, Capital Area MPO |  | REGION C, E |  | NHP | UTILITIES | 1500000 | FY 2027: 750000; FY 2028: 750000
R-5887 | HIGHWAY | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5, 8 | Triangle Area RPO, Capital Area MPO |  | REGION C, E |  | NHP | CONSTRUCTION | 31000000 | FY 2029: 9683000; FY 2030: 12355000; FY 2031: 8053000; FY 2032: 909000
R-5888 | HIGHWAY | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | 6 | Lumber River RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
R-5888 | HIGHWAY | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | 6 | Lumber River RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 900000
R-5888 | HIGHWAY | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | 6 | Lumber River RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
R-5888 | HIGHWAY | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | 6 | Lumber River RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5800000
R-5889 | HIGHWAY | US 29 (FUTURE I-785) | NORTH OF I-785 IN GREENSBORO TO US 158 / NC 14 IN REIDSVILLE. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | REGION D |  |  |  | 10000
R-5889A | HIGHWAY | US 29 (FUTURE I-785) | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 7 | Greensboro Urban Area MPO |  | REGION D |  | T | CONSTRUCTION | 69700000 | FY 2031: 6970000; FY 2032: 10455000; FY 2033: 16728000 | 35547000
R-5889A | HIGHWAY | US 29 (FUTURE I-785) | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 7 | Greensboro Urban Area MPO |  | REGION D |  | T | RIGHT-OF-WAY | 17066000 | FY 2028: 4267000; FY 2029: 8532000; FY 2030: 4267000
R-5889A | HIGHWAY | US 29 (FUTURE I-785) | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 7 | Greensboro Urban Area MPO |  | REGION D |  | T | UTILITIES | 1876000 | FY 2028: 938000; FY 2029: 938000
R-5889B | HIGHWAY | US 29 (FUTURE I-785) | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE TO INTERSTATE STANDARDS. | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 116450000
R-5889B | HIGHWAY | US 29 (FUTURE I-785) | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE TO INTERSTATE STANDARDS. | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 5430000
R-5889B | HIGHWAY | US 29 (FUTURE I-785) | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE TO INTERSTATE STANDARDS. | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9364000
R-5890 | HIGHWAY | US 401 (NORTH MAIN STREET) | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | 6 | Mid-Carolina RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
R-5890 | HIGHWAY | US 401 (NORTH MAIN STREET) | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | 6 | Mid-Carolina RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 100000
R-5890 | HIGHWAY | US 401 (NORTH MAIN STREET) | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | 6 | Mid-Carolina RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 200000
R-5890 | HIGHWAY | US 401 (NORTH MAIN STREET) | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | 6 | Mid-Carolina RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4500000
R-5891 | HIGHWAY | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 8 | Triangle Area RPO |  | REGION E |  | T | RIGHT-OF-WAY | 1900000 | FY 2028: 152000; FY 2029: 912000; FY 2030: 456000; FY 2031: 190000; FY 2032: 190000
R-5891 | HIGHWAY | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 8 | Triangle Area RPO |  | REGION E |  | T | UTILITIES | 1180000 | FY 2028: 590000; FY 2029: 590000
R-5891 | HIGHWAY | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 8 | Triangle Area RPO |  | REGION E |  |  |  | 10000
R-5891 | HIGHWAY | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 20600000 | FY 2031: 3502000; FY 2032: 8240000; FY 2033: 6180000 | 2678000
R-5892 | HIGHWAY | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | 8 | Triangle Area RPO |  | REGION E |  |  |  | 10000
R-5892 | HIGHWAY | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | 8 | Triangle Area RPO |  | REGION E |  | T | RIGHT-OF-WAY | 6300000 | FY 2028: 916000; FY 2029: 2749000; FY 2030: 1375000; FY 2031: 630000; FY 2032: 630000
R-5892 | HIGHWAY | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | 8 | Triangle Area RPO |  | REGION E |  | T | UTILITIES | 1892000 | FY 2028: 946000; FY 2029: 946000
R-5892 | HIGHWAY | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 22000000 | FY 2030: 4477000; FY 2031: 10580000; FY 2032: 6943000
R-5893 | HIGHWAY | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | 5 | Kerr-Tar RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5900000 | [11 empty] | 5900000
R-5893 | HIGHWAY | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | 5 | Kerr-Tar RPO |  | NOT FUNDED |  | T | UTILITIES | 9000000 | [11 empty] | 9000000
R-5893 | HIGHWAY | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | 5 | Kerr-Tar RPO |  | NOT FUNDED |  |  |  | 10000
R-5893 | HIGHWAY | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | 5 | Kerr-Tar RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 21899000 | [11 empty] | 21899000
R-5894 | HIGHWAY | US 601 (SOUTH STATE STREET) | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | 11 | Northwest Piedmont RPO | COORDINATE WITH U-5809. | NOT FUNDED |  |  |  | 10000
R-5894 | HIGHWAY | US 601 (SOUTH STATE STREET) | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | 11 | Northwest Piedmont RPO | COORDINATE WITH U-5809. | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 750000 | [11 empty] | 750000
R-5894 | HIGHWAY | US 601 (SOUTH STATE STREET) | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | 11 | Northwest Piedmont RPO | COORDINATE WITH U-5809. | NOT FUNDED |  | NHP | UTILITIES | 100000 | [11 empty] | 100000
R-5894 | HIGHWAY | US 601 (SOUTH STATE STREET) | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | 11 | Northwest Piedmont RPO | COORDINATE WITH U-5809. | NOT FUNDED |  | NHP | CONSTRUCTION | 4500000 | [11 empty] | 4500000
R-5895 | HIGHWAY | NC 103 (EAST PINE STREET) | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | 11 | Northwest Piedmont RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2700000 | [11 empty] | 2700000
R-5895 | HIGHWAY | NC 103 (EAST PINE STREET) | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | 11 | Northwest Piedmont RPO |  | NOT FUNDED |  | T | UTILITIES | 390000 | [11 empty] | 390000
R-5895 | HIGHWAY | NC 103 (EAST PINE STREET) | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | 11 | Northwest Piedmont RPO |  | NOT FUNDED |  |  |  | 10000
R-5895 | HIGHWAY | NC 103 (EAST PINE STREET) | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | 11 | Northwest Piedmont RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 1600000 | [11 empty] | 1600000
R-5896 | HIGHWAY | US 601 | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | 11 | Northwest Piedmont RPO |  | NOT FUNDED |  |  |  | 10000
R-5896 | HIGHWAY | US 601 | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | 11 | Northwest Piedmont RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2000000 | [11 empty] | 2000000
R-5896 | HIGHWAY | US 601 | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | 11 | Northwest Piedmont RPO |  | NOT FUNDED |  | T | UTILITIES | 300000 | [11 empty] | 300000
R-5896 | HIGHWAY | US 601 | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | 11 | Northwest Piedmont RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 2100000 | [11 empty] | 2100000
R-5897 | HIGHWAY | NC 32 | BRICK KILN ROAD. IMPROVE INTERSECTION. | 2 | Mid-East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 454000 | [11 empty] | 454000
R-5897 | HIGHWAY | NC 32 | BRICK KILN ROAD. IMPROVE INTERSECTION. | 2 | Mid-East RPO |  | NOT FUNDED |  | T | UTILITIES | 200000 | [11 empty] | 200000
R-5897 | HIGHWAY | NC 32 | BRICK KILN ROAD. IMPROVE INTERSECTION. | 2 | Mid-East RPO |  | NOT FUNDED |  |  |  | 10000
R-5897 | HIGHWAY | NC 32 | BRICK KILN ROAD. IMPROVE INTERSECTION. | 2 | Mid-East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 1400000 | [11 empty] | 1400000
R-5898 | HIGHWAY | NC 58 (KINGOLD BOULEVARD) | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  |  |  | 10000
R-5898 | HIGHWAY | NC 58 (KINGOLD BOULEVARD) | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 200000 | [11 empty] | 200000
R-5898 | HIGHWAY | NC 58 (KINGOLD BOULEVARD) | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | UTILITIES | 200000 | [11 empty] | 200000
R-5898 | HIGHWAY | NC 58 (KINGOLD BOULEVARD) | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 7500000 | [11 empty] | 7500000
R-5899 | HIGHWAY | NC 210 | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | 3 | Cape Fear RPO |  | DIVISION 3 |  | T | RIGHT-OF-WAY | 1044000 | FY 2025: 261000; FY 2026: 522000; FY 2027: 261000
R-5899 | HIGHWAY | NC 210 | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | 3 | Cape Fear RPO |  | DIVISION 3 |  | T | UTILITIES | 117000 | FY 2025: 117000
R-5899 | HIGHWAY | NC 210 | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | 3 | Cape Fear RPO |  | DIVISION 3 |  |  |  | 260000
R-5899 | HIGHWAY | NC 210 | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | 3 | Cape Fear RPO |  | DIVISION 3 |  | T | CONSTRUCTION | 2600000 | FY 2027: 1160000; FY 2028: 1440000
R-5900 | HIGHWAY | NC 50/NC 210 | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | 3 | Cape Fear RPO |  | DIVISION 3 |  |  |  | 260000
R-5900 | HIGHWAY | NC 50/NC 210 | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | 3 | Cape Fear RPO |  | DIVISION 3 |  | T | RIGHT-OF-WAY | 5000000 | FY 2025: 1250000; FY 2026: 2500000; FY 2027: 1250000
R-5900 | HIGHWAY | NC 50/NC 210 | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | 3 | Cape Fear RPO |  | DIVISION 3 |  | T | UTILITIES | 800000 | FY 2025: 800000
R-5900 | HIGHWAY | NC 50/NC 210 | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | 3 | Cape Fear RPO |  | DIVISION 3 |  | T | CONSTRUCTION | 1300000 | FY 2028: 179000; FY 2029: 1121000
R-5901 | HIGHWAY | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | 11 | Northwest Piedmont RPO |  | REGION F |  | BGLT5 | RIGHT-OF-WAY | 500000 | FY 2024: 500000
R-5901 | HIGHWAY | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | 11 | Northwest Piedmont RPO |  | REGION F |  | BGLT5 | UTILITIES | 100000 | FY 2024: 100000
R-5901 | HIGHWAY | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | 11 | Northwest Piedmont RPO |  | REGION F |  |  |  | 10000
R-5901 | HIGHWAY | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | 11 | Northwest Piedmont RPO |  | REGION F |  | BGLT5 | CONSTRUCTION | 5200000 | FY 2026: 5200000
R-5902 | HIGHWAY | NC 184 | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  |  |  | 10000
R-5902 | HIGHWAY | NC 184 | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 18200000 | [11 empty] | 18200000
R-5902 | HIGHWAY | NC 184 | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  | T | UTILITIES | 7900000 | [11 empty] | 7900000
R-5902 | HIGHWAY | NC 184 | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 64798000 | [11 empty] | 64798000
R-5903 | HIGHWAY | US 421 | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 30600000 | [11 empty] | 30600000
R-5903 | HIGHWAY | US 421 | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  | T | UTILITIES | 1500000 | [11 empty] | 1500000
R-5903 | HIGHWAY | US 421 | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  |  |  | 10000
R-5903 | HIGHWAY | US 421 | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | 11 | High Country RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 54902000 | [11 empty] | 54902000
R-5904 | HIGHWAY | NC 20 | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | 6 | Lumber River RPO |  | NOT FUNDED |  |  |  | 10000
R-5904 | HIGHWAY | NC 20 | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5400000 | [11 empty] | 5400000
R-5904 | HIGHWAY | NC 20 | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | UTILITIES | 3400000 | [11 empty] | 3400000
R-5904 | HIGHWAY | NC 20 | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 18800000 | [11 empty] | 18800000
R-5905 | HIGHWAY | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BG5200 | RIGHT-OF-WAY | 5899000 | FY 2025: 1452000; FY 2026: 2178000; FY 2027: 1089000; FY 2028: 590000; FY 2029: 590000
R-5905 | HIGHWAY | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BG5200 | UTILITIES | 5800000 | FY 2025: 2900000; FY 2026: 2900000
R-5905 | HIGHWAY | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BG5200 | CONSTRUCTION | 38501000 | FY 2027: 7048000; FY 2028: 14148000; FY 2029: 10937000; FY 2030: 6368000
R-5905 | HIGHWAY | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  |  |  | 10000
R-5906 | HIGHWAY | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | BUILD NC BOND FUNDING: $17M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | BGLT5 | CONSTRUCTION | 52299000 | FY 2031: 14526000; FY 2032: 17552000; FY 2033: 12993000 | 7228000
R-5906 | HIGHWAY | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | BUILD NC BOND FUNDING: $17M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | T | BUILD NC ROW | 21885000 | FY 2028: 1459000; FY 2029: 1459000; FY 2030: 1459000; FY 2031: 1459000; FY 2032: 1459000; FY 2033: 1459000 | 13131000
R-5906 | HIGHWAY | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | BUILD NC BOND FUNDING: $17M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | T | RIGHT-OF-WAY | 19000000 | FY 2028: 0; FY 2029: 455000; FY 2030: 10473000; FY 2031: 872000; FY 2032: 7200000
R-5906 | HIGHWAY | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | BUILD NC BOND FUNDING: $17M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | T | UTILITIES | 600000 | FY 2028: 600000
R-5907 | HIGHWAY | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGLT5 | RIGHT-OF-WAY | 3500000 | FY 2028: 800000; FY 2029: 1600000; FY 2030: 400000; FY 2031: 350000; FY 2032: 350000
R-5907 | HIGHWAY | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGLT5 | UTILITIES | 200000 | FY 2028: 200000
R-5907 | HIGHWAY | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  |  |  | 10000
R-5907 | HIGHWAY | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | 14 | Southwestern RPO |  | DIVISION 14 |  | BGLT5 | CONSTRUCTION | 19900000 | FY 2030: 6977000; FY 2031: 8099000; FY 2032: 4824000
R-5908 | HIGHWAY | US 19/US 74/ US 129 | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | 14 | Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
R-5908 | HIGHWAY | US 19/US 74/ US 129 | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | 14 | Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | RIGHT-OF-WAY | 2000000
R-5908 | HIGHWAY | US 19/US 74/ US 129 | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | 14 | Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | UTILITIES | 870000
R-5908 | HIGHWAY | US 19/US 74/ US 129 | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | 14 | Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 16001000
R-5909 | HIGHWAY | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BGLT5 | RIGHT-OF-WAY | 1900000 | FY 2026: 19000; FY 2027: 958000; FY 2028: 543000; FY 2029: 190000; FY 2030: 190000
R-5909 | HIGHWAY | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BGLT5 | UTILITIES | 5800000 | FY 2026: 2900000; FY 2027: 2900000
R-5909 | HIGHWAY | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  |  |  | 10000
R-5909 | HIGHWAY | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BGLT5 | CONSTRUCTION | 4300000 | FY 2028: 1996000; FY 2029: 2304000
R-5910 | HIGHWAY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | DIVISION 11 |  |  |  | 10000
R-5910 | HIGHWAY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | DIVISION 11 |  | BG5200 | RIGHT-OF-WAY | 400000
R-5910 | HIGHWAY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | DIVISION 11 |  | BG5200 | UTILITIES | 400000
R-5910 | HIGHWAY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | DIVISION 11 |  | BG5200 | CONSTRUCTION | 1800000 | FY 2023: 633000; FY 2024: 1167000
R-5911 | HIGHWAY | US 19E | NC 194 INTERSECTION. CONSTRUCT RIGHT TURN LANE FROM US 19E NORTHBOUND TO NC 194 EASTBOUND. | 11 | High Country RPO | UNDER CONSTRUCTION. | DIVISION 11 |  | BGLT5 | RIGHT-OF-WAY | 200000
R-5911 | HIGHWAY | US 19E | NC 194 INTERSECTION. CONSTRUCT RIGHT TURN LANE FROM US 19E NORTHBOUND TO NC 194 EASTBOUND. | 11 | High Country RPO | UNDER CONSTRUCTION. | DIVISION 11 |  | BGLT5 | CONSTRUCTION | 1100000 | FY 2023: 1100000
R-5911 | HIGHWAY | US 19E | NC 194 INTERSECTION. CONSTRUCT RIGHT TURN LANE FROM US 19E NORTHBOUND TO NC 194 EASTBOUND. | 11 | High Country RPO | UNDER CONSTRUCTION. | DIVISION 11 |  |  |  | 10000
R-5912 | HIGHWAY | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  | T | RIGHT-OF-WAY | 600000 | FY 2023: 600000
R-5912 | HIGHWAY | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  | T | UTILITIES | 100000 | FY 2023: 100000
R-5912 | HIGHWAY | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  | T | CONSTRUCTION | 1200000 | FY 2024: 228000; FY 2025: 972000
R-5912 | HIGHWAY | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  |  |  | 10000
R-5913 | HIGHWAY | NC 67, US 21 BUS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | 11 | Northwest Piedmont RPO | [5 empty] | 10000
R-5913A | HIGHWAY | NC 67, US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BG5200 | UTILITIES | 220000 | FY 2023: 220000
R-5913A | HIGHWAY | NC 67, US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BG5200 | CONSTRUCTION | 3300000 | FY 2025: 1463000; FY 2026: 1837000
R-5913A | HIGHWAY | NC 67, US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | 11 | Northwest Piedmont RPO |  | DIVISION 11 |  | BG5200 | RIGHT-OF-WAY | 1100000 | FY 2023: 11000; FY 2024: 539000; FY 2025: 330000; FY 2026: 110000; FY 2027: 110000
R-5913B | HIGHWAY | US 21 BUSINESS | BRIDGE #850021 OVER YADKIN RIVER. REHABILITATE STRUCTURE AND WIDEN SIDEWALKS. | 11 | Northwest Piedmont RPO |  | HIGHWAY FUND |  | HFB | CONSTRUCTION | 1400000 | FY 2025: 266000; FY 2026: 1134000
R-5914 | HIGHWAY | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $25.2M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | BGLT5 | RIGHT-OF-WAY | 9000000 | FY 2026: 3086000; FY 2027: 4114000; FY 2028: 900000; FY 2029: 900000
R-5914 | HIGHWAY | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $25.2M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | BGLT5 | UTILITIES | 1000000 | FY 2026: 500000; FY 2027: 500000
R-5914 | HIGHWAY | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $25.2M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | T | BUILD NC CON | 32430000 | FY 2028: 2162000; FY 2029: 2162000; FY 2030: 2162000; FY 2031: 2162000; FY 2032: 2162000; FY 2033: 2162000 | 19458000
R-5914 | HIGHWAY | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | 11 | Northwest Piedmont RPO | BUILD NC BONDS: $25.2M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 11 |  | T | CONSTRUCTION | 14700000 | FY 2028: 0; FY 2029: 1547000; FY 2030: 10093000; FY 2031: 3060000
R-5915A | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | 11 | High Country RPO |  | NOT FUNDED |  | NHP | UTILITIES | 400000 | [11 empty] | 400000
R-5915A | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | 11 | High Country RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 165600000 | [11 empty] | 165600000
R-5915A | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | 11 | High Country RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 81700000 | [11 empty] | 81700000
R-5915B | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | 11 | High Country RPO | BUILD NC BOND FUNDING: $6.2M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE) | DIVISION 11 |  | NHP | UTILITIES | 600000 | FY 2028: 300000; FY 2029: 300000
R-5915B | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | 11 | High Country RPO | BUILD NC BOND FUNDING: $6.2M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE) | DIVISION 11 |  | NHP | CONSTRUCTION | 246600000 | FY 2031: 11330000; FY 2032: 49320000; FY 2033: 59184000 | 126766000
R-5915B | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | 11 | High Country RPO | BUILD NC BOND FUNDING: $6.2M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (FY 2028 / YR 10 SALE) | DIVISION 11 |  | NHP | RIGHT-OF-WAY | 84800000 | FY 2028: 16960000; FY 2029: 33920000; FY 2030: 16960000; FY 2031: 8480000; FY 2032: 8480000
R-5915C | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | 11 | High Country RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 133800000 | [11 empty] | 133800000
R-5915C | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | 11 | High Country RPO |  | NOT FUNDED |  | NHP | UTILITIES | 400000 | [11 empty] | 400000
R-5915C | HIGHWAY | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | 11 | High Country RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 384600000 | [11 empty] | 384600000
R-5916 | HIGHWAY | NC 108 (CHARLOTTE STREET) | NC 108 (MAPLE STREET), SOUTH WASHINGTON STREET, MONFREDO STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | RIGHT-OF-WAY | 5200000 | [11 empty] | 5200000
R-5916 | HIGHWAY | NC 108 (CHARLOTTE STREET) | NC 108 (MAPLE STREET), SOUTH WASHINGTON STREET, MONFREDO STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | CONSTRUCTION | 1600000 | [11 empty] | 1600000
R-5916 | HIGHWAY | NC 108 (CHARLOTTE STREET) | NC 108 (MAPLE STREET), SOUTH WASHINGTON STREET, MONFREDO STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | UTILITIES | 300000 | [11 empty] | 300000
R-5917 | HIGHWAY | US 64 (EAST MOUNTAIN STREET) | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  |  |  | 10000
R-5917 | HIGHWAY | US 64 (EAST MOUNTAIN STREET) | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | RIGHT-OF-WAY | 1600000 | [11 empty] | 1600000
R-5917 | HIGHWAY | US 64 (EAST MOUNTAIN STREET) | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | UTILITIES | 300000 | [11 empty] | 300000
R-5917 | HIGHWAY | US 64 (EAST MOUNTAIN STREET) | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | CONSTRUCTION | 900000 | [11 empty] | 900000
R-5918 | HIGHWAY | US 221A (EAST MAIN STREET) | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | RIGHT-OF-WAY | 3100000 | [11 empty] | 3100000
R-5918 | HIGHWAY | US 221A (EAST MAIN STREET) | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | UTILITIES | 400000 | [11 empty] | 400000
R-5918 | HIGHWAY | US 221A (EAST MAIN STREET) | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | 13 | Foothills RPO |  | NOT FUNDED |  |  |  | 10000
R-5918 | HIGHWAY | US 221A (EAST MAIN STREET) | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | 13 | Foothills RPO |  | NOT FUNDED |  | BG5200 | CONSTRUCTION | 3100000 | [11 empty] | 3100000
R-5919 | HIGHWAY | US 178 | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | 14 | Land-of-Sky RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
R-5919 | HIGHWAY | US 178 | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | 14 | Land-of-Sky RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | RIGHT-OF-WAY | 710000
R-5919 | HIGHWAY | US 178 | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | 14 | Land-of-Sky RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | UTILITIES | 280000
R-5919 | HIGHWAY | US 178 | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | 14 | Land-of-Sky RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 22400000
R-5920 | HIGHWAY | US 74 | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | 14 | Southwestern RPO |  | NOT FUNDED |  | BGLT5 | RIGHT-OF-WAY | 20000000 | [11 empty] | 20000000
R-5920 | HIGHWAY | US 74 | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | 14 | Southwestern RPO |  | NOT FUNDED |  | BGLT5 | UTILITIES | 1000000 | [11 empty] | 1000000
R-5920 | HIGHWAY | US 74 | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | 14 | Southwestern RPO |  | NOT FUNDED |  | BGLT5 | CONSTRUCTION | 71998000 | [11 empty] | 71998000
R-5920 | HIGHWAY | US 74 | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | 14 | Southwestern RPO |  | NOT FUNDED |  |  |  | 10000
R-5921 | HIGHWAY | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | 14 | Land-of-Sky RPO, French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  |  |  | 10000
R-5921 | HIGHWAY | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | 14 | Land-of-Sky RPO, French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | BGLT5 | RIGHT-OF-WAY | 6500000 | FY 2023: 1835000; FY 2024: 3365000; FY 2025: 650000; FY 2026: 650000
R-5921 | HIGHWAY | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | 14 | Land-of-Sky RPO, French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | BGLT5 | UTILITIES | 110000 | FY 2023: 110000
R-5921 | HIGHWAY | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | 14 | Land-of-Sky RPO, French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 14 |  | BGLT5 | CONSTRUCTION | 30000000 | FY 2024: 300000; FY 2025: 10751000; FY 2026: 10579000; FY 2027: 6952000; FY 2028: 1418000
R-5922 | HIGHWAY | US 64 | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | 14 | Southwestern RPO |  | NOT FUNDED |  | BGLT5 | RIGHT-OF-WAY | 3700000 | [11 empty] | 3700000
R-5922 | HIGHWAY | US 64 | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | 14 | Southwestern RPO |  | NOT FUNDED |  | BGLT5 | UTILITIES | 2700000 | [11 empty] | 2700000
R-5922 | HIGHWAY | US 64 | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | 14 | Southwestern RPO |  | NOT FUNDED |  |  |  | 10000
R-5922 | HIGHWAY | US 64 | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | 14 | Southwestern RPO |  | NOT FUNDED |  | BGLT5 | CONSTRUCTION | 39700000 | [11 empty] | 39700000
R-5923 | HIGHWAY | NC 226 | US 221 TO NC 226A. WIDEN ROADWAY TO THREE LANES. | 13 | Foothills RPO |  | NOT FUNDED |  |  |  | 10000
R-5923 | HIGHWAY | NC 226 | US 221 TO NC 226A. WIDEN ROADWAY TO THREE LANES. | 13 | Foothills RPO |  | NOT FUNDED |  | BGLT5 | RIGHT-OF-WAY | 100000 | [11 empty] | 100000
R-5923 | HIGHWAY | NC 226 | US 221 TO NC 226A. WIDEN ROADWAY TO THREE LANES. | 13 | Foothills RPO |  | NOT FUNDED |  | BGLT5 | UTILITIES | 600000 | [11 empty] | 600000
R-5923 | HIGHWAY | NC 226 | US 221 TO NC 226A. WIDEN ROADWAY TO THREE LANES. | 13 | Foothills RPO |  | NOT FUNDED |  | BGLT5 | CONSTRUCTION | 4300000 | [11 empty] | 4300000
R-5924 | HIGHWAY | US 25/70 | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | 13 | Land-of-Sky RPO |  | NOT FUNDED |  | BGLT5 | RIGHT-OF-WAY | 1800000 | [11 empty] | 1800000
R-5924 | HIGHWAY | US 25/70 | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | 13 | Land-of-Sky RPO |  | NOT FUNDED |  | BGLT5 | UTILITIES | 3000000 | [11 empty] | 3000000
R-5924 | HIGHWAY | US 25/70 | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | 13 | Land-of-Sky RPO |  | NOT FUNDED |  |  |  | 10000
R-5924 | HIGHWAY | US 25/70 | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | 13 | Land-of-Sky RPO |  | NOT FUNDED |  | BGLT5 | CONSTRUCTION | 32101000 | [11 empty] | 32101000
R-5926 | HIGHWAY | US 158 / NC 86 | SR 1572 (COUNTY HOME ROAD) TO SR 1734 (RP FUQUAY ROAD). CONSTRUCT PASSING LANES. | 7 | Piedmont Triad RPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 269000
R-5926 | HIGHWAY | US 158 / NC 86 | SR 1572 (COUNTY HOME ROAD) TO SR 1734 (RP FUQUAY ROAD). CONSTRUCT PASSING LANES. | 7 | Piedmont Triad RPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 83000
R-5926 | HIGHWAY | US 158 / NC 86 | SR 1572 (COUNTY HOME ROAD) TO SR 1734 (RP FUQUAY ROAD). CONSTRUCT PASSING LANES. | 7 | Piedmont Triad RPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3649000
R-5927 | HIGHWAY | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | UTILITIES | 4100000 | FY 2026: 2050000; FY 2027: 2050000
R-5927 | HIGHWAY | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 43700000 | FY 2029: 11658000; FY 2030: 16108000; FY 2031: 11363000; FY 2032: 4571000
R-5927 | HIGHWAY | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | RIGHT-OF-WAY | 1200000 | FY 2026: 233000; FY 2027: 349000; FY 2028: 349000; FY 2029: 29000; FY 2030: 240000
R-5927 | HIGHWAY | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  |  |  | 10000
R-5928 | HIGHWAY | US 1 | SR 1640 (WIREGRASS ROAD) TO LOCH LAURIN LANE. WIDEN TO MULTI-LANES. | 8 | Lumber River RPO | COORDINATE WITH R-2501BC | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2900000
R-5928 | HIGHWAY | US 1 | SR 1640 (WIREGRASS ROAD) TO LOCH LAURIN LANE. WIDEN TO MULTI-LANES. | 8 | Lumber River RPO | COORDINATE WITH R-2501BC | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 28901000
R-5928 | HIGHWAY | US 1 | SR 1640 (WIREGRASS ROAD) TO LOCH LAURIN LANE. WIDEN TO MULTI-LANES. | 8 | Lumber River RPO | COORDINATE WITH R-2501BC | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5000000
R-5929 | HIGHWAY | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | 8 | Triangle Area RPO | COORDINATE WITH U-3628 | DIVISION 8 |  | T | RIGHT-OF-WAY | 200000 | FY 2026: 200000
R-5929 | HIGHWAY | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | 8 | Triangle Area RPO | COORDINATE WITH U-3628 | DIVISION 8 |  | T | UTILITIES | 1100000 | FY 2026: 550000; FY 2027: 550000
R-5929 | HIGHWAY | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | 8 | Triangle Area RPO | COORDINATE WITH U-3628 | DIVISION 8 |  | T | CONSTRUCTION | 6100000 | FY 2028: 3989000; FY 2029: 2111000
R-5930 | HIGHWAY | NEW ROUTE CHATHAM PARK WAY | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | "O" FUNDING REFLECTS LOCAL PARTICIPATION. | DIVISION 8 |  | O | RIGHT-OF-WAY | 2000000 | FY 2023: 2000000
R-5930 | HIGHWAY | NEW ROUTE CHATHAM PARK WAY | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | "O" FUNDING REFLECTS LOCAL PARTICIPATION. | DIVISION 8 |  | T | RIGHT-OF-WAY | 1693000 | FY 2023: 1693000
R-5930 | HIGHWAY | NEW ROUTE CHATHAM PARK WAY | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | "O" FUNDING REFLECTS LOCAL PARTICIPATION. | DIVISION 8 |  | T | UTILITIES | 360000 | FY 2023: 360000
R-5930A | HIGHWAY | NEW ROUTE - CHATHAM PARK WAY | NORTHERN TERMINUS OF EXISTING CHATHAM PARK WAY JUST NORTH OF US 64 TO NORTH OF PROPOSED GRANT DRIVE. CONSTRUCT ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO |  | DIVISION 8 |  | O | CONSTRUCTION | 7000000 | FY 2024: 1000000; FY 2025: 6000000
R-5930A | HIGHWAY | NEW ROUTE - CHATHAM PARK WAY | NORTHERN TERMINUS OF EXISTING CHATHAM PARK WAY JUST NORTH OF US 64 TO NORTH OF PROPOSED GRANT DRIVE. CONSTRUCT ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 7800000 | FY 2024: 7800000
R-5930B | HIGHWAY | NEW ROUTE - CHATHAM PARK WAY | NORTH OF PROPOSED GRANT DRIVE TO US 15/ US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 17800000 | FY 2024: 2943000; FY 2025: 8534000; FY 2026: 5564000; FY 2027: 759000
R-5931 | HIGHWAY | NC 49 | SR 1174 (WAYNICK MEADOW ROAD) TO SOUTH OF SR 1193 (OLD NC 49). WIDEN TO MULTI-LANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 79999000 | [11 empty] | 79999000
R-5931 | HIGHWAY | NC 49 | SR 1174 (WAYNICK MEADOW ROAD) TO SOUTH OF SR 1193 (OLD NC 49). WIDEN TO MULTI-LANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2964000 | [11 empty] | 2964000
R-5931 | HIGHWAY | NC 49 | SR 1174 (WAYNICK MEADOW ROAD) TO SOUTH OF SR 1193 (OLD NC 49). WIDEN TO MULTI-LANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | UTILITIES | 5766000 | [11 empty] | 5766000
R-5932 | HIGHWAY | NC 24 / NC 27 | I-73 / I-74 / US 220 TO SR 1644 (OLD GLENDON ROAD). MODERNIZE ROADWAY. | 8 | Triangle Area RPO, Piedmont Triad RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 50200000 | [11 empty] | 50200000
R-5932 | HIGHWAY | NC 24 / NC 27 | I-73 / I-74 / US 220 TO SR 1644 (OLD GLENDON ROAD). MODERNIZE ROADWAY. | 8 | Triangle Area RPO, Piedmont Triad RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5800000 | [11 empty] | 5800000
R-5932 | HIGHWAY | NC 24 / NC 27 | I-73 / I-74 / US 220 TO SR 1644 (OLD GLENDON ROAD). MODERNIZE ROADWAY. | 8 | Triangle Area RPO, Piedmont Triad RPO |  | NOT FUNDED |  | T | UTILITIES | 14400000 | [11 empty] | 14400000
R-5936 | HIGHWAY | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  |  |  | 10000
R-5936 | HIGHWAY | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | RIGHT-OF-WAY | 200000 | FY 2026: 200000
R-5936 | HIGHWAY | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | UTILITIES | 200000 | FY 2026: 200000
R-5936 | HIGHWAY | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | CONSTRUCTION | 18700000 | FY 2028: 187000; FY 2029: 8218000; FY 2030: 6832000; FY 2031: 3463000
R-5937 | HIGHWAY | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  |  |  | 10000
R-5937 | HIGHWAY | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | CONSTRUCTION | 12300000 | FY 2032: 2900000; FY 2033: 6368000 | 3032000
R-5937 | HIGHWAY | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | UTILITIES | 200000 | FY 2028: 200000
R-5937 | HIGHWAY | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | RIGHT-OF-WAY | 400000 | FY 2028: 400000
R-5938 | HIGHWAY | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  |  |  | 10000
R-5938 | HIGHWAY | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | RIGHT-OF-WAY | 29184000 | FY 2028: 4245000; FY 2029: 12735000; FY 2030: 6368000; FY 2031: 2918000; FY 2032: 2918000
R-5938 | HIGHWAY | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | UTILITIES | 26976000 | FY 2028: 13488000; FY 2029: 13488000
R-5938 | HIGHWAY | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | CONSTRUCTION | 75901000 | FY 2031: 10163000; FY 2032: 23079000; FY 2033: 18933000 | 23726000
R-5939 | HIGHWAY | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | RIGHT-OF-WAY | 5400000 | FY 2028: 589000; FY 2029: 2356000; FY 2030: 1375000; FY 2031: 540000; FY 2032: 540000
R-5939 | HIGHWAY | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | UTILITIES | 1400000 | FY 2028: 700000; FY 2029: 700000
R-5939 | HIGHWAY | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  |  |  | 10000
R-5939 | HIGHWAY | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | T | CONSTRUCTION | 14100000 | FY 2030: 3184000; FY 2031: 7101000; FY 2032: 3815000
R-5940 | HIGHWAY | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  |  |  | 10000
R-5940 | HIGHWAY | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | RIGHT-OF-WAY | 900000 | FY 2028: 900000
R-5940 | HIGHWAY | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | UTILITIES | 9100000 | FY 2028: 4550000; FY 2029: 4550000
R-5940 | HIGHWAY | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | 1 | Albemarle RPO |  | DIVISION 1 |  | NHP | CONSTRUCTION | 47100000 | FY 2032: 7338000; FY 2033: 16574000 | 23188000
R-5941 | HIGHWAY | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | 2 | Down East RPO |  | DIVISION 2 |  |  |  | 10000
R-5941 | HIGHWAY | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | 2 | Down East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 2000000 | FY 2029: 1139000; FY 2030: 861000
R-5941 | HIGHWAY | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | 2 | Down East RPO |  | DIVISION 2 |  | T | UTILITIES | 1100000 | FY 2027: 550000; FY 2028: 550000
R-5941 | HIGHWAY | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | 2 | Down East RPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 7400000 | FY 2027: 1973000; FY 2028: 2631000; FY 2029: 1316000; FY 2030: 740000; FY 2031: 740000
R-5942 | HIGHWAY | US 13/US 258 | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  |  |  | 10000
R-5942 | HIGHWAY | US 13/US 258 | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 11800000 | [11 empty] | 11800000
R-5942 | HIGHWAY | US 13/US 258 | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | UTILITIES | 2300000 | [11 empty] | 2300000
R-5942 | HIGHWAY | US 13/US 258 | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | 2 | Eastern Carolina RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 62202000 | [11 empty] | 62202000
R-5943 | HIGHWAY | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | BGLT5 | RIGHT-OF-WAY | 2000000 | FY 2025: 20000; FY 2026: 562000; FY 2027: 582000; FY 2028: 436000; FY 2029: 200000; FY 2030: 200000
R-5943 | HIGHWAY | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | BGLT5 | UTILITIES | 300000 | FY 2025: 300000
R-5943 | HIGHWAY | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  |  |  | 10000
R-5943 | HIGHWAY | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | BGLT5 | CONSTRUCTION | 1200000 | FY 2028: 1025000; FY 2029: 175000
R-5944 | HIGHWAY | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | 2 | Down East RPO |  | DIVISION 2 |  |  |  | 10000
R-5944 | HIGHWAY | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | 2 | Down East RPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 337000 | FY 2027: 337000
R-5944 | HIGHWAY | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | 2 | Down East RPO |  | DIVISION 2 |  | T | UTILITIES | 100000 | FY 2027: 100000
R-5944 | HIGHWAY | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | 2 | Down East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 3100000 | FY 2029: 1609000; FY 2030: 1491000
R-5945 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | 2 | Down East RPO |  | DIVISION 2 |  | NHP | RIGHT-OF-WAY | 31800000 | FY 2027: 318000; FY 2028: 19671000; FY 2029: 5451000; FY 2030: 3180000; FY 2031: 3180000
R-5945 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | 2 | Down East RPO |  | DIVISION 2 |  | NHP | UTILITIES | 600000 | FY 2027: 600000
R-5945 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | 2 | Down East RPO |  | DIVISION 2 |  |  |  | 10000
R-5945 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | 2 | Down East RPO |  | DIVISION 2 |  | NHP | CONSTRUCTION | 23601000 | FY 2029: 8197000; FY 2030: 10059000; FY 2031: 5345000
R-5946 | HIGHWAY | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | 2 | Down East RPO |  | DIVISION 2 |  |  |  | 10000
R-5946 | HIGHWAY | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | 2 | Down East RPO |  | DIVISION 2 |  | NHP | RIGHT-OF-WAY | 4900000 | FY 2027: 49000; FY 2028: 3031000; FY 2029: 840000; FY 2030: 490000; FY 2031: 490000
R-5946 | HIGHWAY | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | 2 | Down East RPO |  | DIVISION 2 |  | NHP | UTILITIES | 700000 | FY 2027: 700000
R-5946 | HIGHWAY | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | 2 | Down East RPO |  | DIVISION 2 |  | NHP | CONSTRUCTION | 2200000 | FY 2029: 1982000; FY 2030: 218000
R-5947 | HIGHWAY | NC 211 | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | 3 | Cape Fear RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 7300000 | [11 empty] | 7300000
R-5947 | HIGHWAY | NC 211 | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | 3 | Cape Fear RPO |  | NOT FUNDED |  | T | UTILITIES | 4300000 | [11 empty] | 4300000
R-5947 | HIGHWAY | NC 211 | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | 3 | Cape Fear RPO |  | NOT FUNDED |  |  |  | 500000
R-5947 | HIGHWAY | NC 211 | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | 3 | Cape Fear RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 45700000 | [11 empty] | 45700000
R-5948 | HIGHWAY | SR 1509 (QUEENS CREEK ROAD) | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  |  |  | 500000
R-5948 | HIGHWAY | SR 1509 (QUEENS CREEK ROAD) | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 4600000 | [11 empty] | 4600000
R-5948 | HIGHWAY | SR 1509 (QUEENS CREEK ROAD) | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 10300000 | [11 empty] | 10300000
R-5948 | HIGHWAY | SR 1509 (QUEENS CREEK ROAD) | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 12600000 | [11 empty] | 12600000
R-5949 | HIGHWAY | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 1901000 | FY 2027: 290000; FY 2028: 869000; FY 2029: 362000; FY 2030: 190000; FY 2031: 190000
R-5949 | HIGHWAY | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | UTILITIES | 900000 | FY 2027: 900000
R-5949 | HIGHWAY | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 25400000 | FY 2029: 5003000; FY 2030: 11840000; FY 2031: 7642000; FY 2032: 915000
R-5949 | HIGHWAY | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 10000
R-5950 | HIGHWAY | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 10000
R-5950 | HIGHWAY | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 2000000 | FY 2027: 534000; FY 2028: 914000; FY 2029: 152000; FY 2030: 200000; FY 2031: 200000
R-5950 | HIGHWAY | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | UTILITIES | 1222000 | FY 2027: 1222000
R-5950 | HIGHWAY | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 3600000 | FY 2029: 1440000; FY 2030: 2160000
R-5951 | HIGHWAY | NC 41 (MARTIN LUTHER KING DRIVE) | US 74 TO MARION ROAD. WIDEN ROADWAY. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 10500000 | [11 empty] | 10500000
R-5951 | HIGHWAY | NC 41 (MARTIN LUTHER KING DRIVE) | US 74 TO MARION ROAD. WIDEN ROADWAY. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | UTILITIES | 3200000 | [11 empty] | 3200000
R-5951 | HIGHWAY | NC 41 (MARTIN LUTHER KING DRIVE) | US 74 TO MARION ROAD. WIDEN ROADWAY. | 6 | Lumber River RPO |  | NOT FUNDED |  |  |  | 10000
R-5951 | HIGHWAY | NC 41 (MARTIN LUTHER KING DRIVE) | US 74 TO MARION ROAD. WIDEN ROADWAY. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 18600000 | [11 empty] | 18600000
R-5953 | HIGHWAY | NC 55 | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | 6 | Mid-Carolina RPO |  | NOT FUNDED |  |  |  | 10000
R-5953 | HIGHWAY | NC 55 | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | 6 | Mid-Carolina RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 14600000 | [11 empty] | 14600000
R-5953 | HIGHWAY | NC 55 | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | 6 | Mid-Carolina RPO |  | NOT FUNDED |  | T | UTILITIES | 4600000 | [11 empty] | 4600000
R-5953 | HIGHWAY | NC 55 | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | 6 | Mid-Carolina RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 66299000 | [11 empty] | 66299000
R-5954 | HIGHWAY | SR 1945 (MEADOW ROAD) | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 100000 | [11 empty] | 100000
R-5954 | HIGHWAY | SR 1945 (MEADOW ROAD) | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | UTILITIES | 300000 | [11 empty] | 300000
R-5954 | HIGHWAY | SR 1945 (MEADOW ROAD) | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 2000000 | [11 empty] | 2000000
R-5954 | HIGHWAY | SR 1945 (MEADOW ROAD) | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | 6 | Lumber River RPO |  | NOT FUNDED |  |  |  | 10000
R-5955 | HIGHWAY | SR 1997 (FAYETTEVILLE ROAD) | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | 6 | Lumber River RPO |  | NOT FUNDED |  |  |  | 10000
R-5955 | HIGHWAY | SR 1997 (FAYETTEVILLE ROAD) | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 16000000 | [11 empty] | 16000000
R-5955 | HIGHWAY | SR 1997 (FAYETTEVILLE ROAD) | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | UTILITIES | 6900000 | [11 empty] | 6900000
R-5955 | HIGHWAY | SR 1997 (FAYETTEVILLE ROAD) | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | 6 | Lumber River RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 16300000 | [11 empty] | 16300000
R-5956A | HIGHWAY | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) TO SR 2149 (HUB MORRIS ROAD). WIDEN TO MULTILANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | UTILITIES | 5300000 | [11 empty] | 5300000
R-5956A | HIGHWAY | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) TO SR 2149 (HUB MORRIS ROAD). WIDEN TO MULTILANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 18200000 | [11 empty] | 18200000
R-5956A | HIGHWAY | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) TO SR 2149 (HUB MORRIS ROAD). WIDEN TO MULTILANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 6200000 | [11 empty] | 6200000
R-5956B | HIGHWAY | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2149 (HUB MORRIS ROAD) TO SR 2123 (CAUDLE ROAD). WIDEN TO MULTILANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | UTILITIES | 6005000 | [11 empty] | 6005000
R-5956B | HIGHWAY | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2149 (HUB MORRIS ROAD) TO SR 2123 (CAUDLE ROAD). WIDEN TO MULTILANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 9399000 | [11 empty] | 9399000
R-5956B | HIGHWAY | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2149 (HUB MORRIS ROAD) TO SR 2123 (CAUDLE ROAD). WIDEN TO MULTILANES. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3200000 | [11 empty] | 3200000
R-5957 | HIGHWAY | NC 42 (EAST SALISBURY STREET) | SR 2189 (MARTIN LUTHER KING, JR. DRIVE) / NORTH RANDOLPH AVENUE TO SR 2237 (EAST SALISBURY STREET) IN ASHEBORO. IMPROVE CORRIDOR. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2100000 | [11 empty] | 2100000
R-5957 | HIGHWAY | NC 42 (EAST SALISBURY STREET) | SR 2189 (MARTIN LUTHER KING, JR. DRIVE) / NORTH RANDOLPH AVENUE TO SR 2237 (EAST SALISBURY STREET) IN ASHEBORO. IMPROVE CORRIDOR. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | UTILITIES | 700000 | [11 empty] | 700000
R-5957 | HIGHWAY | NC 42 (EAST SALISBURY STREET) | SR 2189 (MARTIN LUTHER KING, JR. DRIVE) / NORTH RANDOLPH AVENUE TO SR 2237 (EAST SALISBURY STREET) IN ASHEBORO. IMPROVE CORRIDOR. | 8 | Piedmont Triad RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 3400000 | [11 empty] | 3400000
R-5958 | HIGHWAY | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | T | RIGHT-OF-WAY | 320000 | FY 2024: 320000
R-5958 | HIGHWAY | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 1450000 | FY 2026: 708000; FY 2027: 742000
R-5958 | HIGHWAY | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | T | UTILITIES | 265000 | FY 2024: 265000
R-5959 | HIGHWAY | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | RIGHT-OF-WAY | 1900000 | FY 2023: 19000; FY 2024: 1363000; FY 2025: 138000; FY 2026: 190000; FY 2027: 190000
R-5959 | HIGHWAY | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | UTILITIES | 700000 | FY 2023: 700000
R-5959 | HIGHWAY | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 7300000 | FY 2025: 5815000; FY 2026: 1485000
R-5960 | HIGHWAY | NEW ROUTE | SR 1133 (LEE AVENUE) TO EXISTING COMMERCE DRIVE IN SANFORD. CONSTRUCT 2-LANE EXTENSION OF COMMERCE DRIVE. | 8 | Triangle Area RPO |  | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6500000
R-5960 | HIGHWAY | NEW ROUTE | SR 1133 (LEE AVENUE) TO EXISTING COMMERCE DRIVE IN SANFORD. CONSTRUCT 2-LANE EXTENSION OF COMMERCE DRIVE. | 8 | Triangle Area RPO |  | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 138000
R-5960 | HIGHWAY | NEW ROUTE | SR 1133 (LEE AVENUE) TO EXISTING COMMERCE DRIVE IN SANFORD. CONSTRUCT 2-LANE EXTENSION OF COMMERCE DRIVE. | 8 | Triangle Area RPO |  | DIVISION 8 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 104000
R-5961 | HIGHWAY | NC 87 | NC 902 IN PITTSBORO TO US 64 BYPASS. WIDEN TO 12-FT LANES AND 4-FT PAVED SHOULDERS. | 8 | Triangle Area RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 13200000 | [11 empty] | 13200000
R-5961 | HIGHWAY | NC 87 | NC 902 IN PITTSBORO TO US 64 BYPASS. WIDEN TO 12-FT LANES AND 4-FT PAVED SHOULDERS. | 8 | Triangle Area RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2500000 | [11 empty] | 2500000
R-5961 | HIGHWAY | NC 87 | NC 902 IN PITTSBORO TO US 64 BYPASS. WIDEN TO 12-FT LANES AND 4-FT PAVED SHOULDERS. | 8 | Triangle Area RPO |  | NOT FUNDED |  | T | UTILITIES | 2200000 | [11 empty] | 2200000
R-5962 | HIGHWAY | US 70 (CEDAR STREET) | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  |  |  | 10000
R-5962 | HIGHWAY | US 70 (CEDAR STREET) | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3300000 | [11 empty] | 3300000
R-5962 | HIGHWAY | US 70 (CEDAR STREET) | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | UTILITIES | 370000 | [11 empty] | 370000
R-5962 | HIGHWAY | US 70 (CEDAR STREET) | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | 2 | Down East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 1700000 | [11 empty] | 1700000
R-5963A | HIGHWAY | NEW ROUTE | US 15 / US 501 SOUTH OF PITTSBORO TO SR 1012 (MONCURE-PITTSBORO ROAD). CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 23 AND CONSTRUCTION FY 23 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT. | DIVISION 8 |  | T | RIGHT-OF-WAY | 2686000 | FY 2024: 671000; FY 2025: 1342000; FY 2026: 673000
R-5963A | HIGHWAY | NEW ROUTE | US 15 / US 501 SOUTH OF PITTSBORO TO SR 1012 (MONCURE-PITTSBORO ROAD). CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 23 AND CONSTRUCTION FY 23 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT. | DIVISION 8 |  | T | CONSTRUCTION | 12629000 | FY 2027: 2400000; FY 2028: 4799000; FY 2029: 3536000; FY 2030: 1894000
R-5963A | HIGHWAY | NEW ROUTE | US 15 / US 501 SOUTH OF PITTSBORO TO SR 1012 (MONCURE-PITTSBORO ROAD). CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 23 AND CONSTRUCTION FY 23 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT. | DIVISION 8 |  | T | UTILITIES | 26000 | FY 2024: 26000
R-5963B | HIGHWAY | NEW ROUTE | SR 1012 (MONCURE-PITTSBORO ROAD) TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 24 AND CONSTRUCTION FY 24 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT. | DIVISION 8 |  | T | RIGHT-OF-WAY | 3573000 | FY 2024: 893000; FY 2025: 1787000; FY 2026: 893000
R-5963B | HIGHWAY | NEW ROUTE | SR 1012 (MONCURE-PITTSBORO ROAD) TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 24 AND CONSTRUCTION FY 24 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT. | DIVISION 8 |  | T | UTILITIES | 36000 | FY 2024: 36000
R-5963B | HIGHWAY | NEW ROUTE | SR 1012 (MONCURE-PITTSBORO ROAD) TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 8 | Triangle Area RPO | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 24 AND CONSTRUCTION FY 24 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT. | DIVISION 8 |  | T | CONSTRUCTION | 32679000 | FY 2027: 4902000; FY 2028: 9150000; FY 2029: 12418000; FY 2030: 6209000
R-5963C | HIGHWAY | NEW ROUTE | US 64 BUSINESS TO JUST NORTH OF US 64. WIDEN EXISTING 2-LANE ROADWAY TO 4-LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | UTILITIES | 30000 | FY 2024: 30000
R-5963C | HIGHWAY | NEW ROUTE | US 64 BUSINESS TO JUST NORTH OF US 64. WIDEN EXISTING 2-LANE ROADWAY TO 4-LANES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 9771000 | FY 2027: 1856000; FY 2028: 3713000; FY 2029: 2736000; FY 2030: 1466000
R-5963D | HIGHWAY | CHATHAM PARK WAY | CONSTRUCTION OF NEW WESTBOUND ON-RAMP FROM CHATHAM PARK WAY TO US 64 AND REALIGNMENT OF SUTTLES ROAD TO NEW INTERSECTION WITH CHATHAM PARK WAY. | 8 | Triangle Area RPO | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 23 AND CONSTRUCTION FY 23 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT. | DIVISION 8 |  | T | RIGHT-OF-WAY | 500000 | FY 2025: 500000
R-5963D | HIGHWAY | CHATHAM PARK WAY | CONSTRUCTION OF NEW WESTBOUND ON-RAMP FROM CHATHAM PARK WAY TO US 64 AND REALIGNMENT OF SUTTLES ROAD TO NEW INTERSECTION WITH CHATHAM PARK WAY. | 8 | Triangle Area RPO | TOWN OF PITTSBORO FUNDING AND DELIVERING PROJECT RIGHT-OF-WAY FY 23 AND CONSTRUCTION FY 23 SCHEDULE. FUNDS SHOWN REPRESENT FY PAYBACK BY NCDOT. | DIVISION 8 |  | T | CONSTRUCTION | 2000000 | FY 2027: 2000000
R-5964 | HIGHWAY | NEW ROUTE | CONSTRUCT ACCESS ROAD TO UNIVERSAL PROPERTY. | 13 | Foothills RPO | UNDER CONSTRUCTION. ARC # 19098; AWARD AMOUNT = $987,112 | EXEMPT |  | ADHSL | CONSTRUCTION | 922000
R-5964 | HIGHWAY | NEW ROUTE | CONSTRUCT ACCESS ROAD TO UNIVERSAL PROPERTY. | 13 | Foothills RPO | UNDER CONSTRUCTION. ARC # 19098; AWARD AMOUNT = $987,112 | EXEMPT |  |  |  | 65000
R-5965A | HIGHWAY | VARIOUS | NC 205/SR 1108 (LIGHTHOUSE ROAD)/SR 1109 (BUSTER ROAD) INTERSECTION AND SR 1110 (SWIFT ROAD) AT CHARLOTTE PIPE FACILITY. IMPROVE INTERSECTIONS. | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. | DIVISION 10 |  | T | RIGHT-OF-WAY | 120000
R-5965A | HIGHWAY | VARIOUS | NC 205/SR 1108 (LIGHTHOUSE ROAD)/SR 1109 (BUSTER ROAD) INTERSECTION AND SR 1110 (SWIFT ROAD) AT CHARLOTTE PIPE FACILITY. IMPROVE INTERSECTIONS. | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. | DIVISION 10 |  | T | CONSTRUCTION | 2405000
R-5965B | HIGHWAY | VARIOUS | SR 1107 (SILVER ROAD)/SR 1108 (LIGHTHOUSE ROAD) AND SR 1107 (SILVER ROAD)/SR 1110 (SWIFT ROAD) INTERSECTIONS. IMPROVE INTERSECTIONS. SR 1107 (SILVER ROAD), SR 1108 (LIGHTHOUSE ROAD) AND SR 1110 (SWIFT ROAD). VARIOUS ROADWAY IMPROVEMENTS INCLUDING FULL DEPTH RECLAMATION. | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. | DIVISION 10 |  | T | RIGHT-OF-WAY | 250000
R-5965B | HIGHWAY | VARIOUS | SR 1107 (SILVER ROAD)/SR 1108 (LIGHTHOUSE ROAD) AND SR 1107 (SILVER ROAD)/SR 1110 (SWIFT ROAD) INTERSECTIONS. IMPROVE INTERSECTIONS. SR 1107 (SILVER ROAD), SR 1108 (LIGHTHOUSE ROAD) AND SR 1110 (SWIFT ROAD). VARIOUS ROADWAY IMPROVEMENTS INCLUDING FULL DEPTH RECLAMATION. | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. | DIVISION 10 |  | T | CONSTRUCTION | 1586000 | FY 2023: 1586000
R-5966 | HIGHWAY | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. | 99 | STATEWIDE PROJECT | PROGRAM IN PROGRESS | EXEMPT |  |  |  | 21224000
R-5966 | HIGHWAY | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. | 99 | STATEWIDE PROJECT | PROGRAM IN PROGRESS | EXEMPT |  | FTTP | CONSTRUCTION | 1694000 | FY 2026: 1694000
R-5966 | HIGHWAY | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. | 99 | STATEWIDE PROJECT | PROGRAM IN PROGRESS | EXEMPT |  | FTTP | CONSTRUCTION | 5692000 | FY 2023: 5692000
R-5966 | HIGHWAY | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. | 99 | STATEWIDE PROJECT | PROGRAM IN PROGRESS | EXEMPT |  | FTTP | CONSTRUCTION | 9528000 | FY 2024: 5059000; FY 2025: 4469000
R-5967 | HIGHWAY | SR 1687 (GOAT FARM ROAD) | IMPROVE EXISTING SR 1687 (GOAT FARM ROAD) ACCESS ROAD INTO THE PROPOSED INDUSTRIAL PARK. | 13 | Greater Hickory MPO | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY. UNDER CONSTRUCTION. | EXEMPT |  |  |  | 424000
R-5967 | HIGHWAY | SR 1687 (GOAT FARM ROAD) | IMPROVE EXISTING SR 1687 (GOAT FARM ROAD) ACCESS ROAD INTO THE PROPOSED INDUSTRIAL PARK. | 13 | Greater Hickory MPO | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY. UNDER CONSTRUCTION. | EXEMPT |  | ADHSL | CONSTRUCTION | 1076000 | FY 2023: 703000; FY 2024: 373000
R-5967 | HIGHWAY | SR 1687 (GOAT FARM ROAD) | IMPROVE EXISTING SR 1687 (GOAT FARM ROAD) ACCESS ROAD INTO THE PROPOSED INDUSTRIAL PARK. | 13 | Greater Hickory MPO | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY. UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 1076000 | FY 2023: 703000; FY 2024: 373000
R-5968DIV | HIGHWAY | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  | BGANY | CONSTRUCTION | 14400000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 1800000
R-5968REG | HIGHWAY | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. | 99 | STATEWIDE PROJECT | IN PROGRESS | REGION SW |  | BGANY | CONSTRUCTION | 14400000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 1800000
R-5968SW | HIGHWAY | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. | 99 | STATEWIDE PROJECT | IN PROGRESS | STATEWIDE MOBILITY |  | BGANY | CONSTRUCTION | 19200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 2400000
R-9999WM | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 145559000
R-9999WMDIV | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | T | MITIGATION | 150000
R-9999WMDIV | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | NHP | MITIGATION | 150000
R-9999WMREG | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | REGION SW |  | NHP | MITIGATION | 150000
R-9999WMREG | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | REGION SW |  | T | MITIGATION | 150000
R-9999WMSW | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | NHP | MITIGATION | 200000
R-9999WMSW | HIGHWAY | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | T | MITIGATION | 200000
RC-2002A | RAIL | EAST STREET | CLOSURE OF EAST STREET AT CSX (CROSSING 628 794Y) IN BETHEL. | 2 | Mid-East RPO |  | DIVISION 2 |  | RR | CONSTRUCTION | 560000 | FY 2024: 560000
RC-2004A | RAIL | SR 1163 (GOLDSBORO STREET) | AT-GRADE CROSSING IMPROVEMENTS AT CSX (CROSSING 629 847Y) IN WILSON. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 1200000 | FY 2025: 1200000
RC-2004A | RAIL | SR 1163 (GOLDSBORO STREET) | AT-GRADE CROSSING IMPROVEMENTS AT CSX (CROSSING 629 847Y) IN WILSON. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | RIGHT-OF-WAY | 50000 | FY 2024: 50000
RC-2004A | RAIL | SR 1163 (GOLDSBORO STREET) | AT-GRADE CROSSING IMPROVEMENTS AT CSX (CROSSING 629 847Y) IN WILSON. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | UTILITIES | 50000 | FY 2025: 50000
RC-2004B | RAIL | SR 2383 (PRESTON STREET) | CLOSURE OF SR 2383 (PRESTON STREET) AT CSX (CROSSING 629 950L) IN SELMA. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | RIGHT-OF-WAY | 50000 | FY 2024: 50000
RC-2004B | RAIL | SR 2383 (PRESTON STREET) | CLOSURE OF SR 2383 (PRESTON STREET) AT CSX (CROSSING 629 950L) IN SELMA. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | UTILITIES | 20000 | FY 2024: 20000
RC-2004B | RAIL | SR 2383 (PRESTON STREET) | CLOSURE OF SR 2383 (PRESTON STREET) AT CSX (CROSSING 629 950L) IN SELMA. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 500000 | FY 2025: 500000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | L | CONSTRUCTION | 955000 | FY 2025: 955000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | BGDA | ENGINEERING | 398000 | FY 2023: 398000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | BGDA | CONSTRUCTION | 3818000 | FY 2025: 3818000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | DP | ENGINEERING | 400000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | DP | RIGHT-OF-WAY | 160000 | FY 2023: 160000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | DP | CONSTRUCTION | 3930000 | FY 2025: 3930000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | L | ENGINEERING | 400000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | L | ENGINEERING | 100000 | FY 2023: 100000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | L | RIGHT-OF-WAY | 160000 | FY 2023: 160000
RL-0001 | RAIL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS | EXEMPT |  | L | CONSTRUCTION | 3930000 | FY 2025: 3930000
RL-0002 | RAIL | CHARLOTTE RAILYARD PINEVILLE RAILYARD | GRANTS TO REPLACE AGING DIESEL ENGINES (GRADE). | 10 | Charlotte Regional TPO |  | EXEMPT |  | L | CONSTRUCTION | 1635000 | FY 2023: 1635000
RL-0002 | RAIL | CHARLOTTE RAILYARD PINEVILLE RAILYARD | GRANTS TO REPLACE AGING DIESEL ENGINES (GRADE). | 10 | Charlotte Regional TPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 3815000 | FY 2023: 3815000
RX-2001A | RAIL | SR 1409 (HALL SIDING ROAD) | NCVA CROSSING 642347G IN AHOSKIE. | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | DIVISION 1 |  | HSIP | CONSTRUCTION | 355000 | FY 2023: 355000
RX-2002A | RAIL | SR 1726 (PORTERTOWN ROAD) | CLNA CROSSING 465482M IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | RR | CONSTRUCTION | 362000 | FY 2024: 362000
RX-2002B | RAIL | SR 1704 (FOURTEENTH STREET) | CLNA CROSSING 465488D IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | RR | CONSTRUCTION | 345000 | FY 2024: 345000
RX-2002C | RAIL | US 264 ALTERNATE (GREENVILLE BOULEVARD) | CLNA CROSSING 465489K IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | RR | CONSTRUCTION | 345000 | FY 2024: 345000
RX-2002D | RAIL | LINCOLN STREET | NORFOLK SOUTHERN CROSSING 722766G IN KINSTON. CONSTRUCT SAFETY IMPROVEMENTS. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | RR | CONSTRUCTION | 411000 | FY 2025: 411000
RX-2002E | RAIL | SR 1530 (AIRPORT ROAD) | CSX CROSSING 641860P IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | RR | CONSTRUCTION | 530000 | FY 2027: 530000
RX-2004A | RAIL | SR 1163 (GOLDSBORO STREET / HERRING AVENUE) | CSX CROSSING 629847Y IN WILSON. INSTALL ACTIVE WARNING DEVICES. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 800000 | FY 2024: 800000
RX-2004B | RAIL | SR 1100 (CHICOPEE ROAD) | CSX CROSSING 629847Y IN WILSON. INSTALL ACTIVE WARNING DEVICES. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | DIVISION 4 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2004C | RAIL | SR 1357 (GILBERT ROAD) | CSX CROSSING 629731X NEAR BENSON. INSTALL ACTIVE WARNING DEVICES. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | DIVISION 4 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2004D | RAIL | PARRISH DRIVE | CSX CROSSING 629739C IN BENSON. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 388000 | FY 2024: 388000
RX-2004E | RAIL | SR 1329 (VAN SLYKE ROAD) | CSX CROSSING 629843W IN WILSON. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 417000 | FY 2024: 417000
RX-2004F | RAIL | BAIN STREET | NORFOLK SOUTHERN CROSSING 722874X IN GOLDSBORO. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 417000 | FY 2024: 417000
RX-2004G | RAIL | SR 2130 (MAIN STREET) | CSX CROSSING 629943B IN MICRO. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 417000 | FY 2025: 417000
RX-2004H | RAIL | SR 1709 (STALLINGS STREET) | NORFOLK SOUTHERN CROSSING 735396M IN CLAYTON. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Capital Area MPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 475000 | FY 2025: 475000
RX-2004I | RAIL | GREEN STREET | CSX CROSSING 629849M IN WILSON. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 417000 | FY 2025: 417000
RX-2004J | RAIL | SR 2339 (BAGLEY ROAD) | CSX CROSSING 629939L IN KENLY. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 434000 | FY 2026: 434000
RX-2004K | RAIL | LEE STREET | CSX CROSSING 629964U IN SMITHFIELD. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 388000 | FY 2027: 388000
RX-2004L | RAIL | SR 2500 (WALLPAT ROAD) | CSX CROSSING 629966H IN SMITHFIELD. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 388000 | FY 2027: 388000
RX-2004M | RAIL | JEFFERSON STREET | NORFOLK SOUTHERN CROSSING 722868U IN GOLDSBORO. CONSTRUCT SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | RR | CONSTRUCTION | 411000 | FY 2027: 411000
RX-2006A | RAIL | SR 1714 (CHURCH STREET) | CSX CROSSING 629869Y IN WADE. INSTALL ACTIVE WARNING DEVICES. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2006B | RAIL | SR 1154 (UNION SCHOOL ROAD) | CSX CROSSING 629606K NEAR PEMBROKE. INSTALL ACTIVE WARNING DEVICES. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2006C | RAIL | HARNETT STREET | CSX CROSSING 629751J IN DUNN. CONSTRUCT SAFETY IMPROVEMENTS. | 6 | Mid-Carolina RPO |  | DIVISION 6 |  | RR | CONSTRUCTION | 446000 | FY 2025: 446000
RX-2006D | RAIL | EDGERTON STREET | CSX CROSSING 629752R IN DUNN. CONSTRUCT SAFETY IMPROVEMENTS. | 6 | Mid-Carolina RPO |  | DIVISION 6 |  | RR | CONSTRUCTION | 446000 | FY 2025: 446000
RX-2006E | RAIL | NC 41 (MARTIN LUTHER KING JR. DRIVE) | CSX CROSSING 631029P IN LUMBERTON. CONSTRUCT SAFETY IMPROVEMENTS. | 6 | Lumber River RPO |  | DIVISION 6 |  | RR | CONSTRUCTION | 446000 | FY 2026: 446000
RX-2006F | RAIL | US 401 (MAIN STREET) | RFR CROSSING 465860F IN LILLINGTON. CONSTRUCT SAFETY IMPROVEMENTS. | 6 | Mid-Carolina RPO |  | DIVISION 6 |  | RR | CONSTRUCTION | 345000 | FY 2026: 345000
RX-2006G | RAIL | SR 1748 (CRENSHAW ROAD) | CSX CROSSING 629581S IN REX. CONSTRUCT SAFETY IMPROVEMENTS. | 6 | Lumber River RPO |  | DIVISION 6 |  | RR | CONSTRUCTION | 417000 | FY 2027: 417000
RX-2007A | RAIL | SR 2748 (SPRINGWOOD AVENUE) | NORFOLK SOUTHERN RAILROAD CROSSING 722990L IN GIBSONVILLE. INSTALL ACTIVE WARNING DEVICES. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | DIVISION 7 |  | RR | CONSTRUCTION | 500000 | FY 2023: 500000
RX-2007B | RAIL | SR 1120 (MOUNT WILLING ROAD) | NORFOLK SOUTHERN RAILROAD CROSSING 735145T NEAR EFLAND. INSTALL ACTIVE WARNING DEVICES. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | RR | CONSTRUCTION | 800000 | FY 2024: 800000
RX-2007C | RAIL | SR 2531 (HILLCROFT ROAD) | NORFOLK SOUTHERN RAILROAD CROSSING 722545Y NEAR GREENSBORO. INSTALL ACTIVE WARNING DEVICES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2008A | RAIL | SR 1916 (CORINTH ROAD) | CSX CROSSING 630723C NEAR HAYWOOD. INSTALL ACTIVE WARNING DEVICES. | 8 | Triangle Area RPO |  | DIVISION 8 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2008B | RAIL | LS (SOUTH STREET) | ACWR CROSSING 722526U IN ABERDEEN. CONSTRUCT SAFETY IMPROVEMENTS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | RR | CONSTRUCTION | 1832000 | FY 2024: 1832000
RX-2008C | RAIL | SR 1925 (BILTMORE DRIVE) | CSX CROSSING 630856U IN ROCKINGHAM. CONSTRUCT SAFETY IMPROVEMENTS. | 8 | Lumber River RPO |  | DIVISION 8 |  | RR | CONSTRUCTION | 446000 | FY 2024: 446000
RX-2008D | RAIL | SR 1003 (ARABIA ROAD) | AR CROSSING 847348H IN DUNDARRACH. CONSTRUCT SAFETY IMPROVEMENTS. | 8 | Lumber River RPO |  | DIVISION 8 |  | RR | CONSTRUCTION | 345000 | FY 2024: 345000
RX-2008E | RAIL | US 1 BUSINESS (CARTHAGE STREET / CHARLOTTE AVENUE) | ATW CROSSING 721059F IN SANFORD. CONSTRUCT SAFETY IMPROVEMENTS. | 8 | Triangle Area RPO |  | DIVISION 8 |  | RR | CONSTRUCTION | 450000 | FY 2025: 450000
RX-2008F | RAIL | SR 2502 (JULIAN AIRPORT ROAD) | NORFOLK SOUTHERN CROSSING 720943W IN LIBERTY. CONSTRUCT SAFETY IMPROVEMENTS. | 8 | Piedmont Triad RPO |  | DIVISION 8 |  | RR | CONSTRUCTION | 411000 | FY 2026: 411000
RX-2009A | RAIL | LS (FIRST STREET) | WSS CROSSING 849955C IN DENTON. CONSTRUCT SAFETY IMPROVEMENTS. | 9 | High Point Urban Area MPO |  | DIVISION 9 |  | RR | CONSTRUCTION | 303000 | FY 2024: 303000
RX-2009B | RAIL | SR 2385 (WALKERTOWN-GUTHRIE ROAD) | NORFOLK SOUTHERN CROSSING 722063Y IN WALKERTOWN. CONSTRUCT SAFETY IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | RR | CONSTRUCTION | 411000 | FY 2025: 411000
RX-2009C | RAIL | SR 2381 (WILLSTON ROAD) | NORFOLK SOUTHERN CROSSING 470210K IN WALKERTOWN. CONSTRUCT SAFETY IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | RR | CONSTRUCTION | 601000 | FY 2026: 601000
RX-2009D | RAIL | SR 1686 (SHATTALON DRIVE) | NORFOLK SOUTHERN CROSSING 722024H IN WINSTON-SALEM. CONSTRUCT SAFETY IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | RR | CONSTRUCTION | 492000 | FY 2027: 492000
RX-2010A | RAIL | SR 3522 (WEDDINGTON ROAD) | CSX CROSSING 631587H NEAR MONROE. CONSTRUCT SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2010B | RAIL | SR 1714 (STANBACK FERRY ICE PLANT ROAD) | CSX CROSSING 631750C NEAR WADESBORO. CONSTRUCT SAFETY IMPROVEMENTS. | 10 | Rocky River RPO | UNDER CONSTRUCTION. | DIVISION 10 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2011A | RAIL | SR 1159 (PLEASANT HILL ROAD) | CWCY CROSSING 729801L IN HUDSON. CONSTRUCT SAFETY IMPROVEMENTS. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | RR | CONSTRUCTION | 800000 | FY 2023: 800000
RX-2100 | RAIL | VARIOUS | PASSENGER RAIL CROSSING SAFETY IMPROVEMENT INVENTORY PROGRAM | 99 | STATEWIDE PROJECT | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY | DIVISION SW |  | RR | ENGINEERING | 2500000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
RX-9999 | RAIL | VARIOUS | RAILWAY-HIGHWAY CROSSINGS PROGRAM - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | CONSTRUCTION | 85008000 |  | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 14168000
SF-4903F | HIGHWAY | NC 53 | SR 1109 (HOLLY SHELTER ROAD). REALIGNMENT AND LANE CONSTRUCTION. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-5023B AND C. | PRE-STI (TRANSITION) |  |  |  | 49000
SR-5000 | HIGHWAY | VARIOUS | SAFE ROUTES TO SCHOOL PROGRAM. EDUCATIONAL,TRAINING AND OTHER NON-INFRASTRUCTURE NEEDS. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 6435000
SR-5001 | HIGHWAY | VARIOUS | SAFE ROUTES TO SCHOOL PROGRAM. PROJECTS TO IMPROVE SAFETY, REDUCE TRAFFIC, FUEL CONSUMPTION AND AIR POLLUTION IN VICINITY OF SCHOOLS. | 99 | STATEWIDE PROJECT | IN PROGRESS - $200,800 IN STPDA FUNDS ALLOCATED TO SR-5001C | DIVISION SW |  |  |  | 16339000
TA-4710 | PUBLIC TRANSIT | CATS | REPLACEMENT BUS | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL PROGRAM | PUBLIC TRANSIT |  | 5339 | CAPITAL | 6300000 | FY 2023: 2100000
TA-4710 | PUBLIC TRANSIT | CATS | REPLACEMENT BUS | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL PROGRAM | PUBLIC TRANSIT |  | L | CAPITAL | 2726000 | FY 2023: 925000
TA-4710 | PUBLIC TRANSIT | CATS | REPLACEMENT BUS | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL PROGRAM | PUBLIC TRANSIT |  | S | CAPITAL | 2726000 | FY 2023: 925000
TA-4710 | PUBLIC TRANSIT | CATS | REPLACEMENT BUS | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL PROGRAM | PUBLIC TRANSIT |  | 5307 | CAPITAL | 15500000 | FY 2023: 5300000
TA-4711 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 1971000 | FY 2023: 199000; FY 2024: 205000; FY 2025: 211000
TA-4711 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 25831000 | FY 2023: 1590000; FY 2024: 1637000; FY 2025: 1686000
TA-4711 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 1971000 | FY 2023: 199000; FY 2024: 205000; FY 2025: 211000
TA-4726 | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT BUSES | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 1936000 | FY 2023: 242000
TA-4726 | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT BUSES | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 1936000 | FY 2023: 242000
TA-4726 | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT BUSES | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 37313000 | FY 2023: 1939000
TA-4726 | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT BUSES | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 9956000
TA-4726A | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | 3 REPLACEMENT BUSES. | 7 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY CHAPEL HILL TRANSIT | DIVISION 7 |  |  |  | 2235000
TA-4743A | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 6224000
TA-4743A | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 40000
TA-4743A | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 36000
TA-4743B | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 3526000 | FY 2023: 631000
TA-4743B | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 630000
TA-4743B | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 267000 | FY 2023: 63000
TA-4743B | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 348000
TA-4748 | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT - PARATRANSIT VEHICLE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 4421000 | FY 2023: 197000
TA-4767 | PUBLIC TRANSIT | GTA | REPLACEMENT PARATRANSIT BUSES | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | 5309 | CAPITAL | 4598000 | FY 2023: 588000; FY 2024: 588000; FY 2025: 588000; FY 2026: 588000; FY 2027: 588000; FY 2028: 588000
TA-4767 | PUBLIC TRANSIT | GTA | REPLACEMENT PARATRANSIT BUSES | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | L | CAPITAL | 813000 | FY 2023: 104000; FY 2024: 104000; FY 2025: 104000; FY 2026: 104000; FY 2027: 104000; FY 2028: 104000
TA-4771 | PUBLIC TRANSIT | GTA | CLEAN DIESEL REPLACEMENT BUSES | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 1678000 | FY 2023: 451000
TA-4771 | PUBLIC TRANSIT | GTA | CLEAN DIESEL REPLACEMENT BUSES | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1768000
TA-4771 | PUBLIC TRANSIT | GTA | CLEAN DIESEL REPLACEMENT BUSES | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | CMAQ | CAPITAL | 5466000 | FY 2023: 1803000
TA-4818A | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 7141000
TA-4818A | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 269000
TA-4818B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | REPLACEMENT BUS | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 6107000
TA-4818B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | REPLACEMENT BUS | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 192000
TA-4818B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | REPLACEMENT BUS | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | S | CAPITAL | 192000
TA-4903 | PUBLIC TRANSIT | GORALEIGH | REPLACEMENT BUS AND BUS FACILITIES | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 4330000
TA-4903 | PUBLIC TRANSIT | GORALEIGH | REPLACEMENT BUS AND BUS FACILITIES | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 12087000
TA-4903A | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | S | CAPITAL | 684000
TA-4903A | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 688000
TA-4903A | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1980000
TA-4903A | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | CMAQ | CAPITAL | 8100000
TA-4923 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | REPLACEMENT BUS. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY | DIVISION 5 |  | 5307 | CAPITAL | 4332000
TA-4923 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | REPLACEMENT BUS. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY | DIVISION 5 |  | 5339 | CAPITAL | 1686000
TA-4923 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | REPLACEMENT BUS. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY | DIVISION 5 |  | L | CAPITAL | 166000
TA-4927 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | REPLACEMENT BUS | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1290000
TA-4927 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | REPLACEMENT BUS | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 72000
TA-4927 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | REPLACEMENT BUS | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 72000
TA-4928 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS | 11, 12, 13 | Greater Hickory MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 942000
TA-4928 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS | 11, 12, 13 | Greater Hickory MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 72000
TA-4928 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS | 11, 12, 13 | Greater Hickory MPO |  | PUBLIC TRANSIT |  | S | CAPITAL | 72000
TA-4929 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | REPLACEMENT VAN | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | S | CAPITAL | 90000 | FY 2023: 18000
TA-4929 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | REPLACEMENT VAN | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1864000 | FY 2023: 408000
TA-4929 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | REPLACEMENT VAN | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | CAPITAL | 319000 | FY 2023: 18000
TA-4943 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | S | CAPITAL | 176000 | FY 2023: 16000; FY 2024: 16000; FY 2025: 16000; FY 2026: 16000; FY 2027: 16000
TA-4943 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 176000 | FY 2023: 16000; FY 2024: 16000; FY 2025: 16000; FY 2026: 16000; FY 2027: 16000
TA-4943 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2728000 | FY 2023: 125000; FY 2024: 125000; FY 2025: 125000; FY 2026: 125000; FY 2027: 125000
TA-4944 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | REPLACEMENT BUS - FIXED ROUTE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 3884000 | FY 2023: 250000; FY 2024: 250000; FY 2025: 250000; FY 2026: 250000; FY 2027: 250000
TA-4944 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | REPLACEMENT BUS - FIXED ROUTE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 566000 | FY 2023: 63000; FY 2024: 63000; FY 2025: 63000; FY 2026: 63000; FY 2027: 63000
TA-4948A | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 6961000
TA-4948A | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 672000
TA-4948A | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 609000
TA-4960 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 5561000 | FY 2023: 434000; FY 2024: 446000; FY 2025: 460000
TA-4960 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 405000 | FY 2023: 54000; FY 2024: 56000; FY 2025: 58000
TA-4960 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 405000 | FY 2023: 54000; FY 2024: 56000; FY 2025: 58000
TA-4979 | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT VAN | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 4061000 | FY 2023: 792000
TA-5019A | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | PARATRANSIT VEHICLES, BUS REFURBISHMENT, AND BUS SHELTERS. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY CHAPEL HILL TRANSIT | DIVISION 5 |  |  |  | 685000
TA-5116 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH PARK AND RIDE AT POOLE ROAD. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 455000
TA-5123A | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 540000
TA-5123A | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 540000
TA-5123A | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 18190000
TA-5123B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 18466000
TA-5123B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 540000
TA-5123B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 540000
TA-5128A | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - CAPITAL | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | CAPITAL | 3400000 | FY 2023: 500000
TA-5128A | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - CAPITAL | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 850000 | FY 2023: 125000
TA-5128B | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - OPERATING | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 1305000
TA-5128B | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - OPERATING | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 1305000
TA-5128C | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | ADMINISTRATION OF 5310 PROGRAM | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 340000 | FY 2023: 50000
TA-5130A | PUBLIC TRANSIT | CONCORD KANNAPOLIS AREA TRANSIT | TO SUPPORT THE PURCHASE OF ROUTINE CAPITAL: BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, VEHICLES ETC USING SECTION 5339 FUNDS AT A FEDERAL SHARE OF $200,000 AND LOCAL SHARE OF $50,000. | 9, 10 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 200000 | FY 2023: 50000
TA-5130A | PUBLIC TRANSIT | CONCORD KANNAPOLIS AREA TRANSIT | TO SUPPORT THE PURCHASE OF ROUTINE CAPITAL: BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, VEHICLES ETC USING SECTION 5339 FUNDS AT A FEDERAL SHARE OF $200,000 AND LOCAL SHARE OF $50,000. | 9, 10 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 800000 | FY 2023: 200000
TA-5130B | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | 5339 BUS AND BUS FACILITIES - EXPANSION VEHICLES | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 2900000 | FY 2023: 400000
TA-5130B | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | 5339 BUS AND BUS FACILITIES - EXPANSION VEHICLES | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 726000 | FY 2023: 100000
TA-5139 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (NON-TRADITIONAL) | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 224000 | FY 2023: 25000
TA-5139 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (NON-TRADITIONAL) | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | CAPITAL | 897000 | FY 2023: 100000
TA-5140 | PUBLIC TRANSIT | GORALEIGH | BUS REPLACEMENT | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 2225000
TA-5140 | PUBLIC TRANSIT | GORALEIGH | BUS REPLACEMENT | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 2225000
TA-5140 | PUBLIC TRANSIT | GORALEIGH | BUS REPLACEMENT | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 15250000
TA-5165 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | TA-5165 RURAL VEHICLE REPLACEMENT. | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1036000 | FY 2023: 64000
TA-5165 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | TA-5165 RURAL VEHICLE REPLACEMENT. | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 184000 | FY 2023: 11000
TA-5173 | PUBLIC TRANSIT | RIDER TRANSIT/ CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 | 10 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 6800000
TA-5173 | PUBLIC TRANSIT | RIDER TRANSIT/ CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 | 10 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 850000
TA-5173 | PUBLIC TRANSIT | RIDER TRANSIT/ CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 | 10 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | S | CAPITAL | 850000
TA-5181 | PUBLIC TRANSIT | CITY OF SALISBURY | REPLACMENT BUSES | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 13176000 | FY 2023: 1464000; FY 2024: 1464000
TA-5181 | PUBLIC TRANSIT | CITY OF SALISBURY | REPLACMENT BUSES | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 1647000 | FY 2023: 183000; FY 2024: 183000
TA-5181 | PUBLIC TRANSIT | CITY OF SALISBURY | REPLACMENT BUSES | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 366000
TA-5182 | PUBLIC TRANSIT | CITY OF SALISBURY | EXPANSION VEHICLE (ADA PARATRANSIT, ADMINISTRATION) | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 2240000 | FY 2023: 320000; FY 2024: 320000
TA-5182 | PUBLIC TRANSIT | CITY OF SALISBURY | EXPANSION VEHICLE (ADA PARATRANSIT, ADMINISTRATION) | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 560000 | FY 2023: 80000; FY 2024: 80000
TA-5185 | PUBLIC TRANSIT | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | CAPITAL | 6000
TA-5185 | PUBLIC TRANSIT | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | 5310 | CAPITAL | 50000
TA-5185 | PUBLIC TRANSIT | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | L | CAPITAL | 6000
TA-5186 | PUBLIC TRANSIT | GO RALEIGH | SIX EXPANSION BUSES FOR ADDING ROUTE EXPANSION SERVICE. | 5 | Capital Area MPO | ACQUISITION IN PROGRESS BY GO RALEIGH | DIVISION 5 |  |  |  | 2610000
TA-5202 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | ADA EXPANSION BUS | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 720000
TA-5202 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | ADA EXPANSION BUS | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 1200000
TA-5202 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | ADA EXPANSION BUS | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 2208000 | FY 2023: 109000; FY 2024: 114000
TA-5221 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 972000
TA-5221 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 326000
TA-5221 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 23000
TA-5222 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 1540000
TA-5222 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 167000
TA-5222 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 166000
TA-5223 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 4856000
TA-5223 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 607000
TA-5223 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | S | CAPITAL | 607000
TA-5224 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT TROLLEY | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 700000
TA-5229 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | REPLACEMENT TRANSIT VEHICLE ACQUISITION | 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 36000
TA-5229 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | REPLACEMENT TRANSIT VEHICLE ACQUISITION | 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 144000
TA-6149 | PUBLIC TRANSIT | UNION COUNTY | 5307 FUNDS TO REH/REN EQUIPMENT FFY20-21 (20-SU-089) | 10 | Charlotte Regional TPO | ADD FUNDING TO FY20 | PUBLIC TRANSIT |  | L | CAPITAL | 3000
TA-6149 | PUBLIC TRANSIT | UNION COUNTY | 5307 FUNDS TO REH/REN EQUIPMENT FFY20-21 (20-SU-089) | 10 | Charlotte Regional TPO | ADD FUNDING TO FY20 | PUBLIC TRANSIT |  | 5307 | CAPITAL | 14000
TA-6322 | PUBLIC TRANSIT | LINK TRANSIT | IMPROVEMENTS, BUS SHELTERS, CONSTRUCTION, ENGINEERING AND DESIGN. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 865000 | FY 2023: 400000; FY 2024: 465000
TA-6322 | PUBLIC TRANSIT | LINK TRANSIT | IMPROVEMENTS, BUS SHELTERS, CONSTRUCTION, ENGINEERING AND DESIGN. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 216000 | FY 2023: 108000; FY 2024: 108000
TA-6501 | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REPLACEMENT VAN | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | CAPITAL | 813000 | FY 2023: 36000
TA-6501 | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REPLACEMENT VAN | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 45000 | FY 2023: 5000
TA-6501 | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REPLACEMENT VAN | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 50000 | FY 2023: 5000
TA-6507 | PUBLIC TRANSIT | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | CAPITAL | 2589000 | FY 2023: 184000
TA-6507 | PUBLIC TRANSIT | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 161000 | FY 2023: 23000
TA-6507 | PUBLIC TRANSIT | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 184000 | FY 2023: 23000
TA-6626 | PUBLIC TRANSIT | CITY OF ASHEVILLE | ART BUSES AND OTHER ROUTINE CAPITAL ITEMS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 1451000
TA-6626 | PUBLIC TRANSIT | CITY OF ASHEVILLE | ART BUSES AND OTHER ROUTINE CAPITAL ITEMS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 363000
TA-6665 | PUBLIC TRANSIT | STATEWIDE | 5311 CAPITAL PROJECTS FOR RURAL AREAS | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | 5311 | CAPITAL | 13849000 | FY 2023: 2300000; FY 2024: 6800000
TA-6665 | PUBLIC TRANSIT | STATEWIDE | 5311 CAPITAL PROJECTS FOR RURAL AREAS | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | L | CAPITAL | 1120000 | FY 2023: 120000; FY 2024: 1000000
TA-6665 | PUBLIC TRANSIT | STATEWIDE | 5311 CAPITAL PROJECTS FOR RURAL AREAS | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | S | CAPITAL | 1585000 | FY 2023: 585000; FY 2024: 1000000
TA-6666 | PUBLIC TRANSIT | STATEWIDE | 5339 BUS AND BUS FACILITIES | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 6750000
TA-6668 | PUBLIC TRANSIT | GOTRIANGLE TRANSIT | PURCHASE EXPANSION VEHICLES FOR DRX ROUTE. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN ACQUISITION | REGION C |  |  |  | 2431000
TA-6669 | PUBLIC TRANSIT | GOTRIANGLE TRANSIT | PURCHASE EXPANSION VEHICLES FOR CRX ROUTE. | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN ACQUISITION | REGION C, D |  |  |  | 2431000
TA-6670 | PUBLIC TRANSIT | RANDOLPH- MONTGOMERY RESTORE | PURCHASE ADDITIONAL 20-FOOT LIGHT TRANSIT VEHICLES. | 8 | Piedmont Triad RPO | IN ACQUISITION | REGION E |  |  |  | 70000
TA-6671 | PUBLIC TRANSIT | RANDOLPH- MONTGOMERY RESTORE | PURCHASE 20-FT LIGHT TRANSIT VEHICLES FOR SERVICE EXPANSION. | 8 | Piedmont Triad RPO | IN ACQUISITION | REGION E |  |  |  | 70000
TA-6672 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE 6 BUSES FOR THE UNIVERSITY TO CONCORD MILLS BUS ROUTE. | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS | REGION E |  | O | CAPITAL | 2700000
TA-6672 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE 6 BUSES FOR THE UNIVERSITY TO CONCORD MILLS BUS ROUTE. | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS | REGION E |  | T | CAPITAL | 300000
TA-6673 | PUBLIC TRANSIT | MECKLENBURG COUNTY | EXPAND PARATRANSIT FLEET BY PURCHASING ADDITIONAL BUSES. | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS | DIVISION 10 |  | T | CAPITAL | 250000
TA-6673 | PUBLIC TRANSIT | MECKLENBURG COUNTY | EXPAND PARATRANSIT FLEET BY PURCHASING ADDITIONAL BUSES. | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS | DIVISION 10 |  | O | CAPITAL | 2250000
TA-6674 | PUBLIC TRANSIT | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. | 11 | High Country RPO |  | DIVISION 11 |  | T | CAPITAL | 8000
TA-6674 | PUBLIC TRANSIT | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. | 11 | High Country RPO |  | DIVISION 11 |  | 5311 | CAPITAL | 60000
TA-6674 | PUBLIC TRANSIT | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. | 11 | High Country RPO |  | DIVISION 11 |  | L | CAPITAL | 8000
TA-6681 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 | 9, 11 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO |  | REGION D, F |  |  |  | 47000
TA-6681 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 | 9, 11 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO |  | REGION D, F |  | FEDT | CAPITAL | 372000
TA-6681 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 | 9, 11 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO |  | REGION D, F |  | L | CAPITAL | 47000
TA-6681 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 | 9, 11 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO |  | REGION D, F |  | T | CAPITAL | 47000
TA-6685 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | FEDT | CONSTRUCTION | 392000 | FY 2026: 392000
TA-6685 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | T | CONSTRUCTION | 49000 | FY 2026: 49000
TA-6685 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | L | CONSTRUCTION | 49000 | FY 2026: 49000
TA-6690 | PUBLIC TRANSIT | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | REPLACEMENT VEHICLES | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 397000 | FY 2023: 38000; FY 2024: 38000; FY 2025: 38000; FY 2026: 38000; FY 2027: 38000; FY 2028: 38000
TA-6690 | PUBLIC TRANSIT | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | REPLACEMENT VEHICLES | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 76000 | FY 2023: 7000; FY 2024: 7000; FY 2025: 7000; FY 2026: 7000; FY 2027: 7000; FY 2028: 7000
TA-6700 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADA | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 150000
TA-6700 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADA | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 30000
TA-6701 | PUBLIC TRANSIT | BUNCOMBE MOUNTAIN MOBILITY - | REPLACEMENT VANS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 110000 | FY 2024: 26000
TA-6701 | PUBLIC TRANSIT | BUNCOMBE MOUNTAIN MOBILITY - | REPLACEMENT VANS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 434000 | FY 2024: 100000
TA-6703 | PUBLIC TRANSIT | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT LO-NO TRANSIT VEHICLE PURCHASE | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 1453000
TA-6703 | PUBLIC TRANSIT | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT LO-NO TRANSIT VEHICLE PURCHASE | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 5117000
TA-6706 | PUBLIC TRANSIT | CHARLOTTE REGIONAL | INNOVATIVE COORDINATED ACCESS AND MOBILITY PILOT PROGRAM VEHICLES | 10 | Charlotte Regional TPO | ADD PROJECT TA-6706 TO STIP FOR FY 20. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF CRTPO MPO | PUBLIC TRANSIT |  | 5310 | CAPITAL | 112000
TA-6706 | PUBLIC TRANSIT | CHARLOTTE REGIONAL | INNOVATIVE COORDINATED ACCESS AND MOBILITY PILOT PROGRAM VEHICLES | 10 | Charlotte Regional TPO | ADD PROJECT TA-6706 TO STIP FOR FY 20. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF CRTPO MPO | PUBLIC TRANSIT |  | L | CAPITAL | 28000
TA-6707 | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | 12 | Greater Hickory MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2352000 | FY 2023: 336000; FY 2024: 336000; FY 2025: 336000
TA-6707 | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | 12 | Greater Hickory MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 588000 | FY 2023: 84000; FY 2024: 84000; FY 2025: 84000
TA-6708 | PUBLIC TRANSIT | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES | 12 | Greater Hickory MPO | FUNDING ADDED TO FY 21 AT THE REQUEST OF THE MPO (FUNDING UNCHANGED IN FY 20 ALREADY FLEXED FROM CMAQ TO FUZ) | PUBLIC TRANSIT |  | L | CAPITAL | 90000
TA-6708 | PUBLIC TRANSIT | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES | 12 | Greater Hickory MPO | FUNDING ADDED TO FY 21 AT THE REQUEST OF THE MPO (FUNDING UNCHANGED IN FY 20 ALREADY FLEXED FROM CMAQ TO FUZ) | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2361000
TA-6708 | PUBLIC TRANSIT | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES | 12 | Greater Hickory MPO | FUNDING ADDED TO FY 21 AT THE REQUEST OF THE MPO (FUNDING UNCHANGED IN FY 20 ALREADY FLEXED FROM CMAQ TO FUZ) | PUBLIC TRANSIT |  | 5307 | CAPITAL | 360000
TA-6708 | PUBLIC TRANSIT | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES | 12 | Greater Hickory MPO | FUNDING ADDED TO FY 21 AT THE REQUEST OF THE MPO (FUNDING UNCHANGED IN FY 20 ALREADY FLEXED FROM CMAQ TO FUZ) | PUBLIC TRANSIT |  | L | CAPITAL | 116000
TA-6709 | PUBLIC TRANSIT | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES LIGHT TRANSIT VEHICLE | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2476000 | FY 2023: 545000
TA-6709 | PUBLIC TRANSIT | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES LIGHT TRANSIT VEHICLE | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | CAPITAL | 619000 | FY 2023: 136000
TA-6711 | PUBLIC TRANSIT | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. | 5 | Kerr-Tar RPO |  | REGION C |  | FEDT | CAPITAL | 44000
TA-6711 | PUBLIC TRANSIT | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. | 5 | Kerr-Tar RPO |  | REGION C |  | L | CAPITAL | 6000
TA-6711 | PUBLIC TRANSIT | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. | 5 | Kerr-Tar RPO |  | REGION C |  | T | CAPITAL | 6000
TA-6713 | PUBLIC TRANSIT | ICATS INTERCOUNTY EXPRESS BUS | PURCHASE 3 OVER-THE-ROAD COACH BUSES AND 5 SETS OF BUS STOP SHELTERS TO EXPAND INTERCOUNTY SERVICE BETWEEN STATESVILLE, TROUTMAN, MOORESVILLE, AND CATS ROUTES BETWEEN HUNTERSVILLE AND CHARLOTTE. | 10, 12 | Charlotte Regional TPO |  | REGION E, F |  | T | CONSTRUCTION | 1000000
TA-6714 | PUBLIC TRANSIT | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE | 7 | Greensboro Urban Area MPO | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT | PUBLIC TRANSIT |  | L | CAPITAL | 531000 | FY 2023: 531000
TA-6714 | PUBLIC TRANSIT | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE | 7 | Greensboro Urban Area MPO | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT | PUBLIC TRANSIT |  | 5339 | CAPITAL | 3009000 | FY 2023: 3009000
TA-6714 | PUBLIC TRANSIT | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE | 7 | Greensboro Urban Area MPO | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT | PUBLIC TRANSIT |  | CMAQ | CAPITAL | 1145000 | FY 2024: 1145000
TA-6717 | PUBLIC TRANSIT | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | 2 | Down East RPO |  | DIVISION 2 |  | 5311 | CONSTRUCTION | 56000
TA-6717 | PUBLIC TRANSIT | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | 2 | Down East RPO |  | DIVISION 2 |  | L | CONSTRUCTION | 7000
TA-6717 | PUBLIC TRANSIT | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | 2 | Down East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 7000
TA-6718 | PUBLIC TRANSIT | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | 2 | Down East RPO |  | DIVISION 2 |  | L | CONSTRUCTION | 7000
TA-6718 | PUBLIC TRANSIT | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | 2 | Down East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 7000
TA-6718 | PUBLIC TRANSIT | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | 2 | Down East RPO |  | DIVISION 2 |  | 5311 | CONSTRUCTION | 56000
TA-6719 | PUBLIC TRANSIT | VARIOUS | CHATHAM TRANSIT NETWORK. PURCHASE 3 NEW RAMP-EQIPPED MINIVANS. | 8 | Triangle Area RPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 8 |  | T | CAPITAL | 127000
TA-6719 | PUBLIC TRANSIT | VARIOUS | CHATHAM TRANSIT NETWORK. PURCHASE 3 NEW RAMP-EQIPPED MINIVANS. | 8 | Triangle Area RPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 8 |  | L | CAPITAL | 14000
TA-6720 | PUBLIC TRANSIT | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. | 4 | Upper Coastal Plain RPO, Capital Area MPO |  | DIVISION 4 |  | 5311 | CONSTRUCTION | 264000 | FY 2026: 264000
TA-6720 | PUBLIC TRANSIT | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. | 4 | Upper Coastal Plain RPO, Capital Area MPO |  | DIVISION 4 |  | L | CONSTRUCTION | 33000 | FY 2026: 33000
TA-6720 | PUBLIC TRANSIT | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. | 4 | Upper Coastal Plain RPO, Capital Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 33000 | FY 2026: 33000
TA-6721 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | PURCHASE TWO (2) LIGHT TRANSIT VEHICLES | 7 | Triangle Area RPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | CAPITAL | 11000
TA-6721 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | PURCHASE TWO (2) LIGHT TRANSIT VEHICLES | 7 | Triangle Area RPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | T | CAPITAL | 98000
TA-6722 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE VEHICLES FOR VANPOOL FLEET EXPANSION. | 7, 8, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO, High Point Urban Area MPO |  | DIVISION 7, 8, 9 |  | T | CONSTRUCTION | 90000
TA-6722 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE VEHICLES FOR VANPOOL FLEET EXPANSION. | 7, 8, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO, High Point Urban Area MPO |  | DIVISION 7, 8, 9 |  | L | CONSTRUCTION | 10000
TA-6723 | PUBLIC TRANSIT | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | DIVISION 13 |  | T | CONSTRUCTION | 2150000 | FY 2024: 2150000
TA-6723 | PUBLIC TRANSIT | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | DIVISION 13 |  | T | ENGINEERING | 100000 | FY 2023: 100000
TA-6723 | PUBLIC TRANSIT | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | DIVISION 13 |  | L | ENGINEERING | 11000 | FY 2023: 11000
TA-6723 | PUBLIC TRANSIT | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | DIVISION 13 |  | L | CONSTRUCTION | 239000 | FY 2024: 239000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | L | RIGHT-OF-WAY | 98000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | S(M) | CONSTRUCTION | 1560000 | FY 2023: 1560000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | S(M) | RIGHT-OF-WAY | 104000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | S(M) | RIGHT-OF-WAY | 73000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | BGDA | ENGINEERING | 1121000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | S(M) | ENGINEERING | 238000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | L | CONSTRUCTION | 991000 | FY 2023: 991000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | L | RIGHT-OF-WAY | 29000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | L | ENGINEERING | 151000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | CMAQ | CONSTRUCTION | 7354000 | FY 2023: 7354000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 663000
TA-6724 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS | DIVISION 10 |  | CMAQ | RIGHT-OF-WAY | 290000
TA-6729 | PUBLIC TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES | 7 | High Point Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 400000
TA-6729 | PUBLIC TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES | 7 | High Point Urban Area MPO |  | PUBLIC TRANSIT |  | CMAQ | CAPITAL | 400000
TA-6729 | PUBLIC TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES | 7 | High Point Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 200000
TA-6731 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | PURCHASE NEW BUS < 30'. | 7 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 11000
TA-6731 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | PURCHASE NEW BUS < 30'. | 7 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | FED | CAPITAL | 45000
TA-6732 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | VEHICLE REPLACEMENT AND EXPANSION | 7 | Greensboro Urban Area MPO | PROJECT ADDED AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | 5339 | CONSTRUCTION | 6780000
TA-6732 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | VEHICLE REPLACEMENT AND EXPANSION | 7 | Greensboro Urban Area MPO | PROJECT ADDED AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | L | CONSTRUCTION | 1700000
TA-6733 | PUBLIC TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | 5307 | CAPITAL | 3629000 | FY 2023: 2600000
TA-6733 | PUBLIC TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | 5307 | PLANNING | 200000 | FY 2023: 120000; FY 2024: 80000
TA-6733 | PUBLIC TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | L | CAPITAL | 5526000 | FY 2023: 5320000
TA-6733 | PUBLIC TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | L | PLANNING | 50000 | FY 2023: 30000; FY 2024: 20000
TC-0003 | PUBLIC TRANSIT | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | CAPITAL | 137000 | FY 2023: 137000
TC-0003 | PUBLIC TRANSIT | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | CAPITAL | 137000 | FY 2023: 137000
TC-0003 | PUBLIC TRANSIT | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | CAPITAL | 1097000 | FY 2023: 1097000
TC-0005 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | CONSTRUCTION | 550000
TC-0005 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5339 | CONSTRUCTION | 2100000
TC-0006 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5339 | CONSTRUCTION | 1435000
TC-0006 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | CONSTRUCTION | 384000
TC-0007 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR CONSTRUCTION PROJECT | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5339 | CAPITAL | 3189000 | FY 2023: 2000000
TC-0007 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR CONSTRUCTION PROJECT | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | CAPITAL | 787000 | FY 2023: 490000
TC-0008 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | CAPITAL | 2300000 | FY 2023: 1300000
TC-0008 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5339 | CAPITAL | 8600000 | FY 2023: 4600000
TC-0010 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | CONSTRUCTION | 834000
TC-0010 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5339 | CONSTRUCTION | 3235000
TC-0011 | PUBLIC TRANSIT | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5339 | CONSTRUCTION | 719000 | FY 2023: 719000
TC-0011 | PUBLIC TRANSIT | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5339 | CAPITAL | 6391000
TC-0011 | PUBLIC TRANSIT | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | CAPITAL | 2298000
TC-0012 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT TO PURCHASE ELECTRIC BUSES AND CHARGING STATIONS. | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5339 | CAPITAL | 2994000
TC-0012 | PUBLIC TRANSIT | STATEWIDE | 5339(b) DISCRETIONARY GRANT TO PURCHASE ELECTRIC BUSES AND CHARGING STATIONS. | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | CAPITAL | 773000
TC-0013 | PUBLIC TRANSIT | STATEWIDE | MOBILITY FROM ALL GRANT OPPORTUNITY FROM THE FTA.5310 DISCRETIONARY GRANT AWARDED BY FTA. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5310 | CAPITAL | 280000
TC-0013 | PUBLIC TRANSIT | STATEWIDE | MOBILITY FROM ALL GRANT OPPORTUNITY FROM THE FTA.5310 DISCRETIONARY GRANT AWARDED BY FTA. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | CAPITAL | 70000
TC-0014 | PUBLIC TRANSIT | CATS | EXPANSION VANPOOL | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND | PUBLIC TRANSIT |  | L | CAPITAL | 17000
TC-0014 | PUBLIC TRANSIT | CATS | EXPANSION VANPOOL | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND | PUBLIC TRANSIT |  | S | CAPITAL | 17000
TC-0014 | PUBLIC TRANSIT | CATS | EXPANSION VANPOOL | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND | PUBLIC TRANSIT |  | 5307 | CAPITAL | 140000
TC-0015 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH CAPITAL PROJECTS (PASSENGER AMENITIES, PEDESTRIAN CONNECTIONS, FACILITY MAINTENANCE, UPGRADE AND UPKEEPS ETC) | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 9106000
TC-0015 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH CAPITAL PROJECTS (PASSENGER AMENITIES, PEDESTRIAN CONNECTIONS, FACILITY MAINTENANCE, UPGRADE AND UPKEEPS ETC) | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 1816000
TC-0016 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | CONSTRUCTION | 275000
TC-0016 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | RIGHT-OF-WAY | 6000
TC-0016 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | ENGINEERING | 55000
TC-0016 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | ENGINEERING | 55000
TC-0016 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 275000
TC-0016 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | RIGHT-OF-WAY | 6000
TC-0017 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | ENGINEERING | 65000
TC-0017 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | RIGHT-OF-WAY | 7000
TC-0017 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 165000
TC-0017 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | RIGHT-OF-WAY | 7000
TC-0017 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | ENGINEERING | 65000
TC-0017 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | CONSTRUCTION | 165000
TC-0018 | PUBLIC TRANSIT | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL AND URBAN AREAS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | CAPITAL | 1118000 | FY 2023: 404000; FY 2024: 350000
TC-0018 | PUBLIC TRANSIT | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL AND URBAN AREAS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | CAPITAL | 1026000 | FY 2023: 360000; FY 2024: 325000
TC-0018 | PUBLIC TRANSIT | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL AND URBAN AREAS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5310 | CAPITAL | 5811000 | FY 2023: 2929000; FY 2024: 2607000
TC-0019 | PUBLIC TRANSIT | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | CAPITAL | 1715000
TC-0019 | PUBLIC TRANSIT | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | CAPITAL | 13717000
TC-0019 | PUBLIC TRANSIT | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | CAPITAL | 1715000
TC-0020 | PUBLIC TRANSIT | NCDOT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON FY 24 GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | CAPITAL | 65000 | FY 2023: 35000; FY 2024: 30000
TC-0020 | PUBLIC TRANSIT | NCDOT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON FY 24 GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5309 | CAPITAL | 320000 | FY 2023: 100000; FY 2024: 220000
TC-0020 | PUBLIC TRANSIT | NCDOT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON FY 24 GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | CAPITAL | 40000 | FY 2023: 10000; FY 2024: 30000
TC-0021 | PUBLIC TRANSIT | NCDOT | 5339 STATEWIDE RURAL | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 6726000 | FY 2023: 1370000; FY 2024: 820000
TC-0021 | PUBLIC TRANSIT | NCDOT | 5339 STATEWIDE RURAL | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | BGDA | PLANNING | 273000
TC-0021 | PUBLIC TRANSIT | NCDOT | 5339 STATEWIDE RURAL | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | CAPITAL | 777000 | FY 2023: 100000; FY 2024: 110000
TC-0021 | PUBLIC TRANSIT | NCDOT | 5339 STATEWIDE RURAL | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | CAPITAL | 1402000 | FY 2023: 1292000; FY 2024: 110000
TC-0022 | PUBLIC TRANSIT | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | ADTAP | CAPITAL | 1504000
TC-0022 | PUBLIC TRANSIT | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | CAPITAL | 188000
TC-0022 | PUBLIC TRANSIT | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | CAPITAL | 188000
TC-0023 | PUBLIC TRANSIT | SALISBURY TRANSIT ( CITY OF SALISBURY) | REPLACE FOUR TRANSIT BUSES THAT HAVE EXCEEDED THEIR USEFUL LIFE, AND REPLACE VEHICLE RELATED EQUIPMENT SUCH AS FARE BOXES, DESTINATION SIGNS, CAMERA SYSTEMS, AND AUTOMATED VOICE ANNUNCIATION SYSTEMS. | 9 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | 5339(b) | CAPITAL | 3840000 | FY 2023: 640000; FY 2024: 640000; FY 2025: 640000; FY 2026: 640000
TC-0023 | PUBLIC TRANSIT | SALISBURY TRANSIT ( CITY OF SALISBURY) | REPLACE FOUR TRANSIT BUSES THAT HAVE EXCEEDED THEIR USEFUL LIFE, AND REPLACE VEHICLE RELATED EQUIPMENT SUCH AS FARE BOXES, DESTINATION SIGNS, CAMERA SYSTEMS, AND AUTOMATED VOICE ANNUNCIATION SYSTEMS. | 9 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 720000 | FY 2023: 120000; FY 2024: 120000; FY 2025: 120000; FY 2026: 120000
TC-0024 | PUBLIC TRANSIT | CATS | CITY LYNX GOLD LINE - AMERICAN RESCUE PLAN SMALL STARTS | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | 5309 | CAPITAL | 11122000
TC-0026 | PUBLIC TRANSIT | NCDOT | FEDERAL AMERICAN RESCUE PLAN (ARP) FUNDS FOR CAPITAL | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | ARP | CAPITAL | 500000 | FY 2023: 500000
TC-0027 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | BGDA | PLANNING | 339000 | FY 2023: 339000
TC-0027 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 85000 | FY 2023: 85000
TC-5004 | PUBLIC TRANSIT | STATEWIDE | 5311 ADTAP | 99 | STATEWIDE PROJECT | FUMODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | ADTAP | CAPITAL | 3392000
TC-5100 | PUBLIC TRANSIT | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | MOBILITY MANAGEMENT | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 168000 | FY 2023: 24000
TC-5100 | PUBLIC TRANSIT | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | MOBILITY MANAGEMENT | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 42000 | FY 2023: 6000
TD-4701 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 45971000 | FY 2023: 2930000; FY 2024: 2928000; FY 2025: 2926000
TD-4701 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CONSTRUCTION | 3660000 | FY 2023: 366000; FY 2024: 366000; FY 2025: 366000
TD-4701 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CONSTRUCTION | 3660000 | FY 2023: 366000; FY 2024: 366000; FY 2025: 366000
TD-4702 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - TRANSIT CENTER - UPGRADES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 4666000 | FY 2023: 96000; FY 2024: 96000; FY 2025: 96000
TD-4702 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - TRANSIT CENTER - UPGRADES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CONSTRUCTION | 127000 | FY 2023: 12000; FY 2024: 12000; FY 2025: 12000
TD-4702 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - TRANSIT CENTER - UPGRADES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CONSTRUCTION | 127000 | FY 2023: 12000; FY 2024: 12000; FY 2025: 12000
TD-4904 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  |  |  | 755000
TD-4904 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | 5307 | CONSTRUCTION | 4950000
TD-4904 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | 5309 | CONSTRUCTION | 4500000
TD-4904 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 1310000
TD-4904 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | T | CONSTRUCTION | 295000
TD-4912 | PUBLIC TRANSIT | GO RALEIGH TRANSIT | US 64 BUSINESS (NEW HOPE ROAD) IN RALEIGH. CONSTRUCT TRANSFER FACILITY. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY GO RALEIGH | DIVISION 5 |  |  |  | 880000
TD-5155 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | 1 REPLACEMENT LTV (25') AND RADIO, VEHICLE LETTERING AND LOGOS, AND ON-BOARD CAMERA. | 7 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY ORANGE PUBLIC TRANSIT | DIVISION 7 |  | L | CAPITAL | 15000
TD-5155 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | 1 REPLACEMENT LTV (25') AND RADIO, VEHICLE LETTERING AND LOGOS, AND ON-BOARD CAMERA. | 7 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY ORANGE PUBLIC TRANSIT | DIVISION 7 |  |  |  | 77000
TD-5155 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | 1 REPLACEMENT LTV (25') AND RADIO, VEHICLE LETTERING AND LOGOS, AND ON-BOARD CAMERA. | 7 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY ORANGE PUBLIC TRANSIT | DIVISION 7 |  | BGDA | CAPITAL | 62000
TD-5264 | PUBLIC TRANSIT | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 20000000 | FY 2023: 20000000
TD-5264 | PUBLIC TRANSIT | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | T | CONSTRUCTION | 700000 | FY 2023: 700000
TD-5264B | PUBLIC TRANSIT | CARY TRANSIT / C-TRAN | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | CONSTRUCTION | 700000
TD-5264B | PUBLIC TRANSIT | CARY TRANSIT / C-TRAN | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | 5 | Capital Area MPO |  | DIVISION 5 |  |  |  | 88000
TD-5264B | PUBLIC TRANSIT | CARY TRANSIT / C-TRAN | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | 5 | Capital Area MPO |  | DIVISION 5 |  | FEDT | CONSTRUCTION | 5600000
TD-5264B | PUBLIC TRANSIT | CARY TRANSIT / C-TRAN | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 700000
TD-5269 | PUBLIC TRANSIT | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | DIVISION 5 |  | T | CONSTRUCTION | 8860000 | FY 2025: 2215000; FY 2026: 2215000; FY 2027: 2215000; FY 2028: 2215000
TD-5269 | PUBLIC TRANSIT | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | DIVISION 5 |  | DP | CONSTRUCTION | 20000000
TD-5269 | PUBLIC TRANSIT | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | DIVISION 5 |  | O | CONSTRUCTION | 24300000
TD-5273 | PUBLIC TRANSIT | GO TRIANGLE TRANSIT | ROUGEMONT PARK-AND-RIDE. PROFESSIONAL SERVICES AND PROPERTY ACQUISITION. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY TRIANGLE TRANSIT | EXEMPT |  |  |  | 249000
TD-5273 | PUBLIC TRANSIT | GO TRIANGLE TRANSIT | ROUGEMONT PARK-AND-RIDE. PROFESSIONAL SERVICES AND PROPERTY ACQUISITION. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY TRIANGLE TRANSIT | EXEMPT |  | BGDA | CONSTRUCTION | 116000 | FY 2023: 116000
TD-5273 | PUBLIC TRANSIT | GO TRIANGLE TRANSIT | ROUGEMONT PARK-AND-RIDE. PROFESSIONAL SERVICES AND PROPERTY ACQUISITION. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY TRIANGLE TRANSIT | EXEMPT |  | L | CONSTRUCTION | 61000 | FY 2023: 61000
TD-5279 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT | 7 | Greensboro Urban Area MPO | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | L | CAPITAL | 373000
TD-5279 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT | 7 | Greensboro Urban Area MPO | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | S | CAPITAL | 373000
TD-5279 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT | 7 | Greensboro Urban Area MPO | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  |  |  | 1440000
TD-5279 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT | 7 | Greensboro Urban Area MPO | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | 5339 | CAPITAL | 1538000
TD-5281 | PUBLIC TRANSIT | TAR RIVER TRANSIT | ENLARGE DRIVERS BREAKROOM | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | T | CAPITAL | 15000 | FY 2025: 15000
TD-5283 | PUBLIC TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | BUILDING / FACILITY RENOVATION AND UPGRADE FOR PARATRANSIT ADMINISTRATION. | 7 | High Point Urban Area MPO | N PROGRESS | REGION D |  |  |  | 300000
TD-5284 | PUBLIC TRANSIT | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  | 5307 | CONSTRUCTION | 288000 | FY 2024: 288000
TD-5284 | PUBLIC TRANSIT | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  | L | CONSTRUCTION | 36000 | FY 2024: 36000
TD-5284 | PUBLIC TRANSIT | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX | 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION D |  | T | CONSTRUCTION | 36000 | FY 2024: 36000
TD-5285 | PUBLIC TRANSIT | GO TRIANGLE | EXPAND EXISTING GARAGE FACILITY IN MORRISVILLE. | 5 | Capital Area MPO | IN PROGRESS | REGION C |  |  |  | 15300000
TD-5286 | PUBLIC TRANSIT | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | 5307 | CONSTRUCTION | 1272000
TD-5286 | PUBLIC TRANSIT | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | L | CONSTRUCTION | 159000
TD-5286 | PUBLIC TRANSIT | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | T | CONSTRUCTION | 159000
TD-5287 | PUBLIC TRANSIT | GO TRIANGLE | PARK AND RIDE LOT AT SR 1774 (DISTRICT DRIVE). ADD SPACES, IMPROVE LIGHTING AND CONSTRUCT SHELTERS. | 5 | Capital Area MPO | IN PROGRESS | REGION C |  |  |  | 720000
TD-5293 | PUBLIC TRANSIT | GO RALEIGH | INTERSECTION OF SR 2298 (EDENTON STREET) AND NORTH SALISBURY STREET IN RALEIGH. CONSTRUCT BUS STOP SHELTER. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY GO TRIANGLE | REGION C |  |  |  | 44000
TD-5294 | PUBLIC TRANSIT | GO TRIANGLE | NC 98 (HOLLOWAY STREET) TRANSIT CORRIDOR. CONSTRUCT ACCESS AND BUS STOP IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY GO TRIANGLE | REGION C |  |  |  | 1166000
TD-5295 | PUBLIC TRANSIT | GO TRIANGLE | TOWN OF HILLSBOROUGH. CONSTRUCT PARK-AND-RIDE LOT. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY GO TRIANGLE | REGION D |  |  |  | 1200000
TD-5295 | PUBLIC TRANSIT | GO TRIANGLE | TOWN OF HILLSBOROUGH. CONSTRUCT PARK-AND-RIDE LOT. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY GO TRIANGLE | REGION D |  | L | CONSTRUCTION | 800000 | FY 2023: 800000
TD-5295 | PUBLIC TRANSIT | GO TRIANGLE | TOWN OF HILLSBOROUGH. CONSTRUCT PARK-AND-RIDE LOT. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY GO TRIANGLE | REGION D |  | S | CONSTRUCTION | 120000 | FY 2023: 120000
TD-5302 | PUBLIC TRANSIT | CITY OF SALISBURY | PREVENTIVE MAINTENANCE FOR BUS AND BUS FACILITY, FACILITY IMPROVEMENTS AND REPAIRS, AUTOMATIC BUS WASHER, SHOP EQUIPMENT, FUELING SYSTEM, SECURITY GATE UPGRADE, | 9 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 2268000 | FY 2023: 324000; FY 2024: 324000
TD-5302 | PUBLIC TRANSIT | CITY OF SALISBURY | PREVENTIVE MAINTENANCE FOR BUS AND BUS FACILITY, FACILITY IMPROVEMENTS AND REPAIRS, AUTOMATIC BUS WASHER, SHOP EQUIPMENT, FUELING SYSTEM, SECURITY GATE UPGRADE, | 9 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 567000 | FY 2023: 81000; FY 2024: 81000
TD-5303 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5339 BUS AND BUS FACILITIES GRANT | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 7010000 | FY 2023: 620000; FY 2024: 620000; FY 2025: 620000; FY 2026: 620000; FY 2027: 620000
TD-5303 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5339 BUS AND BUS FACILITIES GRANT | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 1302000 | FY 2023: 110000; FY 2024: 110000; FY 2025: 110000; FY 2026: 110000; FY 2027: 110000
TD-5304 | PUBLIC TRANSIT | GORALEIGH | BUS STOP IMPROVEMENTS | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 3273000 | FY 2023: 1273000
TD-5305 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | DOWNTOWN CARY MULTI-MODAL FACILITY. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  |  |  | 2500000
TD-5305 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | DOWNTOWN CARY MULTI-MODAL FACILITY. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 44200000 | FY 2023: 24000000; FY 2024: 20000000
TD-5307 | PUBLIC TRANSIT | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 1500000 | FY 2027: 1500000
TD-5307 | PUBLIC TRANSIT | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 3158000 | FY 2028: 3158000
TD-5307 | PUBLIC TRANSIT | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | 5 | Capital Area MPO |  | DIVISION 5 |  | O | CONSTRUCTION | 1750000 | FY 2028: 875000; FY 2029: 875000
TD-5307 | PUBLIC TRANSIT | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | CONSTRUCTION | 1750000 | FY 2028: 875000; FY 2029: 875000
TD-5308 | PUBLIC TRANSIT | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | RIGHT-OF-WAY | 2750000
TD-5308 | PUBLIC TRANSIT | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 4350000
TD-5308 | PUBLIC TRANSIT | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 13800000 | FY 2023: 13800000
TD-5309 | PUBLIC TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SITES IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE PE | 5 | Capital Area MPO |  | DIVISION 5 |  | L | ENGINEERING | 151000
TD-5309 | PUBLIC TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SITES IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE PE | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | ENGINEERING | 601000
TD-5309A | PUBLIC TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOPS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE ROW | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 200000
TD-5309A | PUBLIC TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOPS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE ROW | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 50000
TD-5309B | PUBLIC TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SIGHTS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE CON | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 1200000
TD-5309B | PUBLIC TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SIGHTS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE CON | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 300000
TD-5314 | PUBLIC TRANSIT | GOTRIANGLE | EXISTING PARK AND RIDE IMPROVEMENTS | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 1105000 | FY 2023: 640000; FY 2024: 355000; FY 2025: 57000
TD-5315 | PUBLIC TRANSIT | GOTRIANGLE | BUILD NEW PARK AND RIDE AT HILLSBOROUGH ST AND I-440 IN RALEIGH. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 5200000 | FY 2023: 5200000
TD-5315 | PUBLIC TRANSIT | GOTRIANGLE | BUILD NEW PARK AND RIDE AT HILLSBOROUGH ST AND I-440 IN RALEIGH. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | ENGINEERING | 2220000
TD-5316 | PUBLIC TRANSIT | GOTRIANGLE | BUILD NEW PARK AND RIDE AT CREEDMOOR AND I-540 OR AT FALLS OF NEUSE AND I-540 IN RALEIGH. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 1500000 | FY 2024: 1500000
TD-5316 | PUBLIC TRANSIT | GOTRIANGLE | BUILD NEW PARK AND RIDE AT CREEDMOOR AND I-540 OR AT FALLS OF NEUSE AND I-540 IN RALEIGH. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | ENGINEERING | 1100000 | FY 2023: 1100000
TD-5317 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH CONSTRUCTION OF PARK AND RIDE IN ROLESVILLE. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 55000
TD-5318 | PUBLIC TRANSIT | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 2989000 | FY 2025: 2989000
TD-5318 | PUBLIC TRANSIT | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | ENGINEERING | 547000 | FY 2024: 547000
TD-5318 | PUBLIC TRANSIT | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | RIGHT-OF-WAY | 2249000 | FY 2024: 562000; FY 2025: 1125000; FY 2026: 562000
TD-5319 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT CRABTREE VALLEY MALL | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 324000
TD-5320 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT TRIANGLE TOWNE CENTER | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 324000
TD-6322 | PUBLIC TRANSIT | BURLINGTON | CAPITAL FOR PEDESTRIAN IMPROVEMENTS FOR FIXED ROUTR SERVICES | 7 | Burlington-Graham MPO | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | 5307 | CAPITAL | 50000
TD-6322 | PUBLIC TRANSIT | BURLINGTON | CAPITAL FOR PEDESTRIAN IMPROVEMENTS FOR FIXED ROUTR SERVICES | 7 | Burlington-Graham MPO | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | L | CAPITAL | 10000
TE-4901 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5309 | CONSTRUCTION | 820908000
TE-4901 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CONSTRUCTION | 93279000
TE-4901 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CONSTRUCTION | 191328000
TE-4902 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 800000
TE-4902 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CONSTRUCTION | 100000
TE-4902 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | FED | CONSTRUCTION | 48068000
TE-4902 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CONSTRUCTION | 100000
TE-4903A | PUBLIC TRANSIT | AUTHORITY TRIANGLE TRANSIT | FIXED GUIDEWAY - LIGHT RAIL SERVICE- CARY/RALEIGH | 5, 7 | Capital Area MPO |  | PUBLIC TRANSIT |  | FED | CONSTRUCTION | 1502000000
TE-4903B | PUBLIC TRANSIT | AUTHORITY TRIANGLE TRANSIT | FIXED GUIDEWAY - COMMUTER RAIL SERVICE- DURHAM/RALEIGH | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | FED | CONSTRUCTION | 666000
TG-0002 | PUBLIC TRANSIT | STATEWIDE | FY21 5307 SBUS CAPITAL | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | CAPITAL | 21000
TG-0004 | PUBLIC TRANSIT | STATEWIDE | FY21 5307 SBUS CAPITAL | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | CAPITAL | 168000
TG-0005 | PUBLIC TRANSIT | STATEWIDE | FY21 5307 SBUS CAPITAL | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | CAPITAL | 168000
TG-0006 | PUBLIC TRANSIT | STATEWIDE | FY21 5307 SBUS CAPITAL | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | CAPITAL | 52000 | FY 2023: 52000
TG-0006 | PUBLIC TRANSIT | STATEWIDE | FY21 5307 SBUS CAPITAL | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | CAPITAL | 329000 | FY 2023: 207000
TG-0010 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE BATTERY ELECTRIC BUSES, CHARGING STATIONS, ONSITE TRAINING AND STARTUP SUPPORT AND TESTING | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 3724000
TG-0010 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE BATTERY ELECTRIC BUSES, CHARGING STATIONS, ONSITE TRAINING AND STARTUP SUPPORT AND TESTING | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 3724000
TG-0011 | PUBLIC TRANSIT | CITY OF ASHEVILLE | BUSES AND BUS FACILITIES - BUS STOP IMPROVEMENT PROGRAM | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5339 | CAPITAL | 1000000
TG-0011 | PUBLIC TRANSIT | CITY OF ASHEVILLE | BUSES AND BUS FACILITIES - BUS STOP IMPROVEMENT PROGRAM | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 250000
TG-0012 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | ROUTINE CAPITAL/PREVENTATIVE, MAINTENANCE/PASSENGER AMENITITES/MOBILITY MANAGEMENT | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 150000 | FY 2023: 25000; FY 2024: 25000; FY 2025: 25000; FY 2026: 25000; FY 2027: 25000; FY 2028: 25000
TG-0012 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | ROUTINE CAPITAL/PREVENTATIVE, MAINTENANCE/PASSENGER AMENITITES/MOBILITY MANAGEMENT | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 600000 | FY 2023: 100000; FY 2024: 100000; FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
TG-0013 | PUBLIC TRANSIT | GORALEIGH | FIXED ROUTE PREVENTATIVE MAINTENANCE | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 7680000
TG-0013 | PUBLIC TRANSIT | GORALEIGH | FIXED ROUTE PREVENTATIVE MAINTENANCE | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 1920000
TG-0015 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH CAPITAL PROJECTS. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 4401000
TG-4726 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 29710000 | FY 2023: 2680000; FY 2024: 2746000; FY 2025: 2815000
TG-4726 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | FMOD | CAPITAL | 1250000
TG-4726 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 4858000 | FY 2023: 670000; FY 2024: 687000; FY 2025: 704000
TG-4729B | PUBLIC TRANSIT | GORALEIGH | GORALEIGH ADA PARATRANSIT SERVICE. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 2500000
TG-4729B | PUBLIC TRANSIT | GORALEIGH | GORALEIGH ADA PARATRANSIT SERVICE. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 2500000
TG-4731B | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | PREVENTIVE MAINTENANCE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 3720000 | FY 2023: 269000
TG-4731B | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | PREVENTIVE MAINTENANCE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 24837000 | FY 2023: 1074000
TG-4732A | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 3488000
TG-4732A | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 432000
TG-4732B | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 810000 | FY 2023: 157000
TG-4732B | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 78000 | FY 2023: 39000
TG-4738 | PUBLIC TRANSIT | AUTHORITY DURHAM AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 926000
TG-4738 | PUBLIC TRANSIT | AUTHORITY DURHAM AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | CMAQ | CAPITAL | 260000
TG-4738 | PUBLIC TRANSIT | AUTHORITY DURHAM AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 6927000 | FY 2023: 475000
TG-4738 | PUBLIC TRANSIT | AUTHORITY DURHAM AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 952000 | FY 2023: 119000
TG-4738A | PUBLIC TRANSIT | AUTHORITY DURHAM AREA TRANSIT | PREVENTIVE MAINTENANCE | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 45860000 | FY 2023: 3000000
TG-4738A | PUBLIC TRANSIT | AUTHORITY DURHAM AREA TRANSIT | PREVENTIVE MAINTENANCE | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 6000000 | FY 2023: 750000
TG-4752A | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 607000 | FY 2023: 24000
TG-4752A | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 48000 | FY 2023: 6000
TG-4752B | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | PREVENTIVE MAINTENANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 414000 | FY 2023: 50000
TG-4752B | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | PREVENTIVE MAINTENANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 2468000 | FY 2023: 201000
TG-4752C | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 280000 | FY 2023: 35000
TG-4752C | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1774000 | FY 2023: 140000
TG-4759 | PUBLIC TRANSIT | GREENSBORO TRANSIT AGENCY | PREVENTIVE MAINTENANCE | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 25073000 | FY 2023: 3103000; FY 2024: 3103000; FY 2025: 3103000; FY 2026: 3103000; FY 2027: 3103000; FY 2028: 3103000
TG-4759 | PUBLIC TRANSIT | GREENSBORO TRANSIT AGENCY | PREVENTIVE MAINTENANCE | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 6270000 | FY 2023: 776000; FY 2024: 776000; FY 2025: 776000; FY 2026: 776000; FY 2027: 776000; FY 2028: 776000
TG-4767 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 6800000 | FY 2023: 481000
TG-4767 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 938000 | FY 2023: 120000
TG-4774 | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 80000 | FY 2023: 10000
TG-4774 | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 658000 | FY 2023: 40000
TG-4774A | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | PREVENTIVE MAINTENANCE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 5225000 | FY 2023: 500000
TG-4774A | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | PREVENTIVE MAINTENANCE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 700000
TG-4774B | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1375000 | FY 2023: 100000
TG-4774B | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 88000 | FY 2023: 11000
TG-4785A | PUBLIC TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1176000 | FY 2023: 100000
TG-4785A | PUBLIC TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 180000 | FY 2023: 20000
TG-4785B | PUBLIC TRANSIT | TAR RIVER TRANSIT | PREVENTIVE MAINTENANCE | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 800000 | FY 2023: 100000
TG-4785B | PUBLIC TRANSIT | TAR RIVER TRANSIT | PREVENTIVE MAINTENANCE | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 5647000 | FY 2023: 500000
TG-4792B | PUBLIC TRANSIT | GORALEIGH | ADA PARATRANSIT SERVICE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 6289000
TG-4792B | PUBLIC TRANSIT | GORALEIGH | ADA PARATRANSIT SERVICE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 11938000
TG-4806 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | PREVENTIVE MAINTENANCE, BUS FACILITIES, SUPPORT EQUIPMENT, AND SOFTWARE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1500000
TG-4806 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | PREVENTIVE MAINTENANCE, BUS FACILITIES, SUPPORT EQUIPMENT, AND SOFTWARE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 1210000
TG-4806 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | PREVENTIVE MAINTENANCE, BUS FACILITIES, SUPPORT EQUIPMENT, AND SOFTWARE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 685000
TG-4814 | PUBLIC TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC ($40K CAPITAL COST OF CONTRACTING) | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2570000 | FY 2023: 181000
TG-4814 | PUBLIC TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC ($40K CAPITAL COST OF CONTRACTING) | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 436000 | FY 2023: 48000
TG-4821B | PUBLIC TRANSIT | AUTHORITY TRIANGLE TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 21379000 | FY 2023: 1575000
TG-4821B | PUBLIC TRANSIT | AUTHORITY TRIANGLE TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 3111000 | FY 2023: 394000
TG-4827 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 901000 | FY 2023: 76000; FY 2024: 83000; FY 2025: 83000
TG-4827 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 5045000 | FY 2023: 313000; FY 2024: 331000; FY 2025: 331000
TG-4935A | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 42800000 | FY 2023: 2200000; FY 2024: 2200000; FY 2025: 2300000
TG-4935A | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | OPERATIONS | 1210000
TG-4935A | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 34480000 | FY 2023: 3520000; FY 2024: 3520000; FY 2025: 3620000
TG-4951 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 2463000 | FY 2023: 175000
TG-4951 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 1304000 | FY 2023: 130000
TG-4951 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 3010000 | FY 2023: 175000
TG-4952 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | NON-FIXED ROUTE ADA PARATRANSIT | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 185000 | FY 2023: 19000; FY 2024: 20000; FY 2025: 20000; FY 2026: 20000; FY 2027: 20000
TG-4952 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | NON-FIXED ROUTE ADA PARATRANSIT | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 742000 | FY 2023: 76000; FY 2024: 78000; FY 2025: 80000; FY 2026: 80000; FY 2027: 80000
TG-4957 | PUBLIC TRANSIT | AUTHORITY GREENSBORO TRANSIT | OPERATING-ADA PARATRANSIT SERVICE | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 11562000 | FY 2023: 658000; FY 2024: 658000; FY 2025: 658000; FY 2026: 658000; FY 2027: 658000; FY 2028: 658000
TG-4957 | PUBLIC TRANSIT | AUTHORITY GREENSBORO TRANSIT | OPERATING-ADA PARATRANSIT SERVICE | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 1957000 | FY 2023: 165000; FY 2024: 165000; FY 2025: 165000; FY 2026: 165000; FY 2027: 165000; FY 2028: 165000
TG-5026 | PUBLIC TRANSIT | CARTS | TG-5026 LEASE OF TABLETS | 2 | New Bern Area MPO |  | PUBLIC TRANSIT |  | 5307 | ADMINISTRATIVE | 0 | FY 2023: 0
TG-5026 | PUBLIC TRANSIT | CARTS | TG-5026 LEASE OF TABLETS | 2 | New Bern Area MPO |  | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 0 | FY 2023: 0
TG-5103A | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 6243000 | FY 2023: 500000
TG-5103A | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 1000000 | FY 2023: 125000
TG-5103B | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - ADA SERVICES | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 544000 | FY 2023: 88000
TG-5103B | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - ADA SERVICES | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 2902000 | FY 2023: 350000
TG-5103C | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | PREVENTIVE MAINTENANCE | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 12625000 | FY 2023: 1400000
TG-5103C | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | PREVENTIVE MAINTENANCE | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 2350000 | FY 2023: 350000
TG-5105 | PUBLIC TRANSIT | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 735000 | FY 2023: 56000; FY 2024: 56000; FY 2025: 56000; FY 2026: 56000; FY 2027: 56000; FY 2028: 56000
TG-5105 | PUBLIC TRANSIT | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 4172000 | FY 2023: 225000; FY 2024: 225000; FY 2025: 225000; FY 2026: 225000; FY 2027: 225000; FY 2028: 225000
TG-5105 | PUBLIC TRANSIT | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 90000
TG-5107B | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | PREVENTIVE MAINTENANCE | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 1085000 | FY 2023: 135000
TG-5107B | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | PREVENTIVE MAINTENANCE | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 7632000 | FY 2023: 540000
TG-5107C | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 2036000 | FY 2023: 120000
TG-5107C | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 298000 | FY 2023: 30000
TG-5109 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2021000 | FY 2023: 206000; FY 2024: 213000; FY 2025: 219000; FY 2026: 219000; FY 2027: 219000
TG-5109 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 574000
TG-5109 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 507000 | FY 2023: 52000; FY 2024: 53000; FY 2025: 55000; FY 2026: 55000; FY 2027: 55000
TG-5118A | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | STATE OF GOOD REPAIR - RAIL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5337 | CAPITAL | 52080000 | FY 2023: 2247000; FY 2024: 2879000; FY 2025: 2965000; FY 2026: 5612000; FY 2027: 5718000 | 13368000
TG-5118A | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | STATE OF GOOD REPAIR - RAIL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 8395000 | FY 2023: 687000; FY 2024: 360000; FY 2025: 371000; FY 2026: 702000; FY 2027: 723000 | 1697000
TG-5118A | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | STATE OF GOOD REPAIR - RAIL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 4825000 | FY 2024: 360000; FY 2025: 371000; FY 2026: 702000; FY 2027: 723000 | 1697000
TG-5118B | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | LIGHT RAIL VEHICLE OVERHAUL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 26542000 | FY 2023: 2260000; FY 2024: 1577000; FY 2025: 1624000
TG-5118B | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | LIGHT RAIL VEHICLE OVERHAUL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5337 | CAPITAL | 2410000
TG-5118B | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | LIGHT RAIL VEHICLE OVERHAUL | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 4138000 | FY 2023: 565000; FY 2024: 394000; FY 2025: 406000
TG-5119 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | PREVENTIVE MAINTENANCE - RAIL, BUS AND FACILITIES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 82330000 | FY 2023: 6098000; FY 2024: 3528000; FY 2025: 3528000
TG-5119 | PUBLIC TRANSIT | SYSTEM CHARLOTTE AREA TRANSIT | PREVENTIVE MAINTENANCE - RAIL, BUS AND FACILITIES | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 13047000 | FY 2023: 1525000; FY 2024: 882000; FY 2025: 882000
TG-5122 | PUBLIC TRANSIT | CARTS | TG-5122 SHORT RANGE PLANNING | 2 | New Bern Area MPO |  | PUBLIC TRANSIT |  | 5307 | PLANNING | 0 | FY 2023: 0
TG-5122 | PUBLIC TRANSIT | CARTS | TG-5122 SHORT RANGE PLANNING | 2 | New Bern Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 0 | FY 2023: 0
TG-5126 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 12918000 | FY 2023: 1214000; FY 2024: 1214000; FY 2025: 1214000; FY 2026: 1214000; FY 2027: 1214000
TG-5126 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 11704000 | FY 2023: 1214000; FY 2024: 1214000; FY 2025: 1214000; FY 2026: 1214000; FY 2027: 1214000
TG-5220 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 400000 | FY 2023: 31000; FY 2024: 31000; FY 2025: 32000; FY 2026: 32000; FY 2027: 33000
TG-5220 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 39000 | FY 2023: 4000; FY 2024: 4000; FY 2025: 4000; FY 2026: 4000; FY 2027: 4000
TG-5220 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | S | CAPITAL | 39000 | FY 2023: 4000; FY 2024: 4000; FY 2025: 4000; FY 2026: 4000; FY 2027: 4000
TG-5224A | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | PREVENTIVE MAINTENANCE | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 2325000 | FY 2023: 300000
TG-5224A | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | PREVENTIVE MAINTENANCE | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 14874000 | FY 2023: 1200000
TG-5224C | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 123000
TG-5224C | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2052000 | FY 2023: 168000
TG-5224C | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 306000 | FY 2023: 42000
TG-5224D | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - SUPPORT VEHICLE | 6 | Fayetteville Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 240000
TG-5224D | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - SUPPORT VEHICLE | 6 | Fayetteville Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 60000
TG-5224E | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - ADA SERVICES | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2365000
TG-5224E | PUBLIC TRANSIT | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - ADA SERVICES | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 595000
TG-5225 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | ROUTINE CAPITAL-BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 723000 | FY 2023: 14000; FY 2024: 15000; FY 2025: 16000; FY 2026: 16000; FY 2027: 16000
TG-5225 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | ROUTINE CAPITAL-BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 44000 | FY 2023: 4000; FY 2024: 4000; FY 2025: 4000; FY 2026: 4000; FY 2027: 4000
TG-5225C | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | MOBILITY MANAGEMENT | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 732000 | FY 2023: 65000; FY 2024: 67000; FY 2025: 69000; FY 2026: 69000; FY 2027: 69000
TG-5225C | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | MOBILITY MANAGEMENT | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 158000 | FY 2023: 16000; FY 2024: 17000; FY 2025: 17000; FY 2026: 17000; FY 2027: 17000
TG-5232 | PUBLIC TRANSIT | CITY OF SALISBURY | PREVENTIVE MAINTENANCE - BUS, FACILITIES | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 4008000 | FY 2023: 334000; FY 2024: 334000; FY 2025: 334000; FY 2026: 334000; FY 2027: 334000
TG-5232 | PUBLIC TRANSIT | CITY OF SALISBURY | PREVENTIVE MAINTENANCE - BUS, FACILITIES | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 996000 | FY 2023: 83000; FY 2024: 83000; FY 2025: 83000; FY 2026: 83000; FY 2027: 83000
TG-5233 | PUBLIC TRANSIT | CITY OF SALISBURY | BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC. | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1792000 | FY 2023: 224000
TG-5233 | PUBLIC TRANSIT | CITY OF SALISBURY | BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC. | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 448000 | FY 2023: 56000
TG-5235 | PUBLIC TRANSIT | GO TRIANGLE | SAFETY AND SECURITY - CAMERAS. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | DIVISION 5 |  | BGDA | CAPITAL | 137000
TG-5235 | PUBLIC TRANSIT | GO TRIANGLE | SAFETY AND SECURITY - CAMERAS. | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | DIVISION 5 |  | L | CAPITAL | 34000
TG-5241 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | PREVENTIVE MAINTENANCE | 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 8155000 | FY 2023: 585000; FY 2024: 585000; FY 2025: 585000; FY 2026: 585000; FY 2027: 585000
TG-5241 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | PREVENTIVE MAINTENANCE | 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 36153000 | FY 2023: 2337000; FY 2024: 2337000; FY 2025: 2337000; FY 2026: 2337000; FY 2027: 2337000
TG-5243 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE PREVENTATIVE MAINTENACE PROJECT WILL ENSURE THE FTA FUNDED ASSESTS ARE MAINTAINED TO THE FTA STATE OF GOOD REPAIR REQUIREMENTS AND THAT SERVICE CONTINUES WITHOUT DISRUPTION. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 900000 | FY 2023: 900000
TG-5243 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE PREVENTATIVE MAINTENACE PROJECT WILL ENSURE THE FTA FUNDED ASSESTS ARE MAINTAINED TO THE FTA STATE OF GOOD REPAIR REQUIREMENTS AND THAT SERVICE CONTINUES WITHOUT DISRUPTION. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 225000 | FY 2023: 225000
TG-5245 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | PREVENTIVE MAINTENANCE | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2562000
TG-5245 | PUBLIC TRANSIT | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | PREVENTIVE MAINTENANCE | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 792000
TG-5246 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE OPERATING ASSISTANCE PROJECT WILL ALLOW THE CONTINUATION OF COMPLEMENTARY PARATRANSIT SERVICE TO TWO COUNTIES AND FOUR MUNICIPLITIES WITHIN THE UZA. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 317000 | FY 2023: 317000
TG-5246 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE OPERATING ASSISTANCE PROJECT WILL ALLOW THE CONTINUATION OF COMPLEMENTARY PARATRANSIT SERVICE TO TWO COUNTIES AND FOUR MUNICIPLITIES WITHIN THE UZA. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 76000 | FY 2023: 76000
TG-5256 | PUBLIC TRANSIT | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | PREVENTIVE MAINTENANCE | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 280000 | FY 2023: 28000
TG-5256 | PUBLIC TRANSIT | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | PREVENTIVE MAINTENANCE | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 72000 | FY 2023: 7000
TG-5257 | PUBLIC TRANSIT | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | ADA/PARATRANSIT | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 503000 | FY 2023: 30000
TG-5257 | PUBLIC TRANSIT | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | ADA/PARATRANSIT | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 128000 | FY 2023: 8000
TG-5260 | PUBLIC TRANSIT | CITY OF SALISBURY | ROUTINE CAPITAL - ADA SERVICES | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 826000 | FY 2023: 70000; FY 2024: 70000; FY 2025: 70000; FY 2026: 70000; FY 2027: 70000
TG-5260 | PUBLIC TRANSIT | CITY OF SALISBURY | ROUTINE CAPITAL - ADA SERVICES | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 212000 | FY 2023: 18000; FY 2024: 18000; FY 2025: 18000; FY 2026: 18000; FY 2027: 18000
TG-6137B | PUBLIC TRANSIT | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PASSENGER AMENITIES, PARTS, EQUIPMENT, PREVENTIVE MAINTENANCE, AND CAPITAL COST OF CONTRACTING. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 800000 | FY 2023: 100000; FY 2024: 100000; FY 2025: 100000
TG-6137B | PUBLIC TRANSIT | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PASSENGER AMENITIES, PARTS, EQUIPMENT, PREVENTIVE MAINTENANCE, AND CAPITAL COST OF CONTRACTING. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 200000 | FY 2023: 25000; FY 2024: 25000; FY 2025: 25000
TG-6142A | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - SERVICE VEHICLE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 8000
TG-6142A | PUBLIC TRANSIT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - SERVICE VEHICLE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | CAPITAL | 113000
TG-6143 | PUBLIC TRANSIT | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 528000 | FY 2023: 31000
TG-6143 | PUBLIC TRANSIT | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | CAPITAL | 7000
TG-6143 | PUBLIC TRANSIT | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 64000 | FY 2023: 8000
TG-6146 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | CAPITAL | 545000 | FY 2023: 44000
TG-6159 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | CAPITAL | 360000 | FY 2023: 16000
TG-6159 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 16000 | FY 2023: 2000
TG-6159 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 16000 | FY 2023: 2000
TG-6173B | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PREVENTIVE MAINTENANCE, SECURITY AND PESSENGER AMENITIES. | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1000000 | FY 2023: 100000; FY 2024: 100000; FY 2025: 100000; FY 2026: 100000
TG-6173B | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PREVENTIVE MAINTENANCE, SECURITY AND PESSENGER AMENITIES. | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 138000 | FY 2023: 25000; FY 2024: 25000; FY 2025: 25000; FY 2026: 25000
TG-6177 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 54000 | FY 2023: 54000
TG-6177 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 6000 | FY 2023: 6000
TG-6177 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | T | CONSTRUCTION | 6000 | FY 2023: 6000
TG-6179 | PUBLIC TRANSIT | CITY OF SALISBURY | AVL SYSTEM | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5339 | CAPITAL | 1792000 | FY 2023: 224000; FY 2024: 224000
TG-6179 | PUBLIC TRANSIT | CITY OF SALISBURY | AVL SYSTEM | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 448000 | FY 2023: 56000; FY 2024: 56000
TG-6181 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | TRANSIT ROUTINE CAPITAL COST OF CONTRACTING | 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 2551000 | FY 2023: 429000
TG-6181 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | TRANSIT ROUTINE CAPITAL COST OF CONTRACTING | 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1695000 | FY 2023: 285000
TG-6183A | PUBLIC TRANSIT | GASTONIA TRANSIT | ADA PARATRANSIT SERVICE | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 884000
TG-6183A | PUBLIC TRANSIT | GASTONIA TRANSIT | ADA PARATRANSIT SERVICE | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | L | OPERATIONS | 221000
TG-6183B | PUBLIC TRANSIT | CITY OF ASHEVILLE | TRANSIT PREVENTATIVE MAINTENANCE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1600000
TG-6183B | PUBLIC TRANSIT | CITY OF ASHEVILLE | TRANSIT PREVENTATIVE MAINTENANCE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 400000
TG-6184B | PUBLIC TRANSIT | GASTONIA TRANSIT | PREVENTATIVE MAINTENANCE | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1428000
TG-6184B | PUBLIC TRANSIT | GASTONIA TRANSIT | PREVENTATIVE MAINTENANCE | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | L | OPERATIONS | 357000
TG-6185 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 966000 | FY 2023: 51000; FY 2024: 51000; FY 2025: 51000; FY 2026: 51000; FY 2027: 74000; FY 2028: 74000
TG-6185 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 226000 | FY 2023: 13000; FY 2024: 13000; FY 2025: 13000; FY 2026: 13000; FY 2027: 19000; FY 2028: 19000
TG-6187 | PUBLIC TRANSIT | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS – CAPITAL PROGRAM | 6, 7, 8, 9, 10, 12 | Charlotte Regional TPO, Cabarrus-Rowan MPO, Burlington-Graham MPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 3000000
TG-6187 | PUBLIC TRANSIT | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS – CAPITAL PROGRAM | 6, 7, 8, 9, 10, 12 | Charlotte Regional TPO, Cabarrus-Rowan MPO, Burlington-Graham MPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 751000
TG-6731 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT |  | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | CMAQ | CAPITAL | 2430000
TG-6731 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT |  | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 609000
TG-6783 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL, PASSENGER SHELTERS, PASSENGER AMENITIES, SHOP EQUIPMENT, SPARE PARTS | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1367000 | FY 2023: 182000; FY 2024: 140000; FY 2025: 140000; FY 2026: 140000; FY 2027: 147000
TG-6783 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL, PASSENGER SHELTERS, PASSENGER AMENITIES, SHOP EQUIPMENT, SPARE PARTS | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 342000 | FY 2023: 45000; FY 2024: 35000; FY 2025: 35000; FY 2026: 35000; FY 2027: 37000
TG-6784 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PREVENTIVE MAINTENANCE | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 70000
TG-6784 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PREVENTIVE MAINTENANCE | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 350000
TG-6786 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY BUNCOMBE - BUNCOMBE COUNTY TRANSIT ROUTINE CAPITAL COST OF CONTRACTING. | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1600000 | FY 2023: 403000
TG-6786 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY BUNCOMBE - BUNCOMBE COUNTY TRANSIT ROUTINE CAPITAL COST OF CONTRACTING. | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 816000 | FY 2023: 101000; FY 2024: 415000
TG-6788 | PUBLIC TRANSIT | CITY OF ASHEVILLE | MOUNTAIN PROJECTS ( HAYWOOD COUNTY) DEVIATED FIXED ROUTE CAPITAL AND CARES FUNDS. | 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 407000
TG-6788 | PUBLIC TRANSIT | CITY OF ASHEVILLE | MOUNTAIN PROJECTS ( HAYWOOD COUNTY) DEVIATED FIXED ROUTE CAPITAL AND CARES FUNDS. | 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 41000
TG-6789 | PUBLIC TRANSIT | CABARRUS COUNTY | CAPITAL FOR CABARRUS COUNTY THROUGH THE CITY OF CONCORD | 10 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2077000 | FY 2023: 230000; FY 2024: 240000; FY 2025: 250000; FY 2026: 260000; FY 2027: 270000
TG-6789 | PUBLIC TRANSIT | CABARRUS COUNTY | CAPITAL FOR CABARRUS COUNTY THROUGH THE CITY OF CONCORD | 10 | Cabarrus-Rowan MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 416000 | FY 2023: 46000; FY 2024: 48000; FY 2025: 50000; FY 2026: 52000; FY 2027: 54000
TG-6790 | PUBLIC TRANSIT | MECKLENBURG TRANSPORTATION | 5307 FUNDING FOR FY20-21 (20-LU-051) | 10 | Charlotte Regional TPO | ADDING FFY20-21 | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1035000
TG-6790 | PUBLIC TRANSIT | MECKLENBURG TRANSPORTATION | 5307 FUNDING FOR FY20-21 (20-LU-051) | 10 | Charlotte Regional TPO | ADDING FFY20-21 | PUBLIC TRANSIT |  | L | CAPITAL | 545000
TG-6791 | PUBLIC TRANSIT | GORALEIGH | CAPITAL COST OF CONTRACTING | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 4000000
TG-6791 | PUBLIC TRANSIT | GORALEIGH | CAPITAL COST OF CONTRACTING | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 1000000
TG-6792 | PUBLIC TRANSIT | GASTON TRANSIT | TRANSIT ENHANCEMENTS - PEDESTRIAN WALKWAYS | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 2119000 | FY 2023: 447000
TG-6792 | PUBLIC TRANSIT | GASTON TRANSIT | TRANSIT ENHANCEMENTS - PEDESTRIAN WALKWAYS | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | L | CONSTRUCTION | 530000 | FY 2023: 112000
TG-6798 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 901000 | FY 2023: 136000; FY 2024: 126000; FY 2025: 126000
TG-6798 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | OPERATIONS | 227000 | FY 2023: 34000; FY 2024: 32000; FY 2025: 32000
TG-6799 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTIVE MAINTANENCE | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | CAPITAL | 879000 | FY 2023: 145000; FY 2024: 120000; FY 2025: 120000
TG-6799 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTIVE MAINTANENCE | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | CAPITAL | 3515000 | FY 2023: 579000; FY 2024: 480000; FY 2025: 480000
TG-6800 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, COMPUTER HARDWARE AND SOFTWARE, AVL SOFTWARE, ETC. | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1383000 | FY 2023: 232000; FY 2024: 200000; FY 2025: 200000
TG-6800 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, COMPUTER HARDWARE AND SOFTWARE, AVL SOFTWARE, ETC. | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | CAPITAL | 326000 | FY 2023: 58000; FY 2024: 40000; FY 2025: 40000
TG-6801 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1853000 | FY 2023: 347000; FY 2024: 200000; FY 2025: 200000
TG-6801 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | OPERATIONS | 464000 | FY 2023: 87000; FY 2024: 50000; FY 2025: 50000
TG-6802 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE-ADA PARATRANSIT | 12 | Greater Hickory MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 70000 | FY 2023: 10000; FY 2024: 10000; FY 2025: 10000
TG-6802 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE-ADA PARATRANSIT | 12 | Greater Hickory MPO |  | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 280000 | FY 2023: 40000; FY 2024: 40000; FY 2025: 40000
TG-6804 | PUBLIC TRANSIT | GASTONIA TRANSIT | TRANSIT APP | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | L | OPERATIONS | 13000
TG-6804 | PUBLIC TRANSIT | GASTONIA TRANSIT | TRANSIT APP | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 50000
TG-6808B | PUBLIC TRANSIT | DAVIDSON COUNTY | PREVENTIVE MAINTENANCE | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 326688000
TG-6808B | PUBLIC TRANSIT | DAVIDSON COUNTY | PREVENTIVE MAINTENANCE | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 81672000
TG-6809 | PUBLIC TRANSIT | DAVIDSON COUNTY | ROUTINE CAPITAL - PASSENGER SHELTERS, PASSENGER AMENITIESA, SHOP EQUIPMENT, SPARE PARTS, CAPITAL COST OF CONTRACTING, ETC. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 163344000
TG-6809 | PUBLIC TRANSIT | DAVIDSON COUNTY | ROUTINE CAPITAL - PASSENGER SHELTERS, PASSENGER AMENITIESA, SHOP EQUIPMENT, SPARE PARTS, CAPITAL COST OF CONTRACTING, ETC. | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 40836000
TG-6811B | PUBLIC TRANSIT | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | FED | CAPITAL | 37000
TG-6811B | PUBLIC TRANSIT | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 59000 | FY 2024: 10000; FY 2025: 10000; FY 2026: 10000; FY 2027: 10000; FY 2028: 10000
TG-6811B | PUBLIC TRANSIT | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 200000 | FY 2024: 40000; FY 2025: 40000; FY 2026: 40000; FY 2027: 40000; FY 2028: 40000
TG-6812A | PUBLIC TRANSIT | BURLINGTON | ADA SERVICES | 7 | Burlington-Graham MPO | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | L | OPERATIONS | 42000
TG-6812A | PUBLIC TRANSIT | BURLINGTON | ADA SERVICES | 7 | Burlington-Graham MPO | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 169000
TG-6814 | PUBLIC TRANSIT | GOTRIANGLE | PURCHASE AND INSTALL SIGNAGE AT DESIGNATED LOCATIONS ALONG I-540 AND I-40 FOR BUS ON SHOULDER SYSTEM. (BOSS) UTILIZE EASTBOUND SHOULDER OF I-540 BETWEEN NC-147 AND CAPITAL BLVD AND EASTBOUND ON I-40 BETWEEN WADE AVENUE AND S SAUNDERS STREET. | 5 | Capital Area MPO |  | EXEMPT |  | BGDA | CAPITAL | 123000
TG-6814 | PUBLIC TRANSIT | GOTRIANGLE | PURCHASE AND INSTALL SIGNAGE AT DESIGNATED LOCATIONS ALONG I-540 AND I-40 FOR BUS ON SHOULDER SYSTEM. (BOSS) UTILIZE EASTBOUND SHOULDER OF I-540 BETWEEN NC-147 AND CAPITAL BLVD AND EASTBOUND ON I-40 BETWEEN WADE AVENUE AND S SAUNDERS STREET. | 5 | Capital Area MPO |  | EXEMPT |  | L | CAPITAL | 331000
TG-6815 | PUBLIC TRANSIT | GORALEIGH | DESIGN, PURCHASE, AND INSTALL NEW AMENITIES AT 13 BUS STOP LOCATIONS ALONG ROUTES IN WAKE COUNTY,UPGRADES INCLUDE SHELTERS, BENCH, PAD, OR SOME COMBINATIONS | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CAPITAL | 259000
TG-6815 | PUBLIC TRANSIT | GORALEIGH | DESIGN, PURCHASE, AND INSTALL NEW AMENITIES AT 13 BUS STOP LOCATIONS ALONG ROUTES IN WAKE COUNTY,UPGRADES INCLUDE SHELTERS, BENCH, PAD, OR SOME COMBINATIONS | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CAPITAL | 648000
TG-6816 | PUBLIC TRANSIT | GORALEIGH | DEVELOPED ENHANCED TRANSFER POINTS THROUGHOUT GO RALEIGH SYSTEM IN LOCATION WITH HIGH RIDERSHIP (75 + BOARDINGS PER DAY) | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CAPITAL | 788000
TG-6816 | PUBLIC TRANSIT | GORALEIGH | DEVELOPED ENHANCED TRANSFER POINTS THROUGHOUT GO RALEIGH SYSTEM IN LOCATION WITH HIGH RIDERSHIP (75 + BOARDINGS PER DAY) | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CAPITAL | 397000
TI-6101 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE | 10, 11, 12 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 6023000 | FY 2023: 246000
TI-6101 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE | 10, 11, 12 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 848000 | FY 2023: 106000
TI-6101 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE | 10, 11, 12 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 1952000 | FY 2023: 244000
TI-6102 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON | 6, 8, 10 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 7470000 | FY 2023: 265000
TI-6102 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON | 6, 8, 10 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 928000 | FY 2023: 116000
TI-6102 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON | 6, 8, 10 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 2120000 | FY 2023: 265000
TI-6103 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE | 7, 9, 11 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 8642000 | FY 2023: 360000
TI-6103 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE | 7, 9, 11 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 1486000 | FY 2023: 161000
TI-6103 | PUBLIC TRANSIT | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE | 7, 9, 11 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 2674000 | FY 2023: 359000
TI-6104 | PUBLIC TRANSIT | GREYHOUND LINES | INTERCITY BUS FROM RALEIGH TO NORFOLK, VA VIA ELIZABETH CITY ALONG US 64, US 301, US 264, AND US 17 WITH STOPS AT RALEIGH, ROCKY MOUNT, WILSON, GREENVILLE, WASHINGTON, WILLIAMSTON, EDENTON, AND ELIZABETH CITY | 1, 2, 4, 5 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 19025000 | FY 2023: 1156000
TI-6104 | PUBLIC TRANSIT | GREYHOUND LINES | INTERCITY BUS FROM RALEIGH TO NORFOLK, VA VIA ELIZABETH CITY ALONG US 64, US 301, US 264, AND US 17 WITH STOPS AT RALEIGH, ROCKY MOUNT, WILSON, GREENVILLE, WASHINGTON, WILLIAMSTON, EDENTON, AND ELIZABETH CITY | 1, 2, 4, 5 |  | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 9248000 | FY 2023: 1156000
TI-6109 | PUBLIC TRANSIT | STATEWIDE | 5311(F) INTERCITY BUS FUNDS FOR FTA GANTS | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2698000
TK-4900Z | PUBLIC TRANSIT | STATEWIDE | 5311 STATE ADMINISTRATION AND 5311 STATE ADMINISTRATION | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 3080000
TK-4902 | PUBLIC TRANSIT | STATEWIDE | STATE ADMINISTRATION OF APPALACHIAN DEVELOPMENT TRANSPORTATION ASSISTANCE PROGRAM | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | ADTAP | ADMINISTRATIVE | 235000
TK-5176 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | ADMINISTRATION | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 53000
TK-5176 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | ADMINISTRATION | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 159000
TK-5176 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | ADMINISTRATION | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1658000 | FY 2023: 135000
TK-5176 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | ADMINISTRATION | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 270000
TK-5178 | PUBLIC TRANSIT | CITY OF WILSON | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 4023000 | FY 2023: 258000
TK-5178 | PUBLIC TRANSIT | CITY OF WILSON | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 405000 | FY 2023: 51000
TK-5178 | PUBLIC TRANSIT | CITY OF WILSON | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 135000 | FY 2023: 17000
TK-5179 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 123000 | FY 2023: 15000
TK-5179 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 3878000 | FY 2023: 245000
TK-5179 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 376000 | FY 2023: 46000
TK-5180 | PUBLIC TRANSIT | TAR RIVER TRANSIT | ADMINISTRATION | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 82000 | FY 2023: 10000
TK-5180 | PUBLIC TRANSIT | TAR RIVER TRANSIT | ADMINISTRATION | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2549000 | FY 2023: 156000
TK-5180 | PUBLIC TRANSIT | TAR RIVER TRANSIT | ADMINISTRATION | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 239000 | FY 2023: 29000
TK-5181 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ADMINISTRATION | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 144000 | FY 2023: 18000
TK-5181 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ADMINISTRATION | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 714000
TK-5181 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ADMINISTRATION | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 3694000 | FY 2023: 284000
TK-5181 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ADMINISTRATION | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 424000 | FY 2023: 53000
TK-6103 | PUBLIC TRANSIT | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 1638000 | FY 2023: 214000
TK-6103 | PUBLIC TRANSIT | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2834000 | FY 2023: 89000
TK-6103 | PUBLIC TRANSIT | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 410000 | FY 2023: 53000
TK-6104 | PUBLIC TRANSIT | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 5197000 | FY 2023: 331000
TK-6104 | PUBLIC TRANSIT | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 500000 | FY 2023: 62000
TK-6104 | PUBLIC TRANSIT | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 169000 | FY 2023: 21000
TK-6105 | PUBLIC TRANSIT | ALLEGHANY COUNTY | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1914000 | FY 2023: 124000
TK-6105 | PUBLIC TRANSIT | ALLEGHANY COUNTY | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 184000 | FY 2023: 23000
TK-6105 | PUBLIC TRANSIT | ALLEGHANY COUNTY | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 64000 | FY 2023: 8000
TK-6106 | PUBLIC TRANSIT | ANSON COUNTY | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2539000 | FY 2023: 164000
TK-6106 | PUBLIC TRANSIT | ANSON COUNTY | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 248000 | FY 2023: 31000
TK-6106 | PUBLIC TRANSIT | ANSON COUNTY | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 80000 | FY 2023: 10000
TK-6107 | PUBLIC TRANSIT | APPALCART | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 5814000 | FY 2023: 375000
TK-6107 | PUBLIC TRANSIT | APPALCART | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 560000 | FY 2023: 70000
TK-6107 | PUBLIC TRANSIT | APPALCART | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 184000 | FY 2023: 23000
TK-6108 | PUBLIC TRANSIT | ASHE COUNTY TRANSPORTATION | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2426000 | FY 2023: 157000
TK-6108 | PUBLIC TRANSIT | ASHE COUNTY TRANSPORTATION | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 80000 | FY 2023: 10000
TK-6108 | PUBLIC TRANSIT | ASHE COUNTY TRANSPORTATION | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 232000 | FY 2023: 29000
TK-6110 | PUBLIC TRANSIT | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1745000 | FY 2023: 113000
TK-6110 | PUBLIC TRANSIT | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 168000 | FY 2023: 21000
TK-6110 | PUBLIC TRANSIT | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 56000 | FY 2023: 7000
TK-6111 | PUBLIC TRANSIT | BLADEN COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1515000 | FY 2023: 97000
TK-6111 | PUBLIC TRANSIT | BLADEN COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 144000 | FY 2023: 18000
TK-6111 | PUBLIC TRANSIT | BLADEN COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 48000 | FY 2023: 6000
TK-6112 | PUBLIC TRANSIT | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2214000 | FY 2023: 142000
TK-6112 | PUBLIC TRANSIT | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 218000 | FY 2023: 27000
TK-6112 | PUBLIC TRANSIT | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 73000 | FY 2023: 9000
TK-6115 | PUBLIC TRANSIT | CARTERET COUNTY | ADMINISTRATION | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 446000
TK-6115 | PUBLIC TRANSIT | CARTERET COUNTY | ADMINISTRATION | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1409000 | FY 2023: 75000
TK-6115 | PUBLIC TRANSIT | CARTERET COUNTY | ADMINISTRATION | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 32000
TK-6115 | PUBLIC TRANSIT | CARTERET COUNTY | ADMINISTRATION | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 11000
TK-6116 | PUBLIC TRANSIT | CASWELL COUNTY | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 68000
TK-6116 | PUBLIC TRANSIT | CASWELL COUNTY | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 18000 | FY 2023: 6000
TK-6116 | PUBLIC TRANSIT | CASWELL COUNTY | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 30000
TK-6116 | PUBLIC TRANSIT | CASWELL COUNTY | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 68000 | FY 2023: 17000
TK-6116 | PUBLIC TRANSIT | CASWELL COUNTY | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 715000 | FY 2023: 89000
TK-6116 | PUBLIC TRANSIT | CASWELL COUNTY | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 669000
TK-6117 | PUBLIC TRANSIT | CHATHAM TRANSIT NETWORK | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2915000 | FY 2023: 188000
TK-6117 | PUBLIC TRANSIT | CHATHAM TRANSIT NETWORK | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 287000 | FY 2023: 36000
TK-6117 | PUBLIC TRANSIT | CHATHAM TRANSIT NETWORK | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 96000 | FY 2023: 12000
TK-6118 | PUBLIC TRANSIT | CHEROKEE COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2217000 | FY 2023: 142000
TK-6118 | PUBLIC TRANSIT | CHEROKEE COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 216000 | FY 2023: 27000
TK-6118 | PUBLIC TRANSIT | CHEROKEE COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 72000 | FY 2023: 9000
TK-6119 | PUBLIC TRANSIT | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | 1, 4 | Peanut Belt RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 200000 | FY 2023: 25000
TK-6119 | PUBLIC TRANSIT | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | 1, 4 | Peanut Belt RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 5712000 | FY 2023: 394000
TK-6119 | PUBLIC TRANSIT | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | 1, 4 | Peanut Belt RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 592000 | FY 2023: 74000
TK-6120 | PUBLIC TRANSIT | CLAY COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 73000 | FY 2023: 9000
TK-6120 | PUBLIC TRANSIT | CLAY COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2211000 | FY 2023: 141000
TK-6120 | PUBLIC TRANSIT | CLAY COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 213000 | FY 2023: 26000
TK-6121 | PUBLIC TRANSIT | COLUMBUS COUNTY | ADMINISTRATION | 6 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2128000 | FY 2023: 137000
TK-6121 | PUBLIC TRANSIT | COLUMBUS COUNTY | ADMINISTRATION | 6 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 208000 | FY 2023: 26000
TK-6121 | PUBLIC TRANSIT | COLUMBUS COUNTY | ADMINISTRATION | 6 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 72000 | FY 2023: 9000
TK-6122 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 48000
TK-6122 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 45000
TK-6122 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 3955000 | FY 2023: 339000
TK-6122 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 678000
TK-6123 | PUBLIC TRANSIT | CUMBERLAND COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 93000 | FY 2023: 12000
TK-6123 | PUBLIC TRANSIT | CUMBERLAND COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 388000 | FY 2023: 51000
TK-6123 | PUBLIC TRANSIT | CUMBERLAND COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 620000 | FY 2023: 17000
TK-6124 | PUBLIC TRANSIT | DARE COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1588000 | FY 2023: 103000
TK-6124 | PUBLIC TRANSIT | DARE COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 152000 | FY 2023: 19000
TK-6124 | PUBLIC TRANSIT | DARE COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 48000 | FY 2023: 6000
TK-6125 | PUBLIC TRANSIT | DAVIDSON COUNTY | ADMINISTRATION | 9 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2511000 | FY 2023: 168000
TK-6125 | PUBLIC TRANSIT | DAVIDSON COUNTY | ADMINISTRATION | 9 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 137000 | FY 2023: 10000
TK-6125 | PUBLIC TRANSIT | DAVIDSON COUNTY | ADMINISTRATION | 9 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 243000 | FY 2023: 31000
TK-6126 | PUBLIC TRANSIT | DURHAM COUNTY ACCESS | ADMINISTRATION | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 163000
TK-6126 | PUBLIC TRANSIT | DURHAM COUNTY ACCESS | ADMINISTRATION | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 838000 | FY 2023: 63000
TK-6126 | PUBLIC TRANSIT | DURHAM COUNTY ACCESS | ADMINISTRATION | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 13000
TK-6126 | PUBLIC TRANSIT | DURHAM COUNTY ACCESS | ADMINISTRATION | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 69000
TK-6127 | PUBLIC TRANSIT | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 48000 | FY 2023: 6000
TK-6127 | PUBLIC TRANSIT | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 137000 | FY 2023: 17000
TK-6127 | PUBLIC TRANSIT | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1461000 | FY 2023: 93000
TK-6128 | PUBLIC TRANSIT | GASTON COUNTY ACCESS | ADMINISTRATION | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 275000 | FY 2023: 35000
TK-6128 | PUBLIC TRANSIT | GASTON COUNTY ACCESS | ADMINISTRATION | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 769000 | FY 2023: 101000
TK-6128 | PUBLIC TRANSIT | GASTON COUNTY ACCESS | ADMINISTRATION | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2125000 | FY 2023: 98000
TK-6129 | PUBLIC TRANSIT | GATES COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 272000
TK-6129 | PUBLIC TRANSIT | GATES COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1632000 | FY 2023: 136000
TK-6131 | PUBLIC TRANSIT | GREENE COUNTY | ADMINISTRATION | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 47000 | FY 2023: 6000
TK-6131 | PUBLIC TRANSIT | GREENE COUNTY | ADMINISTRATION | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 135000 | FY 2023: 17000
TK-6131 | PUBLIC TRANSIT | GREENE COUNTY | ADMINISTRATION | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1425000 | FY 2023: 92000
TK-6132 | PUBLIC TRANSIT | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 264000 | FY 2023: 34000
TK-6132 | PUBLIC TRANSIT | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 928000 | FY 2023: 120000
TK-6132 | PUBLIC TRANSIT | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1927000 | FY 2023: 73000
TK-6133 | PUBLIC TRANSIT | HARNETT COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2700000 | FY 2023: 176000
TK-6133 | PUBLIC TRANSIT | HARNETT COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 264000 | FY 2023: 33000
TK-6133 | PUBLIC TRANSIT | HARNETT COUNTY | ADMINISTRATION | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 88000 | FY 2023: 11000
TK-6135 | PUBLIC TRANSIT | HYDE COUNTY NON-PROFIT | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1264000 | FY 2023: 80000
TK-6135 | PUBLIC TRANSIT | HYDE COUNTY NON-PROFIT | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 120000 | FY 2023: 15000
TK-6135 | PUBLIC TRANSIT | HYDE COUNTY NON-PROFIT | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 40000 | FY 2023: 5000
TK-6137 | PUBLIC TRANSIT | JACKSON COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2336000 | FY 2023: 151000
TK-6137 | PUBLIC TRANSIT | JACKSON COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 224000 | FY 2023: 28000
TK-6137 | PUBLIC TRANSIT | JACKSON COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 72000 | FY 2023: 9000
TK-6138 | PUBLIC TRANSIT | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 120000 | FY 2023: 15000
TK-6138 | PUBLIC TRANSIT | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 3644000 | FY 2023: 235000
TK-6138 | PUBLIC TRANSIT | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 352000 | FY 2023: 44000
TK-6139 | PUBLIC TRANSIT | KERR AREA TRANSPORTATION | ADMINISTRATION | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 208000 | FY 2023: 26000
TK-6139 | PUBLIC TRANSIT | KERR AREA TRANSPORTATION | ADMINISTRATION | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 6319000 | FY 2023: 409000
TK-6139 | PUBLIC TRANSIT | KERR AREA TRANSPORTATION | ADMINISTRATION | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 616000 | FY 2023: 77000
TK-6140 | PUBLIC TRANSIT | LEE COUNTY | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1958000 | FY 2023: 126000
TK-6140 | PUBLIC TRANSIT | LEE COUNTY | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 192000 | FY 2023: 24000
TK-6140 | PUBLIC TRANSIT | LEE COUNTY | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 64000 | FY 2023: 8000
TK-6141 | PUBLIC TRANSIT | LINCOLN COUNTY | ADMINISTRATION | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2523000 | FY 2023: 175000
TK-6141 | PUBLIC TRANSIT | LINCOLN COUNTY | ADMINISTRATION | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 275000 | FY 2023: 33000
TK-6141 | PUBLIC TRANSIT | LINCOLN COUNTY | ADMINISTRATION | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 263000 | FY 2023: 11000
TK-6142 | PUBLIC TRANSIT | MACON COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2503000 | FY 2023: 152000
TK-6142 | PUBLIC TRANSIT | MACON COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 231000 | FY 2023: 29000
TK-6142 | PUBLIC TRANSIT | MACON COUNTY | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 79000 | FY 2023: 10000
TK-6143 | PUBLIC TRANSIT | MADISON COUNTY TRANSPORTATION | ADMINISTRATION | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 56000 | FY 2023: 7000
TK-6143 | PUBLIC TRANSIT | MADISON COUNTY TRANSPORTATION | ADMINISTRATION | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1691000 | FY 2023: 110000
TK-6143 | PUBLIC TRANSIT | MADISON COUNTY TRANSPORTATION | ADMINISTRATION | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 160000 | FY 2023: 20000
TK-6144 | PUBLIC TRANSIT | MARTIN COUNTY | ADMINISTRATION | 1 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 72000 | FY 2023: 9000
TK-6144 | PUBLIC TRANSIT | MARTIN COUNTY | ADMINISTRATION | 1 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 216000 | FY 2023: 27000
TK-6144 | PUBLIC TRANSIT | MARTIN COUNTY | ADMINISTRATION | 1 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2241000 | FY 2023: 145000
TK-6145 | PUBLIC TRANSIT | MECKLENBURG TRANSPORTATION | ADMINISTRATION | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1680000 | FY 2023: 21000
TK-6145 | PUBLIC TRANSIT | MECKLENBURG TRANSPORTATION | ADMINISTRATION | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 291000 | FY 2023: 38000
TK-6145 | PUBLIC TRANSIT | MECKLENBURG TRANSPORTATION | ADMINISTRATION | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 1508000 | FY 2023: 196000
TK-6146 | PUBLIC TRANSIT | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2257000 | FY 2023: 146000
TK-6146 | PUBLIC TRANSIT | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 216000 | FY 2023: 27000
TK-6146 | PUBLIC TRANSIT | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 72000 | FY 2023: 9000
TK-6147 | PUBLIC TRANSIT | MOORE COUNTY | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 482000
TK-6147 | PUBLIC TRANSIT | MOORE COUNTY | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2505000 | FY 2023: 193000
TK-6147 | PUBLIC TRANSIT | MOORE COUNTY | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 288000 | FY 2023: 36000
TK-6147 | PUBLIC TRANSIT | MOORE COUNTY | ADMINISTRATION | 8 | Triangle Area RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 96000 | FY 2023: 12000
TK-6148 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 3184000 | FY 2023: 211000
TK-6148 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 529000 | FY 2023: 68000
TK-6148 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 881000
TK-6148 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5309 | OPERATIONS | 199000
TK-6148 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION | 13 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 1359000 | FY 2023: 175000
TK-6149 | PUBLIC TRANSIT | MOUNTAIN PROJECTS, INC. | ADMINISTRATION | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 471000
TK-6149 | PUBLIC TRANSIT | MOUNTAIN PROJECTS, INC. | ADMINISTRATION | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2365000 | FY 2023: 186000
TK-6149 | PUBLIC TRANSIT | MOUNTAIN PROJECTS, INC. | ADMINISTRATION | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 276000 | FY 2023: 35000
TK-6149 | PUBLIC TRANSIT | MOUNTAIN PROJECTS, INC. | ADMINISTRATION | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 152000 | FY 2023: 12000
TK-6151 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | ADMINISTRATION | 7 | Triangle Area RPO |  | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 370000
TK-6151 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | ADMINISTRATION | 7 | Triangle Area RPO |  | PUBLIC TRANSIT |  | S | OPERATIONS | 296000 | FY 2023: 37000
TK-6151 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | ADMINISTRATION | 7 | Triangle Area RPO |  | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1694000 | FY 2023: 121000
TK-6151 | PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | ADMINISTRATION | 7 | Triangle Area RPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 221000 | FY 2023: 28000
TK-6152 | PUBLIC TRANSIT | PENDER ADULT SERVICES, INC. | ADMINISTRATION | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 235000
TK-6152 | PUBLIC TRANSIT | PENDER ADULT SERVICES, INC. | ADMINISTRATION | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1245000 | FY 2023: 96000
TK-6152 | PUBLIC TRANSIT | PENDER ADULT SERVICES, INC. | ADMINISTRATION | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 144000 | FY 2023: 18000
TK-6152 | PUBLIC TRANSIT | PENDER ADULT SERVICES, INC. | ADMINISTRATION | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 48000 | FY 2023: 6000
TK-6153 | PUBLIC TRANSIT | PERSON COUNTY | ADMINISTRATION | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1822000 | FY 2023: 133000
TK-6153 | PUBLIC TRANSIT | PERSON COUNTY | ADMINISTRATION | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 204000 | FY 2023: 25000
TK-6153 | PUBLIC TRANSIT | PERSON COUNTY | ADMINISTRATION | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 66000 | FY 2023: 8000
TK-6153 | PUBLIC TRANSIT | PERSON COUNTY | ADMINISTRATION | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 151000
TK-6154 | PUBLIC TRANSIT | PITT COUNTY | ADMINISTRATION | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 358000
TK-6154 | PUBLIC TRANSIT | PITT COUNTY | ADMINISTRATION | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1769000 | FY 2023: 134000
TK-6154 | PUBLIC TRANSIT | PITT COUNTY | ADMINISTRATION | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 213000 | FY 2023: 27000
TK-6154 | PUBLIC TRANSIT | PITT COUNTY | ADMINISTRATION | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 163000 | FY 2023: 19000
TK-6155 | PUBLIC TRANSIT | POLK COUNTY TRANSPORTATION | ADMINISTRATION | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2035000 | FY 2023: 147000
TK-6155 | PUBLIC TRANSIT | POLK COUNTY TRANSPORTATION | ADMINISTRATION | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 227000 | FY 2023: 28000
TK-6155 | PUBLIC TRANSIT | POLK COUNTY TRANSPORTATION | ADMINISTRATION | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 368000
TK-6155 | PUBLIC TRANSIT | POLK COUNTY TRANSPORTATION | ADMINISTRATION | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 73000 | FY 2023: 9000
TK-6156 | PUBLIC TRANSIT | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION | 8 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 674000
TK-6156 | PUBLIC TRANSIT | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION | 8 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 3601000 | FY 2023: 279000
TK-6156 | PUBLIC TRANSIT | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION | 8 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 415000 | FY 2023: 52000
TK-6156 | PUBLIC TRANSIT | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION | 8 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 136000 | FY 2023: 17000
TK-6158 | PUBLIC TRANSIT | ROBESON COUNTY | ADMINISTRATION | 6 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2080000 | FY 2023: 160000
TK-6158 | PUBLIC TRANSIT | ROBESON COUNTY | ADMINISTRATION | 6 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 240000 | FY 2023: 30000
TK-6158 | PUBLIC TRANSIT | ROBESON COUNTY | ADMINISTRATION | 6 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 80000 | FY 2023: 10000
TK-6158 | PUBLIC TRANSIT | ROBESON COUNTY | ADMINISTRATION | 6 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 400000
TK-6159 | PUBLIC TRANSIT | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 352000
TK-6159 | PUBLIC TRANSIT | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1841000 | FY 2023: 142000
TK-6159 | PUBLIC TRANSIT | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 208000 | FY 2023: 26000
TK-6159 | PUBLIC TRANSIT | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 72000 | FY 2023: 9000
TK-6160 | PUBLIC TRANSIT | ROWAN COUNTY | ADMINISTRATION | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1885000 | FY 2023: 146000
TK-6160 | PUBLIC TRANSIT | ROWAN COUNTY | ADMINISTRATION | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 215000 | FY 2023: 27000
TK-6160 | PUBLIC TRANSIT | ROWAN COUNTY | ADMINISTRATION | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 362000
TK-6160 | PUBLIC TRANSIT | ROWAN COUNTY | ADMINISTRATION | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 93000 | FY 2023: 9000
TK-6161 | PUBLIC TRANSIT | RUTHERFORD COUNTY | ADMINISTRATION | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 392000
TK-6161 | PUBLIC TRANSIT | RUTHERFORD COUNTY | ADMINISTRATION | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2049000 | FY 2023: 158000
TK-6161 | PUBLIC TRANSIT | RUTHERFORD COUNTY | ADMINISTRATION | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 232000 | FY 2023: 29000
TK-6161 | PUBLIC TRANSIT | RUTHERFORD COUNTY | ADMINISTRATION | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 80000 | FY 2023: 10000
TK-6162 | PUBLIC TRANSIT | SAMPSON COUNTY | ADMINISTRATION | 3 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1640000 | FY 2023: 126000
TK-6162 | PUBLIC TRANSIT | SAMPSON COUNTY | ADMINISTRATION | 3 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 192000 | FY 2023: 24000
TK-6162 | PUBLIC TRANSIT | SAMPSON COUNTY | ADMINISTRATION | 3 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 64000 | FY 2023: 8000
TK-6162 | PUBLIC TRANSIT | SAMPSON COUNTY | ADMINISTRATION | 3 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 316000
TK-6163 | PUBLIC TRANSIT | SCOTLAND COUNTY | ADMINISTRATION | 8 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 236000
TK-6163 | PUBLIC TRANSIT | SCOTLAND COUNTY | ADMINISTRATION | 8 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1188000 | FY 2023: 92000
TK-6163 | PUBLIC TRANSIT | SCOTLAND COUNTY | ADMINISTRATION | 8 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 136000 | FY 2023: 17000
TK-6163 | PUBLIC TRANSIT | SCOTLAND COUNTY | ADMINISTRATION | 8 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 48000 | FY 2023: 6000
TK-6164 | PUBLIC TRANSIT | SCUSA TRANSPORTATION | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 452000
TK-6164 | PUBLIC TRANSIT | SCUSA TRANSPORTATION | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2352000 | FY 2023: 181000
TK-6164 | PUBLIC TRANSIT | SCUSA TRANSPORTATION | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 272000 | FY 2023: 34000
TK-6164 | PUBLIC TRANSIT | SCUSA TRANSPORTATION | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 88000 | FY 2023: 11000
TK-6165 | PUBLIC TRANSIT | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 1659000 | FY 2023: 127000
TK-6165 | PUBLIC TRANSIT | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 101000
TK-6165 | PUBLIC TRANSIT | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 132000
TK-6166 | PUBLIC TRANSIT | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 3108000 | FY 2023: 239000
TK-6166 | PUBLIC TRANSIT | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 360000 | FY 2023: 45000
TK-6166 | PUBLIC TRANSIT | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 577000
TK-6166 | PUBLIC TRANSIT | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 120000 | FY 2023: 15000
TK-6167 | PUBLIC TRANSIT | TRANSYLVANIA COUNTY | ADMINISTRATION | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 341000
TK-6167 | PUBLIC TRANSIT | TRANSYLVANIA COUNTY | ADMINISTRATION | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1820000 | FY 2023: 161000
TK-6167 | PUBLIC TRANSIT | TRANSYLVANIA COUNTY | ADMINISTRATION | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 126000
TK-6167 | PUBLIC TRANSIT | TRANSYLVANIA COUNTY | ADMINISTRATION | 14 | Land-of-Sky RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 54000
TK-6168 | PUBLIC TRANSIT | TYRELL COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 44000
TK-6168 | PUBLIC TRANSIT | TYRELL COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 242000 | FY 2023: 22000
TK-6168 | PUBLIC TRANSIT | TYRELL COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 3000
TK-6168 | PUBLIC TRANSIT | TYRELL COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 19000
TK-6169 | PUBLIC TRANSIT | UNION COUNTY | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2167000 | FY 2023: 147000
TK-6169 | PUBLIC TRANSIT | UNION COUNTY | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 209000 | FY 2023: 27000
TK-6169 | PUBLIC TRANSIT | UNION COUNTY | ADMINISTRATION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 139000 | FY 2023: 9000
TK-6170 | PUBLIC TRANSIT | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 455000 | FY 2023: 59000
TK-6170 | PUBLIC TRANSIT | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 1756000 | FY 2023: 225000
TK-6170 | PUBLIC TRANSIT | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2416000 | FY 2023: 111000
TK-6170 | PUBLIC TRANSIT | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 795000
TK-6171 | PUBLIC TRANSIT | WASHINGTON COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 929000 | FY 2023: 72000
TK-6171 | PUBLIC TRANSIT | WASHINGTON COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 104000 | FY 2023: 13000
TK-6171 | PUBLIC TRANSIT | WASHINGTON COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 32000 | FY 2023: 4000
TK-6171 | PUBLIC TRANSIT | WASHINGTON COUNTY | ADMINISTRATION | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 176000
TK-6172 | PUBLIC TRANSIT | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2376000 | FY 2023: 183000
TK-6172 | PUBLIC TRANSIT | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 272000 | FY 2023: 34000
TK-6172 | PUBLIC TRANSIT | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 456000
TK-6172 | PUBLIC TRANSIT | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 88000 | FY 2023: 11000
TK-6173 | PUBLIC TRANSIT | WILSON COUNTY | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 225000
TK-6173 | PUBLIC TRANSIT | WILSON COUNTY | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 912000 | FY 2023: 69000
TK-6173 | PUBLIC TRANSIT | WILSON COUNTY | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 105000 | FY 2023: 13000
TK-6173 | PUBLIC TRANSIT | WILSON COUNTY | ADMINISTRATION | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 33000 | FY 2023: 4000
TK-6174 | PUBLIC TRANSIT | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 4432000 | FY 2023: 341000
TK-6174 | PUBLIC TRANSIT | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 512000 | FY 2023: 64000
TK-6174 | PUBLIC TRANSIT | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 890000
TK-6174 | PUBLIC TRANSIT | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 168000 | FY 2023: 21000
TK-6175 | PUBLIC TRANSIT | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 290000
TK-6175 | PUBLIC TRANSIT | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1508000 | FY 2023: 116000
TK-6175 | PUBLIC TRANSIT | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 176000 | FY 2023: 22000
TK-6175 | PUBLIC TRANSIT | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 56000 | FY 2023: 7000
TK-6176 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2314000 | FY 2023: 218000
TK-6176 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 66000
TK-6176 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 461000
TK-6176 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 22000
TK-6177 | PUBLIC TRANSIT | DUPLIN COUNTY | ADMINISTRATION | 3 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 2593000 | FY 2023: 168000
TK-6177 | PUBLIC TRANSIT | DUPLIN COUNTY | ADMINISTRATION | 3 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 248000 | FY 2023: 31000
TK-6177 | PUBLIC TRANSIT | DUPLIN COUNTY | ADMINISTRATION | 3 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 80000 | FY 2023: 10000
TK-6178 | PUBLIC TRANSIT | LENOIR COUNTY | ADMINISTRATION | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 3288000 | FY 2023: 210000
TK-6178 | PUBLIC TRANSIT | LENOIR COUNTY | ADMINISTRATION | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 314000 | FY 2023: 39000
TK-6178 | PUBLIC TRANSIT | LENOIR COUNTY | ADMINISTRATION | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 105000 | FY 2023: 13000
TK-6179 | PUBLIC TRANSIT | IREDELL COUNTY | ADMINISTRATION | 12 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 3120000 | FY 2023: 260000
TK-6181 | PUBLIC TRANSIT | STATEWIDE | 5311 ADMINISTRATIVE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 15025000
TL-0001 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | CONSTRUCT AN URBAN FIXED-ROUTE SATELLITE TRANSFER FACILITY FOR JACKSONVILLE TRANSIT TO INCLUDE PUBLIC PARKING, SHELTERS, RESTROOMS AND PESSENGER TERMINAL | 3 | Jacksonville Urban Area MPO | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 1000000
TL-0002 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | CONSTRUCT PEDESTRIAN ACCESS AND SAFETY IMPROVEMENTS FOR JACKSONVILLE TRANSIT WITHIN 1/2 MILE OF HIGH VOLUME URBAN FIXED ROUTE BUS STOPS. IMPROVEMENTS WILL INCLUDE NEW SIDE WALK CONNECTIONS, ADA RETROFIT OF EXISTING SIDE WALKS AND CONSTRUCTION OF HIGH VISIBILITY CROSSWALKS AT KEY ROADWAY INTERSECTIONS. | 3 | Jacksonville Urban Area MPO | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 900000
TL-0005 | PUBLIC TRANSIT | CONCORD KANNAPOLIS AREA TRANSIT | EXPANSION BUS | 9, 10 | Cabarrus-Rowan MPO |  | DIVISION 9, 10 |  | BGDA | CONSTRUCTION | 580000
TL-0005 | PUBLIC TRANSIT | CONCORD KANNAPOLIS AREA TRANSIT | EXPANSION BUS | 9, 10 | Cabarrus-Rowan MPO |  | DIVISION 9, 10 |  | L | CONSTRUCTION | 145000
TL-0006 | PUBLIC TRANSIT | GO RALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT WESTERN CORRIDOR (DOWNTOWN RALEIGH TO DOWNTOWN CARY). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 45168000 | FY 2023: 30254000
TL-0006 | PUBLIC TRANSIT | GO RALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT WESTERN CORRIDOR (DOWNTOWN RALEIGH TO DOWNTOWN CARY). | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 1500000
TL-0007 | PUBLIC TRANSIT | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN ON BUS RAPID TRANSIT IN WAKE TRANSIT PLAN NORTHERN CORRIDOR. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 5540000
TL-0008 | PUBLIC TRANSIT | GOTRIANGLE | EARLY PROJECT DEVELOPMENT ACTIVITIES FOR COMMUTER RAIL FROM GARNER TO WESTERN DURHAM | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 9200000
TL-0009 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | FLEET SERVICE BUILDING EXPANSION. | 2 | Greenville Urban Area MPO |  | PUBLIC TRANSIT |  | CARES | CONSTRUCTION | 878000
TL-0009 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | FLEET SERVICE BUILDING EXPANSION. | 2 | Greenville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 98000
TL-0011 | PUBLIC TRANSIT | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | ENGINEERING | 32000
TL-0011 | PUBLIC TRANSIT | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | RIGHT-OF-WAY | 9000
TL-0011 | PUBLIC TRANSIT | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 126000
TL-0011 | PUBLIC TRANSIT | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | ENGINEERING | 32000
TL-0011 | PUBLIC TRANSIT | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | CONSTRUCTION | 126000
TL-0011 | PUBLIC TRANSIT | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | BGDA | RIGHT-OF-WAY | 9000
TL-0012 | PUBLIC TRANSIT | GTA | EXPANDED SUNDAY SERVICE, NEW SERVICE OPERATIONAL FUNDING | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | CMAQ | OPERATIONS | 2164000
TL-0012 | PUBLIC TRANSIT | GTA | EXPANDED SUNDAY SERVICE, NEW SERVICE OPERATIONAL FUNDING | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 541000
TL-0013 | PUBLIC TRANSIT | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT SOUTHERN CORRIDOR ( DOWNTOWN RALEIGH TO DOWNTOWN GARNER) | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 27777000
TL-0013 | PUBLIC TRANSIT | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT SOUTHERN CORRIDOR ( DOWNTOWN RALEIGH TO DOWNTOWN GARNER) | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 1500000
TL-0014 | PUBLIC TRANSIT | DAVIDSON COUNTY TRANSPORTATION SYSTEM | INSTALLING COVERED BUS SHELTERS WITH ADA ACCESS TO MAJOR STOPS SUCH AS WALMART AND BIG LOTS. INSTALL SIMME SEATS AT THE REMAINDER OF BUS STOPS. SIMME SEATS PROVIDE TWO SEATS ATTACHED TO THE BUS STOP SIGN POLE. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CAPITAL | 28000
TL-0014 | PUBLIC TRANSIT | DAVIDSON COUNTY TRANSPORTATION SYSTEM | INSTALLING COVERED BUS SHELTERS WITH ADA ACCESS TO MAJOR STOPS SUCH AS WALMART AND BIG LOTS. INSTALL SIMME SEATS AT THE REMAINDER OF BUS STOPS. SIMME SEATS PROVIDE TWO SEATS ATTACHED TO THE BUS STOP SIGN POLE. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CAPITAL | 112000
TL-0015 | PUBLIC TRANSIT | TAR RIVER TRANSIT | PURCHASE AND INSTALL 20 BUS SHELTERS | 4 | Rocky Mount Urban Area MPO |  | PUBLIC TRANSIT |  | CARES | CAPITAL | 150000
TL-0016 | PUBLIC TRANSIT | TAR RIVER TRANSIT | UPDATE THE TAR RIVER TANSIT AUTOMATED VEHICLE LOCATOR SYSTEM | 4 | Rocky Mount Urban Area MPO |  | PUBLIC TRANSIT |  | CARES | CAPITAL | 300000
TL-0017 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPITAL IMPROVEMENT PROJECT TO SECURE AUTOMATIC PASSENGER COUNTER (APC) TECHNOLOGY FOR THE PURPOSE OF COLLECTING STOP LEVEL BOARDINGS AND ALIGHTINGS FOR FIXED ROUTE PUBLIC TRANSPORTATION SERVICES. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CAPITAL | 160000
TL-0017 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPITAL IMPROVEMENT PROJECT TO SECURE AUTOMATIC PASSENGER COUNTER (APC) TECHNOLOGY FOR THE PURPOSE OF COLLECTING STOP LEVEL BOARDINGS AND ALIGHTINGS FOR FIXED ROUTE PUBLIC TRANSPORTATION SERVICES. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CAPITAL | 40000
TL-0018 | PUBLIC TRANSIT | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE | 7 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | CMAQ | CONSTRUCTION | 400000 | FY 2023: 320000
TL-0018 | PUBLIC TRANSIT | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE | 7 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 100000 | FY 2023: 80000
TL-0019 | PUBLIC TRANSIT | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 125000
TL-0019 | PUBLIC TRANSIT | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. | 5 | Capital Area MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 42000
TL-0019 | PUBLIC TRANSIT | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. | 5 | Capital Area MPO |  | EXEMPT |  | L | CONSTRUCTION | 286000
TL-0019 | PUBLIC TRANSIT | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 858000
TL-0019 | PUBLIC TRANSIT | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. | 5 | Capital Area MPO |  | EXEMPT |  | L | ENGINEERING | 13000
TL-0019 | PUBLIC TRANSIT | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. | 5 | Capital Area MPO |  | EXEMPT |  | CMAQ | ENGINEERING | 38000
TL-0020 | RAIL | GORALEIGH | RALEIGH UNION STATION BUS FACILITY INTER-CITY/COMMUTER RAIL PARK AND RIDE | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | CMAQ | CONSTRUCTION | 4500000 | FY 2023: 2000000
TL-0020 | RAIL | GORALEIGH | RALEIGH UNION STATION BUS FACILITY INTER-CITY/COMMUTER RAIL PARK AND RIDE | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 1125000 | FY 2023: 500000
TL-0021 | PUBLIC TRANSIT | CONCORD | PURCHASE NEW 35 FOOT HYBRID ELECTRIC HEAVY DUTY LOW FLOOR BUS | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | BGDACV | CONSTRUCTION | 602000 | FY 2023: 602000
TL-0021 | PUBLIC TRANSIT | CONCORD | PURCHASE NEW 35 FOOT HYBRID ELECTRIC HEAVY DUTY LOW FLOOR BUS | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | L | CONSTRUCTION | 123000 | FY 2023: 123000
TL-0023 | PUBLIC TRANSIT | GORALEIGH | BUILD PARK AND RIDE FACILITY AT GORMAN STREET AT I-40 IN RALEIGH | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 1614000 | FY 2027: 1614000
TL-0023 | PUBLIC TRANSIT | GORALEIGH | BUILD PARK AND RIDE FACILITY AT GORMAN STREET AT I-40 IN RALEIGH | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | ENGINEERING | 1432000 | FY 2025: 1432000
TL-0025 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT AUTHORITY | THE INNOVATIVE COORDINATED ACCESS AND MOBILITY (ICAM) GRANT WILL BE USED TO IMPROVE PARATRANSIT TRACKING AND ACCESSIBILITY THROUGH GPS AND NOTIFICATION SERVICES, AS WELL AS PROVIDE MOBILE TICKETING OPTIONS FOR WINSTON SALEM TRANSIT AUTHORITY`S (WSTA) FIXED ROUTE BUS SERVICES. | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 80000 | FY 2023: 80000
TL-0025 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT AUTHORITY | THE INNOVATIVE COORDINATED ACCESS AND MOBILITY (ICAM) GRANT WILL BE USED TO IMPROVE PARATRANSIT TRACKING AND ACCESSIBILITY THROUGH GPS AND NOTIFICATION SERVICES, AS WELL AS PROVIDE MOBILE TICKETING OPTIONS FOR WINSTON SALEM TRANSIT AUTHORITY`S (WSTA) FIXED ROUTE BUS SERVICES. | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 320000 | FY 2023: 320000
TL-0029 | PUBLIC TRANSIT | LINK TRANSIT | CAPITAL IMPROVEMENTS FOR TRANSIT VEHICLES. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1255000 | FY 2023: 185000; FY 2024: 185000; FY 2025: 185000; FY 2026: 185000; FY 2027: 185000; FY 2028: 185000
TL-0029 | PUBLIC TRANSIT | LINK TRANSIT | CAPITAL IMPROVEMENTS FOR TRANSIT VEHICLES. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 295000 | FY 2023: 45000; FY 2024: 45000; FY 2025: 45000; FY 2026: 45000; FY 2027: 45000; FY 2028: 45000
TL-0030 | PUBLIC TRANSIT | INDIAN TRAIL | INSTALL TYPE TWO ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSINGS PATH PARK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | CRPDA | CONSTRUCTION | 468000 | FY 2023: 468000
TL-0030 | PUBLIC TRANSIT | INDIAN TRAIL | INSTALL TYPE TWO ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSINGS PATH PARK. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 117000 | FY 2023: 117000
TL-0031 | PUBLIC TRANSIT | UNION COUNTY TRANSPORTATION | LOW EMISSION ALTERNATIVE FUEL CONVERSION (MOTOR POOL FACILITY). | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | CRPDA | CONSTRUCTION | 160000 | FY 2024: 160000
TL-0031 | PUBLIC TRANSIT | UNION COUNTY TRANSPORTATION | LOW EMISSION ALTERNATIVE FUEL CONVERSION (MOTOR POOL FACILITY). | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 40000 | FY 2024: 40000
TL-0032 | PUBLIC TRANSIT | CATS | INSTALL ELECTRIC BUS CHARGERS AT NORTH DAVIDSON AND SOUTH TRYON BUS GARAGES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | CRPDA | CONSTRUCTION | 6546000 | FY 2023: 6546000
TL-0032 | PUBLIC TRANSIT | CATS | INSTALL ELECTRIC BUS CHARGERS AT NORTH DAVIDSON AND SOUTH TRYON BUS GARAGES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | L | CONSTRUCTION | 1637000 | FY 2023: 1637000
TL-1000 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PROGRAM ADMINISTRATION | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 262000 | FY 2023: 46000; FY 2024: 30000; FY 2025: 30000
TM-0002 | PUBLIC TRANSIT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311 ADMIN/OPERATING/CAPITAL AND 5311(F) | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 3950000 | FY 2023: 3950000
TM-0004 | PUBLIC TRANSIT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311CAPITAL-ADTAP) | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 150000 | FY 2023: 150000
TM-0010 | PUBLIC TRANSIT | STATEWIDE | 5307 OPERATING FUNDS | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 142000
TM-0012 | PUBLIC TRANSIT | STATEWIDE | 5307 OPERATING FUNDS | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 129000
TM-0014 | PUBLIC TRANSIT | STATEWIDE | 5307 OPERATING FUNDS | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 75000
TM-0015 | PUBLIC TRANSIT | STATEWIDE | 5307 OPERATING FUNDS | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | ADMINISTRATIVE | 145000
TM-0020 | PUBLIC TRANSIT | STATEWIDE | 5307 OPERATING FUNDS | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | ADMINISTRATIVE | 45000
TM-0020 | PUBLIC TRANSIT | STATEWIDE | 5307 OPERATING FUNDS | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1073000 | FY 2023: 1073000
TM-0020 | PUBLIC TRANSIT | STATEWIDE | 5307 OPERATING FUNDS | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | L | OPERATIONS | 1073000 | FY 2023: 1073000
TM-0022 | PUBLIC TRANSIT | STATEWIDE | 5307 OPERATING FUNDS | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | PUBLIC TRANSIT |  | 5307 | ADMINISTRATIVE | 18000
TM-0023 | PUBLIC TRANSIT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5310 ADMIN/OPERATING/CAPITAL PURCHASE SERVICE) | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 1022000 | FY 2023: 522000; FY 2024: 500000
TM-0024 | PUBLIC TRANSIT | STATEWIDE | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5312 | OPERATIONS | 250000
TM-0024 | PUBLIC TRANSIT | STATEWIDE | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | OPERATIONS | 63000
TM-0025 | PUBLIC TRANSIT | NCDOT | 5310 OPERATING PROJECTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 2106000
TM-0025 | PUBLIC TRANSIT | NCDOT | 5310 OPERATING PROJECTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | OPERATIONS | 2106000
TM-0026 | PUBLIC TRANSIT | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CAPITAL | 427000
TM-0026 | PUBLIC TRANSIT | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CAPITAL | 183000
TM-0027 | PUBLIC TRANSIT | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 32358000 | FY 2023: 15428000; FY 2024: 2600000
TM-0027 | PUBLIC TRANSIT | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 10868000 | FY 2023: 2868000; FY 2024: 320000
TM-0027 | PUBLIC TRANSIT | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 2204000 | FY 2023: 988000; FY 2024: 320000
TM-0028 | PUBLIC TRANSIT | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 2124000 | FY 2023: 647000; FY 2024: 660000
TM-0028 | PUBLIC TRANSIT | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | OPERATIONS | 2124000 | FY 2023: 647000; FY 2024: 660000
TM-0028 | PUBLIC TRANSIT | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | OPERATIONS | 100000 | FY 2024: 100000
TM-0029 | PUBLIC TRANSIT | NCDOT | 5311 STATE ADMINISTRATIVE FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 3361000
TM-0030 | PUBLIC TRANSIT | NCDOT | 5311 ADTAP STATE ADMINISTRATIVE FUNDS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | ADTAP | ADMINISTRATIVE | 177000
TM-0031 | PUBLIC TRANSIT | NCDOT | RTAP STATEWIDE FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | RTAP | ADMINISTRATIVE | 1628000 | FY 2023: 698000; FY 2024: 650000
TM-0032 | PUBLIC TRANSIT | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 16834000 | FY 2023: 12607000
TM-0032 | PUBLIC TRANSIT | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | OPERATIONS | 12607000 | FY 2023: 12607000
TM-0033 | PUBLIC TRANSIT | NCDOT | 5311(F) INTERCITY BUS - STATE ADMIN | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | ADMINISTRATIVE | 494000
TM-0035 | PUBLIC TRANSIT | GOTRIANGLE | OPERATING ASSISTANCE FOR TOWN OF MORRISVILLE NODE BASED SMART SHUTTLE. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 3621000 | FY 2023: 695000; FY 2024: 712000; FY 2025: 730000; FY 2026: 740000
TM-0036 | PUBLIC TRANSIT | STATEWIDE | 5310 STATE ADMINISTRATIVE FUNDS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 567000
TM-0038 | PUBLIC TRANSIT | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS. (ARP/CRRSAA 5301 OPERATING) | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | FEDT | ADMINISTRATIVE | 1415000 | FY 2023: 1400000; FY 2024: 15000
TM-0038 | PUBLIC TRANSIT | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS. (ARP/CRRSAA 5301 OPERATING) | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 86000 | FY 2024: 86000
TM-0039 | PUBLIC TRANSIT | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 1000000 | FY 2023: 500000
TM-0039 | PUBLIC TRANSIT | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CONSTRUCTION | 1000000 | FY 2023: 500000
TM-0040 | PUBLIC TRANSIT | CHARLOTTE TRANSIT AREA | FIRST MILE-LAST MILE PROJECT WILL PLAN NEW AND REPLACEMENT CIRCULATOR ROUTES WITH A NEW ON-DEMAND STRATEGY OF MICRO-TRANSIT ZONES TO REDUCE TRAVEL TIMES AND IMPROVE CONNECTIVITY TO HIGH-FREQUENCY ROUTES AT MOBILITY HUBS. | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | ARP | PLANNING | 750000 | FY 2023: 750000
TM-0041 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | PUBLIC TRANSIT |  | CMAQ | CAPITAL | 2040000 | FY 2023: 2040000
TM-0041 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | PUBLIC TRANSIT |  | DP | CONSTRUCTION | 15000000 | FY 2024: 15000000
TM-0041 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | PUBLIC TRANSIT |  | L | CONSTRUCTION | 70718000 | FY 2024: 70718000
TM-0041 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | PUBLIC TRANSIT |  | L | CAPITAL | 668000 | FY 2023: 668000
TM-0042 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | S | ACQUISITION | 1393000 | FY 2023: 1393000
TM-0042 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | L | ACQUISITION | 475000 | FY 2023: 475000
TM-0042 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | CMAQ | ACQUISITION | 871000 | FY 2023: 871000
TM-0043 | PUBLIC TRANSIT | GODURHAM | ACQUISITION OF SIX (6) ELECTRIC TRANSIT BUSES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | L | ACQUISITION | 846000 | FY 2023: 846000
TM-0043 | PUBLIC TRANSIT | GODURHAM | ACQUISITION OF SIX (6) ELECTRIC TRANSIT BUSES. | 5 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | CMAQ | ACQUISITION | 883000 | FY 2023: 883000
TM-0045 | PUBLIC TRANSIT | GASTONIA TRANSIT | GASTONIA TRANSIT PAYMENT KIOSK. | 12 | Gaston-Cleveland-Lincoln MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 175000 | FY 2023: 175000
TM-0045 | PUBLIC TRANSIT | GASTONIA TRANSIT | GASTONIA TRANSIT PAYMENT KIOSK. | 12 | Gaston-Cleveland-Lincoln MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 44000 | FY 2023: 44000
TM-0046 | PUBLIC TRANSIT | LINK TRANSIT | PREVENTATIVE MAINTENANCE. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2870000 | FY 2023: 410000; FY 2024: 410000; FY 2025: 410000; FY 2026: 410000; FY 2027: 410000; FY 2028: 410000
TM-0046 | PUBLIC TRANSIT | LINK TRANSIT | PREVENTATIVE MAINTENANCE. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 714000 | FY 2023: 102000; FY 2024: 102000; FY 2025: 102000; FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-5138 | PUBLIC TRANSIT | CITY OF ASHEVILLE | JARC OPERATIONS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 3037 | OPERATIONS | 766000
TM-5138 | PUBLIC TRANSIT | CITY OF ASHEVILLE | JARC OPERATIONS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 766000
TM-5163 | PUBLIC TRANSIT | CITY OF ASHEVILLE | CITY OF ASHEVILLE ADMINISTRATIVE OVERSIGHT OF JARC PROJECTS IN THE ASHEVILLE UAZ | 13, 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 85000
TM-5301 | PUBLIC TRANSIT | SUB REGIONAL | STATE ADMINISTRATION - JOB ACCESS NON-URBAN | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5316 | ADMINISTRATIVE | 5592000
TM-5309 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5316 | OPERATIONS | 550000 | FY 2023: 55000; FY 2024: 55000; FY 2025: 55000
TM-5309 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 550000 | FY 2023: 55000; FY 2024: 55000; FY 2025: 55000
TM-6108 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE - NON-URBAN | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 736000 | FY 2023: 92000
TM-6108 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE - NON-URBAN | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5316 | OPERATIONS | 1902000 | FY 2023: 92000
TN-5102 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | OPERATING ASSISTANCE - NEW FREEDOM - URBAN | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 504000 | FY 2023: 63000
TN-5102 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | OPERATING ASSISTANCE - NEW FREEDOM - URBAN | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5317 | OPERATIONS | 1260000 | FY 2023: 63000
TN-5112 | PUBLIC TRANSIT | SUB REGIONAL | STATE ADMINISTRATION - NEW FREEDOM - 5317 | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5317 | ADMINISTRATIVE | 4270000
TN-6109 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE - SMALL-URBAN | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5317 | OPERATIONS | 270000 | FY 2023: 15000
TN-6109 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE - SMALL-URBAN | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 120000 | FY 2023: 15000
TN-6116 | PUBLIC TRANSIT | WAKE COORDINATED TRANSIT SERVICE | WAKE COORDINATED TRANSIT SERVICES OPERATING ASSISTANCE. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 4070000 | FY 2023: 644000; FY 2024: 725000; FY 2025: 800000; FY 2026: 868000
TN-6125 | PUBLIC TRANSIT | STATEWIDE | 5317 NEW FREEDOM | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | OPERATIONS | 793000 | FY 2023: 88000; FY 2024: 90000; FY 2025: 92000; FY 2026: 94000; FY 2027: 96000
TN-6125 | PUBLIC TRANSIT | STATEWIDE | 5317 NEW FREEDOM | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | FEP | OPERATIONS | 3963000 | FY 2023: 440000; FY 2024: 450000; FY 2025: 460000; FY 2026: 470000; FY 2027: 480000
TO-0002 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1094000
TO-0002 | PUBLIC TRANSIT | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 274000
TO-0003 | PUBLIC TRANSIT | STATEWIDE | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIGNS OF HUMAN TRAFFICKING. THE DEPARTMENT ALSO WILL DEVELOP HUMAN TRAFFICKING AWARENESS EDUCATIONAL MATERIALS TO BE POSTED ON TRANSIT VEHICLES AND STATIONS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5307 | ADMINISTRATIVE | 30000
TO-0003 | PUBLIC TRANSIT | STATEWIDE | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIGNS OF HUMAN TRAFFICKING. THE DEPARTMENT ALSO WILL DEVELOP HUMAN TRAFFICKING AWARENESS EDUCATIONAL MATERIALS TO BE POSTED ON TRANSIT VEHICLES AND STATIONS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5312 | ADMINISTRATIVE | 120000
TO-0004 | PUBLIC TRANSIT | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 176000 | FY 2023: 88000
TO-0004 | PUBLIC TRANSIT | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | PUBLIC TRANSIT |  | SSO | ADMINISTRATIVE | 704000 | FY 2023: 352000
TO-4075 | PUBLIC TRANSIT | CITY OF ASHEVILLE | TRANSIT OPERATIONS | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 3600000
TO-4075 | PUBLIC TRANSIT | CITY OF ASHEVILLE | TRANSIT OPERATIONS | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 7289000
TO-4075 | PUBLIC TRANSIT | CITY OF ASHEVILLE | TRANSIT OPERATIONS | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  |  | OPERATIONS | 1452000
TO-4075 | PUBLIC TRANSIT | CITY OF ASHEVILLE | TRANSIT OPERATIONS | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  |  |  | 484000
TO-4075 | PUBLIC TRANSIT | CITY OF ASHEVILLE | TRANSIT OPERATIONS | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 9600000
TO-4719 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 5546000 | FY 2023: 420000
TO-4719 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 2003000 | FY 2023: 210000
TO-4719 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 2651000 | FY 2023: 210000
TO-4726 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 4397000 | FY 2023: 540000
TO-4726 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 4058000 | FY 2023: 275000
TO-4726 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 10520000 | FY 2023: 540000
TO-4733 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 5818000 | FY 2023: 46000
TO-4733 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 2233000 | FY 2023: 204000
TO-4733 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 17307000 | FY 2023: 1000000
TO-4751 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 44402000 | FY 2023: 1797000
TO-4751 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 20510000 | FY 2023: 1197000
TO-4751 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 11511000 | FY 2023: 600000
TO-4779 | PUBLIC TRANSIT | CITY OF WILSON | OPERATING ASSISTANCE | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 12144000 | FY 2023: 908000
TO-4779 | PUBLIC TRANSIT | CITY OF WILSON | OPERATING ASSISTANCE | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 706000
TO-4779 | PUBLIC TRANSIT | CITY OF WILSON | OPERATING ASSISTANCE | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 2704000 | FY 2023: 208000
TO-4790 | PUBLIC TRANSIT | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 24018000 | FY 2023: 1202000
TO-4790 | PUBLIC TRANSIT | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 12988000 | FY 2023: 1202000
TO-4790 | PUBLIC TRANSIT | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 5588000 | FY 2023: 475000
TO-4923 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 2084000 | FY 2023: 109000; FY 2024: 105000; FY 2025: 101000; FY 2026: 97000; FY 2027: 93000
TO-4923 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 8199000 | FY 2023: 494000; FY 2024: 504000; FY 2025: 514000; FY 2026: 524000; FY 2027: 534000
TO-4923 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 3783000 | FY 2023: 385000; FY 2024: 399000; FY 2025: 413000; FY 2026: 427000; FY 2027: 441000
TO-4971 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 15143000 | FY 2023: 1647000; FY 2024: 1647000; FY 2025: 1647000; FY 2026: 1647000; FY 2027: 1647000; FY 2028: 1647000
TO-4971 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 18187000 | FY 2023: 2243000; FY 2024: 2243000; FY 2025: 2243000; FY 2026: 2243000; FY 2027: 2243000; FY 2028: 2243000
TO-4971 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 33330000 | FY 2023: 3890000; FY 2024: 3890000; FY 2025: 3890000; FY 2026: 3890000; FY 2027: 3890000; FY 2028: 3890000
TO-5024 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | 2 | New Bern Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1530000 | FY 2023: 275000
TO-5024 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | 2 | New Bern Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 1530000 | FY 2023: 275000
TO-5126 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 11992000
TO-5126 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 8332000
TO-5126 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 7004000
TO-5127 | PUBLIC TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 6607000 | FY 2023: 500000
TO-5127 | PUBLIC TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 3341000 | FY 2023: 250000
TO-5127 | PUBLIC TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 2250000 | FY 2023: 250000
TO-5128 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 58500000
TO-5128 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 85480000 | FY 2023: 14121000; FY 2024: 14580000; FY 2025: 14437000; FY 2026: 18036000
TO-5128 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 40308000 | FY 2023: 3000000
TO-5129 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 3226000 | FY 2023: 230000; FY 2024: 230000; FY 2025: 240000
TO-5129 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 300000
TO-5129 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 20513000 | FY 2023: 3859000; FY 2024: 3956000; FY 2025: 4054000; FY 2026: 4156000
TO-5130 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | OPERATING ASSISTANCE | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 39184000 | FY 2023: 2806000
TO-5131 | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | OPERATING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 27619000 | FY 2023: 1952000
TO-5131 | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | OPERATING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 31999000 | FY 2023: 4948000; FY 2024: 5087000; FY 2025: 6657000; FY 2026: 6838000
TO-5132 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 7530000 | FY 2023: 534000
TO-5133 | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | OPERATING ASSISTANCE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 50081000 | FY 2023: 3570000
TO-5134 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 7276000 | FY 2023: 750000; FY 2024: 750000; FY 2025: 750000; FY 2026: 750000; FY 2027: 750000; FY 2028: 750000
TO-5134 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 6476000 | FY 2023: 750000; FY 2024: 750000; FY 2025: 750000; FY 2026: 750000; FY 2027: 750000; FY 2028: 750000
TO-5134C | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | 7, 9 | High Point Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 4600000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
TO-5134C | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | 7, 9 | High Point Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 3900000 | FY 2023: 500000; FY 2024: 500000; FY 2025: 500000
TO-5135 | PUBLIC TRANSIT | CITY OF SALISBURY | OPERATING | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 3420000 | FY 2023: 285000; FY 2024: 285000; FY 2025: 285000; FY 2026: 285000; FY 2027: 285000
TO-5135 | PUBLIC TRANSIT | CITY OF SALISBURY | OPERATING | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 1920000 | FY 2023: 160000; FY 2024: 160000; FY 2025: 160000; FY 2026: 160000; FY 2027: 160000
TO-5135 | PUBLIC TRANSIT | CITY OF SALISBURY | OPERATING | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 430000
TO-5136 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 11817000 | FY 2023: 817000
TO-5137 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING ASSISTANCE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 200670000 | FY 2023: 12552000; FY 2024: 12552000; FY 2025: 12552000
TO-5138 | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 11112000 | FY 2023: 1100000
TO-5138 | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 4072000 | FY 2023: 313000
TO-5138 | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 19684000 | FY 2023: 1300000
TO-5139 | PUBLIC TRANSIT | CITY OF SALISBURY | OPERATING - FREE FARE | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 96000 | FY 2023: 8000; FY 2024: 8000; FY 2025: 8000; FY 2026: 8000; FY 2027: 8000
TO-5139 | PUBLIC TRANSIT | CITY OF SALISBURY | OPERATING - FREE FARE | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | CMAQ | OPERATIONS | 408000 | FY 2023: 34000; FY 2024: 34000; FY 2025: 34000; FY 2026: 34000; FY 2027: 34000
TO-5142 | PUBLIC TRANSIT | GASTONIA TRANSIT | OPERATING ASSISTANCE | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 8289000
TO-5142 | PUBLIC TRANSIT | GASTONIA TRANSIT | OPERATING ASSISTANCE | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 5909000
TO-5142 | PUBLIC TRANSIT | GASTONIA TRANSIT | OPERATING ASSISTANCE | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 3470000 | FY 2023: 267000
TO-5144 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE (LESS THAN 75 BUSES) MAP 21 | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 4630000
TO-5144 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE (LESS THAN 75 BUSES) MAP 21 | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 4630000
TO-5149 | PUBLIC TRANSIT | IREDELL COUNTY | OPERATING ASSISTANCE FOR THE IREDELL COUNTY AREA TRANSPORTATION SYSTEM (ICATS) | 12 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 1174000
TO-5149 | PUBLIC TRANSIT | IREDELL COUNTY | OPERATING ASSISTANCE FOR THE IREDELL COUNTY AREA TRANSPORTATION SYSTEM (ICATS) | 12 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1440000
TO-5201 | PUBLIC TRANSIT | CITY OF SALISBURY | OPERATING ASSISTANCE | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | CMAQ | OPERATIONS | 1311000
TO-5201 | PUBLIC TRANSIT | CITY OF SALISBURY | OPERATING ASSISTANCE | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 3164000 | FY 2023: 226000
TO-5204 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1121000
TO-5204 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 1121000
TO-5206 | PUBLIC TRANSIT | DURHAM | 5307 OPERATING FUNDS NC 2019-060-01-P11 | 7 | Durham-Chapel Hill-Carrboro MPO | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 311000
TO-5209 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 4278000 | FY 2023: 509000; FY 2024: 509000; FY 2025: 509000; FY 2026: 509000; FY 2027: 353000; FY 2028: 353000
TO-5209 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | PUBLIC TRANSIT |  | L | OPERATIONS | 5614000 | FY 2023: 509000; FY 2024: 509000; FY 2025: 509000; FY 2026: 509000; FY 2027: 1021000; FY 2028: 1021000
TO-5209 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE | 7 | Greensboro Urban Area MPO | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 4676000 | FY 2023: 668000; FY 2024: 668000; FY 2025: 668000; FY 2026: 668000; FY 2027: 668000; FY 2028: 668000
TO-5214 | PUBLIC TRANSIT | ALAMANACE COUNTY TRANSPORTATION | OPERATING FOR ALAMANCE COUNTY TRANSPORTATION IN THE BURLINGTON URBAN AREA - THROUGH NCDOT | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 7603000 | FY 2023: 680000; FY 2024: 805000; FY 2025: 805000; FY 2026: 805000; FY 2027: 805000; FY 2028: 805000
TO-5214 | PUBLIC TRANSIT | ALAMANACE COUNTY TRANSPORTATION | OPERATING FOR ALAMANCE COUNTY TRANSPORTATION IN THE BURLINGTON URBAN AREA - THROUGH NCDOT | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 6277000 | FY 2023: 340000; FY 2024: 805000; FY 2025: 805000; FY 2026: 805000; FY 2027: 805000; FY 2028: 805000
TO-5215 | PUBLIC TRANSIT | DAVIDSON COUNTY | OPERATING FUNIDING FOR DAVIDSON COUNTY TRANSPORATION FOR SERVICE IN THE HIGH POINT URBAN AREA - THROUGH NCDOT | 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 270000
TO-5215 | PUBLIC TRANSIT | DAVIDSON COUNTY | OPERATING FUNIDING FOR DAVIDSON COUNTY TRANSPORATION FOR SERVICE IN THE HIGH POINT URBAN AREA - THROUGH NCDOT | 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 270000
TO-5216 | PUBLIC TRANSIT | GUILFORD COUNTY TRANSPORTATION | OPERATING FUNDING FOR GUILFORD COUNTY THROUGH HIGH-POINT MPO | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 525000 | FY 2023: 55000; FY 2024: 60000; FY 2025: 65000; FY 2026: 70000; FY 2027: 75000
TO-5216 | PUBLIC TRANSIT | GUILFORD COUNTY TRANSPORTATION | OPERATING FUNDING FOR GUILFORD COUNTY THROUGH HIGH-POINT MPO | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 980000 | FY 2023: 110000; FY 2024: 120000; FY 2025: 130000; FY 2026: 140000; FY 2027: 150000
TO-5220 | PUBLIC TRANSIT | BURLINGTON -GRAHAM | 5307 OPERATING FUNDS NC-2019-060-01-P10 | 7 | Burlington-Graham MPO | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY 2020 GRANTS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 282000
TO-5221 | PUBLIC TRANSIT | GUILFORD COUNTY TRANSPORTATION | OPERATING- RURAL TRANSIT | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | PUBLIC TRANSIT |  | L | OPERATIONS | 280000 | FY 2023: 35000; FY 2024: 35000; FY 2025: 35000; FY 2026: 35000; FY 2027: 35000; FY 2028: 35000
TO-5221 | PUBLIC TRANSIT | GUILFORD COUNTY TRANSPORTATION | OPERATING- RURAL TRANSIT | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 280000 | FY 2023: 35000; FY 2024: 35000; FY 2025: 35000; FY 2026: 35000; FY 2027: 35000; FY 2028: 35000
TO-6061 | PUBLIC TRANSIT | GASTONIA TRANSIT | OPERATING EXPENSES | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 2086000
TO-6061 | PUBLIC TRANSIT | GASTONIA TRANSIT | OPERATING EXPENSES | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | PUBLIC TRANSIT |  | L | OPERATIONS | 2086000
TO-6101 | PUBLIC TRANSIT | APPALCART | OPERATING ASSISTANCE | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 17748000 | FY 2023: 453000
TO-6101 | PUBLIC TRANSIT | APPALCART | OPERATING ASSISTANCE | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 15464000 | FY 2023: 1933000
TO-6102 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 866000 | FY 2023: 43000
TO-6102 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 344000 | FY 2023: 43000
TO-6103 | PUBLIC TRANSIT | KERR AREA TRANSPORTATION | OPERATING ASSISTANCE | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1228000 | FY 2023: 60000
TO-6103 | PUBLIC TRANSIT | KERR AREA TRANSPORTATION | OPERATING ASSISTANCE | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 486000 | FY 2023: 60000
TO-6104 | PUBLIC TRANSIT | APPALCART | OPERATING ASSISTANCE | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | OPERATIONS | 9212000 | FY 2023: 658000
TO-6106 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | OPERATING ASSISTANCE | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 448000 | FY 2023: 28000
TO-6106 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | OPERATING ASSISTANCE | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 224000 | FY 2023: 28000
TO-6107 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 436000 | FY 2023: 21000
TO-6107 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 168000 | FY 2023: 21000
TO-6109 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 1802000 | FY 2023: 98000
TO-6109 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 784000 | FY 2023: 98000
TO-6135 | PUBLIC TRANSIT | STATEWIDE | 5311 OPERATING FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 947000
TO-6139 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 OPERATING | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 787000 | FY 2023: 18000; FY 2024: 35000; FY 2025: 35000; FY 2026: 35000; FY 2027: 51000
TO-6139 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 OPERATING | 7 | Greensboro Urban Area MPO | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO | PUBLIC TRANSIT |  | L | OPERATIONS | 789000 | FY 2023: 18000; FY 2024: 35000; FY 2025: 35000; FY 2026: 35000; FY 2027: 51000
TO-6142 | PUBLIC TRANSIT | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS - OPERATING | 99 | Burlington-Graham MPO, Charlotte Regional TPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 9389000
TO-6142 | PUBLIC TRANSIT | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS - OPERATING | 99 | Burlington-Graham MPO, Charlotte Regional TPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 9389000
TO-6150 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 4619000 | FY 2023: 439000; FY 2024: 439000; FY 2025: 439000; FY 2026: 439000; FY 2027: 485000
TO-6150 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 4526000 | FY 2023: 439000; FY 2024: 439000; FY 2025: 439000; FY 2026: 439000; FY 2027: 485000
TO-6151 | PUBLIC TRANSIT | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | OPERATING | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 2016000
TO-6151 | PUBLIC TRANSIT | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | OPERATING | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 2016000
TO-6154 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | BUNCOMBE COUNTY TRANSIT OPERATING ASSISTANCE. | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1340000 | FY 2023: 261000
TO-6154 | PUBLIC TRANSIT | MOUNTAIN MOBILITY - BUNCOMBE | BUNCOMBE COUNTY TRANSIT OPERATING ASSISTANCE. | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 1091000 | FY 2023: 262000
TO-6155 | PUBLIC TRANSIT | STATEWIDE | 5311 OPERATING AND 5311 OPERATING F | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | OPERATIONS | 115650000 | FY 2023: 12850000; FY 2024: 12870000; FY 2025: 12890000; FY 2026: 12910000; FY 2027: 12930000
TO-6155 | PUBLIC TRANSIT | STATEWIDE | 5311 OPERATING AND 5311 OPERATING F | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | OPERATIONS | 57825000 | FY 2023: 6425000; FY 2024: 6435000; FY 2025: 6445000; FY 2026: 6455000; FY 2027: 6465000
TO-6156 | PUBLIC TRANSIT | UNION COUNTY | 5307 OPERATIONS FOR FFY20-21 (20-LU-089) | 10 | Charlotte Regional TPO | ADDING FUNDS FOR FFY20-21 | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 783000
TO-6156 | PUBLIC TRANSIT | UNION COUNTY | 5307 OPERATIONS FOR FFY20-21 (20-LU-089) | 10 | Charlotte Regional TPO | ADDING FUNDS FOR FFY20-21 | PUBLIC TRANSIT |  | L | OPERATIONS | 783000
TO-6157 | PUBLIC TRANSIT | HOKE COUNTY | OPERATING ASSISTANCE FY20-21 | 8 | Fayetteville Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 466000 | FY 2023: 120000
TO-6157 | PUBLIC TRANSIT | HOKE COUNTY | OPERATING ASSISTANCE FY20-21 | 8 | Fayetteville Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 466000 | FY 2023: 120000
TO-6158 | PUBLIC TRANSIT | IREDELL COUNTY | OPERATION FOR FY20-21 | 12 | Charlotte Regional TPO | ADDING FUNDS FOR FFY2020 | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1186000 | FY 2023: 300000
TO-6158 | PUBLIC TRANSIT | IREDELL COUNTY | OPERATION FOR FY20-21 | 12 | Charlotte Regional TPO | ADDING FUNDS FOR FFY2020 | PUBLIC TRANSIT |  | L | OPERATIONS | 1186000 | FY 2023: 300000
TO-6159 | PUBLIC TRANSIT | MECKLENBURG TRANSPORTATION | OPERATING ASSISTANCE FY20-21 (20-LU-051) | 10 | Charlotte Regional TPO | ADDING CURRENT YEAR TO THE STIP | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1537000 | FY 2023: 385000
TO-6159 | PUBLIC TRANSIT | MECKLENBURG TRANSPORTATION | OPERATING ASSISTANCE FY20-21 (20-LU-051) | 10 | Charlotte Regional TPO | ADDING CURRENT YEAR TO THE STIP | PUBLIC TRANSIT |  | L | OPERATIONS | 1537000 | FY 2023: 385000
TO-6162 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | OPERATIONS | 11365000 | FY 2023: 1736000; FY 2024: 1700000; FY 2025: 1700000
TO-6162 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 11365000 | FY 2023: 1736000; FY 2024: 1700000; FY 2025: 1700000
TO-6165 | PUBLIC TRANSIT | DAVIDSON COUNTY | OPERATING ASSISTANCE | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 163344000
TO-6165 | PUBLIC TRANSIT | DAVIDSON COUNTY | OPERATING ASSISTANCE | 9 | High Point Urban Area MPO, Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 163344000
TO-6166A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7649000
TO-6166A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2126000
TO-6166A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40224000
TO-6166A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | UTILITIES | 3988000
TO-6166A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 14344000
TO-6166A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 1500000
TO-6166A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 75425000
TO-6166B | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, CARY TO RALEIGH. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C |  | L | ENGINEERING | 1500000
TO-6166B | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, CARY TO RALEIGH. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C |  | L | CONSTRUCTION | 45168000 | FY 2023: 30254000
TO-6166C | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, RALEIGH TO GARNER. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C |  | L | ENGINEERING | 1500000
TO-6166C | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, RALEIGH TO GARNER. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5 | Capital Area MPO |  | REGION C |  | L | CONSTRUCTION | 27777000
TO-6166D | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 4, 5 | Capital Area MPO |  | REGION A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40224000
TO-6166D | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 4, 5 | Capital Area MPO |  | REGION A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | ENGINEERING | 1500000
TO-6166D | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 4, 5 | Capital Area MPO |  | REGION A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 14344000
TO-6166D | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 4, 5 | Capital Area MPO |  | REGION A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | UTILITIES | 3988000
TO-6166D | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 4, 5 | Capital Area MPO |  | REGION A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 75426000
TO-6166D | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 4, 5 | Capital Area MPO |  | REGION A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7649000
TO-6166D | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 4, 5 | Capital Area MPO |  | REGION A, C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2126000
TO-6168 | PUBLIC TRANSIT | GORALEIGH | TOWN OF WAKE FOREST REVERSE CIRCULATOR OPERATING ASSISTANCE | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 2283000 | FY 2023: 375000; FY 2024: 387000; FY 2025: 394000; FY 2026: 404000
TO-6170 | PUBLIC TRANSIT | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1349000
TO-6170 | PUBLIC TRANSIT | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 6008000 | FY 2023: 820000; FY 2024: 820000; FY 2025: 820000; FY 2026: 820000; FY 2027: 820000; FY 2028: 820000
TO-6170 | PUBLIC TRANSIT | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | PUBLIC TRANSIT |  | L | OPERATIONS | 5890000 | FY 2023: 820000; FY 2024: 820000; FY 2025: 820000; FY 2026: 820000; FY 2027: 820000; FY 2028: 820000
TO-6170 | PUBLIC TRANSIT | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. | 7 | Burlington-Graham MPO | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO. | PUBLIC TRANSIT |  | L | OPERATIONS | 792000
TO-6812A | PUBLIC TRANSIT | LINK TRANSIT | ADA SERVICE. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 1260000 | FY 2023: 180000; FY 2024: 180000; FY 2025: 180000; FY 2026: 180000; FY 2027: 180000; FY 2028: 180000
TO-6812A | PUBLIC TRANSIT | LINK TRANSIT | ADA SERVICE. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 322000 | FY 2023: 46000; FY 2024: 46000; FY 2025: 46000; FY 2026: 46000; FY 2027: 46000; FY 2028: 46000
TP-4732A | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | PLANNING | 7257000 | FY 2023: 590000
TP-4732A | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 586000 | FY 2023: 74000
TP-4732A | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 586000 | FY 2023: 74000
TP-4732B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | PLANNING | 7257000 | FY 2023: 590000
TP-4732B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 586000 | FY 2023: 74000
TP-4732B | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 586000 | FY 2023: 74000
TP-4733A | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | PLANNING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2281000
TP-4733B | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PLANNING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | PLANNING | 64000 | FY 2023: 16000
TP-4733B | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PLANNING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | S | CAPITAL | 20000
TP-4733B | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PLANNING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | PLANNING | 348000 | FY 2023: 69000
TP-4733B | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PLANNING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | CAPITAL | 501000
TP-4733B | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PLANNING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | CAPITAL | 20000
TP-4733B | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PLANNING ASSISTANCE | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | S | PLANNING | 5000
TP-4901 | PUBLIC TRANSIT | REGIONAL COORDINATED AREA TRANSPORTION | PLANNING ASSISTANCE - RESEARCH SUPPORT ACTIVITIES | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | FSPR | CAPITAL | 7139000
TP-4901 | PUBLIC TRANSIT | REGIONAL COORDINATED AREA TRANSPORTION | PLANNING ASSISTANCE - RESEARCH SUPPORT ACTIVITIES | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 630000
TP-4908 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | S | PLANNING | 91000 | FY 2023: 9000; FY 2024: 10000; FY 2025: 10000; FY 2026: 10000; FY 2027: 10000
TP-4908 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | PLANNING | 911000 | FY 2023: 74000; FY 2024: 76000; FY 2025: 78000; FY 2026: 78000; FY 2027: 80000
TP-4908 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 91000 | FY 2023: 9000; FY 2024: 10000; FY 2025: 10000; FY 2026: 10000; FY 2027: 10000
TP-5100A | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 368000 | FY 2023: 46000
TP-5100A | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | PLANNING | 4831000 | FY 2023: 375000
TP-5100A | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 376000 | FY 2023: 47000
TP-5100B | PUBLIC TRANSIT | GORALEIGH | PLANNING ASSISTANCE - 5307 | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | PLANNING | 8086000 | FY 2023: 400000
TP-5100B | PUBLIC TRANSIT | GORALEIGH | PLANNING ASSISTANCE - 5307 | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 946000 | FY 2023: 50000
TP-5100B | PUBLIC TRANSIT | GORALEIGH | PLANNING ASSISTANCE - 5307 | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 400000 | FY 2023: 50000
TP-5101 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303 | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | SMAP | PLANNING | 162000 | FY 2023: 24000; FY 2024: 24000; FY 2025: 24000; FY 2026: 24000
TP-5101 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303 | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | PLANNING | 1311000 | FY 2023: 195000; FY 2024: 195000; FY 2025: 195000; FY 2026: 195000
TP-5101 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303 | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 162000 | FY 2023: 24000; FY 2024: 24000; FY 2025: 24000; FY 2026: 24000
TP-5102 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | S | PLANNING | 53000 | FY 2023: 5000; FY 2024: 6000; FY 2025: 6000; FY 2026: 6000; FY 2027: 6000
TP-5102 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5303 | PLANNING | 499000 | FY 2023: 31000; FY 2024: 31000; FY 2025: 32000; FY 2026: 32000; FY 2027: 32000
TP-5102 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 53000 | FY 2023: 5000; FY 2024: 6000; FY 2025: 6000; FY 2026: 6000; FY 2027: 6000
TP-5103 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | CAPITAL | 815000 | FY 2023: 53000
TP-5103 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 56000 | FY 2023: 7000
TP-5103 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 48000 | FY 2023: 6000
TP-5103B | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 353000 | FY 2023: 45000
TP-5103B | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | OPERATIONS | 3866000 | FY 2023: 360000
TP-5103B | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 353000 | FY 2023: 45000
TP-5104 | PUBLIC TRANSIT | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 32000 | FY 2023: 4000
TP-5104 | PUBLIC TRANSIT | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | CAPITAL | 552000 | FY 2023: 36000
TP-5104 | PUBLIC TRANSIT | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 | 7 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 32000 | FY 2023: 4000
TP-5105 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 | 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | CAPITAL | 1393000 | FY 2023: 83000; FY 2024: 83000; FY 2025: 83000
TP-5105 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 | 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 94000 | FY 2023: 10000; FY 2024: 10000; FY 2025: 10000
TP-5105 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 | 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 94000 | FY 2023: 10000; FY 2024: 10000; FY 2025: 10000
TP-5106 | PUBLIC TRANSIT | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | PUBLIC TRANSIT |  | 5303 | PLANNING | 319000 | FY 2023: 110000; FY 2024: 55000
TP-5106 | PUBLIC TRANSIT | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | PUBLIC TRANSIT |  | S | PLANNING | 41000 | FY 2023: 14000; FY 2024: 7000
TP-5106 | PUBLIC TRANSIT | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | PUBLIC TRANSIT |  | S | CAPITAL | 16000
TP-5106 | PUBLIC TRANSIT | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | PUBLIC TRANSIT |  | L | PLANNING | 41000 | FY 2023: 14000; FY 2024: 7000
TP-5106 | PUBLIC TRANSIT | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | PUBLIC TRANSIT |  | 5303 | CAPITAL | 377000
TP-5106 | PUBLIC TRANSIT | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP | PUBLIC TRANSIT |  | L | CAPITAL | 16000
TP-5107 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | PLANNING | 413000 | FY 2023: 27000
TP-5107 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 24000 | FY 2023: 3000
TP-5107 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 24000 | FY 2023: 3000
TP-5108 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5303 | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | CAPITAL | 1736000 | FY 2023: 112000
TP-5108 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5303 | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 112000 | FY 2023: 14000
TP-5108 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5303 | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 112000 | FY 2023: 14000
TP-5109 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5307 | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 5494000 | FY 2023: 384000
TP-5109 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5307 | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 384000 | FY 2023: 48000
TP-5109 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5307 | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 384000 | FY 2023: 48000
TP-5110 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 20000
TP-5110 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 38000 | FY 2023: 38000
TP-5110 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | PLANNING | 152000 | FY 2023: 152000
TP-5110 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 260000
TP-5110 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 20000
TP-5111 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | PLANNING | 4184000 | FY 2023: 384000
TP-5111 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 112000 | FY 2023: 14000
TP-5111 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 112000 | FY 2023: 14000
TP-5112 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5311 | PLANNING | 48000
TP-5112 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 466000 | FY 2023: 52000; FY 2024: 54000; FY 2025: 56000
TP-5112 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | PLANNING | 2461000 | FY 2023: 260000; FY 2024: 270000; FY 2025: 280000
TP-5112 | PUBLIC TRANSIT | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 14000
TP-5113 | PUBLIC TRANSIT | CITY OF ASHEVILLE | PLANNING ASSISTANCE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | CAPITAL | 680000
TP-5113 | PUBLIC TRANSIT | CITY OF ASHEVILLE | PLANNING ASSISTANCE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 14000
TP-5113 | PUBLIC TRANSIT | CITY OF ASHEVILLE | PLANNING ASSISTANCE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 14000
TP-5114 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | PLANNING | 5206000 | FY 2023: 347000; FY 2024: 347000; FY 2025: 347000
TP-5114 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 430000 | FY 2023: 43000; FY 2024: 43000; FY 2025: 43000
TP-5114 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 430000 | FY 2023: 43000; FY 2024: 43000; FY 2025: 43000
TP-5116 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | CAPITAL | 324000 | FY 2023: 25000
TP-5116 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 24000 | FY 2023: 3000
TP-5116 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 24000 | FY 2023: 3000
TP-5118 | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | CAPITAL | 632000 | FY 2023: 60000
TP-5118 | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 64000 | FY 2023: 8000
TP-5118 | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 64000 | FY 2023: 8000
TP-5122 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | SHORT RANGE PLANNING | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | PLANNING | 56000
TP-5122 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | SHORT RANGE PLANNING | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 14000
TP-5150 | PUBLIC TRANSIT | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5303 | PLANNING | 270000 | FY 2023: 30000; FY 2024: 30000
TP-5150 | PUBLIC TRANSIT | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | PLANNING | 36000 | FY 2023: 4000; FY 2024: 4000
TP-5150 | PUBLIC TRANSIT | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | PLANNING | 8000
TP-5153 | PUBLIC TRANSIT | CITY OF ASHEVILLE | PLANNING FOR MOUNTAIN MOBILITY | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5307 | PLANNING | 726000 | FY 2023: 121000
TP-5153 | PUBLIC TRANSIT | CITY OF ASHEVILLE | PLANNING FOR MOUNTAIN MOBILITY | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 180000 | FY 2023: 30000
TP-5154 | PUBLIC TRANSIT | STATEWIDE | 5304 PLANNING | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5303 | PLANNING | 4770000 | FY 2023: 530000; FY 2024: 540000; FY 2025: 550000; FY 2026: 560000; FY 2027: 570000
TP-5154 | PUBLIC TRANSIT | STATEWIDE | 5304 PLANNING | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | PLANNING | 954000 | FY 2023: 106000; FY 2024: 108000; FY 2025: 110000; FY 2026: 112000; FY 2027: 114000
TP-5156 | PUBLIC TRANSIT | CATS | ADD A LIGHT RAIL STATION ON THE LYNX BLUE LINE NEAR IVERSON WAY IN SOUTH CHARLOTTE | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND, CITY OF CHARLOTTE CAPITAL FUNDS, PRIVATE DEVELOPER PARTICIPATION. | PUBLIC TRANSIT |  | L | CAPITAL | 7582000 | FY 2023: 3000000
TP-5159 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE TOD PLANNING IN COOPERATION WITH CATS, CRTPO AND GCLMPO. | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | 5303 | PLANNING | 1325000 | FY 2023: 202000; FY 2024: 203000
TP-5159 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE TOD PLANNING IN COOPERATION WITH CATS, CRTPO AND GCLMPO. | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | L | PLANNING | 331000 | FY 2023: 51000; FY 2024: 51000
TP-5160 | PUBLIC TRANSIT | GO RALEIGH | CONSTRUCT BUS RAPID TRANSIT ON NEW BERN CORRIDOR. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  |  |  | 4316000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | FUZ | PLANNING | 1195000 | FY 2023: 1195000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | L | RIGHT-OF-WAY | 1757000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | L | PLANNING | 4605000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 25358000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 13650000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | FUZ | RIGHT-OF-WAY | 302000 | FY 2023: 302000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | ARP | CAPITAL | 5404000 | FY 2023: 5404000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | 5309 | CONSTRUCTION | 24336000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | 5309 | RIGHT-OF-WAY | 1027000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | 5309 | CAPITAL | 3687000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | 5309 | PLANNING | 5950000
TP-5160A | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | 5 | Capital Area MPO |  | DIVISION 5 |  | FUZ | CONSTRUCTION | 5163000 | FY 2023: 5163000
TP-5160B | PUBLIC TRANSIT | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR, BETTERMENT FUNDING | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 814000 | FY 2023: 814000
TP-5161 | PUBLIC TRANSIT | BURLINGTON | PLANNING FOR FIXED ROUTE SERVICE EXPANSION | 7 | Burlington-Graham MPO | ADD PROJECT TP-5161 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | 5307 | PLANNING | 4000
TP-5161 | PUBLIC TRANSIT | BURLINGTON | PLANNING FOR FIXED ROUTE SERVICE EXPANSION | 7 | Burlington-Graham MPO | ADD PROJECT TP-5161 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | L | PLANNING | 1000
TP-5162 | PUBLIC TRANSIT | BURLINGTON | PLANNING FOR PLANNING FACILITY FEASIBILITY STUDY | 7 | Burlington-Graham MPO | ADD PROJECT TP-5162 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | 5307 | PLANNING | 76000
TP-5162 | PUBLIC TRANSIT | BURLINGTON | PLANNING FOR PLANNING FACILITY FEASIBILITY STUDY | 7 | Burlington-Graham MPO | ADD PROJECT TP-5162 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | PUBLIC TRANSIT |  | L | PLANNING | 19000
TQ-6186 | PUBLIC TRANSIT | ASHEVILLE REDEFINES TRANSIT | 5310 TRADITIONAL PROJECTS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5310 | CAPITAL | 555000
TQ-6186 | PUBLIC TRANSIT | ASHEVILLE REDEFINES TRANSIT | 5310 TRADITIONAL PROJECTS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 138000
TQ-6187 | PUBLIC TRANSIT | CITY OF ASHEVILLE | 5310 OTHER PROJECTS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 344000
TQ-6187 | PUBLIC TRANSIT | CITY OF ASHEVILLE | 5310 OTHER PROJECTS | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 344000
TQ-6503 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | PREVENTIVE MAINTENANCE - PARATRANSIT | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 127000 | FY 2023: 9000
TQ-6503 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | PREVENTIVE MAINTENANCE - PARATRANSIT | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 5000
TQ-6503 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | PREVENTIVE MAINTENANCE - PARATRANSIT | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | OPERATIONS | 5000
TQ-6507 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ELDERLY AND DISABLED PERSONS | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23 | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 1128000 | FY 2023: 174000
TQ-6507 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ELDERLY AND DISABLED PERSONS | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23 | PUBLIC TRANSIT |  | L | OPERATIONS | 787000 | FY 2023: 174000
TQ-6513 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT PROVIDES OPERATING SUPPORT FOR FIXED BUS ROUTE 205 LONG LEAF PARK WHICH SERVICES NOVANT HOSPITAL AND THE MEDICAL CENTER. THIS ROUTE CARRIES A HIGH CONCENTRATION OF INDIVIDUALS WITH DISABILITIES AS IDENTIFIED THROUGH AN EXTENSIVE ONBOARD SURVEY EFFORT CONDUCTED IN FY17. A SURVEY EFFORT IS SLATED FOR FY23. | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 768000 | FY 2023: 85000; FY 2024: 88000
TQ-6513 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT PROVIDES OPERATING SUPPORT FOR FIXED BUS ROUTE 205 LONG LEAF PARK WHICH SERVICES NOVANT HOSPITAL AND THE MEDICAL CENTER. THIS ROUTE CARRIES A HIGH CONCENTRATION OF INDIVIDUALS WITH DISABILITIES AS IDENTIFIED THROUGH AN EXTENSIVE ONBOARD SURVEY EFFORT CONDUCTED IN FY17. A SURVEY EFFORT IS SLATED FOR FY23. | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 768000 | FY 2023: 85000; FY 2024: 88000
TQ-6514 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (TRADITIONAL) | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 248000 | FY 2023: 31000
TQ-6514 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (TRADITIONAL) | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 1000000 | FY 2023: 125000
TQ-6597 | PUBLIC TRANSIT | CHARLOTTE REGIONAL | OPERATING PROJECTS FOR ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | PUBLIC TRANSIT |  | L | OPERATIONS | 1395000 | FY 2023: 304000
TQ-6597 | PUBLIC TRANSIT | CHARLOTTE REGIONAL | OPERATING PROJECTS FOR ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 1395000 | FY 2023: 304000
TQ-6702 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPET GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE TRANSPORTATION NEEDS OF LOW INCOME, DISABLED AND ELDERLY POPULATIONS | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 3468000 | FY 2023: 355000; FY 2024: 355000; FY 2025: 355000
TQ-6702 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPET GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE TRANSPORTATION NEEDS OF LOW INCOME, DISABLED AND ELDERLY POPULATIONS | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 869000 | FY 2023: 89000; FY 2024: 89000; FY 2025: 89000
TQ-6782 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPETE GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE NEEDS OF LOW INCOME, DISABLED, AND ELDERLY POPULATIONS | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 4867000 | FY 2023: 358000; FY 2024: 358000; FY 2025: 358000; FY 2026: 358000; FY 2027: 358000
TQ-6782 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPETE GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE NEEDS OF LOW INCOME, DISABLED, AND ELDERLY POPULATIONS | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | OPERATIONS | 1221000 | FY 2023: 90000; FY 2024: 90000; FY 2025: 90000; FY 2026: 90000; FY 2027: 90000
TQ-6783 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 CAPITAL PROJECT | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 442000 | FY 2023: 87000; FY 2024: 54000; FY 2025: 54000; FY 2026: 54000
TQ-6783 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 CAPITAL PROJECT | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | 5310 | CAPITAL | 1765000 | FY 2023: 348000; FY 2024: 215000; FY 2025: 215000; FY 2026: 215000
TQ-6953 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | 5310 OPERATING | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 2086000
TQ-6953 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | 5310 OPERATING | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | OPERATIONS | 2086000
TQ-6954 | PUBLIC TRANSIT | STATEWIDE | 5310 OPERATING PROJECTS FOR RURAL AREAS | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 6103000 | FY 2023: 2138000; FY 2024: 2005000
TQ-6954 | PUBLIC TRANSIT | STATEWIDE | 5310 OPERATING PROJECTS FOR RURAL AREAS | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | L | OPERATIONS | 2832000 | FY 2023: 2137000; FY 2024: 695000
TQ-6957 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING PROJECT FOR ENHANCED MOBILITY OF SENIORS AND INDIVIDUALS WITH DISABILITIES | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 4218000 | FY 2023: 304000
TQ-6957 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING PROJECT FOR ENHANCED MOBILITY OF SENIORS AND INDIVIDUALS WITH DISABILITIES | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | PUBLIC TRANSIT |  | L | OPERATIONS | 2347000 | FY 2023: 304000
TQ-7000 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 PROGRAM ADMINISTRATION | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 221000 | FY 2023: 41000; FY 2024: 28000; FY 2025: 28000; FY 2026: 28000
TQ-7005 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT IS FOR ADMINISTRATIVE SUPPORT REQUIRED TO EFFECTVELY MANAGE THE SECTION 5310 PROGRAM AND ANNUAL FUNDING ALLOCATION FROM FTA. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 205000 | FY 2023: 24000; FY 2024: 25000
TQ-7006 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | 5310 ADMIN. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 295000
TQ-7009 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | ADMINISTRATIVE OVERSIGHT FOR 5310 | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL TO FY 20-25 FOR THE ADMINISTRATIVE OVERSIGHT OF THE 5310 PROGRAM AS REQUESTED BY THE CRTPO | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 692000 | FY 2023: 101000
TQ-7010 | PUBLIC TRANSIT | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT. 5310 ADMINISTRATIVE OVERSIGHT. | 13 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5310 | CAPITAL | 163000
TQ-8019 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | MOBILITY MANAGER PROVIDES OVERSIGHT AND MANAGEMENT OF SECTION 5310 FUNDS AND ADMINISTERS THE PROGRAMS AND PROJECTS SUPPORTED BY THESE FUNDS. | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | CAPITAL | 366000 | FY 2023: 60000; FY 2024: 60000
TQ-8019 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | MOBILITY MANAGER PROVIDES OVERSIGHT AND MANAGEMENT OF SECTION 5310 FUNDS AND ADMINISTERS THE PROGRAMS AND PROJECTS SUPPORTED BY THESE FUNDS. | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 90000 | FY 2023: 15000; FY 2024: 15000
TQ-9001 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECTS FULFILLS THE ALLOCATION FOR NON-TRADITIONAL TRANSPORTATION PROJECTS AS DEFINED IN THE GRANT. THE PROJECT SUPPORTS THE COMMUNITY GRANT OFFERING TO NON-PROFITS AND GOVERNMENTAL ORGANIZAIONS TO REMOVE TRANSPORTATION BARRIERS AND CONNECT ELDERS AND INDIVIDUALS WITH DISABILITIES TO NEEDED RESOURCES. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | 5310 | CAPITAL | 584000 | FY 2023: 73000; FY 2024: 79000
TQ-9001 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECTS FULFILLS THE ALLOCATION FOR NON-TRADITIONAL TRANSPORTATION PROJECTS AS DEFINED IN THE GRANT. THE PROJECT SUPPORTS THE COMMUNITY GRANT OFFERING TO NON-PROFITS AND GOVERNMENTAL ORGANIZAIONS TO REMOVE TRANSPORTATION BARRIERS AND CONNECT ELDERS AND INDIVIDUALS WITH DISABILITIES TO NEEDED RESOURCES. | 3 | Wilmington Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 38000 | FY 2023: 18000; FY 2024: 20000
TQ-9033 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | PUBLIC TRANSIT |  | L | CAPITAL | 1879000 | FY 2023: 152000; FY 2024: 101000; FY 2025: 104000
TQ-9033 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | PUBLIC TRANSIT |  | S | CAPITAL | 240000
TQ-9033 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | 10 | Charlotte Regional TPO | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO | PUBLIC TRANSIT |  | 5310 | CAPITAL | 8193000 | FY 2023: 609000; FY 2024: 810000; FY 2025: 834000
TQ9037 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | 5310 ADMINISTRATION | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 295000
TQ-9037 | PUBLIC TRANSIT | GORALEIGH | 5310 CAPITAL AND ADMIN | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | CAPITAL | 2591000
TQ-9037 | PUBLIC TRANSIT | GORALEIGH | 5310 CAPITAL AND ADMIN | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 648000
TQ-9038 | PUBLIC TRANSIT | STATEWIDE | 5310 CAPITAL PROJECTS FOR RURAL AREAS AND SMALL URBAN AREAS | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUND S RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | 5310 | CAPITAL | 2850000
TQ-9039 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | CAPITAL PURCHASE OF SERVICE | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | CAPITAL | 262000 | FY 2023: 46000; FY 2024: 30000; FY 2025: 30000
TQ-9039 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | CAPITAL PURCHASE OF SERVICE | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5310 | CAPITAL | 1049000 | FY 2023: 185000; FY 2024: 120000; FY 2025: 120000
TQ-9040 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | 12 | Greater Hickory MPO | MODIFYING FUNDING IN FY 20, FY 21, FY 22, FY 23 | PUBLIC TRANSIT |  | L | OPERATIONS | 10000
TQ-9040 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | 12 | Greater Hickory MPO | MODIFYING FUNDING IN FY 20, FY 21, FY 22, FY 23 | PUBLIC TRANSIT |  | L | CAPITAL | 63000 | FY 2023: 11000; FY 2024: 10000; FY 2025: 10000
TQ-9040 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | 12 | Greater Hickory MPO | MODIFYING FUNDING IN FY 20, FY 21, FY 22, FY 23 | PUBLIC TRANSIT |  | 5310 | CAPITAL | 249000 | FY 2023: 44000; FY 2024: 40000; FY 2025: 40000
TQ-9040 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | 12 | Greater Hickory MPO | MODIFYING FUNDING IN FY 20, FY 21, FY 22, FY 23 | PUBLIC TRANSIT |  | 5310 | OPERATIONS | 40000
TS-4758 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | SAFETY & SECURITY | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | 5307 | CAPITAL | 549000 | FY 2023: 65000; FY 2024: 65000; FY 2025: 65000; FY 2026: 65000; FY 2027: 65000; FY 2028: 65000
TS-4758 | PUBLIC TRANSIT | GREENSBORO TRANSIT AUTHORITY | SAFETY & SECURITY | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | PUBLIC TRANSIT |  | L | CAPITAL | 136000 | FY 2023: 16000; FY 2024: 16000; FY 2025: 16000; FY 2026: 16000; FY 2027: 16000; FY 2028: 16000
TS-4900Z | PUBLIC TRANSIT | STATEWIDE | STATEWIDE RTAP | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | PUBLIC TRANSIT |  | RTAP | ADMINISTRATIVE | 480000
TS-5101 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 29000 | FY 2023: 1000
TS-5101 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 21000 | FY 2023: 2000
TS-5102 | PUBLIC TRANSIT | CITY OF ASHEVILLE | SAFETY & SECURITY - MIN. 1% SET ASIDE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 103000 | FY 2023: 10000
TS-5102 | PUBLIC TRANSIT | CITY OF ASHEVILLE | SAFETY & SECURITY - MIN. 1% SET ASIDE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 12000 | FY 2023: 2000
TS-5103 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 310000 | FY 2023: 22000
TS-5103 | PUBLIC TRANSIT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 16000 | FY 2023: 2000
TS-5104 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 1218000 | FY 2023: 85000
TS-5104 | PUBLIC TRANSIT | CAPITAL AREA TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 214000 | FY 2023: 21000
TS-5107 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | SAFETY & SECURITY - MIN. 1% SET ASIDE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 7276000 | FY 2023: 490000; FY 2024: 490000; FY 2025: 490000
TS-5107 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | SAFETY & SECURITY - MIN. 1% SET ASIDE | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 1224000 | FY 2023: 122000; FY 2024: 122000; FY 2025: 122000
TS-5108 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 543000 | FY 2023: 39000
TS-5108 | PUBLIC TRANSIT | DURHAM AREA TRANSIT AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 32000 | FY 2023: 4000
TS-5109 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 339000 | FY 2023: 24000
TS-5109 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 48000 | FY 2023: 6000
TS-5112 | PUBLIC TRANSIT | GREENVILLE AREA TRANSIT | SAFETY & SECURITY | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 177000
TS-5113 | PUBLIC TRANSIT | HIGH POINT TRANSIT SYSTEM / HI-TRAN | SAFETY & SECURITY - MIN. 1% SET ASIDE | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 204000 | FY 2023: 14000
TS-5113 | PUBLIC TRANSIT | HIGH POINT TRANSIT SYSTEM / HI-TRAN | SAFETY & SECURITY - MIN. 1% SET ASIDE | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 16000 | FY 2023: 2000
TS-5114 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | 3 | Jacksonville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 254000 | FY 2023: 20000; FY 2024: 21000; FY 2025: 21000
TS-5115 | PUBLIC TRANSIT | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | SAFETY & SECURITY - MIN. 1% SET ASIDE | 7, 9 | Winston-Salem Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 39000 | FY 2023: 2000
TS-5116 | PUBLIC TRANSIT | RIDER TRANSIT / CONCORD | SAFETY & SECURITY - MIN. 1% SET ASIDE | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 303000 | FY 2023: 25000
TS-5119 | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 390000 | FY 2023: 17000
TS-5119 | PUBLIC TRANSIT | TRIANGLE TRANSIT AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 14000 | FY 2023: 2000
TS-5120 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 72000 | FY 2023: 8000; FY 2024: 8000; FY 2025: 8000
TS-5120 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | SMAP | CAPITAL | 7000
TS-5120 | PUBLIC TRANSIT | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | 9 | Winston-Salem Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 499000 | FY 2023: 33000; FY 2024: 33000; FY 2025: 33000
TS-5128 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | SAFETY & SECURITY | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 25000
TS-5128 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSPORTATION | SAFETY & SECURITY | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 254000
TS-5129 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 79000 | FY 2023: 4000
TS-5129 | PUBLIC TRANSIT | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 8000 | FY 2023: 1000
TS-5133 | PUBLIC TRANSIT | CITY OF SALISBURY | SAFETY & SECURITY MIN. 1% SET ASIDE | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 56000 | FY 2023: 7000
TS-7001 | PUBLIC TRANSIT | STATEWIDE | 5329 STATE SAFETY AND OVERSIGHT | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | ADMINISTRATIVE | 70000 | FY 2027: 70000
TS-7001 | PUBLIC TRANSIT | STATEWIDE | 5329 STATE SAFETY AND OVERSIGHT | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | ADMINISTRATIVE | 812000 | FY 2023: 69000; FY 2024: 69000; FY 2025: 69000; FY 2026: 70000; FY 2027: 70000
TS-7001 | PUBLIC TRANSIT | STATEWIDE | 5329 STATE SAFETY AND OVERSIGHT | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | FED | ADMINISTRATIVE | 4224000 | FY 2023: 345000; FY 2024: 345000; FY 2025: 345000; FY 2026: 346000; FY 2027: 346000
TS-7002 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | SAFETY AND SECURITY | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | L | CAPITAL | 76000 | FY 2023: 14000; FY 2024: 8000; FY 2025: 8000
TS-7002 | PUBLIC TRANSIT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | SAFETY AND SECURITY | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | PUBLIC TRANSIT |  | 5307 | CAPITAL | 296000 | FY 2023: 58000; FY 2024: 28000; FY 2025: 28000
TT-4907 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | TECHNOLOGY - VEHICLE TRACKING, FARE COLLECTION, PASSENGER INFORMATION, DATA COMMUNICATIONS, TRAFFIC SIGNAL PRIORITY | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | 5307 | CAPITAL | 2171000 | FY 2023: 80000; FY 2024: 80000; FY 2025: 80000; FY 2026: 80000; FY 2027: 80000
TT-4907 | PUBLIC TRANSIT | JACKSONVILLE TRANSIT | TECHNOLOGY - VEHICLE TRACKING, FARE COLLECTION, PASSENGER INFORMATION, DATA COMMUNICATIONS, TRAFFIC SIGNAL PRIORITY | 3 | Jacksonville Urban Area MPO |  | PUBLIC TRANSIT |  | L | CAPITAL | 262000 | FY 2023: 20000; FY 2024: 20000; FY 2025: 20000; FY 2026: 20000; FY 2027: 20000
TT-5204 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 17000
TT-5204 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 182000
TT-5204 | PUBLIC TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 17000
TT-5206 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | LEASE OF TABLETS | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 14000
TT-5206 | PUBLIC TRANSIT | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | LEASE OF TABLETS | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 70000
TT-5207 | PUBLIC TRANSIT | GTA | TRANSIT SAFETY INNOVATIONS | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY20, FY21, FY22 AT THE REQUEST OF GREENSBORO MPO |  |  | 5312 | OPERATIONS | 68000
TT-5207 | PUBLIC TRANSIT | GTA | TRANSIT SAFETY INNOVATIONS | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY20, FY21, FY22 AT THE REQUEST OF GREENSBORO MPO |  |  | L | OPERATIONS | 18000
TU-0001 | PUBLIC TRANSIT | CATS | LYNX SILVER LINE LIGHT RAIL PROJECT | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | 5307 | PLANNING | 1353000
TU-0001 | PUBLIC TRANSIT | CATS | LYNX SILVER LINE LIGHT RAIL PROJECT | 10 | Charlotte Regional TPO |  | PUBLIC TRANSIT |  | L | PLANNING | 48647000
TU-0002 | PUBLIC TRANSIT | GTA | THE CITY OF GREENSBORO WILL RECEIVE FUNDING TO PREPARE A TECHNICAL PLAN TO ESTABLISH WHAT WILL BE REQUIRED TO PROVIDE FREE BROADBAND INTERNET ACCESS IN LOW - INCOME AREAS USING TRANSIT, TRANSPORTATION AND OTHER PUBLIC INFRASTRUCTURE. | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 26000
TU-0002 | PUBLIC TRANSIT | GTA | THE CITY OF GREENSBORO WILL RECEIVE FUNDING TO PREPARE A TECHNICAL PLAN TO ESTABLISH WHAT WILL BE REQUIRED TO PROVIDE FREE BROADBAND INTERNET ACCESS IN LOW - INCOME AREAS USING TRANSIT, TRANSPORTATION AND OTHER PUBLIC INFRASTRUCTURE. | 7 | Greensboro Urban Area MPO |  | PUBLIC TRANSIT |  | 5305 | PLANNING | 234000
TU-0003 | PUBLIC TRANSIT | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. | 99 | STATEWIDE PROJECT | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | PUBLIC TRANSIT |  | S | PLANNING | 32000 | FY 2023: 20000
TU-0003 | PUBLIC TRANSIT | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. | 99 | STATEWIDE PROJECT | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | PUBLIC TRANSIT |  | 5303 | PLANNING | 80000 | FY 2023: 80000
TU-0003 | PUBLIC TRANSIT | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. | 99 | STATEWIDE PROJECT | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD. | PUBLIC TRANSIT |  | 5312 | PLANNING | 110000
TU-0004 | PUBLIC TRANSIT | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Triangle Area RPO | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | PUBLIC TRANSIT |  | FED | PLANNING | 900000
TU-0004 | PUBLIC TRANSIT | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Triangle Area RPO | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | PUBLIC TRANSIT |  | L | PLANNING | 505000
TU-0004 | PUBLIC TRANSIT | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Triangle Area RPO | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS | PUBLIC TRANSIT |  | S | PLANNING | 100000
TU-0005 | PUBLIC TRANSIT | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | PLANNING | 1081000 | FY 2023: 750000
TU-0005 | PUBLIC TRANSIT | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | PLANNING | 1081000 | FY 2023: 750000
TU-0005 | PUBLIC TRANSIT | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5303 | PLANNING | 8647000 | FY 2023: 6000000
TU-0006 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE WAKE COUNTY BUS PLAN UPDATE. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | CMAQ | PLANNING | 650000 | FY 2023: 650000
TU-0006 | PUBLIC TRANSIT | GOTRIANGLE | GOTRIANGLE WAKE COUNTY BUS PLAN UPDATE. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 90000
TU-0007 | PUBLIC TRANSIT | GORALEIGH | MAJOR INVESTMENT STUDY/ALTERNATIVES ANALYSIS FOR BUS RAPID TRANSIT EXTENSION TO RESEARCH TRIANGLE PARK AND CLAYTON. | 5 | Capital Area MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 430000
TU-0008 | PUBLIC TRANSIT | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | PLANNING | 470000
TU-0008 | PUBLIC TRANSIT | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | S | PLANNING | 118000
TU-0009 | PUBLIC TRANSIT | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | RTAP | PLANNING | 765000
TU-0010 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | PROGRAM SUPPORT. | 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | 5307 | PLANNING | 480000
TU-0010 | PUBLIC TRANSIT | APPLE COUNTRY TRANSIT | PROGRAM SUPPORT. | 14 | French Broad River MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 120000
TU-0011 | PUBLIC TRANSIT | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5303 | PLANNING | 2834000 | FY 2024: 1700000
TU-0011 | PUBLIC TRANSIT | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | PLANNING | 227000
TU-0011 | PUBLIC TRANSIT | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5303 | ADMINISTRATIVE | 370000 | FY 2023: 370000
TU-0012 | PUBLIC TRANSIT | NCDOT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY. PLANNING STUDY ON THE TRANSITION TO ZERO EMISSIONS LIGHT AND HEAVY DUTY PASSENGER VEHICLES. THE TRANSITION PLAN IS AREQUIREMENT BY FTA TO APPLY FOR GRANT FUNDS SUPPORTING ANY ZEV PROJECTS, INCLUDING VEHICLES AND ALL RELATED INFRASTRUCTURE. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5303 | PLANNING | 80000 | FY 2023: 80000
TU-0012 | PUBLIC TRANSIT | NCDOT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY. PLANNING STUDY ON THE TRANSITION TO ZERO EMISSIONS LIGHT AND HEAVY DUTY PASSENGER VEHICLES. THE TRANSITION PLAN IS AREQUIREMENT BY FTA TO APPLY FOR GRANT FUNDS SUPPORTING ANY ZEV PROJECTS, INCLUDING VEHICLES AND ALL RELATED INFRASTRUCTURE. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | PLANNING | 20000 | FY 2023: 20000
TU-0013 | PUBLIC TRANSIT | GODURHAM | GODURHAM IS PLANNING IMPROVEMENTS TO DURHAM STATION TO EXPAND EQUITABLE ACCESS TO TRANSIT, IMPROVE STATION AMENITIES, AND INCREASE CONNECTIONS TO EMPLOYMENT, HEALTHCARE AND EDUCATION OPPORTUNITIES AND CONSTRUCT 8 BUS BAYS, REDESIGNED BUS LANES, AND PLACE NEW PAVEMENT. | 5 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 2700000 | FY 2023: 360000; FY 2024: 2340000
TU-0013 | PUBLIC TRANSIT | GODURHAM | GODURHAM IS PLANNING IMPROVEMENTS TO DURHAM STATION TO EXPAND EQUITABLE ACCESS TO TRANSIT, IMPROVE STATION AMENITIES, AND INCREASE CONNECTIONS TO EMPLOYMENT, HEALTHCARE AND EDUCATION OPPORTUNITIES AND CONSTRUCT 8 BUS BAYS, REDESIGNED BUS LANES, AND PLACE NEW PAVEMENT. | 5 | Durham-Chapel Hill-Carrboro MPO |  | PUBLIC TRANSIT |  | 5339(b) | PLANNING | 10800000 | FY 2023: 1440000; FY 2024: 9360000
TU-0014 | PUBLIC TRANSIT | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | L | PLANNING | 127000 | FY 2023: 127000
TU-0014 | PUBLIC TRANSIT | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | 5311 | PLANNING | 507000 | FY 2023: 507000
TU-0015 | PUBLIC TRANSIT | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO THE DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. | 99 | STATEWIDE PROJECT |  | PUBLIC TRANSIT |  | RTAP | PLANNING | 73000 | FY 2023: 73000
TU-0016 | PUBLIC TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT SYSTEM MANAGEMENT. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | 5307 | PLANNING | 1080000 | FY 2023: 240000; FY 2024: 100000; FY 2025: 185000; FY 2026: 185000; FY 2027: 185000; FY 2028: 185000
TU-0016 | PUBLIC TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT SYSTEM MANAGEMENT. | 7 | Burlington-Graham MPO |  | PUBLIC TRANSIT |  | L | PLANNING | 265000 | FY 2023: 60000; FY 2024: 25000; FY 2025: 45000; FY 2026: 45000; FY 2027: 45000; FY 2028: 45000
TV-4903 | PUBLIC TRANSIT | SUB REGIONAL | 5310 STATE ADMIN | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5310 | ADMINISTRATIVE | 450000
TW-4901 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | FMOD | CAPITAL | 2700000
TW-4901 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 1208000 | FY 2023: 71000; FY 2024: 73000; FY 2025: 75000; FY 2026: 77000; FY 2027: 80000 | 167000
TW-4901 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5337 | CAPITAL | 7979000 | FY 2023: 567000; FY 2024: 584000; FY 2025: 601000; FY 2026: 619000; FY 2027: 638000 | 1333000
TW-4901 | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 1208000 | FY 2023: 71000; FY 2024: 73000; FY 2025: 75000; FY 2026: 77000; FY 2027: 80000 | 167000
TW-5102A | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | BRIDGE INSPECTIONS AND REPAIRS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CONSTRUCTION | 3364000 | FY 2023: 240000; FY 2024: 240000; FY 2025: 240000
TW-5102A | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | BRIDGE INSPECTIONS AND REPAIRS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CONSTRUCTION | 355000 | FY 2023: 30000; FY 2024: 30000; FY 2025: 30000
TW-5102A | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | BRIDGE INSPECTIONS AND REPAIRS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CONSTRUCTION | 355000 | FY 2023: 30000; FY 2024: 30000; FY 2025: 30000
TW-5102B | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | FIXED GUIDEWAY MODERNIZATION - BRIDGE INSPECTION & EMERGENCY REPAIRS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | FMOD | CONSTRUCTION | 2845000 | FY 2023: 240000
TW-5102B | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | FIXED GUIDEWAY MODERNIZATION - BRIDGE INSPECTION & EMERGENCY REPAIRS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CONSTRUCTION | 410000 | FY 2023: 50000
TW-5104B | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5307 | CAPITAL | 15989000
TW-5104B | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | S | CAPITAL | 2372000 | FY 2023: 235000; FY 2024: 242000; FY 2025: 249000
TW-5104B | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | 5337 | CAPITAL | 18977000 | FY 2023: 1877000; FY 2024: 1933000; FY 2025: 1991000
TW-5104B | PUBLIC TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | CAPITAL | 2372000 | FY 2023: 235000; FY 2024: 242000; FY 2025: 249000
U-0071 | HIGHWAY | NEW ROUTE | EAST END CONNECTOR, NC 147 (DURHAM FREEWAY) TO NORTH OF NC 98 IN DURHAM. FOUR-LANE DIVIDED FREEWAY WITH AUXILIARY LANES, PART ON NEW LOCATION. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 219683000
U-0209 | HIGHWAY | US 74 (INDEPENDENCE BOULEVARD) | BROOKSHIRE FREEWAY TO IDLEWILD ROAD IN CHARLOTTE. ADD ADDITIONAL LANES AND CONSTRUCT INTERCHANGES WITH SHARON AMITY ROAD AND IDLEWILD ROAD AND SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $50M FOR RIGHT-OF-WAY, PAYBACK FY 2010-2021; $2M FOR CONSTRUCTION, PAYBACK FY 2013-2024 |  |  |  |  | 334267000
U-0209B | HIGHWAY | US 74 (INDEPENDENCE BOULEVARD) | NC 24/NC 27 (ALBEMARLE ROAD) TO IDLEWILD ROAD | 10 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | PRE-STI (TRANSITION) |  | NHP | GARVEE ROW | 10968000
U-0209B | HIGHWAY | US 74 (INDEPENDENCE BOULEVARD) | NC 24/NC 27 (ALBEMARLE ROAD) TO IDLEWILD ROAD | 10 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 1025000 | FY 2023: 205000; FY 2024: 205000
U-2307 | HIGHWAY | HICKORY | EAST SIDE THOROUGHFARE (MCDONALD PARKWAY), US 70-321 TO NC 127. MULTI-LANES, PART ON NEW LOCATION. | 12 | Greater Hickory MPO | STBG-DA FUNDS (W/ STATE MATCH) AS A RESULT OF FUNDING SWAP WITH EB-5911. |  |  |  |  | 58010000
U-2307B | HIGHWAY | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGANY | RIGHT-OF-WAY | 18040000 | FY 2025: 4510000; FY 2026: 9020000; FY 2027: 4510000
U-2307B | HIGHWAY | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGANY | UTILITIES | 9800000 | FY 2025: 4900000; FY 2026: 4900000
U-2307B | HIGHWAY | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 3600000 | FY 2025: 900000; FY 2026: 1800000; FY 2027: 900000
U-2307B | HIGHWAY | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | S(M) | RIGHT-OF-WAY | 960000 | FY 2025: 240000; FY 2026: 480000; FY 2027: 240000
U-2307B | HIGHWAY | MCDONALD PARKWAY | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | CONSTRUCTION | 42000000 | FY 2028: 420000; FY 2029: 12738000; FY 2030: 13651000; FY 2031: 10151000; FY 2032: 5040000
U-2412 | HIGHWAY | SR 1486 (GREENSBORO ROAD) / SR 4121 (HIGH POINT RO | PROPOSED US 311 BYPASS IN HIGH POINT TO SR 1424 (HILLTOP ROAD) IN GREENSBORO. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | [5 empty] | 127674000
U-2412A | HIGHWAY | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | BUILD NC CON | 36780000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 2452000 | 4904000
U-2412A | HIGHWAY | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | CONSTRUCTION | 16138000
U-2412A | HIGHWAY | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | BUILD NC CON | 27681000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1845000 | 1851000
U-2507 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD) | SR 2480 (SUGAR CREEK ROAD) TO SR 2472 (MALLARD CREEK CHURCH ROAD) IN CHARLOTTE. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 10 | Charlotte Regional TPO | [5 empty] | 63399000
U-2509AA | HIGHWAY | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 64401000 | FY 2024: 7806000; FY 2025: 18735000; FY 2026: 18735000; FY 2027: 12880000; FY 2028: 6245000
U-2509AA | HIGHWAY | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | STATEWIDE MOBILITY |  | NHP | UTILITIES | 1800000 | FY 2024: 900000; FY 2025: 900000
U-2509AA | HIGHWAY | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | 10 | Charlotte Regional TPO | SEGMENTS C1, C2 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 40401000 | FY 2028: 10611000; FY 2029: 15017000; FY 2030: 9354000; FY 2031: 5419000
U-2509AB | HIGHWAY | US 74 | SARDIS ROAD AND SR 3473 (SAM NEWELL ROAD) INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROAD NORTH EXTENSION TO SAM NEWELL ROAD. | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 45306000 | FY 2028: 11298000; FY 2029: 16222000; FY 2030: 10473000; FY 2031: 6396000; FY 2032: 917000
U-2509AB | HIGHWAY | US 74 | SARDIS ROAD AND SR 3473 (SAM NEWELL ROAD) INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROAD NORTH EXTENSION TO SAM NEWELL ROAD. | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 66499000 | FY 2024: 8061000; FY 2025: 19345000; FY 2026: 19345000; FY 2027: 6448000; FY 2028: 13300000
U-2509AB | HIGHWAY | US 74 | SARDIS ROAD AND SR 3473 (SAM NEWELL ROAD) INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROAD NORTH EXTENSION TO SAM NEWELL ROAD. | 10 | Charlotte Regional TPO | SEGMENTS C6, C7A, C8 | STATEWIDE MOBILITY |  | NHP | UTILITIES | 2700000 | FY 2024: 1350000; FY 2025: 1350000
U-2509AC | HIGHWAY | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 10 | Charlotte Regional TPO | SEGMENT C11 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 11199000 | FY 2028: 4402000; FY 2029: 4971000; FY 2030: 1826000
U-2509AC | HIGHWAY | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 10 | Charlotte Regional TPO | SEGMENT C11 | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 18201000 | FY 2024: 2206000; FY 2025: 5295000; FY 2026: 5295000; FY 2027: 1765000; FY 2028: 3640000
U-2509AC | HIGHWAY | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 10 | Charlotte Regional TPO | SEGMENT C11 | STATEWIDE MOBILITY |  | NHP | UTILITIES | 3000000 | FY 2024: 1500000; FY 2025: 1500000
U-2509AD | HIGHWAY | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 51601000 | FY 2024: 6255000; FY 2025: 15011000; FY 2026: 15011000; FY 2027: 5004000; FY 2028: 10320000
U-2509AD | HIGHWAY | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | STATEWIDE MOBILITY |  | NHP | UTILITIES | 1800000 | FY 2024: 900000; FY 2025: 900000
U-2509AD | HIGHWAY | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | 10 | Charlotte Regional TPO | SEGMENT C10, C13 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 26999000 | FY 2028: 7900000; FY 2029: 10782000; FY 2030: 6188000; FY 2031: 2129000
U-2509B | HIGHWAY | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | 10 | Charlotte Regional TPO | SEGMENT M1 | STATEWIDE MOBILITY |  | NHP | UTILITIES | 0 | FY 2025: 0; FY 2026: 0
U-2509B | HIGHWAY | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | 10 | Charlotte Regional TPO | SEGMENT M1 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 25250000 | FY 2028: 7625000; FY 2029: 10268000; FY 2030: 5748000; FY 2031: 1609000
U-2509B | HIGHWAY | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | 10 | Charlotte Regional TPO | SEGMENT M1 | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 26001000 | FY 2025: 3152000; FY 2026: 7564000; FY 2027: 7564000; FY 2028: 2521000; FY 2029: 5200000
U-2509C | HIGHWAY | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | 10 | Charlotte Regional TPO | SEGMENT M2 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 39200000
U-2509C | HIGHWAY | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | 10 | Charlotte Regional TPO | SEGMENT M2 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 5600000
U-2509C | HIGHWAY | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | 10 | Charlotte Regional TPO | SEGMENT M2 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 70350000
U-2509D | HIGHWAY | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 92300000
U-2509D | HIGHWAY | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 10300000
U-2509D | HIGHWAY | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 10 | Charlotte Regional TPO | SEGMENTS C14, M3 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 202205000
U-2509E | HIGHWAY | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | NOT FUNDED |  | T | RIGHT-OF-WAY | 43200000 | [11 empty] | 43200000
U-2509E | HIGHWAY | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | NOT FUNDED |  | T | UTILITIES | 3500000 | [11 empty] | 3500000
U-2509E | HIGHWAY | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | 10 | Charlotte Regional TPO | SEGMENTS C3, C4, C5, C7B, C12 | NOT FUNDED |  | T | CONSTRUCTION | 61200000 | [11 empty] | 61200000
U-2509EA | HIGHWAY | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 3000000 | FY 2026: 750000; FY 2027: 1500000; FY 2028: 750000
U-2509EA | HIGHWAY | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 2029000 | FY 2029: 986000; FY 2030: 912000; FY 2031: 131000
U-2509EA | HIGHWAY | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | T(DA) | RIGHT-OF-WAY | 5568000 | FY 2026: 1392000; FY 2027: 2784000; FY 2028: 1392000
U-2509EA | HIGHWAY | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 10 | Charlotte Regional TPO | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP. | DIVISION 10 |  | T(DA) | CONSTRUCTION | 3767000 | FY 2029: 1831000; FY 2030: 1694000; FY 2031: 242000
U-2509EB | HIGHWAY | INDEPENDENCE POINTE PARKWAY | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | SEGMENT C9 | DIVISION 10 |  | T | UTILITIES | 600000 | FY 2026: 300000; FY 2027: 300000
U-2509EB | HIGHWAY | INDEPENDENCE POINTE PARKWAY | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | SEGMENT C9 | DIVISION 10 |  | T | CONSTRUCTION | 8200000 | FY 2029: 3222000; FY 2030: 3639000; FY 2031: 1339000; FY 2032: 0
U-2509EB | HIGHWAY | INDEPENDENCE POINTE PARKWAY | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | SEGMENT C9 | DIVISION 10 |  | T | RIGHT-OF-WAY | 12600000 | FY 2026: 3150000; FY 2027: 6300000; FY 2028: 3150000
U-2519 | HIGHWAY | I-295 (FAYETTEVILLE OUTER LOOP) | I-95 SOUTH OF FAYETTEVILLE TO WEST OF NC 24/87 (BRAGG BOULEVARD). FREEWAY ON NEW LOCATION. | 6 | Fayetteville Area MPO, Lumber River RPO | [5 empty] | 544102000
U-2519AA | HIGHWAY | I-295 | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | 6 | Lumber River RPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | REGION C |  | NHP | CONSTRUCTION | 125600000 | FY 2023: 41866000; FY 2024: 41868000
U-2519AA | HIGHWAY | I-295 | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | 6 | Lumber River RPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | REGION C |  | NHP | GARVEE CON | 123812000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000 | 9524000
U-2519AA | HIGHWAY | I-295 | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | 6 | Lumber River RPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032. | REGION C |  | S(M) | CONSTRUCTION | 11030000
U-2519BA | HIGHWAY | I-295 | SOUTH OF SR 1003 (CAMDEN ROAD) TO SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD). | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | REGION C |  | NHP | CONSTRUCTION | 161113000 | FY 2023: 78147000; FY 2024: 34451000; FY 2025: 26920000; FY 2026: 15908000
U-2519BB | HIGHWAY | I-295 | SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD) TO SOUTH OF US 401. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | REGION C |  | NHP | CONSTRUCTION | 55880000 | FY 2023: 20117000; FY 2024: 17323000; FY 2025: 12294000; FY 2026: 3352000
U-2519F | HIGHWAY | I-295 | ITS FOR FAYETTEVILLE OUTER LOOP. | 6 | Fayetteville Area MPO, Lumber River RPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 6000000 | FY 2025: 3015000; FY 2026: 2985000
U-2523 | HIGHWAY | NC 279 | NC 7 TO WEST OF NC 275 IN DALLAS. WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  |  |  | 17423000
U-2523B | HIGHWAY | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | REGION F |  | BG50200 | UTILITIES | 2300000 | FY 2026: 1150000; FY 2027: 1150000
U-2523B | HIGHWAY | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | REGION F |  | BG50200 | CONSTRUCTION | 20200000 | FY 2028: 202000; FY 2029: 7618000; FY 2030: 7675000; FY 2031: 4705000
U-2523B | HIGHWAY | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | 12 | Gaston-Cleveland-Lincoln MPO | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778). | REGION F |  | BG50200 | RIGHT-OF-WAY | 12500000 | FY 2026: 5714000; FY 2027: 4286000; FY 2028: 1250000; FY 2029: 1250000
U-2524 | HIGHWAY | I-73 / I-840 / FUTURE I-840 / US 421 | GREENSBORO WESTERN LOOP, NORTH OF I-85 TO LAWNDALE DRIVE IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 7 | Greensboro Urban Area MPO | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 635532000
U-2524C | HIGHWAY | FUTURE I-840 | GREENSBORO WESTERN LOOP, NORTH OF SR 2176 (BRYAN BOULEVARD) TO US 220 (BATTLEGROUND AVENUE) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING $105.9 MILLION; PAYBACK FY 2013-2024 | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 54285000 | FY 2023: 10857000; FY 2024: 10857000
U-2524F | HIGHWAY | FUTURE I-840 | GREENSBORO WESTERN LOOP, INTERCHANGE AT PROPOSED LEWISTON-FLEMING ROAD EXTENSION | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 15000000 | [11 empty] | 15000000
U-2525 | HIGHWAY | I-785 / I-840; FUTURE I-785; FUTURE I-840 | GREENSBORO EASTERN LOOP, LAWNDALE DRIVE TO NORTH OF I-40 / I-85 IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 7 | Greensboro Urban Area MPO | [5 empty] | 367708000
U-2525C | HIGHWAY | FUTURE I-840 | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 57121000
U-2525C | HIGHWAY | FUTURE I-840 | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | STATEWIDE MOBILITY |  | T | BUILD NC CON | 37710000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 2514000 | 5028000
U-2525C | HIGHWAY | FUTURE I-840 | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | STATEWIDE MOBILITY |  | T | ENGINEERING | 8340000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 556000 | 1112000
U-2525D | HIGHWAY | FUTURE I-840 | INTERCHANGE AT PROPOSED CONE BOULEVARD EXTENSION | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 15000000 | [11 empty] | 15000000
U-2530 | HIGHWAY | NC 127 | WIDEN NC 127 TO MULTI-LANES, SR 1132 TO SR 1008. UPGRADE AND EXTEND SR 1213 (CURRENTLY NC 127), PROPOSED US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182. | 12 | Greater Hickory MPO | [5 empty] | 12399000
U-2530A | HIGHWAY | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 23900000 | FY 2025: 7284000; FY 2026: 10926000; FY 2027: 910000; FY 2028: 2390000; FY 2029: 2390000
U-2530A | HIGHWAY | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | UTILITIES | 3800000 | FY 2025: 1900000; FY 2026: 1900000
U-2530A | HIGHWAY | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | CONSTRUCTION | 25500000 | FY 2027: 7770000; FY 2028: 9368000; FY 2029: 6423000; FY 2030: 1939000
U-2561 | HIGHWAY | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. WIDEN TO MULTI-LANES. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 6745000
U-2561C | HIGHWAY | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BGLT5 | RIGHT-OF-WAY | 3131000 | FY 2026: 527000; FY 2027: 1582000; FY 2028: 396000; FY 2029: 313000; FY 2030: 313000
U-2561C | HIGHWAY | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BGLT5 | UTILITIES | 2968000 | FY 2026: 1484000; FY 2027: 1484000
U-2561C | HIGHWAY | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BGLT5 | CONSTRUCTION | 7601000 | FY 2028: 1755000; FY 2029: 4268000; FY 2030: 1578000
U-2567 | HIGHWAY | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 25200000
U-2567 | HIGHWAY | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1500000
U-2567 | HIGHWAY | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 21200000
U-2567 | HIGHWAY | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-5929 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1700000
U-2579 | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO US 52. MULTI-LANE FREEWAY ON NEW LOCATION. | 9 | Winston-Salem Urban Area MPO | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 588926000
U-2579AA | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO I-40 | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | NHP | CONSTRUCTION | 144951000 | FY 2023: 33799000; FY 2024: 40567000; FY 2025: 33028000; FY 2026: 24396000; FY 2027: 13161000
U-2579AB | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | REGION D |  | NHP | GARVEE CON | 77220000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 5148000 | 15444000
U-2579AB | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | REGION D |  | NHP | CONSTRUCTION | 213147000 | FY 2023: 23225000; FY 2024: 42523000; FY 2025: 34648000; FY 2026: 31503000
U-2579AB | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 | REGION D |  | S(M) | CONSTRUCTION | 20000000 | FY 2023: 5000000; FY 2024: 5000000; FY 2025: 5000000
U-2579B | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158 | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $96 MILLION FOR CONSTRUCTION - PAYBACK 2015-2026 | PRE-STI (TRANSITION) |  | NHP | GARVEE CON | 68971000 | FY 2023: 9853000; FY 2024: 9853000; FY 2025: 9853000; FY 2026: 9853000
U-2579BA | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158. STREAM RELOCATION. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  | NHP | CONSTRUCTION | 9300000 | FY 2023: 2450000
U-2579BB | HIGHWAY | FUTURE I-74 | CONSTRUCT NOISE WALL | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  | T | UTILITIES | 234000
U-2579BB | HIGHWAY | FUTURE I-74 | CONSTRUCT NOISE WALL | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  | T | CONSTRUCTION | 2855000 | FY 2023: 1501000; FY 2024: 1354000
U-2579C | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION D |  | T | BUILD NC CON | 11662000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 777000 | 1561000
U-2579C | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION D |  | NHP | GARVEE ROW | 6138000 | 558000 | 558000 | 558000 | 558000 | 558000 | 558000 | 558000 | 558000
U-2579C | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION D |  | NHP | CONSTRUCTION | 15560000
U-2579D | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 311 TO SR 2211 (BAUX MOUNTAIN ROAD) | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $38 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 42380000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000 | 3260000
U-2579E | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, SR 2211 (BAUX MOUNTAIN ROAD) TO NC 8 | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $30 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 33462000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000
U-2579F | HIGHWAY | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, NC 8 TO WEST OF NC 66 (UNIVERSITY PARKWAY) | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $24 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 26767000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000
U-2581 | HIGHWAY | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 7 | Greensboro Urban Area MPO | [5 empty] | 6281000
U-2581BA | HIGHWAY | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | BUILD NC CON | 13000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0
U-2581BA | HIGHWAY | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | BUILD NC CON | 11910000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 794000 | 1588000
U-2581BA | HIGHWAY | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | CONSTRUCTION | 3612000
U-2581BA | HIGHWAY | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | BUILD NC ROW | 2618000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000
U-2581BA | HIGHWAY | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | ENGINEERING | 1414000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000 | 101000
U-2581BA | HIGHWAY | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | ENGINEERING | 195000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 26000
U-2581BB | HIGHWAY | US 70 | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2113000 | [11 empty] | 2113000
U-2581BB | HIGHWAY | US 70 | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 626000 | [11 empty] | 626000
U-2581BB | HIGHWAY | US 70 | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 8200000 | [11 empty] | 8200000
U-2581BC | HIGHWAY | US 70 | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3040000 | [11 empty] | 3040000
U-2581BC | HIGHWAY | US 70 | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 901000 | [11 empty] | 901000
U-2581BC | HIGHWAY | US 70 | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 11800000 | [11 empty] | 11800000
U-2707 | HIGHWAY | SR 3000 (IDOLS ROAD) | SR 2999 (HAMPTON ROAD) TO US 158 IN CLEMMONS. CONSTRUCT TWO-LANE SHOULDER SECTION ON NEW LOCATION AND REPLACE BRIDGE 330109 OVER NORFOLK SOUTHERN RAILROAD. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 20759000
U-2714 | HIGHWAY | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | ENGINEERING | 4230000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000 | 282000
U-2714 | HIGHWAY | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | BUILD NC CON | 16875000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 1125000 | 2250000
U-2714 | HIGHWAY | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | CONSTRUCTION | 5985000
U-2714 | HIGHWAY | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | L | CONSTRUCTION | 1327000
U-2714 | HIGHWAY | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  |  |  | 9483000
U-2714 | HIGHWAY | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | ENGINEERING | 60000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 8000
U-2714 | HIGHWAY | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | REGION A |  | T | BUILD NC ROW | 3510000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000 | 234000
U-2719 | HIGHWAY | I-440/US-1 | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT OF WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | STATEWIDE MOBILITY |  |  |  | 262047000
U-2719 | HIGHWAY | I-440/US-1 | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT OF WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | STATEWIDE MOBILITY |  | NHP | GARVEE ROW | 34749000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2317000 | 2311000
U-2719 | HIGHWAY | I-440/US-1 | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT OF WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | STATEWIDE MOBILITY |  | NHP | GARVEE CON | 158558000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000 | 10725000
U-2729 | HIGHWAY | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 9 |  |  |  | 3710000
U-2729 | HIGHWAY | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 9 |  | T | CONSTRUCTION | 17599000 | FY 2023: 176000; FY 2024: 6923000; FY 2025: 6772000; FY 2026: 3728000
U-2729 | HIGHWAY | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 9 |  | T | ENGINEERING | 1092000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000 | 78000
U-2729 | HIGHWAY | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 9 |  | T | BUILD NC ROW | 686000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000
U-2801 | HIGHWAY | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO ROBERTS ROAD IN ASHEVILLE. WIDEN TO MULTI-LANES. | 13 | French Broad River MPO | [5 empty] | 22226000
U-2801AA | HIGHWAY | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | 13 | French Broad River MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 92500000
U-2801AA | HIGHWAY | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | 13 | French Broad River MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 10200000
U-2801AA | HIGHWAY | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | 13 | French Broad River MPO |  | REGION G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 39400000
U-2801AB | HIGHWAY | US 25A (SWEETEN CREEK ROAD) | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | 13 | French Broad River MPO |  | REGION G |  | BGANY | RIGHT-OF-WAY | 56599000 | FY 2028: 12349000; FY 2029: 16465000; FY 2030: 16465000; FY 2031: 5660000; FY 2032: 5660000
U-2801AB | HIGHWAY | US 25A (SWEETEN CREEK ROAD) | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | 13 | French Broad River MPO |  | REGION G |  | BGANY | UTILITIES | 7100000 | FY 2028: 3550000; FY 2029: 3550000
U-2801AB | HIGHWAY | US 25A (SWEETEN CREEK ROAD) | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | 13 | French Broad River MPO |  | REGION G |  | BGANY | CONSTRUCTION | 53499000 | FY 2031: 535000; FY 2032: 13695000; FY 2033: 15591000 | 23678000
U-2810 | HIGHWAY | SR 1003 (CAMDEN ROAD) | NC 59 (HOPE MILLS ROAD) TO SR 1007 (OWEN DRIVE) IN FAYETTEVILLE. WIDEN ROADWAY TO MULTI-LANES, PART ON NEW LOCATION. | 6 | Fayetteville Area MPO | [5 empty] | 53156000
U-2817 | HIGHWAY | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  |  |  | 60010000
U-2817 | HIGHWAY | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | BG5200 | RIGHT-OF-WAY | 22800000
U-2817 | HIGHWAY | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | BG5200 | UTILITIES | 3972000
U-2817 | HIGHWAY | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | BG5200 | CONSTRUCTION | 67545000 | FY 2025: 2687000; FY 2026: 22373000; FY 2027: 19001000; FY 2028: 14070000; FY 2029: 9414000
U-2823 | HIGHWAY | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3775000
U-2823 | HIGHWAY | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 84202000
U-2823 | HIGHWAY | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 37100000
U-2823 | HIGHWAY | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES WITH REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1200000
U-2827 | HIGHWAY | US 158 / US 421 / NC 150 / BUSINESS 40 | I-40 TO WEST OF US 158 IN WINSTON-SALEM. PAVEMENT REHABILITATION, REPLACE BRIDGES 330178, 330269, 330278, 330286, 330288 330291, 330293, 330305, 330312 330313, 330336 AND VARIOUS SAFETY IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | [5 empty] | 189167000
U-2901 | HIGHWAY | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD) IN APEX. WIDEN TO A MULTI-LANE CURB AND GUTTER FACILITY. | 5 | Capital Area MPO | PROJECTS U-2901AA AND AB COMPLETE |  |  |  |  | 4860000
U-2901B | HIGHWAY | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 20002000
U-2901B | HIGHWAY | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 11000000
U-2901B | HIGHWAY | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3650000
U-2901BA | HIGHWAY | NC 55 (WILLIAMS STREET) | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. | 5 | Capital Area MPO |  | REGION C |  | T | CONSTRUCTION | 17000000 | FY 2029: 2146000; FY 2030: 6325000; FY 2031: 4968000; FY 2032: 3561000
U-2901BA | HIGHWAY | NC 55 (WILLIAMS STREET) | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. | 5 | Capital Area MPO |  | REGION C |  | T | RIGHT-OF-WAY | 1000000 | FY 2027: 1000000
U-2901BA | HIGHWAY | NC 55 (WILLIAMS STREET) | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. | 5 | Capital Area MPO |  | REGION C |  | T | UTILITIES | 250000 | FY 2027: 250000
U-2925 | HIGHWAY | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE) TO SR 4325 (MARTIN LUTHER KING, JR. DRIVE) IN WINSTON-SALEM. MULTI-LANE FACILITY ON NEW LOCATION. | 9 | Winston-Salem Urban Area MPO | DESIGN-BUILD PROJECT COMPLETE | PRE-STI (TRANSITION) |  |  |  | 93832000
U-2925C | HIGHWAY | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGANY | CONSTRUCTION | 1086000 | FY 2024: 1086000
U-2925C | HIGHWAY | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGDA | ENGINEERING | 362000
U-2925C | HIGHWAY | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | ENGINEERING | 91000
U-2925C | HIGHWAY | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | CONSTRUCTION | 272000 | FY 2024: 272000
U-3109 | HIGHWAY | NC 119 | NC 119 RELOCATION, I-85 TO SOUTH OF SR 1918 (MRS. WHITE ROAD) IN MEBANE. FOUR-TO-SIX-LANE FACILITY ON NEW LOCATION. | 7 | Burlington-Graham MPO | [5 empty] | 84313000
U-3109A | HIGHWAY | NC 119 | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION D |  | T | BUILD NC CON | 24772000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 1651000 | 3309000
U-3109A | HIGHWAY | NC 119 | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION D |  | T | ENGINEERING | 360000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 48000
U-3109A | HIGHWAY | NC 119 | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION D |  | T | BUILD NC CON | 18195000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000 | 1213000
U-3109B | HIGHWAY | NC 119 | NC 119 RELOCATION, NORTH OF SR 1921 (MEBANE ROGERS ROAD) TO SOUTH OF SR 1918 (MRS. WHITE ROAD) | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.533 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION D |  | T | BUILD NC CON | 5835000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 778000
U-3110 | HIGHWAY | NEW ROUTE | NEW ROUTE, US 70 TO NC 100 IN ELON. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | 7 | Burlington-Graham MPO | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS |  |  |  |  | 27033000
U-3110B | HIGHWAY | NEW ROUTE | IMPROVEMENTS ON SR 1311 (COOK ROAD), SR 1309 (WESTBROOK AVENUE) TO NC 100, PART ON NEW LOCATION | 7 | Burlington-Graham MPO | COMPLETE; GARVEE BOND FUNDING $10.5 MILLION; PAYBACK FY 2011 - FY 2022 | PRE-STI (TRANSITION) |  | BG5200 | GARVEE CON | 3444000
U-3125 | HIGHWAY | US 117 (FUTURE I-795) | I-40 TO I-795. UPGRADE ROADWAY TO INTERSTATE STANDARDS, PART ON NEW LOCATION. | 3, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO, Mid-Carolina RPO | [5 empty] | 1000000
U-3125A | HIGHWAY | US 117 (FUTURE 1-795) | I-40 TO SR 1006 (WEST TRADE ROAD). | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | CONSTRUCTION | 103500000 | [11 empty] | 103500000
U-3125A | HIGHWAY | US 117 (FUTURE 1-795) | I-40 TO SR 1006 (WEST TRADE ROAD). | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 7183000 | [11 empty] | 7183000
U-3125A | HIGHWAY | US 117 (FUTURE 1-795) | I-40 TO SR 1006 (WEST TRADE ROAD). | 3 | Eastern Carolina RPO, Mid-Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | UTILITIES | 2238000 | [11 empty] | 2238000
U-3125B | HIGHWAY | US 117 (FUTURE I-795) | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 25266000 | [11 empty] | 25266000
U-3125B | HIGHWAY | US 117 (FUTURE I-795) | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | UTILITIES | 10475000 | [11 empty] | 10475000
U-3125B | HIGHWAY | US 117 (FUTURE I-795) | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | 3, 4 | Eastern Carolina RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | NOT FUNDED |  | NHP | CONSTRUCTION | 73300000 | [11 empty] | 73300000
U-3125C | HIGHWAY | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | REGION A |  | NHP | RIGHT-OF-WAY | 100000 | FY 2026: 100000
U-3125C | HIGHWAY | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | REGION A |  | NHP | UTILITIES | 138000 | FY 2026: 138000
U-3125C | HIGHWAY | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO |  | REGION A |  | NHP | CONSTRUCTION | 13300000 | FY 2028: 5193000; FY 2029: 5859000; FY 2030: 2248000
U-3125D | HIGHWAY | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | 4 | Goldsboro Urban Area MPO |  | REGION A |  | NHP | RIGHT-OF-WAY | 13530000 | FY 2027: 3608000; FY 2028: 5412000; FY 2029: 1804000; FY 2030: 1353000; FY 2031: 1353000
U-3125D | HIGHWAY | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | 4 | Goldsboro Urban Area MPO |  | REGION A |  | NHP | UTILITIES | 2172000 | FY 2027: 1086000; FY 2028: 1086000
U-3125D | HIGHWAY | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | 4 | Goldsboro Urban Area MPO |  | REGION A |  | NHP | CONSTRUCTION | 59400000 | FY 2029: 14073000; FY 2030: 18418000; FY 2031: 14362000; FY 2032: 10078000; FY 2033: 2469000
U-3125E | HIGHWAY | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | 4 | Goldsboro Urban Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 35788000 | [11 empty] | 35788000
U-3125E | HIGHWAY | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | 4 | Goldsboro Urban Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 1513000 | [11 empty] | 1513000
U-3125E | HIGHWAY | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | 4 | Goldsboro Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 135500000 | [11 empty] | 135500000
U-3125F | HIGHWAY | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | 4 | Goldsboro Urban Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 20760000 | [11 empty] | 20760000
U-3125F | HIGHWAY | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | 4 | Goldsboro Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 62700000 | [11 empty] | 62700000
U-3125F | HIGHWAY | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | 4 | Goldsboro Urban Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 4729000 | [11 empty] | 4729000
U-3301 | HIGHWAY | NC 63 (LEICESTER HIGHWAY) | SR 1615 (GILBERT ROAD) TO WEST OF SR 1004 (NEWFOUND ROAD) IN ASHEVILLE. WIDEN TO MULTI-LANES, SOME RELOCATION. | 13 | French Broad River MPO | UNDER CONSTRUCTION - DESIGN BUILD PROJECT | PRE-STI (TRANSITION) |  |  |  | 55129000
U-3308 | HIGHWAY | NC 55 (ALSTON AVENUE) | NC 147 (DURHAM FREEWAY) TO US 70 BUSINESS / NC 98 (HOLLOWAY STREET) IN DURHAM. WIDEN TO FOUR-LANE DIVIDED FACILITY FROM NC 147 TO MAIN STREET AND REPLACE NORFOLK SOUTHERN RAILROAD BRIDGES. MODERNIZE FROM MAIN STREET TO US 70 BUSINESS / NC 98 (HOLLOWAY ST | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 41348000
U-3326 | HIGHWAY | US 29 BUSINESS/US 158 (FREEWAY DRIVE) | SOUTH SCALES STREET TO NC 14 IN REIDSVILLE. WIDEN TO MULTI-LANES. | 7 | Piedmont Triad RPO | [5 empty] | 101957000
U-3338 | HIGHWAY | SR 1175 (KERR AVENUE) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO | [5 empty] | 76486000
U-3338C | HIGHWAY | SR 1175 (KERR AVENUE) | SR 1175 (KERR AVENUE) INTERCHANGE AT US 74 (MARTIN LUTHER KING, JR. PARKWAY). | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  | BGANY | CONSTRUCTION | 26800000 | FY 2028: 7221000; FY 2029: 10365000; FY 2030: 7126000; FY 2031: 2088000
U-3400 | HIGHWAY | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 7, 8 | High Point Urban Area MPO |  | DIVISION 7, 8 |  |  |  | 1520000
U-3400 | HIGHWAY | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 7, 8 | High Point Urban Area MPO |  | DIVISION 7, 8 |  | T | RIGHT-OF-WAY | 7901000 | FY 2024: 79000; FY 2025: 2231000; FY 2026: 2231000; FY 2027: 1859000; FY 2028: 1501000
U-3400 | HIGHWAY | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 7, 8 | High Point Urban Area MPO |  | DIVISION 7, 8 |  | T | UTILITIES | 12126000 | FY 2024: 6063000; FY 2025: 6063000
U-3400 | HIGHWAY | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 7, 8 | High Point Urban Area MPO |  | DIVISION 7, 8 |  | T | CONSTRUCTION | 18600000 | FY 2029: 3832000; FY 2030: 8254000; FY 2031: 5508000; FY 2032: 1006000
U-3403 | HIGHWAY | NC 191 (BREVARD ROAD) | NC 280 TO NC 112 (SARDIS ROAD). WIDEN TO MULTI-LANES. | 13, 14 | French Broad River MPO | [5 empty] | 16273000
U-3403A | HIGHWAY | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NC 280 (BOYLSTON HIGHWAY) TO SR 3498 (LEDBETTER ROAD). | 13, 14 | French Broad River MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 9000000 | [11 empty] | 9000000
U-3403A | HIGHWAY | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NC 280 (BOYLSTON HIGHWAY) TO SR 3498 (LEDBETTER ROAD). | 13, 14 | French Broad River MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 17700000 | [11 empty] | 17700000
U-3403B | HIGHWAY | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 23800000 | [11 empty] | 23800000
U-3403B | HIGHWAY | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 48873000 | [11 empty] | 48873000
U-3403B | HIGHWAY | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | UTILITIES | 3900000 | [11 empty] | 3900000
U-3415 | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | SR 1445 (DERITA ROAD) TO US 29/601 BYPASS. WIDEN TO MULTI-LANES. | 10 | Cabarrus-Rowan MPO | [5 empty] | 2732000
U-3415A | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY. WIDEN TO MULTI-LANES. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | T | RIGHT-OF-WAY | 12900000 | FY 2025: 543000; FY 2026: 3259000; FY 2027: 3259000; FY 2028: 3259000; FY 2029: 2580000
U-3415A | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY. WIDEN TO MULTI-LANES. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | T | UTILITIES | 900000 | FY 2025: 450000; FY 2026: 450000
U-3415A | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY. WIDEN TO MULTI-LANES. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | T | CONSTRUCTION | 27713000 | FY 2028: 277000; FY 2029: 10877000; FY 2030: 10058000; FY 2031: 5428000; FY 2032: 1073000
U-3415B | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | GEORGE LILES PARKWAY TO US 29/601. WIDEN TO MULTI-LANES. | 10 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | UTILITIES | 13200000 | [11 empty] | 13200000
U-3415B | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | GEORGE LILES PARKWAY TO US 29/601. WIDEN TO MULTI-LANES. | 10 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 32900000 | [11 empty] | 32900000
U-3415B | HIGHWAY | SR 1394 (POPLAR TENT ROAD) | GEORGE LILES PARKWAY TO US 29/601. WIDEN TO MULTI-LANES. | 10 | Cabarrus-Rowan MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 9900000 | [11 empty] | 9900000
U-3422 | HIGHWAY | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | DIVISION 6 |  | BGANY | RIGHT-OF-WAY | 9975000
U-3422 | HIGHWAY | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | DIVISION 6 |  | BGANY | UTILITIES | 2825000
U-3422 | HIGHWAY | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | DIVISION 6 |  | T | BUILD NC CON | 19305000 |  | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 6435000
U-3422 | HIGHWAY | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | DIVISION 6 |  | T | CONSTRUCTION | 17675000 | FY 2024: 0; FY 2025: 3624000; FY 2026: 9803000; FY 2027: 4248000
U-3422 | HIGHWAY | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). | DIVISION 6 |  |  |  | 2500000
U-3431 | HIGHWAY | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | 2 | Down East RPO |  | DIVISION 2 |  | T | UTILITIES | 4864000 | FY 2026: 2432000; FY 2027: 2432000
U-3431 | HIGHWAY | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | 2 | Down East RPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 18759000 | FY 2026: 938000; FY 2027: 11255000; FY 2028: 2814000; FY 2029: 1876000; FY 2030: 1876000
U-3431 | HIGHWAY | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | 2 | Down East RPO |  | DIVISION 2 |  |  |  | 1450000
U-3431 | HIGHWAY | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | 2 | Down East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 36399000 | FY 2028: 8379000; FY 2029: 13471000; FY 2030: 9726000; FY 2031: 4823000
U-3440 | HIGHWAY | NC 3 | PROPOSED WEST SIDE BYPASS (U-2009) TO SR 1691 (LOOP ROAD) IN KANNAPOLIS. WIDEN TO A FOUR-LANE DIVIDED FACILITY. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 48456000
U-3465 | HIGHWAY | SR 1121 (RAY ROAD) | NC 210 TO SR 1120 (OVERHILLS ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  |  |  | 40292000
U-3467 | HIGHWAY | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | REGION E |  | BGANY | CONSTRUCTION | 44899000 | FY 2027: 14206000; FY 2028: 15872000; FY 2029: 9599000; FY 2030: 5222000
U-3467 | HIGHWAY | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | REGION E |  |  |  | 18015000
U-3467 | HIGHWAY | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | REGION E |  | BGANY | RIGHT-OF-WAY | 70000000 | FY 2024: 2154000; FY 2025: 25846000; FY 2026: 25846000; FY 2027: 2154000; FY 2028: 14000000
U-3467 | HIGHWAY | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | REGION E |  | BGANY | UTILITIES | 3000000 | FY 2024: 1500000; FY 2025: 1500000
U-3609 | HIGHWAY | US 13 (BERKELEY BOULEVARD) | SR 1560 (ROYAL AVENUE) TO NORTH OF SR 1572 (SAULSTON ROAD) IN GOLDSBORO. WIDEN TO MULTI-LANES. | 4 | Goldsboro Urban Area MPO | [5 empty] | 5806000
U-3609B | HIGHWAY | US 13 (BERKELEY BOULEVARD) | WIDEN TO FOUR LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 WITH INTERSECTION IMPROVEMENT AT SR 1572 (SAULSTON ROAD). | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE). | REGION A |  | T | BUILD NC ROW | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
U-3609B | HIGHWAY | US 13 (BERKELEY BOULEVARD) | WIDEN TO FOUR LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 WITH INTERSECTION IMPROVEMENT AT SR 1572 (SAULSTON ROAD). | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE). | REGION A |  | T | RIGHT-OF-WAY | 23324000 | FY 2025: 7000000
U-3609B | HIGHWAY | US 13 (BERKELEY BOULEVARD) | WIDEN TO FOUR LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 WITH INTERSECTION IMPROVEMENT AT SR 1572 (SAULSTON ROAD). | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE). | REGION A |  | T | UTILITIES | 3750000
U-3609B | HIGHWAY | US 13 (BERKELEY BOULEVARD) | WIDEN TO FOUR LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 WITH INTERSECTION IMPROVEMENT AT SR 1572 (SAULSTON ROAD). | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE). | REGION A |  | T | BUILD NC CON | 12870000 |  |  | 1716000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 4290000
U-3609B | HIGHWAY | US 13 (BERKELEY BOULEVARD) | WIDEN TO FOUR LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 WITH INTERSECTION IMPROVEMENT AT SR 1572 (SAULSTON ROAD). | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE). | REGION A |  | T | CONSTRUCTION | 16800000 | FY 2025: 0; FY 2026: 9296000; FY 2027: 6968000; FY 2028: 536000
U-3609B | HIGHWAY | US 13 (BERKELEY BOULEVARD) | WIDEN TO FOUR LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 WITH INTERSECTION IMPROVEMENT AT SR 1572 (SAULSTON ROAD). | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE). | REGION A |  | T | ENGINEERING | 2400000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000
U-3609BA | HIGHWAY | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF HOOD SWAMP ROAD. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | T | CONSTRUCTION | 1780000 | FY 2023: 280000
U-3615 | HIGHWAY | SR 1820 (SKEET CLUB ROAD) | US 311 TO NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. WIDEN TO FOUR- AND FIVE-LANE DIVIDED FACILITY. | 7 | High Point Urban Area MPO | [5 empty] | 57587000
U-3615A | HIGHWAY | SR 1820 (SKEET CLUB ROAD) | US 311 TO EAST OF SR 1818 (JOHNSON STREET). WIDEN TO FIVE-LANE FACILITY FROM US 311 TO NORTH OF US 311 AND TO FOUR-LANE MEDIAN DIVIDED FACILITY FROM NORTH OF US 311 TO EAST OF SR1818 (JOHNSON STREET). | 7 | High Point Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5700000 | [11 empty] | 5700000
U-3615A | HIGHWAY | SR 1820 (SKEET CLUB ROAD) | US 311 TO EAST OF SR 1818 (JOHNSON STREET). WIDEN TO FIVE-LANE FACILITY FROM US 311 TO NORTH OF US 311 AND TO FOUR-LANE MEDIAN DIVIDED FACILITY FROM NORTH OF US 311 TO EAST OF SR1818 (JOHNSON STREET). | 7 | High Point Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 15500000 | [11 empty] | 15500000
U-3618 | HIGHWAY | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  |  |  | 1258000
U-3618 | HIGHWAY | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | BGANY | RIGHT-OF-WAY | 4699000 | FY 2025: 47000; FY 2026: 1287000; FY 2027: 1455000; FY 2028: 970000; FY 2029: 470000; FY 2030: 470000
U-3618 | HIGHWAY | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | BGANY | UTILITIES | 1000000 | FY 2025: 500000; FY 2026: 500000
U-3618 | HIGHWAY | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 2 | Eastern Carolina RPO |  | DIVISION 2 |  | BGANY | CONSTRUCTION | 28301000 | FY 2028: 283000; FY 2029: 11518000; FY 2030: 9610000; FY 2031: 6365000; FY 2032: 525000
U-3628 | HIGHWAY | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | REGION E |  |  |  | 1924000
U-3628 | HIGHWAY | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | REGION E |  | T | RIGHT-OF-WAY | 2950000 | FY 2023: 1475000; FY 2024: 1475000
U-3628 | HIGHWAY | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929 | REGION E |  | T | CONSTRUCTION | 4600000 | FY 2025: 2894000; FY 2026: 1706000
U-3633 | HIGHWAY | NC 273 (SOUTH MAINSTREET) | TUCKASEEGEE ROAD (AT BEATTY DRIVE) TO HIGHLAND STREET (AT A & E DRIVE) IN MOUNT HOLLY. WIDEN TO FOUR-LANES DIVIDED. | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746 | REGION F |  |  |  | 22983000
U-3633 | HIGHWAY | NC 273 (SOUTH MAINSTREET) | TUCKASEEGEE ROAD (AT BEATTY DRIVE) TO HIGHLAND STREET (AT A & E DRIVE) IN MOUNT HOLLY. WIDEN TO FOUR-LANES DIVIDED. | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746 | REGION F |  | T | BUILD NC CON | 6315000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 421000 | 842000
U-4007 | HIGHWAY | US 17 | US 17 BUSINESS TO SR 1326 (DRUMMER KELLUM ROAD) IN JACKSONVILLE. ADD ADDITIONAL LANES AND CONSTRUCT ROUTES ON NEW LOCATION. | 3 | Jacksonville Urban Area MPO | [5 empty] | 93309000
U-4007C | HIGHWAY | US 17 | WESTERN BOULEVARD TO FAIRWAY DRIVE. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 26300000 | [11 empty] | 26300000
U-4007C | HIGHWAY | US 17 | WESTERN BOULEVARD TO FAIRWAY DRIVE. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 34775000 | [11 empty] | 34775000
U-4007D | HIGHWAY | US 17 | FAIRWAY DRIVE TO DRUMMER KELLUM ROAD. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 16600000 | [11 empty] | 16600000
U-4007D | HIGHWAY | US 17 | FAIRWAY DRIVE TO DRUMMER KELLUM ROAD. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 32345000 | [11 empty] | 32345000
U-4007E | HIGHWAY | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736 AND U-5508. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 8099000 | FY 2028: 1564000; FY 2029: 2681000; FY 2030: 2234000; FY 2031: 810000; FY 2032: 810000
U-4007E | HIGHWAY | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736 AND U-5508. | STATEWIDE MOBILITY |  | T | UTILITIES | 400000 | FY 2028: 400000
U-4007E | HIGHWAY | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-5736 AND U-5508. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 7200000 | FY 2030: 72000; FY 2031: 4371000; FY 2032: 2757000
U-4015 | HIGHWAY | SR 1556 (GALLIMORE DAIRY ROAD) | NC 68 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO | [5 empty] | 7113000
U-4015A | HIGHWAY | SR 1556 (GALLIMORE DAIRY ROAD) | NC 68 TO AIRPARK ROAD IN GREENSBORO. WIDEN TO MULTILANES | 7 | Greensboro Urban Area MPO | RIGHT OF WAY IN PROGRESS | DIVISION 7 |  | T | CONSTRUCTION | 11500000 | FY 2024: 115000; FY 2025: 6731000; FY 2026: 3702000; FY 2027: 952000
U-4024 | HIGHWAY | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | REGION E |  |  |  | 2045000
U-4024 | HIGHWAY | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | REGION E |  | T | RIGHT-OF-WAY | 3300000 | FY 2028: 360000; FY 2029: 1440000; FY 2030: 840000; FY 2031: 330000; FY 2032: 330000
U-4024 | HIGHWAY | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | REGION E |  | T | UTILITIES | 400000 | FY 2028: 400000
U-4024 | HIGHWAY | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH U-5723 | REGION E |  | T | CONSTRUCTION | 13699000 | FY 2030: 2880000; FY 2031: 6989000; FY 2032: 3481000; FY 2033: 349000
U-4403 | HIGHWAY | US 401 (RAMSEY STREET) | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO NORTH OF SLOCUMB ROAD. WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO | [5 empty] | 5900000
U-4403A | HIGHWAY | US 401 BUSINESS | NC 24/210 (GROVE STREET) TO US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY). | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 7400000 | [11 empty] | 7400000
U-4403A | HIGHWAY | US 401 BUSINESS | NC 24/210 (GROVE STREET) TO US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY). | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3121000 | [11 empty] | 3121000
U-4403B | HIGHWAY | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 33002000
U-4403B | HIGHWAY | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 12020000
U-4403B | HIGHWAY | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 10123000
U-4403C | HIGHWAY | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | RIGHT-OF-WAY | 5116000 | FY 2026: 0; FY 2027: 0; FY 2028: 0; FY 2029: 692000; FY 2030: 2212000; FY 2031: 2212000
U-4403C | HIGHWAY | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | BUILD NC UTL | 20595000 |  |  |  | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 1373000 | 9611000
U-4403C | HIGHWAY | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | UTILITIES | 5733000 | FY 2026: 0; FY 2027: 5733000
U-4403C | HIGHWAY | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | CONSTRUCTION | 34699000 | FY 2029: 4400000; FY 2030: 12667000; FY 2031: 10569000; FY 2032: 7063000
U-4403C | HIGHWAY | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT-OF-WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | BUILD NC ROW | 21885000 |  |  |  | 1459000 | 1459000 | 1459000 | 1459000 | 1459000 | 1459000 | 1459000 | 1459000 | 10213000
U-4404 | HIGHWAY | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | T | RIGHT-OF-WAY | 4391000 | FY 2028: 44000; FY 2029: 1796000; FY 2030: 1673000; FY 2031: 439000; FY 2032: 439000
U-4404 | HIGHWAY | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | T | UTILITIES | 1020000 | FY 2028: 510000; FY 2029: 510000
U-4404 | HIGHWAY | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  |  |  | 1500000
U-4404 | HIGHWAY | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | T | CONSTRUCTION | 10400000 | FY 2030: 104000; FY 2031: 5419000; FY 2032: 4192000; FY 2033: 685000
U-4405 | HIGHWAY | US 401 (RAEFORD ROAD) | SR 3569 (OLD RAEFORD ROAD) TO EAST OF SR 3828 (ROBESON STREET) IN FAYETTEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 6 | Fayetteville Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 6 |  |  |  | 70096000
U-4405A | HIGHWAY | US 401 (RAEFORD ROAD) | OLD RAEFORD ROAD TO EAST OF BUNCE ROAD. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | BGANY | CONSTRUCTION | 35403000 | FY 2023: 10093000; FY 2024: 7003000; FY 2025: 1370000
U-4405B | HIGHWAY | US 401 (RAEFORD ROAD) | EAST OF BUNCE ROAD TO EAST OF GLENSFORD DRIVE. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | BGANY | CONSTRUCTION | 23099000 | FY 2024: 3240000; FY 2025: 8896000; FY 2026: 7156000; FY 2027: 3807000
U-4405C | HIGHWAY | US 401 (RAEFORD ROAD) | EAST OF SR 1596 (GLENSFORD DRIVE) TO EAST OF ROBESON STREET. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | BGANY | CONSTRUCTION | 41401000 | FY 2025: 414000; FY 2026: 13075000; FY 2027: 13949000; FY 2028: 10445000; FY 2029: 3518000
U-4407 | HIGHWAY | US 70 BUSINESS (EAST ASH STREET) | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 4 | Goldsboro Urban Area MPO |  | REGION A |  | T | UTILITIES | 2090000 | FY 2026: 1045000; FY 2027: 1045000
U-4407 | HIGHWAY | US 70 BUSINESS (EAST ASH STREET) | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 4 | Goldsboro Urban Area MPO |  | REGION A |  | T | CONSTRUCTION | 17500000 | FY 2028: 3071000; FY 2029: 8009000; FY 2030: 5251000; FY 2031: 1169000
U-4407 | HIGHWAY | US 70 BUSINESS (EAST ASH STREET) | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 4 | Goldsboro Urban Area MPO |  | REGION A |  |  |  | 750000
U-4407 | HIGHWAY | US 70 BUSINESS (EAST ASH STREET) | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 4 | Goldsboro Urban Area MPO |  | REGION A |  | T | RIGHT-OF-WAY | 3979000 | FY 2026: 764000; FY 2027: 1528000; FY 2028: 891000; FY 2029: 398000; FY 2030: 398000
U-4414 | HIGHWAY | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2363000
U-4414 | HIGHWAY | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1548000
U-4414 | HIGHWAY | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 919000
U-4414 | HIGHWAY | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 67101000
U-4424 | HIGHWAY | NC 111 (WILSON STREET) | US 64 ALTERNATE (WESTERN BOULEVARD) TO NC 122 (MCNAIR ROAD). WIDEN TO THREE LANES. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | DIVISION 4 |  | T | CONSTRUCTION | 20000000 | FY 2023: 200000; FY 2024: 8600000; FY 2025: 8000000; FY 2026: 3200000
U-4424 | HIGHWAY | NC 111 (WILSON STREET) | US 64 ALTERNATE (WESTERN BOULEVARD) TO NC 122 (MCNAIR ROAD). WIDEN TO THREE LANES. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 5072000
U-4434 | HIGHWAY | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGANY | CONSTRUCTION | 128601000 | FY 2031: 6622000; FY 2032: 37497000; FY 2033: 34104000 | 50378000
U-4434 | HIGHWAY | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGANY | UTILITIES | 3632000 | FY 2027: 1816000; FY 2028: 1816000
U-4434 | HIGHWAY | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  |  |  | 4163000
U-4434 | HIGHWAY | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGANY | RIGHT-OF-WAY | 88701000 | FY 2027: 887000; FY 2028: 24917000; FY 2029: 25804000; FY 2030: 19353000; FY 2031: 17740000
U-4437 | HIGHWAY | NC 54 (HILLSBOROUGH STREET) | SR 1664 / SR 3074 (BLUE RIDGE ROAD) IN VICINITY OF NC RAILROAD (CSX CORPORATION AND NORFOLK SOUTHERN) IN RALEIGH. CONSTRUCT GRADE SEPARATIONS AND ACCESS ROAD BETWEEN NC 54 AND SR 1664 / SR 3074. | 5 | Capital Area MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT - LET WITH U-2719; INCLUDES $19.9 MILLION FEDERAL TIGER GRANT | DIVISION 5 |  |  |  | 69748000
U-4700 | HIGHWAY | US 321 | NORTH OF US 70 IN HICKORY TO SR 1933 (SOUTHWEST BOULEVARD). WIDEN TO SIX LANES. | 11, 12, 13 | Greater Hickory MPO | INCLUDES B-4450. |  |  |  |  | 11864000
U-4700A | HIGHWAY | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | STATEWIDE MOBILITY |  | NHP | GARVEE ROW | 57915000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 3861000 | 7722000
U-4700A | HIGHWAY | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | STATEWIDE MOBILITY |  | S(M) | RIGHT-OF-WAY | 15000000 | FY 2023: 5000000
U-4700A | HIGHWAY | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | STATEWIDE MOBILITY |  | L | CONSTRUCTION | 699000 | FY 2026: 7000; FY 2027: 188000; FY 2028: 194000; FY 2029: 171000; FY 2030: 139000
U-4700A | HIGHWAY | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 219600000 | FY 2026: 2196000; FY 2027: 59118000; FY 2028: 60954000; FY 2029: 53653000; FY 2030: 43679000
U-4700A | HIGHWAY | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | 11, 12, 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035 | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 15100000 | FY 2023: 5034000
U-4700AA | HIGHWAY | US 321 | INTERIM STRUCTURE IMPROVEMENTS ON US 321 SOUTHBOUND BRIDGE OVER LAKE HICKORY. | 11, 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 2400000 | FY 2023: 1083000
U-4700B | HIGHWAY | US 321 | US 321A TO SR 1108 (MISSION ROAD) | 11 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 35000000 | [11 empty] | 35000000
U-4700B | HIGHWAY | US 321 | US 321A TO SR 1108 (MISSION ROAD) | 11 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | UTILITIES | 4000000 | [11 empty] | 4000000
U-4700B | HIGHWAY | US 321 | US 321A TO SR 1108 (MISSION ROAD) | 11 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 57500000 | [11 empty] | 57500000
U-4700C | HIGHWAY | US 321 | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | 11 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 5000000 | [11 empty] | 5000000
U-4700C | HIGHWAY | US 321 | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | 11 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | UTILITIES | 2000000 | [11 empty] | 2000000
U-4700C | HIGHWAY | US 321 | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | 11 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 12000000 | [11 empty] | 12000000
U-4700CA | HIGHWAY | US 321 | SR 1160 (MOUNT HERMAN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 11 | Greater Hickory MPO | DESIGN BY DIVISION. UNDER CONSTRUCTION. | REGION F |  | NHP | RIGHT-OF-WAY | 420000
U-4700CA | HIGHWAY | US 321 | SR 1160 (MOUNT HERMAN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 11 | Greater Hickory MPO | DESIGN BY DIVISION. UNDER CONSTRUCTION. | REGION F |  | NHP | CONSTRUCTION | 4101000 | FY 2023: 308000; FY 2024: 2876000; FY 2025: 917000
U-4700CB | HIGHWAY | US 321 | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 400000
U-4700CB | HIGHWAY | US 321 | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | UTILITIES | 100000
U-4700CB | HIGHWAY | US 321 | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 9200000 | FY 2024: 735000; FY 2025: 5109000; FY 2026: 3356000
U-4700CC | HIGHWAY | US 321 | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 5900000 | FY 2024: 556000; FY 2025: 3813000; FY 2026: 1531000
U-4700CC | HIGHWAY | US 321 | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | UTILITIES | 100000
U-4700CC | HIGHWAY | US 321 | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 450000
U-4709 | HIGHWAY | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | T | RIGHT-OF-WAY | 9556000 | FY 2023: 4778000
U-4709 | HIGHWAY | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | T | UTILITIES | 1575000 | FY 2023: 787000
U-4709 | HIGHWAY | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | T | CONSTRUCTION | 13700000 | FY 2024: 137000; FY 2025: 5847000; FY 2026: 5560000; FY 2027: 2156000
U-4709 | HIGHWAY | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  |  |  | 1400000
U-4712 | HIGHWAY | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 14 | French Broad River MPO |  | DIVISION 14 |  |  |  | 680000
U-4712 | HIGHWAY | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 14 | French Broad River MPO |  | DIVISION 14 |  | T | RIGHT-OF-WAY | 25200000 | FY 2027: 252000; FY 2028: 7812000; FY 2029: 9677000; FY 2030: 2419000; FY 2031: 5040000
U-4712 | HIGHWAY | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 14 | French Broad River MPO |  | DIVISION 14 |  | T | UTILITIES | 3800000 | FY 2027: 1900000; FY 2028: 1900000
U-4712 | HIGHWAY | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 14 | French Broad River MPO |  | DIVISION 14 |  | T | CONSTRUCTION | 20000000 | FY 2030: 4366000; FY 2031: 8067000; FY 2032: 5441000; FY 2033: 2126000
U-4713 | HIGHWAY | NEW ROUTE | SR 3457 (CAMPUS RIDGE ROAD) TO SR 3448 (PLEASANT PLAINS ROAD) IN MATTHEWS. CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MATTHEWS. U-4713A TO BE LET WITH U-4714AC AND B. |  |  |  |  | 5399000
U-4713A | HIGHWAY | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | CONSTRUCTION | 1100000 | FY 2024: 0; FY 2025: 0; FY 2026: 953000; FY 2027: 147000
U-4713A | HIGHWAY | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | BUILD NC CON | 5160000 |  | 344000 | 344000 | 344000 | 344000 | 344000 | 344000 | 344000 | 344000 | 344000 | 344000 | 1720000
U-4713A | HIGHWAY | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | UTILITIES | 500000
U-4713A | HIGHWAY | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | BUILD NC ROW | 360000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000 | 24000
U-4713A | HIGHWAY | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | ENGINEERING | 1155000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000 | 77000
U-4713A | HIGHWAY | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | L | CONSTRUCTION | 2000000 | FY 2024: 20000; FY 2025: 1161000; FY 2026: 761000; FY 2027: 58000
U-4713A | HIGHWAY | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | RIGHT-OF-WAY | 2320000
U-4714 | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO SR 1377 (WESLEY CHAPEL-STOUTS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL. |  |  |  |  | 23619000
U-4714AA | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGANY | CONSTRUCTION | 14300000 | FY 2030: 5564000; FY 2031: 5923000; FY 2032: 2813000
U-4714AA | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | RIGHT-OF-WAY | 9149000 | FY 2028: 92000; FY 2029: 5538000; FY 2030: 1689000; FY 2031: 915000; FY 2032: 915000
U-4714AA | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | UTILITIES | 1900000 | FY 2028: 950000; FY 2029: 950000
U-4714AC | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGANY | RIGHT-OF-WAY | 498000
U-4714AC | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | T(DA) | CONSTRUCTION | 7700000 | FY 2025: 608000; FY 2026: 3999000; FY 2027: 2353000; FY 2028: 740000
U-4714AC | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | T | BUILD NC CON | 10815000 |  |  | 1442000 | 721000 | 721000 | 721000 | 721000 | 721000 | 721000 | 721000 | 721000 | 3605000
U-4714AC | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | T | UTILITIES | 2200000
U-4714AC | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | S(M) | CONSTRUCTION | 1924000 | FY 2025: 152000; FY 2026: 999000; FY 2027: 588000; FY 2028: 185000
U-4714AC | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 9026000
U-4714AC | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | 10 | Charlotte Regional TPO | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 10 |  | S(M) | RIGHT-OF-WAY | 2256000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | O | RIGHT-OF-WAY | 2000000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | T | CONSTRUCTION | 12000000 | FY 2025: 0; FY 2026: 0; FY 2027: 0; FY 2028: 8269000; FY 2029: 3731000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | T | BUILD NC CON | 10935000 |  |  |  | 729000 | 729000 | 729000 | 729000 | 729000 | 729000 | 729000 | 729000 | 5103000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | T | BUILD NC CON | 25740000 |  |  | 3432000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 8580000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | O | CONSTRUCTION | 3000000 | FY 2025: 30000; FY 2026: 1034000; FY 2027: 1041000; FY 2028: 618000; FY 2029: 277000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 5000000 | FY 2023: 1666000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | BGANY | UTILITIES | 2300000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | BGANY | RIGHT-OF-WAY | 37750000 | FY 2023: 12584000
U-4714B | HIGHWAY | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE). | DIVISION 10 |  | S(M) | RIGHT-OF-WAY | 1250000 | FY 2023: 416000
U-4715 | HIGHWAY | CITYWIDE | ASHEVILLE SIGNAL SYSTEM. | 13 | French Broad River MPO | A PORTION OF THE SIGNALS ARE NOT ELIGIBLE FOR FEDERAL FUNDING DUE THE ROAD'S FUNCTIONAL CLASSIFICATION. THE RESULTING FUNDING SPLIT IS 74% FEDERAL AND 26% STATE |  |  |  |  | 16377000
U-4716 | RAIL | VARIOUS PIEDMONT CORRIDOR | VARIOUS ROUTES AND NORFOLK SOUTHERN RAILROAD-NORTH CAROLINA RAILROAD IN DURHAM AND MORRISVILLE, SOUTH OF I-40 TO NORTH OF MCCRIMMON PARKWAY. CONSTRUCT A GRADE SEPARATION AT SR 1978 (HOPSON ROAD), EXTEND CHURCH STREET TO HOPSON ROAD, CLOSE CHURCH STREET C | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO | [5 empty] | 31776000
U-4716D | RAIL | SR 1978 (HOPSON ROAD) | SR 1978 (HOPSON ROAD), EAST OF SR 1999 (DAVIS DRIVE) TO NC 54, WIDEN TO MULTILANES | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | O | CONSTRUCTION | 3160000 | [11 empty] | 3160000
U-4716D | RAIL | SR 1978 (HOPSON ROAD) | SR 1978 (HOPSON ROAD), EAST OF SR 1999 (DAVIS DRIVE) TO NC 54, WIDEN TO MULTILANES | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | O | RIGHT-OF-WAY | 1126000 | [11 empty] | 1126000
U-4724 | BIKE/PED | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 1004000 | FY 2024: 1004000
U-4724 | BIKE/PED | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | PRE-STI (TRANSITION) |  | L | RIGHT-OF-WAY | 448000 | FY 2023: 448000
U-4724 | BIKE/PED | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | PRE-STI (TRANSITION) |  | BGDA | CONSTRUCTION | 120000 | FY 2024: 120000
U-4724 | BIKE/PED | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | PRE-STI (TRANSITION) |  | BGANY | CONSTRUCTION | 3854000 | FY 2024: 3854000
U-4724 | BIKE/PED | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | PRE-STI (TRANSITION) |  |  |  | 856000
U-4724 | BIKE/PED | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | PRE-STI (TRANSITION) |  | BGANY | RIGHT-OF-WAY | 1785000 | FY 2023: 1785000
U-4726 | BIKE/PED | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | DIVISION 5, 7, 8 |  |  |  | 12842000
U-4726 | BIKE/PED | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | DIVISION 5, 7, 8 |  | L | CONSTRUCTION | 2353000
U-4726 | BIKE/PED | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | DIVISION 5, 7, 8 |  | L | RIGHT-OF-WAY | 382000
U-4726 | BIKE/PED | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | DIVISION 5, 7, 8 |  | BGDA | CONSTRUCTION | 8984000
U-4726 | BIKE/PED | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | DIVISION 5, 7, 8 |  | BGANY | CONSTRUCTION | 429000
U-4726 | BIKE/PED | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | DIVISION 5, 7, 8 |  | BGDA | RIGHT-OF-WAY | 1527000
U-4726DF | BIKE/PED | VARIOUS | BICYCLE DETECTION AT SIGNALIZED INTERSECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | CMAQ | CONSTRUCTION | 29000 | FY 2023: 29000
U-4726DF | BIKE/PED | VARIOUS | BICYCLE DETECTION AT SIGNALIZED INTERSECTIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | CONSTRUCTION | 7000 | FY 2023: 7000
U-4726HN | BIKE/PED | SR 1321 (HILLANDALE ROAD) | I-85 TO NC 147 (DURHAM FREEWAY) IN DURHAM. PEDESTRIAN IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | BGDA | CONSTRUCTION | 2155000 | FY 2023: 2155000
U-4726HN | BIKE/PED | SR 1321 (HILLANDALE ROAD) | I-85 TO NC 147 (DURHAM FREEWAY) IN DURHAM. PEDESTRIAN IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | CONSTRUCTION | 784000 | FY 2023: 784000
U-4726HO | BIKE/PED | CARPENTER - FLETCHER ROAD | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | BGANY | CONSTRUCTION | 6305000 | FY 2024: 6305000
U-4726HO | BIKE/PED | CARPENTER - FLETCHER ROAD | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | RIGHT-OF-WAY | 5000 | FY 2023: 5000
U-4726HO | BIKE/PED | CARPENTER - FLETCHER ROAD | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | L | CONSTRUCTION | 1576000 | FY 2024: 1576000
U-4726HO | BIKE/PED | CARPENTER - FLETCHER ROAD | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | EXEMPT |  | TADA | RIGHT-OF-WAY | 22000 | FY 2023: 22000
U-4726IK | BIKE/PED | SR 1777 (HOMESTEAD ROAD) | SR 1843 (SEAWELL SCHOOL ROAD) TO SR 1733 (WEAVER DAIRY ROAD EXTENSION). | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | BGDA | CONSTRUCTION | 1040000 | FY 2023: 1040000
U-4726IK | BIKE/PED | SR 1777 (HOMESTEAD ROAD) | SR 1843 (SEAWELL SCHOOL ROAD) TO SR 1733 (WEAVER DAIRY ROAD EXTENSION). | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 260000 | FY 2023: 260000
U-4727 | HIGHWAY | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | DIVISION 5, 7, 8 |  |  |  | 15908000
U-4727 | HIGHWAY | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | DIVISION 5, 7, 8 |  | BGDA | PLANNING | 22797000 | 2800000 | 2940000 | 3087000 | 3241000 | 3403000 | 3574000 | 3752000
U-4727 | HIGHWAY | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT | DIVISION 5, 7, 8 |  | L | PLANNING | 5021000 | 617000 | 647000 | 680000 | 714000 | 750000 | 787000 | 826000
U-4734 | HIGHWAY | NEW ROUTE | MACY GROVE ROAD EXTENSION, SR 1005 (EAST MOUNTAIN STREET) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. FOUR-LANE DIVIDED FACILITY ON NEW LOCATION. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 9 |  |  |  | 13700000
U-4734 | HIGHWAY | NEW ROUTE | MACY GROVE ROAD EXTENSION, SR 1005 (EAST MOUNTAIN STREET) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. FOUR-LANE DIVIDED FACILITY ON NEW LOCATION. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 9 |  | T | BUILD NC CON | 11172000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000
U-4735 | HIGHWAY | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | 4, 5, 6 | Capital Area MPO |  | DIVISION 4, 5, 6 |  | BGDA | CONSTRUCTION | 77938000 | FY 2028: 3688000; FY 2029: 14850000; FY 2030: 14850000; FY 2031: 14850000; FY 2032: 14850000; FY 2033: 14850000
U-4739 | HIGHWAY | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | UTILITIES | 7400000 | FY 2025: 3700000; FY 2026: 3700000
U-4739 | HIGHWAY | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | CONSTRUCTION | 38900000 | FY 2028: 8550000; FY 2029: 12385000; FY 2030: 10251000; FY 2031: 7714000
U-4739 | HIGHWAY | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 18500000 | FY 2025: 2242000; FY 2026: 5382000; FY 2027: 5382000; FY 2028: 1794000; FY 2029: 3700000
U-4739 | HIGHWAY | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 13 | French Broad River MPO |  | DIVISION 13 |  |  |  | 622000
U-4741 | BIKE/PED | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TADA | CONSTRUCTION | 276000
U-4741 | BIKE/PED | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 630000
U-4741 | BIKE/PED | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGANY | CONSTRUCTION | 487000
U-4741 | BIKE/PED | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 1599000
U-4741 | BIKE/PED | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 158000
U-4741 | BIKE/PED | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 522000
U-4741 | BIKE/PED | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 69000
U-4741 | BIKE/PED | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 13675000
U-4741OK | BIKE/PED | PIEDMONT REGIONAL GREENWAY | WINSTON-SALEM - PIEDMONT REGIONAL GREENWAY | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | RIGHT-OF-WAY | 180000 | FY 2023: 180000
U-4741OK | BIKE/PED | PIEDMONT REGIONAL GREENWAY | WINSTON-SALEM - PIEDMONT REGIONAL GREENWAY | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TADA | RIGHT-OF-WAY | 720000 | FY 2023: 720000
U-4742 | HIGHWAY | VARIOUS | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 7170000
U-4742 | HIGHWAY | VARIOUS | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 700000
U-4742 | HIGHWAY | VARIOUS | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | L | CONSTRUCTION | 175000
U-4744 | HIGHWAY | VARIOUS | STBG-DA IN CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO). | 10, 12 | Charlotte Regional TPO |  | DIVISION 10, 12 |  | BGDA | CONSTRUCTION | 184762000 | 0 | 0 | 0 | 9776000 | 11658000 | 18781000 | 17390000 | 20932000 | 21245000 | 21245000 | 21245000 | 42490000
U-4744 | HIGHWAY | VARIOUS | STBG-DA IN CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO). | 10, 12 | Charlotte Regional TPO |  | DIVISION 10, 12 |  | L | CONSTRUCTION | 46190000 | 0 | 0 | 0 | 2444000 | 2915000 | 4695000 | 4348000 | 5233000 | 5311000 | 5311000 | 5311000 | 10622000
U-4751 | HIGHWAY | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | STATEWIDE MOBILITY |  |  |  | 255562000
U-4751 | HIGHWAY | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 28490000
U-4751 | HIGHWAY | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | STATEWIDE MOBILITY |  | T | ENGINEERING | 14850000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 1980000
U-4751 | HIGHWAY | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | STATEWIDE MOBILITY |  | T | BUILD NC CON | 36135000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 2409000 | 4818000
U-4753 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO US 70 IN GOLDSBORO. WIDEN TO FOUR LANES. | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  |  |  | 920000
U-4753 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO US 70 IN GOLDSBORO. WIDEN TO FOUR LANES. | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  | T | CONSTRUCTION | 8260000 | FY 2025: 732000; FY 2026: 4964000; FY 2027: 2564000
U-4753 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO US 70 IN GOLDSBORO. WIDEN TO FOUR LANES. | 4 | Goldsboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  | T | RIGHT-OF-WAY | 4180000
U-4758 | HIGHWAY | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 7518000
U-4758 | HIGHWAY | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | S(M) | RIGHT-OF-WAY | 1694000 | FY 2023: 847000
U-4758 | HIGHWAY | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | HP | RIGHT-OF-WAY | 6776000 | FY 2023: 3388000
U-4758 | HIGHWAY | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BG5200 | RIGHT-OF-WAY | 4751000 | FY 2023: 2376000
U-4758 | HIGHWAY | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BG5200 | UTILITIES | 7200000
U-4758 | HIGHWAY | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BG5200 | CONSTRUCTION | 45699000 | FY 2024: 12760000; FY 2025: 16754000; FY 2026: 9712000; FY 2027: 5629000; FY 2028: 844000
U-4762 | HIGHWAY | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  |  |  | 2892000
U-4762 | HIGHWAY | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | ENGINEERING | 1995000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 266000
U-4762 | HIGHWAY | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | BUILD NC CON | 2895000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000 | 193000
U-4762 | HIGHWAY | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | BUILD NC CON | 3360000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 224000 | 448000
U-4850 | HIGHWAY | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | DIVISION 4, 5, 6 |  |  |  | 7089000
U-4850 | HIGHWAY | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | DIVISION 4, 5, 6 |  | BGDA | PLANNING | 15200000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000
U-4850 | HIGHWAY | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. | 4, 5, 6 | Capital Area MPO | FORMERLY U-9999B - IN PROGRESS | DIVISION 4, 5, 6 |  | L | PLANNING | 3800000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000
U-4900 | HIGHWAY | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | EXEMPT |  | S(M) | RIGHT-OF-WAY | 2120000 | FY 2023: 530000; FY 2024: 1060000; FY 2025: 530000
U-4900 | HIGHWAY | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | EXEMPT |  | S(M) | UTILITIES | 3000000 | FY 2023: 1500000; FY 2024: 1500000
U-4900 | HIGHWAY | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | EXEMPT |  | BGDA | CONSTRUCTION | 18641000 | FY 2025: 2137000; FY 2026: 7912000; FY 2027: 6218000; FY 2028: 2374000
U-4900 | HIGHWAY | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | EXEMPT |  | BGDA | RIGHT-OF-WAY | 8480000 | FY 2023: 2120000; FY 2024: 4240000; FY 2025: 2120000
U-4900 | HIGHWAY | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | EXEMPT |  |  |  | 3372000
U-4900 | HIGHWAY | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | EXEMPT |  | BGDA | UTILITIES | 12000000 | FY 2023: 6000000; FY 2024: 6000000
U-4900 | HIGHWAY | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT. | EXEMPT |  | S(M) | CONSTRUCTION | 4659000 | FY 2025: 534000; FY 2026: 1977000; FY 2027: 1554000; FY 2028: 594000
U-4902 | HIGHWAY | US 17 BUSINESS (MARKET STREET) | COLONIAL DRIVE TO SR 1402 (PORTERS NECK ROAD). ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | [5 empty] | 54718000
U-4902B | HIGHWAY | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 9700000 | [11 empty] | 9700000
U-4902B | HIGHWAY | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 10000000 | [11 empty] | 10000000
U-4902B | HIGHWAY | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 2900000 | [11 empty] | 2900000
U-4902C | HIGHWAY | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 55101000 | FY 2030: 551000; FY 2031: 15991000; FY 2032: 16796000; FY 2033: 12889000 | 8874000
U-4902C | HIGHWAY | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 46088000 | FY 2028: 4254000; FY 2029: 17017000; FY 2030: 15599000; FY 2031: 4609000; FY 2032: 4609000
U-4902C | HIGHWAY | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | 3 | Wilmington Urban Area MPO | INCLUDES U-5880. | STATEWIDE MOBILITY |  | T | UTILITIES | 10811000 | FY 2028: 5405000; FY 2029: 5406000
U-4902D | HIGHWAY | US 17 BUSINESS (MARKET STREET) | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | STATEWIDE MOBILITY |  | T | ENGINEERING | 4290000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 286000 | 572000
U-4902D | HIGHWAY | US 17 BUSINESS (MARKET STREET) | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | STATEWIDE MOBILITY |  | T | BUILD NC CON | 12795000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 853000 | 1706000
U-4902D | HIGHWAY | US 17 BUSINESS (MARKET STREET) | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 11814000
U-4906 | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | WEST OF SR 1313 (MILLS FIELDS ROAD) TO EAST OF SR 1324 (RAMSEY ROAD) IN JACKSONVILLE. WIDENING. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  |  |  | 5278000
U-4906 | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | WEST OF SR 1313 (MILLS FIELDS ROAD) TO EAST OF SR 1324 (RAMSEY ROAD) IN JACKSONVILLE. WIDENING. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | BGANY | CONSTRUCTION | 15953000
U-4910 | HIGHWAY | SR 1445 (DERITA ROAD) | SR 2894 (CONCORD MILLS BOULEVARD) TO SR 1394 (POPLAR TENT ROAD) IN CONCORD. WIDEN TO 4-LANES DIVIDED. | 10 | Cabarrus-Rowan MPO | SEGMENTS A AND B LET TOGETHER |  |  |  |  | 23417000
U-4913 | HIGHWAY | SR 3174 / 1501 (IDLEWILD ROAD) | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY | 10 | Charlotte Regional TPO | [5 empty] | 1545000
U-4913A | HIGHWAY | SR 3174) (IDLEWILD ROAD) | SR 3175 (STALLINGS ROAD) TO I-485. WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | RIGHT-OF-WAY | 750000 | FY 2026: 750000
U-4913A | HIGHWAY | SR 3174) (IDLEWILD ROAD) | SR 3175 (STALLINGS ROAD) TO I-485. WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | UTILITIES | 250000 | FY 2026: 250000
U-4913A | HIGHWAY | SR 3174) (IDLEWILD ROAD) | SR 3175 (STALLINGS ROAD) TO I-485. WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | CONSTRUCTION | 4400000 | FY 2028: 2200000; FY 2029: 2200000
U-4913B | HIGHWAY | SR 3174 / SR 1501 (IDLEWILD ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 14886000 | [11 empty] | 14886000
U-4913B | HIGHWAY | SR 3174 / SR 1501 (IDLEWILD ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | UTILITIES | 636000 | [11 empty] | 636000
U-4913B | HIGHWAY | SR 3174 / SR 1501 (IDLEWILD ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | CONSTRUCTION | 21500000 | [11 empty] | 21500000
U-4916 | HIGHWAY | SR 1165 (BECKFORD DRIVE) | HARRISON STREET TO NORTH PARK DRIVE IN HENDERSON. WIDEN TO THREE LANES WITH CURB AND GUTTER, STORM DRAINAGE, AND SIDEWALKS. | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION BY CITY OF HENDERSON | PRE-STI (TRANSITION) |  |  |  | 961000
U-4950 | HIGHWAY | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. | 10, 12 | Charlotte Regional TPO | FORMERLY U-9999C - IN PROGRESS | DIVISION 10, 12 |  | L | PLANNING | 3007000 | 375000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000
U-4950 | HIGHWAY | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. | 10, 12 | Charlotte Regional TPO | FORMERLY U-9999C - IN PROGRESS | DIVISION 10, 12 |  |  |  | 1500000
U-4950 | HIGHWAY | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. | 10, 12 | Charlotte Regional TPO | FORMERLY U-9999C - IN PROGRESS | DIVISION 10, 12 |  | BGDA | PLANNING | 12558000 | 1500000 | 1634000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000
U-4951 | HIGHWAY | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 9 | Winston-Salem Urban Area MPO | FORMERLY U-9999D - IN PROGRESS | DIVISION 9 |  |  |  | 1560000
U-4951 | HIGHWAY | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 9 | Winston-Salem Urban Area MPO | FORMERLY U-9999D - IN PROGRESS | DIVISION 9 |  | BGDA | PLANNING | 3544000 | FY 2023: 0; FY 2024: 684000
U-4951 | HIGHWAY | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 9 | Winston-Salem Urban Area MPO | FORMERLY U-9999D - IN PROGRESS | DIVISION 9 |  | L | PLANNING | 886000 | FY 2023: 0; FY 2024: 171000
U-5007 | HIGHWAY | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 10700000
U-5007 | HIGHWAY | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 39201000
U-5007 | HIGHWAY | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 600000
U-5007 | HIGHWAY | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 68000000
U-5008 | HIGHWAY | SR 2975 (SUGAR CREEK ROAD) | CONSTRUCT GRADE SEPARATION OVER NORTH CAROLINA RAILROAD/NORFOLK SOUTHERN RAILWAY CROSSING 715 352H AND THE CLOSURE OF CRAIGHEAD ROAD CROSSING 715 355D. | 10 | Charlotte Regional TPO | DP ARE FEDERAL RAILROAD ADMINISTRATION (FRA) PRIIA GRANT, NCRR, NSR AND CITY OF CHARLOTTE FUNDS |  |  |  |  | 38497000
U-5008A | HIGHWAY | NORTH DAVIDSON STREET | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | DP | RIGHT-OF-WAY | 1000000
U-5008A | HIGHWAY | NORTH DAVIDSON STREET | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | DP | UTILITIES | 25000
U-5008A | HIGHWAY | NORTH DAVIDSON STREET | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | PRE-STI (TRANSITION) |  | DP | CONSTRUCTION | 1200000 | FY 2023: 270000; FY 2024: 930000
U-5015 | HIGHWAY | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 14900000 | [11 empty] | 14900000
U-5015 | HIGHWAY | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | UTILITIES | 2200000 | [11 empty] | 2200000
U-5015 | HIGHWAY | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  |  |  | 10000
U-5015 | HIGHWAY | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 8300000 | [11 empty] | 8300000
U-5019 | HIGHWAY | ASHEVILLE EAST OF THE RIVERWAY MULTI-MODAL NETWORK | CONSTRUCT INTERCONNECTED NETWORK OF PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. PROJECT INCLUDES: CLINGMAN FOREST AND TOWN BRANCH GREENWAYS, FRENCH BROAD RIVER WEST GREENWAY, WILMA DIKEMAN RIVERWAY AND FIVE POINTS ROUNDABOUT, LIVINGSTON S | 13 | French Broad River MPO | SEGMENT A - $3.42M IN BGANY USED AS PART OF FUND SWAP, $8K USED FOR PRELIMINARY ENGINEERING |  |  |  |  | 10130000
U-5019A | HIGHWAY | RIVERWAY MULTI-MODAL NETWORK | CONSTRUCT TOWN BRANCH GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | CONSTRUCTION | 3412000 | FY 2023: 1706000; FY 2024: 1706000
U-5019A | HIGHWAY | RIVERWAY MULTI-MODAL NETWORK | CONSTRUCT TOWN BRANCH GREENWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 855000 | FY 2023: 855000
U-5019D | HIGHWAY | RIVERWAY MULTI-MODAL NETWORK | LIVINGSTON STREET COMPLETE STREETS IMPROVEMENTS. | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 1500000 | FY 2023: 1500000
U-5019E | HIGHWAY | RIVERWAY MULTI-MODAL NETWORK | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER | 13 | French Broad River MPO |  | DIVISION 13 |  | L | CONSTRUCTION | 1050000 | FY 2024: 1050000
U-5019E | HIGHWAY | RIVERWAY MULTI-MODAL NETWORK | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | CONSTRUCTION | 4200000 | FY 2024: 4200000
U-5021 | HIGHWAY | VARIOUS | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | BGDA | CONSTRUCTION | 71646000 | 15366000 | 4162000 | 5402000 | 5402000 | 5902000 | 5902000 | 5902000 | 5902000 | 5902000 | 5902000 | 5902000
U-5022 | HIGHWAY | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGDA | CONSTRUCTION | 93095000 | 25181000 | 4187000 | 4649000 | 7264000 | 7402000 | 7402000 | 7402000 | 7402000 | 7402000 | 7402000 | 7402000
U-5023 | HIGHWAY | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | INCLUDES $137K TO BE ALLOCATED TO TG-5235; $1548K ALLOCATED TO U-4726. | DIVISION 5, 7, 8 |  | BGDA | CONSTRUCTION | 48984000 | 5139000 | 2386000 | 3493000 | 2635000 | 3177000 | 3006000 | 2828000 | 6580000 | 6580000 | 6580000 | 6580000
U-5026 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  |  |  | 2826000
U-5026 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | L | CONSTRUCTION | 208000
U-5026 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | RIGHT-OF-WAY | 32058000
U-5026 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | UTILITIES | 336000
U-5026 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | BUILD NC CON | 26505000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 1767000 | 3534000
U-5026 | HIGHWAY | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | DIVISION 4 |  | T | CONSTRUCTION | 49423000 | FY 2023: 12356000
U-5100 | HIGHWAY | VARIOUS | STBG-DA IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | BGDA | CONSTRUCTION | 32155000 | 0 | 0 | 0 | 0 | 0 | 0 | 3283000 | 4812000 | 4812000 | 4812000 | 4812000 | 9624000
U-5100 | HIGHWAY | VARIOUS | STBG-DA IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | L | CONSTRUCTION | 8039000 | 0 | 0 | 0 | 0 | 0 | 0 | 821000 | 1203000 | 1203000 | 1203000 | 1203000 | 2406000
U-5101 | HIGHWAY | SR 1437 (SHAW ROAD) SR 1614 (SHAW MILL ROAD) SR 16 | NC 24/87 (BRAGG BLVD) TO US 401 (RAMSEY STREET). WIDEN ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  |  |  | 1250000
U-5101A | HIGHWAY | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT OF WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | UTILITIES | 2732000 | FY 2026: 2732000
U-5101A | HIGHWAY | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT OF WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | CONSTRUCTION | 36601000 | FY 2028: 5937000; FY 2029: 13309000; FY 2030: 10919000; FY 2031: 6436000
U-5101A | HIGHWAY | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT OF WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | RIGHT-OF-WAY | 2785000 | FY 2026: 0; FY 2027: 0; FY 2028: 0; FY 2029: 1010000; FY 2030: 1775000
U-5101A | HIGHWAY | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT OF WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | BUILD NC ROW | 19305000 |  |  |  | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 9009000
U-5101A | HIGHWAY | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT OF WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE). | DIVISION 6 |  | T | BUILD NC UTL | 6435000 |  |  |  | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 3003000
U-5101B | HIGHWAY | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | UTILITIES | 21445000 | [11 empty] | 21445000
U-5101B | HIGHWAY | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 36300000 | [11 empty] | 36300000
U-5101B | HIGHWAY | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 38500000 | [11 empty] | 38500000
U-5105 | HIGHWAY | NC 225 SR 1164 (ERKWOOD DRIVE) | NC 225/SR 1164 (ERKWOOD DRIVE)/SR 1779(SHEPHERD STREET) IN HENDERSONVILLE. IMPROVE INTERSECTION. | 14 | French Broad River MPO | DIVISION PROJECT - UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 7210000
U-5108 | HIGHWAY | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | PRE-STI (TRANSITION) |  | BA | ENGINEERING | 960000
U-5108 | HIGHWAY | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | PRE-STI (TRANSITION) |  | S(M) | CONSTRUCTION | 473000 | FY 2024: 41000; FY 2025: 268000; FY 2026: 140000; FY 2027: 24000
U-5108 | HIGHWAY | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 2024000 | FY 2024: 176000; FY 2025: 1144000; FY 2026: 598000; FY 2027: 106000
U-5108 | HIGHWAY | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | PRE-STI (TRANSITION) |  | L | RIGHT-OF-WAY | 1750000
U-5108 | HIGHWAY | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | PRE-STI (TRANSITION) |  | BGANY | RIGHT-OF-WAY | 1750000
U-5108 | HIGHWAY | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | PRE-STI (TRANSITION) |  |  |  | 2925000
U-5108 | HIGHWAY | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP. | PRE-STI (TRANSITION) |  | BGANY | CONSTRUCTION | 13403000 | FY 2024: 1163000; FY 2025: 7578000; FY 2026: 3959000; FY 2027: 703000
U-5112 | HIGHWAY | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | PRE-STI (TRANSITION) |  | BGDA | CONSTRUCTION | 1657000 | FY 2024: 1657000
U-5112 | HIGHWAY | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 414000 | FY 2024: 414000
U-5112 | HIGHWAY | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 400000 | FY 2024: 400000
U-5112 | HIGHWAY | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | PRE-STI (TRANSITION) |  | L | RIGHT-OF-WAY | 135000
U-5112 | HIGHWAY | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | PRE-STI (TRANSITION) |  | CMAQ | CONSTRUCTION | 1600000 | FY 2024: 1600000
U-5112 | HIGHWAY | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | PRE-STI (TRANSITION) |  | BGDA | RIGHT-OF-WAY | 541000
U-5112 | HIGHWAY | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | PRE-STI (TRANSITION) |  |  |  | 1216000
U-5112 | HIGHWAY | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | PRE-STI (TRANSITION) |  | HSIP | CONSTRUCTION | 500000 | FY 2024: 500000
U-5114 | HIGHWAY | HUNTERSVILLE | INTERSECTION OF US 21 AND GILEAD ROAD IN HUNTERSVILLE. CONSTRUCT INTERSECTION IMPROVEMENTS, INCLUDING BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 19322000
U-5118 | HIGHWAY | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. | 4, 5, 6 | Capital Area MPO | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. | DIVISION 4, 5, 6 |  |  |  | 21170000
U-5118 | HIGHWAY | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. | 4, 5, 6 | Capital Area MPO | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. | DIVISION 4, 5, 6 |  | BGDA | CONSTRUCTION | 3000000
U-5118 | HIGHWAY | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. | 4, 5, 6 | Capital Area MPO | IN PROGRESS. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. | DIVISION 4, 5, 6 |  | L | CONSTRUCTION | 750000
U-5119A | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | ALTERNATIVE ANALYSIS - ENVIRONMENTAL ASSESSMENT, DESIGN, AND ENGINEERING | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | FED | ENGINEERING | 3376000
U-5119A | PUBLIC TRANSIT | CHAPEL HILL TRANSIT | ALTERNATIVE ANALYSIS - ENVIRONMENTAL ASSESSMENT, DESIGN, AND ENGINEERING | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | PUBLIC TRANSIT |  | L | ENGINEERING | 844000
U-5169 | HIGHWAY | I-74 / US 311 | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. RECONSTRUCT INTERCHANGE AND APPROACHES. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | REGION D |  |  |  | 32225000
U-5190 | HIGHWAY | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | PRE-STI (TRANSITION) |  | L | RIGHT-OF-WAY | 48000
U-5190 | HIGHWAY | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | PRE-STI (TRANSITION) |  | L | CONSTRUCTION | 664000
U-5190 | HIGHWAY | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | PRE-STI (TRANSITION) |  | BGDA | CONSTRUCTION | 459000
U-5190 | HIGHWAY | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | PRE-STI (TRANSITION) |  | BGANY | CONSTRUCTION | 2199000
U-5190 | HIGHWAY | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | PRE-STI (TRANSITION) |  |  |  | 202000
U-5190 | HIGHWAY | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 13 | French Broad River MPO | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE | PRE-STI (TRANSITION) |  | BGDA | RIGHT-OF-WAY | 193000
U-5207 | HIGHWAY | VARIOUS | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | DIVISION 6, 8 |  |  |  | 2650000
U-5207 | HIGHWAY | VARIOUS | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | DIVISION 6, 8 |  | BGDA | PLANNING | 2360000 | 160000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 900000
U-5207 | HIGHWAY | VARIOUS | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | DIVISION 6, 8 |  | L | PLANNING | 590000 | 40000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 225000
U-5301 | HIGHWAY | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | T | UTILITIES | 4012000 | FY 2027: 2006000; FY 2028: 2006000
U-5301 | HIGHWAY | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 134598000 | FY 2030: 26617000; FY 2031: 35388000; FY 2032: 30284000; FY 2033: 23309000 | 19000000
U-5301 | HIGHWAY | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 100558000 | FY 2027: 19502000; FY 2028: 29253000; FY 2029: 29253000; FY 2030: 2438000; FY 2031: 20112000
U-5301 | HIGHWAY | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY |  |  |  | 1000000
U-5302 | HIGHWAY | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | REGION C |  | T | ENGINEERING | 1801000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 121000
U-5302 | HIGHWAY | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | REGION C |  | T | BUILD NC ROW | 4128000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 278000
U-5302 | HIGHWAY | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | REGION C |  | T | RIGHT-OF-WAY | 5803000
U-5302 | HIGHWAY | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | REGION C |  | T | BUILD NC CON | 3862000 |  | 515000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 1034000
U-5302 | HIGHWAY | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | REGION C |  | T | CONSTRUCTION | 19100000 | FY 2024: 191000; FY 2025: 9054000; FY 2026: 6570000; FY 2027: 3285000
U-5302 | HIGHWAY | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | REGION C |  |  |  | 3345000
U-5304 | HIGHWAY | US 15 / US 501 (FORDHAM BOULEVARD) | NC 86 (SOUTH COLUMBIA STREET) TO I-40 IN CHAPEL HILL. UPGRADE CORRIDOR. | 5, 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH EB-5998 AND U-5774 |  |  |  |  | 10000
U-5304A | HIGHWAY | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 22001000 | [11 empty] | 22001000
U-5304A | HIGHWAY | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 1040000 | [11 empty] | 1040000
U-5304A | HIGHWAY | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 10000000 | [11 empty] | 10000000
U-5304B | HIGHWAY | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 6000000 | [11 empty] | 6000000
U-5304B | HIGHWAY | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 285000 | [11 empty] | 285000
U-5304B | HIGHWAY | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 22001000 | [11 empty] | 22001000
U-5304D | HIGHWAY | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5000000 | [11 empty] | 5000000
U-5304D | HIGHWAY | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 344000 | [11 empty] | 344000
U-5304D | HIGHWAY | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 30001000 | [11 empty] | 30001000
U-5304E | HIGHWAY | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 12000000 | [11 empty] | 12000000
U-5304E | HIGHWAY | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 446000 | [11 empty] | 446000
U-5304E | HIGHWAY | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 25000000 | [11 empty] | 25000000
U-5304F | HIGHWAY | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION C, D |  | T | RIGHT-OF-WAY | 6000000 | FY 2028: 1500000; FY 2029: 3000000; FY 2030: 1500000
U-5304F | HIGHWAY | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION C, D |  | T | UTILITIES | 726000 | FY 2028: 363000; FY 2029: 363000
U-5304F | HIGHWAY | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION C, D |  | T | CONSTRUCTION | 26999000 | FY 2030: 2813000; FY 2031: 4848000; FY 2032: 12429000; FY 2033: 6909000
U-5306 | HIGHWAY | US 220 (BATTLEGROUND AVENUE) | INTERSECTION AND SIDEWALK IMPROVEMENTS AT CONE BOULEVARD-BENJAMIN PARKWAY, WESTRIDGE ROAD, NEW GARDEN ROAD, AND BRASSFIELD ROAD INTERSECTIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO | [5 empty] | 9926000
U-5307 | HIGHWAY | US 1 | I-540 IN RALEIGH TO SR 1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. UPGRADE ROADWAY TO CONTROLLED ACCESS FACILITY. | 5 | Capital Area MPO | [5 empty] | 1000000
U-5307A | HIGHWAY | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT | STATEWIDE MOBILITY |  | T | UTILITIES | 12200000 | FY 2026: 6100000; FY 2027: 6100000
U-5307A | HIGHWAY | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 184700000 | FY 2026: 28395000; FY 2027: 47965000; FY 2028: 43583000; FY 2029: 36283000; FY 2030: 28474000
U-5307A | HIGHWAY | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | 5 | Capital Area MPO | DESIGN-BUILD PROJECT | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 94301000 | FY 2026: 943000; FY 2027: 36777000; FY 2028: 37721000; FY 2029: 9430000; FY 2030: 9430000
U-5307B | HIGHWAY | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 5 | Capital Area MPO | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE) | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 92400000
U-5307B | HIGHWAY | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 5 | Capital Area MPO | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE) | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | BUILD NC ROW | 24453000
U-5307B | HIGHWAY | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 5 | Capital Area MPO | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE) | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 55950000
U-5307B | HIGHWAY | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 5 | Capital Area MPO | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2027-2040 (FY 2026 / YR 8 SALE) | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 6700000
U-5307C | HIGHWAY | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 108799000
U-5307C | HIGHWAY | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 28199000
U-5307C | HIGHWAY | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 5100000
U-5307D | HIGHWAY | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 48900000
U-5307D | HIGHWAY | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 83999000
U-5307D | HIGHWAY | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 8300000
U-5308 | HIGHWAY | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 8 |  | T | RIGHT-OF-WAY | 2215000
U-5308 | HIGHWAY | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 8 |  | T | UTILITIES | 3500000
U-5308 | HIGHWAY | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 8 |  | T | ENGINEERING | 2703000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 183000
U-5308 | HIGHWAY | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 8 |  | T | BUILD NC ROW | 244000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 20000
U-5308 | HIGHWAY | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 8 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 8 |  | T | CONSTRUCTION | 26800000 | FY 2027: 268000; FY 2028: 9718000; FY 2029: 9670000; FY 2030: 6442000; FY 2031: 702000
U-5312 | HIGHWAY | US 421 | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO REDUCED CONFLICT INTERSECTIONS AND ADD SERVICE ROADS. | 11 | High Country RPO | UNDER CONSTRUCTION. | REGION F |  |  |  | 6367000
U-5312 | HIGHWAY | US 421 | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO REDUCED CONFLICT INTERSECTIONS AND ADD SERVICE ROADS. | 11 | High Country RPO | UNDER CONSTRUCTION. | REGION F |  | NHP | CONSTRUCTION | 31700000 | FY 2023: 317000; FY 2024: 10068000; FY 2025: 10374000; FY 2026: 7465000; FY 2027: 3476000
U-5315 | HIGHWAY | MORRISVILLE PARKWAY EXTENSION | SR 1600 / SR 1625 (GREEN LEVEL CHURCH ROAD) TO EAST OF NC 55 IN CARY. MULTI-LANE FACILITY ON NEW LOCATION, INCLUDING INTERCHANGE AT NC 540 (TRIANGLE EXPRESSWAY / WESTERN WAKE FREEWAY). | 5 | Capital Area MPO | PART C CONSTRUCTION BY TOWN OF CARY |  |  |  |  | 19749000
U-5315C | HIGHWAY | MORRISVILLE PARKWAY EXTENSION | SR 1600 / SR 1625 (GREEN LEVEL CHURCH ROAD) TO EAST OF NC 55 IN CARY. WIDEN TO 4 LANES WITH LANDSCAPED MEDIAN. | 5 | Capital Area MPO |  | NOT FUNDED |  | L | CONSTRUCTION | 7900000 | [11 empty] | 7900000
U-5317 | HIGHWAY | NORTH JUDD PARKWAY | NC 55 (NORTH BROAD STREET) TO NC 42 (WEST ACADEMY STREET) IN FUQUAY-VARINA, WAKE COUNTY. MULTI-LANE FACILITY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF FUQUAY-VARINA | DIVISION 5 |  |  |  | 25112000
U-5319 | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | SR 1470 (WESTERN BOULEVARD) IN JACKSONVILLE. IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 6403000
U-5323 | HIGHWAY | US 64 BUSINESS (WENDELL BOULEVARD) | SR 1003 (ROLESVILLE ROAD-EAGLE ROCK ROAD) IN WENDELL. CONNECTIVITY AND ACCESS IMPROVEMENTS AND SAFETY ENHANCEMENTS. | 5 | Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY TOWN OF WENDELL - IN PROGRESS | REGION C |  |  |  | 180000
U-5326 | HIGHWAY | SR 1008 (MARKET STREET) | SR 1546 (COLLEGE ROAD) IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION BY CITY OF GREENSBORO | DIVISION 7 |  |  |  | 7980000
U-5501 | HIGHWAY | SR 1650 (REEDY CREEK ROAD) | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | DIVISION 5 |  | L | CONSTRUCTION | 3166000
U-5501 | HIGHWAY | SR 1650 (REEDY CREEK ROAD) | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | DIVISION 5 |  |  |  | 1869000
U-5501 | HIGHWAY | SR 1650 (REEDY CREEK ROAD) | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF CARY | DIVISION 5 |  | BGDA | CONSTRUCTION | 4526000
U-5508 | HIGHWAY | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 3 | Jacksonville Urban Area MPO | COMBINE WITH U-5736 AND U-4007E. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1650000 | FY 2030: 16000; FY 2031: 1634000
U-5508 | HIGHWAY | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 3 | Jacksonville Urban Area MPO | COMBINE WITH U-5736 AND U-4007E. | STATEWIDE MOBILITY |  | T | UTILITIES | 150000 | FY 2028: 150000
U-5508 | HIGHWAY | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 3 | Jacksonville Urban Area MPO | COMBINE WITH U-5736 AND U-4007E. | STATEWIDE MOBILITY |  |  |  | 1262000
U-5508 | HIGHWAY | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 3 | Jacksonville Urban Area MPO | COMBINE WITH U-5736 AND U-4007E. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 799000 | FY 2028: 799000
U-5515 | HIGHWAY | SR 1930 (STADIUM DRIVE) SR 1933 (WEST NORTH AVENUE | SR 1930 (STADIUM DRIVE), US 1 TO SR 1954 (NORTH WINGATE STREET) IN WAKE FOREST. COMPLETE STREETS IMPROVEMENTS TO INCLUDE: WIDEN TO THREE-LANE CURB AND GUTTER SECTION, CONSTRUCT SIDEWALK, MULTI-USE PATH, BICYCLE LANES, AND PEDESTRIAN / TRANSIT AMENITIES. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF WAKE FOREST | DIVISION 5 |  |  |  | 8251000
U-5516 | HIGHWAY | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 935000
U-5516 | HIGHWAY | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 2000000
U-5516 | HIGHWAY | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 9292000
U-5516 | HIGHWAY | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2076000
U-5516 | HIGHWAY | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 12402000
U-5518 | HIGHWAY | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 168498000 | FY 2026: 34338000; FY 2027: 42852000; FY 2028: 37482000; FY 2029: 30309000; FY 2030: 23517000
U-5518 | HIGHWAY | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | STATEWIDE MOBILITY |  |  |  | 12447000
U-5518 | HIGHWAY | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 153208000 | FY 2026: 61283000; FY 2027: 61283000; FY 2028: 15321000; FY 2029: 15321000
U-5518 | HIGHWAY | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT | STATEWIDE MOBILITY |  | NHP | UTILITIES | 15714000 | FY 2026: 7857000; FY 2027: 7857000
U-5521 | HIGHWAY | WEST STREET | CABARRUS STREET TO MARTIN STREET IN RALEIGH. EXTEND WEST STREET ON NEW LOCATION, WITH GRADE SEPARATION AT NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN "H" LINE. | 5 | Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY CITY OF RALEIGH - IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 716000 | FY 2024: 716000
U-5521 | HIGHWAY | WEST STREET | CABARRUS STREET TO MARTIN STREET IN RALEIGH. EXTEND WEST STREET ON NEW LOCATION, WITH GRADE SEPARATION AT NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN "H" LINE. | 5 | Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY CITY OF RALEIGH - IN PROGRESS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 1671000 | FY 2024: 1671000
U-5525 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  |  |  | 313000
U-5525 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | PLANNING | 15468000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 679000 | 6111000
U-5525 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | PLANNING | 3872000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 1530000
U-5527 | BIKE/PED | VARIOUS | WILMINGTON URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS. | DIVISION 3 |  |  |  | 273000
U-5527 | BIKE/PED | VARIOUS | WILMINGTON URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS. | DIVISION 3 |  | TADA | CONSTRUCTION | 11914000 | 2455000 | 9000 | 525000 | 525000 | 525000 | 525000 | 525000 | 525000 | 525000 | 525000 | 525000 | 4725000
U-5528 | BIKE/PED | VARIOUS | FAYETTEVILLE URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | DIVISION 6, 8 |  |  |  | 910000
U-5528 | BIKE/PED | VARIOUS | FAYETTEVILLE URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. | 6, 8 | Fayetteville Area MPO | IN PROGRESS. | DIVISION 6, 8 |  | TADA | CONSTRUCTION | 19017000 | 3123000 | 25000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 6660000
U-5529 | HIGHWAY | SR 1115 (AVENT FERRY ROAD) | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | DIVISION 5 |  |  |  | 280000
U-5529 | HIGHWAY | SR 1115 (AVENT FERRY ROAD) | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | DIVISION 5 |  | BGDA | CONSTRUCTION | 1464000
U-5529 | HIGHWAY | SR 1115 (AVENT FERRY ROAD) | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS | DIVISION 5 |  | L | CONSTRUCTION | 366000
U-5530 | BIKE/PED | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. | 4, 5, 6 | Capital Area MPO |  | DIVISION 4, 5, 6 |  | BGDA | CONSTRUCTION | 2000000
U-5530 | BIKE/PED | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. | 4, 5, 6 | Capital Area MPO |  | DIVISION 4, 5, 6 |  | TADA | CONSTRUCTION | 800000
U-5530 | BIKE/PED | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. | 4, 5, 6 | Capital Area MPO |  | DIVISION 4, 5, 6 |  | L | CONSTRUCTION | 200000
U-5530 | BIKE/PED | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. | 4, 5, 6 | Capital Area MPO |  | DIVISION 4, 5, 6 |  |  |  | 12955000
U-5530 | BIKE/PED | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. | 4, 5, 6 | Capital Area MPO |  | DIVISION 4, 5, 6 |  | L | CONSTRUCTION | 500000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 1000000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TAANY | CONSTRUCTION | 512000 | FY 2023: 512000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TAANY | CONSTRUCTION | 462000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TAANY | RIGHT-OF-WAY | 50000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 1253000 | FY 2023: 1253000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | RIGHT-OF-WAY | 100000 | FY 2023: 100000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 700000 | FY 2024: 700000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TADA | CONSTRUCTION | 200000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | ENGINEERING | 20000 | FY 2023: 20000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 50000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 115000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 100000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGDA | CONSTRUCTION | 4000000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 12000 | FY 2023: 12000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 2843000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGANY | RIGHT-OF-WAY | 50000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGANY | CONSTRUCTION | 400000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | RIGHT-OF-WAY | 12000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGDA | RIGHT-OF-WAY | 100000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGDA | ENGINEERING | 80000 | FY 2023: 80000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGDA | RIGHT-OF-WAY | 400000 | FY 2023: 400000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGDA | CONSTRUCTION | 4500000 | FY 2023: 4500000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGDA | CONSTRUCTION | 2800000 | FY 2024: 2800000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | RIGHT-OF-WAY | 24000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | RIGHT-OF-WAY | 12000
U-5532 | BIKE/PED | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | BGANY | CONSTRUCTION | 50000 | FY 2023: 50000
U-5532E | BIKE/PED | VARIOUS | BIG TREE WAY-WENDOVER AVENUE TO ELKHOUND TRAIL; SHELBY DRIVE-BIG TREE WAY TO EDITH LANE; HEWITT STREET-NORWOLK STREET TO MERRITT DRIVE; BRIDFORD PARKWAY AND HORNADAY ROAD-WENDOVER AVENUE TO EXISTING WEST OF NICHOLAS ROAD. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 487000 | FY 2023: 487000
U-5532E | BIKE/PED | VARIOUS | BIG TREE WAY-WENDOVER AVENUE TO ELKHOUND TRAIL; SHELBY DRIVE-BIG TREE WAY TO EDITH LANE; HEWITT STREET-NORWOLK STREET TO MERRITT DRIVE; BRIDFORD PARKWAY AND HORNADAY ROAD-WENDOVER AVENUE TO EXISTING WEST OF NICHOLAS ROAD. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TADA | CONSTRUCTION | 1949000 | FY 2023: 1949000
U-5532F | BIKE/PED | VARIOUS | HOLDEN ROAD SIDEWALK (1) HOLDEN ROAD FROM WALKER AVENUE TO SPRING GARDEN STREET - BOTH SIDES, 2) HOLDEN ROAD FROM DARDEN ROAD TO VANDALIA ROAD - WEST SIDE, 3) HOLDEN ROAD FROM MADISON AVENUE TO WALKER AVENUE - BOTH SIDES, 4) RANKIN ROAD / MARTIN AVENUE SOUTH SIDE OF RANKIN ROAD FROM SUMMIT AVENUE TO MARTIN AVENUE. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 380000 | FY 2023: 380000
U-5532F | BIKE/PED | VARIOUS | HOLDEN ROAD SIDEWALK (1) HOLDEN ROAD FROM WALKER AVENUE TO SPRING GARDEN STREET - BOTH SIDES, 2) HOLDEN ROAD FROM DARDEN ROAD TO VANDALIA ROAD - WEST SIDE, 3) HOLDEN ROAD FROM MADISON AVENUE TO WALKER AVENUE - BOTH SIDES, 4) RANKIN ROAD / MARTIN AVENUE SOUTH SIDE OF RANKIN ROAD FROM SUMMIT AVENUE TO MARTIN AVENUE. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TADA | CONSTRUCTION | 1518000 | FY 2023: 1518000
U-5532G | BIKE/PED | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | UTILITIES | 1000
U-5532G | BIKE/PED | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | CONSTRUCTION | 230000 | FY 2023: 230000
U-5532G | BIKE/PED | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TADA | RIGHT-OF-WAY | 56000
U-5532G | BIKE/PED | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TADA | UTILITIES | 4000
U-5532G | BIKE/PED | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | TADA | CONSTRUCTION | 920000 | FY 2023: 920000
U-5532G | BIKE/PED | VARIOUS | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | L | RIGHT-OF-WAY | 14000
U-5532H | BIKE/PED | VARIOUS | NORTH SIDE OF SEMINOLE DRIVE FROM JOSEHPINE BOYD STREET; NORTH SIDE OF WHIPPOORWILL DRIVE FROM PENNYDALE DRIVE TO JANE STREET; AND NORTH SIDE OF WEST BESSEMER AVENUE FROM GRECADE STREET TO HILL STREET | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TADA | CONSTRUCTION | 536000 | FY 2023: 536000
U-5532H | BIKE/PED | VARIOUS | NORTH SIDE OF SEMINOLE DRIVE FROM JOSEHPINE BOYD STREET; NORTH SIDE OF WHIPPOORWILL DRIVE FROM PENNYDALE DRIVE TO JANE STREET; AND NORTH SIDE OF WEST BESSEMER AVENUE FROM GRECADE STREET TO HILL STREET | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 134000 | FY 2023: 134000
U-5532I | BIKE/PED | VARIOUS | HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TADA | CONSTRUCTION | 934000 | FY 2023: 934000
U-5532I | BIKE/PED | VARIOUS | HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TADA | RIGHT-OF-WAY | 320000 | FY 2023: 320000
U-5532I | BIKE/PED | VARIOUS | HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TADA | ENGINEERING | 65000 | FY 2023: 65000
U-5532I | BIKE/PED | VARIOUS | HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | CONSTRUCTION | 234000 | FY 2023: 234000
U-5532I | BIKE/PED | VARIOUS | HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | ENGINEERING | 16000 | FY 2023: 16000
U-5532I | BIKE/PED | VARIOUS | HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | L | RIGHT-OF-WAY | 80000 | FY 2023: 80000
U-5534 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS | DIVISION 3 |  | BGDA | CONSTRUCTION | 8570000 | FY 2023: 3463000; FY 2024: 586000
U-5534 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS | DIVISION 3 |  | L | CONSTRUCTION | 1012000 | FY 2023: 866000; FY 2024: 146000
U-5534 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS | DIVISION 3 |  | BGDACV | CONSTRUCTION | 168000 | FY 2023: 168000
U-5534 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS | DIVISION 3 |  | BGANY | CONSTRUCTION | 492000
U-5534 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS | DIVISION 3 |  |  |  | 3126000
U-5534 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS | DIVISION 3 |  | L | CONSTRUCTION | 496000
U-5534 | HIGHWAY | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | 3 | Wilmington Urban Area MPO | IN PROGRESS | DIVISION 3 |  | BGDA | RIGHT-OF-WAY | 220000
U-5535 | BIKE/PED | VARIOUS | FRENCH BROAD RIVER MPO TRANSPORTATION ALTERNATIVES (TA) PROGRAM. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | L | CONSTRUCTION | 1096000 | 0 | 0 | 0 | 0 | 0 | 0 | 94000 | 167000 | 167000 | 167000 | 167000 | 334000
U-5535 | BIKE/PED | VARIOUS | FRENCH BROAD RIVER MPO TRANSPORTATION ALTERNATIVES (TA) PROGRAM. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | TADA | CONSTRUCTION | 4391000 | 0 | 0 | 0 | 0 | 0 | 0 | 377000 | 669000 | 669000 | 669000 | 669000 | 1338000
U-5536 | HIGHWAY | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | UTILITIES | 1300000
U-5536 | HIGHWAY | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | CONSTRUCTION | 18792000 | FY 2024: 179000; FY 2025: 7610000; FY 2026: 7128000; FY 2027: 2983000; FY 2028: 892000
U-5536 | HIGHWAY | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | RIGHT-OF-WAY | 14792000
U-5536 | HIGHWAY | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 644000
U-5537 | HIGHWAY | SR 1521 (LAKE PINE DRIVE) | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTI-USE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | DIVISION 5 |  | BGDA | CONSTRUCTION | 468000
U-5537 | HIGHWAY | SR 1521 (LAKE PINE DRIVE) | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTI-USE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | DIVISION 5 |  | L | CONSTRUCTION | 117000
U-5537 | HIGHWAY | SR 1521 (LAKE PINE DRIVE) | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTI-USE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF APEX | DIVISION 5 |  |  |  | 1286000
U-5539A | HIGHWAY | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | CONSTRUCTION | 438000 | FY 2024: 438000
U-5539A | HIGHWAY | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  |  |  | 120000
U-5539A | HIGHWAY | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 500000 | FY 2023: 500000
U-5539A | HIGHWAY | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | BGANY | CONSTRUCTION | 1750000 | FY 2024: 1750000
U-5539A | HIGHWAY | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | DIVISION 9 |  | L | RIGHT-OF-WAY | 100000 | FY 2023: 100000
U-5543 | HIGHWAY | VARIOUS | VARIABLE MESSAGE SIGNS FOR TRAFFIC MANAGEMENT ON MAJOR CORRIDORS IN CHAPEL HILL. | 5, 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | EXEMPT |  |  |  | 1077000
U-5544 | BIKE/PED | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | 10, 12 | Charlotte Regional TPO |  | DIVISION 10, 12 |  | TADA | CONSTRUCTION | 18366000 |  | 0 | 0 | 0 | 0 | 0 | 1476000 | 2815000 | 2815000 | 2815000 | 2815000 | 5630000
U-5544 | BIKE/PED | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | 10, 12 | Charlotte Regional TPO |  | DIVISION 10, 12 |  | L | CONSTRUCTION | 4593000 |  | 0 | 0 | 0 | 0 | 0 | 369000 | 704000 | 704000 | 704000 | 704000 | 1408000
U-5545 | BIKE/PED | VARIOUS | CABARRUS ROWAN MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | 9, 10 | Cabarrus-Rowan MPO |  | DIVISION 9, 10 |  | L | CONSTRUCTION | 1245000 | 0 | 0 | 0 | 93000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 256000
U-5545 | BIKE/PED | VARIOUS | CABARRUS ROWAN MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | 9, 10 | Cabarrus-Rowan MPO |  | DIVISION 9, 10 |  | TADA | CONSTRUCTION | 4978000 | 0 | 0 | 0 | 370000 | 512000 | 512000 | 512000 | 512000 | 512000 | 512000 | 512000 | 1024000
U-5546 | BIKE/PED | VARIOUS | GREATER HICKORY MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | 11, 12, 13 | Greater Hickory MPO |  | DIVISION 11, 12, 13 |  | L | CONSTRUCTION | 1069000 | 0 | 0 | 0 | 0 | 53000 | 127000 | 127000 | 127000 | 127000 | 127000 | 127000 | 254000
U-5546 | BIKE/PED | VARIOUS | GREATER HICKORY MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | 11, 12, 13 | Greater Hickory MPO |  | DIVISION 11, 12, 13 |  | TADA | CONSTRUCTION | 4765000 | 0 | 0 | 0 | 211000 | 506000 | 506000 | 506000 | 506000 | 506000 | 506000 | 506000 | 1012000
U-5550 | HIGHWAY | US 15 / US 501 (FORDHAM BOULEVARD) | SR 1742 (EPHESUS CHURCH ROAD) IN CHAPEL HILL. INTERSECTION IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | STATEWIDE MOBILITY |  |  |  | 2170000
U-5604 | HIGHWAY | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | REGION G |  |  |  | 9756000
U-5604 | HIGHWAY | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | REGION G |  | T | BUILD NC CON | 3885000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 259000 | 518000
U-5604 | HIGHWAY | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | REGION G |  | T | ENGINEERING | 1830000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 122000 | 244000
U-5604 | HIGHWAY | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 14 | Southwestern RPO | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE). | REGION G |  | T | BUILD NC CON | 3195000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000 | 213000
U-5606 | HIGHWAY | SR 1598 (DICKINSON AVENUE) | NC 11 TO READE CIRCLE. IMPROVE ROADWAY. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 2 |  |  |  | 3554000
U-5606 | HIGHWAY | SR 1598 (DICKINSON AVENUE) | NC 11 TO READE CIRCLE. IMPROVE ROADWAY. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 2 |  | BG5200 | CONSTRUCTION | 18365000 | FY 2023: 5968000; FY 2024: 3093000
U-5608 | HIGHWAY | NEW ROUTE | SR 1211 (KIMBALL ROAD) EXTENSION, NORTH CHAPEL STREET TO SR 1221 (BOSTIAN ROAD) IN LANDIS. CONSTRUCT TWO-LANE CONNECTOR ON NEW LOCATION. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 8025000
U-5614 | HIGHWAY | VARIOUS | STBG-DA IN THE CABARRUS-ROWAN METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. | 9, 10 | Cabarrus-Rowan MPO | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP | DIVISION 9, 10 |  | BGDA | CONSTRUCTION | 46029000 | 0 | 0 | 5359000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 8134000
U-5614 | HIGHWAY | VARIOUS | STBG-DA IN THE CABARRUS-ROWAN METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. | 9, 10 | Cabarrus-Rowan MPO | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP | DIVISION 9, 10 |  | L | CONSTRUCTION | 11510000 | 0 | 0 | 1340000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 2034000
U-5615 | HIGHWAY | VARIOUS | STBG-DA IN THE GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. | 11, 12, 13 | Greater Hickory MPO |  | DIVISION 11, 12, 13 |  | L | CONSTRUCTION | 10312000 | 0 | 0 | 1267000 | 629000 | 584000 | 979000 | 979000 | 979000 | 979000 | 979000 | 979000 | 1958000
U-5615 | HIGHWAY | VARIOUS | STBG-DA IN THE GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. | 11, 12, 13 | Greater Hickory MPO |  | DIVISION 11, 12, 13 |  | BGDA | CONSTRUCTION | 40859000 | 0 | 0 | 5069000 | 2117000 | 2337000 | 3917000 | 3917000 | 3917000 | 3917000 | 3917000 | 3917000 | 7834000
U-5616 | HIGHWAY | VARIOUS | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | BGDA | PLANNING | 3251000 | 608000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
U-5616 | HIGHWAY | VARIOUS | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | L | PLANNING | 816000 | 152000 | 63000 | 63000 | 63000 | 63000 | 63000 | 63000
U-5616 | HIGHWAY | VARIOUS | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  |  |  | 313000
U-5617 | HIGHWAY | SR 1173 (WILLIAMS ROAD) | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 9 |  |  |  | 1196000
U-5617 | HIGHWAY | SR 1173 (WILLIAMS ROAD) | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 9 |  | BGANY | CONSTRUCTION | 1687000 | FY 2023: 1687000
U-5617 | HIGHWAY | SR 1173 (WILLIAMS ROAD) | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 9 |  | L | CONSTRUCTION | 422000 | FY 2023: 422000
U-5618 | HIGHWAY | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | DIVISION 5 |  | BGDA | CONSTRUCTION | 5670000
U-5618 | HIGHWAY | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | DIVISION 5 |  | L | CONSTRUCTION | 1418000
U-5618 | HIGHWAY | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | DIVISION 5 |  |  |  | 900000
U-5618 | HIGHWAY | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION | DIVISION 5 |  | S | CONSTRUCTION | 375000
U-5702 | HIGHWAY | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | [5 empty] | 2770000
U-5702A | HIGHWAY | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 15149000 | FY 2028: 4215000; FY 2029: 6323000; FY 2030: 1581000; FY 2031: 1515000; FY 2032: 1515000
U-5702A | HIGHWAY | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | UTILITIES | 5380000 | FY 2028: 2690000; FY 2029: 2690000
U-5702A | HIGHWAY | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 3 | Wilmington Urban Area MPO | PLANNING/DESIGN IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 15999000 | FY 2030: 5216000; FY 2031: 6993000; FY 2032: 3790000
U-5702B | HIGHWAY | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 8592000 | [11 empty] | 8592000
U-5702B | HIGHWAY | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 33800000 | [11 empty] | 33800000
U-5702B | HIGHWAY | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 14240000 | [11 empty] | 14240000
U-5703 | HIGHWAY | US 74 (ROOSEVELT BOULEVARD) | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO REDUCED CONFLICT INTERSECTION. | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF MONROE |  |  |  |  | 3961000
U-5703B | HIGHWAY | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 250000 | FY 2026: 22000; FY 2027: 228000
U-5703B | HIGHWAY | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 3457000 | FY 2023: 638000; FY 2024: 1276000; FY 2025: 851000; FY 2026: 346000; FY 2027: 346000
U-5703B | HIGHWAY | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | UTILITIES | 325000 | FY 2023: 325000
U-5703B | HIGHWAY | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 1491000 | FY 2026: 131000; FY 2027: 1360000
U-5704 | HIGHWAY | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 21182000
U-5704 | HIGHWAY | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2422000
U-5704 | HIGHWAY | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1100000
U-5704 | HIGHWAY | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 14100000
U-5706 | HIGHWAY | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 8 |  |  |  | 1685000
U-5706 | HIGHWAY | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 8 |  | T | RIGHT-OF-WAY | 8600000 | FY 2025: 86000; FY 2026: 2207000; FY 2027: 2752000; FY 2028: 1835000; FY 2029: 860000; FY 2030: 860000
U-5706 | HIGHWAY | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 8 |  | T | UTILITIES | 1800000 | FY 2025: 900000; FY 2026: 900000
U-5706 | HIGHWAY | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 8 |  | T | CONSTRUCTION | 18200000 | FY 2027: 0; FY 2028: 2948000; FY 2029: 9276000; FY 2030: 5976000
U-5706 | HIGHWAY | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 8 | Lumber River RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 8 |  | T | BUILD NC CON | 12870000 |  |  |  |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 6864000
U-5709 | HIGHWAY | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  |  |  | 1214000
U-5709 | HIGHWAY | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | CONSTRUCTION | 13198000 | FY 2025: 132000; FY 2026: 5982000; FY 2027: 5277000; FY 2028: 1807000
U-5709 | HIGHWAY | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | UTILITIES | 1700000
U-5709 | HIGHWAY | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | RIGHT-OF-WAY | 3427000
U-5710 | HIGHWAY | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  |  |  | 8833000
U-5710 | HIGHWAY | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 16900000 | FY 2023: 169000; FY 2024: 6591000; FY 2025: 6760000; FY 2026: 1690000; FY 2027: 1690000
U-5710 | HIGHWAY | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | UTILITIES | 4000000 | FY 2023: 2000000; FY 2024: 2000000
U-5710 | HIGHWAY | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 45000000 | FY 2026: 450000; FY 2027: 14850000; FY 2028: 15300000; FY 2029: 10800000; FY 2030: 3600000
U-5710A | HIGHWAY | NEW LOCATION | FROM SR 1409 (MILITARY CUTOFF ROAD) AT DRYSDALE DRIVE TO US 74 (EASTWOOD ROAD). ROADWAY ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 2575000
U-5710A | HIGHWAY | NEW LOCATION | FROM SR 1409 (MILITARY CUTOFF ROAD) AT DRYSDALE DRIVE TO US 74 (EASTWOOD ROAD). ROADWAY ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGANY | CONSTRUCTION | 8200000 | FY 2023: 6135000
U-5711 | HIGHWAY | SR 1712 (PINEVIEW STREET) | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  |  |  | 2376000
U-5711 | HIGHWAY | SR 1712 (PINEVIEW STREET) | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | CONSTRUCTION | 7900000 | FY 2024: 3461000; FY 2025: 3856000; FY 2026: 583000
U-5713 | HIGHWAY | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | STATEWIDE MOBILITY |  |  |  | 1700000
U-5713 | HIGHWAY | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 75600000 | FY 2023: 1500000
U-5713 | HIGHWAY | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | STATEWIDE MOBILITY |  | T | UTILITIES | 1000000
U-5713 | HIGHWAY | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 152337000 | FY 2023: 27298000; FY 2024: 23299000; FY 2025: 45660000
U-5716 | HIGHWAY | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 26700000 | FY 2028: 1335000; FY 2029: 16020000; FY 2030: 4005000; FY 2031: 2670000; FY 2032: 2670000
U-5716 | HIGHWAY | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | STATEWIDE MOBILITY |  | T | UTILITIES | 2700000 | FY 2028: 1350000; FY 2029: 1350000
U-5716 | HIGHWAY | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | STATEWIDE MOBILITY |  |  |  | 2150000
U-5716 | HIGHWAY | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH U-5739. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 40700000 | FY 2030: 8765000; FY 2031: 14680000; FY 2032: 11018000; FY 2033: 6237000
U-5717 | HIGHWAY | US 15 / US 501 | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067 | STATEWIDE MOBILITY |  |  |  | 11400000
U-5717 | HIGHWAY | US 15 / US 501 | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067 | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 32001000 | FY 2027: 10320000; FY 2028: 11347000; FY 2029: 7828000; FY 2030: 2506000
U-5720 | HIGHWAY | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO EAST OF SR 2095 (PAGE ROAD EXTENSION). UPGRADE TO CONTROLLED-ACCESS FACILITY AND CONVERT SR 1811 AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | Durham-Chapel Hill-Carrboro MPO | [5 empty] | 2000000
U-5720A | HIGHWAY | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 36502000
U-5720A | HIGHWAY | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 46401000
U-5720A | HIGHWAY | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1306000
U-5720B | HIGHWAY | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | 5 | Durham-Chapel Hill-Carrboro MPO | INCLUDES INTERCHANGE AT SR 1811 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 81700000
U-5720B | HIGHWAY | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | 5 | Durham-Chapel Hill-Carrboro MPO | INCLUDES INTERCHANGE AT SR 1811 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 140500000
U-5720B | HIGHWAY | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | 5 | Durham-Chapel Hill-Carrboro MPO | INCLUDES INTERCHANGE AT SR 1811 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1218000
U-5722 | HIGHWAY | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 8 | Triangle Area RPO |  | REGION E |  |  |  | 3500000
U-5722 | HIGHWAY | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 8 | Triangle Area RPO |  | REGION E |  | T | RIGHT-OF-WAY | 24700000 | FY 2028: 3640000; FY 2029: 6240000; FY 2030: 6240000; FY 2031: 3640000; FY 2032: 4940000
U-5722 | HIGHWAY | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 8 | Triangle Area RPO |  | REGION E |  | T | UTILITIES | 7564000 | FY 2028: 3782000; FY 2029: 3782000
U-5722 | HIGHWAY | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 15099000 | FY 2031: 2963000; FY 2032: 7052000; FY 2033: 4587000 | 497000
U-5723 | HIGHWAY | US 74 | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024 | STATEWIDE MOBILITY |  |  |  | 3846000
U-5723 | HIGHWAY | US 74 | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024 | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 15000000 | FY 2026: 150000; FY 2027: 7019000; FY 2028: 5763000; FY 2029: 2068000
U-5724 | HIGHWAY | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF SR 1709 (CENTRAL HEIGHTS ROAD) AT BERKELEY BOULEVARD IN GOLDSBORO. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  |  |  | 2670000
U-5724 | HIGHWAY | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF SR 1709 (CENTRAL HEIGHTS ROAD) AT BERKELEY BOULEVARD IN GOLDSBORO. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | T | CONSTRUCTION | 19839000 | FY 2023: 8512000; FY 2024: 7164000; FY 2025: 4163000
U-5725 | HIGHWAY | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | DIVISION 4 |  |  |  | 17376000
U-5725 | HIGHWAY | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | DIVISION 4 |  | T | ENGINEERING | 2130000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 142000 | 284000
U-5725 | HIGHWAY | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | DIVISION 4 |  | T | BUILD NC CON | 14880000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 992000 | 1984000
U-5725 | HIGHWAY | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3). | DIVISION 4 |  | T | CONSTRUCTION | 12360000
U-5726 | HIGHWAY | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 750000
U-5726 | HIGHWAY | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BG5T50 | CONSTRUCTION | 14600000 | FY 2027: 2758000; FY 2028: 7171000; FY 2029: 4671000
U-5726 | HIGHWAY | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BG5T50 | RIGHT-OF-WAY | 11200000 | FY 2025: 3360000; FY 2026: 4480000; FY 2027: 1120000; FY 2028: 1120000; FY 2029: 1120000
U-5726 | HIGHWAY | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BG5T50 | UTILITIES | 1400000 | FY 2025: 700000; FY 2026: 700000
U-5727 | HIGHWAY | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION AND RELOCATE NC 78 (TRAMWAY ROAD). | 8 | Triangle Area RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS | REGION E |  |  |  | 3000000
U-5727 | HIGHWAY | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION AND RELOCATE NC 78 (TRAMWAY ROAD). | 8 | Triangle Area RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS | REGION E |  | NHP | RIGHT-OF-WAY | 12300000 | FY 2023: 3075000; FY 2024: 6150000; FY 2025: 3075000
U-5727 | HIGHWAY | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION AND RELOCATE NC 78 (TRAMWAY ROAD). | 8 | Triangle Area RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS | REGION E |  | NHP | UTILITIES | 1500000 | FY 2023: 1500000
U-5727 | HIGHWAY | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION AND RELOCATE NC 78 (TRAMWAY ROAD). | 8 | Triangle Area RPO | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | CONSTRUCTION | 14401000 | FY 2026: 5132000; FY 2027: 6467000; FY 2028: 2802000
U-5728 | HIGHWAY | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  |  |  | 3201000
U-5728 | HIGHWAY | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  | T | CONSTRUCTION | 4800000 | FY 2025: 48000; FY 2026: 3633000; FY 2027: 1119000
U-5729 | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO | [5 empty] | 14510000
U-5729REG | HIGHWAY | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | REGION B |  | T | RIGHT-OF-WAY | 21200000 | FY 2028: 5300000; FY 2029: 10600000; FY 2030: 5300000
U-5729REG | HIGHWAY | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | REGION B |  | T | UTILITIES | 6560000 | FY 2028: 3280000; FY 2029: 3280000
U-5729REG | HIGHWAY | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | REGION B |  | T | CONSTRUCTION | 16160000 | FY 2030: 5818000; FY 2031: 6302000; FY 2032: 4040000
U-5729SW | HIGHWAY | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 4040000 | FY 2030: 1454000; FY 2031: 1576000; FY 2032: 1010000
U-5729SW | HIGHWAY | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 5300000 | FY 2028: 1325000; FY 2029: 2650000; FY 2030: 1325000
U-5729SW | HIGHWAY | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | T | UTILITIES | 1640000 | FY 2028: 820000; FY 2029: 820000
U-5730 | HIGHWAY | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  | T | UTILITIES | 125000 | FY 2023: 125000
U-5730 | HIGHWAY | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  |  |  | 200000
U-5730 | HIGHWAY | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  | T | CONSTRUCTION | 1200000 | FY 2025: 456000; FY 2026: 744000
U-5731 | HIGHWAY | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  |  |  | 1500000
U-5731 | HIGHWAY | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | BGLT5 | RIGHT-OF-WAY | 5200000 | FY 2027: 693000; FY 2028: 2080000; FY 2029: 1387000; FY 2030: 520000; FY 2031: 520000
U-5731 | HIGHWAY | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | BGLT5 | UTILITIES | 241000 | FY 2027: 241000
U-5731 | HIGHWAY | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY |  | BGLT5 | CONSTRUCTION | 31500000 | FY 2029: 315000; FY 2030: 12075000; FY 2031: 10640000; FY 2032: 7149000; FY 2033: 1321000
U-5732 | HIGHWAY | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 3 | Wilmington Urban Area MPO |  | REGION B | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 18604000
U-5732 | HIGHWAY | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 3 | Wilmington Urban Area MPO |  | REGION B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 19536000
U-5732 | HIGHWAY | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 3 | Wilmington Urban Area MPO |  | REGION B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 35900000
U-5734 | HIGHWAY | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO |  | REGION B |  |  |  | 1000000
U-5734 | HIGHWAY | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO |  | REGION B |  | T | RIGHT-OF-WAY | 13940000 | FY 2025: 139000; FY 2026: 6421000; FY 2027: 4592000; FY 2028: 1394000; FY 2029: 1394000
U-5734 | HIGHWAY | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO |  | REGION B |  | T | UTILITIES | 1032000 | FY 2025: 516000; FY 2026: 516000
U-5734 | HIGHWAY | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO |  | REGION B |  | T | CONSTRUCTION | 10300000 | FY 2027: 2185000; FY 2028: 5476000; FY 2029: 2639000
U-5735 | HIGHWAY | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | RIGHT-OF-WAY | 28864000 | FY 2027: 2566000; FY 2028: 10263000; FY 2029: 10263000; FY 2030: 2886000; FY 2031: 2886000
U-5735 | HIGHWAY | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | UTILITIES | 8328000 | FY 2027: 4164000; FY 2028: 4164000
U-5735 | HIGHWAY | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  |  |  | 1900000
U-5735 | HIGHWAY | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | CONSTRUCTION | 51624000 | FY 2031: 516000; FY 2032: 15613000; FY 2033: 16257000 | 19238000
U-5735A | HIGHWAY | US 17 (WILMINGTON HIGHWAY) | ROADWAY IMPROVEMENTS TO DOUGLAS GATE ENTRANCE. | 3 | Jacksonville Urban Area MPO | COMPLETED. OTHER FUNDS REPRESENT DEPARTMENT OF DEFENSE FUNDS. | EXEMPT |  | O | CONSTRUCTION | 1075000
U-5736 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E AND U-5508. | REGION B |  |  |  | 7800000
U-5736 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E AND U-5508. | REGION B |  | T | RIGHT-OF-WAY | 10501000 | FY 2028: 2028000; FY 2029: 3476000; FY 2030: 2897000; FY 2031: 1050000; FY 2032: 1050000
U-5736 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E AND U-5508. | REGION B |  | T | UTILITIES | 2440000 | FY 2028: 1220000; FY 2029: 1220000
U-5736 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | COMBINED WITH U-4007E AND U-5508. | REGION B |  | T | CONSTRUCTION | 31300000 | FY 2030: 313000; FY 2031: 11968000; FY 2032: 10582000; FY 2033: 7123000 | 1314000
U-5737 | HIGHWAY | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 8 | Triangle Area RPO |  | REGION E |  |  |  | 1656000
U-5737 | HIGHWAY | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 20501000 | FY 2028: 205000; FY 2029: 8118000; FY 2030: 7824000; FY 2031: 4354000
U-5737 | HIGHWAY | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 8 | Triangle Area RPO |  | REGION E |  | T | RIGHT-OF-WAY | 4931000 | FY 2024: 50000; FY 2025: 1333000; FY 2026: 1333000; FY 2027: 1333000; FY 2028: 882000
U-5737 | HIGHWAY | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 8 | Triangle Area RPO |  | REGION E |  | T | UTILITIES | 2671000 | FY 2024: 500000; FY 2025: 2171000
U-5738 | HIGHWAY | SR 2528 (JULIAN ROAD) | US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2667 (SUMMIT PARK DRIVE) IN SALISBURY. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 3900000
U-5738 | HIGHWAY | SR 2528 (JULIAN ROAD) | US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2667 (SUMMIT PARK DRIVE) IN SALISBURY. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  | T | CONSTRUCTION | 14995000 | FY 2023: 7099000; FY 2024: 4777000; FY 2025: 1368000
U-5739 | HIGHWAY | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | REGION B |  | T | CONSTRUCTION | 19800000 | FY 2030: 5310000; FY 2031: 8440000; FY 2032: 5508000; FY 2033: 542000
U-5739 | HIGHWAY | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | REGION B |  |  |  | 5200000
U-5739 | HIGHWAY | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | REGION B |  | T | RIGHT-OF-WAY | 3500000 | FY 2028: 187000; FY 2029: 2240000; FY 2030: 373000; FY 2031: 350000; FY 2032: 350000
U-5739 | HIGHWAY | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO | PROJECT BEING LET WITH WITH U-5716. | REGION B |  | T | UTILITIES | 2900000 | FY 2028: 1450000; FY 2029: 1450000
U-5741 | HIGHWAY | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | PROJECT INCLUDES B-5650. | REGION B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 49600000
U-5741 | HIGHWAY | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | PROJECT INCLUDES B-5650. | REGION B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3664000
U-5741 | HIGHWAY | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | PROJECT INCLUDES B-5650. | REGION B | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2500000
U-5741 | HIGHWAY | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | PROJECT INCLUDES B-5650. | REGION B | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7368000
U-5742 | HIGHWAY | FAYETTEVILLE | FAYETTEVILLE COMPUTERIZED TRAFFIC SIGNAL SYSTEM. | 6 | Fayetteville Area MPO | COMPLETED. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | REGION C |  |  |  | 9034000
U-5742 | HIGHWAY | FAYETTEVILLE | FAYETTEVILLE COMPUTERIZED TRAFFIC SIGNAL SYSTEM. | 6 | Fayetteville Area MPO | COMPLETED. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | REGION C |  | T | BUILD NC CON | 735000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000
U-5743 | HIGHWAY | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | CONSTRUCTION | 8099000 | FY 2025: 590000; FY 2026: 4899000; FY 2027: 2610000
U-5743 | HIGHWAY | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  |  |  | 2151000
U-5743 | HIGHWAY | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | RIGHT-OF-WAY | 2006000
U-5743 | HIGHWAY | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | UTILITIES | 900000
U-5744 | HIGHWAY | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1700000
U-5744 | HIGHWAY | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 14400000
U-5744 | HIGHWAY | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 138000
U-5744 | HIGHWAY | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 13998000
U-5745 | HIGHWAY | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | REGION C |  |  |  | 2749000
U-5745 | HIGHWAY | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | REGION C |  | T | BUILD NC CON | 1313000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 88000 | 81000
U-5745 | HIGHWAY | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | REGION C |  | T | ENGINEERING | 624000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 39000 | 78000
U-5745 | HIGHWAY | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | REGION C |  | T | BUILD NC ROW | 435000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000
U-5746 | HIGHWAY | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION C |  |  |  | 4276000
U-5746 | HIGHWAY | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | RIGHT-OF-WAY | 2938000
U-5746 | HIGHWAY | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | UTILITIES | 610000
U-5746 | HIGHWAY | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | CONSTRUCTION | 5699000 | FY 2024: 2006000; FY 2025: 3067000; FY 2026: 626000
U-5747 | HIGHWAY | NC 54; SR 1635 (MCCRIMMON PARKWAY) | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET); NC 54 AT SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. WIDEN SR 1635 AND CONVERT NC 54 AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION | 5 | Capital Area MPO | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) |  |  |  |  | 9396000
U-5747 | HIGHWAY | NC 54; SR 1635 (MCCRIMMON PARKWAY) | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET); NC 54 AT SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. WIDEN SR 1635 AND CONVERT NC 54 AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION | 5 | Capital Area MPO | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) |  |  | T | ENGINEERING | 3001000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 201000
U-5747A | HIGHWAY | SR 1635 (MCCRIMMON PARKWAY) | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966 | DIVISION 5 |  | T | UTILITIES | 500000
U-5747A | HIGHWAY | SR 1635 (MCCRIMMON PARKWAY) | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966 | DIVISION 5 |  | T | CONSTRUCTION | 19600000 | FY 2025: 2801000; FY 2026: 8287000; FY 2027: 5918000; FY 2028: 2594000
U-5747A | HIGHWAY | SR 1635 (MCCRIMMON PARKWAY) | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966 | DIVISION 5 |  | T | RIGHT-OF-WAY | 4000000
U-5747B | HIGHWAY | NC 54 | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | REGION C |  | T | BUILD NC ROW | 72000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 7000
U-5747B | HIGHWAY | NC 54 | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | REGION C |  | T | UTILITIES | 620000 | FY 2024: 620000
U-5747B | HIGHWAY | NC 54 | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | REGION C |  | T | CONSTRUCTION | 22100000 | FY 2025: 3100000; FY 2026: 9189000; FY 2027: 6689000; FY 2028: 3122000
U-5748 | HIGHWAY | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | REGION C |  |  |  | 2133000
U-5748 | HIGHWAY | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | ENGINEERING | 1921000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000
U-5748 | HIGHWAY | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | BUILD NC ROW | 1996000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000
U-5748 | HIGHWAY | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | RIGHT-OF-WAY | 4844000
U-5748 | HIGHWAY | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | UTILITIES | 212000
U-5748 | HIGHWAY | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE). RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | CONSTRUCTION | 22500000 | FY 2024: 1492000; FY 2025: 9573000; FY 2026: 7309000; FY 2027: 4126000
U-5750 | HIGHWAY | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $10 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | BUILD NC CON | 12870000 |  |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 5148000
U-5750 | HIGHWAY | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $10 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | UTILITIES | 1900000 | FY 2023: 1600000
U-5750 | HIGHWAY | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $10 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | CONSTRUCTION | 9200000 | FY 2025: 0; FY 2026: 0; FY 2027: 4784000; FY 2028: 4416000
U-5750 | HIGHWAY | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $10 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | ENGINEERING | 1620000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000
U-5750 | HIGHWAY | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $10 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | REGION C |  |  |  | 12093000
U-5750 | HIGHWAY | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE); BUILD NC BONDS: $10 MILLION CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR6 SALE); RIGHT-OF-WAY IN PROGRESS | REGION C |  | T | BUILD NC ROW | 3468000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000
U-5751 | HIGHWAY | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 5 | Capital Area MPO |  | REGION C |  | T | CONSTRUCTION | 68300000 | FY 2031: 8386000; FY 2032: 21358000; FY 2033: 18045000 | 20511000
U-5751 | HIGHWAY | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 5 | Capital Area MPO |  | REGION C |  |  |  | 700000
U-5751 | HIGHWAY | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 5 | Capital Area MPO |  | REGION C |  | T | RIGHT-OF-WAY | 39151000 | FY 2028: 6594000; FY 2029: 9891000; FY 2030: 9891000; FY 2031: 4945000; FY 2032: 7830000
U-5751 | HIGHWAY | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 5 | Capital Area MPO |  | REGION C |  | T | UTILITIES | 2620000 | FY 2028: 1310000; FY 2029: 1310000
U-5753 | HIGHWAY | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | CONSTRUCTION | 35400000 | FY 2026: 0; FY 2027: 4794000; FY 2028: 14800000; FY 2029: 10813000; FY 2030: 4993000
U-5753 | HIGHWAY | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | BUILD NC CON | 12870000 |  |  |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 6006000
U-5753 | HIGHWAY | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | BGANY | UTILITIES | 5000000 | FY 2023: 4800000
U-5753 | HIGHWAY | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  |  |  | 800000
U-5753 | HIGHWAY | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 8 | Fayetteville Area MPO | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | BGANY | RIGHT-OF-WAY | 42100000 | FY 2023: 13690000; FY 2024: 20000000; FY 2025: 4200000; FY 2026: 4200000
U-5754 | HIGHWAY | US 29 / US 70 / US 220 (O'HENRY BOULEVARD) | I-40 / BUSINESS 85 TO SOUTH OF FLORIDA STREET IN GREENSBORO. ADD LANE ON I-40 / BUSINESS 85 EASTBOUND RAMP ONTO NORTHBOUND US 29 / US 70 / US 220 AND EXTEND US 29 / US 70 / US 220 SOUTHBOUND RAMP ONTO SR 3762 (MARTIN LUTHER KING, JR. DRIVE) | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | REGION D |  | T | CONSTRUCTION | 6750000 | FY 2023: 3787000; FY 2024: 237000
U-5756 | HIGHWAY | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 8 | Triangle Area RPO |  | REGION E |  | T | UTILITIES | 8200000 | FY 2023: 4100000; FY 2024: 4100000
U-5756 | HIGHWAY | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 33999000 | FY 2025: 340000; FY 2026: 11370000; FY 2027: 11518000; FY 2028: 8034000; FY 2029: 2737000
U-5756 | HIGHWAY | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 8 | Triangle Area RPO |  | REGION E |  |  |  | 2800000
U-5756 | HIGHWAY | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 8 | Triangle Area RPO |  | REGION E |  | T | RIGHT-OF-WAY | 4600000 | FY 2023: 2300000; FY 2024: 2300000
U-5757 | HIGHWAY | NC 8 (WINSTON ROAD) | 9TH STREET TO SR 1408 (BIESECKER ROAD) IN LEXINGTON. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  |  |  | 1861000
U-5757 | HIGHWAY | NC 8 (WINSTON ROAD) | 9TH STREET TO SR 1408 (BIESECKER ROAD) IN LEXINGTON. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | T | RIGHT-OF-WAY | 17575000
U-5757 | HIGHWAY | NC 8 (WINSTON ROAD) | 9TH STREET TO SR 1408 (BIESECKER ROAD) IN LEXINGTON. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | T | CONSTRUCTION | 8800000 | FY 2024: 88000; FY 2025: 4190000; FY 2026: 3633000; FY 2027: 889000
U-5758 | HIGHWAY | US 220 BUSINESS (FAYETTEVILLE STREET) | INTERSECTION OF US 220 BUSINESS (FAYETTEVILLE STREET) AND PRESNELL STREET IN ASHEBORO. INTERSECTION IMPROVEMENTS. | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION | REGION E |  |  |  | 1541000
U-5760 | HIGHWAY | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | T | UTILITIES | 4000000 | FY 2023: 1900000; FY 2024: 1900000
U-5760 | HIGHWAY | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | T | CONSTRUCTION | 31592000 | FY 2025: 416000; FY 2026: 15584000; FY 2027: 2796000; FY 2028: 8957000; FY 2029: 3839000
U-5760 | HIGHWAY | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | T | RIGHT-OF-WAY | 11500000 | FY 2023: 5500000; FY 2024: 5500000
U-5760 | HIGHWAY | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  |  |  | 2905000
U-5760 | HIGHWAY | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 9 | Winston-Salem Urban Area MPO | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | T | BUILD NC CON | 12870000 |  |  |  | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 6006000
U-5761 | HIGHWAY | NC 3 (DALE EARNHARDT BOULEVARD) | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  |  |  | 3660000
U-5761 | HIGHWAY | NC 3 (DALE EARNHARDT BOULEVARD) | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | CONSTRUCTION | 8100000 | FY 2024: 81000; FY 2025: 4503000; FY 2026: 3077000; FY 2027: 439000
U-5763 | HIGHWAY | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO |  | REGION E |  |  |  | 1000000
U-5763 | HIGHWAY | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 16000000 | FY 2026: 2422000; FY 2027: 4151000; FY 2028: 4151000; FY 2029: 2076000; FY 2030: 3200000
U-5763 | HIGHWAY | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 5600000 | FY 2026: 2800000; FY 2027: 2800000
U-5763 | HIGHWAY | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 21700000 | FY 2029: 3930000; FY 2030: 9935000; FY 2031: 5722000; FY 2032: 2113000
U-5764 | HIGHWAY | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | REGION E |  |  |  | 10572000
U-5764 | HIGHWAY | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | REGION E |  | T | CONSTRUCTION | 43399000 | FY 2028: 434000; FY 2029: 14940000; FY 2030: 15063000; FY 2031: 8988000; FY 2032: 3974000
U-5764 | HIGHWAY | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | REGION E |  | T | UTILITIES | 2700000 | FY 2025: 1350000; FY 2026: 1350000
U-5764 | HIGHWAY | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931 | REGION E |  | T | RIGHT-OF-WAY | 24501000 | FY 2025: 530000; FY 2026: 6357000; FY 2027: 6357000; FY 2028: 6357000; FY 2029: 4900000
U-5765 | HIGHWAY | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. | REGION E |  |  |  | 510000
U-5765 | HIGHWAY | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | RIGHT-OF-WAY | 58430000 | FY 2023: 7012000; FY 2024: 14023000; FY 2025: 14023000; FY 2026: 11686000; FY 2027: 11686000
U-5765 | HIGHWAY | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | UTILITIES | 7500000 | FY 2023: 3750000; FY 2024: 3750000
U-5765 | HIGHWAY | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | CONSTRUCTION | 31500000 | FY 2026: 315000; FY 2027: 13022000; FY 2028: 10620000; FY 2029: 5900000; FY 2030: 1643000
U-5766 | HIGHWAY | NC 160 | SOUTH CAROLINA LINE TO I-485. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | [5 empty] | 3000000
U-5766A | HIGHWAY | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 20500000 | FY 2025: 3364000; FY 2026: 5046000; FY 2027: 5046000; FY 2028: 2944000; FY 2029: 4100000
U-5766A | HIGHWAY | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 4100000 | FY 2025: 2050000; FY 2026: 2050000
U-5766A | HIGHWAY | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 65399000 | FY 2028: 11347000; FY 2029: 29109000; FY 2030: 17692000; FY 2031: 7251000
U-5766B | HIGHWAY | NC 160 | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 59400000 | FY 2025: 9734000; FY 2026: 14601000; FY 2027: 14601000; FY 2028: 13384000; FY 2029: 7080000
U-5766B | HIGHWAY | NC 160 | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 6500000 | FY 2025: 3250000; FY 2026: 3250000
U-5766B | HIGHWAY | NC 160 | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 65800000 | FY 2029: 658000; FY 2030: 22497000; FY 2031: 20587000; FY 2032: 13388000; FY 2033: 8670000
U-5767 | HIGHWAY | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | REGION E |  | T | BUILD NC ROW | 15180000 |  |  |  | 1012000 | 1012000 | 1012000 | 1012000 | 1012000 | 1012000 | 1012000 | 1012000 | 7084000
U-5767 | HIGHWAY | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | REGION E |  | T | CONSTRUCTION | 27303000 | FY 2029: 4665000; FY 2030: 11903000; FY 2031: 7440000; FY 2032: 3295000
U-5767 | HIGHWAY | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | REGION E |  | T | UTILITIES | 4400000 | FY 2026: 2200000; FY 2027: 2200000
U-5767 | HIGHWAY | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | REGION E |  |  |  | 4593000
U-5767 | HIGHWAY | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE) | REGION E |  | T | RIGHT-OF-WAY | 23900000 | FY 2026: 239000; FY 2027: 2241000; FY 2028: 9520000; FY 2029: 4760000; FY 2030: 7140000
U-5768 | HIGHWAY | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | REGION E |  | T | CONSTRUCTION | 44200000 | FY 2029: 5363000; FY 2030: 15915000; FY 2031: 12148000; FY 2032: 7404000; FY 2033: 3370000
U-5768 | HIGHWAY | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | REGION E |  |  |  | 2000000
U-5768 | HIGHWAY | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | REGION E |  | L | CONSTRUCTION | 12100000 | FY 2029: 1468000; FY 2030: 4357000; FY 2031: 3326000; FY 2032: 2027000; FY 2033: 922000
U-5768 | HIGHWAY | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | REGION E |  | T | RIGHT-OF-WAY | 29400000 | FY 2026: 3267000; FY 2027: 7840000; FY 2028: 7840000; FY 2029: 4573000; FY 2030: 5880000
U-5768 | HIGHWAY | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 10 | Charlotte Regional TPO | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE | REGION E |  | T | UTILITIES | 4000000 | FY 2026: 2000000; FY 2027: 2000000
U-5769 | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | [5 empty] | 3840000
U-5769A | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 3400000 | FY 2024: 1700000; FY 2025: 1700000
U-5769A | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 26402000 | FY 2028: 264000; FY 2029: 10363000; FY 2030: 9582000; FY 2031: 5171000; FY 2032: 1022000
U-5769A | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 5701000 | FY 2024: 933000; FY 2025: 1244000; FY 2026: 1244000; FY 2027: 1140000; FY 2028: 1140000
U-5769AA | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | REGION E |  | HSIP | CONSTRUCTION | 1225000 | FY 2025: 1225000
U-5769AA | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 4000000 | FY 2023: 4000000
U-5769AA | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 1000000 | FY 2024: 1000000
U-5769B | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 15500000 | FY 2024: 2536000; FY 2025: 3382000; FY 2026: 3382000; FY 2027: 3100000; FY 2028: 3100000
U-5769B | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 31400000 | FY 2028: 314000; FY 2029: 11682000; FY 2030: 11075000; FY 2031: 6193000; FY 2032: 2136000
U-5769B | HIGHWAY | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 2800000 | FY 2024: 1400000; FY 2025: 1400000
U-5770 | HIGHWAY | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | 8 | High Point Urban Area MPO | “S” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | REGION E |  |  |  | 1702000
U-5770 | HIGHWAY | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | 8 | High Point Urban Area MPO | “S” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | REGION E |  | T | RIGHT-OF-WAY | 6358000
U-5770 | HIGHWAY | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | 8 | High Point Urban Area MPO | “S” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. | REGION E |  | T | UTILITIES | 2200000
U-5770A | HIGHWAY | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | 8 | High Point Urban Area MPO |  | REGION E |  | S | CONSTRUCTION | 669000 | FY 2023: 89000; FY 2024: 580000
U-5770A | HIGHWAY | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | 8 | High Point Urban Area MPO |  | REGION E |  | T | CONSTRUCTION | 1024000 | FY 2023: 136000; FY 2024: 888000
U-5770B | HIGHWAY | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCI IMPROVEMENTS. | 8 | High Point Urban Area MPO |  | REGION E |  | T | CONSTRUCTION | 17500000 | FY 2026: 175000; FY 2027: 8690000; FY 2028: 6222000; FY 2029: 2413000
U-5771 | HIGHWAY | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  |  |  | 2098000
U-5771 | HIGHWAY | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | BA | RIGHT-OF-WAY | 450000
U-5771 | HIGHWAY | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | RIGHT-OF-WAY | 52600000 | FY 2023: 8525000; FY 2024: 22525000; FY 2025: 14000000
U-5771 | HIGHWAY | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | UTILITIES | 1600000
U-5771 | HIGHWAY | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | CONSTRUCTION | 22401000 | FY 2025: 3971000; FY 2026: 10121000; FY 2027: 5991000; FY 2028: 2318000
U-5772 | HIGHWAY | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 4300000 | FY 2028: 2150000; FY 2029: 2150000
U-5772 | HIGHWAY | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 33700000 | FY 2031: 5430000; FY 2032: 14066000; FY 2033: 9129000 | 5075000
U-5772 | HIGHWAY | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  |  |  | 3500000
U-5772 | HIGHWAY | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 6500000 | FY 2028: 709000; FY 2029: 2836000; FY 2030: 1655000; FY 2031: 650000; FY 2032: 650000
U-5774 | HIGHWAY | NC 54 | US 15 / US 501 IN CHAPEL HILL TO NC 55 IN DURHAM. UPGRADE ROADWAY CORRIDOR. | 5, 7 | Durham-Chapel Hill-Carrboro MPO | PARTS A THROUGH F ON EXPANDED NHS |  |  |  |  | 1905000
U-5774A | HIGHWAY | NC 54 | US 15 / US 501. UPGRADE INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2800000 | [11 empty] | 2800000
U-5774A | HIGHWAY | NC 54 | US 15 / US 501. UPGRADE INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 140000 | [11 empty] | 140000
U-5774A | HIGHWAY | NC 54 | US 15 / US 501. UPGRADE INTERCHANGE. | 7 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 16100000 | [11 empty] | 16100000
U-5774B | HIGHWAY | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 74000
U-5774B | HIGHWAY | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 23300000
U-5774B | HIGHWAY | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | REGION C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 43001000
U-5774C | HIGHWAY | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 267000
U-5774C | HIGHWAY | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 11599000
U-5774C | HIGHWAY | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 934000
U-5774F | HIGHWAY | I-40 | NC 54 INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS, INCLUDING UPGRADE OF NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 91470000 | FY 2028: 16726000; FY 2029: 25089000; FY 2030: 25089000; FY 2031: 6272000; FY 2032: 18294000
U-5774F | HIGHWAY | I-40 | NC 54 INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS, INCLUDING UPGRADE OF NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | UTILITIES | 15700000 | FY 2028: 15700000
U-5774F | HIGHWAY | I-40 | NC 54 INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS, INCLUDING UPGRADE OF NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 88399000 | FY 2031: 19289000; FY 2032: 24558000; FY 2033: 20532000 | 24020000
U-5774G | HIGHWAY | NC 54 | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 16900000 | [11 empty] | 16900000
U-5774G | HIGHWAY | NC 54 | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 800000 | [11 empty] | 800000
U-5774G | HIGHWAY | NC 54 | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 1800000 | [11 empty] | 1800000
U-5774H | HIGHWAY | NC 54 | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 726000 | [11 empty] | 726000
U-5774H | HIGHWAY | NC 54 | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 18000000 | [11 empty] | 18000000
U-5774H | HIGHWAY | NC 54 | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5900000 | [11 empty] | 5900000
U-5774I | HIGHWAY | NC 54 | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2500000 | [11 empty] | 2500000
U-5774I | HIGHWAY | NC 54 | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 617000 | [11 empty] | 617000
U-5774I | HIGHWAY | NC 54 | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 12300000 | [11 empty] | 12300000
U-5774J | HIGHWAY | NC 54 | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | UTILITIES | 420000 | [11 empty] | 420000
U-5774J | HIGHWAY | NC 54 | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 17100000 | [11 empty] | 17100000
U-5774J | HIGHWAY | NC 54 | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. | 5 | Durham-Chapel Hill-Carrboro MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 3200000 | [11 empty] | 3200000
U-5775 | HIGHWAY | US 74 BUSINESS (MARION STREET) | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $300,000 FROM CITY OF SHELBY | REGION F |  | L | CONSTRUCTION | 299000 | FY 2023: 195000; FY 2024: 40000
U-5775 | HIGHWAY | US 74 BUSINESS (MARION STREET) | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $300,000 FROM CITY OF SHELBY | REGION F |  | T | CONSTRUCTION | 3700000 | FY 2023: 2410000; FY 2024: 496000
U-5775 | HIGHWAY | US 74 BUSINESS (MARION STREET) | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. $300,000 FROM CITY OF SHELBY | REGION F |  |  |  | 1153000
U-5777 | HIGHWAY | NC 127 | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  | T | RIGHT-OF-WAY | 2150000
U-5777 | HIGHWAY | NC 127 | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  |  |  | 275000
U-5777 | HIGHWAY | NC 127 | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | REGION F |  | T | CONSTRUCTION | 3951000 | FY 2025: 1626000; FY 2026: 2325000
U-5779 | HIGHWAY | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9100000
U-5779 | HIGHWAY | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 22099000
U-5779 | HIGHWAY | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-5779 | HIGHWAY | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6400000
U-5780 | HIGHWAY | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | REGION F |  |  |  | 223000
U-5780 | HIGHWAY | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | REGION F |  | T | CONSTRUCTION | 1450000 | FY 2024: 705000; FY 2025: 745000
U-5780 | HIGHWAY | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U. | REGION F |  | T | RIGHT-OF-WAY | 550000
U-5783 | HIGHWAY | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | REGION G |  |  |  | 1500000
U-5783 | HIGHWAY | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | REGION G |  | T | RIGHT-OF-WAY | 17400000 | FY 2023: 8700000
U-5783 | HIGHWAY | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | REGION G |  | T | UTILITIES | 3900000 | FY 2023: 1750000; FY 2024: 1750000
U-5783 | HIGHWAY | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | REGION G |  | T | CONSTRUCTION | 20198000 | FY 2024: 202000; FY 2025: 8200000; FY 2026: 6977000; FY 2027: 4819000
U-5785 | HIGHWAY | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | TO BE LET WITH U-5917. | DIVISION 2 |  |  |  | 18000000
U-5785 | HIGHWAY | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | TO BE LET WITH U-5917. | DIVISION 2 |  | T | RIGHT-OF-WAY | 17620000 | FY 2024: 176000; FY 2025: 5865000; FY 2026: 8055000; FY 2027: 1762000; FY 2028: 1762000
U-5785 | HIGHWAY | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | TO BE LET WITH U-5917. | DIVISION 2 |  | T | UTILITIES | 1000000 | FY 2024: 500000; FY 2025: 500000
U-5785 | HIGHWAY | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | TO BE LET WITH U-5917. | DIVISION 2 |  | T | CONSTRUCTION | 20500000 | FY 2026: 205000; FY 2027: 8365000; FY 2028: 7649000; FY 2029: 4281000
U-5786 | HIGHWAY | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGANY | CONSTRUCTION | 22000000 | FY 2028: 2304000; FY 2029: 9400000; FY 2030: 6987000; FY 2031: 3309000
U-5786 | HIGHWAY | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  |  |  | 890000
U-5786 | HIGHWAY | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 5000000 | FY 2026: 762000; FY 2027: 2286000; FY 2028: 952000; FY 2029: 500000; FY 2030: 500000
U-5786 | HIGHWAY | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGANY | UTILITIES | 5100000 | FY 2026: 2550000; FY 2027: 2550000
U-5787 | HIGHWAY | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  |  |  | 800000
U-5787 | HIGHWAY | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | T | RIGHT-OF-WAY | 11700000 | FY 2024: 468000; FY 2025: 4446000; FY 2026: 4446000; FY 2027: 1170000; FY 2028: 1170000
U-5787 | HIGHWAY | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | T | UTILITIES | 1500000 | FY 2024: 1500000
U-5787 | HIGHWAY | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 3 |  | T | CONSTRUCTION | 5900000 | FY 2026: 59000; FY 2027: 3835000; FY 2028: 2006000
U-5788 | HIGHWAY | US 17 BUSINESS (MAIN STREET) | WALL STREET/SHALLOTTE AVENUE. REALIGN INTERSECTION. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  | T | CONSTRUCTION | 1939000
U-5788 | HIGHWAY | US 17 BUSINESS (MAIN STREET) | WALL STREET/SHALLOTTE AVENUE. REALIGN INTERSECTION. | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 1245000
U-5789 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  |  |  | 1983000
U-5789 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION B |  | T | CONSTRUCTION | 4550000 | FY 2025: 1705000; FY 2026: 2740000; FY 2027: 105000
U-5790 | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  |  |  | 1500000
U-5790 | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | RIGHT-OF-WAY | 6064000 | FY 2027: 485000; FY 2028: 2911000; FY 2029: 1456000; FY 2030: 606000; FY 2031: 606000
U-5790 | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | UTILITIES | 6428000 | FY 2027: 3214000; FY 2028: 3214000
U-5790 | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | CONSTRUCTION | 20500000 | FY 2029: 3437000; FY 2030: 8908000; FY 2031: 6225000; FY 2032: 1930000
U-5791 | HIGHWAY | SR 2714 (JACKSONVILLE PARKWAY EXTENSION) | NC 53 (WESTERN BOULEVARD) TO US 17 (NEW BERN HIGHWAY). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  |  |  | 1750000
U-5791A | HIGHWAY | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2026 / YR 8 SALE). | DIVISION 3 |  | T | RIGHT-OF-WAY | 6709000 | FY 2026: 67000; FY 2027: 2233000; FY 2028: 3067000; FY 2029: 671000; FY 2030: 671000
U-5791A | HIGHWAY | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2026 / YR 8 SALE). | DIVISION 3 |  | T | CONSTRUCTION | 28700000 | FY 2028: 0; FY 2029: 3158000; FY 2030: 12771000; FY 2031: 8901000; FY 2032: 3870000
U-5791A | HIGHWAY | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2026 / YR 8 SALE). | DIVISION 3 |  | T | UTILITIES | 1964000 | FY 2026: 982000; FY 2027: 982000
U-5791A | HIGHWAY | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 3 | Jacksonville Urban Area MPO | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2026 / YR 8 SALE). | DIVISION 3 |  | T | BUILD NC CON | 13728000 | FY 2028: 1716000; FY 2029: 858000; FY 2030: 858000; FY 2031: 858000; FY 2032: 858000; FY 2033: 858000 | 7722000
U-5791B | HIGHWAY | SR 2714 | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 7900000 | [11 empty] | 7900000
U-5791B | HIGHWAY | SR 2714 | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 2300000 | [11 empty] | 2300000
U-5791B | HIGHWAY | SR 2714 | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 22600000 | [11 empty] | 22600000
U-5792 | HIGHWAY | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  |  |  | 1500000
U-5792 | HIGHWAY | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | RIGHT-OF-WAY | 22701000 | FY 2025: 3131000; FY 2026: 7515000; FY 2027: 7515000; FY 2028: 2270000; FY 2029: 2270000
U-5792 | HIGHWAY | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | UTILITIES | 8910000 | FY 2025: 4455000; FY 2026: 4455000
U-5792 | HIGHWAY | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | CONSTRUCTION | 106300000 | FY 2027: 1063000; FY 2028: 36142000; FY 2029: 36142000; FY 2030: 24449000; FY 2031: 8504000
U-5793 | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO | [5 empty] | 10000
U-5793A | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6200000
U-5793A | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1600000
U-5793A | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9199000
U-5793B | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40100000
U-5793B | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7100000
U-5793B | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 15600000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 10000 | [11 empty] | 10000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 717000 | [11 empty] | 717000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 73000 | [11 empty] | 73000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 100000 | [11 empty] | 100000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 100000 | [11 empty] | 100000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | UTILITIES | 946000 | [11 empty] | 946000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 3388000 | [11 empty] | 3388000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 4393000 | [11 empty] | 4393000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 1418000 | [11 empty] | 1418000
U-5794 | HIGHWAY | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | 4 | Upper Coastal Plain RPO |  | NOT FUNDED |  |  |  | 750000
U-5796 | HIGHWAY | US 117 | SR 1120 (O'BERRY ROAD) IN GOLDSBORO. CONSTRUCT INTERCHANGE. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 1980000
U-5797 | HIGHWAY | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | T | UTILITIES | 2208000 | FY 2023: 1104000; FY 2024: 1104000
U-5797 | HIGHWAY | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | T | CONSTRUCTION | 29100000 | FY 2024: 291000; FY 2025: 11058000; FY 2026: 9894000; FY 2027: 6984000; FY 2028: 873000
U-5797 | HIGHWAY | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  | T | RIGHT-OF-WAY | 9200000 | FY 2023: 3099000; FY 2024: 4261000; FY 2025: 920000; FY 2026: 920000
U-5797 | HIGHWAY | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6 |  |  |  | 1334000
U-5798 | HIGHWAY | SR 1102 (GILLIS HILL ROAD) | US 401 (RAEFORD ROAD) TO SR 1418 (LINDSAY ROAD). WIDEN TO FOUR LANES. | 6, 8 | Fayetteville Area MPO | COORDINATE WITH U-5753, U-5857, AND U-5858. | DIVISION 6, 8 |  |  |  | 1010000
U-5798A | HIGHWAY | SR 1102 (GILLIS HILL ROAD) | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO FOUR LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | RIGHT-OF-WAY | 9322000 | FY 2023: 459000; FY 2024: 2000000; FY 2025: 3000000
U-5798A | HIGHWAY | SR 1102 (GILLIS HILL ROAD) | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO FOUR LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | UTILITIES | 475000
U-5798A | HIGHWAY | SR 1102 (GILLIS HILL ROAD) | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO FOUR LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | CONSTRUCTION | 26036000 | FY 2023: 11458000; FY 2024: 9111000; FY 2025: 3905000
U-5798B | HIGHWAY | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO FOUR LANES. | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6, 8 |  | T | UTILITIES | 710000 | FY 2023: 710000
U-5798B | HIGHWAY | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO FOUR LANES. | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6, 8 |  | T | CONSTRUCTION | 15500000 | FY 2025: 1860000; FY 2026: 8060000; FY 2027: 5580000
U-5798B | HIGHWAY | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO FOUR LANES. | 6, 8 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 6, 8 |  | T | RIGHT-OF-WAY | 3700000 | FY 2023: 1741000; FY 2024: 1219000; FY 2025: 0; FY 2026: 370000; FY 2027: 370000
U-5799 | HIGHWAY | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | REGION F |  | T | ENGINEERING | 2265000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000 | 151000
U-5799 | HIGHWAY | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | REGION F |  | T | BUILD NC ROW | 60000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
U-5799 | HIGHWAY | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | REGION F |  | T | RIGHT-OF-WAY | 22300000
U-5799 | HIGHWAY | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | REGION F |  | T | UTILITIES | 1600000
U-5799 | HIGHWAY | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | REGION F |  | T | CONSTRUCTION | 20200000 | FY 2024: 202000; FY 2025: 7618000; FY 2026: 7675000; FY 2027: 4705000
U-5799 | HIGHWAY | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | REGION F |  |  |  | 543000
U-5800 | HIGHWAY | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719. | REGION F |  | BGANY | UTILITIES | 3600000 | FY 2024: 1800000; FY 2025: 1800000
U-5800 | HIGHWAY | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719. | REGION F |  | BGANY | CONSTRUCTION | 4400000 | FY 2024: 425000; FY 2025: 3188000; FY 2026: 787000
U-5800 | HIGHWAY | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719. | REGION F |  | BGANY | RIGHT-OF-WAY | 2400000 | FY 2024: 24000; FY 2025: 936000; FY 2026: 960000; FY 2027: 240000; FY 2028: 240000
U-5800 | HIGHWAY | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719. | REGION F |  |  |  | 180000
U-5802 | HIGHWAY | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | 6 | Fayetteville Area MPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 33200000
U-5802 | HIGHWAY | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | 6 | Fayetteville Area MPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4800000
U-5802 | HIGHWAY | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | 6 | Fayetteville Area MPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 25101000
U-5802 | HIGHWAY | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | 6 | Fayetteville Area MPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 2500000
U-5803 | HIGHWAY | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 600000 | FY 2024: 600000
U-5803 | HIGHWAY | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  | T(DA) | CONSTRUCTION | 7819000 | FY 2025: 3910000; FY 2026: 3909000
U-5803 | HIGHWAY | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  | T | CONSTRUCTION | 5600000 | FY 2025: 2800000; FY 2026: 2800000
U-5803 | HIGHWAY | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  | T | RIGHT-OF-WAY | 2400000 | FY 2024: 1200000; FY 2025: 1200000
U-5803 | HIGHWAY | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 4400000 | FY 2025: 2200000; FY 2026: 2200000
U-5803 | HIGHWAY | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  |  |  | 705000
U-5803 | HIGHWAY | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 7819000 | FY 2025: 3910000; FY 2026: 3909000
U-5804 | HIGHWAY | SR 3448 (SOUTH TRADE STREET) | FULLWOOD LANE TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO | [5 empty] | 2223000
U-5804B | HIGHWAY | SR 3448 (SOUTH TRADE STREET) | FOUR MILE CREEK TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO | COMPLETE. BUILD NC BOND FUNDING: $1.134 M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE). | DIVISION 10 |  | T | BUILD NC CON | 1470000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000 | 98000
U-5805 | HIGHWAY | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | BGANY | CONSTRUCTION | 2140000 | FY 2023: 1070000; FY 2024: 1070000
U-5805 | HIGHWAY | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | T | RIGHT-OF-WAY | 750000
U-5805 | HIGHWAY | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  |  |  | 510000
U-5805 | HIGHWAY | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | BGANY | CONSTRUCTION | 4240000 | FY 2023: 2120000; FY 2024: 2120000
U-5805 | HIGHWAY | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 1060000 | FY 2023: 530000; FY 2024: 530000
U-5806 | HIGHWAY | SR 2894 (CONCORD MILLS BOULEVARD) | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 10 |  |  |  | 13096000
U-5806 | HIGHWAY | SR 2894 (CONCORD MILLS BOULEVARD) | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 10 |  | T | ENGINEERING | 1755000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 117000 | 234000
U-5806 | HIGHWAY | SR 2894 (CONCORD MILLS BOULEVARD) | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | 10 | Cabarrus-Rowan MPO | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 10 |  | T | BUILD NC CON | 10380000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 692000 | 1384000
U-5807 | HIGHWAY | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 10 |  | T | RIGHT-OF-WAY | 17700000 | FY 2028: 0; FY 2029: 3607000; FY 2030: 7353000; FY 2031: 3370000; FY 2032: 3370000
U-5807 | HIGHWAY | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 10 |  | T | CONSTRUCTION | 8700000 | FY 2030: 2132000; FY 2031: 4838000; FY 2032: 1730000
U-5807 | HIGHWAY | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 10 |  | T | UTILITIES | 2000000 | FY 2028: 1000000; FY 2029: 1000000
U-5807 | HIGHWAY | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 10 |  | T | BUILD NC CON | 1373000 | FY 2028: 1373000
U-5807 | HIGHWAY | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 10 |  |  |  | 1757000
U-5807 | HIGHWAY | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO | BUILD NC BONDS: $16M FOR RIGHT-OF-WAY, PAYBACK FY 2028-2042 (YR 10 / 2028 SALE) | DIVISION 10 |  | T | BUILD NC ROW | 20595000 | FY 2028: 1373000; FY 2029: 1373000; FY 2030: 1373000; FY 2031: 1373000; FY 2032: 1373000; FY 2033: 1373000 | 12357000
U-5808 | HIGHWAY | SR 1362 (CHESTNUT LANE CONNECTOR) | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 10 |  | T | CONSTRUCTION | 13501000 | FY 2024: 135000; FY 2025: 6152000; FY 2026: 5176000; FY 2027: 2038000
U-5808 | HIGHWAY | SR 1362 (CHESTNUT LANE CONNECTOR) | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 10 |  |  |  | 1185000
U-5808 | HIGHWAY | SR 1362 (CHESTNUT LANE CONNECTOR) | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 10 |  | T | RIGHT-OF-WAY | 1615000
U-5808 | HIGHWAY | SR 1362 (CHESTNUT LANE CONNECTOR) | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 10 |  | T | UTILITIES | 1200000 | FY 2023: 1200000
U-5809 | HIGHWAY | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | DIVISION 11 |  | T | CONSTRUCTION | 11401000 | FY 2024: 4387000; FY 2025: 4823000; FY 2026: 2191000
U-5809 | HIGHWAY | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | DIVISION 11 |  | T | UTILITIES | 800000 | FY 2023: 800000
U-5809 | HIGHWAY | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894. | DIVISION 11 |  |  |  | 2450000
U-5810 | HIGHWAY | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 11 |  |  |  | 883000
U-5810 | HIGHWAY | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 11 |  | T | RIGHT-OF-WAY | 8900000 | FY 2023: 4450000
U-5810 | HIGHWAY | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 11 |  | T | BUILD NC ROW | 4500000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 900000
U-5810 | HIGHWAY | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 11 |  | T | UTILITIES | 1500000
U-5810 | HIGHWAY | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE) | DIVISION 11 |  | T | CONSTRUCTION | 22300000 | FY 2024: 6936000; FY 2025: 8154000; FY 2026: 5591000; FY 2027: 1619000
U-5811 | HIGHWAY | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULT-ILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | RIGHT-OF-WAY | 8420000 | FY 2026: 84000; FY 2027: 4275000; FY 2028: 2377000; FY 2029: 842000; FY 2030: 842000
U-5811 | HIGHWAY | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULT-ILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | UTILITIES | 556000 | FY 2026: 556000
U-5811 | HIGHWAY | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULT-ILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | 5 | Capital Area MPO |  | DIVISION 5 |  |  |  | 2000000
U-5811 | HIGHWAY | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULT-ILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | CONSTRUCTION | 31401000 | FY 2028: 4731000; FY 2029: 12093000; FY 2030: 9199000; FY 2031: 5378000
U-5812 | HIGHWAY | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 150000
U-5812 | HIGHWAY | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 525000
U-5812 | HIGHWAY | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 144000
U-5812 | HIGHWAY | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 600000
U-5812 | HIGHWAY | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 36000
U-5813 | HIGHWAY | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | REGION E |  | NHP | UTILITIES | 399000
U-5813 | HIGHWAY | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | REGION E |  | NHP | CONSTRUCTION | 46299000 | FY 2024: 2419000; FY 2025: 16813000; FY 2026: 14081000; FY 2027: 9882000; FY 2028: 3104000
U-5813 | HIGHWAY | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | REGION E |  |  |  | 3000000
U-5813 | HIGHWAY | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 8 | Piedmont Triad RPO | RIGHT OF WAY IN PROGRESS. | REGION E |  | NHP | RIGHT-OF-WAY | 15934000
U-5814 | HIGHWAY | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5815 | REGION E |  |  |  | 3750000
U-5814 | HIGHWAY | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5815 | REGION E |  | T | RIGHT-OF-WAY | 11500000 | FY 2023: 2500000; FY 2024: 6000000; FY 2025: 3000000
U-5814 | HIGHWAY | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5815 | REGION E |  | T | UTILITIES | 1250000 | FY 2023: 250000; FY 2024: 1000000
U-5814 | HIGHWAY | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5815 | REGION E |  | T | CONSTRUCTION | 24000000 | FY 2025: 4848000; FY 2026: 11571000; FY 2027: 7581000
U-5815 | HIGHWAY | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 8 | Triangle Area RPO | COORDINATE WITH U-5814 | REGION E |  |  |  | 4650000
U-5815A | HIGHWAY | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | 8 | Triangle Area RPO |  | REGION E |  | T | RIGHT-OF-WAY | 700000 | FY 2025: 700000
U-5815A | HIGHWAY | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | 8 | Triangle Area RPO |  | REGION E |  | T | UTILITIES | 1600000 | FY 2025: 800000; FY 2026: 800000
U-5815A | HIGHWAY | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 4401000 | FY 2027: 1301000; FY 2028: 2755000; FY 2029: 345000
U-5815B | HIGHWAY | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | RIGHT-OF-WAY | 6650000 | FY 2023: 3325000; FY 2024: 3325000
U-5815B | HIGHWAY | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | CONSTRUCTION | 37600000 | FY 2025: 6376000; FY 2026: 15399000; FY 2027: 11182000; FY 2028: 4643000
U-5815BA | HIGHWAY | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. RELOCATE WATER TRANSMISSION LINE. | 8 | Triangle Area RPO |  | REGION E |  | T | CONSTRUCTION | 17900000 | FY 2023: 11249000; FY 2024: 6651000
U-5816 | HIGHWAY | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | T | UTILITIES | 3200000 | FY 2026: 1600000; FY 2027: 1600000
U-5816 | HIGHWAY | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | T | CONSTRUCTION | 29601000 | FY 2029: 296000; FY 2030: 10767000; FY 2031: 9753000; FY 2032: 6762000; FY 2033: 2023000
U-5816 | HIGHWAY | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  |  |  | 500000
U-5816 | HIGHWAY | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 12600000 | FY 2026: 796000; FY 2027: 3183000; FY 2028: 3183000; FY 2029: 2918000; FY 2030: 2520000
U-5817 | HIGHWAY | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 2403000
U-5817 | HIGHWAY | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | DIVISION 12 |  |  |  | 4853000
U-5817 | HIGHWAY | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | DIVISION 12 |  | BA | RIGHT-OF-WAY | 2725000
U-5817 | HIGHWAY | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | DIVISION 12 |  | BGANY | RIGHT-OF-WAY | 672000
U-5817 | HIGHWAY | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | DIVISION 12 |  | BGANY | UTILITIES | 1900000
U-5817 | HIGHWAY | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. | DIVISION 12 |  | BGANY | CONSTRUCTION | 17700000 | FY 2025: 177000; FY 2026: 6924000; FY 2027: 6910000; FY 2028: 3689000
U-5818 | HIGHWAY | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | BUILD NC CON | 5505000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000 | 367000
U-5818 | HIGHWAY | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | BUILD NC ROW | 90000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
U-5818 | HIGHWAY | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | ENGINEERING | 150000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 20000
U-5818 | HIGHWAY | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  |  |  | 2536000
U-5818 | HIGHWAY | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | BUILD NC CON | 7725000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 1030000
U-5818 | HIGHWAY | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 13 | Foothills RPO | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | ENGINEERING | 1560000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000
U-5819 | HIGHWAY | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | CONSTRUCTION | 2800000 | FY 2030: 802000; FY 2031: 1998000
U-5819 | HIGHWAY | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | UTILITIES | 600000 | FY 2028: 600000
U-5819 | HIGHWAY | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 200000
U-5819 | HIGHWAY | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 700000 | FY 2028: 700000
U-5820 | HIGHWAY | NEW ROUTE | SR 2576 (BENDIX DRIVE) TO US 52 (EAST INNES STREET) AT NEWSOME ROAD IN SALISBURY. CONSTRUCT A NEW MULTI-LANE ROADWAY. | 9 | Cabarrus-Rowan MPO | FUNDING FOR PART B REFLECTS REIMBURSEMENT TO CITY OF SALISBURY |  |  |  |  | 5151000
U-5820A | HIGHWAY | NEW ROUTE | SR 2576 (BENDIX DRIVE) TO SR 1006 (FAITH ROAD) IN SALISBURY. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.023 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 9 |  | T | BUILD NC CON | 2609000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000 | 174000
U-5820B | HIGHWAY | NEW ROUTE | SR 1006 (FAITH ROAD) TO US 52 (EAST INNES STREET) IN SALISBURY. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | T | CONSTRUCTION | 1100000
U-5821 | HIGHWAY | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  |  |  | 1300000
U-5821 | HIGHWAY | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | T | RIGHT-OF-WAY | 29510000 | FY 2023: 10000; FY 2024: 6984000; FY 2025: 10596000; FY 2026: 5960000; FY 2027: 5960000
U-5821 | HIGHWAY | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | T | BUILD NC ROW | 25740000 |  | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 8580000
U-5821 | HIGHWAY | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | T | UTILITIES | 6010000 | FY 2023: 10000; FY 2024: 3000000; FY 2025: 3000000
U-5821 | HIGHWAY | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 12 | Gaston-Cleveland-Lincoln MPO | BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE), RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | T | CONSTRUCTION | 51700000 | FY 2026: 6512000; FY 2027: 16348000; FY 2028: 14053000; FY 2029: 9970000; FY 2030: 4817000
U-5823 | HIGHWAY | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | DIVISION 5 |  | BGANY | CONSTRUCTION | 3000000 | FY 2025: 3000000
U-5823 | HIGHWAY | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | DIVISION 5 |  | L | UTILITIES | 80000 | FY 2024: 80000
U-5823 | HIGHWAY | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | DIVISION 5 |  | L | RIGHT-OF-WAY | 435000 | FY 2024: 435000
U-5823 | HIGHWAY | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | DIVISION 5 |  | BGANY | RIGHT-OF-WAY | 465000 | FY 2024: 465000
U-5823 | HIGHWAY | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | DIVISION 5 |  |  |  | 595000
U-5823 | HIGHWAY | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | DIVISION 5 |  | L | CONSTRUCTION | 750000 | FY 2025: 750000
U-5823 | HIGHWAY | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 5 | Durham-Chapel Hill-Carrboro MPO | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM | DIVISION 5 |  | BGANY | UTILITIES | 320000 | FY 2024: 320000
U-5824 | HIGHWAY | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 5399000
U-5824 | HIGHWAY | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | RIGHT-OF-WAY | 18798000 | FY 2023: 6266000
U-5824 | HIGHWAY | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO MULTI-LANES. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | CONSTRUCTION | 19900000 | FY 2024: 3673000; FY 2025: 8450000; FY 2026: 5710000; FY 2027: 2067000
U-5825 | HIGHWAY | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 5 | Capital Area MPO | COORDINATE WITH U-6066 | DIVISION 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3000000
U-5825 | HIGHWAY | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 5 | Capital Area MPO | COORDINATE WITH U-6066 | DIVISION 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 63900000
U-5825 | HIGHWAY | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 5 | Capital Area MPO | COORDINATE WITH U-6066 | DIVISION 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 26800000
U-5825 | HIGHWAY | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 5 | Capital Area MPO | COORDINATE WITH U-6066 | DIVISION 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 4700000
U-5826 | HIGHWAY | SR 2000 (FALLS OF NEUSE ROAD) | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  |  |  | 4569000
U-5826 | HIGHWAY | SR 2000 (FALLS OF NEUSE ROAD) | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | T | CONSTRUCTION | 13501000 | FY 2023: 2069000; FY 2024: 8051000; FY 2025: 3381000
U-5827 | HIGHWAY | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 5 |  | T | BUILD NC ROW | 1340000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 89000 | 94000
U-5827 | HIGHWAY | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 5 |  | T | CONSTRUCTION | 712000
U-5827 | HIGHWAY | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 5 |  | T | ENGINEERING | 16000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 3000
U-5827 | HIGHWAY | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 5 |  | T | ENGINEERING | 1215000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000 | 81000
U-5827 | HIGHWAY | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 5 |  |  |  | 54000
U-5827 | HIGHWAY | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 5 |  | T | BUILD NC CON | 6987000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 479000 | 562000
U-5828 | HIGHWAY | MCCRIMMON PARKWAY | SR 3015 (AIRPORT BOULEVARD) TO SR 1002 (AVIATION PARKWAY) IN MORRISVILLE. WIDEN TO A FOUR LANE DIVIDED FACILITY, PART ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 5 |  |  |  | 10935000
U-5828 | HIGHWAY | MCCRIMMON PARKWAY | SR 3015 (AIRPORT BOULEVARD) TO SR 1002 (AVIATION PARKWAY) IN MORRISVILLE. WIDEN TO A FOUR LANE DIVIDED FACILITY, PART ON NEW LOCATION. | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | DIVISION 5 |  | T | BUILD NC CON | 3097000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 206000 | 213000
U-5832 | HIGHWAY | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | T | UTILITIES | 1700000 | FY 2028: 850000; FY 2029: 850000
U-5832 | HIGHWAY | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | T | CONSTRUCTION | 21901000 | FY 2030: 9150000; FY 2031: 3398000; FY 2032: 6905000; FY 2033: 2448000
U-5832 | HIGHWAY | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  | T | RIGHT-OF-WAY | 24400000 | FY 2028: 1952000; FY 2029: 11712000; FY 2030: 5856000; FY 2031: 2440000; FY 2032: 2440000
U-5832 | HIGHWAY | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 |  |  |  | 500000
U-5833 | HIGHWAY | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | ENGINEERING | 975000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000
U-5833 | HIGHWAY | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | ENGINEERING | 75000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 10000
U-5833 | HIGHWAY | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | BUILD NC ROW | 435000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000
U-5833 | HIGHWAY | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | BUILD NC CON | 2805000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000
U-5833 | HIGHWAY | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  | T | BUILD NC CON | 4725000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 630000
U-5833 | HIGHWAY | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | DIVISION 13 |  |  |  | 3114000
U-5834 | HIGHWAY | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | DIVISION 13 |  | T | RIGHT-OF-WAY | 12333000
U-5834 | HIGHWAY | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | DIVISION 13 |  | T | CONSTRUCTION | 7200000 | FY 2024: 0; FY 2025: 4366000; FY 2026: 2834000
U-5834 | HIGHWAY | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | DIVISION 13 |  | T | BUILD NC CON | 7725000 |  | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 2575000
U-5834 | HIGHWAY | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). | DIVISION 13 |  |  |  | 6844000
U-5835 | HIGHWAY | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  |  |  | 415000
U-5835 | HIGHWAY | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 6600000 | FY 2023: 352000; FY 2024: 4224000; FY 2025: 704000; FY 2026: 660000; FY 2027: 660000
U-5835 | HIGHWAY | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | BGANY | UTILITIES | 2000000 | FY 2023: 1000000; FY 2024: 1000000
U-5835 | HIGHWAY | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 13 |  | BGANY | CONSTRUCTION | 14800000 | FY 2025: 2371000; FY 2026: 6435000; FY 2027: 4686000; FY 2028: 1308000
U-5836 | HIGHWAY | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | 13 | Greater Hickory MPO |  | REGION G |  | T | RIGHT-OF-WAY | 3000000 | FY 2027: 497000; FY 2028: 993000; FY 2029: 910000; FY 2030: 300000; FY 2031: 300000
U-5836 | HIGHWAY | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | 13 | Greater Hickory MPO |  | REGION G |  | T | CONSTRUCTION | 7800000 | FY 2029: 78000; FY 2030: 3584000; FY 2031: 3328000; FY 2032: 810000
U-5836 | HIGHWAY | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | 13 | Greater Hickory MPO |  | REGION G |  |  |  | 3571000
U-5837 | HIGHWAY | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9600000
U-5837 | HIGHWAY | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7000000
U-5837 | HIGHWAY | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9100000
U-5837 | HIGHWAY | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 250000
U-5839 | HIGHWAY | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | DIVISION 14 |  | T | BUILD NC ROW | 2790000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000
U-5839 | HIGHWAY | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | DIVISION 14 |  | T | CONSTRUCTION | 24600000 | FY 2024: 243000; FY 2025: 9848000; FY 2026: 8739000; FY 2027: 5770000
U-5839 | HIGHWAY | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | DIVISION 14 |  | T | RIGHT-OF-WAY | 4040000
U-5839 | HIGHWAY | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | DIVISION 14 |  |  |  | 2743000
U-5839 | HIGHWAY | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | DIVISION 14 |  | T | UTILITIES | 750000
U-5839 | HIGHWAY | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888. | DIVISION 14 |  | T | ENGINEERING | 3330000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000 | 222000
U-5840 | HIGHWAY | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | DIVISION 14 |  | T | BUILD NC CON | 4605000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 307000 | 614000
U-5840 | HIGHWAY | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | DIVISION 14 |  |  |  | 5430000
U-5840 | HIGHWAY | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | DIVISION 14 |  | T | ENGINEERING | 1575000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000
U-5840 | HIGHWAY | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | DIVISION 14 |  | T | BUILD NC ROW | 855000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000
U-5840 | HIGHWAY | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 14 | French Broad River MPO | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE). | DIVISION 14 |  | T | BUILD NC CON | 7545000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000
U-5841 | HIGHWAY | FRIENDLY AVENUE | WEST OF GREEN VALLEY ROAD TO LINDELL ROAD IN GREENSBORO. WIDENING AND INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 1050000
U-5841 | HIGHWAY | FRIENDLY AVENUE | WEST OF GREEN VALLEY ROAD TO LINDELL ROAD IN GREENSBORO. WIDENING AND INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  | T | CONSTRUCTION | 1400000 | FY 2023: 14000; FY 2024: 1327000; FY 2025: 59000
U-5842 | HIGHWAY | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 |  |  |  | 100000
U-5842 | HIGHWAY | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 |  | BGANY | RIGHT-OF-WAY | 144000 | FY 2023: 144000
U-5842 | HIGHWAY | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 |  | BGANY | CONSTRUCTION | 600000 | FY 2024: 600000
U-5842 | HIGHWAY | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 |  | L | RIGHT-OF-WAY | 36000 | FY 2023: 36000
U-5842 | HIGHWAY | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 |  | L | CONSTRUCTION | 150000 | FY 2024: 150000
U-5843 | HIGHWAY | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  |  |  | 1032000
U-5843 | HIGHWAY | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | BUILD NC CON | 1383000 | 99000 | 99000 | 99000 | 99000 | 99000 | 99000 |  | 99000 | 99000 | 99000 | 99000 | 195000
U-5843 | HIGHWAY | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | BUILD NC CON | 784000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000 | 56000
U-5843 | HIGHWAY | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | ENGINEERING | 810000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 108000
U-5844 | HIGHWAY | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  |  |  | 1750000
U-5844 | HIGHWAY | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 13300000 | FY 2024: 4092000; FY 2025: 6548000; FY 2026: 1330000; FY 2027: 1330000
U-5844 | HIGHWAY | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | T | UTILITIES | 3400000 | FY 2024: 1700000; FY 2025: 1700000
U-5844 | HIGHWAY | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | T | CONSTRUCTION | 8700000 | FY 2025: 852000; FY 2026: 5449000; FY 2027: 2399000
U-5845 | HIGHWAY | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 10200000 | FY 2028: 604000; FY 2029: 3627000; FY 2030: 3627000; FY 2031: 302000; FY 2032: 2040000
U-5845 | HIGHWAY | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | T | UTILITIES | 1200000 | FY 2028: 600000; FY 2029: 600000
U-5845 | HIGHWAY | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  |  |  | 2500000
U-5845 | HIGHWAY | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 7 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7 |  | T | CONSTRUCTION | 24001000 | FY 2031: 9140000; FY 2032: 9472000; FY 2033: 4444000 | 945000
U-5846 | HIGHWAY | SR 1772 (GREENSBORO STREET) | SR 1780 (ESTES DRIVE) IN CARRBORO. CONSTRUCT ROUNDABOUT. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 3185000
U-5850 | HIGHWAY | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 830000
U-5850 | HIGHWAY | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | RIGHT-OF-WAY | 800000
U-5850 | HIGHWAY | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | UTILITIES | 500000
U-5850 | HIGHWAY | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | CONSTRUCTION | 3000000 | FY 2025: 2173000; FY 2026: 827000
U-5851 | HIGHWAY | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 9400000 | FY 2028: 1367000; FY 2029: 4102000; FY 2030: 2051000; FY 2031: 940000; FY 2032: 940000
U-5851 | HIGHWAY | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | UTILITIES | 997000 | FY 2028: 997000
U-5851 | HIGHWAY | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  |  |  | 650000
U-5851 | HIGHWAY | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | CONSTRUCTION | 11999000 | FY 2030: 2744000; FY 2031: 6414000; FY 2032: 2841000
U-5852 | HIGHWAY | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1140000
U-5852 | HIGHWAY | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 855000
U-5852 | HIGHWAY | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 600000
U-5852 | HIGHWAY | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 11599000
U-5854 | HIGHWAY | SR 1008 (MT. CARMEL CHURCH ROAD) | SR 1913 (BENNETT ROAD) IN CHAPEL HILL. CONSTRUCT ROUNDABOUT AND RELATED SAFETY IMPROVEMENTS. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 2607000
U-5857 | HIGHWAY | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | DIVISION 8 |  |  |  | 800000
U-5857 | HIGHWAY | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | DIVISION 8 |  | T | CONSTRUCTION | 46001000 | FY 2029: 9238000; FY 2030: 15930000; FY 2031: 12365000; FY 2032: 8468000
U-5857 | HIGHWAY | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | DIVISION 8 |  | T | RIGHT-OF-WAY | 18000000 | FY 2027: 11520000; FY 2028: 2880000; FY 2029: 1800000; FY 2030: 1800000
U-5857 | HIGHWAY | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 8 | Fayetteville Area MPO | COORDINATE WITH U-5753 AND U-5798. | DIVISION 8 |  | T | UTILITIES | 5700000 | FY 2027: 2850000; FY 2028: 2850000
U-5860 | HIGHWAY | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 2 | Mid-East RPO |  | DIVISION 2 |  |  |  | 914000
U-5860 | HIGHWAY | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 2 | Mid-East RPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 8900000 | FY 2026: 2191000; FY 2027: 3286000; FY 2028: 1643000; FY 2029: 890000; FY 2030: 890000
U-5860 | HIGHWAY | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 2 | Mid-East RPO |  | DIVISION 2 |  | T | UTILITIES | 2800000 | FY 2026: 1400000; FY 2027: 1400000
U-5860 | HIGHWAY | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 2 | Mid-East RPO |  | DIVISION 2 |  | T | CONSTRUCTION | 11000000 | FY 2028: 2593000; FY 2029: 5735000; FY 2030: 2672000
U-5862 | HIGHWAY | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 3 | Grand Strand Area Transportation Study |  | REGION B |  |  |  | 1000000
U-5862 | HIGHWAY | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 3 | Grand Strand Area Transportation Study |  | REGION B |  | T | CONSTRUCTION | 22000000 | FY 2030: 3604000; FY 2031: 9284000; FY 2032: 6633000; FY 2033: 2479000
U-5862 | HIGHWAY | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 3 | Grand Strand Area Transportation Study |  | REGION B |  | T | RIGHT-OF-WAY | 5240000 | FY 2028: 1006000; FY 2029: 2012000; FY 2030: 1174000; FY 2031: 524000; FY 2032: 524000
U-5862 | HIGHWAY | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 3 | Grand Strand Area Transportation Study |  | REGION B |  | T | UTILITIES | 1840000 | FY 2028: 920000; FY 2029: 920000
U-5863 | HIGHWAY | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  |  |  | 1300000
U-5863 | HIGHWAY | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 4800000 | [11 empty] | 4800000
U-5863 | HIGHWAY | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 4600000 | [11 empty] | 4600000
U-5863 | HIGHWAY | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3 | Wilmington Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 26800000 | [11 empty] | 26800000
U-5864 | HIGHWAY | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 7, 8 | High Point Urban Area MPO |  | DIVISION 7, 8 |  | BGANY | UTILITIES | 5100000 | FY 2026: 2550000; FY 2027: 2550000
U-5864 | HIGHWAY | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 7, 8 | High Point Urban Area MPO |  | DIVISION 7, 8 |  | BGANY | CONSTRUCTION | 23701000 | FY 2029: 6913000; FY 2030: 9343000; FY 2031: 6240000; FY 2032: 1205000
U-5864 | HIGHWAY | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 7, 8 | High Point Urban Area MPO |  | DIVISION 7, 8 |  | BGANY | RIGHT-OF-WAY | 5063000 | FY 2026: 506000; FY 2027: 1079000; FY 2028: 2114000; FY 2029: 352000; FY 2030: 1012000
U-5864 | HIGHWAY | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 7, 8 | High Point Urban Area MPO |  | DIVISION 7, 8 |  |  |  | 3512000
U-5866 | HIGHWAY | NEW ROUTE | US 129 (RODNEY ORR BYPASS) TO ROBINSVILLE HIGH SCHOOL AND MIDDLE SCHOOL. CONSTRUCT NEW ROUTE INCLUDING BRIDGE OVER CHEOAH RIVER. | 14 | Southwestern RPO | UNDER CONSTRUCTION | DIVISION 14 |  |  |  | 6284000
U-5870 | HIGHWAY | SR 1708 (FIRETOWER ROAD) | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  |  |  | 12950000
U-5870 | HIGHWAY | SR 1708 (FIRETOWER ROAD) | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 12616000 | FY 2024: 126000; FY 2025: 4199000; FY 2026: 5767000; FY 2027: 1262000; FY 2028: 1262000
U-5870 | HIGHWAY | SR 1708 (FIRETOWER ROAD) | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | UTILITIES | 1600000 | FY 2024: 800000; FY 2025: 800000
U-5870 | HIGHWAY | SR 1708 (FIRETOWER ROAD) | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | CONSTRUCTION | 28199000 | FY 2026: 282000; FY 2027: 10367000; FY 2028: 9859000; FY 2029: 6492000; FY 2030: 1199000
U-5873 | HIGHWAY | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  |  |  | 1900000
U-5873 | HIGHWAY | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | S(M) | CONSTRUCTION | 683000 | FY 2024: 94000; FY 2025: 515000; FY 2026: 74000
U-5873 | HIGHWAY | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | CONSTRUCTION | 2733000 | FY 2024: 377000; FY 2025: 2061000; FY 2026: 295000
U-5873 | HIGHWAY | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | BA | ENGINEERING | 100000
U-5873 | HIGHWAY | CORNELIUS NC 115 | POTTS STREET. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | BA | RIGHT-OF-WAY | 1700000
U-5874 | HIGHWAY | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  |  |  | 1829000
U-5874 | HIGHWAY | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BGANY | CONSTRUCTION | 7096000 | FY 2023: 3548000
U-5874 | HIGHWAY | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 1673000
U-5874 | HIGHWAY | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BGDA | CONSTRUCTION | 8887000 | FY 2023: 6820000
U-5874 | HIGHWAY | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | RIGHT-OF-WAY | 1673000
U-5874 | HIGHWAY | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | CONSTRUCTION | 2222000 | FY 2023: 1188000
U-5874 | HIGHWAY | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | CONSTRUCTION | 1774000
U-5874 | HIGHWAY | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | O | CONSTRUCTION | 11442000
U-5875 | HIGHWAY | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  |  |  | 5063000
U-5875 | HIGHWAY | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO FOUR LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 2 |  | T | CONSTRUCTION | 40100000 | FY 2024: 8822000; FY 2025: 16040000; FY 2026: 10827000; FY 2027: 4411000
U-5876 | HIGHWAY | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | 2 | Down East RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 85201000
U-5876 | HIGHWAY | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | 2 | Down East RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 7000000
U-5876 | HIGHWAY | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | 2 | Down East RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 10800000
U-5876 | HIGHWAY | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | 2 | Down East RPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1300000
U-5878 | HIGHWAY | COMMERCE DRIVE EXTENSION | COMMERCE DRIVE TO SR 1406 (PINEY GREEN ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | T | CONSTRUCTION | 3417000 | FY 2023: 2609000; FY 2024: 99000
U-5878 | HIGHWAY | COMMERCE DRIVE EXTENSION | COMMERCE DRIVE TO SR 1406 (PINEY GREEN ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 2225000
U-5881 | HIGHWAY | NC 132 (COLLEGE ROAD) | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1000000
U-5881 | HIGHWAY | NC 132 (COLLEGE ROAD) | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3081000
U-5881 | HIGHWAY | NC 132 (COLLEGE ROAD) | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1912000
U-5881 | HIGHWAY | NC 132 (COLLEGE ROAD) | SOUTH OF SR 1272 (NEW CENTRE DRIVE) TO US 17 BUSINESS (MARKET STREET). UPGRADE ROADWAY. | 3 | Wilmington Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 33800000
U-5886 | HIGHWAY | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | DIVISION 14 |  |  |  | 1470000
U-5886 | HIGHWAY | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | DIVISION 14 |  | T | CONSTRUCTION | 15200000 | FY 2026: 3162000; FY 2027: 6666000; FY 2028: 4352000; FY 2029: 1020000
U-5886 | HIGHWAY | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | DIVISION 14 |  | T | RIGHT-OF-WAY | 18700000 | FY 2023: 1448000; FY 2024: 5791000; FY 2025: 5791000; FY 2026: 1930000; FY 2027: 3740000
U-5886 | HIGHWAY | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049. | DIVISION 14 |  | T | UTILITIES | 2600000 | FY 2023: 1300000; FY 2024: 1300000
U-5887 | HIGHWAY | SR 1783 (HIGHLAND LAKE ROAD) | NC 225 TO US 176. UPGRADE ROADWAY. | 14 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 14 |  |  |  | 810000
U-5887 | HIGHWAY | SR 1783 (HIGHLAND LAKE ROAD) | NC 225 TO US 176. UPGRADE ROADWAY. | 14 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 14 |  | T | RIGHT-OF-WAY | 2295000
U-5887 | HIGHWAY | SR 1783 (HIGHLAND LAKE ROAD) | NC 225 TO US 176. UPGRADE ROADWAY. | 14 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 14 |  | T | CONSTRUCTION | 7676000 | FY 2023: 2732000
U-5888 | HIGHWAY | US 23 BUSINESS | INTERSECTION OF US 23 BUSINESS (NORTH MAIN STREET) AND WALNUT STREET. CONSTRUCT INTERSECTION IMPROVEMENTS. | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH U-5839. | DIVISION 14 |  | T | CONSTRUCTION | 7022000 | FY 2023: 3882000; FY 2024: 1505000
U-5888 | HIGHWAY | US 23 BUSINESS | INTERSECTION OF US 23 BUSINESS (NORTH MAIN STREET) AND WALNUT STREET. CONSTRUCT INTERSECTION IMPROVEMENTS. | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH U-5839. | DIVISION 14 |  |  |  | 1411000
U-5889 | HIGHWAY | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | CONSTRUCTION | 7300000 | FY 2028: 7300000
U-5889 | HIGHWAY | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | UTILITIES | 500000 | FY 2026: 500000
U-5889 | HIGHWAY | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | RIGHT-OF-WAY | 1200000 | FY 2026: 1200000
U-5889 | HIGHWAY | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 5 | Capital Area MPO |  | DIVISION 5 |  |  |  | 10000
U-5890 | HIGHWAY | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 5 | Kerr-Tar RPO |  | DIVISION 5 |  |  |  | 1000000
U-5890 | HIGHWAY | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 5 | Kerr-Tar RPO |  | DIVISION 5 |  | T | RIGHT-OF-WAY | 41300000 | FY 2026: 9440000; FY 2027: 18880000; FY 2028: 4720000; FY 2029: 4130000; FY 2030: 4130000
U-5890 | HIGHWAY | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 5 | Kerr-Tar RPO |  | DIVISION 5 |  | T | UTILITIES | 7300000 | FY 2026: 3650000; FY 2027: 3650000
U-5890 | HIGHWAY | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 5 | Kerr-Tar RPO |  | DIVISION 5 |  | T | CONSTRUCTION | 16801000 | FY 2028: 4234000; FY 2029: 7539000; FY 2030: 5028000
U-5891 | HIGHWAY | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 56401000
U-5891 | HIGHWAY | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1700000
U-5891 | HIGHWAY | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 300000
U-5891 | HIGHWAY | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5 | Capital Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 66001000
U-5892 | HIGHWAY | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | REGION D |  |  |  | 2350000
U-5892 | HIGHWAY | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | REGION D |  | NHP | RIGHT-OF-WAY | 7531000 | FY 2023: 25000; FY 2024: 2524000; FY 2025: 2781000; FY 2026: 695000; FY 2027: 753000; FY 2028: 753000
U-5892 | HIGHWAY | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | REGION D |  | NHP | UTILITIES | 1472000 | FY 2023: 736000; FY 2024: 736000
U-5892 | HIGHWAY | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 7 | Greensboro Urban Area MPO |  | REGION D |  | NHP | CONSTRUCTION | 12400000 | FY 2026: 5401000; FY 2027: 5211000; FY 2028: 1788000
U-5893 | HIGHWAY | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 7 | Piedmont Triad RPO |  | REGION D |  |  |  | 645000
U-5893 | HIGHWAY | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 7 | Piedmont Triad RPO |  | REGION D |  | BG5T50 | CONSTRUCTION | 12199000 | FY 2026: 3745000; FY 2027: 6213000; FY 2028: 2241000
U-5893 | HIGHWAY | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 7 | Piedmont Triad RPO |  | REGION D |  | BG5T50 | UTILITIES | 717000 | FY 2024: 717000
U-5893 | HIGHWAY | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 7 | Piedmont Triad RPO |  | REGION D |  | BG5T50 | RIGHT-OF-WAY | 1643000 | FY 2024: 6000; FY 2025: 620000; FY 2026: 689000; FY 2027: 164000; FY 2028: 164000
U-5896 | HIGHWAY | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 7 |  |  |  | 3138000
U-5896 | HIGHWAY | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 7 |  | T | ENGINEERING | 1820000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000
U-5896 | HIGHWAY | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 7 |  | T | BUILD NC ROW | 8834000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000 | 631000
U-5896 | HIGHWAY | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) | DIVISION 7 |  | T | CONSTRUCTION | 15400000 | FY 2023: 8466000; FY 2024: 3946000; FY 2025: 945000
U-5899 | HIGHWAY | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | RIGHT-OF-WAY | 4300000 | FY 2023: 3655000
U-5899 | HIGHWAY | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | UTILITIES | 1300000 | FY 2023: 1105000
U-5899 | HIGHWAY | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 2730000
U-5899 | HIGHWAY | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | CONSTRUCTION | 9001000 | FY 2024: 90000; FY 2025: 4285000; FY 2026: 3716000; FY 2027: 910000
U-5901 | HIGHWAY | NEW ROUTE | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTI-LANE RIGHT OF WAY. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  |  |  | 1000000
U-5901 | HIGHWAY | NEW ROUTE | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTI-LANE RIGHT OF WAY. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | T | RIGHT-OF-WAY | 8900000 | FY 2027: 445000; FY 2028: 2670000; FY 2029: 2670000; FY 2030: 1335000; FY 2031: 1780000
U-5901 | HIGHWAY | NEW ROUTE | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTI-LANE RIGHT OF WAY. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | T | UTILITIES | 6900000 | FY 2027: 3450000; FY 2028: 3450000
U-5901 | HIGHWAY | NEW ROUTE | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTI-LANE RIGHT OF WAY. | 9 | Cabarrus-Rowan MPO |  | DIVISION 9 |  | T | CONSTRUCTION | 39502000 | FY 2030: 5506000; FY 2031: 14059000; FY 2032: 11112000; FY 2033: 7702000 | 1123000
U-5903 | HIGHWAY | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | T | RIGHT-OF-WAY | 7400000 | FY 2028: 1822000; FY 2029: 2732000; FY 2030: 1366000; FY 2031: 740000; FY 2032: 740000
U-5903 | HIGHWAY | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | T | UTILITIES | 4400000 | FY 2028: 2200000; FY 2029: 2200000
U-5903 | HIGHWAY | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | T | CONSTRUCTION | 43600000 | FY 2030: 5984000; FY 2031: 15454000; FY 2032: 12559000; FY 2033: 8659000 | 944000
U-5903 | HIGHWAY | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  |  |  | 1000000
U-5905 | HIGHWAY | SR 2112 (LAKEVIEW ROAD) | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | 10 | Charlotte Regional TPO | SEGMENTS A AND B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. |  |  |  |  | 3000000
U-5905A | HIGHWAY | SR 2112 (LAKEVIEW ROAD) | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 10 |  | BA | CONSTRUCTION | 8506000
U-5905A | HIGHWAY | SR 2112 (LAKEVIEW ROAD) | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 10 |  | BGDA | CONSTRUCTION | 155000
U-5905B | HIGHWAY | SR 2112 (LAKEVIEW ROAD) | IMPROVE INTERSECTIONS OF SR 2112 (LAKEVIEW ROAD)/NC 24 (HARRIS BOULEVARD) AND SR 2112 (LAKEVIEW ROAD)/US 21 (STATESVILLE ROAD). | 10 | Charlotte Regional TPO |  | EXEMPT |  | BA | CONSTRUCTION | 3000000
U-5905B | HIGHWAY | SR 2112 (LAKEVIEW ROAD) | IMPROVE INTERSECTIONS OF SR 2112 (LAKEVIEW ROAD)/NC 24 (HARRIS BOULEVARD) AND SR 2112 (LAKEVIEW ROAD)/US 21 (STATESVILLE ROAD). | 10 | Charlotte Regional TPO |  | EXEMPT |  | BGDA | CONSTRUCTION | 162000
U-5906 | HIGHWAY | CHAPEL ROAD) CORNELIUS SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE). INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  |  |  | 3001000
U-5906 | HIGHWAY | CHAPEL ROAD) CORNELIUS SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE). INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | BA | ENGINEERING | 949000
U-5906 | HIGHWAY | CHAPEL ROAD) CORNELIUS SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE). INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | T(DA) | CONSTRUCTION | 3741000 | FY 2024: 577000; FY 2025: 1994000; FY 2026: 1009000; FY 2027: 161000
U-5906 | HIGHWAY | CHAPEL ROAD) CORNELIUS SR 2195 (TORRENCE | SR 5544 (WEST CATAWBA AVENUE). INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | BA | RIGHT-OF-WAY | 9153000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | T(DA) | CONSTRUCTION | 3779000 | FY 2024: 3779000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | T(DA) | RIGHT-OF-WAY | 500000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BGDA | CONSTRUCTION | 2117000 | FY 2027: 2117000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | CONSTRUCTION | 529000 | FY 2027: 529000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | RIGHT-OF-WAY | 207000 | FY 2025: 207000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | ENGINEERING | 25000 | FY 2023: 25000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BGDA | ENGINEERING | 100000 | FY 2023: 100000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BA | CONSTRUCTION | 1064000 | FY 2024: 1064000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BA | RIGHT-OF-WAY | 548000 | FY 2023: 548000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  |  |  | 1650000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BA | ENGINEERING | 419000 | FY 2023: 150000
U-5907 | HIGHWAY | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 828000 | FY 2025: 828000
U-5908 | HIGHWAY | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; SEGMENTS A & B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADD'L FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. BGANY USED AS PART OF FUND SWAP. |  |  |  |  | 3050000
U-5908A | HIGHWAY | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGANY | RIGHT-OF-WAY | 660000
U-5908A | HIGHWAY | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | CONSTRUCTION | 29000
U-5908A | HIGHWAY | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | CONSTRUCTION | 1832000
U-5908A | HIGHWAY | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | L | RIGHT-OF-WAY | 165000
U-5908A | HIGHWAY | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGANY | CONSTRUCTION | 2748000
U-5908A | HIGHWAY | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | DIVISION 10 |  | BGDA | CONSTRUCTION | 44000
U-5908B | HIGHWAY | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 1355000
U-5908B | HIGHWAY | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | BGANY | CONSTRUCTION | 2032000
U-5908B | HIGHWAY | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 2327000
U-5908B | HIGHWAY | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | BGDA | CONSTRUCTION | 3490000
U-5908B | HIGHWAY | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | BGANY | RIGHT-OF-WAY | 660000
U-5908B | HIGHWAY | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | EXEMPT |  | L | RIGHT-OF-WAY | 165000
U-5910 | HIGHWAY | VARIOUS | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 3 | Grand Strand Area Transportation Study | IN PROGRESS | DIVISION 3 |  |  |  | 26000
U-5910 | HIGHWAY | VARIOUS | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 3 | Grand Strand Area Transportation Study | IN PROGRESS | DIVISION 3 |  | BGDA | PLANNING | 212000 | FY 2023: 212000
U-5910 | HIGHWAY | VARIOUS | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | 3 | Grand Strand Area Transportation Study | IN PROGRESS | DIVISION 3 |  | L | PLANNING | 78000 | FY 2023: 78000
U-5911 | HIGHWAY | NC 48 | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. INTERSECTION IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  |  |  | 50000
U-5911 | HIGHWAY | NC 48 | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. INTERSECTION IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 69000 | FY 2025: 69000
U-5911 | HIGHWAY | NC 48 | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. INTERSECTION IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | T | UTILITIES | 2136000 | FY 2025: 1068000; FY 2026: 1068000
U-5911 | HIGHWAY | NC 48 | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. INTERSECTION IMPROVEMENTS. | 4 | Rocky Mount Urban Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 5625000 | FY 2027: 1977000; FY 2028: 3343000; FY 2029: 305000
U-5914 | HIGHWAY | NC 133 | US 17/US 74/US 76 TO SR 1554 (OLD RIVER ROAD). MODERNIZE ROADWAY. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  |  |  | 140000
U-5914 | HIGHWAY | NC 133 | US 17/US 74/US 76 TO SR 1554 (OLD RIVER ROAD). MODERNIZE ROADWAY. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | T | CONSTRUCTION | 2428000 | FY 2023: 2234000; FY 2024: 194000
U-5917 | HIGHWAY | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5785. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 2 |  | T | CONSTRUCTION | 14902000 | FY 2026: 149000; FY 2027: 6814000; FY 2028: 5791000; FY 2029: 2148000
U-5917 | HIGHWAY | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5785. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 2 |  | T | UTILITIES | 2772000 | FY 2024: 1386000; FY 2025: 1386000
U-5917 | HIGHWAY | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5785. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 2 |  |  |  | 5897000
U-5917 | HIGHWAY | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5785. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 2 |  | T | ENGINEERING | 1740000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000 | 116000
U-5917 | HIGHWAY | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5785. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | DIVISION 2 |  | T | BUILD NC ROW | 952000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 68000
U-5924 | HIGHWAY | VARIOUS | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. | 11, 12, 13 | Greater Hickory MPO |  | DIVISION 11, 12, 13 |  |  |  | 125000
U-5924 | HIGHWAY | VARIOUS | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. | 11, 12, 13 | Greater Hickory MPO |  | DIVISION 11, 12, 13 |  | BGDA | PLANNING | 1400000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
U-5924 | HIGHWAY | VARIOUS | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. | 11, 12, 13 | Greater Hickory MPO |  | DIVISION 11, 12, 13 |  | L | PLANNING | 350000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
U-5925 | HIGHWAY | SR 1340 (PROSPECT STREET/ NORTH ODUM ROAD) | SR 1566 (CORINTH ROAD) TO NC 711 (THIRD STREET). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | DIVISION 6 |  |  |  | 8596000
U-5926 | HIGHWAY | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | DIVISION 3 |  |  |  | 3410000
U-5926 | HIGHWAY | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | DIVISION 3 |  | T | UTILITIES | 172000 | FY 2024: 172000
U-5926 | HIGHWAY | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | DIVISION 3 |  | T | RIGHT-OF-WAY | 703000 | FY 2024: 176000; FY 2025: 351000; FY 2026: 176000
U-5926 | HIGHWAY | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | DIVISION 3 |  | L | RIGHT-OF-WAY | 703000 | FY 2024: 176000; FY 2025: 351000; FY 2026: 176000
U-5926 | HIGHWAY | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 3 | Wilmington Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434. | DIVISION 3 |  | L | UTILITIES | 172000 | FY 2024: 172000
U-5928 | HIGHWAY | APEX PEAKWAY | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | CONSTRUCTION | 10000000 | FY 2023: 10000000
U-5928 | HIGHWAY | APEX PEAKWAY | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGDA | CONSTRUCTION | 2500000 | FY 2023: 2500000
U-5928 | HIGHWAY | APEX PEAKWAY | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | 5 | Capital Area MPO |  | DIVISION 5 |  | L | CONSTRUCTION | 12500000 | FY 2023: 12500000
U-5929 | HIGHWAY | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7200000
U-5929 | HIGHWAY | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2000000
U-5929 | HIGHWAY | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6500000
U-5929 | HIGHWAY | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | TO BE LET WITH U-2567 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-5930 | HIGHWAY | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | 6 | Fayetteville Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-5930 | HIGHWAY | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | 6 | Fayetteville Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 22400000
U-5930 | HIGHWAY | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | 6 | Fayetteville Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7500000
U-5930 | HIGHWAY | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | 6 | Fayetteville Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 67500000
U-5931 | HIGHWAY | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 1099000 | FY 2025: 24000; FY 2026: 285000; FY 2027: 285000; FY 2028: 285000; FY 2029: 220000
U-5931 | HIGHWAY | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | STATEWIDE MOBILITY |  | T | UTILITIES | 1000000 | FY 2025: 500000; FY 2026: 500000
U-5931 | HIGHWAY | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | STATEWIDE MOBILITY |  |  |  | 3500000
U-5931 | HIGHWAY | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764. | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 4600000 | FY 2028: 46000; FY 2029: 3143000; FY 2030: 1411000
U-5932 | HIGHWAY | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1300000
U-5932 | HIGHWAY | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 38989000
U-5932 | HIGHWAY | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1920000
U-5932 | HIGHWAY | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | 3 | Cape Fear RPO, Grand Strand Area Transportation Study |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 36102000
U-5933 | HIGHWAY | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | S(M) | CONSTRUCTION | 708000 | FY 2023: 404000; FY 2024: 304000
U-5933 | HIGHWAY | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 17000 | FY 2023: 17000
U-5933 | HIGHWAY | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | T | UTILITIES | 23000 | FY 2023: 23000
U-5933 | HIGHWAY | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  |  |  | 700000
U-5933 | HIGHWAY | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGDA | CONSTRUCTION | 979000 | FY 2023: 558000; FY 2024: 421000
U-5933 | HIGHWAY | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | BGDACV | CONSTRUCTION | 1853000 | FY 2023: 1056000; FY 2024: 797000
U-5934 | HIGHWAY | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  |  |  | 300000
U-5934 | HIGHWAY | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 100000 | FY 2028: 100000
U-5934 | HIGHWAY | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | UTILITIES | 300000 | FY 2028: 300000
U-5934 | HIGHWAY | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 142301000 | FY 2029: 32139000; FY 2030: 36160000; FY 2031: 31018000; FY 2032: 23953000; FY 2033: 19031000
U-5936 | HIGHWAY | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-5936 | HIGHWAY | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 900000
U-5936 | HIGHWAY | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1300000
U-5936 | HIGHWAY | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | 5 | Capital Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 74499000
U-5937 | HIGHWAY | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 7750000
U-5937 | HIGHWAY | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 64300000
U-5937 | HIGHWAY | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9300000
U-5937 | HIGHWAY | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 200000
U-5939 | HIGHWAY | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 1 | Albemarle RPO |  | REGION A |  | BG5T50 | RIGHT-OF-WAY | 2808000 | FY 2024: 1057000; FY 2025: 1189000; FY 2026: 281000; FY 2027: 281000
U-5939 | HIGHWAY | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 1 | Albemarle RPO |  | REGION A |  | BG5T50 | UTILITIES | 299000 | FY 2024: 299000
U-5939 | HIGHWAY | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 1 | Albemarle RPO |  | REGION A |  | BG5T50 | CONSTRUCTION | 9100000 | FY 2025: 91000; FY 2026: 4466000; FY 2027: 3675000; FY 2028: 868000
U-5939 | HIGHWAY | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 1 | Albemarle RPO |  | REGION A |  |  |  | 500000
U-5940 | HIGHWAY | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1 | Albemarle RPO |  | REGION A |  | T | RIGHT-OF-WAY | 15989000 | FY 2025: 160000; FY 2026: 5322000; FY 2027: 7309000; FY 2028: 1599000; FY 2029: 1599000
U-5940 | HIGHWAY | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1 | Albemarle RPO |  | REGION A |  | T | UTILITIES | 476000 | FY 2025: 476000
U-5940 | HIGHWAY | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1 | Albemarle RPO |  | REGION A |  |  |  | 2000000
U-5940 | HIGHWAY | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1 | Albemarle RPO |  | REGION A |  | T | CONSTRUCTION | 12900000 | FY 2027: 129000; FY 2028: 5669000; FY 2029: 4713000; FY 2030: 2389000
U-5941 | HIGHWAY | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | REGION A |  |  |  | 50000
U-5941 | HIGHWAY | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | REGION A |  | BG5T50 | RIGHT-OF-WAY | 12100000 | FY 2026: 2420000; FY 2027: 5808000; FY 2028: 1452000; FY 2029: 1210000; FY 2030: 1210000
U-5941 | HIGHWAY | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | REGION A |  | BG5T50 | UTILITIES | 3900000 | FY 2026: 1950000; FY 2027: 1950000
U-5941 | HIGHWAY | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 4 | Upper Coastal Plain RPO |  | REGION A |  | BG5T50 | CONSTRUCTION | 11000000 | FY 2028: 2323000; FY 2029: 5901000; FY 2030: 2776000
U-5942 | HIGHWAY | ELIZABETH CITY | ELIZABETH CITY SIGNAL SYSTEM. | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | REGION A |  | BG5200 | CONSTRUCTION | 4997000 | FY 2023: 494000
U-5942 | HIGHWAY | ELIZABETH CITY | ELIZABETH CITY SIGNAL SYSTEM. | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | REGION A |  | HP | CONSTRUCTION | 62000 | FY 2023: 6000
U-5942 | HIGHWAY | ELIZABETH CITY | ELIZABETH CITY SIGNAL SYSTEM. | 1 | Albemarle RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368. | REGION A |  |  |  | 540000
U-5943 | HIGHWAY | CLAYTON | CLAYTON SIGNAL SYSTEM. | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  |  |  | 328000
U-5943 | HIGHWAY | CLAYTON | CLAYTON SIGNAL SYSTEM. | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | BGANY | RIGHT-OF-WAY | 10000 | FY 2023: 10000
U-5943 | HIGHWAY | CLAYTON | CLAYTON SIGNAL SYSTEM. | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | BGANY | UTILITIES | 260000 | FY 2023: 260000
U-5943 | HIGHWAY | CLAYTON | CLAYTON SIGNAL SYSTEM. | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | REGION A |  | BGANY | CONSTRUCTION | 4500000 | FY 2025: 2070000; FY 2026: 2430000
U-5945 | HIGHWAY | WILSON | WILSON CITY SIGNAL SYSTEM. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 10000
U-5945 | HIGHWAY | WILSON | WILSON CITY SIGNAL SYSTEM. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BG5200 | UTILITIES | 700000 | FY 2024: 700000
U-5945 | HIGHWAY | WILSON | WILSON CITY SIGNAL SYSTEM. | 4 | Upper Coastal Plain RPO |  | DIVISION 4 |  | BG5200 | CONSTRUCTION | 6600000 | FY 2025: 2904000; FY 2026: 3168000; FY 2027: 528000
U-5947 | HIGHWAY | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  |  |  | 51000
U-5947 | HIGHWAY | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | T | RIGHT-OF-WAY | 80000
U-5947 | HIGHWAY | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | T | UTILITIES | 800000
U-5947 | HIGHWAY | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | REGION A |  | T | CONSTRUCTION | 4600000 | FY 2023: 3408000; FY 2024: 1146000
U-5949 | HIGHWAY | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | RIGHT-OF-WAY | 8344000 | FY 2028: 1391000; FY 2029: 3338000; FY 2030: 1947000; FY 2031: 834000; FY 2032: 834000
U-5949 | HIGHWAY | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | UTILITIES | 17594000 | FY 2028: 8797000; FY 2029: 8797000
U-5949 | HIGHWAY | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 3 | Jacksonville Urban Area MPO |  | REGION B |  |  |  | 1150000
U-5949 | HIGHWAY | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | CONSTRUCTION | 69901000 | FY 2032: 8577000; FY 2033: 21736000 | 39588000
U-5950 | HIGHWAY | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | REGION B |  |  |  | 500000
U-5950 | HIGHWAY | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | BG5200 | RIGHT-OF-WAY | 75000 | FY 2025: 75000
U-5950 | HIGHWAY | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | BG5200 | UTILITIES | 154000 | FY 2025: 154000
U-5950 | HIGHWAY | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | BG5200 | CONSTRUCTION | 825000 | FY 2027: 8000; FY 2028: 817000
U-5951 | HIGHWAY | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  |  |  | 1350000
U-5951 | HIGHWAY | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | RIGHT-OF-WAY | 400000 | FY 2026: 400000
U-5951 | HIGHWAY | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | UTILITIES | 69000 | FY 2026: 69000
U-5951 | HIGHWAY | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 3 | Jacksonville Urban Area MPO |  | REGION B |  | T | CONSTRUCTION | 14200000 | FY 2028: 2711000; FY 2029: 6940000; FY 2030: 4549000
U-5952 | HIGHWAY | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | 2 | Greenville Urban Area MPO |  | REGION B |  |  |  | 1610000
U-5952 | HIGHWAY | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | 2 | Greenville Urban Area MPO |  | REGION B |  | BG5200 | CONSTRUCTION | 12000000 | FY 2028: 4999000; FY 2029: 5291000; FY 2030: 1710000
U-5952 | HIGHWAY | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | 2 | Greenville Urban Area MPO |  | REGION B |  | BG5200 | UTILITIES | 750000 | FY 2026: 750000
U-5954 | HIGHWAY | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 3 | Wilmington Urban Area MPO |  | REGION B |  | BGLT5 | UTILITIES | 507000 | FY 2025: 507000
U-5954 | HIGHWAY | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 3 | Wilmington Urban Area MPO |  | REGION B |  | BGLT5 | CONSTRUCTION | 3800000 | FY 2027: 38000; FY 2028: 2776000; FY 2029: 986000
U-5954 | HIGHWAY | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 3 | Wilmington Urban Area MPO |  | REGION B |  |  |  | 500000
U-5954 | HIGHWAY | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 3 | Wilmington Urban Area MPO |  | REGION B |  | BGLT5 | RIGHT-OF-WAY | 721000 | FY 2025: 721000
U-5955 | HIGHWAY | NC 16 (BROOKSHIRE BOULEVARD) |  | 10 | Charlotte Regional TPO |  | REGION E |  |  |  | 1095000
U-5955A | HIGHWAY | NC 16 (BROOKSHIRE BOULEVARD) | IMPROVE I-85 NORTHBOUND RAMP TO EASTBOUND NC 16. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | REGION E |  | T | CONSTRUCTION | 2100000 | FY 2023: 950000; FY 2024: 1150000
U-5955B | HIGHWAY | NC 16 (BROOKSHIRE BOULEVARD) | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. CONVERT NC 16 AND IDAHO DRIVE INTERSECTION TO AN INTERCHANGE. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 4300000 | FY 2025: 43000; FY 2026: 969000; FY 2027: 1214000; FY 2028: 1214000; FY 2029: 860000
U-5955B | HIGHWAY | NC 16 (BROOKSHIRE BOULEVARD) | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. CONVERT NC 16 AND IDAHO DRIVE INTERSECTION TO AN INTERCHANGE. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 345000 | FY 2025: 345000
U-5955B | HIGHWAY | NC 16 (BROOKSHIRE BOULEVARD) | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. CONVERT NC 16 AND IDAHO DRIVE INTERSECTION TO AN INTERCHANGE. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 12699000 | FY 2028: 127000; FY 2029: 6210000; FY 2030: 4833000; FY 2031: 1529000
U-5956 | HIGHWAY | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  |  |  | 450000
U-5956 | HIGHWAY | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | RIGHT-OF-WAY | 3400000
U-5956 | HIGHWAY | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | UTILITIES | 2100000 | FY 2023: 1050000
U-5956 | HIGHWAY | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | REGION E |  | T | CONSTRUCTION | 11800000 | FY 2025: 1589000; FY 2026: 6345000; FY 2027: 3299000; FY 2028: 567000
U-5957 | HIGHWAY | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | UTILITIES | 500000 | FY 2026: 500000
U-5957 | HIGHWAY | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | CONSTRUCTION | 17900000 | FY 2029: 3382000; FY 2030: 8465000; FY 2031: 4609000; FY 2032: 1444000
U-5957 | HIGHWAY | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | T | RIGHT-OF-WAY | 13100000 | FY 2026: 2620000; FY 2027: 5240000; FY 2028: 2620000; FY 2029: 1310000; FY 2030: 1310000
U-5957 | HIGHWAY | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  |  |  | 1920000
U-5959 | HIGHWAY | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9400000
U-5959 | HIGHWAY | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1300000
U-5959 | HIGHWAY | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5999000
U-5959 | HIGHWAY | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 153000
U-5960 | HIGHWAY | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 18700000
U-5960 | HIGHWAY | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3800000
U-5960 | HIGHWAY | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 400000
U-5960 | HIGHWAY | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 27000000
U-5961 | HIGHWAY | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | REGION F |  | BG50200 | RIGHT-OF-WAY | 13400000 | FY 2024: 1072000; FY 2025: 3216000; FY 2026: 3216000; FY 2027: 3216000; FY 2028: 2680000
U-5961 | HIGHWAY | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | REGION F |  | BG50200 | UTILITIES | 3700000 | FY 2024: 1850000; FY 2025: 1850000
U-5961 | HIGHWAY | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | REGION F |  | BG50200 | CONSTRUCTION | 6400000 | FY 2027: 1923000; FY 2028: 3182000; FY 2029: 1295000
U-5961 | HIGHWAY | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 12 | Gaston-Cleveland-Lincoln MPO | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA | REGION F |  | O | CONSTRUCTION | 5000000 | FY 2027: 1502000; FY 2028: 2486000; FY 2029: 1012000
U-5962 | HIGHWAY | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | REGION F |  | T | UTILITIES | 300000 | FY 2024: 300000
U-5962 | HIGHWAY | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | REGION F |  | T | CONSTRUCTION | 3912000 | FY 2026: 39000; FY 2027: 2443000; FY 2028: 1430000
U-5962 | HIGHWAY | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | REGION F |  |  |  | 700000
U-5962 | HIGHWAY | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | REGION F |  | O | CONSTRUCTION | 288000 | FY 2026: 3000; FY 2027: 180000; FY 2028: 105000
U-5962 | HIGHWAY | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 12 | Gaston-Cleveland-Lincoln MPO | OTHER FUNDING PROVIDED BY LINCOLN COUNTY | REGION F |  | T | RIGHT-OF-WAY | 3300000 | FY 2024: 33000; FY 2025: 1098000; FY 2026: 1509000; FY 2027: 330000; FY 2028: 330000
U-5964 | HIGHWAY | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 12 | Charlotte Regional TPO |  | REGION F |  |  |  | 150000
U-5964 | HIGHWAY | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 12 | Charlotte Regional TPO |  | REGION F |  | BGANY | RIGHT-OF-WAY | 11000000 | FY 2024: 2200000; FY 2025: 4400000; FY 2026: 2200000; FY 2027: 1100000; FY 2028: 1100000
U-5964 | HIGHWAY | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 12 | Charlotte Regional TPO |  | REGION F |  | BGANY | UTILITIES | 700000 | FY 2024: 700000
U-5964 | HIGHWAY | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 12 | Charlotte Regional TPO |  | REGION F |  | BGANY | CONSTRUCTION | 3298000 | FY 2026: 221000; FY 2027: 2441000; FY 2028: 636000
U-5965 | HIGHWAY | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  |  |  | 450000
U-5965 | HIGHWAY | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  | T | CONSTRUCTION | 3600000 | FY 2025: 1482000; FY 2026: 2118000
U-5965 | HIGHWAY | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  | T | RIGHT-OF-WAY | 6900000 | FY 2023: 920000; FY 2024: 3680000; FY 2025: 920000; FY 2026: 690000; FY 2027: 690000
U-5965 | HIGHWAY | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  | T | UTILITIES | 300000 | FY 2023: 300000
U-5966 | HIGHWAY | NEW ROUTE | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 750000
U-5966 | HIGHWAY | NEW ROUTE | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 12900000
U-5966 | HIGHWAY | NEW ROUTE | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2398000
U-5966 | HIGHWAY | NEW ROUTE | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 93701000
U-5967 | HIGHWAY | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO |  | REGION C |  | BGANY | UTILITIES | 25000 | FY 2028: 25000
U-5967 | HIGHWAY | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO |  | REGION C |  | T | CONSTRUCTION | 350000 | FY 2029: 282000; FY 2030: 68000
U-5967 | HIGHWAY | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO |  | REGION C |  |  |  | 163000
U-5967 | HIGHWAY | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO |  | REGION C |  | T | UTILITIES | 8000 | FY 2028: 8000
U-5967 | HIGHWAY | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO |  | REGION C |  | BGANY | CONSTRUCTION | 603000 | FY 2029: 487000; FY 2030: 116000
U-5968 | HIGHWAY | VARIOUS | CITY OF DURHAM. UPGRADE ITS / SIGNAL SYSTEM. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION C |  |  |  | 14315000
U-5968 | HIGHWAY | VARIOUS | CITY OF DURHAM. UPGRADE ITS / SIGNAL SYSTEM. | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | REGION C |  | T | BUILD NC CON | 13000000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 867000 | 1729000
U-5969 | HIGHWAY | US 501 | SOUTH OF US 158 TO SR 1601 (NORTH MAIN STREET) IN ROXBORO. CONVERT TO 4-LANE MEDIAN DIVIDED FACILITY, IMPROVE VARIOUS INTERSECTIONS WITH SOME CONSOLIDATION OF INTERSECTIONS, AND FILL IN SIDEWALK GAPS. | 5 | Kerr-Tar RPO | [5 empty] | 1700000
U-5969A | HIGHWAY | US 501 | SOUTH OF US 158 TO NC 157. | 5 | Kerr-Tar RPO |  | DIVISION 5 |  | T | UTILITIES | 1288000 | FY 2027: 644000; FY 2028: 644000
U-5969A | HIGHWAY | US 501 | SOUTH OF US 158 TO NC 157. | 5 | Kerr-Tar RPO |  | DIVISION 5 |  | T | CONSTRUCTION | 4400000 | FY 2029: 2430000; FY 2030: 1970000
U-5969A | HIGHWAY | US 501 | SOUTH OF US 158 TO NC 157. | 5 | Kerr-Tar RPO |  | DIVISION 5 |  | T | RIGHT-OF-WAY | 7200000 | FY 2027: 2356000; FY 2028: 3142000; FY 2029: 262000; FY 2030: 720000; FY 2031: 720000
U-5969B | HIGHWAY | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | 5 | Kerr-Tar RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 917000
U-5969B | HIGHWAY | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | 5 | Kerr-Tar RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9200000
U-5969B | HIGHWAY | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | 5 | Kerr-Tar RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6700000
U-5969C | HIGHWAY | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | 5 | Kerr-Tar RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6300000
U-5969C | HIGHWAY | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | 5 | Kerr-Tar RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1346000
U-5969C | HIGHWAY | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | 5 | Kerr-Tar RPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6600000
U-5970 | HIGHWAY | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1900000
U-5970 | HIGHWAY | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 500000
U-5970 | HIGHWAY | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2100000
U-5970 | HIGHWAY | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 700000
U-5971 | HIGHWAY | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY) . CONSTRUCTION INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO | [5 empty] | 1369000
U-5971AA | HIGHWAY | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT DRAINAGE IMPROVEMENTS. | 13 | French Broad River MPO | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION. | REGION G |  | T | RIGHT-OF-WAY | 100000
U-5971AA | HIGHWAY | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT DRAINAGE IMPROVEMENTS. | 13 | French Broad River MPO | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION. | REGION G |  | T | CONSTRUCTION | 550000
U-5971B | HIGHWAY | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 6500000 | [11 empty] | 6500000
U-5971B | HIGHWAY | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 35590000 | [11 empty] | 35590000
U-5971B | HIGHWAY | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | UTILITIES | 300000 | [11 empty] | 300000
U-5972 | HIGHWAY | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 31899000 | [11 empty] | 31899000
U-5972 | HIGHWAY | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | UTILITIES | 6700000 | [11 empty] | 6700000
U-5972 | HIGHWAY | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  |  |  | 4260000
U-5972 | HIGHWAY | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 66000000 | [11 empty] | 66000000
U-5973 | HIGHWAY | WEAVERVILLE | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  |  |  | 260000
U-5973 | HIGHWAY | WEAVERVILLE | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 200000 | [11 empty] | 200000
U-5974 | HIGHWAY | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122 | REGION D |  | T | UTILITIES | 6600000 | FY 2027: 3300000; FY 2028: 3300000
U-5974 | HIGHWAY | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122 | REGION D |  | T | RIGHT-OF-WAY | 10200000 | FY 2027: 9169000; FY 2028: 1031000
U-5974 | HIGHWAY | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122 | REGION D |  |  |  | 1675000
U-5974 | HIGHWAY | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLIARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 7 | High Point Urban Area MPO | COORDINATE WITH U-6122 | REGION D |  | T | CONSTRUCTION | 27300000 | FY 2029: 8421000; FY 2030: 10061000; FY 2031: 5637000; FY 2032: 3181000
U-5975 | HIGHWAY | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 8 | Triangle Area RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS | REGION E |  |  |  | 3846000
U-5975 | HIGHWAY | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 8 | Triangle Area RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS | REGION E |  | BGANY | CONSTRUCTION | 29899000 | FY 2026: 10655000; FY 2027: 13427000; FY 2028: 5817000
U-5975 | HIGHWAY | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 8 | Triangle Area RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | RIGHT-OF-WAY | 4100000 | FY 2023: 339000; FY 2024: 1357000; FY 2025: 1357000; FY 2026: 226000; FY 2027: 821000
U-5975 | HIGHWAY | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 8 | Triangle Area RPO | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS | REGION E |  | T | UTILITIES | 3300000 | FY 2023: 100000; FY 2024: 1600000; FY 2025: 1600000
U-5976 | HIGHWAY | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 8 | Triangle Area RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | DIVISION 8 |  | T | RIGHT-OF-WAY | 25800000 | FY 2028: 6880000; FY 2029: 11794000; FY 2030: 1966000; FY 2031: 2580000; FY 2032: 2580000
U-5976 | HIGHWAY | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 8 | Triangle Area RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | DIVISION 8 |  | T | BUILD NC CON | 12870000 | FY 2030: 858000; FY 2031: 858000; FY 2032: 858000; FY 2033: 858000 | 9438000
U-5976 | HIGHWAY | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 8 | Triangle Area RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | DIVISION 8 |  | T | UTILITIES | 630000 | FY 2028: 630000
U-5976 | HIGHWAY | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 8 | Triangle Area RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | DIVISION 8 |  |  |  | 600000
U-5976 | HIGHWAY | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 8 | Triangle Area RPO | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2026 / YR 8 SALE) | DIVISION 8 |  | T | CONSTRUCTION | 18101000 | FY 2030: 0; FY 2031: 8695000; FY 2032: 7401000; FY 2033: 2005000
U-5977 | HIGHWAY | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 8 | Lumber River RPO |  | REGION E |  |  |  | 3888000
U-5977 | HIGHWAY | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 8 | Lumber River RPO |  | REGION E |  | T | RIGHT-OF-WAY | 4800000 | FY 2028: 1182000; FY 2029: 1772000; FY 2030: 886000; FY 2031: 480000; FY 2032: 480000
U-5977 | HIGHWAY | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 8 | Lumber River RPO |  | REGION E |  | T | UTILITIES | 2900000 | FY 2028: 1450000; FY 2029: 1450000
U-5977 | HIGHWAY | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 8 | Lumber River RPO |  | REGION E |  | T | CONSTRUCTION | 19400000 | FY 2030: 3562000; FY 2031: 8518000; FY 2032: 5823000; FY 2033: 1497000
U-5978 | HIGHWAY | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 8500000 | [11 empty] | 8500000
U-5978 | HIGHWAY | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | T | UTILITIES | 1700000 | [11 empty] | 1700000
U-5978 | HIGHWAY | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | 13 | Greater Hickory MPO |  | NOT FUNDED |  |  |  | 2760000
U-5978 | HIGHWAY | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 14000000 | [11 empty] | 14000000
U-5987 | HIGHWAY | INDIAN TRAIL | UNIONVILLE-INDIAN TRAIL ROAD AND SARDIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | COMPLETE. $1.68M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | CONSTRUCTION | 389000
U-5987 | HIGHWAY | INDIAN TRAIL | UNIONVILLE-INDIAN TRAIL ROAD AND SARDIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | COMPLETE. $1.68M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 19000
U-5987 | HIGHWAY | INDIAN TRAIL | UNIONVILLE-INDIAN TRAIL ROAD AND SARDIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | COMPLETE. $1.68M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | BGDA | CONSTRUCTION | 1167000
U-5987 | HIGHWAY | INDIAN TRAIL | UNIONVILLE-INDIAN TRAIL ROAD AND SARDIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | COMPLETE. $1.68M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1680000
U-5987 | HIGHWAY | INDIAN TRAIL | UNIONVILLE-INDIAN TRAIL ROAD AND SARDIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | COMPLETE. $1.68M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | RIGHT-OF-WAY | 6000
U-5987 | HIGHWAY | INDIAN TRAIL | UNIONVILLE-INDIAN TRAIL ROAD AND SARDIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | COMPLETE. $1.68M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. | DIVISION 10 |  | L | CONSTRUCTION | 560000
U-5989 | HIGHWAY | VARIOUS | WILMINGTON URBAN METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 84016000 | 20590000 | 1885000 | 2296000 | 3485000 | 3485000 | 3485000 | 3485000 | 3485000 | 3485000 | 3485000 | 3485000 | 31365000
U-5990 | HIGHWAY | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | 3 | Grand Strand Area Transportation Study |  | DIVISION 3 |  |  |  | 825000
U-5990 | HIGHWAY | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | 3 | Grand Strand Area Transportation Study |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 9483000 | 2187000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 384000 | 3456000
U-5991 | HIGHWAY | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | CONSTRUCTION | 30200000 | FY 2029: 302000; FY 2030: 11071000; FY 2031: 10567000; FY 2032: 6976000; FY 2033: 1284000
U-5991 | HIGHWAY | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  |  |  | 900000
U-5991 | HIGHWAY | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 14000000 | FY 2027: 140000; FY 2028: 4660000; FY 2029: 6400000; FY 2030: 1400000; FY 2031: 1400000
U-5991 | HIGHWAY | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | UTILITIES | 7500000 | FY 2027: 3750000; FY 2028: 3750000
U-5993 | HIGHWAY | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | 2 | New Bern Area MPO |  | REGION B |  | T | CONSTRUCTION | 4200000 | FY 2028: 3084000; FY 2029: 1116000
U-5993 | HIGHWAY | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | 2 | New Bern Area MPO |  | REGION B |  |  |  | 750000
U-5993 | HIGHWAY | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | 2 | New Bern Area MPO |  | REGION B |  | T | RIGHT-OF-WAY | 400000 | FY 2026: 400000
U-5994 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | LOCKHAVEN DRIVE TO COUNTRY DAY ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 800000
U-5994 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | LOCKHAVEN DRIVE TO COUNTRY DAY ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | T | CONSTRUCTION | 450000 | FY 2023: 450000
U-5996 | HIGHWAY | SR 1603 (OLD CARRIAGE ROAD) | WIDEN TO FOUR LANES FROM GREEN HILLS ROAD THROUGH US 64 BRIDGE. WIDEN TO THREE LANES FROM SOUTH OF US 64 BRIDGE TO SR 1770 (EASTERN AVENUE). | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  |  |  | 1000000
U-5996 | HIGHWAY | SR 1603 (OLD CARRIAGE ROAD) | WIDEN TO FOUR LANES FROM GREEN HILLS ROAD THROUGH US 64 BRIDGE. WIDEN TO THREE LANES FROM SOUTH OF US 64 BRIDGE TO SR 1770 (EASTERN AVENUE). | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | T | RIGHT-OF-WAY | 529000
U-5996 | HIGHWAY | SR 1603 (OLD CARRIAGE ROAD) | WIDEN TO FOUR LANES FROM GREEN HILLS ROAD THROUGH US 64 BRIDGE. WIDEN TO THREE LANES FROM SOUTH OF US 64 BRIDGE TO SR 1770 (EASTERN AVENUE). | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | T | CONSTRUCTION | 23940000 | FY 2023: 10020000; FY 2024: 7307000; FY 2025: 3374000
U-5998 | HIGHWAY | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | DIVISION 4 |  |  |  | 10000
U-5998 | HIGHWAY | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | DIVISION 4 |  | T | CONSTRUCTION | 14800000 | FY 2027: 3631000; FY 2028: 7289000; FY 2029: 3880000
U-5998 | HIGHWAY | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 3400000 | FY 2025: 544000; FY 2026: 1632000; FY 2027: 544000; FY 2028: 340000; FY 2029: 340000
U-5998 | HIGHWAY | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | DIVISION 4 |  | T | UTILITIES | 3000000 | FY 2025: 1500000; FY 2026: 1500000
U-6001 | HIGHWAY | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 1300000
U-6001 | HIGHWAY | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 700000
U-6001 | HIGHWAY | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1028000
U-6001 | HIGHWAY | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 10699000
U-6002 | HIGHWAY | WILKESBORO STREET | YADKINVILLE ROAD IN MOCKSVILLE. CONSTRUCT ROUNDABOUT. | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 750000
U-6002 | HIGHWAY | WILKESBORO STREET | YADKINVILLE ROAD IN MOCKSVILLE. CONSTRUCT ROUNDABOUT. | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | CONSTRUCTION | 1800000 | FY 2023: 1409000; FY 2024: 373000
U-6003 | HIGHWAY | NEW ROUTE | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | CONSTRUCTION | 12400000 | FY 2024: 2752000; FY 2025: 6071000; FY 2026: 3577000
U-6003 | HIGHWAY | NEW ROUTE | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 2670000
U-6004 | HIGHWAY | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | T | BUILD NC CON | 6435000 |  |  |  | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 3003000
U-6004 | HIGHWAY | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  |  |  | 750000
U-6004 | HIGHWAY | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 15400000 | FY 2024: 2843000; FY 2025: 5686000; FY 2026: 3791000; FY 2027: 1540000; FY 2028: 1540000
U-6004 | HIGHWAY | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | BGANY | UTILITIES | 2600000 | FY 2024: 1300000; FY 2025: 1300000
U-6004 | HIGHWAY | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | T | CONSTRUCTION | 17300000 | FY 2026: 0; FY 2027: 7291000; FY 2028: 6352000; FY 2029: 3657000
U-6005 | HIGHWAY | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | CONSTRUCTION | 5300000 | FY 2025: 2711000; FY 2026: 2589000
U-6005 | HIGHWAY | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | UTILITIES | 900000 | FY 2023: 900000
U-6005 | HIGHWAY | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 500000
U-6005 | HIGHWAY | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | T | RIGHT-OF-WAY | 3800000 | FY 2023: 1120000; FY 2024: 1920000; FY 2026: 380000; FY 2027: 380000
U-6006 | HIGHWAY | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 8 | Piedmont Triad RPO | COORDINATE WITH R-5956 | DIVISION 8 |  |  |  | 944000
U-6006 | HIGHWAY | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 8 | Piedmont Triad RPO | COORDINATE WITH R-5956 | DIVISION 8 |  | T | RIGHT-OF-WAY | 1000000 | FY 2024: 348000; FY 2025: 417000; FY 2026: 35000; FY 2027: 100000; FY 2028: 100000
U-6006 | HIGHWAY | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 8 | Piedmont Triad RPO | COORDINATE WITH R-5956 | DIVISION 8 |  | T | UTILITIES | 2748000 | FY 2024: 2748000
U-6006 | HIGHWAY | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 8 | Piedmont Triad RPO | COORDINATE WITH R-5956 | DIVISION 8 |  | T | CONSTRUCTION | 8500000 | FY 2027: 3895000; FY 2028: 4226000; FY 2029: 379000
U-6007 | HIGHWAY | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF SR 1453. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | CONSTRUCTION | 1400000 | FY 2023: 982000; FY 2024: 418000
U-6007 | HIGHWAY | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF SR 1453. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  |  |  | 876000
U-6007 | HIGHWAY | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF SR 1453. | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 8 |  | T | UTILITIES | 300000
U-6008 | HIGHWAY | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  |  |  | 680000
U-6008 | HIGHWAY | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 1600000 | FY 2027: 7000; FY 2028: 671000; FY 2029: 602000; FY 2030: 160000; FY 2031: 160000
U-6008 | HIGHWAY | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | UTILITIES | 300000 | FY 2027: 300000
U-6008 | HIGHWAY | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | CONSTRUCTION | 4600000 | FY 2029: 720000; FY 2030: 3207000; FY 2031: 673000
U-6009 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 7 | Burlington-Graham MPO |  | REGION D |  |  |  | 650000
U-6009 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 7 | Burlington-Graham MPO |  | REGION D |  | T | RIGHT-OF-WAY | 26600000 | FY 2028: 14187000; FY 2029: 7093000; FY 2030: 2660000; FY 2031: 2660000
U-6009 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 7 | Burlington-Graham MPO |  | REGION D |  | T | UTILITIES | 5100000 | FY 2028: 2550000; FY 2029: 2550000
U-6009 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 7 | Burlington-Graham MPO |  | REGION D |  | T | CONSTRUCTION | 11700000 | FY 2030: 2676000; FY 2031: 6254000; FY 2032: 2770000
U-6010 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | REGION D |  |  |  | 3450000
U-6010 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | REGION D |  | T | RIGHT-OF-WAY | 6000000 | FY 2023: 1000000; FY 2024: 2500000; FY 2025: 2500000
U-6010 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | REGION D |  | T | CONSTRUCTION | 16100000 | FY 2023: 11145000; FY 2024: 4794000
U-6011 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | T | CONSTRUCTION | 2400000 | FY 2025: 1577000; FY 2026: 823000
U-6011 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | T | UTILITIES | 630000
U-6011 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | T | RIGHT-OF-WAY | 3000000
U-6011 | HIGHWAY | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  |  |  | 450000
U-6013 | HIGHWAY | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | RIGHT-OF-WAY | 5500000 | FY 2023: 2829000; FY 2024: 1571000; FY 2025: 550000; FY 2026: 550000
U-6013 | HIGHWAY | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | UTILITIES | 900000 | FY 2023: 900000
U-6013 | HIGHWAY | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | CONSTRUCTION | 7300000 | FY 2024: 2022000; FY 2025: 4192000; FY 2026: 1086000
U-6013 | HIGHWAY | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 1391000
U-6014 | HIGHWAY | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | UTILITIES | 1200000 | FY 2023: 600000; FY 2024: 600000
U-6014 | HIGHWAY | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | CONSTRUCTION | 10300000 | FY 2025: 967000; FY 2026: 6313000; FY 2027: 2751000; FY 2028: 269000
U-6014 | HIGHWAY | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | RIGHT-OF-WAY | 1500000 | FY 2023: 57000; FY 2024: 686000; FY 2025: 457000; FY 2026: 150000; FY 2027: 150000
U-6014 | HIGHWAY | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 1205000
U-6015 | HIGHWAY | VARIOUS | UPGRADE BURLINGTON-GRAHAM SIGNAL SYSTEM. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  | T | BUILD NC CON | 6125000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 821000
U-6015 | HIGHWAY | VARIOUS | UPGRADE BURLINGTON-GRAHAM SIGNAL SYSTEM. | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | DIVISION 7 |  |  |  | 3094000
U-6016 | HIGHWAY | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 350000
U-6016 | HIGHWAY | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | RIGHT-OF-WAY | 836000
U-6016 | HIGHWAY | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | UTILITIES | 215000
U-6016 | HIGHWAY | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | CONSTRUCTION | 1300000 | FY 2024: 482000; FY 2025: 818000
U-6017 | HIGHWAY | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 949000
U-6017 | HIGHWAY | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | CONSTRUCTION | 2100000 | FY 2024: 21000; FY 2025: 1703000; FY 2026: 376000
U-6017 | HIGHWAY | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | RIGHT-OF-WAY | 2000000
U-6017 | HIGHWAY | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | UTILITIES | 550000
U-6018 | HIGHWAY | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  |  |  | 17000
U-6018 | HIGHWAY | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | RIGHT-OF-WAY | 2600000
U-6018 | HIGHWAY | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | UTILITIES | 1311000
U-6018 | HIGHWAY | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 7 |  | T | CONSTRUCTION | 14200000 | FY 2024: 142000; FY 2025: 8323000; FY 2026: 4376000; FY 2027: 1359000
U-6019 | HIGHWAY | SR 2334 (AIR HARBOR ROAD) | SR 2347 (LAKE BRANDT ROAD). CONSTRUCT TURN LANES AND SIDEWALKS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  | T | CONSTRUCTION | 1300000 | FY 2023: 1287000
U-6019 | HIGHWAY | SR 2334 (AIR HARBOR ROAD) | SR 2347 (LAKE BRANDT ROAD). CONSTRUCT TURN LANES AND SIDEWALKS. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | DIVISION 7 |  |  |  | 425000
U-6020 | HIGHWAY | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | DIVISION 5 |  | T | CONSTRUCTION | 4800000 | FY 2025: 2492000; FY 2026: 2151000; FY 2027: 157000
U-6020 | HIGHWAY | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | DIVISION 5 |  |  |  | 1500000
U-6020 | HIGHWAY | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | 5 | Kerr-Tar RPO | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER | DIVISION 5 |  | L | CONSTRUCTION | 1200000 | FY 2025: 623000; FY 2026: 538000; FY 2027: 39000
U-6021 | HIGHWAY | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 15200000
U-6021 | HIGHWAY | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 500000
U-6021 | HIGHWAY | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 9100000
U-6021 | HIGHWAY | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1700000
U-6022 | HIGHWAY | VARIOUS | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION | REGION C |  | BGANY | CONSTRUCTION | 2744000 | FY 2023: 926000; FY 2024: 1672000; FY 2025: 146000
U-6022 | HIGHWAY | VARIOUS | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION | REGION C |  |  |  | 325000
U-6022 | HIGHWAY | VARIOUS | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION | REGION C |  | BGANY | UTILITIES | 451000
U-6023 | HIGHWAY | VARIOUS | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  |  |  | 451000
U-6023 | HIGHWAY | VARIOUS | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGANY | UTILITIES | 250000
U-6023 | HIGHWAY | VARIOUS | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGANY | CONSTRUCTION | 2743000 | FY 2023: 1363000; FY 2024: 1380000
U-6024 | HIGHWAY | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | DIVISION 5 |  | T | CONSTRUCTION | 15998000 | FY 2031: 2766000; FY 2032: 7049000; FY 2033: 4717000 | 1466000
U-6024 | HIGHWAY | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | DIVISION 5 |  |  |  | 750000
U-6024 | HIGHWAY | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | DIVISION 5 |  | T | RIGHT-OF-WAY | 3200000 | FY 2028: 80000; FY 2029: 960000; FY 2030: 960000; FY 2031: 560000; FY 2032: 640000
U-6024 | HIGHWAY | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 5 | Kerr-Tar RPO | COORDINATE WITH R-3608 | DIVISION 5 |  | T | UTILITIES | 1800000 | FY 2028: 900000; FY 2029: 900000
U-6026 | HIGHWAY | VARIOUS | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION. FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION | DIVISION 5 |  | BGANY | CONSTRUCTION | 1350000 | FY 2023: 821000; FY 2024: 529000
U-6026 | HIGHWAY | VARIOUS | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION. FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION | DIVISION 5 |  |  |  | 324000
U-6026 | HIGHWAY | VARIOUS | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | 5 | Capital Area MPO | UNDER CONSTRUCTION. FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION | DIVISION 5 |  | BGANY | UTILITIES | 450000
U-6027 | HIGHWAY | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 8 | Lumber River RPO |  | DIVISION 8 |  |  |  | 650000
U-6027 | HIGHWAY | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 8 | Lumber River RPO |  | DIVISION 8 |  | T | RIGHT-OF-WAY | 1700000 | FY 2024: 17000; FY 2025: 631000; FY 2026: 712000; FY 2027: 170000; FY 2028: 170000
U-6027 | HIGHWAY | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 8 | Lumber River RPO |  | DIVISION 8 |  | T | UTILITIES | 2000000 | FY 2024: 2000000
U-6027 | HIGHWAY | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 8 | Lumber River RPO |  | DIVISION 8 |  | T | CONSTRUCTION | 4700000 | FY 2027: 47000; FY 2028: 3208000; FY 2029: 1445000
U-6028 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  |  |  | 2340000
U-6028 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | CONSTRUCTION | 20400000 | FY 2030: 204000; FY 2031: 8757000; FY 2032: 7632000; FY 2033: 3807000
U-6028 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | UTILITIES | 4000000 | FY 2027: 2000000; FY 2028: 2000000
U-6028 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | RIGHT-OF-WAY | 7700000 | FY 2027: 1680000; FY 2028: 2240000; FY 2029: 2240000; FY 2030: 770000; FY 2031: 770000
U-6029 | HIGHWAY | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 6540000
U-6029 | HIGHWAY | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 43403000 | [11 empty] | 43403000
U-6029 | HIGHWAY | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO |  | NOT FUNDED |  | T | UTILITIES | 1085000 | [11 empty] | 1085000
U-6029 | HIGHWAY | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO |  | NOT FUNDED |  | T | CONSTRUCTION | 80200000 | [11 empty] | 80200000
U-6030 | HIGHWAY | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 22700000 | [11 empty] | 22700000
U-6030 | HIGHWAY | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | UTILITIES | 4610000 | [11 empty] | 4610000
U-6030 | HIGHWAY | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 3540000
U-6030 | HIGHWAY | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | CONSTRUCTION | 24298000 | [11 empty] | 24298000
U-6031 | HIGHWAY | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | CONSTRUCTION | 10101000 | FY 2030: 2378000; FY 2031: 5492000; FY 2032: 2231000
U-6031 | HIGHWAY | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  |  |  | 330000
U-6031 | HIGHWAY | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | RIGHT-OF-WAY | 7700000 | FY 2028: 1339000; FY 2029: 3214000; FY 2030: 1607000; FY 2031: 770000; FY 2032: 770000
U-6031 | HIGHWAY | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | T | UTILITIES | 4500000 | FY 2028: 2250000; FY 2029: 2250000
U-6032 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | BUILD NC CON | 7725000 |  |  | 1030000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 2575000
U-6032 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | CONSTRUCTION | 19800000 | FY 2025: 0; FY 2026: 4364000; FY 2027: 9374000; FY 2028: 5068000; FY 2029: 994000
U-6032 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  |  |  | 1050000
U-6032 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | UTILITIES | 2600000
U-6032 | HIGHWAY | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO SIX LANES. | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE) | DIVISION 10 |  | T | RIGHT-OF-WAY | 14400000 | FY 2023: 4800000; FY 2024: 4800000
U-6033 | HIGHWAY | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 11 |  |  |  | 137000
U-6033 | HIGHWAY | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 11 |  | T | RIGHT-OF-WAY | 400000
U-6033 | HIGHWAY | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 11 |  | T | UTILITIES | 450000 | FY 2023: 450000
U-6033 | HIGHWAY | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. | DIVISION 11 |  | T | CONSTRUCTION | 2246000 | FY 2023: 22000; FY 2024: 1556000; FY 2025: 668000
U-6034 | HIGHWAY | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 11 | Greater Hickory MPO |  | DIVISION 11 |  |  |  | 349000
U-6034 | HIGHWAY | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGANY | CONSTRUCTION | 14400000 | FY 2026: 144000; FY 2027: 6458000; FY 2028: 5344000; FY 2029: 2454000
U-6034 | HIGHWAY | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGANY | RIGHT-OF-WAY | 9000000 | FY 2024: 4320000; FY 2025: 2880000; FY 2026: 900000; FY 2027: 900000
U-6034 | HIGHWAY | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 11 | Greater Hickory MPO |  | DIVISION 11 |  | BGANY | UTILITIES | 3000000 | FY 2024: 1500000; FY 2025: 1500000
U-6035 | HIGHWAY | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  | T | CONSTRUCTION | 1700000 | FY 2024: 250000; FY 2025: 1450000
U-6035 | HIGHWAY | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  |  |  | 150000
U-6035 | HIGHWAY | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  | T | RIGHT-OF-WAY | 200000
U-6035 | HIGHWAY | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  | T | UTILITIES | 230000
U-6036 | HIGHWAY | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  | T | UTILITIES | 400000
U-6036 | HIGHWAY | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  | T | CONSTRUCTION | 12599000 | FY 2024: 126000; FY 2025: 5734000; FY 2026: 5120000; FY 2027: 1619000
U-6036 | HIGHWAY | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  |  |  | 800000
U-6036 | HIGHWAY | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 11 |  | T | RIGHT-OF-WAY | 1500000
U-6037 | HIGHWAY | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  |  |  | 5000000
U-6037 | HIGHWAY | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 15500000 | FY 2027: 155000; FY 2028: 3978000; FY 2029: 5511000; FY 2030: 2756000; FY 2031: 3100000
U-6037 | HIGHWAY | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | T | UTILITIES | 4600000 | FY 2027: 2300000; FY 2028: 2300000
U-6037 | HIGHWAY | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 12 | Charlotte Regional TPO |  | DIVISION 12 |  | T | CONSTRUCTION | 23800000 | FY 2030: 3758000; FY 2031: 9591000; FY 2032: 7194000; FY 2033: 3257000
U-6038 | HIGHWAY | US 74 (WILKINSON BOULEVARD) | NC 7 (CATAWBA STREET) TO SR 2209 (WESLEYAN DRIVE). IMPLEMENT ADAPTIVE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | DIVISION 12 |  |  |  | 735000
U-6038 | HIGHWAY | US 74 (WILKINSON BOULEVARD) | NC 7 (CATAWBA STREET) TO SR 2209 (WESLEYAN DRIVE). IMPLEMENT ADAPTIVE SIGNAL SYSTEM. | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE) | DIVISION 12 |  | T | BUILD NC CON | 600000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
U-6039 | HIGHWAY | SR 2321 (EAST BROAD STREET) | VINE STREET TO SR 2422 (SIGNAL HILL DRIVE). UPGRADE ROADWAY AND IMPLEMENT ACCESS MANAGEMENT SOLUTIONS. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B | DIVISION 12 |  |  |  | 10050000
U-6039 | HIGHWAY | SR 2321 (EAST BROAD STREET) | VINE STREET TO SR 2422 (SIGNAL HILL DRIVE). UPGRADE ROADWAY AND IMPLEMENT ACCESS MANAGEMENT SOLUTIONS. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B | DIVISION 12 |  | T | CONSTRUCTION | 5350000
U-6041 | HIGHWAY | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | CONSTRUCTION | 1450000 | FY 2025: 457000; FY 2026: 993000
U-6041 | HIGHWAY | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | 12 | Greater Hickory MPO |  | DIVISION 12 |  |  |  | 100000
U-6041 | HIGHWAY | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 200000 | FY 2024: 200000
U-6041 | HIGHWAY | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | UTILITIES | 400000 | FY 2024: 400000
U-6042 | HIGHWAY | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 12 | Greater Hickory MPO |  | DIVISION 12 |  |  |  | 375000
U-6042 | HIGHWAY | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 1400000 | FY 2027: 14000; FY 2028: 658000; FY 2029: 448000; FY 2030: 140000; FY 2031: 140000
U-6042 | HIGHWAY | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | UTILITIES | 200000 | FY 2027: 200000
U-6042 | HIGHWAY | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 12 | Greater Hickory MPO |  | DIVISION 12 |  | T | CONSTRUCTION | 3300000 | FY 2029: 895000; FY 2030: 2272000; FY 2031: 133000
U-6043 | HIGHWAY | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | T | CONSTRUCTION | 2700000 | FY 2025: 27000; FY 2026: 1897000; FY 2027: 776000
U-6043 | HIGHWAY | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  |  |  | 1300000
U-6043 | HIGHWAY | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | T | RIGHT-OF-WAY | 1300000 | FY 2023: 80000; FY 2024: 480000; FY 2025: 480000; FY 2026: 130000; FY 2027: 130000
U-6043 | HIGHWAY | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | T | UTILITIES | 900000 | FY 2023: 900000
U-6044 | HIGHWAY | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | BG50200 | CONSTRUCTION | 5400000 | FY 2028: 54000; FY 2029: 3033000; FY 2030: 2313000
U-6044 | HIGHWAY | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | BG50200 | UTILITIES | 1200000 | FY 2025: 600000; FY 2026: 600000
U-6044 | HIGHWAY | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 1000000
U-6044 | HIGHWAY | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | BG50200 | RIGHT-OF-WAY | 21100000 | FY 2025: 211000; FY 2026: 6138000; FY 2027: 6138000; FY 2028: 4604000; FY 2029: 4009000
U-6045 | HIGHWAY | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  |  |  | 250000
U-6045 | HIGHWAY | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | RIGHT-OF-WAY | 6800000 | FY 2027: 21000; FY 2028: 2085000; FY 2029: 2106000; FY 2030: 1228000; FY 2031: 1360000
U-6045 | HIGHWAY | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | UTILITIES | 1200000 | FY 2027: 600000; FY 2028: 600000
U-6045 | HIGHWAY | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | T | CONSTRUCTION | 23100000 | FY 2030: 4321000; FY 2031: 10918000; FY 2032: 5732000; FY 2033: 2129000
U-6046 | HIGHWAY | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | 13 | French Broad River MPO | COORDINATE WITH U-5832. | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2100000
U-6046 | HIGHWAY | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | 13 | French Broad River MPO | COORDINATE WITH U-5832. | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 16300000
U-6046 | HIGHWAY | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | 13 | French Broad River MPO | COORDINATE WITH U-5832. | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 3443000
U-6046 | HIGHWAY | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | 13 | French Broad River MPO | COORDINATE WITH U-5832. | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 24700000
U-6047 | HIGHWAY | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 13 | French Broad River MPO |  | DIVISION 13 |  |  |  | 6100000
U-6047 | HIGHWAY | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | RIGHT-OF-WAY | 60799000 | FY 2028: 608000; FY 2029: 17079000; FY 2030: 17687000; FY 2031: 13265000; FY 2032: 12160000
U-6047 | HIGHWAY | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | UTILITIES | 6800000 | FY 2028: 3400000; FY 2029: 3400000
U-6047 | HIGHWAY | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 13 | French Broad River MPO |  | DIVISION 13 |  | BGANY | CONSTRUCTION | 68999000 | FY 2031: 690000; FY 2032: 18372000; FY 2033: 19747000 | 30190000
U-6048 | HIGHWAY | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | T | CONSTRUCTION | 28201000 | FY 2030: 4532000; FY 2031: 10478000; FY 2032: 7986000; FY 2033: 5205000
U-6048 | HIGHWAY | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  |  |  | 2226000
U-6048 | HIGHWAY | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | T | RIGHT-OF-WAY | 300000 | FY 2028: 300000
U-6048 | HIGHWAY | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 13, 14 | French Broad River MPO |  | DIVISION 13, 14 |  | T | UTILITIES | 700000 | FY 2028: 700000
U-6049 | HIGHWAY | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | REGION G |  | T | CONSTRUCTION | 4000000 | FY 2026: 2925000; FY 2027: 1075000
U-6049 | HIGHWAY | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | REGION G |  | T | UTILITIES | 400000 | FY 2023: 400000
U-6049 | HIGHWAY | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | REGION G |  |  |  | 680000
U-6049 | HIGHWAY | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886 | REGION G |  | T | RIGHT-OF-WAY | 3400000 | FY 2023: 263000; FY 2024: 1053000; FY 2025: 1053000; FY 2026: 351000; FY 2027: 680000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  |  |  | 166000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | L | ENGINEERING | 101000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | L | CONSTRUCTION | 206000 | FY 2024: 206000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | L | CONSTRUCTION | 368000 | FY 2024: 368000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | L | RIGHT-OF-WAY | 103000 | FY 2023: 103000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | L | RIGHT-OF-WAY | 374000 | FY 2023: 374000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | BGDA | ENGINEERING | 225000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | BGANY | CONSTRUCTION | 824000 | FY 2024: 824000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | BGANY | CONSTRUCTION | 820000 | FY 2024: 820000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | BGANY | RIGHT-OF-WAY | 331000 | FY 2023: 331000
U-6054 | HIGHWAY | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 12 | Charlotte Regional TPO | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS. | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 732000 | FY 2023: 732000
U-6055 | HIGHWAY | CANTON | NC 110 (PISGAH DRIVE) AT LOCUST STREET. IMPROVE INTERSECTION. | 14 | French Broad River MPO | UNDER CONSTRUCTION. STBGDA FUNDS ARE EXEMPT BECAUSE THEY ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE IS PAYING MATCH BECAUSE PROJECT CAME IN RANK ORDER OFF P3.0 PRIORITIZATION LIST | EXEMPT |  |  |  | 1816000
U-6057 | HIGHWAY | MORGANTON | SOUTH STERLING STREET TO WEST PARKER ROAD. CONSTRUCT CONNECTOR ROAD. | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. ARC PROJECT NO. 18703. AWARD AMOUNT = $1,374,714. | EXEMPT |  |  |  | 1405000
U-6058 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | REGION B |  |  |  | 300000
U-6058 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | REGION B |  | L | CONSTRUCTION | 16000 | FY 2025: 7000; FY 2026: 9000
U-6058 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | REGION B |  | T | RIGHT-OF-WAY | 859000 | FY 2023: 859000
U-6058 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | REGION B |  | T | UTILITIES | 193000 | FY 2023: 193000
U-6058 | HIGHWAY | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT. | REGION B |  | T | CONSTRUCTION | 3534000 | FY 2025: 1556000; FY 2026: 1978000
U-6059 | HIGHWAY | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD) IN WINSTON-SALEM. UPGRADE INTERCHANGE AND REPLACE BRIDGE 330211 ON SR 2377 (OLD GREENSBORO ROAD NE) OVER NORFOLK SOUTHERN RAILROAD. | 9 | Winston-Salem Urban Area MPO | [5 empty] | 150000
U-6059A | HIGHWAY | SR 2377 (OLD GREENSBORO ROAD NE) | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | UTILITIES | 1100000 | FY 2025: 550000; FY 2026: 550000
U-6059A | HIGHWAY | SR 2377 (OLD GREENSBORO ROAD NE) | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | CONSTRUCTION | 6800000 | FY 2027: 68000; FY 2028: 4090000; FY 2029: 2642000
U-6059A | HIGHWAY | SR 2377 (OLD GREENSBORO ROAD NE) | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | BGOFF | RIGHT-OF-WAY | 4229000 | FY 2025: 16000; FY 2026: 1595000; FY 2027: 1772000; FY 2028: 423000; FY 2029: 423000
U-6059B | HIGHWAY | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | 9 | Winston-Salem Urban Area MPO | COORDINATE WITH U-6068 | NOT FUNDED |  | T | UTILITIES | 1332000 | [11 empty] | 1332000
U-6059B | HIGHWAY | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | 9 | Winston-Salem Urban Area MPO | COORDINATE WITH U-6068 | NOT FUNDED |  | T | CONSTRUCTION | 28860000 | [11 empty] | 28860000
U-6059B | HIGHWAY | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | 9 | Winston-Salem Urban Area MPO | COORDINATE WITH U-6068 | NOT FUNDED |  | T | RIGHT-OF-WAY | 11100000 | [11 empty] | 11100000
U-6062 | HIGHWAY | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 9, 10 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | DIVISION 9, 10 |  |  |  | 750000
U-6062 | HIGHWAY | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 9, 10 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | DIVISION 9, 10 |  | T | RIGHT-OF-WAY | 28900000 | FY 2028: 83000; FY 2029: 8174000; FY 2030: 9909000; FY 2031: 4954000; FY 2032: 2890000; FY 2033: 2890000
U-6062 | HIGHWAY | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 9, 10 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | DIVISION 9, 10 |  | T | UTILITIES | 3900000 | FY 2028: 1950000; FY 2029: 1950000
U-6062 | HIGHWAY | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 9, 10 | Cabarrus-Rowan MPO | COORDINATE WITH EB-5921 | DIVISION 9, 10 |  | T | CONSTRUCTION | 28399000 | FY 2031: 4410000; FY 2032: 11176000; FY 2033: 8397000 | 4416000
U-6065 | HIGHWAY | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY |  |  |  | 750000
U-6065 | HIGHWAY | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 1500000 | FY 2027: 376000; FY 2028: 825000; FY 2029: 299000
U-6065 | HIGHWAY | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY |  | T | RIGHT-OF-WAY | 1000000 | FY 2025: 10000; FY 2026: 490000; FY 2027: 300000; FY 2028: 100000; FY 2029: 100000
U-6065 | HIGHWAY | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY |  | T | UTILITIES | 1178000 | FY 2025: 589000; FY 2026: 589000
U-6065 | HIGHWAY | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 7201000 | FY 2027: 1806000; FY 2028: 3959000; FY 2029: 1436000
U-6066 | HIGHWAY | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5825 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1600000
U-6066 | HIGHWAY | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5825 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 40799000
U-6066 | HIGHWAY | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5825 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6066 | HIGHWAY | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | 5 | Capital Area MPO | COORDINATE WITH U-5825 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 32400000
U-6067 | HIGHWAY | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | 5 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5717 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6067 | HIGHWAY | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | 5 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5717 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 42800000
U-6067 | HIGHWAY | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | 5 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5717 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3700000
U-6067 | HIGHWAY | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | 5 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5717 | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 62898000
U-6068 | HIGHWAY | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 7, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH U-6059B | NOT FUNDED |  |  |  | 10000
U-6068 | HIGHWAY | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 7, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH U-6059B | NOT FUNDED |  | T | RIGHT-OF-WAY | 57300000 | [11 empty] | 57300000
U-6068 | HIGHWAY | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 7, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH U-6059B | NOT FUNDED |  | T | UTILITIES | 2114000 | [11 empty] | 2114000
U-6068 | HIGHWAY | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 7, 9 | Winston-Salem Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH U-6059B | NOT FUNDED |  | T | CONSTRUCTION | 71300000 | [11 empty] | 71300000
U-6072 | HIGHWAY | SR 1112 (ROCKFISH ROAD) | STRICKLAND BRIDGE ROAD TO GOLFVIEW ROAD. WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO | [5 empty] | 4500000
U-6072A | HIGHWAY | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 13600000 | [11 empty] | 13600000
U-6072A | HIGHWAY | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | UTILITIES | 4960000 | [11 empty] | 4960000
U-6072A | HIGHWAY | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 24500000 | [11 empty] | 24500000
U-6072B | HIGHWAY | SR 1112 (ROCKFISH ROAD) | CAMDEN ROAD TO GOLFVIEW ROAD. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 10400000 | [11 empty] | 10400000
U-6072B | HIGHWAY | SR 1112 (ROCKFISH ROAD) | CAMDEN ROAD TO GOLFVIEW ROAD. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 4300000 | [11 empty] | 4300000
U-6072B | HIGHWAY | SR 1112 (ROCKFISH ROAD) | CAMDEN ROAD TO GOLFVIEW ROAD. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | UTILITIES | 1100000 | [11 empty] | 1100000
U-6073 | HIGHWAY | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  |  |  | 2010000
U-6073 | HIGHWAY | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | BGANY | RIGHT-OF-WAY | 17600000 | FY 2026: 5760000; FY 2027: 7680000; FY 2028: 640000; FY 2029: 1760000; FY 2030: 1760000
U-6073 | HIGHWAY | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | BGANY | UTILITIES | 2138000 | FY 2026: 1069000; FY 2027: 1069000
U-6073 | HIGHWAY | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | BGANY | CONSTRUCTION | 22300000 | FY 2028: 7669000; FY 2029: 8610000; FY 2030: 6021000
U-6078 | HIGHWAY | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | RIGHT-OF-WAY | 3000000 | FY 2025: 458000; FY 2026: 1371000; FY 2027: 571000; FY 2028: 300000; FY 2029: 300000
U-6078 | HIGHWAY | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | UTILITIES | 400000 | FY 2025: 400000
U-6078 | HIGHWAY | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  |  |  | 200000
U-6078 | HIGHWAY | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | T | CONSTRUCTION | 5500000 | FY 2027: 1756000; FY 2028: 3528000; FY 2029: 216000
U-6081 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  |  |  | 1000000
U-6081 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2400000 | [11 empty] | 2400000
U-6081 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 1000000 | [11 empty] | 1000000
U-6081 | HIGHWAY | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 50800000 | [11 empty] | 50800000
U-6082 | HIGHWAY | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | BG5200 | CONSTRUCTION | 4300000 | FY 2028: 821000; FY 2029: 3017000; FY 2030: 462000
U-6082 | HIGHWAY | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | BG5200 | UTILITIES | 900000 | FY 2025: 900000
U-6082 | HIGHWAY | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  | BG5200 | RIGHT-OF-WAY | 1300000 | FY 2025: 13000; FY 2026: 702000; FY 2027: 325000; FY 2028: 130000; FY 2029: 130000
U-6082 | HIGHWAY | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | DIVISION 3 |  |  |  | 500000
U-6084 | HIGHWAY | NC 16 (BROOKSHIRE BOULEVARD) | NC 16 (BROOKSHIRE BOULEVARD) AT SR 2004 (MOUNT HOLLY HUNTERSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE. | REGION E |  | T | CONSTRUCTION | 1963000
U-6084 | HIGHWAY | NC 16 (BROOKSHIRE BOULEVARD) | NC 16 (BROOKSHIRE BOULEVARD) AT SR 2004 (MOUNT HOLLY HUNTERSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE. | REGION E |  |  |  | 6135000
U-6085 | HIGHWAY | VARIOUS | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. | 7 | Greensboro Urban Area MPO | IN PROGRESS | DIVISION 7 |  |  |  | 153000
U-6085 | HIGHWAY | VARIOUS | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. | 7 | Greensboro Urban Area MPO | IN PROGRESS | DIVISION 7 |  | BGDA | PLANNING | 4240000 | FY 2023: 500000; FY 2024: 840000; FY 2025: 800000; FY 2026: 800000; FY 2027: 800000
U-6085 | HIGHWAY | VARIOUS | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. | 7 | Greensboro Urban Area MPO | IN PROGRESS | DIVISION 7 |  | L | PLANNING | 1060000 | FY 2023: 125000; FY 2024: 210000; FY 2025: 200000; FY 2026: 200000; FY 2027: 200000
U-6086 | HIGHWAY | NC 51 | PARK ROAD TO CARMEL ROAD IN PINEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Charlotte Regional TPO | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP | EXEMPT |  | BGANY | CONSTRUCTION | 5643000 | FY 2025: 3084000; FY 2026: 2208000; FY 2027: 351000
U-6086 | HIGHWAY | NC 51 | PARK ROAD TO CARMEL ROAD IN PINEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 10 | Charlotte Regional TPO | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP | EXEMPT |  | L | CONSTRUCTION | 1910000 | FY 2025: 1044000; FY 2026: 747000; FY 2027: 119000
U-6087 | HIGHWAY | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | DIVISION 10 |  | BGDA | CONSTRUCTION | 262000 | FY 2024: 262000
U-6087 | HIGHWAY | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1006000 | FY 2024: 1006000
U-6087 | HIGHWAY | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 254000 | FY 2024: 254000
U-6087 | HIGHWAY | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 65000 | FY 2024: 65000
U-6087 | HIGHWAY | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | DIVISION 10 |  | S(M) | CONSTRUCTION | 293000 | FY 2024: 293000
U-6087 | HIGHWAY | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP. | DIVISION 10 |  |  |  | 297000
U-6088 | HIGHWAY | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | BGDA | CONSTRUCTION | 362000 | FY 2023: 362000
U-6088 | HIGHWAY | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | S(M) | CONSTRUCTION | 293000 | FY 2023: 293000
U-6088 | HIGHWAY | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  |  |  | 800000
U-6088 | HIGHWAY | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 96000 | FY 2023: 96000
U-6088 | HIGHWAY | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1192000 | FY 2023: 1192000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 27000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | S(M) | CONSTRUCTION | 306000 | FY 2023: 202000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | S(M) | RIGHT-OF-WAY | 41000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 182000 | FY 2023: 120000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1955000 | FY 2023: 1288000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | RIGHT-OF-WAY | 193000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | CMAQ | ENGINEERING | 258000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  |  |  | 200000
U-6090 | HIGHWAY | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | DIVISION 10 |  | S(M) | ENGINEERING | 133000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | S(M) | CONSTRUCTION | 79000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | S(M) | RIGHT-OF-WAY | 40000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | L | CONSTRUCTION | 478000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | S(M) | ENGINEERING | 75000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | O | CONSTRUCTION | 351000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | CMAQ | CONSTRUCTION | 1517000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | CMAQ | RIGHT-OF-WAY | 360000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  |  |  | 185000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | CMAQ | ENGINEERING | 300000
U-6091 | HIGHWAY | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | COMPLETE. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT. | DIVISION 10 |  | L | RIGHT-OF-WAY | 50000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | L | RIGHT-OF-WAY | 130000 | FY 2023: 130000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | L | CONSTRUCTION | 242000 | FY 2025: 242000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | L | RIGHT-OF-WAY | 30000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | L | ENGINEERING | 30000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | CONSTRUCTION | 966000 | FY 2024: 966000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 120000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | ENGINEERING | 120000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | L | CONSTRUCTION | 252000 | FY 2025: 252000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | BGDA | CONSTRUCTION | 1011000 | FY 2024: 1011000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  |  |  | 150000
U-6092 | HIGHWAY | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | EXEMPT |  | CMAQ | RIGHT-OF-WAY | 515000 | FY 2023: 515000
U-6093 | HIGHWAY | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | CONSTRUCTION | 7743000
U-6093 | HIGHWAY | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | RIGHT-OF-WAY | 567000
U-6093 | HIGHWAY | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 1324000
U-6093 | HIGHWAY | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  |  |  | 1230000
U-6093 | HIGHWAY | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | DIVISION 5 |  | L | CONSTRUCTION | 3319000
U-6094 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | DIVISION 5 |  |  |  | 1022000
U-6094 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 1184000
U-6094 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | DIVISION 5 |  | BGDA | CONSTRUCTION | 1217000 | FY 2023: 1217000
U-6094 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | DIVISION 5 |  | L | RIGHT-OF-WAY | 296000
U-6094 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS | DIVISION 5 |  | L | CONSTRUCTION | 304000 | FY 2023: 304000
U-6096 | HIGHWAY | SR 2763 (OLD HONEYCUTT ROAD) SR 1301 (PURFOY ROAD) | INTERSECTION OF OLD HONEYCUTT ROAD (SR 2763) AND PURFOY ROAD (SR 1301) IN FUQUAY-VARINA. INTERSECTION IMPROVEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  |  |  | 1142000
U-6098 | HIGHWAY | VARIOUS | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73. CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD). CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP | 10 | Cabarrus-Rowan MPO | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION. | DIVISION 10 |  | T | CONSTRUCTION | 850000
U-6098 | HIGHWAY | VARIOUS | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73. CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD). CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP | 10 | Cabarrus-Rowan MPO | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION. | DIVISION 10 |  |  |  | 850000
U-6099 | HIGHWAY | SR 5220 (JONES SAUSAGE ROAD) | SR 1004 (EAST GARNER ROAD) TO I-40 IN GARNER. WIDEN ROADWAY FROM SOUTH OF SR 2585 (WILMINGTON ROAD) TO I-40, INCLUDING ACCESS POINT IMPROVEMENTS, AND CONSTRUCT IMPROVEMENTS AT SR 1004 INTERSECTION AND I-40 INTERCHANGE. | 5 | Capital Area MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMAZON | DIVISION 5 |  |  |  | 5100000
U-6100 | HIGHWAY | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6100 | HIGHWAY | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 4400000 | [11 empty] | 4400000
U-6100 | HIGHWAY | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 2200000 | [11 empty] | 2200000
U-6100 | HIGHWAY | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 7 | Greensboro Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 24000000 | [11 empty] | 24000000
U-6101 | HIGHWAY | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | 4, 5 | Capital Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6101 | HIGHWAY | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | 4, 5 | Capital Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 1000000 | [11 empty] | 1000000
U-6101 | HIGHWAY | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | 4, 5 | Capital Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 500000 | [11 empty] | 500000
U-6101 | HIGHWAY | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | 4, 5 | Capital Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 138201000 | [11 empty] | 138201000
U-6102 | HIGHWAY | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | 2 | New Bern Area MPO |  | NOT FUNDED |  |  |  | 110000
U-6102 | HIGHWAY | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | 2 | New Bern Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2700000 | [11 empty] | 2700000
U-6102 | HIGHWAY | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | 2 | New Bern Area MPO |  | NOT FUNDED |  | T | UTILITIES | 500000 | [11 empty] | 500000
U-6102 | HIGHWAY | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | 2 | New Bern Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 21200000 | [11 empty] | 21200000
U-6103 | HIGHWAY | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | NHP | RIGHT-OF-WAY | 10500000 | FY 2025: 105000; FY 2026: 4095000; FY 2027: 4200000; FY 2028: 1050000; FY 2029: 1050000
U-6103 | HIGHWAY | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | NHP | UTILITIES | 1100000 | FY 2025: 550000; FY 2026: 550000
U-6103 | HIGHWAY | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  |  |  | 1010000
U-6103 | HIGHWAY | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 10 | Charlotte Regional TPO |  | STATEWIDE MOBILITY |  | NHP | CONSTRUCTION | 93200000 | FY 2028: 21011000; FY 2029: 28987000; FY 2030: 13652000; FY 2031: 21070000; FY 2032: 8480000
U-6104 | HIGHWAY | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | 3 | Grand Strand Area Transportation Study |  | NOT FUNDED |  |  |  | 760000
U-6104 | HIGHWAY | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | 3 | Grand Strand Area Transportation Study |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 4233000 | [11 empty] | 4233000
U-6104 | HIGHWAY | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | 3 | Grand Strand Area Transportation Study |  | NOT FUNDED |  | NHP | UTILITIES | 300000 | [11 empty] | 300000
U-6104 | HIGHWAY | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | 3 | Grand Strand Area Transportation Study |  | NOT FUNDED |  | NHP | CONSTRUCTION | 19200000 | [11 empty] | 19200000
U-6105 | HIGHWAY | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | DIVISION 10 |  |  |  | 490000
U-6105 | HIGHWAY | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | DIVISION 10 |  | BGANY | RIGHT-OF-WAY | 756000 | FY 2023: 756000
U-6105 | HIGHWAY | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | DIVISION 10 |  | BGANY | CONSTRUCTION | 2244000 | FY 2024: 501000; FY 2025: 1491000; FY 2026: 252000
U-6105 | HIGHWAY | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 276000 | FY 2023: 276000
U-6105 | HIGHWAY | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | DIVISION 10 |  | L | RIGHT-OF-WAY | 1032000 | FY 2023: 1032000
U-6105 | HIGHWAY | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP | DIVISION 10 |  | L | CONSTRUCTION | 2389000 | FY 2024: 534000; FY 2025: 1587000; FY 2026: 268000
U-6106 | HIGHWAY | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 460000
U-6106 | HIGHWAY | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 2095000 | FY 2025: 2095000
U-6106 | HIGHWAY | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 10 |  | L | RIGHT-OF-WAY | 167000
U-6106 | HIGHWAY | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 10 |  | BGANY | CONSTRUCTION | 1343000 | FY 2025: 1323000; FY 2026: 20000
U-6106 | HIGHWAY | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 10 |  | BGANY | CONSTRUCTION | 6910000 | FY 2025: 3455000; FY 2026: 3455000
U-6106 | HIGHWAY | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 10 |  | BGANY | RIGHT-OF-WAY | 1840000
U-6106 | HIGHWAY | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 10 |  | BGDA | RIGHT-OF-WAY | 667000
U-6106 | HIGHWAY | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 336000 | FY 2025: 331000; FY 2026: 5000
U-6107 | HIGHWAY | US 17 | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 3000000
U-6107 | HIGHWAY | US 17 | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6107 | HIGHWAY | US 17 | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 1000000
U-6107 | HIGHWAY | US 17 | MCDANIEL DRIVE / WORKSHOP LANE. UPGRADE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | STATEWIDE MOBILITY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 100000
U-6108 | HIGHWAY | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | 7 | Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 12500000
U-6108 | HIGHWAY | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | 7 | Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1600000
U-6108 | HIGHWAY | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | 7 | Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6108 | HIGHWAY | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEGROUND COURT AND WINSTEAD PLACE. ACCOMMODATE PEDESTRIANS, BICYCLES AND THE A&Y GREENWAY. MAY INCLUDE ROADWAY BRIDGES, PEDESTRIAN GRADE SEPARATIONS, AND MODIFICATIONS TO INTERSECTING STREETS WITHIN THE CORRIDOR. | 7 | Greensboro Urban Area MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 44600000
U-6109 | HIGHWAY | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | NHP | CONSTRUCTION | 47400000 | FY 2028: 2782000; FY 2029: 18896000; FY 2030: 14082000; FY 2031: 8448000; FY 2032: 3192000
U-6109 | HIGHWAY | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  |  |  | 10000
U-6109 | HIGHWAY | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | NHP | RIGHT-OF-WAY | 5000000 | FY 2025: 1200000; FY 2026: 1600000; FY 2027: 1200000; FY 2028: 500000; FY 2029: 500000
U-6109 | HIGHWAY | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | REGION E |  | NHP | UTILITIES | 1700000 | FY 2025: 850000; FY 2026: 850000
U-6110 | HIGHWAY | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 4 | Goldsboro Urban Area MPO |  | REGION A |  | NHP | CONSTRUCTION | 4100000 | FY 2027: 1595000; FY 2028: 2278000; FY 2029: 227000
U-6110 | HIGHWAY | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 4 | Goldsboro Urban Area MPO |  | REGION A |  | NHP | UTILITIES | 2200000 | FY 2025: 1100000; FY 2026: 1100000
U-6110 | HIGHWAY | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 4 | Goldsboro Urban Area MPO |  | REGION A |  | NHP | RIGHT-OF-WAY | 200000 | FY 2025: 200000
U-6110 | HIGHWAY | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 4 | Goldsboro Urban Area MPO |  | REGION A |  |  |  | 10000
U-6111 | HIGHWAY | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 4 | Upper Coastal Plain RPO |  | REGION A |  |  |  | 10000
U-6111 | HIGHWAY | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 4 | Upper Coastal Plain RPO |  | REGION A |  | T | RIGHT-OF-WAY | 700000 | FY 2027: 700000
U-6111 | HIGHWAY | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 4 | Upper Coastal Plain RPO |  | REGION A |  | T | UTILITIES | 400000 | FY 2027: 400000
U-6111 | HIGHWAY | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 4 | Upper Coastal Plain RPO |  | REGION A |  | T | CONSTRUCTION | 5400000 | FY 2029: 1413000; FY 2030: 3252000; FY 2031: 735000
U-6112 | HIGHWAY | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 56400000
U-6112 | HIGHWAY | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1600000
U-6112 | HIGHWAY | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6112 | HIGHWAY | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | 5 | Capital Area MPO | COORDINATE WITH R-2721 AND U-5746 | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 24099000
U-6113 | HIGHWAY | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | 4, 5 | Capital Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 83200000 | [11 empty] | 83200000
U-6113 | HIGHWAY | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | 4, 5 | Capital Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6113 | HIGHWAY | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | 4, 5 | Capital Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 7600000 | [11 empty] | 7600000
U-6113 | HIGHWAY | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTIONS. | 4, 5 | Capital Area MPO |  | NOT FUNDED |  | T | UTILITIES | 1500000 | [11 empty] | 1500000
U-6114 | HIGHWAY | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 900000
U-6114 | HIGHWAY | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6114 | HIGHWAY | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6114 | HIGHWAY | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 600000
U-6115 | HIGHWAY | NC 54 | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) TO SOUTH OF SR 2107 (WHITTEMORE ROAD) IN GRAHAM. IMPROVE SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTION, UPGRADE RAMP INTERSECTIONS AT I-40 / I-85, IMPROVE SR 2106 (WOODY ROAD) INTERSECTION. | 7 | Burlington-Graham MPO |  | REGION D |  |  |  | 10000
U-6115A | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1300000
U-6115A | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6115A | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3500000
U-6115B | HIGHWAY | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
U-6115B | HIGHWAY | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 8001000
U-6115B | HIGHWAY | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1100000
U-6115C | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 250000
U-6115C | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3200000
U-6115C | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2700000
U-6115D | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2100000
U-6115D | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 490000
U-6115D | HIGHWAY | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. | 7 | Burlington-Graham MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 120000
U-6116 | HIGHWAY | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 4500000 | [11 empty] | 4500000
U-6116 | HIGHWAY | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | UTILITIES | 1400000 | [11 empty] | 1400000
U-6116 | HIGHWAY | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6116 | HIGHWAY | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES WITH REDUCED CONFLICT INTERSECTIONS. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2200000 | [11 empty] | 2200000
U-6117 | HIGHWAY | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2027: 100000
U-6117 | HIGHWAY | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | UTILITIES | 300000 | FY 2027: 300000
U-6117 | HIGHWAY | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | CONSTRUCTION | 3800000 | FY 2028: 1696000; FY 2029: 2104000
U-6118 | HIGHWAY | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  |  |  | 10000
U-6118 | HIGHWAY | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | T | RIGHT-OF-WAY | 300000 | FY 2028: 300000
U-6118 | HIGHWAY | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | T | UTILITIES | 200000 | FY 2028: 200000
U-6118 | HIGHWAY | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | T | CONSTRUCTION | 4799000 | FY 2029: 814000; FY 2030: 2751000; FY 2031: 1234000
U-6119 | HIGHWAY | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2027: 100000
U-6119 | HIGHWAY | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | UTILITIES | 200000 | FY 2027: 200000
U-6119 | HIGHWAY | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | CONSTRUCTION | 4300000 | FY 2028: 2177000; FY 2029: 2123000
U-6120 | HIGHWAY | NC 98 (HOLLOWAY STREET) | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  |  |  | 10000
U-6120 | HIGHWAY | NC 98 (HOLLOWAY STREET) | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | T | CONSTRUCTION | 9999000 | FY 2030: 2097000; FY 2031: 5190000; FY 2032: 2712000
U-6120 | HIGHWAY | NC 98 (HOLLOWAY STREET) | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | T | UTILITIES | 1200000 | FY 2028: 600000; FY 2029: 600000
U-6120 | HIGHWAY | NC 98 (HOLLOWAY STREET) | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | 5 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | T | RIGHT-OF-WAY | 7000000 | FY 2028: 1723000; FY 2029: 2585000; FY 2030: 1292000; FY 2031: 700000; FY 2032: 700000
U-6121 | HIGHWAY | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH EB-6010 | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 13000000
U-6121 | HIGHWAY | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH EB-6010 | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1000000
U-6121 | HIGHWAY | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | COORDINATE WITH EB-6010 | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 39499000
U-6122 | HIGHWAY | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6122 | HIGHWAY | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5000000
U-6122 | HIGHWAY | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3500000
U-6122 | HIGHWAY | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | COORDINATE WITH U-5974 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 14200000
U-6123 | HIGHWAY | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | 13 | Greater Hickory MPO |  | NOT FUNDED |  |  |  | 10000
U-6123 | HIGHWAY | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 200000 | [11 empty] | 200000
U-6123 | HIGHWAY | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | UTILITIES | 300000 | [11 empty] | 300000
U-6123 | HIGHWAY | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 2000000 | [11 empty] | 2000000
U-6124 | HIGHWAY | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 3300000 | [11 empty] | 3300000
U-6124 | HIGHWAY | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | UTILITIES | 1800000 | [11 empty] | 1800000
U-6124 | HIGHWAY | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | 14 | French Broad River MPO |  | NOT FUNDED |  |  |  | 10000
U-6124 | HIGHWAY | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | 14 | French Broad River MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 23000000 | [11 empty] | 23000000
U-6125 | HIGHWAY | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6125 | HIGHWAY | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 6800000 | [11 empty] | 6800000
U-6125 | HIGHWAY | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 3500000 | [11 empty] | 3500000
U-6125 | HIGHWAY | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 14199000 | [11 empty] | 14199000
U-6126 | HIGHWAY | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 302000 | [11 empty] | 302000
U-6126 | HIGHWAY | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | NHP | UTILITIES | 126000 | [11 empty] | 126000
U-6126 | HIGHWAY | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  |  |  | 260000
U-6126 | HIGHWAY | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | 3 | Mid-Carolina RPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 2500000 | [11 empty] | 2500000
U-6127 | HIGHWAY | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | COORDINATE WITH R-5725 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6127 | HIGHWAY | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | COORDINATE WITH R-5725 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1500000
U-6127 | HIGHWAY | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | COORDINATE WITH R-5725 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1000000
U-6127 | HIGHWAY | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | COORDINATE WITH R-5725 | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9800000
U-6128 | HIGHWAY | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 3 | Wilmington Urban Area MPO |  | REGION B |  | BGANY | UTILITIES | 600000 | FY 2027: 600000
U-6128 | HIGHWAY | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 3 | Wilmington Urban Area MPO |  | REGION B |  | BGANY | CONSTRUCTION | 3600000 | FY 2029: 1908000; FY 2030: 1692000
U-6128 | HIGHWAY | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 3 | Wilmington Urban Area MPO |  | REGION B |  | BGANY | RIGHT-OF-WAY | 3700000 | FY 2027: 37000; FY 2028: 1443000; FY 2029: 1480000; FY 2030: 370000; FY 2031: 370000
U-6128 | HIGHWAY | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 3 | Wilmington Urban Area MPO |  | REGION B |  |  |  | 260000
U-6129 | HIGHWAY | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 110000
U-6129 | HIGHWAY | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 42000
U-6129 | HIGHWAY | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 440000
U-6129 | HIGHWAY | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 30000
U-6129 | HIGHWAY | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | UTILITIES | 10000
U-6129 | HIGHWAY | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | 7 | Greensboro Urban Area MPO | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 120000
U-6130 | HIGHWAY | US 29 | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2000000
U-6130 | HIGHWAY | US 29 | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6130 | HIGHWAY | US 29 | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6130 | HIGHWAY | US 29 | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO |  | REGION D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2500000
U-6131 | HIGHWAY | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 7 | Burlington-Graham MPO |  | REGION D |  | BG50200 | CONSTRUCTION | 3500000 | FY 2026: 866000; FY 2027: 2383000; FY 2028: 251000
U-6131 | HIGHWAY | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 7 | Burlington-Graham MPO |  | REGION D |  |  |  | 10000
U-6131 | HIGHWAY | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 7 | Burlington-Graham MPO |  | REGION D |  | BG50200 | RIGHT-OF-WAY | 4100000 | FY 2025: 2187000; FY 2026: 1093000; FY 2027: 410000; FY 2028: 410000
U-6131 | HIGHWAY | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 7 | Burlington-Graham MPO |  | REGION D |  | BG50200 | UTILITIES | 1100000 | FY 2025: 550000; FY 2026: 550000
U-6132 | HIGHWAY | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1500000
U-6132 | HIGHWAY | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
U-6132 | HIGHWAY | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 300000
U-6133 | HIGHWAY | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6133 | HIGHWAY | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7900000
U-6133 | HIGHWAY | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1100000
U-6133 | HIGHWAY | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | 6 | Fayetteville Area MPO |  | REGION C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6900000
U-6134 | HIGHWAY | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | T | RIGHT-OF-WAY | 500000 | FY 2024: 500000
U-6134 | HIGHWAY | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | T | UTILITIES | 100000 | FY 2024: 100000
U-6134 | HIGHWAY | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  |  |  | 10000
U-6134 | HIGHWAY | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | T | CONSTRUCTION | 25400000 | FY 2026: 3711000; FY 2027: 10009000; FY 2028: 7807000; FY 2029: 3873000
U-6135 | HIGHWAY | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Greater Hickory MPO |  | NOT FUNDED |  |  |  | 10000
U-6135 | HIGHWAY | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Greater Hickory MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 19700000 | [11 empty] | 19700000
U-6135 | HIGHWAY | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Greater Hickory MPO |  | NOT FUNDED |  | T | UTILITIES | 6100000 | [11 empty] | 6100000
U-6135 | HIGHWAY | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Greater Hickory MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 23299000 | [11 empty] | 23299000
U-6138 | HIGHWAY | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  |  |  | 10000
U-6138 | HIGHWAY | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | BG50200 | CONSTRUCTION | 800000 | FY 2026: 8000; FY 2027: 792000
U-6138 | HIGHWAY | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | BG50200 | UTILITIES | 300000 | FY 2025: 300000
U-6138 | HIGHWAY | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | BG50200 | RIGHT-OF-WAY | 5600000 | FY 2025: 56000; FY 2026: 4424000; FY 2027: 560000; FY 2028: 560000
U-6139 | HIGHWAY | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  |  |  | 10000
U-6139 | HIGHWAY | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 5900000 | [11 empty] | 5900000
U-6139 | HIGHWAY | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | NHP | UTILITIES | 1500000 | [11 empty] | 1500000
U-6139 | HIGHWAY | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 42000000 | [11 empty] | 42000000
U-6140 | HIGHWAY | NC 27 (EAST MAIN STREET) | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 34999000
U-6140 | HIGHWAY | NC 27 (EAST MAIN STREET) | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9300000
U-6140 | HIGHWAY | NC 27 (EAST MAIN STREET) | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6140 | HIGHWAY | NC 27 (EAST MAIN STREET) | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 33500000
U-6141 | HIGHWAY | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  |  |  | 10000
U-6141 | HIGHWAY | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 12200000 | [11 empty] | 12200000
U-6141 | HIGHWAY | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | NHP | UTILITIES | 900000 | [11 empty] | 900000
U-6141 | HIGHWAY | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 8800000 | [11 empty] | 8800000
U-6142 | HIGHWAY | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | UTILITIES | 4800000 | [11 empty] | 4800000
U-6142 | HIGHWAY | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 69302000 | [11 empty] | 69302000
U-6142 | HIGHWAY | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 32300000 | [11 empty] | 32300000
U-6142 | HIGHWAY | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  |  |  | 10000
U-6143 | HIGHWAY | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | REGION F |  | L | CONSTRUCTION | 2200000 | FY 2024: 22000; FY 2025: 1694000; FY 2026: 484000
U-6143 | HIGHWAY | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | REGION F |  | NHP | RIGHT-OF-WAY | 1600000 | FY 2023: 1600000
U-6143 | HIGHWAY | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | REGION F |  | NHP | UTILITIES | 1100000 | FY 2023: 1100000
U-6143 | HIGHWAY | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | REGION F |  | NHP | CONSTRUCTION | 2200000 | FY 2024: 22000; FY 2025: 1694000; FY 2026: 484000
U-6143 | HIGHWAY | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 12 | Gaston-Cleveland-Lincoln MPO | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS. | REGION F |  |  |  | 10000
U-6144 | HIGHWAY | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5500000 | [11 empty] | 5500000
U-6144 | HIGHWAY | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | UTILITIES | 4900000 | [11 empty] | 4900000
U-6144 | HIGHWAY | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  |  |  | 10000
U-6144 | HIGHWAY | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 21599000 | [11 empty] | 21599000
U-6145 | HIGHWAY | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | NOT FUNDED |  | T | CONSTRUCTION | 28801000 | [11 empty] | 28801000
U-6145 | HIGHWAY | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
U-6145 | HIGHWAY | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5200000 | [11 empty] | 5200000
U-6145 | HIGHWAY | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | 12 | Charlotte Regional TPO |  | NOT FUNDED |  | T | UTILITIES | 3300000 | [11 empty] | 3300000
U-6146 | HIGHWAY | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | T | RIGHT-OF-WAY | 5800000 | FY 2023: 2900000
U-6146 | HIGHWAY | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | T | UTILITIES | 5500000 | FY 2023: 2475000
U-6146 | HIGHWAY | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | T | CONSTRUCTION | 20098000 | FY 2024: 2217000; FY 2025: 7439000; FY 2026: 6078000; FY 2027: 4364000
U-6146 | HIGHWAY | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  |  |  | 10000
U-6146 | HIGHWAY | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | HFB | CONSTRUCTION | 14502000 | FY 2024: 1600000; FY 2025: 5367000; FY 2026: 4386000; FY 2027: 3149000
U-6146 | HIGHWAY | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); | REGION F |  | T | BUILD NC ROW | 2580000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 516000
U-6147 | HIGHWAY | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6147 | HIGHWAY | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 12001000 | [11 empty] | 12001000
U-6147 | HIGHWAY | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 5900000 | [11 empty] | 5900000
U-6147 | HIGHWAY | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 800000 | [11 empty] | 800000
U-6148 | HIGHWAY | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  |  |  | 260000
U-6148 | HIGHWAY | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 329000 | [11 empty] | 329000
U-6148 | HIGHWAY | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 140000 | [11 empty] | 140000
U-6148 | HIGHWAY | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 750000 | [11 empty] | 750000
U-6149 | HIGHWAY | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | 4 | Rocky Mount Urban Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 2200000 | [11 empty] | 2200000
U-6149 | HIGHWAY | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | 4 | Rocky Mount Urban Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 137000000 | [11 empty] | 137000000
U-6149 | HIGHWAY | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | 4 | Rocky Mount Urban Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6149 | HIGHWAY | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | 4 | Rocky Mount Urban Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 11800000 | [11 empty] | 11800000
U-6150 | HIGHWAY | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  |  |  | 10000
U-6150 | HIGHWAY | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 300000 | [11 empty] | 300000
U-6150 | HIGHWAY | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | UTILITIES | 1500000 | [11 empty] | 1500000
U-6150 | HIGHWAY | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 12 | Gaston-Cleveland-Lincoln MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 1700000 | [11 empty] | 1700000
U-6151 | HIGHWAY | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | 12 | Greater Hickory MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 17300000 | [11 empty] | 17300000
U-6151 | HIGHWAY | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | 12 | Greater Hickory MPO |  | NOT FUNDED |  | T | UTILITIES | 3500000 | [11 empty] | 3500000
U-6151 | HIGHWAY | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | 12 | Greater Hickory MPO |  | NOT FUNDED |  |  |  | 10000
U-6151 | HIGHWAY | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | 12 | Greater Hickory MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 55000000 | [11 empty] | 55000000
U-6152 | HIGHWAY | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6152 | HIGHWAY | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | NHP | RIGHT-OF-WAY | 17500000 | [11 empty] | 17500000
U-6152 | HIGHWAY | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | NHP | UTILITIES | 19700000 | [11 empty] | 19700000
U-6152 | HIGHWAY | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | NHP | CONSTRUCTION | 19900000 | [11 empty] | 19900000
U-6153 | HIGHWAY | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | DIVISION 12 |  | O | CONSTRUCTION | 2550000 | FY 2024: 2550000
U-6153 | HIGHWAY | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | DIVISION 12 |  | T | CONSTRUCTION | 2098000 | FY 2024: 1049000; FY 2025: 1049000
U-6153 | HIGHWAY | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | DIVISION 12 |  |  |  | 10000
U-6153 | HIGHWAY | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT. | DIVISION 12 |  | BA | ENGINEERING | 452000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | ENGINEERING | 68000 | FY 2023: 68000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | CONSTRUCTION | 373000 | FY 2023: 373000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | RIGHT-OF-WAY | 50000 | FY 2023: 50000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGDA | RIGHT-OF-WAY | 179000 | FY 2023: 179000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGDA | ENGINEERING | 273000 | FY 2023: 273000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | CONSTRUCTION | 1494000 | FY 2023: 1494000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 200000 | FY 2023: 200000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  |  |  | 120000
U-6154 | HIGHWAY | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 9 | Winston-Salem Urban Area MPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS | DIVISION 9 |  | L | RIGHT-OF-WAY | 45000 | FY 2023: 45000
U-6157 | HIGHWAY | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  |  |  | 10000
U-6157 | HIGHWAY | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  | BGANY | RIGHT-OF-WAY | 9200000 | FY 2023: 92000; FY 2024: 4237000; FY 2025: 3031000; FY 2026: 920000; FY 2027: 920000
U-6157 | HIGHWAY | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  | BGANY | UTILITIES | 10200000 | FY 2023: 5100000; FY 2024: 5100000
U-6157 | HIGHWAY | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 11 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 11 |  | BGANY | CONSTRUCTION | 23901000 | FY 2025: 3530000; FY 2026: 9148000; FY 2027: 7115000; FY 2028: 4108000
U-6158 | HIGHWAY | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 14 | French Broad River MPO |  | DIVISION 14 |  |  |  | 10000
U-6158 | HIGHWAY | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 14 | French Broad River MPO |  | DIVISION 14 |  | T | CONSTRUCTION | 3101000 | FY 2030: 982000; FY 2031: 1858000; FY 2032: 261000
U-6158 | HIGHWAY | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 14 | French Broad River MPO |  | DIVISION 14 |  | T | UTILITIES | 200000 | FY 2028: 200000
U-6158 | HIGHWAY | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 14 | French Broad River MPO |  | DIVISION 14 |  | T | RIGHT-OF-WAY | 500000 | FY 2028: 250000; FY 2029: 250000
U-6159 | HIGHWAY | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 14 | French Broad River MPO |  | DIVISION 14 |  |  |  | 10000
U-6159 | HIGHWAY | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 14 | French Broad River MPO |  | DIVISION 14 |  | BGANY | RIGHT-OF-WAY | 14500000 | FY 2028: 4350000; FY 2029: 5800000; FY 2030: 1450000; FY 2031: 1450000; FY 2032: 1450000
U-6159 | HIGHWAY | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 14 | French Broad River MPO |  | DIVISION 14 |  | BGANY | UTILITIES | 2300000 | FY 2028: 1150000; FY 2029: 1150000
U-6159 | HIGHWAY | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 14 | French Broad River MPO |  | DIVISION 14 |  | BGANY | CONSTRUCTION | 13401000 | FY 2030: 4729000; FY 2031: 5423000; FY 2032: 3249000
U-6161 | HIGHWAY | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | DIVISION 11 |  | NHP | RIGHT-OF-WAY | 800000 | FY 2025: 400000; FY 2026: 400000
U-6161 | HIGHWAY | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | DIVISION 11 |  | NHP | UTILITIES | 200000 | FY 2025: 200000
U-6161 | HIGHWAY | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | DIVISION 11 |  |  |  | 10000
U-6161 | HIGHWAY | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 11 | Greater Hickory MPO | COORDINATE WITH U-4700A | DIVISION 11 |  | NHP | CONSTRUCTION | 4000000 | FY 2027: 1279000; FY 2028: 2237000; FY 2029: 484000
U-6162 | HIGHWAY | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6162 | HIGHWAY | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 13200000
U-6162 | HIGHWAY | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 800000
U-6162 | HIGHWAY | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | 13 | French Broad River MPO |  | DIVISION 13 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 6000000
U-6163 | HIGHWAY | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 13 | French Broad River MPO | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS | DIVISION 13 |  | S | RIGHT-OF-WAY | 100000 | FY 2024: 100000
U-6163 | HIGHWAY | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 13 | French Broad River MPO | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS | DIVISION 13 |  | T | CONSTRUCTION | 2000000 | FY 2024: 484000; FY 2025: 1516000
U-6163 | HIGHWAY | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 13 | French Broad River MPO | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS | DIVISION 13 |  | S | CONSTRUCTION | 400000 | FY 2024: 97000; FY 2025: 303000
U-6163 | HIGHWAY | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 13 | French Broad River MPO | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS | DIVISION 13 |  | S | UTILITIES | 300000 | FY 2024: 300000
U-6164 | HIGHWAY | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | 13 | Greater Hickory MPO |  | NOT FUNDED |  |  |  | 10000
U-6164 | HIGHWAY | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | BGLT5 | RIGHT-OF-WAY | 4000000 | [11 empty] | 4000000
U-6164 | HIGHWAY | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | BGLT5 | UTILITIES | 6500000 | [11 empty] | 6500000
U-6164 | HIGHWAY | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | 13 | Greater Hickory MPO |  | NOT FUNDED |  | BGLT5 | CONSTRUCTION | 36300000 | [11 empty] | 36300000
U-6165 | HIGHWAY | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | RIGHT-OF-WAY | 21255000 | [11 empty] | 21255000
U-6165 | HIGHWAY | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | UTILITIES | 2000000 | [11 empty] | 2000000
U-6165 | HIGHWAY | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
U-6165 | HIGHWAY | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | CONSTRUCTION | 9400000 | [11 empty] | 9400000
U-6166 | HIGHWAY | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
U-6166 | HIGHWAY | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 6600000 | [11 empty] | 6600000
U-6166 | HIGHWAY | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | UTILITIES | 500000 | [11 empty] | 500000
U-6166 | HIGHWAY | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | CONSTRUCTION | 8498000 | [11 empty] | 8498000
U-6167 | HIGHWAY | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | RIGHT-OF-WAY | 94300000 | [11 empty] | 94300000
U-6167 | HIGHWAY | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | UTILITIES | 1500000 | [11 empty] | 1500000
U-6167 | HIGHWAY | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | CONSTRUCTION | 31401000 | [11 empty] | 31401000
U-6167 | HIGHWAY | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
U-6168 | HIGHWAY | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
U-6168 | HIGHWAY | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 9700000 | [11 empty] | 9700000
U-6168 | HIGHWAY | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | UTILITIES | 1600000 | [11 empty] | 1600000
U-6168 | HIGHWAY | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | CONSTRUCTION | 18800000 | [11 empty] | 18800000
U-6169 | HIGHWAY | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | RIGHT-OF-WAY | 3000000 | [11 empty] | 3000000
U-6169 | HIGHWAY | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | UTILITIES | 2800000 | [11 empty] | 2800000
U-6169 | HIGHWAY | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
U-6169 | HIGHWAY | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | BGANY | CONSTRUCTION | 26100000 | [11 empty] | 26100000
U-6170 | HIGHWAY | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  |  |  | 10000
U-6170 | HIGHWAY | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGANY | RIGHT-OF-WAY | 3000000 | FY 2027: 686000; FY 2028: 1371000; FY 2029: 343000; FY 2030: 300000; FY 2031: 300000
U-6170 | HIGHWAY | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGANY | UTILITIES | 1400000 | FY 2027: 14000; FY 2028: 1386000
U-6170 | HIGHWAY | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | BGANY | CONSTRUCTION | 8800000 | FY 2029: 4130000; FY 2030: 3822000; FY 2031: 848000
U-6171 | HIGHWAY | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 900000 | [11 empty] | 900000
U-6171 | HIGHWAY | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | UTILITIES | 2300000 | [11 empty] | 2300000
U-6171 | HIGHWAY | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  | T | CONSTRUCTION | 19500000 | [11 empty] | 19500000
U-6171 | HIGHWAY | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | 10 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
U-6172 | HIGHWAY | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | 14 | French Broad River MPO, Southwestern RPO |  | DIVISION 14 |  |  |  | 10000
U-6172A | HIGHWAY | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | BLUE RIDGE PARKWAY INTERCHANGE IMPROVEMENTS. | 14 | Southwestern RPO, French Broad River MPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | RIGHT-OF-WAY | 110000
U-6172A | HIGHWAY | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | BLUE RIDGE PARKWAY INTERCHANGE IMPROVEMENTS. | 14 | Southwestern RPO, French Broad River MPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | UTILITIES | 110000
U-6172A | HIGHWAY | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | BLUE RIDGE PARKWAY INTERCHANGE IMPROVEMENTS. | 14 | Southwestern RPO, French Broad River MPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 1700000
U-6172B | HIGHWAY | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | 14 | French Broad River MPO, Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | RIGHT-OF-WAY | 80000
U-6172B | HIGHWAY | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | 14 | French Broad River MPO, Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | UTILITIES | 250000
U-6172B | HIGHWAY | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD). MODERNIZE ROADWAY. | 14 | French Broad River MPO, Southwestern RPO |  | DIVISION 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 2800000
U-6173 | HIGHWAY | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | 13 | French Broad River MPO, Land-of-Sky RPO |  | NOT FUNDED |  |  |  | 10000
U-6173 | HIGHWAY | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | 13 | French Broad River MPO, Land-of-Sky RPO |  | NOT FUNDED |  | BGANY | RIGHT-OF-WAY | 300000 | [11 empty] | 300000
U-6173 | HIGHWAY | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | 13 | French Broad River MPO, Land-of-Sky RPO |  | NOT FUNDED |  | BGANY | UTILITIES | 600000 | [11 empty] | 600000
U-6173 | HIGHWAY | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. | 13 | French Broad River MPO, Land-of-Sky RPO |  | NOT FUNDED |  | BGANY | CONSTRUCTION | 33249000 | [11 empty] | 33249000
U-6175 | HIGHWAY | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | 12 | Charlotte Regional TPO |  | NOT FUNDED |  | BGLT5 | UTILITIES | 3540000 | [11 empty] | 3540000
U-6175 | HIGHWAY | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | 12 | Charlotte Regional TPO |  | NOT FUNDED |  | BGLT5 | CONSTRUCTION | 28602000 | [11 empty] | 28602000
U-6175 | HIGHWAY | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | 12 | Charlotte Regional TPO |  | NOT FUNDED |  | BGLT5 | RIGHT-OF-WAY | 21800000 | [11 empty] | 21800000
U-6175 | HIGHWAY | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | 12 | Charlotte Regional TPO |  | NOT FUNDED |  |  |  | 10000
U-6176 | HIGHWAY | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Greater Hickory MPO |  | DIVISION 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 26200000
U-6176 | HIGHWAY | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Greater Hickory MPO |  | DIVISION 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 2900000
U-6176 | HIGHWAY | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Greater Hickory MPO |  | DIVISION 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 20499000
U-6176 | HIGHWAY | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 12 | Greater Hickory MPO |  | DIVISION 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6181 | HIGHWAY | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6181 | HIGHWAY | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1400000
U-6181 | HIGHWAY | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 216000
U-6182 | HIGHWAY | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 180000
U-6182 | HIGHWAY | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1100000
U-6182 | HIGHWAY | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1200000
U-6183 | HIGHWAY | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 400000
U-6183 | HIGHWAY | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1200000
U-6183 | HIGHWAY | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2900000
U-6184 | HIGHWAY | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
U-6184 | HIGHWAY | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 8400000
U-6184 | HIGHWAY | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5800000
U-6185 | HIGHWAY | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 480000
U-6185 | HIGHWAY | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 160000
U-6185 | HIGHWAY | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 1040000
U-6185 | HIGHWAY | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | RIGHT-OF-WAY | 120000
U-6185 | HIGHWAY | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | UTILITIES | 40000
U-6185 | HIGHWAY | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | 7 | Greensboro Urban Area MPO | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 260000
U-6186 | HIGHWAY | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 600000
U-6186 | HIGHWAY | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1500000
U-6186 | HIGHWAY | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2850000
U-6187 | HIGHWAY | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | BGANY | RIGHT-OF-WAY | 3400000 | FY 2024: 1360000; FY 2025: 1360000; FY 2026: 340000; FY 2027: 340000
U-6187 | HIGHWAY | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | BGANY | UTILITIES | 300000 | FY 2024: 300000
U-6187 | HIGHWAY | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | T | BUILD NC CON | 6435000 |  |  |  | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 3003000
U-6187 | HIGHWAY | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 9 | Winston-Salem Urban Area MPO | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE) | DIVISION 9 |  | T | CONSTRUCTION | 23600000 | FY 2025: 7225000; FY 2026: 11921000; FY 2027: 1329000; FY 2028: 2625000; FY 2029: 500000
U-6188 | HIGHWAY | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | UTILITIES | 400000 | FY 2027: 400000
U-6188 | HIGHWAY | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | CONSTRUCTION | 4100000 | FY 2029: 1173000; FY 2030: 2521000; FY 2031: 406000
U-6188 | HIGHWAY | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | RIGHT-OF-WAY | 1100000 | FY 2027: 160000; FY 2028: 480000; FY 2029: 240000; FY 2030: 110000; FY 2031: 110000
U-6189 | HIGHWAY | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | RIGHT-OF-WAY | 10700000 | FY 2027: 451000; FY 2028: 5406000; FY 2029: 2703000; FY 2030: 1070000; FY 2031: 1070000
U-6189 | HIGHWAY | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | UTILITIES | 800000 | FY 2027: 800000
U-6189 | HIGHWAY | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | CONSTRUCTION | 12400000 | FY 2029: 2422000; FY 2030: 6053000; FY 2031: 3925000
U-6190 | HIGHWAY | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | RIGHT-OF-WAY | 1700000 | FY 2027: 8000; FY 2028: 792000; FY 2029: 560000; FY 2030: 170000; FY 2031: 170000
U-6190 | HIGHWAY | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | UTILITIES | 400000 | FY 2027: 400000
U-6190 | HIGHWAY | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | T | CONSTRUCTION | 3100000 | FY 2029: 1010000; FY 2030: 2090000
U-6191 | HIGHWAY | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | 8 | High Point Urban Area MPO |  | DIVISION 8 |  | T | RIGHT-OF-WAY | 5701000 | FY 2028: 1086000; FY 2029: 2606000; FY 2030: 869000; FY 2031: 570000; FY 2032: 570000
U-6191 | HIGHWAY | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | 8 | High Point Urban Area MPO |  | DIVISION 8 |  | T | UTILITIES | 4700000 | FY 2028: 2350000; FY 2029: 2350000
U-6191 | HIGHWAY | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | 8 | High Point Urban Area MPO |  | DIVISION 8 |  | T | CONSTRUCTION | 12400000 | FY 2030: 3363000; FY 2031: 6120000; FY 2032: 2917000
U-6192 | HIGHWAY | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | 7, 8 | Triangle Area RPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7, 8 |  | T | RIGHT-OF-WAY | 9299000 | FY 2028: 451000; FY 2029: 2705000; FY 2030: 2705000; FY 2031: 1578000; FY 2032: 1860000
U-6192 | HIGHWAY | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | 7, 8 | Triangle Area RPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7, 8 |  | T | UTILITIES | 30000000 | FY 2028: 15000000; FY 2029: 15000000
U-6192 | HIGHWAY | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | 7, 8 | Triangle Area RPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 7, 8 |  | T | CONSTRUCTION | 78400000 | FY 2031: 10033000; FY 2032: 23380000; FY 2033: 20480000 | 24507000
U-6193 | HIGHWAY | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 8500000 | [11 empty] | 8500000
U-6193 | HIGHWAY | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | UTILITIES | 770000 | [11 empty] | 770000
U-6193 | HIGHWAY | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | 5 | Capital Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 12400000 | [11 empty] | 12400000
U-6194 | HIGHWAY | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2027: 100000
U-6194 | HIGHWAY | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | CONSTRUCTION | 3200000 | FY 2028: 1881000; FY 2029: 1319000
U-6194 | HIGHWAY | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM | 5 | Capital Area MPO |  | DIVISION 5 |  | BGANY | UTILITIES | 360000 | FY 2027: 360000
U-6195 | HIGHWAY | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6195 | HIGHWAY | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 9000000 | [11 empty] | 9000000
U-6195 | HIGHWAY | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 2100000 | [11 empty] | 2100000
U-6195 | HIGHWAY | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 21601000 | [11 empty] | 21601000
U-6196 | HIGHWAY | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 9500000 | [11 empty] | 9500000
U-6196 | HIGHWAY | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 2900000 | [11 empty] | 2900000
U-6196 | HIGHWAY | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6196 | HIGHWAY | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | 2 | Greenville Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 9300000 | [11 empty] | 9300000
U-6197 | HIGHWAY | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  |  |  | 10000
U-6197 | HIGHWAY | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | RIGHT-OF-WAY | 900000 | FY 2027: 900000
U-6197 | HIGHWAY | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | UTILITIES | 500000 | FY 2027: 500000
U-6197 | HIGHWAY | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 2 | Greenville Urban Area MPO |  | DIVISION 2 |  | T | CONSTRUCTION | 1600000 | FY 2029: 732000; FY 2030: 868000
U-6198 | HIGHWAY | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2 | New Bern Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 18000000 | [11 empty] | 18000000
U-6198 | HIGHWAY | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2 | New Bern Area MPO |  | NOT FUNDED |  | T | UTILITIES | 3100000 | [11 empty] | 3100000
U-6198 | HIGHWAY | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2 | New Bern Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6198 | HIGHWAY | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2 | New Bern Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 24700000 | [11 empty] | 24700000
U-6199 | HIGHWAY | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  |  |  | 10000
U-6199 | HIGHWAY | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | RIGHT-OF-WAY | 100000 | FY 2028: 100000
U-6199 | HIGHWAY | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | UTILITIES | 950000 | FY 2028: 950000
U-6199 | HIGHWAY | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | CONSTRUCTION | 15360000 | FY 2030: 2841000; FY 2031: 7323000; FY 2032: 4754000; FY 2033: 442000
U-6200 | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 2127000 | [11 empty] | 2127000
U-6200 | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | UTILITIES | 1137000 | [11 empty] | 1137000
U-6200 | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6200 | HIGHWAY | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 3 | Jacksonville Urban Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 8800000 | [11 empty] | 8800000
U-6201 | HIGHWAY | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  |  |  | 10000
U-6201 | HIGHWAY | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | RIGHT-OF-WAY | 4200000 | FY 2028: 1120000; FY 2029: 1493000; FY 2030: 747000; FY 2031: 420000; FY 2032: 420000
U-6201 | HIGHWAY | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | UTILITIES | 400000 | FY 2028: 400000
U-6201 | HIGHWAY | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | T | CONSTRUCTION | 4498000 | FY 2030: 1428000; FY 2031: 2784000; FY 2032: 286000
U-6202 | HIGHWAY | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | DIVISION 3 |  | T | BUILD NC ROW | 6435000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 1287000
U-6202 | HIGHWAY | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | DIVISION 3 |  | T | CONSTRUCTION | 33601000 | FY 2025: 336000; FY 2026: 11328000; FY 2027: 11416000; FY 2028: 7874000; FY 2029: 2647000
U-6202 | HIGHWAY | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | DIVISION 3 |  |  |  | 10000
U-6202 | HIGHWAY | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | DIVISION 3 |  | T | RIGHT-OF-WAY | 6400000 | FY 2023: 6300000
U-6202 | HIGHWAY | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE). | DIVISION 3 |  | T | UTILITIES | 5300000 | FY 2023: 2650000
U-6203 | HIGHWAY | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 4 | Capital Area MPO |  | DIVISION 4 |  |  |  | 10000
U-6203 | HIGHWAY | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 28963000 | FY 2026: 6620000; FY 2027: 13241000; FY 2028: 3310000; FY 2029: 2896000; FY 2030: 2896000
U-6203 | HIGHWAY | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | UTILITIES | 4360000 | FY 2026: 2180000; FY 2027: 2180000
U-6203 | HIGHWAY | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 45201000 | FY 2028: 8630000; FY 2029: 16609000; FY 2030: 12377000; FY 2031: 7585000
U-6204 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  |  |  | 10000
U-6204 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | BG50200 | CONSTRUCTION | 11400000 | FY 2028: 2325000; FY 2029: 5950000; FY 2030: 3125000
U-6204 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | BG50200 | RIGHT-OF-WAY | 3500000 | FY 2025: 35000; FY 2026: 729000; FY 2027: 1018000; FY 2028: 1018000; FY 2029: 350000; FY 2030: 350000
U-6204 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | BG50200 | UTILITIES | 2400000 | FY 2025: 1200000; FY 2026: 1200000
U-6205 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  |  |  | 10000
U-6205 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 1900000 | FY 2027: 19000; FY 2028: 965000; FY 2029: 536000; FY 2030: 190000; FY 2031: 190000
U-6205 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | UTILITIES | 1000000 | FY 2027: 500000; FY 2028: 500000
U-6205 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 20300000 | FY 2029: 3310000; FY 2030: 8747000; FY 2031: 5993000; FY 2032: 2250000
U-6206 | HIGHWAY | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  |  |  | 10000
U-6206 | HIGHWAY | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 5600000 | FY 2029: 1465000; FY 2030: 3372000; FY 2031: 763000
U-6206 | HIGHWAY | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | UTILITIES | 900000 | FY 2027: 900000
U-6206 | HIGHWAY | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 2500000 | FY 2027: 480000; FY 2028: 960000; FY 2029: 560000; FY 2030: 250000; FY 2031: 250000
U-6207 | HIGHWAY | NC 581 (BILL LANE BOULEVARD) | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  |  |  | 10000
U-6207 | HIGHWAY | NC 581 (BILL LANE BOULEVARD) | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 1700000 | FY 2027: 136000; FY 2028: 816000; FY 2029: 408000; FY 2030: 170000; FY 2031: 170000
U-6207 | HIGHWAY | NC 581 (BILL LANE BOULEVARD) | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | UTILITIES | 400000 | FY 2027: 400000
U-6207 | HIGHWAY | NC 581 (BILL LANE BOULEVARD) | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | 4 | Goldsboro Urban Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 5001000 | FY 2029: 1386000; FY 2030: 3105000; FY 2031: 510000
U-6208 | HIGHWAY | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 3000000 | FY 2027: 240000; FY 2028: 1440000; FY 2029: 720000; FY 2030: 300000; FY 2031: 300000
U-6208 | HIGHWAY | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | UTILITIES | 10000000 | FY 2027: 5000000; FY 2028: 5000000
U-6208 | HIGHWAY | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 4 | Capital Area MPO |  | DIVISION 4 |  |  |  | 10000
U-6208 | HIGHWAY | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 14499000 | FY 2029: 2872000; FY 2030: 7361000; FY 2031: 4266000
U-6209 | HIGHWAY | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | 6 | Fayetteville Area MPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | 10000
U-6209 | HIGHWAY | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | 6 | Fayetteville Area MPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 32300000
U-6209 | HIGHWAY | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | 6 | Fayetteville Area MPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 17300000
U-6209 | HIGHWAY | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | 6 | Fayetteville Area MPO |  | DIVISION 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 36400000
U-6210 | HIGHWAY | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6210 | HIGHWAY | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 22800000 | [11 empty] | 22800000
U-6210 | HIGHWAY | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 15000000 | [11 empty] | 15000000
U-6210 | HIGHWAY | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | UTILITIES | 7900000 | [11 empty] | 7900000
U-6211 | HIGHWAY | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1100000
U-6211 | HIGHWAY | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
U-6211 | HIGHWAY | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2100000
U-6212 | HIGHWAY | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1500000
U-6212 | HIGHWAY | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 200000
U-6212 | HIGHWAY | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 100000
U-6213 | HIGHWAY | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | CONSTRUCTION | 22500000 | [11 empty] | 22500000
U-6213 | HIGHWAY | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | UTILITIES | 19750000 | [11 empty] | 19750000
U-6213 | HIGHWAY | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  |  |  | 10000
U-6213 | HIGHWAY | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | 6 | Fayetteville Area MPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 16600000 | [11 empty] | 16600000
U-6214 | HIGHWAY | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3401000
U-6214 | HIGHWAY | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2400000
U-6214 | HIGHWAY | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | 7 | Burlington-Graham MPO |  | DIVISION 7 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5600000
U-6215 | HIGHWAY | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | 2 | Greenville Urban Area MPO, Mid-East RPO |  | NOT FUNDED |  |  |  | 10000
U-6215 | HIGHWAY | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | 2 | Greenville Urban Area MPO, Mid-East RPO |  | NOT FUNDED |  | T | CONSTRUCTION | 70099000 | [11 empty] | 70099000
U-6215 | HIGHWAY | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | 2 | Greenville Urban Area MPO, Mid-East RPO |  | NOT FUNDED |  | T | RIGHT-OF-WAY | 30100000 | [11 empty] | 30100000
U-6215 | HIGHWAY | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | 2 | Greenville Urban Area MPO, Mid-East RPO |  | NOT FUNDED |  | T | UTILITIES | 2900000 | [11 empty] | 2900000
U-6216 | HIGHWAY | SR 1010 (CLEVELAND ROAD) | NC 42 TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | RIGHT-OF-WAY | 34300000 | FY 2027: 9147000; FY 2028: 12195000; FY 2029: 6098000; FY 2030: 3430000; FY 2031: 3430000
U-6216 | HIGHWAY | SR 1010 (CLEVELAND ROAD) | NC 42 TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | UTILITIES | 6654000 | FY 2027: 3327000; FY 2028: 3327000
U-6216 | HIGHWAY | SR 1010 (CLEVELAND ROAD) | NC 42 TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | 4 | Capital Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 43700000 | FY 2029: 6118000; FY 2030: 16169000; FY 2031: 12673000; FY 2032: 8740000
U-6217 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 5 | Capital Area MPO |  | DIVISION 5 |  |  |  | 10000
U-6217 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | RIGHT-OF-WAY | 13401000 | FY 2028: 346000; FY 2029: 4150000; FY 2030: 4150000; FY 2031: 2075000; FY 2032: 2680000
U-6217 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | UTILITIES | 1142000 | FY 2028: 571000; FY 2029: 571000
U-6217 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 5 | Capital Area MPO |  | DIVISION 5 |  | T | CONSTRUCTION | 27100000 | FY 2031: 4188000; FY 2032: 10666000; FY 2033: 8029000 | 4217000
U-6218 | HIGHWAY | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | 4, 5, 6 | Capital Area MPO |  | DIVISION 4, 5, 6 |  | TADA | CONSTRUCTION | 21180000 | 1554000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000 | 2110000
U-6219 | HIGHWAY | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5, 7, 8 |  | TADA | CONSTRUCTION | 9449000 | 1159000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000
U-6220 | HIGHWAY | VARIOUS | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | TADA | CONSTRUCTION | 11164000 | 2325000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000 | 744000
U-6221 | HIGHWAY | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | 9 | Winston-Salem Urban Area MPO |  | DIVISION 9 |  | TADA | CONSTRUCTION | 12941000 | 1868000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000 | 933000
U-6222 | HIGHWAY | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | EXEMPT |  | BGDA | ENGINEERING | 120000
U-6222 | HIGHWAY | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | EXEMPT |  | S | CONSTRUCTION | 210000
U-6222 | HIGHWAY | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | EXEMPT |  | S | ENGINEERING | 30000
U-6222 | HIGHWAY | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 5 | Capital Area MPO | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION | EXEMPT |  | BGDA | CONSTRUCTION | 840000
U-6223 | HIGHWAY | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | DIVISION 4 |  | BGDA | RIGHT-OF-WAY | 1735000
U-6223 | HIGHWAY | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | DIVISION 4 |  | BGDA | CONSTRUCTION | 7500000 | FY 2023: 5742000; FY 2024: 1683000
U-6223 | HIGHWAY | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | DIVISION 4 |  | HF | CONSTRUCTION | 1000000 | FY 2023: 766000; FY 2024: 224000
U-6223 | HIGHWAY | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | DIVISION 4 |  | L | CONSTRUCTION | 1500000 | FY 2023: 1148000; FY 2024: 337000
U-6223 | HIGHWAY | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | DIVISION 4 |  | S | RIGHT-OF-WAY | 434000
U-6223 | HIGHWAY | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 4 | Capital Area MPO | UNDER CONSTRUCTION. S FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS. | DIVISION 4 |  | S | CONSTRUCTION | 1250000 | FY 2023: 957000; FY 2024: 281000
U-6225 | HIGHWAY | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  |  |  | 28000
U-6225 | HIGHWAY | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 56000
U-6225 | HIGHWAY | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | BGDA | CONSTRUCTION | 1560000 | FY 2023: 1560000
U-6225 | HIGHWAY | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | L | RIGHT-OF-WAY | 19000
U-6225 | HIGHWAY | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | L | CONSTRUCTION | 520000 | FY 2023: 520000
U-6227 | HIGHWAY | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 5 |  | BGDA | CONSTRUCTION | 3645000 | FY 2023: 3645000
U-6227 | HIGHWAY | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 5 |  | L | RIGHT-OF-WAY | 3096000
U-6227 | HIGHWAY | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 2533000
U-6227 | HIGHWAY | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | DIVISION 5 |  | L | CONSTRUCTION | 4455000 | FY 2023: 4455000
U-6229 | HIGHWAY | NC 24 (BRAGG BOULEVARD) | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 1800000 | FY 2023: 1800000
U-6229 | HIGHWAY | NC 24 (BRAGG BOULEVARD) | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | UTILITIES | 200000
U-6229 | HIGHWAY | NC 24 (BRAGG BOULEVARD) | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | T | CONSTRUCTION | 3600000 | FY 2023: 3600000
U-6230 | HIGHWAY | WALK OFF WAY | CONSTRUCT WALK OFF WAY EXTENSION FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR HAAKON INDUSTRIES. AWARD AMOUNT = $1,300,000 - COMPLETE. | DIVISION 13 |  | T | CONSTRUCTION | 1300000
U-6231 | HIGHWAY | NEW ROUTE | SR 4001 (REYNOLDS BOULEVARD) TO SR 2264 (AKRON DRIVE) AT INTERSECTION OF SR 1763 (INDIANA AVENUE) IN WINSTON-SALEM. CONSTRUCT ACCESS ROAD. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL. | DIVISION 9 |  | T | CONSTRUCTION | 1300000
U-6231 | HIGHWAY | NEW ROUTE | SR 4001 (REYNOLDS BOULEVARD) TO SR 2264 (AKRON DRIVE) AT INTERSECTION OF SR 1763 (INDIANA AVENUE) IN WINSTON-SALEM. CONSTRUCT ACCESS ROAD. | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL. | DIVISION 9 |  | L | CONSTRUCTION | 2700000
U-6233 | HIGHWAY | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | DIVISION 3 |  | S | CONSTRUCTION | 51000 | FY 2023: 51000
U-6233 | HIGHWAY | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | DIVISION 3 |  | S | RIGHT-OF-WAY | 8000
U-6233 | HIGHWAY | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | DIVISION 3 |  | S | ENGINEERING | 4000
U-6233 | HIGHWAY | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | DIVISION 3 |  | BGDA | CONSTRUCTION | 205000 | FY 2023: 205000
U-6233 | HIGHWAY | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | DIVISION 3 |  | BGDA | ENGINEERING | 14000
U-6233 | HIGHWAY | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS. | DIVISION 3 |  | BGDA | RIGHT-OF-WAY | 32000
U-6234 | HIGHWAY | WILMINGTON | WILMINGTON MULTI-MODAL TRANSPORTATION CENTER PHASE 1B. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | CONSTRUCTION | 1290000
U-6234 | HIGHWAY | WILMINGTON | WILMINGTON MULTI-MODAL TRANSPORTATION CENTER PHASE 1B. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | L | ENGINEERING | 63000
U-6234 | HIGHWAY | WILMINGTON | WILMINGTON MULTI-MODAL TRANSPORTATION CENTER PHASE 1B. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGDA | CONSTRUCTION | 5160000
U-6234 | HIGHWAY | WILMINGTON | WILMINGTON MULTI-MODAL TRANSPORTATION CENTER PHASE 1B. | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 3 |  | BGDA | ENGINEERING | 254000
U-6235 | HIGHWAY | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | CONSTRUCTION | 627000 | FY 2024: 627000
U-6235 | HIGHWAY | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | ENGINEERING | 97000
U-6235 | HIGHWAY | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | L | CONSTRUCTION | 157000 | FY 2024: 157000
U-6235 | HIGHWAY | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. | 3 | Wilmington Urban Area MPO |  | DIVISION 3 |  | BGDA | ENGINEERING | 390000
U-6237 | HIGHWAY | SR 2120 (LONG FERRY ROAD) | SR 2182 (I-85 SERVICE ROAD) NEAR SPENCER. CONSTRUCT RIGHT-TURN LANE ON SR 2120, AND CONSTRUCT CUL-DE-SAC, REMOVE RESIDUAL PAVEMENT AND STRENGTHEN REMAINING PAVEMENT ON SR 2182. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM | DIVISION 9 |  | T | CONSTRUCTION | 365000
U-6237 | HIGHWAY | SR 2120 (LONG FERRY ROAD) | SR 2182 (I-85 SERVICE ROAD) NEAR SPENCER. CONSTRUCT RIGHT-TURN LANE ON SR 2120, AND CONSTRUCT CUL-DE-SAC, REMOVE RESIDUAL PAVEMENT AND STRENGTHEN REMAINING PAVEMENT ON SR 2182. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM | DIVISION 9 |  | T | UTILITIES | 50000
U-6238 | HIGHWAY | TRIVIUM PARKWAY, NEW ROUTE | EXTEND TRIVIUM PARKWAY AND CONSTRUCT NEW ROADWAY IN TRIVIUM CORPORATE CENTER. | 12 | Greater Hickory MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CATALER NORTH AMERICA. | DIVISION 12 |  | T | CONSTRUCTION | 1316000 | FY 2023: 1316000
U-6239 | HIGHWAY | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | EXEMPT |  | DP | RIGHT-OF-WAY | 1014000
U-6239 | HIGHWAY | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | EXEMPT |  | DP | CONSTRUCTION | 12175000 | FY 2023: 12175000
U-6239 | HIGHWAY | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | EXEMPT |  | L | ENGINEERING | 105000
U-6239 | HIGHWAY | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | EXEMPT |  | L | RIGHT-OF-WAY | 5135000
U-6239 | HIGHWAY | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | EXEMPT |  | L | CONSTRUCTION | 2881000 | FY 2023: 2881000
U-6239 | HIGHWAY | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE | EXEMPT |  | DP | ENGINEERING | 420000
U-6240 | HIGHWAY | SR 1571 (WEST 5TH STREET) | REHABILITATION AND REALIGNMENT OF SR 1571 (WEST 5TH STREET) FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | DIVISION 2 |  |  |  | 2803000
U-6240 | HIGHWAY | SR 1571 (WEST 5TH STREET) | REHABILITATION AND REALIGNMENT OF SR 1571 (WEST 5TH STREET) FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | DIVISION 2 |  | L | CONSTRUCTION | 6690000
U-6240 | HIGHWAY | SR 1571 (WEST 5TH STREET) | REHABILITATION AND REALIGNMENT OF SR 1571 (WEST 5TH STREET) FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | DIVISION 2 |  | DP | CONSTRUCTION | 11790000
U-6241 | HIGHWAY | US 401 BUSINESS (SOUTH MAIN STREET) SR 2051 ROAD); | SR 2051 (BURLINGTON MILLS ROAD), EAST OF ROLESVILLE MIDDLE SCHOOL TO US 401 BUSINESS (SOUTH MAIN STREET) IN ROLESVILLE. REALIGN ROADWAY AND CONSTRUCT NEW INTERSECTION WITH SOUTH MAIN STREET. US 401 BUSINESS (SOUTH MAIN STREET), SR 2051 (BURLINGTON MILLS ROAD) TO NORTH OF SR 1003 (EAST YOUNG STREET) / SR 1945 (WEST YOUNG STREET) IN ROLESVILLE. CONSTRUCT SIDEWALK EXTENSIONS AND COMPLETE STREET IMRPOVEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGDA | CONSTRUCTION | 12041000
U-6241 | HIGHWAY | US 401 BUSINESS (SOUTH MAIN STREET) SR 2051 ROAD); | SR 2051 (BURLINGTON MILLS ROAD), EAST OF ROLESVILLE MIDDLE SCHOOL TO US 401 BUSINESS (SOUTH MAIN STREET) IN ROLESVILLE. REALIGN ROADWAY AND CONSTRUCT NEW INTERSECTION WITH SOUTH MAIN STREET. US 401 BUSINESS (SOUTH MAIN STREET), SR 2051 (BURLINGTON MILLS ROAD) TO NORTH OF SR 1003 (EAST YOUNG STREET) / SR 1945 (WEST YOUNG STREET) IN ROLESVILLE. CONSTRUCT SIDEWALK EXTENSIONS AND COMPLETE STREET IMRPOVEMENTS. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | CONSTRUCTION | 8411000
U-6242 | HIGHWAY | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | L | RIGHT-OF-WAY | 340000 | FY 2023: 340000
U-6242 | HIGHWAY | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | L | UTILITIES | 220000 | FY 2023: 220000
U-6242 | HIGHWAY | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | BGDA | CONSTRUCTION | 8918000 | FY 2023: 8918000
U-6242 | HIGHWAY | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | BGDA | UTILITIES | 880000 | FY 2023: 880000
U-6242 | HIGHWAY | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | BGDA | RIGHT-OF-WAY | 1360000 | FY 2023: 1360000
U-6242 | HIGHWAY | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 5 |  | L | CONSTRUCTION | 2230000 | FY 2023: 2230000
U-6243 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO SR 1301 (SUNSET LAKE ROAD) IN HOLLY SPRINGS. WIDEN TO A FOUR-LANE MEDIAN-DIVIDED FACILITY AND CONSTRUCT SIDEWALK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | BGDA | CONSTRUCTION | 3600000
U-6243 | HIGHWAY | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO SR 1301 (SUNSET LAKE ROAD) IN HOLLY SPRINGS. WIDEN TO A FOUR-LANE MEDIAN-DIVIDED FACILITY AND CONSTRUCT SIDEWALK. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | L | CONSTRUCTION | 14400000
U-6244 | HIGHWAY | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | CONSTRUCTION | 106000 | FY 2023: 106000
U-6244 | HIGHWAY | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | BGDA | RIGHT-OF-WAY | 83000
U-6244 | HIGHWAY | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | BGDA | CONSTRUCTION | 317000 | FY 2023: 317000
U-6244 | HIGHWAY | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | EXEMPT |  | L | RIGHT-OF-WAY | 27000
U-6245 | HIGHWAY | SR 1146 (WEST TEN ROAD) | SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1137 (BUSHY COOK ROAD). CONSTRUCT OVERLAY, PAVED SHOULDERS AND TURN LANES. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE. | DIVISION 7 |  | T | CONSTRUCTION | 829000
U-6245 | HIGHWAY | SR 1146 (WEST TEN ROAD) | SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1137 (BUSHY COOK ROAD). CONSTRUCT OVERLAY, PAVED SHOULDERS AND TURN LANES. | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE. | DIVISION 7 |  | T | ENGINEERING | 109000
U-6246 | HIGHWAY | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | EXEMPT |  | BGDA | ENGINEERING | 160000
U-6246 | HIGHWAY | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | EXEMPT |  | BGDA | RIGHT-OF-WAY | 280000 | FY 2024: 280000
U-6246 | HIGHWAY | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | EXEMPT |  | BGDA | CONSTRUCTION | 1365000 | FY 2025: 1365000
U-6246 | HIGHWAY | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | EXEMPT |  | L | CONSTRUCTION | 100000 | FY 2025: 100000
U-6246 | HIGHWAY | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | EXEMPT |  | S(M) | ENGINEERING | 40000
U-6246 | HIGHWAY | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | EXEMPT |  | S(M) | RIGHT-OF-WAY | 70000 | FY 2024: 70000
U-6246 | HIGHWAY | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS. | EXEMPT |  | S(M) | CONSTRUCTION | 615000 | FY 2025: 615000
U-6247 | HIGHWAY | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | BGDA | ENGINEERING | 254000
U-6247 | HIGHWAY | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | S(M) | RIGHT-OF-WAY | 81000 | FY 2024: 81000
U-6247 | HIGHWAY | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | S(M) | ENGINEERING | 109000
U-6247 | HIGHWAY | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | L | CONSTRUCTION | 387000 | FY 2026: 387000
U-6247 | HIGHWAY | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | BGDA | RIGHT-OF-WAY | 189000 | FY 2024: 189000
U-6247 | HIGHWAY | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | S(M) | CONSTRUCTION | 381000 | FY 2026: 381000
U-6247 | HIGHWAY | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 10 | Charlotte Regional TPO | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | BGDA | CONSTRUCTION | 1787000 | FY 2026: 1787000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | T(DA) | ENGINEERING | 160000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | T(DA) | CONSTRUCTION | 2180000 | FY 2025: 1318000; FY 2026: 862000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | T(DA) | CONSTRUCTION | 654000 | FY 2025: 395000; FY 2026: 259000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | T(DA) | RIGHT-OF-WAY | 898000 | FY 2024: 898000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | T(DA) | RIGHT-OF-WAY | 380000 | FY 2024: 380000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | L | CONSTRUCTION | 164000 | FY 2025: 99000; FY 2026: 65000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | L | CONSTRUCTION | 545000 | FY 2025: 329000; FY 2026: 216000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | L | RIGHT-OF-WAY | 225000 | FY 2024: 225000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | L | ENGINEERING | 40000
U-6248 | HIGHWAY | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | EXEMPT |  | L | RIGHT-OF-WAY | 95000 | FY 2024: 95000
U-6249 | HIGHWAY | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT | EXEMPT |  | BGDA | ENGINEERING | 448000
U-6249 | HIGHWAY | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT | EXEMPT |  | BGDA | RIGHT-OF-WAY | 400000 | FY 2023: 400000
U-6249 | HIGHWAY | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT | EXEMPT |  | BGDA | CONSTRUCTION | 3205000 | FY 2025: 3205000
U-6249 | HIGHWAY | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT | EXEMPT |  | L | ENGINEERING | 112000
U-6249 | HIGHWAY | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT | EXEMPT |  | L | RIGHT-OF-WAY | 100000 | FY 2023: 100000
U-6249 | HIGHWAY | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT | EXEMPT |  | L | CONSTRUCTION | 801000 | FY 2025: 801000
U-6251 | HIGHWAY | NEW ROUTE- ENKA HERITAGE ROAD | CONSTRUCT ACCESS ROAD FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | 13 | French Broad River MPO | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. STATE FUNDS ARE SPOT MOBILITY FUNDS. | EXEMPT |  |  |  | 250000
U-6251 | HIGHWAY | NEW ROUTE- ENKA HERITAGE ROAD | CONSTRUCT ACCESS ROAD FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | 13 | French Broad River MPO | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. STATE FUNDS ARE SPOT MOBILITY FUNDS. | EXEMPT |  | ADHSL | MITIGATION | 140000
U-6251A | HIGHWAY | NEW ROUTE - ENKA HERITAGE ROAD | US 19/23 (SMOKEY PARK HIGHWAY) TO WALKOFF WAY. CONSTRUCT ACCESS ROAD ON NEW LOCATION. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHSL | CONSTRUCTION | 1850000 | FY 2023: 789000
U-6251A | HIGHWAY | NEW ROUTE - ENKA HERITAGE ROAD | US 19/23 (SMOKEY PARK HIGHWAY) TO WALKOFF WAY. CONSTRUCT ACCESS ROAD ON NEW LOCATION. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 1000000 | FY 2023: 426000
U-6251B | HIGHWAY | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHSL | RIGHT-OF-WAY | 900000
U-6251B | HIGHWAY | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | EXEMPT |  | ADHSL | CONSTRUCTION | 160000 | FY 2023: 160000
U-6251B | HIGHWAY | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | EXEMPT |  | L | CONSTRUCTION | 35000 | FY 2023: 35000
U-6251B | HIGHWAY | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | EXEMPT |  | S | CONSTRUCTION | 200000 | FY 2023: 200000
W-5114 | HIGHWAY | NC 68 | SOUTH OF SR 2111 (EAST HARRELL ROAD) TO SR 4831 (BARTONSHIRE DRIVE) IN OAK RIDGE AND SUMMERFIELD. CONSTRUCT TURN LANES, CLOSE ACCESS TO SR 2029 (WEST HARRELL ROAD), AND RELOCATE SR 2111 INTERSECTION AND PORTION OF SR 2111. | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION |  |  |  |  | 2923000
W-5143 | HIGHWAY | SR 1004 (EFLAND-CEDAR GROVE ROAD) | NORTH OF INTERSECTION WITH SR 1332 (HIGHLAND FARM ROAD). IMPROVE HORIZONTAL ALIGNMENT OF CURVE TO PROVIDE A MINIMUM OF 60 MPH DESIGN SPEED. | 7 | Triangle Area RPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 1276000
W-5201 | HIGHWAY | VARIOUS | DIVISION 1 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS. |  |  |  |  | 695000
W-5202 | HIGHWAY | VARIOUS | DIVISION 2 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS | REGION B |  |  |  | 8819000
W-5203 | HIGHWAY | VARIOUS | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS. |  |  |  |  | 21485000
W-5203U | HIGHWAY | NC 53 (WESTERN BOULEVARD) | NC 53 (WESTERN BOULEVARD) AT SR 1336 (HENDERSON DRIVE). INTERSECTION IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 1550000 | FY 2023: 1313000; FY 2024: 237000
W-5203U | HIGHWAY | NC 53 (WESTERN BOULEVARD) | NC 53 (WESTERN BOULEVARD) AT SR 1336 (HENDERSON DRIVE). INTERSECTION IMPROVEMENTS. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | UTILITIES | 23000 | FY 2023: 23000
W-5204 | HIGHWAY | VARIOUS | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 7548000
W-5204E | HIGHWAY | SR 1524 (OLD DRUG STORE ROAD) | IMPROVE SUPERELEVATION IN CURVE ON SR 1524 (OLD DRUG STORE ROAD) SOUTH OF SR 1525 (CORNWALLIS ROAD). INSTALL SIGNAL AT INTERSECTION OF SR 1524 (OLD DRUG STORE ROAD) AND SR 1525 (CORNWALLIS ROAD). | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  | HSIP | CONSTRUCTION | 650000 | FY 2024: 650000
W-5204E | HIGHWAY | SR 1524 (OLD DRUG STORE ROAD) | IMPROVE SUPERELEVATION IN CURVE ON SR 1524 (OLD DRUG STORE ROAD) SOUTH OF SR 1525 (CORNWALLIS ROAD). INSTALL SIGNAL AT INTERSECTION OF SR 1524 (OLD DRUG STORE ROAD) AND SR 1525 (CORNWALLIS ROAD). | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 4 |  | HSIP | RIGHT-OF-WAY | 200000 | FY 2023: 200000
W-5205 | HIGHWAY | VARIOUS | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION |  |  |  |  | 10184000
W-5206 | HIGHWAY | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS. |  |  |  |  | 49662000
W-5207 | HIGHWAY | VARIOUS | DIVISION 7 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO | COMPLETED |  |  |  |  | 5636000
W-5208 | HIGHWAY | VARIOUS | DIVISION 8 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION |  |  |  |  | 5463000
W-5209 | HIGHWAY | VARIOUS | DIVISION 9 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | COMPELTE |  |  |  |  | 4925000
W-5210 | HIGHWAY | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 12515000
W-5211 | HIGHWAY | VARIOUS | DIVISION 11 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 292000
W-5212 | HIGHWAY | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS; SEGMENT J: ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. STATE MATCH TO BE FUNDED WITH SPOT SAFETY FUNDS. |  |  |  |  | 19025000
W-5212DIV | HIGHWAY | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. | 12 | Charlotte Regional TPO, Greater Hickory MPO | IN PROGRESS. | DIVISION 12 |  | HSIP | RIGHT-OF-WAY | 50000
W-5212DIV | HIGHWAY | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. | 12 | Charlotte Regional TPO, Greater Hickory MPO | IN PROGRESS. | DIVISION 12 |  | HSIP | CONSTRUCTION | 2500000
W-5212J | HIGHWAY | SR 1302 (PERTH ROAD) | SR 1302 (PERTH ROAD) AT SR 1378 (JUDAS ROAD) AND SR1302 (CORNELIUS ROAD) INTERSECTIONS. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | $178K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | BGDA | ENGINEERING | 178000
W-5212J | HIGHWAY | SR 1302 (PERTH ROAD) | SR 1302 (PERTH ROAD) AT SR 1378 (JUDAS ROAD) AND SR1302 (CORNELIUS ROAD) INTERSECTIONS. CONSTRUCT INTERSECTION IMPROVEMENTS. | 12 | Charlotte Regional TPO | $178K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | S(M) | ENGINEERING | 178000
W-5212JA | HIGHWAY | SR 1302 (PERTH ROAD) | INSTALL SIGNAL AT SR 1302 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | DIVISION 12 |  | S(M) | RIGHT-OF-WAY | 12000
W-5212JA | HIGHWAY | SR 1302 (PERTH ROAD) | INSTALL SIGNAL AT SR 1302 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | DIVISION 12 |  | S(M) | CONSTRUCTION | 63000
W-5212JA | HIGHWAY | SR 1302 (PERTH ROAD) | INSTALL SIGNAL AT SR 1302 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | DIVISION 12 |  | BGANY | CONSTRUCTION | 62000
W-5212JA | HIGHWAY | SR 1302 (PERTH ROAD) | INSTALL SIGNAL AT SR 1302 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION. | DIVISION 12 |  | BGDA | RIGHT-OF-WAY | 13000
W-5212JB | HIGHWAY | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | S(M) | CONSTRUCTION | 89000 | FY 2023: 67000; FY 2024: 22000
W-5212JB | HIGHWAY | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | BGANY | RIGHT-OF-WAY | 100000
W-5212JB | HIGHWAY | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | BGANY | CONSTRUCTION | 4000 | FY 2023: 3000; FY 2024: 1000
W-5212JB | HIGHWAY | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | BGANY | CONSTRUCTION | 356000 | FY 2023: 269000; FY 2024: 87000
W-5212JB | HIGHWAY | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | S(M) | RIGHT-OF-WAY | 25000
W-5212JB | HIGHWAY | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP. | DIVISION 12 |  | S(M) | CONSTRUCTION | 1000 | FY 2023: 1000; FY 2024: 0
W-5212N | HIGHWAY | NC 279 (DALLAS CHERRYVILLE HIGHWAY) | SOUTH OF (ST MARK'S CHURCH ROAD) TO NORTH OF NC 275 - CONSTRUCT SAFETY IMPROVEMENTS, INCLUDING PASSING ZONES | 12 | Gaston-Cleveland-Lincoln MPO | COMPELTE; BUILD NC BOND FUNDING: $9.912 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | REGION F |  | T | BUILD NC CON | 12750000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 1700000
W-5213 | HIGHWAY | VARIOUS | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS |  |  |  |  | 4768000
W-5213DIV | HIGHWAY | VARIOUS | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. | 13 | French Broad River MPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 50000
W-5213DIV | HIGHWAY | VARIOUS | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. | 13 | French Broad River MPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 700000
W-5213G | HIGHWAY | SR 2002 (RICEVILLE ROAD) | US 70 TO SR 2419 (BULL CREEK ROAD) NEAR HAW CREEK. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | HSIP | CONSTRUCTION | 1225000 | FY 2023: 12000; FY 2024: 1213000
W-5214 | HIGHWAY | VARIOUS | DIVISION 14 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 14 | Southwestern RPO, Land-of-Sky RPO, French Broad River MPO, Foothills RPO | IN PROGRESS - DIVISION PURCHASE ORDER CONTRACT (DPOC) |  |  |  |  | 6673000
W-5303 | HIGHWAY | SR 1004 (STOKES FERRY ROAD) | SR 2380 (ODDIE ROAD). INTERSECTION IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION - LET WITH B-4257 |  |  |  |  | 230000
W-5305 | HIGHWAY | NC 62; SR 1129 (GROOMETOWN ROAD) | SR 1129 AT SR 4019 (GROOMETOWN ROAD); NC 62 AT SR 1129 (GROOMETOWN ROAD). REALIGN BOTH INTERSECTIONS AND REMOVE ACCESS BETWEEN SR 4019 AND NC 62. | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION | REGION D |  |  |  | 735000
W-5314 | HIGHWAY | NC 801; SR 1951 (PARKS ROAD) | NC 801 AT SR 2048 (COOL SPRINGS ROAD / WOODLEAF ROAD), SR 1951 (PARKS ROAD) AT SR 2048 (WOODLEAF ROAD) AND NC 801 AT SR 2004 (WOODLEAF BARBER ROAD / QUARRY ROAD). WIDENING, INTERSECTION REALIGNMENT, TURN LANES AND GEOMETRIC IMPROVEMENTS. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 4292000
W-5500 | HIGHWAY | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1622 (WOODSIDE DRIVE) TO SR 1752 (SAULSTON-PATETOWN ROAD). SAFETY IMPROVEMENTS INCLUDING WIDENING, SHOULDERS, SUPERELEVATION REVISIONS, OVERLAYING PAVEMENT MARKINGS AND SIGNING. | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION | PRE-STI (TRANSITION) |  |  |  | 3727000
W-5503 | HIGHWAY | NC 268 | NC 268 EAST OF NORTH WILKESBORO. WIDEN MULTIPLE SECTIONS, IMPROVE SHOULDERS, AND INSTALL GUARDRAIL, RUMBLE STRIPS, AND PAVEMENT MARKINGS. | 11 | High Country RPO | PART COMPLETE | REGION F |  |  |  | 3850000
W-5503A | HIGHWAY | NC 268 | SR 1966 (AIRPORT ROAD) TO SR 2026 (AUSTIN TRAPHILL ROAD). INSTALL GUARDRAIL AND PAVEMENT MARKINGS. | 11 | High Country RPO | UNDER CONSTRUCTION. | REGION F |  | HSIP | CONSTRUCTION | 1000000
W-5508 | HIGHWAY | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. TRAFFIC ENGINEERING BRANCH TO PARTICIPATE IN A THREE YEAR DATA COLLECTION PROGRAM. | 99 | STATEWIDE PROJECT | [5 empty] | 1500000
W-5510 | HIGHWAY | SR 4315 (SOUTH MAIN STREET); SR 2648 (OLD WINSTON | SR 4315 (SOUTH MAIN STREET), BUSINESS 40 / US 421 / NC 150 TO NORTH OF SR 4278 (SOUTH CHERRY STREET), AND SR 2648 (OLD WINSTON ROAD), WEST OF SOUTH CHERRY STREET TO SOUTH MAIN STREET IN KERNERSVILLE. SAFETY IMPROVEMENTS, INCLUDING RAISED MEDIAN, TURN LANE | 9 | Winston-Salem Urban Area MPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 7034000
W-5516 | HIGHWAY | SR 1221 (OLD BEATTY FORD ROAD) | SR 1210 (OLD BEATTY FORD ROAD) / SR 1221 (BOSTIAN ROAD) TO SR 1337 (LENTZ ROAD). RELOCATE EXISTING ROAD WITH GRADE SEPARATION OVER I-85. | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | DIVISION 9 |  |  |  | 17693000
W-5517 | HIGHWAY | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | 99 | STATEWIDE PROJECT | [5 empty] | 22101000
W-5519 | HIGHWAY | I-95 BUSINESS/US 301 | NC 87 SOUTH TO NC 59. SAFETY IMPROVEMENTS. | 6 | Fayetteville Area MPO | COMPLETED. | REGION C |  |  |  | 10123000
W-5600 | HIGHWAY | US 70 | US 70 BUSINESS TO NEUSE RIVER BRIDGE. CONVERT TO FREEWAY WITH INTERCHANGES AT SR 1501 (SWIFT CREEK ROAD) AND SR 1919 (WILSON'S MILLS ROAD). | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  |  |  | 9292000
W-5600 | HIGHWAY | US 70 | US 70 BUSINESS TO NEUSE RIVER BRIDGE. CONVERT TO FREEWAY WITH INTERCHANGES AT SR 1501 (SWIFT CREEK ROAD) AND SR 1919 (WILSON'S MILLS ROAD). | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | NHP | CONSTRUCTION | 67693000 | FY 2023: 25667000
W-5601 | HIGHWAY | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 130411000
W-5601DIV | HIGHWAY | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON DIVISION CATEGORY. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | CONSTRUCTION | 3670000
W-5601DIV | HIGHWAY | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON DIVISION CATEGORY. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | RIGHT-OF-WAY | 68000
W-5601R | HIGHWAY | NC 274 | SR 1443 (DAMERON ROAD) TO SR 1405 (RAMSEUR ROAD) REALIGNMENT AND WIDENING. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | HSIP | CONSTRUCTION | 2500000 | FY 2025: 25000; FY 2026: 2268000; FY 2027: 207000
W-5601REG | HIGHWAY | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON REGIONAL CATEGORY. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | CONSTRUCTION | 6170000 | FY 2024: 3650000
W-5601REG | HIGHWAY | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON REGIONAL CATEGORY. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | RIGHT-OF-WAY | 68000
W-5601SW | HIGHWAY | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON STATWIDE CATEGORY. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 3360000
W-5601SW | HIGHWAY | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON STATWIDE CATEGORY. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 90000
W-5601U | HIGHWAY | NC 150 | NC 150 AT NC 152 (WESTERN INTERSECTION) | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  | HSIP | CONSTRUCTION | 1150000 | FY 2024: 1150000
W-5601U | HIGHWAY | NC 150 | NC 150 AT NC 152 (WESTERN INTERSECTION) | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | REGION F |  | HSIP | RIGHT-OF-WAY | 472000
W-5602 | HIGHWAY | NC 172 | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | REGION B |  |  |  | 13657000
W-5602 | HIGHWAY | NC 172 | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | REGION B |  | T | BUILD NC CON | 7080000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 472000 | 944000
W-5602 | HIGHWAY | NC 172 | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | REGION B |  | T | CONSTRUCTION | 5103000
W-5700 | HIGHWAY | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. | 99 | STATEWIDE PROJECT | IN PROGRESS |  |  |  |  | 3500000
W-5701 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | IN PROGRESS. |  |  |  |  | 970000
W-5701C | HIGHWAY | SR 1333 (WEST MAIN STREET EXTENSION) | FROM 0.6 MILES NORTH OF SR 1338 (BEREA CHURCH ROAD) TO 0.2 MILES SOUTH OF SR 1338 (BEREA CHURCH ROAD). | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | HSIP | CONSTRUCTION | 1025000 | FY 2024: 10000; FY 2025: 1015000
W-5701C | HIGHWAY | SR 1333 (WEST MAIN STREET EXTENSION) | FROM 0.6 MILES NORTH OF SR 1338 (BEREA CHURCH ROAD) TO 0.2 MILES SOUTH OF SR 1338 (BEREA CHURCH ROAD). | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | DIVISION 1 |  | HSIP | RIGHT-OF-WAY | 170000 | FY 2023: 170000
W-5701DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | DIVISION 1 |  | HSIP | CONSTRUCTION | 375000 | FY 2023: 180000
W-5701DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | DIVISION 1 |  | HSIP | RIGHT-OF-WAY | 30000
W-5701REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | REGION A |  | HSIP | CONSTRUCTION | 375000 | FY 2023: 180000
W-5701REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | REGION A |  | HSIP | RIGHT-OF-WAY | 30000
W-5701SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 500000 | FY 2023: 240000
W-5701SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5702 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | IN PROGRESS |  |  |  |  | 17780000
W-5702DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | DIVISION 2 |  | HSIP | CONSTRUCTION | 375000 | FY 2023: 180000
W-5702DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | DIVISION 2 |  | HSIP | RIGHT-OF-WAY | 30000
W-5702REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 3125000 | FY 2023: 2930000
W-5702REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | REGION B |  | HSIP | RIGHT-OF-WAY | 131000
W-5702SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5702SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 500000 | FY 2023: 240000
W-5703 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | IN PROGRESS |  |  |  |  | 2536000
W-5703C | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | REGION B |  | HSIP | RIGHT-OF-WAY | 600000 | FY 2023: 600000
W-5703C | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | REGION B |  | HSIP | UTILITIES | 127000 | FY 2023: 127000
W-5703C | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | REGION B |  | HSIP | CONSTRUCTION | 3260000 | FY 2024: 1112000; FY 2025: 2148000
W-5703C | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | REGION B |  | L | CONSTRUCTION | 116000 | FY 2024: 116000
W-5703C | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | REGION B |  | T | CONSTRUCTION | 440000 | FY 2024: 440000
W-5703C | HIGHWAY | US 421 (CAROLINA BEACH ROAD) | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT. | REGION B |  | BGDA | CONSTRUCTION | 462000 | FY 2024: 462000
W-5703DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | DIVISION 3 |  | HSIP | RIGHT-OF-WAY | 30000
W-5703DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | DIVISION 3 |  | HSIP | CONSTRUCTION | 375000 | FY 2023: 180000
W-5703REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | REGION B |  | HSIP | RIGHT-OF-WAY | 30000
W-5703REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | REGION B |  | HSIP | CONSTRUCTION | 375000 | FY 2023: 180000
W-5703SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5703SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 500000 | FY 2023: 240000
W-5704 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | IN PROGRESS |  |  |  |  | 20827000
W-5704DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | DIVISION 4 |  | HSIP | CONSTRUCTION | 360000 | FY 2023: 180000
W-5704DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | DIVISION 4 |  | HSIP | RIGHT-OF-WAY | 144000
W-5704E | HIGHWAY | SR 1700 (COVERED BRIDGE ROAD) | SAFETY IMPROVEMENTS FROM 0.1 MILES EAST OF SR 1003 (BUFFALO ROAD) TO 0.1 MILES WEST OF SR 2685 (HELENA LANE). | 4 | Capital Area MPO |  | DIVISION 4 |  | HSIP | CONSTRUCTION | 3533000 | FY 2024: 35000; FY 2025: 2297000; FY 2026: 1201000
W-5704E | HIGHWAY | SR 1700 (COVERED BRIDGE ROAD) | SAFETY IMPROVEMENTS FROM 0.1 MILES EAST OF SR 1003 (BUFFALO ROAD) TO 0.1 MILES WEST OF SR 2685 (HELENA LANE). | 4 | Capital Area MPO |  | DIVISION 4 |  | T | CONSTRUCTION | 7067000 | FY 2024: 71000; FY 2025: 4593000; FY 2026: 2403000
W-5704K | HIGHWAY | SR 1927 (GENOA ROAD) | SR 1927 (GENOA ROAD) AT CRESCENT DRIVE. INTERSECTION IMPROVEMENTS. | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | DIVISION 4 |  | HSIP | CONSTRUCTION | 274000 | FY 2024: 274000
W-5704REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | REGION A |  | HSIP | RIGHT-OF-WAY | 30000
W-5704REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | REGION A |  | HSIP | CONSTRUCTION | 455000 | FY 2023: 180000
W-5704SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5704SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 480000 | FY 2023: 240000
W-5705 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS; |  |  |  |  | 6001000
W-5705AI | HIGHWAY | US 501 BUSINESS (ROXBORO STREET) | US 501 BUSINESS (ROXBORO STREET) AT SR 1443 (HORTON ROAD) AND SR 1641 (DENFIELD STREET) | 5 | Capital Area MPO |  | REGION C |  | HSIP | CONSTRUCTION | 1320000 | FY 2024: 1320000
W-5705DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 540000
W-5705DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 5 |  | HSIP | RIGHT-OF-WAY | 104000
W-5705G | HIGHWAY | SR 1001 (WARRENTON ROAD) | SR 1001 (WARRENTON ROAD) AT SR 1507 (BROOKSTON ROAD). SAFETY IMPROVEMENTS. | 5 | Kerr-Tar RPO |  | DIVISION 5 |  | HSIP | CONSTRUCTION | 503000 | FY 2024: 503000
W-5705REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | HSIP | CONSTRUCTION | 540000
W-5705REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 104000
W-5705SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 137000
W-5705SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 720000
W-5706 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | IN PROGRESS |  |  |  |  | 14907000
W-5706DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | DIVISION 6 |  | HSIP | RIGHT-OF-WAY | 30000
W-5706DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | DIVISION 6 |  | HSIP | CONSTRUCTION | 375000 | FY 2023: 180000
W-5706L | HIGHWAY | NC 27 | CONSTRUCT ROUNDABOUTS AT NC 27/SR 1006 (OLD STAGE ROAD) AND SR 2084 (LESLIE CAMPBELL AVENUE) AND AT NC 27/SR 1006 (OLD STAGE ROAD) AND SR 1516. CLOSE NC 27/SR 1516 INTERSECTION. | 6 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | HSIP | CONSTRUCTION | 2500000 | FY 2024: 1074000; FY 2025: 1426000
W-5706L | HIGHWAY | NC 27 | CONSTRUCT ROUNDABOUTS AT NC 27/SR 1006 (OLD STAGE ROAD) AND SR 2084 (LESLIE CAMPBELL AVENUE) AND AT NC 27/SR 1006 (OLD STAGE ROAD) AND SR 1516. CLOSE NC 27/SR 1516 INTERSECTION. | 6 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | HSIP | UTILITIES | 275000 | FY 2024: 275000
W-5706N | HIGHWAY | NC 710 | AT SR 1339 (DEEP BRANCH ROAD) IN PEMBROKE. CONVERT SIGNALIZED INTERSECTION TO A ROUNDABOUT. | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | REGION C |  | HSIP | CONSTRUCTION | 2850000 | FY 2024: 1425000; FY 2025: 1425000
W-5706REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 135000
W-5706REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | REGION C |  | HSIP | CONSTRUCTION | 519000 | FY 2023: 180000
W-5706SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 90000
W-5706SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 500000 | FY 2023: 240000
W-5706U | HIGHWAY | SR 1404 (HAY STREET / MORGANTON ROAD) | AT THE SR 3578 (FORT BRAGG ROAD), OAKRIDGE AVENUE, AND HIGHLAND AVENUE INTERSECTION IN FAYETTEVILLE. UPGRADE TRAFFIC SIGNALS AND IMPROVE PEDESTRIAN CROSSINGS. | 6 | Fayetteville Area MPO |  | DIVISION 6 |  | HSIP | CONSTRUCTION | 100000 | FY 2025: 100000
W-5707 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO | IN PROGRESS |  |  |  |  | 4057000
W-5707DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO |  | DIVISION 7 |  | HSIP | CONSTRUCTION | 555000
W-5707DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO |  | DIVISION 7 |  | HSIP | RIGHT-OF-WAY | 90000
W-5707REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO |  | REGION D |  | HSIP | RIGHT-OF-WAY | 90000
W-5707REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO |  | REGION D |  | HSIP | CONSTRUCTION | 555000
W-5707SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 740000
W-5707SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Triangle Area RPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 120000
W-5708 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS |  |  |  |  | 8324000
W-5708DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 8 |  | HSIP | CONSTRUCTION | 540000
W-5708DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | DIVISION 8 |  | HSIP | RIGHT-OF-WAY | 90000
W-5708L | HIGHWAY | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) FROM BEASLEY STREET TO BALFOUR AVENUE IN ASHEBORO. | 8 | Piedmont Triad RPO |  | REGION E |  | HSIP | CONSTRUCTION | 320000 | FY 2026: 320000
W-5708REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | REGION E |  | HSIP | CONSTRUCTION | 540000
W-5708REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | REGION E |  | HSIP | RIGHT-OF-WAY | 90000
W-5708SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 720000
W-5708SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 8 | Lumber River RPO, Triangle Area RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 120000
W-5709 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | IN PROGRESS; $1.3M NHP FUNDING APPLIED TO W-5709E |  |  |  |  | 6306000
W-5709DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | DIVISION 9 |  | HSIP | CONSTRUCTION | 555000
W-5709DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | DIVISION 9 |  | HSIP | RIGHT-OF-WAY | 90000
W-5709E | HIGHWAY | NC 153 (RICE STREET) | NC 153 (RICE STREET) AT SR 1197 (CANNON FARM ROAD / MT MORIAH CHURCH ROAD) IN CHINA GROVE | 9 | Cabarrus-Rowan MPO |  | REGION D |  | HSIP | CONSTRUCTION | 700000 | FY 2024: 700000
W-5709REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | REGION D |  | HSIP | CONSTRUCTION | 555000
W-5709REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | REGION D |  | HSIP | RIGHT-OF-WAY | 90000
W-5709SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 120000
W-5709SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 9 | Northwest Piedmont RPO, Winston-Salem Urban Area MPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 740000
W-5710 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | STATE MATCH FOR SEGMENTS Y & Z ARE SPOT SAFETY FUNDS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. |  |  |  |  | 15485000
W-5710AD | HIGHWAY | SR 1005 (LANDSFORD ROAD) | SR 1937 (OLD PAGELAND MARSHVILLE ROAD). INSTALL AN ALL WAY STOP. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | HSIP | CONSTRUCTION | 30000 | FY 2024: 30000
W-5710AH | HIGHWAY | NC 200 (LANCASTER HIGHWAY) | SR 1137 (POTTER ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | REGION E |  | HSIP | CONSTRUCTION | 2200000 | FY 2024: 2200000
W-5710AN | HIGHWAY | SR 1009 (OLD CHARLOTTE HIGHWAY) | WILLIAMS ROAD IN MONROE. CONSTRUCT SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO |  | DIVISION 10 |  | HSIP | CONSTRUCTION | 570000 | FY 2024: 570000
W-5710AO | HIGHWAY | SR 1002 (OLD SALISBURY CONCORD ROAD) | SR 2400 (IRISH POTATO ROAD) NEAR KANNAPOLIS. CONSTRUCT SAFETY IMPROVEMENTS. | 10 | Cabarrus-Rowan MPO |  | DIVISION 10 |  | HSIP | CONSTRUCTION | 1000000 | FY 2024: 1000000
W-5710DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | DIVISION 10 |  | HSIP | CONSTRUCTION | 180000
W-5710DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | DIVISION 10 |  | HSIP | RIGHT-OF-WAY | 30000
W-5710DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | DIVISION 10 |  | HSIP | RIGHT-OF-WAY | 320000 | FY 2023: 320000
W-5710DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | DIVISION 10 |  | HSIP | CONSTRUCTION | 1485000 | FY 2023: 1485000
W-5710DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | DIVISION 10 |  | HSIP | CONSTRUCTION | 180000
W-5710DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | DIVISION 10 |  | HSIP | CONSTRUCTION | 180000
W-5710DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | DIVISION 10 |  | HSIP | RIGHT-OF-WAY | 30000
W-5710DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | DIVISION 10 |  | HSIP | RIGHT-OF-WAY | 30000
W-5710REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | REGION E |  | HSIP | CONSTRUCTION | 180000
W-5710REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | REGION E |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5710REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | REGION E |  | HSIP | RIGHT-OF-WAY | 450000 | FY 2023: 450000
W-5710REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | REGION E |  | HSIP | RIGHT-OF-WAY | 30000
W-5710REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | REGION E |  | HSIP | RIGHT-OF-WAY | 30000
W-5710REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | REGION E |  | HSIP | CONSTRUCTION | 180000
W-5710REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | REGION E |  | HSIP | RIGHT-OF-WAY | 30000
W-5710REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | REGION E |  | HSIP | CONSTRUCTION | 180000
W-5710SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5710SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2023: 40000
W-5710SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
W-5710SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5710SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5710SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5710SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5710SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5710X | HIGHWAY | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | DIVISION 10 |  | BGANY | CONSTRUCTION | 6644000 | FY 2025: 4791000; FY 2026: 1853000
W-5710X | HIGHWAY | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | DIVISION 10 |  | HSIP | CONSTRUCTION | 650000 | FY 2025: 469000; FY 2026: 181000
W-5710X | HIGHWAY | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 10 | Charlotte Regional TPO | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP. | DIVISION 10 |  | L | CONSTRUCTION | 1920000 | FY 2025: 1385000; FY 2026: 535000
W-5710Y | HIGHWAY | UNION COUNTY | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | BGANY | CONSTRUCTION | 1385000
W-5710Y | HIGHWAY | UNION COUNTY | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | HSIP | CONSTRUCTION | 850000
W-5710Y | HIGHWAY | UNION COUNTY | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | 10 | Charlotte Regional TPO | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP. | DIVISION 10 |  | S(M) | CONSTRUCTION | 346000
W-5710Z | HIGHWAY | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | REGION E |  | L | CONSTRUCTION | 200000 | FY 2023: 41000
W-5710Z | HIGHWAY | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | REGION E |  | S(M) | CONSTRUCTION | 214000 | FY 2023: 44000
W-5710Z | HIGHWAY | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | REGION E |  | S(M) | ENGINEERING | 39000
W-5710Z | HIGHWAY | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | REGION E |  | BGDA | RIGHT-OF-WAY | 28000
W-5710Z | HIGHWAY | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | REGION E |  | BGDA | ENGINEERING | 156000
W-5710Z | HIGHWAY | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | REGION E |  | BGANY | CONSTRUCTION | 1486000 | FY 2023: 306000
W-5710Z | HIGHWAY | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | REGION E |  | S(M) | RIGHT-OF-WAY | 7000
W-5710Z | HIGHWAY | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP. | REGION E |  | HSIP | CONSTRUCTION | 671000 | FY 2023: 138000
W-5711 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | [5 empty] | 1178000
W-5711DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | DIVISION 11 |  | HSIP | RIGHT-OF-WAY | 30000
W-5711DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | DIVISION 11 |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5711DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | DIVISION 11 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5711DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | DIVISION 11 |  | HSIP | CONSTRUCTION | 180000
W-5711DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | DIVISION 11 |  | HSIP | CONSTRUCTION | 180000
W-5711DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | DIVISION 11 |  | HSIP | CONSTRUCTION | 180000
W-5711DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | DIVISION 11 |  | HSIP | RIGHT-OF-WAY | 30000
W-5711DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | DIVISION 11 |  | HSIP | RIGHT-OF-WAY | 30000
W-5711REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | REGION F |  | HSIP | CONSTRUCTION | 180000
W-5711REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | REGION F |  | HSIP | RIGHT-OF-WAY | 30000
W-5711REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | REGION F |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5711REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | REGION F |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5711REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | REGION F |  | HSIP | CONSTRUCTION | 180000
W-5711REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | REGION F |  | HSIP | RIGHT-OF-WAY | 30000
W-5711REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | REGION F |  | HSIP | CONSTRUCTION | 180000
W-5711REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | REGION F |  | HSIP | RIGHT-OF-WAY | 30000
W-5711SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5711SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
W-5711SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2023: 40000
W-5711SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5711SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5711SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5711SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5711SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5712 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS |  |  |  |  | 5273000
W-5712DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | DIVISION 12 |  | HSIP | RIGHT-OF-WAY | 30000
W-5712DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | DIVISION 12 |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5712DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | DIVISION 12 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5712DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | DIVISION 12 |  | HSIP | CONSTRUCTION | 180000
W-5712DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | DIVISION 12 |  | HSIP | RIGHT-OF-WAY | 30000
W-5712DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | DIVISION 12 |  | HSIP | CONSTRUCTION | 180000
W-5712DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | DIVISION 12 |  | HSIP | RIGHT-OF-WAY | 30000
W-5712DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | DIVISION 12 |  | HSIP | CONSTRUCTION | 180000
W-5712R | HIGHWAY | SR 1003 (BUFFALO SHOALS ROAD) | SR 1343 (IVEY CHURCH ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | DIVISION 12 |  | HSIP | CONSTRUCTION | 625000 | FY 2025: 625000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | CONSTRUCTION | 180000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | CONSTRUCTION | 180000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | CONSTRUCTION | 180000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2023: 40000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5712U | HIGHWAY | NC 150 | MILEPOST 19.3 TO GASTON COUNTY LINE AND FROM THE CLEVELAND COUNTY LINE TO MILEPOST 1.2. CONSTRUCT SAFETY IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | HSIP | CONSTRUCTION | 625000 | FY 2025: 625000
W-5713 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | COMPLETE |  |  |  |  | 6567000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 180000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 180000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 180000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2023: 40000
W-5714 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS |  |  |  |  | 1499000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714E | HIGHWAY | US 64 | SR 1119 (SAPPHIRE POSTOFFICE ROAD) AT CHRYSLER CURVE NEAR SAPPHIRE. CONSTRUCT SAFETY IMPROVEMENTS. | 14 | Southwestern RPO |  | REGION G |  | HSIP | CONSTRUCTION | 975000 | FY 2024: 975000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2023: 40000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5715DIV | HIGHWAY | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | ENGINEERING | 9180000 | 1230000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 900000
W-5715REG | HIGHWAY | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | ENGINEERING | 9180000 | 1230000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 900000
W-5715SW | HIGHWAY | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | ENGINEERING | 12240000 | 1640000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 1200000
W-5716DIV | HIGHWAY | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | ENGINEERING | 26400000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 3300000
W-5716REG | HIGHWAY | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | ENGINEERING | 26400000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 3300000
W-5716SW | HIGHWAY | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | ENGINEERING | 35200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 4400000
W-5717DIV | HIGHWAY | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | ENGINEERING | 10200000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1500000
W-5717REG | HIGHWAY | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | ENGINEERING | 10200000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1500000
W-5717SW | HIGHWAY | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | ENGINEERING | 13600000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 2000000
W-5802A | HIGHWAY | SR 1493 | SR 1493 (LIVE OAK STREET) AT CAMPEN ROAD. REVISE TRAFFIC SIGNAL, INSTALL PEDESTRIAN CROSSING WITH SIGNAL HEADS, AND UPGRADE SIDEWALK. | 2 | Down East RPO | COMPLETED. | DIVISION 2 |  | HSIP | CONSTRUCTION | 38000
W-5802B | HIGHWAY | NC 58 | NC 58 (E. FORT MACON ROAD) AT BROOKS STREET. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | 2 | Down East RPO | COMPLETED. | REGION B |  | HSIP | CONSTRUCTION | 30000
W-5802C | HIGHWAY | NC 58 | NC 58 (E. FORT MACON ROAD) AT E. BOGUE SOUND DRIVE. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | 2 | Down East RPO | COMPLETED. | REGION B |  | HSIP | CONSTRUCTION | 30000
W-5802E | HIGHWAY | US 70, NC 55 | US 70 BETWEEN NUNN STREET AND SR 1605 (FRIENDLY ROAD) IN MOREHEAD CITY, AND NC 55 BETWEEN US 17 IN BRIDGETON AND SR 1210 (1ST STREET) IN BAYBORO. INSTALL 6 INCH LONG LIFE PAVEMENT MARKINGS. | 2 | Down East RPO | COMPLETED. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 865000
W-5803A | HIGHWAY | US 74 | US 74 (EASTWOOD ROAD) AT US 17 (MILITARY CUTOFF ROAD), AND US 74 (EASTWOOD ROAD) AT CAVALIER DRIVE IN WILMINGTON. UPGRADE PEDESTRIAN SIGNALS. | 3 | Wilmington Urban Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 42000 | FY 2023: 42000
W-5803B | HIGHWAY | US 17 | US 17 BETWEEN NEW HANOVER / PENDER COUNTY LINE AND MILE POST 19.3 IN ONSLOW COUNTY. INSTALL SHOULDER RUMBLE STRIPS. | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Cape Fear RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 438000 | FY 2023: 438000
W-5803C | HIGHWAY | US 17 BUSINESS | US 17 BUSINESS (MARINE BOULEVARD) AND SR 1402 (OLD BRIDGE STREET). UPGRADE TRAFFIC SIGNAL, PAVEMENT MARKINGS, AND IMPROVE SIGHT DISTANCE. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 85000 | FY 2023: 85000
W-5803D | HIGHWAY | NC 24 | NC 24 (WEST CORBETT AVENUE) AND SR 1512 (OLD HAMMOCKS ROAD). UPGRADE PEDESTRIAN SIGNALS. | 3 | Jacksonville Urban Area MPO | COMPLETED. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 17000
W-5803E | HIGHWAY | NC 53 | NC 53 (WESTERN BOULEVARD) AND CENTER STREET / LIBERTY DRIVE. UPGRADE TRAFFIC SIGNAL AND ADD ADDITIONAL SPEED LIMIT SIGNS. | 3 | Jacksonville Urban Area MPO | COMPLETED. | REGION B |  | HSIP | CONSTRUCTION | 57000
W-5804A | HIGHWAY | US 301 | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | RIGHT-OF-WAY | 100000
W-5804A | HIGHWAY | US 301 | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 2334000
W-5804B | HIGHWAY | NC 43 | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | RIGHT-OF-WAY | 45000 | FY 2023: 45000
W-5804B | HIGHWAY | NC 43 | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 651000 | FY 2023: 7000; FY 2024: 644000
W-5805A | HIGHWAY | NC 42 | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 5 | Capital Area MPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 235000 | FY 2023: 235000
W-5805A | HIGHWAY | NC 42 | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 5 | Capital Area MPO |  | REGION C |  | HSIP | CONSTRUCTION | 725000 | FY 2024: 239000; FY 2025: 486000
W-5805C | HIGHWAY | SR 1820 (LEAD MINE ROAD) | SR 1827 (LYNN ROAD) INTERSECTION IN RALEIGH. CONSTRUCT PEDESTRIAN REFUGE ISLANDS, AND REVISE CURB RAMPS, CROSSWALKS, AND OTHER PAVEMENT MARKINGS. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | HSIP | CONSTRUCTION | 292000 | FY 2023: 288000
W-5805D | HIGHWAY | NC 42 | BRIDGE 910023 OVER MIDDLE CREEK. INSTALL GUARDRAIL. | 5 | Capital Area MPO | UNDER CONSTRUCTION | REGION C |  | HSIP | CONSTRUCTION | 184000 | FY 2023: 172000
W-5805E | HIGHWAY | NC 98 | SR 2057 / SR 4465 (MOORES POND ROAD) | 5 | Capital Area MPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 100000 | FY 2023: 100000
W-5805E | HIGHWAY | NC 98 | SR 2057 / SR 4465 (MOORES POND ROAD) | 5 | Capital Area MPO |  | REGION C |  | HSIP | CONSTRUCTION | 1230000 | FY 2024: 12000; FY 2025: 1218000
W-5805F | HIGHWAY | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS | 5 | Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | DIVISION 5 |  | HSIP | CONSTRUCTION | 2553000 | FY 2023: 256000
W-5805G | HIGHWAY | US 1 | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | 5 | Kerr-Tar RPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 45000 | FY 2023: 45000
W-5805G | HIGHWAY | US 1 | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | 5 | Kerr-Tar RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 955000 | FY 2023: 10000; FY 2024: 945000
W-5805H | HIGHWAY | SR 1004 (GARNER ROAD); TIMBER DRIVE EAST | SR 2539 (YEARGAN ROAD), SR 2564 (CREECH ROAD), AND SHENSTONE BOULEVARD INTERSECTIONS IN GARNER. UPGRADE TRAFFIC SIGNALS | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | HSIP | CONSTRUCTION | 75000
W-5806A | HIGHWAY | NC 11 | NC 11 AT SR 1740 (OLD LAKE ROAD). CONSTRUCT ROUNDABOUT. | 6 | Cape Fear RPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 85000 | FY 2024: 85000
W-5806A | HIGHWAY | NC 11 | NC 11 AT SR 1740 (OLD LAKE ROAD). CONSTRUCT ROUNDABOUT. | 6 | Cape Fear RPO |  | REGION C |  | HSIP | CONSTRUCTION | 1342000 | FY 2025: 630000; FY 2026: 712000
W-5806B | HIGHWAY | SR 1117, SR 3242, SR 1615 | SR 1117 (NURSERY ROAD) FROM NC 27 TO SR 3242 (OVERHILLS ROAD). SR 3242 (OVERHILLS ROAD) FROM NC 24/87 TO SR 1117 (NURSERY ROAD). SR 1121 (RAY ROAD) FROM SR 1117 (NURSERY ROAD) TO SR 3242 (OVERHILLS ROAD). WIDEN CURVES AND INSTALL RUMBLE STRIPS. | 6 | Fayetteville Area MPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 400000 | FY 2023: 396000
W-5806C | HIGHWAY | SR 1615 (ROSEHILL ROAD) | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 1850000 | FY 2023: 1850000
W-5806C | HIGHWAY | SR 1615 (ROSEHILL ROAD) | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | RIGHT-OF-WAY | 75000